## Sheet1
Monitor Field Indicator | Work center | Earliest start date | Latest Allowed Finish Date | Order Type | Priority | ABC indicator | Priority text | Order | Activity | Order Description | Object Description | Notes 2 | Unloading Point | Notes 1 | Remaining Work | Number | Work | Actual work | Order User Status | Op User Status | Order System Status | Functional Location | Description of functional location | Revision | Sort field | Control key | Main Work Center | User Field 1 | Subnetwork of
| PRODTECH | 2023-12-31 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0020 | Replace stem gasket DFGA-LCV-340022 | Isolate equipment | 2 |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0030 | Replace stem gasket DFGA-LCV-340022 | Dismantle actuator from valve | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-02 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0040 | Replace stem gasket DFGA-LCV-340022 | Rig out actuator | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0050 | Replace stem gasket DFGA-LCV-340022 | Exchange stem gasket | 2 |  |  | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-04 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0060 | Replace stem gasket DFGA-LCV-340022 | Rig in actuator | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0070 | Replace stem gasket DFGA-LCV-340022 | Install actuator | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0080 | Replace stem gasket DFGA-LCV-340022 | Remove isolation | 2 |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-06 | 2020-02-27 | WDF | 4 | V | 4. Long | 2100022353 | 0090 | Replace stem gasket DFGA-LCV-340022 | Remove rigging equipment | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20/DFGA-LCV-340022 | LEVEL CONTROL VALVE | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-12-03 | WDF | 3 | V | 3. Intermediate | 2100022355 | 0020 | DFC LCV-34018 check/cleaning of trim. | L3 Separation of valve /cleaning |  |  |  | 10 | 1 | 10 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-LCV-34018 | H.P.SEPARATOR V-3402 (PRODUCT) | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-12-03 | WDF | 3 | V | 3. Intermediate | 2100022355 | 0030 | DFC LCV-34018 check/cleaning of trim. | L3 Replacement of softgoods kit |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-LCV-34018 | H.P.SEPARATOR V-3402 (PRODUCT) | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2019-12-03 | WDF | 3 | V | 3. Intermediate | 2100022355 | 0040 | DFC LCV-34018 check/cleaning of trim. | L3 Mount the valve |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-LCV-34018 | H.P.SEPARATOR V-3402 (PRODUCT) | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-12-03 | WDF | 3 | V | 3. Intermediate | 2100022355 | 0045 | DFC LCV-34018 check/cleaning of trim. | L3 Check checkvalve next to LCV-34018, t |  |  |  | 10 | 1 | 10 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-LCV-34018 | H.P.SEPARATOR V-3402 (PRODUCT) | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2019-12-03 | WDF | 3 | V | 3. Intermediate | 2100022355 | 0050 | DFC LCV-34018 check/cleaning of trim. | L3 De-Isolate/test DFC LCV-34018 |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-LCV-34018 | H.P.SEPARATOR V-3402 (PRODUCT) | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-12-04 | WDF | 3 | V | 3. Intermediate | 2100022376 | 0020 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Disassemble/clean/repack/assemble bre | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /20/DFCI-ESDV-34020 | H.P.SEP.V-3402 TO CRUDE OIL HEAT E-3401 | DFCHPSEP | SECE TEAM L0512443 | INLC | VEN-INST |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-12-04 | WDF | 3 | V | 3. Intermediate | 2100022376 | 0030 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Disassemble/clean/repack/assemble bre | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /20/DFCI-ESDV-34020 | H.P.SEP.V-3402 TO CRUDE OIL HEAT E-3401 | DFCHPSEP | SECE TEAM L0512443 | INLC | VEN-INST |  | 99000116
| PRODTECH | 2024-01-02 | 2019-12-04 | WDF | 3 | V | 3. Intermediate | 2100022376 | 0040 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 De-Isolate DFCI-SOV/ESDV-34020 | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /20/DFCI-ESDV-34020 | H.P.SEP.V-3402 TO CRUDE OIL HEAT E-3401 | DFCHPSEP | SECE TEAM L0512443 | INLC | VEN-INST |  | 99000116
| MTN-ELEC | 2023-12-31 | 2018-10-10 | WDF | 4 | V | 4. Long | 2100022386 | 0015 | DFFA-XCV-500042 valve and actuator has t | L3 assistance regarding actuator change | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500042 | UNCLASSIFIED VALVE | DAN-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2018-10-10 | WDF | 4 | V | 4. Long | 2100022386 | 0020 | DFFA-XCV-500042 valve and actuator has t | L2 Replace DFFA-XCV-500042 | 2 |  |  | 5 | 1 | 5 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500042 | UNCLASSIFIED VALVE | DAN-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2018-10-10 | WDF | 4 | V | 4. Long | 2100022386 | 0030 | DFFA-XCV-500042 valve and actuator has t | L3 De-isolate and leaktest DFFA-XCV-5000 | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500042 | UNCLASSIFIED VALVE | DAN-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-07-29 | WDF | 2 | V | 2. Short | 2100022421 | 0020 | Cancel - Inspect 1"/1/2" check vavles AS | L3 Inspect/function test valves | 1 |  |  | 6 | 1 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2019-07-29 | WDF | 2 | V | 2. Short | 2100022421 | 0030 | Cancel - Inspect 1"/1/2" check vavles AS | L3 De-Isolate/test valves | 1 |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0020 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-02 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0025 | Exchange 24" valve HCV-340071 | L3 Prepare lifting plan | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-04 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0030 | Exchange 24" valve HCV-340071 | L3 Prepare lifting equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| PRODTECH | 2024-01-06 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0040 | Exchange 24" valve HCV-340071 | L3 Isolate equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-08 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0050 | Exchange 24" valve HCV-340071 | L3 Loosen bolts on flanges | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-08 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0060 | Exchange 24" valve HCV-340071 | L3 Rig out of valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-10 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0070 | Exchange 24" valve HCV-340071 | L3 Rig in of valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-12 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0080 | Exchange 24" valve HCV-340071 | L2 Install new valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| PRODTECH | 2024-01-13 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0090 | Exchange 24" valve HCV-340071 | L3 Remove isolation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-14 | 2019-05-20 | WDF | 3 | S | 3. Intermediate | 2100022650 | 0100 | Exchange 24" valve HCV-340071 | L3 Remove lifting equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-HCV-340071 | LO - HAND CONTROL VALVE | DFFHPSEP |  | INLC | MTN-PIPF
| PRODTECH | 2024-01-01 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0020 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Isolation of valve |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0030 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Dismantle actuator from valve |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-02 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0040 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Rig actuator off valve |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0050 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Exchange stem gasket |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-04 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0060 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Rig new actuator onto valve |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0070 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Install actuator onto valve |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2019-06-09 | WDF | 3 | V | 3. Intermediate | 2100022676 | 0080 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Remove isolation |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-LCV-36110 | LEVEL CONTROL - CRUDE OIL TO COOLERS | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2019-06-05 | WDF | 3 | V | 3. Intermediate | 2100022701 | 0010 | CMAT:Exchange 2" HCV & CHK valve Interst | L3 Isolate equipment |  |  |  | 12 | 2 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2019-06-05 | WDF | 3 | V | 3. Intermediate | 2100022701 | 0020 | CMAT:Exchange 2" HCV & CHK valve Interst | L2 Exchange valve |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2019-06-05 | WDF | 3 | V | 3. Intermediate | 2100022701 | 0030 | CMAT:Exchange 2" HCV & CHK valve Interst | L2 Exchange chk valve |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2019-06-05 | WDF | 3 | V | 3. Intermediate | 2100022701 | 0040 | CMAT:Exchange 2" HCV & CHK valve Interst | L3 Remove isolation |  |  |  | 12 | 2 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2018-10-21 | WDF | 3 | I | 3. Intermediate | 2100022762 | 0010 | Cancel - CMAT:Change of Valtek Act. DFEY | L3 Isolate system |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /51/DFEY-FCV-35515 | FLOW CONT. BACKWASH OF DUAL MEDIA FILT | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2018-10-21 | WDF | 3 | I | 3. Intermediate | 2100022762 | 0020 | Cancel - CMAT:Change of Valtek Act. DFEY | L3 isolate actuator |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /51/DFEY-FCV-35515 | FLOW CONT. BACKWASH OF DUAL MEDIA FILT | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-10-21 | WDF | 3 | I | 3. Intermediate | 2100022762 | 0030 | Cancel - CMAT:Change of Valtek Act. DFEY | L2 change to new actuator. |  |  |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /51/DFEY-FCV-35515 | FLOW CONT. BACKWASH OF DUAL MEDIA FILT | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2018-10-21 | WDF | 3 | I | 3. Intermediate | 2100022762 | 0040 | Cancel - CMAT:Change of Valtek Act. DFEY | L3 Deisolate actuator |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /51/DFEY-FCV-35515 | FLOW CONT. BACKWASH OF DUAL MEDIA FILT | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2018-10-21 | WDF | 3 | I | 3. Intermediate | 2100022762 | 0050 | Cancel - CMAT:Change of Valtek Act. DFEY | L3 isolate system |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /51/DFEY-FCV-35515 | FLOW CONT. BACKWASH OF DUAL MEDIA FILT | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2018-10-21 | WDF | 3 | I | 3. Intermediate | 2100022762 | 0060 | Cancel - CMAT:Change of Valtek Act. DFEY | L3 test and clean |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /51/DFEY-FCV-35515 | FLOW CONT. BACKWASH OF DUAL MEDIA FILT | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0010 | Cancel - PMAT:DFE check of 12" 1500# WI | Phase 1 Rigning of spool and check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 60.3 | 2 | 60.3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-INST | 2023-12-31 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0015 | Cancel - PMAT:DFE check of 12" 1500# WI | Demol of instrument tubing (DFE-12"-WI-3 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2023-12-31 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0020 | Cancel - PMAT:DFE check of 12" 1500# WI | Phase 1 Demolish of 12" Check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 50.3 | 2 | 50.3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-02 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0030 | Cancel - PMAT:DFE check of 12" 1500# WI | Phase 1 Inspection of 12" Check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-02 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0035 | Cancel - PMAT:DFE check of 12" 1500# WI | Phase 1, Demol of Outlet spool on P-3551 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.7 | 2 | 6.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2023-12-31 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0050 | Cancel - PMAT:DFE check of 12" 1500# WI | Phase 2 Installation of new check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 80.4 | 2 | 80.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0060 | Cancel - PMAT:DFE check of 12" 1500# WI | Phase 2 Rigning of exis/new check valves | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 30.8 | 1 | 30.8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-INST | 2024-01-04 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0065 | Cancel - PMAT:DFE check of 12" 1500# WI | Reinstallation of instrument tubing (DFE | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-06 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0066 | Cancel - PMAT:DFE check of 12" 1500# WI | Test of instrument (DFE-12"-WI-355010-FE | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 20.1 | 1 | 20.1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-04 | 2019-07-09 | WDF | 1 | V | 1. Urgent | 2100022880 | 0070 | Cancel - PMAT:DFE check of 12" 1500# WI | Clean up | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFE-3551 |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0009 | PMAT:Valves internleaking Tyra EP-3805 3 | Make ICC - Prod | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.5 | 1 | 6.5 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-01 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0010 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2024-01-01 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0020 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Weld | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-01 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0030 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-02 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0040 | PMAT:Valves internleaking Tyra EP-3805 3 | Build scaffold Acc. drawing - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0050 | PMAT:Valves internleaking Tyra EP-3805 3 | Isolate for changing Valves - Prod | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2024-01-05 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0060 | PMAT:Valves internleaking Tyra EP-3805 3 | Replace needel valve whit SDBB - Weld | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-05 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0070 | PMAT:Valves internleaking Tyra EP-3805 3 | Ass. Replace needel valve whit SDBB - In | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2024-01-06 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0080 | PMAT:Valves internleaking Tyra EP-3805 3 | Replace needel valve whit SDBB - Weld | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-06 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0090 | PMAT:Valves internleaking Tyra EP-3805 3 | Ass. Replace needel valve whit SDBB - In | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2024-01-06 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0100 | PMAT:Valves internleaking Tyra EP-3805 3 | Replace needel valve whit SDBB - Weld | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-06 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0110 | PMAT:Valves internleaking Tyra EP-3805 3 | Ass. Replace needel valve whit SDBB - In | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-07 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0120 | PMAT:Valves internleaking Tyra EP-3805 3 | Make/Replace tubbing between valves - In | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 1 | 17.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-11 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0130 | PMAT:Valves internleaking Tyra EP-3805 3 | Leak test of tubbing - Prod | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.5 | 1 | 6.5 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-13 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0140 | PMAT:Valves internleaking Tyra EP-3805 3 | remove Isolate for changing Valves - Pro | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-14 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100022907 | 0150 | PMAT:Valves internleaking Tyra EP-3805 3 | Remove scaffolding - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-09-07 | WDF | 3 | V | 3. Intermediate | 2100022948 | 0020 | CMAT:DFE defekt ventil i slimline ventil | L2 change valve |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-09-07 | WDF | 3 | V | 3. Intermediate | 2100022948 | 0030 | CMAT:DFE defekt ventil i slimline ventil | L3 deisolate valve |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /E /75 | CHEMICAL STOR & INJECT (INCL METHANOL) | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0040 | Change gasket on | Isolate XCV |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0060 | Change gasket on | Rigging assist. Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0070 | Change gasket on | Demount XCV |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0080 | Change gasket on | Rigging assist. Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0090 | Change gasket on | Mount new XCV |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-03 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0100 | Change gasket on | Connect Pneumatic and controls |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0110 | Change gasket on | Functional test XCV |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2019-07-24 | WDF | 3 | I | 3. Intermediate | 2100022971 | 0120 | Change gasket on | De-Isolate XCV |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PPRT PRC SETC | DF /C /27/DFCM-XCV-34304 | CTRL VALVE - INLET FROM TEST SEPARATOR | DFC-TSEP | SECE - MECH | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0020 | 17/03-21 Kontraordre. Oprindelig PO bliv | Isolate equipment |  |  |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0030 | 17/03-21 Kontraordre. Oprindelig PO bliv | Dismantle valve mech |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-02 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0040 | 17/03-21 Kontraordre. Oprindelig PO bliv | Dismantle valve inst |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0050 | 17/03-21 Kontraordre. Oprindelig PO bliv | Rig out and in of valve |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0060 | 17/03-21 Kontraordre. Oprindelig PO bliv | Install new valve mech |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-04 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0070 | 17/03-21 Kontraordre. Oprindelig PO bliv | Install new valve inst |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0080 | 17/03-21 Kontraordre. Oprindelig PO bliv | Remove isolation |  |  |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-06 | 2020-09-03 | WDF | 4 | V | 4. Long | 2100023108 | 0090 | 17/03-21 Kontraordre. Oprindelig PO bliv | Remove rigging equipment |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL VPAS | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /10/DFAA-XCV-30336 | CONTROL VALVE - MFA-18 TO HP MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0020 | Exchange manifold valves for DFF-10 | Isolate equipment | 2 |  |  | 8 | 2 | 8 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0030 | Exchange manifold valves for DFF-10 | Dismantle top valve | 2 |  |  | 4 | 2 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0040 | Exchange manifold valves for DFF-10 | Rig out & in of top valve | 2 |  |  | 6 | 2 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0050 | Exchange manifold valves for DFF-10 | Install top valve | 2 |  |  | 4 | 2 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0060 | Exchange manifold valves for DFF-10 | Dismantle lower valve | 2 |  |  | 4 | 2 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-03 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0070 | Exchange manifold valves for DFF-10 | Rig out & in of lover valve | 2 |  |  | 6 | 2 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0080 | Exchange manifold valves for DFF-10 | Install lover valve | 2 |  |  | 4 | 2 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| PRODTECH | 2024-01-05 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0090 | Exchange manifold valves for DFF-10 | Remove isolation | 2 |  |  | 8 | 2 | 8 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-06 | 2020-08-15 | WDF | 4 | V | 4. Long | 2100023195 | 0100 | Exchange manifold valves for DFF-10 | Remove rigging equipment | 2 |  |  | 4 | 2 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2019-12-19 | WDF | 3 | I | 3. Intermediate | 2100023406 | 0020 | DFB-05, 400 bars anlæg, Defekt PRV | Change out PRV | 2 |  |  | 4 | 1 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-PRV-30118 | WELL 05 WING VALVE HYDRAULIC RELIEF | DFB-W05 |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-12-19 | WDF | 3 | I | 3. Intermediate | 2100023406 | 0030 | DFB-05, 400 bars anlæg, Defekt PRV | De-isolate drawer for well DFB-05 | 2 |  |  | 4 | 2 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-PRV-30118 | WELL 05 WING VALVE HYDRAULIC RELIEF | DFB-W05 |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0020 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Hang up the waist for valve removal | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-02 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0030 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Safing XCV-33071 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-03 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0040 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Remove Actuator (If needed) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-03 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0050 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Remove XCV-33071 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 2 | 5.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-03 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0060 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L2 mount new XCV-33071 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 2 | 5.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-03 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0070 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Mount Actuator (Is mount on new Valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-04 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0080 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Desafing XCV-33071 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-04 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0081 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Remove waist again and valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-06 | 2018-11-16 | WDF | 4 | V | 4. Long | 2100023440 | 0090 | PMAT:DFC- XCV-33071 Flowline FF int.læk | L3 Test and Documation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCM-XCV-33071 | SELECTOR VALVE ON CROSS-OVER MANIFOLD | DFX-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-MECH | 2023-12-31 | 2018-04-21 | WDF | 3 | V | 3. Intermediate | 2100023450 | 0010 | SMAT:Korroderede bolte på Transmitter DF | Skift af transmitter, plus dobbelt block |  |  |  | 54 | 2 | 26 | 6 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /C /70/DFCI-PDT-57127 | PRESSURE DIFF. TRANSMITTER | DFC-FUEL | SECE-CLJ003 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-04-21 | WDF | 3 | V | 3. Intermediate | 2100023450 | 0020 | SMAT:Korroderede bolte på Transmitter DF | De safing |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /C /70/DFCI-PDT-57127 | PRESSURE DIFF. TRANSMITTER | DFC-FUEL | SECE-CLJ003 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-04-21 | WDF | 3 | V | 3. Intermediate | 2100023450 | 0030 | SMAT:Korroderede bolte på Transmitter DF | leak test |  |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /C /70/DFCI-PDT-57127 | PRESSURE DIFF. TRANSMITTER | DFC-FUEL | SECE-CLJ003 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2018-03-18 | WDF | 3 | V | 3. Intermediate | 2100023525 | 0030 | SMAT:Changeout of SOV. | De-isolation. | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWSC | APPR OPND | REL PRT MANC PRC SETC | DF /F /10/DFFA-WCV-300420 | WING CONTROL VALVE (WS) | DFF-O20 |  | INLC | VEN-INST |  | 99000116
| MTN-MECH | 2024-01-01 | 2018-03-18 | WDF | 3 | V | 3. Intermediate | 2100023525 | 0040 | SMAT:Changeout of SOV. | Test and Cleanup. | 2 |  |  | 2 | 2 | 2 | 0 | APPR AWSC | APPR OPND | REL PRT MANC PRC SETC | DF /F /10/DFFA-WCV-300420 | WING CONTROL VALVE (WS) | DFF-O20 |  | INLC | VEN-INST |  | 99000116
| MTN-SCAF | 2023-12-31 | 2018-10-10 | WDF | 4 | V | 4. Long | 2100023702 | 0015 | SMAT:DFF 3'th ventil på bullheadline int | Scaffold/ rigging assist | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 1 | 17.4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-O05 |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-05 | 2018-10-10 | WDF | 4 | V | 4. Long | 2100023702 | 0020 | SMAT:DFF 3'th ventil på bullheadline int | L2 Replace 3 Psc Valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10.1 | 1 | 10.1 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-O05 |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-06 | 2018-10-10 | WDF | 4 | V | 4. Long | 2100023702 | 0030 | SMAT:DFF 3'th ventil på bullheadline int | L3 Sesafing of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-O05 |  | INLC | MTN-PIPF |  | 99000116
| MTN-ROPE | 2023-12-31 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0011 | ANOP DFF Korroderet flang på flare syst | Paint; Prep/Gear/Net/Barrier+Post |  |  |  | 12 | 3 | 12 | 0 | WREA APOG WMAT AWSC RDBL | WREA OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE | DFF2145788
| MTN-ROPE | 2024-01-01 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0012 | ANOP DFF Korroderet flang på flare syst | Paint; Clean, Inspect, Waste, QC, Primer |  |  |  | 12 | 3 | 12 | 0 | WREA APOG WMAT AWSC RDBL | WREA OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-02 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0013 | ANOP DFF Korroderet flang på flare syst | Paint; QC-Log, Recoat to Spec |  |  |  | 12 | 3 | 12 | 0 | WREA APOG WMAT AWSC RDBL | WREA OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-03 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0014 | ANOP DFF Korroderet flang på flare syst | Paint; Clean-Up+Backload |  |  |  | 6 | 3 | 6 | 0 | WREA APOG WMAT AWSC RDBL | WREA OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE
| MTN-MECH | 2024-01-03 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0019 | ANOP DFF Korroderet flang på flare syst | L3 Cleaning the welded flange | DAN-2022-FM-02 |  |  | 3 | 2 | 3 | 0 | WREA APOG WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE
| MTN-PIPF | 2024-01-04 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0020 | ANOP DFF Korroderet flang på flare syst | L2 Replace 1" 150# BL Flange | DAN-2022-FM-02 |  |  | 2 | 2 | 2 | 0 | WREA APOG WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE | 2150657
| PRODTECH | 2024-01-04 | 2018-08-30 | WDF | 3 | V | 3. Intermediate | 2100023776 | 0030 | ANOP DFF Korroderet flang på flare syst | L3 Desafe of DFFA-FI-570103 | DAN-2022-FM-02 |  |  | 3 | 2 | 3 | 0 | WREA APOG WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | DFGFLARE | 2022 | INLC | MTN-ROPE
| MTN-SCAF | 2023-12-31 | 2016-04-28 | WDF | 3 | S | 3. Intermediate | 2100023788 | 0001 | @+DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-HCV-303529 | HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-04-28 | WDF | 3 | S | 3. Intermediate | 2100023788 | 0010 | @+DFF-29 OIL HCV nedstrømschoke | Preparation for rigging | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-HCV-303529 | HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2016-04-28 | WDF | 3 | S | 3. Intermediate | 2100023788 | 0030 | @+DFF-29 OIL HCV nedstrømschoke | Safing of the HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-HCV-303529 | HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-04-28 | WDF | 3 | S | 3. Intermediate | 2100023788 | 0040 | @+DFF-29 OIL HCV nedstrømschoke | Rigging assistance during replacement of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 1 | 17.4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-HCV-303529 | HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2016-04-28 | WDF | 3 | S | 3. Intermediate | 2100023788 | 0060 | @+DFF-29 OIL HCV nedstrømschoke | Desafing and leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-HCV-303529 | HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-04-28 | WDF | 3 | S | 3. Intermediate | 2100023788 | 0070 | @+DFF-29 OIL HCV nedstrømschoke | Removal of rigging equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-HCV-303529 | HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2014-11-09 | WDF | 4 | V | 4. Long | 2100023804 | 0050 | @-DFF-06 OIL XCV-301306 intern læk | Rigging assistance during replacement of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSD SCH RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301306 | WELL 6 TO DFF HP PROD. MANIFOLD | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2023-12-31 | 2014-11-09 | WDF | 4 | V | 4. Long | 2100023804 | 0070 | @-DFF-06 OIL XCV-301306 intern læk | Installation of the new XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSD SCH RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301306 | WELL 6 TO DFF HP PROD. MANIFOLD | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-01 | 2014-11-09 | WDF | 4 | V | 4. Long | 2100023804 | 0080 | @-DFF-06 OIL XCV-301306 intern læk | Reestablishing hydr supply for the XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR WMAT AWSD SCH RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301306 | WELL 6 TO DFF HP PROD. MANIFOLD | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-01 | 2014-11-09 | WDF | 4 | V | 4. Long | 2100023804 | 0085 | @-DFF-06 OIL XCV-301306 intern læk | Reinstalling the positioner for the XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR WMAT AWSD SCH RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301306 | WELL 6 TO DFF HP PROD. MANIFOLD | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-01 | 2014-11-09 | WDF | 4 | V | 4. Long | 2100023804 | 0090 | @-DFF-06 OIL XCV-301306 intern læk | Desafing and leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSD SCH RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301306 | WELL 6 TO DFF HP PROD. MANIFOLD | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-01-23 | WDF | 3 | V | 3. Intermediate | 2100023810 | 0010 | @+DFF-23 OIL HCV opstrøms Manif. XCVs | Preparation for rigging | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2016-01-23 | WDF | 3 | V | 3. Intermediate | 2100023810 | 0030 | @+DFF-23 OIL HCV opstrøms Manif. XCVs | Safing of the HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-01 | 2016-01-23 | WDF | 3 | V | 3. Intermediate | 2100023810 | 0040 | @+DFF-23 OIL HCV opstrøms Manif. XCVs | Rigging assistance during replacement of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 1 | 17.4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-01 | 2016-01-23 | WDF | 3 | V | 3. Intermediate | 2100023810 | 0050 | @+DFF-23 OIL HCV opstrøms Manif. XCVs | Replacement of the HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-02 | 2016-01-23 | WDF | 3 | V | 3. Intermediate | 2100023810 | 0060 | @+DFF-23 OIL HCV opstrøms Manif. XCVs | Desafing and leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-01-23 | WDF | 3 | V | 3. Intermediate | 2100023810 | 0070 | @+DFF-23 OIL HCV opstrøms Manif. XCVs | Removal of rigging equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFF-OIL |  | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023869 | 0010 | SMAT:DFC Defekt HCV Upstrøms FE-50787 | Montering af stillads |  |  |  | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023869 | 0030 | SMAT:DFC Defekt HCV Upstrøms FE-50787 | udskifte ventil |  |  |  | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-08 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023869 | 0050 | SMAT:DFC Defekt HCV Upstrøms FE-50787 | Demontering af stillads. |  |  |  | 13 | 2 | 13 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023870 | 0005 | SMAT:DFC Defekt HCV Nedstrøms FE-50787 | Montering af stillads |  |  |  | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023870 | 0020 | SMAT:DFC Defekt HCV Nedstrøms FE-50787 | udskifte ventil |  |  |  | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-08 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023870 | 0030 | SMAT:DFC Defekt HCV Nedstrøms FE-50787 | Demontering af stillads. |  |  |  | 13 | 2 | 13 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2017-09-08 | WDF | 3 | V | 3. Intermediate | 2100023894 | 0020 | DFA-07 hydraulikskuffe udskiftes/back | Replacement with spare drawer | 4 |  |  | 12 | 2 | 12 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O07 |  | INLC | MTN-INST |  | 99000116
| PRODTECH | 2024-01-02 | 2017-09-08 | WDF | 3 | V | 3. Intermediate | 2100023894 | 0030 | DFA-07 hydraulikskuffe udskiftes/back | Desafing and leaking test | 4 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O07 |  | INLC | MTN-INST |  | 99000116
| MTN-MECH | 2024-01-02 | 2017-09-08 | WDF | 3 | V | 3. Intermediate | 2100023894 | 0040 | DFA-07 hydraulikskuffe udskiftes/back | Backload for rep and return | 4 |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O07 |  | INLC | MTN-INST |  | 99000116
| MTN-MECH | 2024-01-03 | 2017-09-08 | WDF | 3 | V | 3. Intermediate | 2100023894 | 0050 | DFA-07 hydraulikskuffe udskiftes/back | Returneret/renoveret skuffe lægges på of | 4 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O07 |  | INLC | MTN-INST |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-10-12 | WDF | 4 |  | 4. Long | 2100023913 | 0020 | Exchange 2" bypass valve over hcv-380229 | L2 Exchange valve |  |  |  | 6 | 2 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /12 | TRANSFER | DAB-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2019-10-12 | WDF | 4 |  | 4. Long | 2100023913 | 0030 | Exchange 2" bypass valve over hcv-380229 | L3 Remove isolation |  |  |  | 6 | 2 | 6 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /12 | TRANSFER | DAB-OIL |  | INLC | MTN-MECH
| VEN-INST | 2023-12-31 | 2019-04-15 | WDF | 3 | V | 3. Intermediate | 2100023940 | 0030 | Change valve using parts from offshore s | L3 deisolate system | 2 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-OIL | SECE - MECH @US37 | INLC | VEN-INST |  | 99000116
| VEN-INST | 2024-01-01 | 2019-04-15 | WDF | 3 | V | 3. Intermediate | 2100023940 | 0040 | Change valve using parts from offshore s | L3 Test and clean | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-OIL | SECE - MECH @US37 | INLC | VEN-INST |  | 99000116
| MTN-INST | 2023-12-31 | 2019-01-18 | WDF | 3 |  | 3. Intermediate | 2100024011 | 0020 | Change of valve for DFG-FIT-340441 | L2 Replace valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-CRAN | 2025-02-02 | 2016-07-25 | WDF | 3 | V | 3. Intermediate | 2100024146 | 0010 | DFE/78: SMAT:Dæksel v batteribox er besk | Dæksel over batteribox er beskadiget DFE |  |  |  | 10 | 1 | 80 | 70 | APPR AWDO RDBL ROUT | APPR OPND | REL PCNF MANC PRC SETC | DF /E /78/DFEZ-X-6150 | CRANE - 25 T | NOSD |  | INLC | MAINONSH |  | DK0500013007
| MTN-SCAF | 2023-12-31 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0020 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Build Scaffolding. | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 144 | 3 | 144 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-PAIN | 2024-01-12 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0021 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Cleaning/sandblastning of pipe | DAN-2022-FM-06 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16 | 2 | 16 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-PIPF | 2024-01-13 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0023 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Safing and cutting of pipe | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 24 | 2 | 24 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-RIGG | 2024-01-14 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0024 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Down/op rigging of pipe | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-PIPF | 2024-01-16 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0025 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Mounting of new spool | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE | 2134646
| MTN-PAIN | 2024-01-17 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0028 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Painting of pipe/Pyplog | DAN-2022-FM-06 |  | ¦10/01/2022 Wrk. Ctr. Migration | 32 | 2 | 32 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-PIPF | 2024-01-18 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0030 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Desafing of pipe | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-SCAF | 2024-01-19 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0031 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Demol of scaffolding | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 90 | 3 | 90 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| VEN-ELEC | 2024-01-26 | 2018-12-16 | WDF | 4 |  | 4. Long | 2100024395 | 0032 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | Demol of working light | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /28/DFF-4-DO-050-8032-AB-U | 4 OPEN DRAIN LINE | NOSD | 2022 Q4 | INLC | MTN-ROPE
| MTN-ROPE | 2023-12-31 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0010 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10.1 | 1 | 10.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2023-12-31 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0020 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Elec) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10.1 | 1 | 10.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2023-12-31 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0030 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10.1 | 1 | 10.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2023-12-31 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0040 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10.1 | 1 | 10.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-01 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0050 | ANOP Replace spool and valve for service | L3 Liftning procedure (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-02 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0052 | ANOP Replace spool and valve for service | L3 Install scaff (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-04 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0054 | ANOP Replace spool and valve for service | L1 Demol insulation (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-05 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0056 | ANOP Replace spool and valve for service | L1 Demol heatracing (El) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-06 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0060 | ANOP Replace spool and valve for service | L1 Install liftning equipment (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-07 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0070 | ANOP Replace spool and valve for service | L3 Check Marerials (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| PRODTECH | 2024-01-09 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0080 | ANOP Replace spool and valve for service | L1 Isolate (Prod) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-12 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0090 | ANOP Replace spool and valve for service | L1 Demol spool (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-13 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0092 | ANOP Replace spool and valve for service | L1 Scaff ass demol/install Spool (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-15 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0100 | ANOP Replace spool and valve for service | L1 Inspektion of Joint faces (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-15 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0110 | ANOP Replace spool and valve for service | L1 Install nye spool (weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| PRODTECH | 2024-01-16 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0120 | ANOP Replace spool and valve for service | L1 De-isolate (Prod) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-19 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0122 | ANOP Replace spool and valve for service | L3 Demol Liftning equipment (scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-20 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0130 | ANOP Replace spool and valve for service | L3 Re-Install Heatracing and check (El) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-22 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0140 | ANOP Replace spool and valve for service | L3 Re-Install insulation (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 1 | 16.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-26 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0150 | ANOP Replace spool and valve for service | L3 Demol scaff (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-28 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0160 | ANOP Replace spool and valve for service | L3 Cleaning (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-29 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0170 | ANOP Replace spool and valve for service | L3 Cleaning (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-ROPE | 2024-01-30 | 2019-06-30 | WDF | 3 |  | 3. Intermediate | 2100024400 | 0180 | ANOP Replace spool and valve for service | L3 Cleaning (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /77 | INDUSTRIAL WATER/GEN AND DIST | NOSD | AG - | INLC | MTN-ROPE |  | DK0500014763
| MTN-SCAF | 2023-12-31 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0010 | Leak on oxygen scav spool to DFE WI | Erection of scaffold | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 1 | 16.1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| VEN-ELEC | 2024-01-04 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0020 | Leak on oxygen scav spool to DFE WI | Isolate heat tracing | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| MTN-LAGG | 2024-01-04 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0030 | Leak on oxygen scav spool to DFE WI | Remove insulation | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| MTN-PAIN | 2024-01-05 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0040 | Leak on oxygen scav spool to DFE WI | Clean and apply furmafast wrap to pinhol | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| MTN-LAGG | 2024-01-06 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0050 | Leak on oxygen scav spool to DFE WI | Install insulation | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| VEN-ELEC | 2024-01-07 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0060 | Leak on oxygen scav spool to DFE WI | Deisolate heat tracing | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| MTN-SCAF | 2024-01-07 | 2019-07-05 | WDF | 2 |  | 2. Short | 2100024401 | 0070 | Leak on oxygen scav spool to DFE WI | Remove scaffold | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFA-1-WI-035-4141-AS-U | 1 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | INP-SITE |  | DK0500014763
| PRODTECH | 2023-12-31 | 2019-07-12 | WDF | 2 |  | 2. Short | 2100024404 | 0010 | Cancel/close 12”spoolWI-359015-AB to be | ICC sæt afspæring | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR PROK AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /54/DFE-12-WI-035-9015-AB-U | 12 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | VEN-MECH |  | DK0500014763
| MTN-SCAF | 2024-01-02 | 2019-07-12 | WDF | 2 |  | 2. Short | 2100024404 | 0020 | Cancel/close 12”spoolWI-359015-AB to be | scaffolding | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 45 | 1 | 45 | 0 | APPR PROK AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /54/DFE-12-WI-035-9015-AB-U | 12 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | VEN-MECH |  | DK0500014763
| MTN-ROPE | 2024-01-13 | 2019-07-12 | WDF | 2 |  | 2. Short | 2100024404 | 0030 | Cancel/close 12”spoolWI-359015-AB to be | demontering af 12”spoolWI-359015-AB og m | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 30.2 | 1 | 30.2 | 0 | APPR PROK AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /54/DFE-12-WI-035-9015-AB-U | 12 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | VEN-MECH |  | DK0500014763
| PRODTECH | 2024-01-20 | 2019-07-12 | WDF | 2 |  | 2. Short | 2100024404 | 0040 | Cancel/close 12”spoolWI-359015-AB to be | ophæv afsæringen | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR PROK AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /54/DFE-12-WI-035-9015-AB-U | 12 INJECTION WATER LINE | DFE-3551 | IF NOT DECOM P-3551 | INLC | VEN-MECH |  | DK0500014763
| MTN-SCAF | 2023-12-31 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0020 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Permit Preparation - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0040 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Preparation - Scaff | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0070 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Rigging of new Valve - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-02 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0080 | SMAT:DFF HCV-380027/HCV-380028 intern læ | isolator for replaceing HCV´s | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.5 | 1 | 6.5 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0120 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Replace HCV-380027 - Scaff ass | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0130 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.5 | 1 | 6.5 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-01 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0140 | SMAT:DFF HCV-380027/HCV-380028 intern læ | de-isolator after replaceing HCV´s | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.5 | 1 | 6.5 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-03 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0150 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Rigging of old Valve - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-08-14 | WDF | 4 | S | 4. Long | 2100024594 | 0180 | SMAT:DFF HCV-380027/HCV-380028 intern læ | Cleaning on site - Scaf | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /54/DFFA-HCV-380028 | HAND CONTROL VALVE | DAN-WI | AWSR | INLC | MTN-PIPF |  | 99000116
| MTN-INST | 2024-01-01 | 2020-07-14 | WDF | 4 | S | 4. Long | 2100024609 | 0030 | CMAT:Replace of ball valve HCV 40117 | L2 Replace valve |  |  |  | 8 | 2 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /37/DFBA-HCV-40117 | LC - HAND CONTROL VALVE | DFB-O08 | AWSR | INLC | MTN-INST |  | 99000116
| MTN-INST | 2024-01-02 | 2020-07-14 | WDF | 4 | S | 4. Long | 2100024609 | 0040 | CMAT:Replace of ball valve HCV 40117 | L3 De-Isolate and test for leak |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /37/DFBA-HCV-40117 | LC - HAND CONTROL VALVE | DFB-O08 | AWSR | INLC | MTN-INST |  | 99000116
| MTN-RIGG | 2023-12-31 | 2020-05-01 | WDF | 4 | V | 4. Long | 2100024676 | 0010 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWDO RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45092 | GAS LIFT FROM GAS EXPORT MANIFOLD VIA FB | SIWL | AWSR AWZMOG | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-01 | WDF | 4 | V | 4. Long | 2100024676 | 0020 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L2 Isolate DFAA-ESDV-45092 |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45092 | GAS LIFT FROM GAS EXPORT MANIFOLD VIA FB | SIWL | AWSR AWZMOG | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2020-05-01 | WDF | 4 | V | 4. Long | 2100024676 | 0040 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Help replace DFAA-ESDV-45092 |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45092 | GAS LIFT FROM GAS EXPORT MANIFOLD VIA FB | SIWL | AWSR AWZMOG | INLC | MTN-MECH
| PRODTECH | 2024-01-05 | 2020-05-01 | WDF | 4 | V | 4. Long | 2100024676 | 0050 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L2 De-Isolate/test DFAA-ESDV-45092 |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45092 | GAS LIFT FROM GAS EXPORT MANIFOLD VIA FB | SIWL | AWSR AWZMOG | INLC | MTN-MECH
| MTN-RIGG | 2024-01-06 | 2020-05-01 | WDF | 4 | V | 4. Long | 2100024676 | 0060 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg down |  |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWDO RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45092 | GAS LIFT FROM GAS EXPORT MANIFOLD VIA FB | SIWL | AWSR AWZMOG | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2019-05-21 | WDF | 4 | I | 4. Long | 2100024888 | 0020 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L2 Exchange valve |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /27/DFCM-P-5015 | SLOP OIL PUMP | DFCHPSEP | DANDPS | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-05-21 | WDF | 4 | I | 4. Long | 2100024888 | 0025 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L2 Exchange check valve |  |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /27/DFCM-P-5015 | SLOP OIL PUMP | DFCHPSEP | DANDPS | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2019-05-21 | WDF | 4 | I | 4. Long | 2100024888 | 0030 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L3 Remove isolation |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /27/DFCM-P-5015 | SLOP OIL PUMP | DFCHPSEP | DANDPS | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0001 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Prepare Permits Scaff | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0010 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Preparation for rigging MS | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0060 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Rigging assistance during replacement of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0080 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Installation of the new XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-01 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0090 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Reestablishing hydraulic supply for the | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-01 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0100 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Reinstalling the positioner for the XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0130 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Clean-up | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2023-12-31 | 2016-02-10 | WDF | 3 | V | 3. Intermediate | 2100024898 | 0020 | @DFB Gasliftmanifold HCVér til PI int | DFB, Udskift 2" 1500# HCV ventil Weld | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 2 | 16.1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /37/LIFT-GAS-MANIFOLD | LIFT GAS MANIFOLD | DFB-OIL | DFB OIL SD ASTD13 | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-01 | 2019-04-27 | WDF | 4 |  | 4. Long | 2100024915 | 0010 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Isolation of EP-3804 2" Bypass HCV | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /12 | TRANSFER | DFF-WI | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2019-04-27 | WDF | 4 |  | 4. Long | 2100024915 | 0015 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger assistance | 2 |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /12 | TRANSFER | DFF-WI | DFF | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2019-04-27 | WDF | 4 |  | 4. Long | 2100024915 | 0020 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L2 Changeout 2" Bypass HCV valve | 2 |  |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /12 | TRANSFER | DFF-WI | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2019-04-27 | WDF | 4 |  | 4. Long | 2100024915 | 0030 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 De-Isolation/leaktest EP-3804 2" Bypa | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /12 | TRANSFER | DFF-WI | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2019-11-15 | WDF | 3 | V | 3. Intermediate | 2100024935 | 0020 | Dan FA, Change of HCV on DFFA-EP-3804 | Isolate DFFA-EP-3804 |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DFF-WI | DFF | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2019-11-15 | WDF | 3 | V | 3. Intermediate | 2100024935 | 0030 | Dan FA, Change of HCV on DFFA-EP-3804 | Replace HCV on WI-line DFFA-EP-3804 |  |  |  | 8 | 1 | 8 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DFF-WI | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2019-11-15 | WDF | 3 | V | 3. Intermediate | 2100024935 | 0040 | Dan FA, Change of HCV on DFFA-EP-3804 | Assist in replacement |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DFF-WI | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2019-11-15 | WDF | 3 | V | 3. Intermediate | 2100024935 | 0050 | Dan FA, Change of HCV on DFFA-EP-3804 | Leaktest |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DFF-WI | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2019-11-15 | WDF | 3 | V | 3. Intermediate | 2100024935 | 0060 | Dan FA, Change of HCV on DFFA-EP-3804 | De-isolate DFFA-EP-3804 |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DFF-WI | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2019-11-15 | WDF | 3 | V | 3. Intermediate | 2100024935 | 0070 | Dan FA, Change of HCV on DFFA-EP-3804 | Rig-down hoist |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DFF-WI | DFF | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2020-04-11 | WDF | 3 | S | 3. Intermediate | 2100024985 | 0030 | DFFA-LG-340037 Lower leg blocked to leve | Changeout lower and upper leg valve |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-LG-340037 | LEVEL GAUGE | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2020-04-11 | WDF | 3 | S | 3. Intermediate | 2100024985 | 0040 | DFFA-LG-340037 Lower leg blocked to leve | Changeout drain valve DFFA-LG-340037 |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-LG-340037 | LEVEL GAUGE | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2020-04-11 | WDF | 3 | S | 3. Intermediate | 2100024985 | 0050 | DFFA-LG-340037 Lower leg blocked to leve | De-isolate/test V-3401 - PVI |  |  |  | 3 | 2 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-LG-340037 | LEVEL GAUGE | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2020-04-11 | WDF | 3 | S | 3. Intermediate | 2100024987 | 0030 | DFFA-LG-340033 Lower leg blocked to leve | Changeout lower and upper leg valve |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-LG-340033 | LEVEL GAUGE | DFFHPSEP | AWST | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2020-04-11 | WDF | 3 | S | 3. Intermediate | 2100024987 | 0040 | DFFA-LG-340033 Lower leg blocked to leve | Changeout drain valve DFFA-LG-340033 |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-LG-340033 | LEVEL GAUGE | DFFHPSEP | AWST | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2020-04-11 | WDF | 3 | S | 3. Intermediate | 2100024987 | 0050 | DFFA-LG-340033 Lower leg blocked to leve | De-isolate/test V-3401 - PVI |  |  |  | 3 | 2 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /20/DFFA-LG-340033 | LEVEL GAUGE | DFFHPSEP | AWST | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2020-06-28 | WDF | 4 | V | 4. Long | 2100024993 | 0020 | Exchange XCV-500041 | Exchange XCV mech | 2 |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500041 | UNCLASSIFIED VALVE | DFF-TSEP | DFF | INLC | MTN-MECH
| MTN-INST | 2023-12-31 | 2020-06-28 | WDF | 4 | V | 4. Long | 2100024993 | 0030 | Exchange XCV-500041 | Exchange XCV inst | 2 |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500041 | UNCLASSIFIED VALVE | DFF-TSEP | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-06-28 | WDF | 4 | V | 4. Long | 2100024993 | 0040 | Exchange XCV-500041 | Remove isolation | 2 |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500041 | UNCLASSIFIED VALVE | DFF-TSEP | DFF | INLC | MTN-MECH
| MTN-SCAF | 2024-01-01 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0015 | Actautor valve drivetrain repair DFFA-ES | L3 Erect scaffold to remove Spool above | 2 |  |  | 16 | 1 | 16 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0017 | Actautor valve drivetrain repair DFFA-ES | L3 Assist lifting spool / actutor | 2 |  |  | 8 | 1 | 8 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-07 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0030 | Actautor valve drivetrain repair DFFA-ES | L2 Isolate, depressurise and disconnect | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-07 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0040 | Actautor valve drivetrain repair DFFA-ES | L2 Remove the actuator from the valve to | 2 |  |  | 6 | 2 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-07 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0050 | Actautor valve drivetrain repair DFFA-ES | L2 Remove the valve transition plate to | 2 |  |  | 6 | 2 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-07 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0060 | Actautor valve drivetrain repair DFFA-ES | L2 Re-fit transition plate and tighten c | 2 |  |  | 6 | 2 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-08 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0070 | Actautor valve drivetrain repair DFFA-ES | L2 Fit jig plate for the magnetic drill | 2 |  |  | 6 | 2 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-08 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0080 | Actautor valve drivetrain repair DFFA-ES | L2 Set up magnetic base drill on valve t | 2 |  |  | 4 | 2 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-08 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0090 | Actautor valve drivetrain repair DFFA-ES | L2 Fit replacement, press-fit, high stre | 2 |  |  | 4 | 2 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-08 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0100 | Actautor valve drivetrain repair DFFA-ES | L2 Refit actuator to valve topworks tigh | 2 |  |  | 4 | 2 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| VEN-MECH | 2024-01-09 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0110 | Actautor valve drivetrain repair DFFA-ES | L2 Re-commission valve+return to service | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| MTN-SCAF | 2024-01-09 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0120 | Actautor valve drivetrain repair DFFA-ES | L3 Remove scaffold | 2 |  |  | 8 | 1 | 8 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-01-11 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0125 | Actautor valve drivetrain repair DFFA-ES | L3 L3 Assist lifting spool / actutor | 2 |  |  | 8 | 1 | 8 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-13 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0130 | Actautor valve drivetrain repair DFFA-ES | L3 De-Safing of DFFA-ESDV-340048 | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| PRODTECH | 2024-01-13 | 2019-04-26 | WDF | 4 | V | 4. Long | 2100025025 | 0135 | Actautor valve drivetrain repair DFFA-ES | L3 Remove Inhibit DFFA-ESDV-340048 | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /F /20/DFFA-ESDV-340048 | V-3401 GAS OUTLET TO V-4301 SHUTDOWN | DFFHPSEP | DFF | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0005 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 52.3 | 3 | 52.3 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-04 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0010 | CMAT:Demol of flare valve, level glass a | L3 Construction tent | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 52.3 | 3 | 52.3 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-08 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0020 | CMAT:Demol of flare valve, level glass a | L3 Establishing lights and blowers | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| PRODTECH | 2024-01-09 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0030 | CMAT:Demol of flare valve, level glass a | L3 Safing of the flare valve and flare m | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-09 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0040 | CMAT:Demol of flare valve, level glass a | L3 Demol of the old spool, valve and lev | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-10 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0050 | CMAT:Demol of flare valve, level glass a | L1 Welding on flange | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-11 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0055 | CMAT:Demol of flare valve, level glass a | L1 Test of flange | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-12 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0060 | CMAT:Demol of flare valve, level glass a | L1 Removing the level glass and installi | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| PRODTECH | 2024-01-13 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0070 | CMAT:Demol of flare valve, level glass a | L2 Desafing and leaktest | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PAIN | 2024-01-13 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0075 | CMAT:Demol of flare valve, level glass a | L3 Painting of flanges | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| QAQCPAIN | 2024-01-14 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0076 | CMAT:Demol of flare valve, level glass a | L3 QC of painted flanges | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1 | 1 | 1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INT | MTN-PIPF
| MTN-PIPF | 2024-01-14 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0080 | CMAT:Demol of flare valve, level glass a | L3 Demol of lights and blowers | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-15 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0090 | CMAT:Demol of flare valve, level glass a | L3 Demol of the tent | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-17 | 2018-07-26 | WDF | 3 | S | 3. Intermediate | 2100025039 | 0100 | CMAT:Demol of flare valve, level glass a | L3 Demol of scaffolding | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /32/DFFA-LG-340126 | LEVEL GAUGE | D-FLARE | DFF | INLC | MTN-PIPF
| PRODTECH | 2024-01-01 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0020 | Replacement of DFFA-PDCV-500606 | Isolate PDCV | 2 |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-02 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0030 | Replacement of DFFA-PDCV-500606 | Isolate pneumatic and controls | 2 |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0040 | Replacement of DFFA-PDCV-500606 | Rigging assist. Rig in/out | 2 |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0060 | Replacement of DFFA-PDCV-500606 | Rigging assist. Rig in/out | 2 |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-03 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0080 | Replacement of DFFA-PDCV-500606 | Re-build tubing if any | 2 |  |  | 1 | 1 | 1 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-03 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0090 | Replacement of DFFA-PDCV-500606 | Connect Controls and pneumatic | 2 |  |  | 1 | 1 | 1 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0110 | Replacement of DFFA-PDCV-500606 | Deisolate PDCV | 2 |  |  | 1 | 1 | 1 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2017-12-07 | WDF | 3 | V | 3. Intermediate | 2100025050 | 0040 | SMAT:Defekt tilbagemelding ZSO/ZSC på DF | Udskiftning af BDV-410521 | 2 |  |  | 10 | 2 | 10 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | D-FLARE | DFF | INLC | MTN-INST |  | 99000116
| MTN-ELEC | 2024-01-01 | 2017-12-07 | WDF | 3 | V | 3. Intermediate | 2100025050 | 0050 | SMAT:Defekt tilbagemelding ZSO/ZSC på DF | Demontering/montering elektrisk | 2 |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | D-FLARE | DFF | INLC | MTN-INST |  | 99000116
| MTN-INST | 2024-01-02 | 2017-12-07 | WDF | 3 | V | 3. Intermediate | 2100025050 | 0051 | SMAT:Defekt tilbagemelding ZSO/ZSC på DF | Montering af hydraulik panel | 2 |  |  | 10 | 1 | 10 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | D-FLARE | DFF | INLC | MTN-INST |  | 99000116
| MTN-INST | 2024-01-04 | 2017-12-07 | WDF | 3 | V | 3. Intermediate | 2100025050 | 0052 | SMAT:Defekt tilbagemelding ZSO/ZSC på DF | Fabrikering af nye instrument rør | 2 |  |  | 10 | 1 | 10 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | D-FLARE | DFF | INLC | MTN-INST |  | 99000116
| PRODTECH | 2024-01-07 | 2017-12-07 | WDF | 3 | V | 3. Intermediate | 2100025050 | 0060 | SMAT:Defekt tilbagemelding ZSO/ZSC på DF | Desafing og leaktest | 2 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | D-FLARE | DFF | INLC | MTN-INST |  | 99000116
| MTN-ROPE | 2023-12-31 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0015 | DFFE: Dismount/mount over spooling arran | Erect small scaffold |  |  |  | 10 | 2 | 10 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-01 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0020 | DFFE: Dismount/mount over spooling arran | Dismount overspooling arrangement | 6 |  |  | 12 | 1 | 12 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-ROPE | 2024-01-01 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0030 | DFFE: Dismount/mount over spooling arran | Rigging down overspooling arrangement | 2 |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-03 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0040 | DFFE: Dismount/mount over spooling arran | Clean mounting surfaces | 6 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-ROPE | 2024-01-03 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0050 | DFFE: Dismount/mount over spooling arran | Rig up new overspooling arrengement | 2 |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-05 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0060 | DFFE: Dismount/mount over spooling arran | Install new overspooling arrengement | 2 |  |  | 12 | 1 | 12 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-08 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0070 | DFFE: Dismount/mount over spooling arran | Adjustments | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-08 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0080 | DFFE: Dismount/mount over spooling arran | Assist in replacement | 6 |  |  | 12 | 1 | 12 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-11 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0090 | DFFE: Dismount/mount over spooling arran | De-isolation of crane & test | 6 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| VEN-CRAN | 2024-01-12 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0100 | DFFE: Dismount/mount over spooling arran | Function test, QC, Clean up, report | 2 |  |  | 4 | 1 | 4 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| MTN-ROPE | 2024-01-12 | 2019-05-07 | WDF | 3 | V | 3. Intermediate | 2100025052 | 0110 | DFFE: Dismount/mount over spooling arran | Remove scaffold |  |  |  | 10 | 2 | 10 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD | DFF | INLC | MTN-CRAN
| VEN-MECH | 2023-12-31 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0030 | Replace DFFA-ESDV-570071 | L1 Dismantle valve mech | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH | 329666 | 99000116
| VEN-ELEC | 2023-12-31 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0040 | Replace DFFA-ESDV-570071 | L3 Dismantle valve elec | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH |  | 99000116
| VEN-SCAF | 2024-01-01 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0050 | Replace DFFA-ESDV-570071 | L3 Rig out & in of valve | 2 |  |  | 4 | 2 | 4 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0060 | Replace DFFA-ESDV-570071 | L1 Install new valve mech | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH |  | 99000116
| VEN-ELEC | 2024-01-01 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0070 | Replace DFFA-ESDV-570071 | L1 Install new valve elec | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0080 | Replace DFFA-ESDV-570071 | L3 Remove isolation | 2 |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH |  | 99000116
| VEN-SCAF | 2024-01-02 | 2019-05-03 | WDF | 4 | V | 4. Long | 2100025077 | 0090 | Replace DFFA-ESDV-570071 | L3 Remove rigging equipment | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /70/DFFA-ESDV-570071 | ACTUATED BALL VALVE | DFF-COOL | SECE MECH | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0020 | CMAT:Exchange packing set on valve stem. | L3 Isolation of valve |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0030 | CMAT:Exchange packing set on valve stem. | L3 Dismantle actuator from valve |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-02 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0040 | CMAT:Exchange packing set on valve stem. | L3 Rig actuator off valve |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0050 | CMAT:Exchange packing set on valve stem. | L3 Exchange stem gasket |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-04 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0060 | CMAT:Exchange packing set on valve stem. | L3 Rig actuator onto valve |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0070 | CMAT:Exchange packing set on valve stem. | L3 Install actuator onto valve |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2019-03-29 | WDF | 3 | I | 3. Intermediate | 2100025138 | 0080 | CMAT:Exchange packing set on valve stem. | L3 Remove isolation |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /50/DFFA-PCV-530001 | PRESSURE CONTROL VALVE | DFF-COOL | DFFNWI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100025174 | 0010 | CMAT:Clean Water clarifier quill. | L3 isolate quill and |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /75/DFGA-CP-5001 | CORROSION PROBE FITTING | DFG-IGF | DFGDEV | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100025174 | 0020 | CMAT:Clean Water clarifier quill. | L3 Dismantle quill |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /75/DFGA-CP-5001 | CORROSION PROBE FITTING | DFG-IGF | DFGDEV | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100025174 | 0030 | CMAT:Clean Water clarifier quill. | L3 clean quill |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /75/DFGA-CP-5001 | CORROSION PROBE FITTING | DFG-IGF | DFGDEV | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100025174 | 0040 | CMAT:Clean Water clarifier quill. | L3 install and deisolate quill |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /75/DFGA-CP-5001 | CORROSION PROBE FITTING | DFG-IGF | DFGDEV | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2019-06-20 | WDF | 3 | V | 3. Intermediate | 2100025174 | 0050 | CMAT:Clean Water clarifier quill. | L3 Test system |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /75/DFGA-CP-5001 | CORROSION PROBE FITTING | DFG-IGF | DFGDEV | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2019-03-02 | WDF | 3 | V | 3. Intermediate | 2100025274 | 0020 | Specialist to clean pipe for sand. | L3 Isolate Pipe. | 4 |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-XCV-340413 | CLEAN SOLIDS TO SAND DRAIN HEADER | NOSD | DFGDEV | INLC | MTN-MECH
| VEN-MECH | 2024-01-02 | 2019-03-02 | WDF | 3 | V | 3. Intermediate | 2100025274 | 0030 | Specialist to clean pipe for sand. | L3 specialist to clean pipe | 4 |  |  | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-XCV-340413 | CLEAN SOLIDS TO SAND DRAIN HEADER | NOSD | DFGDEV | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2019-03-02 | WDF | 3 | V | 3. Intermediate | 2100025274 | 0040 | Specialist to clean pipe for sand. | L3 Desolate | 4 |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-XCV-340413 | CLEAN SOLIDS TO SAND DRAIN HEADER | NOSD | DFGDEV | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2019-03-02 | WDF | 3 | V | 3. Intermediate | 2100025274 | 0050 | Specialist to clean pipe for sand. | L3 check if valve closes. | 4 |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-XCV-340413 | CLEAN SOLIDS TO SAND DRAIN HEADER | NOSD | DFGDEV | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2018-11-06 | WDF | 3 | I | 3. Intermediate | 2100025277 | 0010 | Exchange of valve and actuator. | L3 Isolate valve |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /28/DFGA-XCV-500412 | P-5041 DISCHARGE TO HAZ. OPEN DRAINS | DAN FG | DFGDEV | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2018-11-06 | WDF | 3 | I | 3. Intermediate | 2100025277 | 0020 | Exchange of valve and actuator. | L2 exchange valve |  |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /28/DFGA-XCV-500412 | P-5041 DISCHARGE TO HAZ. OPEN DRAINS | DAN FG | DFGDEV | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2018-11-06 | WDF | 3 | I | 3. Intermediate | 2100025277 | 0030 | Exchange of valve and actuator. | L3 Remove isolation |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /28/DFGA-XCV-500412 | P-5041 DISCHARGE TO HAZ. OPEN DRAINS | DAN FG | DFGDEV | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-03 | 2018-11-06 | WDF | 3 | I | 3. Intermediate | 2100025277 | 0040 | Exchange of valve and actuator. | L3 Remove valve from lower deck |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /28/DFGA-XCV-500412 | P-5041 DISCHARGE TO HAZ. OPEN DRAINS | DAN FG | DFGDEV | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2018-12-21 | WDF | 3 | V | 3. Intermediate | 2100025282 | 0010 | Exhaust ducting repairs | Install scaffolding | 2 |  |  | 32.2 | 2 | 32.2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /54/DFGA-A-3590 | WI PUMP UNIT | DFG-3590 | DFGDEV | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-04 | 2018-12-21 | WDF | 3 | V | 3. Intermediate | 2100025282 | 0020 | Exhaust ducting repairs | Repair ducting | 2 |  |  | 48.2 | 2 | 48.2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /54/DFGA-A-3590 | WI PUMP UNIT | DFG-3590 | DFGDEV | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-07 | 2018-12-21 | WDF | 3 | V | 3. Intermediate | 2100025282 | 0030 | Exhaust ducting repairs | Remove scaffolding | 2 |  |  | 32.2 | 2 | 32.2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /54/DFGA-A-3590 | WI PUMP UNIT | DFG-3590 | DFGDEV | INLC | MTN-PIPF
| MTN-MECH | 2023-12-31 | 2017-06-07 | WDF | 3 | V | 3. Intermediate | 2100025284 | 0010 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Aktuator er Ekstern læk | 2 |  |  | 6 | 2 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /G /27/DFGA-ESDV-500650 | EMERGENCY SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | MTN-MECH |  | DK0500013007
| MTN-ROPE | 2023-12-31 | 2016-02-15 | WDF | 3 | V | 3. Intermediate | 2100025286 | 0002 | SMAT:HCV nedtsrøms FG fuel heater int læ | Ophængning af taljer for 6" HCV Ventil, | On removed List 2 |  |  | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL ROUT | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /G /70/DFGA-XE-5742 | SHELL FOR HE-5742 | DFG-FUEL | DFGDEV | INT | MTN-MECH
| MTN-ROPE | 2024-01-02 | 2016-02-15 | WDF | 3 | V | 3. Intermediate | 2100025286 | 0003 | SMAT:HCV nedtsrøms FG fuel heater int læ | I forbindelse med udskiftning af HCV, sk | On removed List 2 |  |  | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL ROUT | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /G /70/DFGA-XE-5742 | SHELL FOR HE-5742 | DFG-FUEL | DFGDEV | INT | MTN-MECH
| MTN-ROPE | 2024-01-04 | 2016-02-15 | WDF | 3 | V | 3. Intermediate | 2100025286 | 0005 | SMAT:HCV nedtsrøms FG fuel heater int læ | Afmontering af isolering. | On removed List 2 |  |  | 17.4 | 1 | 17.4 | 0 | APPR AWSD AWSC RDBL ROUT | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /G /70/DFGA-XE-5742 | SHELL FOR HE-5742 | DFG-FUEL | DFGDEV | INT | MTN-MECH
| MTN-ROPE | 2024-01-08 | 2016-02-15 | WDF | 3 | V | 3. Intermediate | 2100025286 | 0010 | SMAT:HCV nedtsrøms FG fuel heater int læ | Afmontering og montering af HCV. | On removed List 2 |  |  | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWSC RDBL ROUT | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /G /70/DFGA-XE-5742 | SHELL FOR HE-5742 | DFG-FUEL | DFGDEV | INT | MTN-MECH
| PRODTECH | 2023-12-31 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0020 | ANOP DAN FC, Corroded pipes & valveses. | Safing of pipe and system. | DAN-2022-FM-11 |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-ELEC | 2024-01-02 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0030 | ANOP DAN FC, Corroded pipes & valveses. | Demol heattracing for instruments. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 4 | 1 | 4 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | 2138634 | 99000116
| MTN-LAGG | 2024-01-03 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0040 | ANOP DAN FC, Corroded pipes & valveses. | Demol insulation for instruments. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-PIPF | 2024-01-03 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0050 | ANOP DAN FC, Corroded pipes & valveses. | Demol flanges and valves. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | 2138271 | 99000116
| MTN-ELEC | 2024-01-04 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0060 | ANOP DAN FC, Corroded pipes & valveses. | Demol instrument tubing for instruments. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | 2138390 | 99000116
| MTN-ROPE | 2024-01-05 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0062 | ANOP DAN FC, Corroded pipes & valveses. | Paint; Prep/Scaf/Rope/Gear/Net+Post |  |  |  | 12 | 3 | 12 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | DFC2139178 | 99000116
| MTN-ROPE | 2024-01-06 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0063 | ANOP DAN FC, Corroded pipes & valveses. | Paint; Clean-Off, Inspect, QC.Log, Waste |  |  |  | 12 | 3 | 12 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-ROPE | 2024-01-07 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0064 | ANOP DAN FC, Corroded pipes & valveses. | Paint; QC-Log, Recoat to Spec |  |  |  | 12 | 3 | 12 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-ROPE | 2024-01-08 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0065 | ANOP DAN FC, Corroded pipes & valveses. | Paint; Clean-Up+Color-Cote+Backload |  |  |  | 6 | 3 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-PIPF | 2024-01-09 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0070 | ANOP DAN FC, Corroded pipes & valveses. | Install new flanges and 2xValves. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | 2138271 | 99000116
| MTN-ELEC | 2024-01-09 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0080 | ANOP DAN FC, Corroded pipes & valveses. | Install new tubing for instruments. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 18 | 1 | 18 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | 2138390 | 99000116
| MTN-ELEC | 2024-01-14 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0090 | ANOP DAN FC, Corroded pipes & valveses. | Install and test heat tracing. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE | 2138634 | 99000116
| MTN-ELEC | 2024-01-15 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0100 | ANOP DAN FC, Corroded pipes & valveses. | Install insulation tubing instruments. | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 8 | 1 | 8 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-ELEC | 2024-01-17 | 2019-10-25 | WDF | 3 | V | 3. Intermediate | 2100025311 | 0110 | ANOP DAN FC, Corroded pipes & valveses. | Test instrument to SCADA (CCR). | DAN-2022-FM-11 |  | Fabric maintenance - Corroded piping | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /70/DFCI-PT-57132 | PRESSURE TRANSMITTER (ESD) | DFC-FUEL | 2022 DFGFES- | INLC | MTN-ROPE |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0010 | Exchange actuator & positioner. | L3 Prepare lifting equipment |  |  |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0020 | Exchange actuator & positioner. | L3 Isolate equipment |  |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0030 | Exchange actuator & positioner. | L3 Dismantle actuator |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-03 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0040 | Exchange actuator & positioner. | L3 Rig out of Actuator |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-04 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0050 | Exchange actuator & positioner. | L3 Rig in of Actuator |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0060 | Exchange actuator & positioner. | L2 Install new actuator & positioner |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0070 | Exchange actuator & positioner. | L3 Remove isolation |  |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-07 | 2019-02-16 | WDF | 3 | I | 3. Intermediate | 2100025335 | 0080 | Exchange actuator & positioner. | L3 Remove lifting equipment |  |  |  | 10 | 2 | 10 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /50/DFGA-FCV-530530 | CONTROL VALVE | NOSD | DFGPRO | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0004 | DFC HCV-03067 LV05 Intern læk | Permit Scaff | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 13 | 1 | 13 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2023-12-31 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0005 | DFC HCV-03067 LV05 Intern læk | Permit Rigger | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 13 | 1 | 13 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2024-01-01 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0020 | DFC HCV-03067 LV05 Intern læk | Rig-up hoist for removal | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-PIPF | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0040 | DFC HCV-03067 LV05 Intern læk | Replace DFC-HCV-03067 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2024-01-01 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0050 | DFC HCV-03067 LV05 Intern læk | Assist in replacement | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-PIPF | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0070 | DFC HCV-03067 LV05 Intern læk | Leaktest | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0080 | DFC HCV-03067 LV05 Intern læk | Rig-down hoist | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10 | 2 | 10 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-SCAF | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0090 | DFC HCV-03067 LV05 Intern læk | Rig-down scaffold and clean-up area | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 27 | 3 | 27 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| MTN-SCAF | 2023-12-31 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0010 | DFBA-HCV-35730 has to be changed | L3 Scaffold up | 7 |  |  | 24 | 3 | 24 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0015 | DFBA-HCV-35730 has to be changed | L3 Rick up hoist | 7 |  |  | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0020 | DFBA-HCV-35730 has to be changed | L3 Isolate DFBA-HCV-35730 | 7 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-04 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0030 | DFBA-HCV-35730 has to be changed | L3 Rigger assistance | 7 |  |  | 8 | 1 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0040 | DFBA-HCV-35730 has to be changed | L2 Replace DFBA-HCV-35730 | 7 |  |  | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0050 | DFBA-HCV-35730 has to be changed | L3 De-isolate and leaktest HDFBA-HCV-357 | 7 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-07 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0060 | DFBA-HCV-35730 has to be changed | L3 Rick down hoist | 7 |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-08 | 2020-06-15 | WDF | 4 | S | 4. Long | 2100025580 | 0070 | DFBA-HCV-35730 has to be changed | L3 Scaffold down | 7 |  |  | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35730 | CONTROL VALVE - WI. TO MANIFOLD SOUTH | DFX-WI | FWI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-03-16 | WDF | 3 | I | 3. Intermediate | 2100025589 | 0020 | CMAT:Exchange inlet HCV for P-3511 | L3 Isolate equipment |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /54/DFCM-P-3511 | SEAWATER FILTER FEED PUMP | DFE-3551 | FWI | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-03-16 | WDF | 3 | I | 3. Intermediate | 2100025589 | 0030 | CMAT:Exchange inlet HCV for P-3511 | L2 Exchange valve |  |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /54/DFCM-P-3511 | SEAWATER FILTER FEED PUMP | DFE-3551 | FWI | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-01 | 2019-03-16 | WDF | 3 | I | 3. Intermediate | 2100025589 | 0040 | CMAT:Exchange inlet HCV for P-3511 | L3 Rigging of valve |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /54/DFCM-P-3511 | SEAWATER FILTER FEED PUMP | DFE-3551 | FWI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2019-03-16 | WDF | 3 | I | 3. Intermediate | 2100025589 | 0050 | CMAT:Exchange inlet HCV for P-3511 | L3 Remove isolation |  |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /54/DFCM-P-3511 | SEAWATER FILTER FEED PUMP | DFE-3551 | FWI | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0020 | Exchange ESDV-441327. | L3 Pre permit & linewalk | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-02 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0040 | Exchange ESDV-441327. | L3 Rig in valve to access platform | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| PRODTECH | 2024-01-04 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0050 | Exchange ESDV-441327. | L3 Isolate equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-05 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0060 | Exchange ESDV-441327. | L3 Dismantle valve mech | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-05 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0070 | Exchange ESDV-441327. | L3 Dismantle valve elec | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-06 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0080 | Exchange ESDV-441327. | L3 Rig out & in of valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-08 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0090 | Exchange ESDV-441327. | L1 Install new valve mech | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-08 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0100 | Exchange ESDV-441327. | L1 Install new valve elec | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| PRODTECH | 2024-01-09 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0110 | Exchange ESDV-441327. | L3 Remove isolation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-11 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0120 | Exchange ESDV-441327. | L3 Clean up area | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-11 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026132 | 0130 | Exchange ESDV-441327. | L3 Clean up area | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441327 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | HALBR2 | INLC | MTN-PIPF
| MTN-SCAF | 2023-12-31 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0020 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4.4 | 1 | 4.4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| PRODTECH | 2024-01-01 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0040 | Exchange DFFA-ESDV-441330 | L3 Isolate equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-01 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0050 | Exchange DFFA-ESDV-441330 | L3 Dismantle valve mech | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-01 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0060 | Exchange DFFA-ESDV-441330 | L3 Dismantle valve elec | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2 | 1 | 2 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-01 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0070 | Exchange DFFA-ESDV-441330 | L3 Rig out & in of valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-02 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0080 | Exchange DFFA-ESDV-441330 | L1 Install new valve mech | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| VEN-ELEC | 2024-01-02 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0090 | Exchange DFFA-ESDV-441330 | L1 Install new valve elec | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2 | 1 | 2 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| PRODTECH | 2024-01-02 | 2019-04-15 | WDF | 4 | V | 4. Long | 2100026133 | 0100 | Exchange DFFA-ESDV-441330 | L3 Remove isolation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /31/DFFA-ESDV-441330 | EMERGENCY SHUTDOWN VALVE | DAN-GAS | SECE TEAM L0512443 | INLC | MTN-PIPF
| MTN-SCAF | 2023-12-31 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0005 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up scaffold | 2 |  |  | 24 | 3 | 24 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0010 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | 2 |  |  | 10 | 2 | 10 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0020 | Replace DFFA-XCV-380604 (Halfdan riser) | L2 Isolate DFFA-XCV-380604 | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-INST | 2024-01-04 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0025 | Replace DFFA-XCV-380604 (Halfdan riser) | L2 Dismantle inst-pipe | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0030 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Replace DFFA-XCV-380604 | 2 |  |  | 18 | 2 | 18 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-RIGG | 2024-01-04 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0040 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Assist in replacing DFFA-XCV-380604 | 2 |  |  | 10 | 1 | 10 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-INST | 2024-01-06 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0045 | Replace DFFA-XCV-380604 (Halfdan riser) | L2 Re-mount inst-pipe | 2 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| PRODTECH | 2024-01-07 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0050 | Replace DFFA-XCV-380604 (Halfdan riser) | L2 De-Isolate/test DFFA-XCV-380604 | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-RIGG | 2024-01-08 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0060 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-down hoist | 2 |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-SCAF | 2024-01-09 | 2019-12-20 | WDF | 3 | V | 3. Intermediate | 2100026134 | 0070 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-down scaffold & clean area | 2 |  |  | 21 | 3 | 21 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-XCV-380604 | WI LINE BLOCK VALVE | DFF-WI | HALBRI | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2015-01-25 | WDF | 4 | S | 4. Long | 2100026139 | 0010 | Skift HCV-380326 (*NSD). | Bygning af stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380326 | CONTROL VALVE - EP-3805 IN/OUT | DHDLPGAS | HALDC1 | INLC | PRODTECH |  | 99000116
| PRODTECH | 2024-01-02 | 2015-01-25 | WDF | 4 | S | 4. Long | 2100026139 | 0020 | Skift HCV-380326 (*NSD). | Safing | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5 | 1 | 5 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380326 | CONTROL VALVE - EP-3805 IN/OUT | DHDLPGAS | HALDC1 | INLC | PRODTECH |  | 99000116
| VEN-ELEC | 2024-01-03 | 2015-01-25 | WDF | 4 | S | 4. Long | 2100026139 | 0030 | Skift HCV-380326 (*NSD). | El assistance | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380326 | CONTROL VALVE - EP-3805 IN/OUT | DHDLPGAS | HALDC1 | INLC | PRODTECH |  | 99000116
| MTN-PIPF | 2024-01-04 | 2015-01-25 | WDF | 4 | S | 4. Long | 2100026139 | 0040 | Skift HCV-380326 (*NSD). | Udskiftning af HCV-380326 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 2 | 16.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380326 | CONTROL VALVE - EP-3805 IN/OUT | DHDLPGAS | HALDC1 | INLC | PRODTECH |  | 99000116
| PRODTECH | 2024-01-05 | 2015-01-25 | WDF | 4 | S | 4. Long | 2100026139 | 0050 | Skift HCV-380326 (*NSD). | Desafing | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5 | 1 | 5 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380326 | CONTROL VALVE - EP-3805 IN/OUT | DHDLPGAS | HALDC1 | INLC | PRODTECH |  | 99000116
| MTN-SCAF | 2024-01-06 | 2015-01-25 | WDF | 4 | S | 4. Long | 2100026139 | 0060 | Skift HCV-380326 (*NSD). | Nedtagning af stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380326 | CONTROL VALVE - EP-3805 IN/OUT | DHDLPGAS | HALDC1 | INLC | PRODTECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2020-05-05 | WDF | 3 | V | 3. Intermediate | 2100026509 | 0010 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | 6 |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-BDV-380137 | BLOWDOWN VALVE | DFG20MPH | HN3DFG | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-05 | WDF | 3 | V | 3. Intermediate | 2100026509 | 0020 | DFG Lvl 2 Replace BDV 380137 | Isolate BDV 380137 | 6 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-BDV-380137 | BLOWDOWN VALVE | DFG20MPH | HN3DFG | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2020-05-05 | WDF | 3 | V | 3. Intermediate | 2100026509 | 0040 | DFG Lvl 2 Replace BDV 380137 | Functional test of BDV 380137 | 6 |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-BDV-380137 | BLOWDOWN VALVE | DFG20MPH | HN3DFG | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2020-05-05 | WDF | 3 | V | 3. Intermediate | 2100026509 | 0050 | DFG Lvl 2 Replace BDV 380137 | De-isolate BDV 380137 | 6 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-BDV-380137 | BLOWDOWN VALVE | DFG20MPH | HN3DFG | INLC | MTN-MECH
| MTN-RIGG | 2024-01-04 | 2020-05-05 | WDF | 3 | V | 3. Intermediate | 2100026509 | 0060 | DFG Lvl 2 Replace BDV 380137 | Rig-down hoist | 6 |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-BDV-380137 | BLOWDOWN VALVE | DFG20MPH | HN3DFG | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2020-08-29 | WDF | 4 | V | 4. Long | 2100026510 | 0020 | 1" HCV to PI-381302 internal leak | Prod prepare permit/isolation |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-EP-3813 | PIG RECEIVER | DFG20MPH | HN3DFG | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2020-08-29 | WDF | 4 | V | 4. Long | 2100026510 | 0030 | 1" HCV to PI-381302 internal leak | Replace 1" Neeedle Valve |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-EP-3813 | PIG RECEIVER | DFG20MPH | HN3DFG | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2020-08-29 | WDF | 4 | V | 4. Long | 2100026510 | 0040 | 1" HCV to PI-381302 internal leak | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-EP-3813 | PIG RECEIVER | DFG20MPH | HN3DFG | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2020-08-29 | WDF | 4 | V | 4. Long | 2100026510 | 0050 | 1" HCV to PI-381302 internal leak | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-EP-3813 | PIG RECEIVER | DFG20MPH | HN3DFG | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-01 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0030 | Udskiftning af HCV-38170 | Konstruktion af repos omkring ventilen | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 40.2 | 3 | 40.2 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2024-01-04 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0040 | Udskiftning af HCV-38170 | Klargøring for udrigning af ventil | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0070 | Udskiftning af HCV-38170 | Udrigning af gammel HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2024-01-03 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0080 | Udskiftning af HCV-38170 | Indrigning af ny HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 26.1 | 3 | 26.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2024-01-03 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0090 | Udskiftning af HCV-38170 | Montering af ny HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| PRODTECH | 2024-01-04 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0100 | Udskiftning af HCV-38170 | Desafing og leaktest | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027001 | 0110 | Udskiftning af HCV-38170 | Demol af repos og nedtagning af taljer m | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 52.3 | 3 | 52.3 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HV-38170 | HAND VALVE KRAKA FLOW | KRA-OIL | KTI | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0003 | CMAT:Udskiftning af XCV-30664 DFB-02 | Byg stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 40.2 | 3 | 40.2 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2024-01-01 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0007 | CMAT:Udskiftning af XCV-30664 DFB-02 | adskillelse af ZSC/ZSO (ikke elektrisk) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-01 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0009 | CMAT:Udskiftning af XCV-30664 DFB-02 | Rigger assistance | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 1 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2024-01-05 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0010 | CMAT:Udskiftning af XCV-30664 DFB-02 | Udskiftning af XCV-30664 DFB-02 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 1 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2023-12-31 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0060 | CMAT:Udskiftning af XCV-30664 DFB-02 | Test af XCV-30664 incl testsheet | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0070 | CMAT:Udskiftning af XCV-30664 DFB-02 | Rive stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 20.1 | 3 | 20.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2023-12-31 | 2016-07-26 | WDF | 3 | V | 3. Intermediate | 2100027108 | 0065 | DFA-25, XCV 30537 fundet intern læk | Tubing removal/installation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /10/DFAA-XCV-30537 | CHANGE-OVER VALVE TO PRODUCTION MANIFOLD | DFA-OIL | PO ETA 21.12.2016 | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2023-12-31 | 2016-07-26 | WDF | 3 | V | 3. Intermediate | 2100027108 | 0095 | DFA-25, XCV 30537 fundet intern læk | test with ccr and make test sheet | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /10/DFAA-XCV-30537 | CHANGE-OVER VALVE TO PRODUCTION MANIFOLD | DFA-OIL | PO ETA 21.12.2016 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2017-01-12 | WDF | 3 | V | 3. Intermediate | 2100027149 | 0020 | Replacement of DFCM-PDCV-50355 | Udskiftning af DFCM-PDCV-50355 | 2 |  |  | 20 | 2 | 20 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /27/DFCM-PDCV-50355 | PR.DIFF.CONT.VALVE L.P.SEP. HYDROCYCL | DFCLPSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| MTN-RIGG | 2024-01-03 | 2017-01-12 | WDF | 3 | V | 3. Intermediate | 2100027149 | 0025 | Replacement of DFCM-PDCV-50355 | Dismount of rigger equipment | 2 |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /27/DFCM-PDCV-50355 | PR.DIFF.CONT.VALVE L.P.SEP. HYDROCYCL | DFCLPSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| PRODTECH | 2024-01-03 | 2017-01-12 | WDF | 3 | V | 3. Intermediate | 2100027149 | 0030 | Replacement of DFCM-PDCV-50355 | desafing af DFCM-PDCV-50355 | 2 |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /27/DFCM-PDCV-50355 | PR.DIFF.CONT.VALVE L.P.SEP. HYDROCYCL | DFCLPSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| MTN-MECH | 2023-12-31 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100027150 | 0020 | Replacement of DFCM-PDCV-50346 | Udskiftning af DFCM-PDCV-50346 | 2 |  |  | 24 | 2 | 24 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /27/DFCM-PDCV-50346 | LP/HP CYCLONES TO CLOSED DRAIN HEATER | DFCHPSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| PRODTECH | 2024-01-03 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100027150 | 0030 | Replacement of DFCM-PDCV-50346 | Desafing af DFCM-PDCV-50346 | 2 |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /27/DFCM-PDCV-50346 | LP/HP CYCLONES TO CLOSED DRAIN HEATER | DFCHPSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| MTN-MECH | 2023-12-31 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100027151 | 0020 | Replacement of DFCM-PDCV-50335 | Uskiftning af DFCM-PDCV-50335 | 2 |  |  | 24 | 2 | 24 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /27/DFCM-PDCV-50335 | LP/HP CYCLONES TO CLOSED DRAIN HEADER | DFC-TSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| PRODTECH | 2024-01-03 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100027151 | 0030 | Replacement of DFCM-PDCV-50335 | Desafing af DFCM-PDCV-50335 | 2 |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /27/DFCM-PDCV-50335 | LP/HP CYCLONES TO CLOSED DRAIN HEADER | DFC-TSEP | PTW 5-9-17 - RETUR TIL RPJ006 | INLC | MTN-MECH |  | DK0500013123
| MTN-SCAF | 2023-12-31 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0040 | CMAT:Replacement of HCV-380115 | Rigging assistance for removal of the HC | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 2 | 16.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| MTN-PIPF | 2024-01-02 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0050 | CMAT:Replacement of HCV-380115 | Unmounting of the old HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 2 | 16.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| MTN-SCAF | 2024-01-03 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0060 | CMAT:Replacement of HCV-380115 | Rigging assistance for installation of t | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 1 | 16.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| MTN-PIPF | 2024-01-07 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0070 | CMAT:Replacement of HCV-380115 | Mounting of the new HCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16.1 | 1 | 16.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| VEN-ELEC | 2024-01-08 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0080 | CMAT:Replacement of HCV-380115 | Remounting of the hydraulic supply to th | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| MTN-SCAF | 2024-01-09 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0100 | CMAT:Replacement of HCV-380115 | Removal of rigging equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| MTN-LAGG | 2023-12-31 | 2018-04-15 | WDF | 3 |  | 3. Intermediate | 2100027611 | 0050 | ANOP SMATinstall Foamglas potable wat | L3-Install insulation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 33.5 | 2 | 33.5 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /A /85/P-G | PIPING GROUP | NOSD | 2022 | INLC | MTN-ROPE |  | DK0500014763
| MTN-SCAF | 2024-01-02 | 2018-04-15 | WDF | 3 |  | 3. Intermediate | 2100027611 | 0060 | ANOP SMATinstall Foamglas potable wat | L3-Remove scaffolding | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 148.1 | 3 | 167.1 | 19 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /A /85/P-G | PIPING GROUP | NOSD | 2022 | INT | MTN-ROPE |  | DK0500014763
| MTN-SCAF | 2023-12-31 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0025 | CMAT:DFB replacement of dripring at ESDV | L3 Rigging equipment is prepared | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| PRODTECH | 2024-01-01 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0030 | CMAT:DFB replacement of dripring at ESDV | L3 Safing performed by Prod | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-02 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0035 | CMAT:DFB replacement of dripring at ESDV | L3 Rigger assistance | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 19.4 | 1 | 19.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-07 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0040 | CMAT:DFB replacement of dripring at ESDV | L2 Welders changes dripring | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 20.8 | 1 | 20.8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| PRODTECH | 2024-01-09 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0070 | CMAT:DFB replacement of dripring at ESDV | L2 Desafing + leaktest performed by Prod | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-10 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0075 | CMAT:DFB replacement of dripring at ESDV | L3 Removal of rigging equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-11 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0080 | CMAT:DFB replacement of dripring at ESDV | L3 Cleaning | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-11 | 2018-09-06 | WDF | 4 | V | 4. Long | 2100027675 | 0090 | CMAT:DFB replacement of dripring at ESDV | L3 Cleaning | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFC-5705 | TMM | INLC | MTN-PIPF
| MTN-RIGG | 2023-12-31 | 2019-06-25 | WDF | 3 | I | 3. Intermediate | 2100027690 | 0015 | Change DFFA-XCV-500732 | Rigging of DFFA-XCV-500732 | 6 |  | Not able to isolate | 4 | 1 | 4 | 0 | APPR CMAT SCH RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500732 | UNCLASSIFIED VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-06-25 | WDF | 3 | I | 3. Intermediate | 2100027690 | 0020 | Change DFFA-XCV-500732 | Replace DFFA-XCV-500732 | 6 |  | Not able to isolate | 6 | 1 | 6 | 0 | APPR CMAT SCH RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500732 | UNCLASSIFIED VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-ELEC | 2024-01-01 | 2019-06-25 | WDF | 3 | I | 3. Intermediate | 2100027690 | 0030 | Change DFFA-XCV-500732 | Replace DFFA-XCV-500732 | 6 |  | Not able to isolate | 2 | 1 | 2 | 0 | APPR CMAT SCH RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500732 | UNCLASSIFIED VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2019-06-25 | WDF | 3 | I | 3. Intermediate | 2100027690 | 0040 | Change DFFA-XCV-500732 | De-Isolate/test DFFA-XCV-500732 | 6 |  | Not able to isolate | 1 | 1 | 1 | 0 | APPR CMAT SCH RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /27/DFFA-XCV-500732 | UNCLASSIFIED VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0004 | LV 24, DFCI-HCV-03349 Intern læk | Permit Rigger | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 13 | 1 | 13 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-SCAF | 2023-12-31 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0005 | LV 24, DFCI-HCV-03349 Intern læk | Permit Scaff | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 13 | 1 | 13 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-SCAF | 2024-01-03 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0010 | LV 24, DFCI-HCV-03349 Intern læk | Konstruktion af stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 45 | 3 | 45 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2024-01-07 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0015 | LV 24, DFCI-HCV-03349 Intern læk | Opsæt talje | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-PIPF | 2024-01-09 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0030 | LV 24, DFCI-HCV-03349 Intern læk | Udskiftning af ventil | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 24 | 2 | 24 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-PIPF | 2024-01-11 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0050 | LV 24, DFCI-HCV-03349 Intern læk | Leaktest | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2 | 2 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2024-01-11 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0055 | LV 24, DFCI-HCV-03349 Intern læk | Nedtag talje | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 10 | 2 | 10 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-SCAF | 2024-01-12 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0060 | LV 24, DFCI-HCV-03349 Intern læk | Demol af stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 30 | 3 | 30 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| PRODTECH | 2023-12-31 | 2019-01-11 | WDF | 3 | S | 3. Intermediate | 2100027730 | 0010 | SMAT:Replace DFFA-HCV-500729 | L3 Isolation of DFFA-HCV-500729 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-HCV-500729 | HAND CONTROL VALVE | DFFHPSEP | TMM902 | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-01 | 2019-01-11 | WDF | 3 | S | 3. Intermediate | 2100027730 | 0020 | SMAT:Replace DFFA-HCV-500729 | L3 Assist in replacing 18" valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 60.3 | 2 | 60.3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-HCV-500729 | HAND CONTROL VALVE | DFFHPSEP | TMM902 | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-01 | 2019-01-11 | WDF | 3 | S | 3. Intermediate | 2100027730 | 0030 | SMAT:Replace DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 60.3 | 2 | 60.3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-HCV-500729 | HAND CONTROL VALVE | DFFHPSEP | TMM902 | INLC | MTN-PIPF
| PRODTECH | 2024-01-04 | 2019-01-11 | WDF | 3 | S | 3. Intermediate | 2100027730 | 0040 | SMAT:Replace DFFA-HCV-500729 | L3 De-Isolation/test of DFFA-HCV-500729 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-HCV-500729 | HAND CONTROL VALVE | DFFHPSEP | TMM902 | INLC | MTN-PIPF
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0010 | Udskiftning af checkvalve | Construction of a small scaffold by the | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0012 | Udskiftning af checkvalve | Preparation for rigging | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0015 | Udskiftning af checkvalve | Checking of the received materials | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 2 | 2.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| PRODTECH | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0020 | Udskiftning af checkvalve | Safing of the check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2024-01-01 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0030 | Udskiftning af checkvalve | Rigging assistance for the replacement o | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.7 | 1 | 6.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2024-01-01 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0040 | Udskiftning af checkvalve | Replacement of the check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 13.4 | 2 | 13.4 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| PRODTECH | 2024-01-01 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0050 | Udskiftning af checkvalve | Desafing and leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0060 | Udskiftning af checkvalve | Demol of scaffolding | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0070 | Udskiftning af checkvalve | Clean-up | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2023-12-31 | 2016-07-18 | WDF | 3 | V | 3. Intermediate | 2100027948 | 0080 | Udskiftning af checkvalve | Clean-up | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 2 | 1.3 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12 | TRANSFER | KRA-OIL | VALVE ETA 11.09.2016 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2015-02-04 | WDF | 3 | I | 3. Intermediate | 2100027950 | 0060 | @+DFF-05 OIL XCV-301205 intern læk. | Rigging assistance during replacement of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301205 | WELL 5 TO DFG HP PROD. MANIFOLD | DFF-OIL | VALVE ETA 27.02.2017 | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2023-12-31 | 2015-02-04 | WDF | 3 | I | 3. Intermediate | 2100027950 | 0080 | @+DFF-05 OIL XCV-301205 intern læk. | Installation of the new XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301205 | WELL 5 TO DFG HP PROD. MANIFOLD | DFF-OIL | VALVE ETA 27.02.2017 | INLC | MTN-PIPF |  | 99000116
| VEN-ELEC | 2024-01-01 | 2015-02-04 | WDF | 3 | I | 3. Intermediate | 2100027950 | 0090 | @+DFF-05 OIL XCV-301205 intern læk. | Reestablishing hydraulic supply for the | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301205 | WELL 5 TO DFG HP PROD. MANIFOLD | DFF-OIL | VALVE ETA 27.02.2017 | INLC | MTN-PIPF |  | 99000116
| VEN-ELEC | 2024-01-01 | 2015-02-04 | WDF | 3 | I | 3. Intermediate | 2100027950 | 0100 | @+DFF-05 OIL XCV-301205 intern læk. | Reinstalling the positioner for the XCV | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301205 | WELL 5 TO DFG HP PROD. MANIFOLD | DFF-OIL | VALVE ETA 27.02.2017 | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-01 | 2015-02-04 | WDF | 3 | I | 3. Intermediate | 2100027950 | 0110 | @+DFF-05 OIL XCV-301205 intern læk. | Desafing and leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301205 | WELL 5 TO DFG HP PROD. MANIFOLD | DFF-OIL | VALVE ETA 27.02.2017 | INLC | MTN-PIPF |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-08-31 | WDF | 3 | I | 3. Intermediate | 2100028057 | 0020 | Tighten stuffing box FCV-290134 | L3 Tighten stuffing box | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290134 | FLOW CONTROL VALVE -GAS LIFT TO WELL 32 | DFF-O34 | WFDMOD | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-08-31 | WDF | 3 | I | 3. Intermediate | 2100028057 | 0030 | Tighten stuffing box FCV-290134 | L3 Remove isolation & leaktest | 2 |  |  | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290134 | FLOW CONTROL VALVE -GAS LIFT TO WELL 32 | DFF-O34 | WFDMOD | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2020-06-23 | WDF | 3 | S | 3. Intermediate | 2100029105 | 0030 | DFA-03 def. ventil på WI manifold. | Troubleshooting Gearbox | 7 |  |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFAA-HCV-35054 | HAND CONTROL VALVE | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2020-06-23 | WDF | 3 | S | 3. Intermediate | 2100029105 | 0040 | DFA-03 def. ventil på WI manifold. | Prod deisolate w function/leak test | 7 |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFAA-HCV-35054 | HAND CONTROL VALVE | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2020-06-23 | WDF | 3 | S | 3. Intermediate | 2100029105 | 0050 | DFA-03 def. ventil på WI manifold. | Housekeeping | 7 |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFAA-HCV-35054 | HAND CONTROL VALVE | SIWL |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-01 | WDF | 3 | V | 3. Intermediate | 2100029430 | 0025 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3101 | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/DFFA-FP-3101 | WELLHEAD CONTROL PANEL | DFF-W03 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-01 | WDF | 3 | V | 3. Intermediate | 2100029430 | 0030 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3101 | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/DFFA-FP-3101 | WELLHEAD CONTROL PANEL | DFF-W03 |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-01 | WDF | 3 | V | 3. Intermediate | 2100029431 | 0025 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3102 | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/DFFA-FP-3102 | WELLHEAD CONTROL PANEL | DFF-O02 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-01 | WDF | 3 | V | 3. Intermediate | 2100029431 | 0030 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3102 | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/DFFA-FP-3102 | WELLHEAD CONTROL PANEL | DFF-O02 |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-01 | WDF | 3 | V | 3. Intermediate | 2100029433 | 0025 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3103 | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/DFFA-FP-3103 | WELLHEAD CONTROL PANEL | DFF-W03 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-01 | WDF | 3 | V | 3. Intermediate | 2100029433 | 0030 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3103 | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/DFFA-FP-3103 | WELLHEAD CONTROL PANEL | DFF-W03 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2020-11-01 | WDF | 4 | V | 4. Long | 2100029698 | 0020 | HCV 3" Seawater supply sidder fast | Demount valve |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT RREQ | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-V-5010 | DEGASSSING VESSEL | DFF-5010 |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2020-11-01 | WDF | 4 | V | 4. Long | 2100029698 | 0030 | HCV 3" Seawater supply sidder fast | Rig valve in and out |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT RREQ | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-V-5010 | DEGASSSING VESSEL | DFF-5010 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2020-11-01 | WDF | 4 | V | 4. Long | 2100029698 | 0040 | HCV 3" Seawater supply sidder fast | Mount new valve |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT RREQ | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-V-5010 | DEGASSSING VESSEL | DFF-5010 |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2020-11-01 | WDF | 4 | V | 4. Long | 2100029698 | 0050 | HCV 3" Seawater supply sidder fast | De-isolate |  |  |  | 8 | 2 | 8 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT RREQ | APPR OPND | REL MANC PRC SETC | DF /F /27/DFFA-V-5010 | DEGASSSING VESSEL | DFF-5010 |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2023-12-31 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029878 | 0025 | FE03 er internal leak på MCV i hydraulik | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /07/DFEZ-A-3102 | WELLHEAD HYD. PANEL PACKAGE A-3102 | SIWL |  | INLC | VEN-MECH
| PRODTECH | 2024-01-01 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029878 | 0030 | FE03 er internal leak på MCV i hydraulik | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /07/DFEZ-A-3102 | WELLHEAD HYD. PANEL PACKAGE A-3102 | SIWL |  | INLC | VEN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029879 | 0025 | FE07 lækker internt i Master ventil | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /07/DFEZ-A-3102 | WELLHEAD HYD. PANEL PACKAGE A-3102 | SIWL |  | INLC | VEN-MECH
| PRODTECH | 2024-01-01 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029879 | 0030 | FE07 lækker internt i Master ventil | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /07/DFEZ-A-3102 | WELLHEAD HYD. PANEL PACKAGE A-3102 | SIWL |  | INLC | VEN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029881 | 0025 | DFB01 lækker i hydraulk skuffe til MCV | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029881 | 0030 | DFB01 lækker i hydraulk skuffe til MCV | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029882 | 0025 | DFB 09 intern læk i hydraulik skuffe | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-05-02 | WDF | 3 | V | 3. Intermediate | 2100029882 | 0030 | DFB 09 intern læk i hydraulik skuffe | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2020-05-03 | WDF | 3 | V | 3. Intermediate | 2100029886 | 0025 | DFB 05 intern leak på skuffe | Mounting of drawer | 6 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-INST
| PRODTECH | 2024-01-01 | 2020-05-03 | WDF | 3 | V | 3. Intermediate | 2100029886 | 0030 | DFB 05 intern leak på skuffe | Desafing and leaking test | 6 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-INST
| MTN-MECH | 2023-12-31 | 2020-07-29 | WDF | 3 | S | 3. Intermediate | 2100030730 | 0020 | DFBA-HCV-35121 Manifold Valve WI intern | Preparation for valves replacement | 2 |  |  | 3 | 2 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35121 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2020-07-29 | WDF | 3 | S | 3. Intermediate | 2100030730 | 0030 | DFBA-HCV-35121 Manifold Valve WI intern | Isolate DFBA-HCV-35121 | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35121 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2020-07-29 | WDF | 3 | S | 3. Intermediate | 2100030730 | 0040 | DFBA-HCV-35121 Manifold Valve WI intern | Rigging assistance during replacement | 2 |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35121 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2020-07-29 | WDF | 3 | S | 3. Intermediate | 2100030730 | 0050 | DFBA-HCV-35121 Manifold Valve WI intern | Replacement DFBA-HCV-35121 | 2 |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35121 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2020-07-29 | WDF | 3 | S | 3. Intermediate | 2100030730 | 0060 | DFBA-HCV-35121 Manifold Valve WI intern | De-Isolate/test | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35121 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2020-07-29 | WDF | 3 | S | 3. Intermediate | 2100030730 | 0070 | DFBA-HCV-35121 Manifold Valve WI intern | Rigg down | 2 |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-HCV-35121 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0030 | DFG US HCV-440140 intern læk mod pcv | Prod prepare permit/isolation w purging | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0040 | DFG US HCV-440140 intern læk mod pcv | Rigger Assistance | 2 |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0050 | DFG US HCV-440140 intern læk mod pcv | Valve removal | 2 |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0060 | DFG US HCV-440140 intern læk mod pcv | Valve installation | 2 |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0070 | DFG US HCV-440140 intern læk mod pcv | Prod deisolate w function/leak test | 2 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0080 | DFG US HCV-440140 intern læk mod pcv | Housekeeping | 2 |  |  | 4 | 2 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-LAGG | 2024-01-04 | 2021-04-13 | WDF | 4 | S | 4. Long | 2100031501 | 0090 | DFG US HCV-440140 intern læk mod pcv | Lagger assistance | 2 |  |  | 8 | 1 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-HCV-440140 | BALL VALVE ON DFG-12"-GPS-440016-FD | DFG-FUEL |  | INLC | MTN-MECH |  | 99000116
| VEN-INST | 2024-01-01 | 2020-07-04 | WDF | 3 | V | 3. Intermediate | 2100033284 | 0020 | Replace DFCI-BDV-34057 (opens only 15 to | Remove connections DFCI-BDV-34057 | 4 |  |  | 1 | 1 | 1 | 0 | APPR SECE WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /C /20/DFCI-BDV-34057 | HP SEPARATOR, TO FLARE | DFCHPSEP | SECE - MECH | INLC | VEN-MECH | 340664 | 99000116
| VEN-MECH | 2024-01-01 | 2020-07-04 | WDF | 3 | V | 3. Intermediate | 2100033284 | 0030 | Replace DFCI-BDV-34057 (opens only 15 to | Replace DFCI-BDV-34057 | 4 |  |  | 5 | 1 | 5 | 0 | APPR SECE WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /C /20/DFCI-BDV-34057 | HP SEPARATOR, TO FLARE | DFCHPSEP | SECE - MECH | INLC | VEN-MECH | 340664 | 99000116
| VEN-INST | 2024-01-01 | 2020-07-04 | WDF | 3 | V | 3. Intermediate | 2100033284 | 0040 | Replace DFCI-BDV-34057 (opens only 15 to | Connect DFCI-BDV-34057 | 4 |  |  | 1 | 1 | 1 | 0 | APPR SECE WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /C /20/DFCI-BDV-34057 | HP SEPARATOR, TO FLARE | DFCHPSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2020-07-04 | WDF | 3 | V | 3. Intermediate | 2100033284 | 0050 | Replace DFCI-BDV-34057 (opens only 15 to | De-Isolate/Test DFCI-BDV-34057 | 4 |  |  | 5 | 1 | 5 | 0 | APPR SECE WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /C /20/DFCI-BDV-34057 | HP SEPARATOR, TO FLARE | DFCHPSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| MTN-RIGG | 2024-01-06 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0035 | ESDV-330065 - Fail function test | Rigging assisit. rig in/rig out | 4 |  | Single block as depressurizing of test manifold is not possible | 5 | 1 | 5 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-RIGG | 2024-01-07 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0045 | ESDV-330065 - Fail function test | Rigging assisit. rig in/rig out | 4 |  | Single block as depressurizing of test manifold is not possible | 5 | 1 | 5 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| PRODTECH | 2024-01-05 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0080 | ESDV-330065 - Fail function test | De-Isolate ESDV | 4 |  | Single block as depressurizing of test manifold is not possible | 3 | 1 | 3 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-PIPF | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0300 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Weld - Prep. Linewalk | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 16 | 2 | 16 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0310 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Scaff/Rigger Prep. Liewalk | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 5 | 1 | 5 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-LAGG | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0320 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Lagger - Prep. Linewalk | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 5 | 1 | 5 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-09 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0330 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Scaff - build scaffolding inside/outside | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 96 | 6 | 96 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-10 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0340 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Scaff - Built presurized habitat | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 120 | 6 | 120 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-ELEC | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0341 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Move cable tray, heat tracing | DAN-2022-FM-B |  |  | 32 | 2 | 32 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-10 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0350 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Rigger - Hang-up rigging equitment | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 32 | 4 | 32 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| PRODTECH | 2024-01-12 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0360 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Prod - Assist (breaking containment) | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 2 | 1 | 2 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-12 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0370 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Rigger - Rigging old spools down | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 48 | 4 | 48 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-PIPF | 2024-01-12 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0380 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Weld - Demol old spools | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 24 | 3 | 24 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH | 2104484
| MTN-SCAF | 2024-01-15 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0390 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Rigger - Rigging up new 12" spools | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 48 | 4 | 48 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-PIPF | 2024-01-15 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0400 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Weld - Inst.new 12" spools | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 40 | 3 | 40 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH | 2104696 & 2104484
| PRODTECH | 2024-01-17 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0450 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Prod - Desafeing and leaktest of 12" | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-LAGG | 2024-01-18 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0460 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Lagger - Install noise protection on 12" | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 50 | 1 | 50 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-23 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0470 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Scaff - Remove scaffold / Habitat | DAN-2022-FM-B |  | 3520 - 12" ¦10/01/2022 Wrk. Ctr. Migration | 96 | 4 | 96 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| PRODTECH | 2023-12-31 | 2020-11-06 | WDF | 3 | V | 3. Intermediate | 2100038001 | 0402 | DD02 WCV-30540 ZSC-30540 slipper ikke. | Remove inhibit Input device | 2 |  | 14-01 DUCSAT | 2.5 | 1 | 2.5 | 0 | APPR SMAT AWSC | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DA /D /10/DD-WCV-30540 | WING CONTROL VALVE | DAB-OD02 |  | INT | MTN-INST |  | 99000116
| PRODTECH | 2024-01-03 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0030 | XCV-354164 air leakage on actuator | Isolate XCV-354164 | 2 |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INLC | MTN-MECH
| MTN-INST | 2024-01-04 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0040 | XCV-354164 air leakage on actuator | Demoll electric installation | 2 |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-MECH | 2024-01-04 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0060 | XCV-354164 air leakage on actuator | Replace complete XCV-354164 | 2 |  |  | 8 | 2 | 8 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0070 | XCV-354164 air leakage on actuator | Assist in removal | 2 |  |  | 3 | 2 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-INST | 2023-12-31 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0100 | XCV-354164 air leakage on actuator | Functional test of XCV-354164 | 2 |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| PRODTECH | 2023-12-31 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0110 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | 2 |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0120 | XCV-354164 air leakage on actuator | Rig-down hoist | 2 |  |  | 6 | 2 | 6 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0130 | XCV-354164 air leakage on actuator | Rig-down scaffold and clean area | 2 |  |  | 10 | 2 | 10 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0020 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | 2 |  |  | 18 | 3 | 18 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0030 | Replace valves for LT 34002 TEST SEP. | Prod prepare permit/isolation w flushing | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0040 | Replace valves for LT 34002 TEST SEP. | Replace high pressure Vlv | 2 |  |  | 3 | 2 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0050 | Replace valves for LT 34002 TEST SEP. | Replace low pressure Vlv | 2 |  |  | 3 | 2 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-03 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0060 | Replace valves for LT 34002 TEST SEP. | Instrument assistance on LT Calibration | 2 |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0070 | Replace valves for LT 34002 TEST SEP. | Prod prepare permit/isolation w purging | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0080 | Replace valves for LT 34002 TEST SEP. | Housekeeping | 2 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-05 | 2021-01-22 | WDF | 3 | V | 3. Intermediate | 2100038915 | 0090 | Replace valves for LT 34002 TEST SEP. | Scaffold removal | 2 |  |  | 12 | 3 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /11/DFCI-V-3401 | TEST SEPARATOR | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0010 | XCV-33082 intern læk | Scaffold erection |  |  |  | 42 | 3 | 42 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0020 | XCV-33082 intern læk | Prepare Rigging equip. |  |  |  | 24 | 2 | 24 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-06 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0030 | XCV-33082 intern læk | Prepare Permit/Tools/Matr |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-07 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0040 | XCV-33082 intern læk | Prod prepare permit/isolation |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-08 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0050 | XCV-33082 intern læk | Rigger Assistance |  |  |  | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-10 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0060 | XCV-33082 intern læk | Scaffold Asistance |  |  |  | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-12 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0070 | XCV-33082 intern læk | Instrument Assistance |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-13 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0080 | XCV-33082 intern læk | Valve removal |  |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-14 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0090 | XCV-33082 intern læk | Valve installation w torque/bolts |  |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-15 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0100 | XCV-33082 intern læk | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-16 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0110 | XCV-33082 intern læk | Housekeeping |  |  |  | 4 | 2 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-16 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0120 | XCV-33082 intern læk | Riggging equip removal |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-17 | 2021-09-27 | WDF | 4 | V | 4. Long | 2100039360 | 0130 | XCV-33082 intern læk | Scaffold removal |  |  |  | 24 | 3 | 24 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /12/DFCM-XCV-33082 | HP SEP. MANIF.VALVE FROM FA PROD HEADER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0010 | DFG-HCV-440412B not able to close | Scaffold erection | 7 |  |  | 21 | 3 | 21 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0030 | DFG-HCV-440412B not able to close | Prod prepare permit/isolation |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0040 | DFG-HCV-440412B not able to close | Replace 2" DBB Vlv |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| MTN-INST | 2024-01-04 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0050 | DFG-HCV-440412B not able to close | Transmitter 440412 calibration |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-05 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0060 | DFG-HCV-440412B not able to close | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0070 | DFG-HCV-440412B not able to close | Housekeeping/backload old Vlv |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| MTN-SCAF | 2024-01-06 | 2021-06-23 | WDF | 4 | S | 4. Long | 2100040410 | 0080 | DFG-HCV-440412B not able to close | Scaffold removal |  |  |  | 15 | 3 | 15 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /32/DFGA-HCV-440412B-I | HAND CONTROL VALVE | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0120 | ESDV-38169 failing inflow test DGS 63863 | Isolate ESDV-38169 |  |  |  | 15 | 1 | 15 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0130 | ESDV-38169 failing inflow test DGS 63863 | Isolate Hydralic and controls |  |  |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-06 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0139 | ESDV-38169 failing inflow test DGS 63863 | Rigging assist. Rig in/out |  |  |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-07 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0140 | ESDV-38169 failing inflow test DGS 63863 | Demount Actuator |  |  |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-08 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0150 | ESDV-38169 failing inflow test DGS 63863 | Rigging assist. Rig in/out |  |  |  | 8 | 1 | 8 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-10 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0160 | ESDV-38169 failing inflow test DGS 63863 | Remove Valve Bonnet |  |  |  | 8 | 1 | 8 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-11 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0161 | ESDV-38169 failing inflow test DGS 63863 | Remove Valve Bonnet |  |  |  | 8 | 1 | 8 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-13 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0168 | ESDV-38169 failing inflow test DGS 63863 | Rigging assist. Rig in/out |  |  |  | 12 | 1 | 12 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-16 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0169 | ESDV-38169 failing inflow test DGS 63863 | Remove Ball and seats |  |  |  | 12 | 1 | 12 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-19 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0170 | ESDV-38169 failing inflow test DGS 63863 | Remove Ball and seats |  |  |  | 12 | 1 | 12 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-20 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0179 | ESDV-38169 failing inflow test DGS 63863 | Rigging assist. Rig in/out |  |  |  | 12 | 1 | 12 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-23 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0180 | ESDV-38169 failing inflow test DGS 63863 | Mount new seats and ball |  |  |  | 12 | 1 | 12 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-26 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0181 | ESDV-38169 failing inflow test DGS 63863 | Mount new seats and ball |  |  |  | 12 | 1 | 12 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-27 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0189 | ESDV-38169 failing inflow test DGS 63863 | Rigging assist. Rig in/out |  |  |  | 6 | 1 | 6 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-29 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0190 | ESDV-38169 failing inflow test DGS 63863 | Mount Valve bonnet |  |  |  | 6 | 1 | 6 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-29 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0191 | ESDV-38169 failing inflow test DGS 63863 | Mount Valve bonnet |  |  |  | 6 | 1 | 6 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-31 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0199 | ESDV-38169 failing inflow test DGS 63863 | Rigging assist. Rig in/out |  |  |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-02-01 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0200 | ESDV-38169 failing inflow test DGS 63863 | Mount Actuator |  |  |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-02-02 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0210 | ESDV-38169 failing inflow test DGS 63863 | De Isolate Hydralic and controls |  |  |  | 2 | 1 | 2 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-02-02 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0220 | ESDV-38169 failing inflow test DGS 63863 | Functional test ESDV-38169 |  |  |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-02-03 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0230 | ESDV-38169 failing inflow test DGS 63863 | De Isolate ESDV-38169 |  |  |  | 5 | 1 | 5 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | INIT OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| MTN-INST | 2023-12-31 | 2020-10-13 | WDF | 3 | V | 3. Intermediate | 2100041605 | 0070 | DFF - XCV-354127 air leakage on actuator | Re-install electric installation | 2 |  |  | 0 | 1 | 3 | 8 | APPR SMAT AWSC RDBL | APPR OPND | REL PCNF CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354127 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-INST | 2023-12-31 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0030 | DFA mess dæk proces. XCV-33196 defekt | Isolate hydraulic and controls |  |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0040 | DFA mess dæk proces. XCV-33196 defekt | Rigging assist. Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0050 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator |  |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0060 | DFA mess dæk proces. XCV-33196 defekt | Rigging assist. Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0070 | DFA mess dæk proces. XCV-33196 defekt | Mount new Actuator |  |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-04 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0080 | DFA mess dæk proces. XCV-33196 defekt | Re-build tubing if any |  |  |  | 4 | 1 | 4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-05 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0090 | DFA mess dæk proces. XCV-33196 defekt | Connect Controls and hydraulic |  |  |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-06 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0100 | DFA mess dæk proces. XCV-33196 defekt | Functional test |  |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0110 | DFA mess dæk proces. XCV-33196 defekt | Deisolate XCV |  |  |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-07 | 2021-01-25 | WDF | 3 | V | 3. Intermediate | 2100042149 | 0120 | DFA mess dæk proces. XCV-33196 defekt | Housekeeping |  |  |  | 4 | 1 | 4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /12/DFAA-XCV-33196 | 16" 300# RF PRODUCTION MANIFOLD | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0010 | ESD Isolation Vlv DFF-LIT-340038 Interna | Prepare Permit/Tools/Matr | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2 | 1 | 2 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0020 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 16 | 2 | 16 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0030 | ESD Isolation Vlv DFF-LIT-340038 Interna | Insulation removal | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2 | 1 | 2 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INT | MTN-MECH
| PRODTECH | 2024-01-03 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0040 | ESD Isolation Vlv DFF-LIT-340038 Interna | Prod prepare permit/isolation w flushing | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0050 | ESD Isolation Vlv DFF-LIT-340038 Interna | Replace 2" Valve | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 2 | 6 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0060 | ESD Isolation Vlv DFF-LIT-340038 Interna | Prod deisolate w function/leak test | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-LAGG | 2024-01-05 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0070 | ESD Isolation Vlv DFF-LIT-340038 Interna | Rectify Insulation | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-SCAF | 2024-01-06 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0080 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold removal | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042479 | 0090 | ESD Isolation Vlv DFF-LIT-340038 Interna | Housekeeping | 6 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1 | 1 | 1 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER MANC PRC SETC | DF /F /20/DFFA-LIT-340038 | DISP. LEVEL INDICATOR TRANSMITTER (ESD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0020 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | 2 |  |  | 16 | 2 | 16 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| VEN-MECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0030 | ESD Afspæringsventil DFF-LIT-340102 | Insulation removal | 2 |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0040 | ESD Afspæringsventil DFF-LIT-340102 | Prod prepare permit/isolation w flushing | 2 |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| VEN-MECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0050 | ESD Afspæringsventil DFF-LIT-340102 | Replace 2" Valve | 2 |  |  | 6 | 2 | 6 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0060 | ESD Afspæringsventil DFF-LIT-340102 | Prod deisolate w function/leak test | 2 |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| MTN-SCAF | 2024-01-04 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0080 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold removal | 2 |  |  | 12 | 2 | 12 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0020 | ESD Afspæringsventil DFF-LIT-340108 | Scaffold Work PF erection | 2 |  |  | 16 | 2 | 16 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| VEN-MECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0030 | ESD Afspæringsventil DFF-LIT-340108 | Insulation removal | 6 |  |  | 2 | 1 | 2 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0040 | ESD Afspæringsventil DFF-LIT-340108 | Prod prepare permit/isolation w flushing | 6 |  |  | 3 | 1 | 3 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| VEN-MECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0050 | ESD Afspæringsventil DFF-LIT-340108 | Replace 2" Valve | 6 |  |  | 6 | 2 | 6 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0060 | ESD Afspæringsventil DFF-LIT-340108 | Prod deisolate w function/leak test | 6 |  |  | 3 | 1 | 3 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| MTN-ROPE | 2024-01-03 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0070 | ESD Afspæringsventil DFF-LIT-340108 | Rectify Insulation |  |  |  | 6 | 1 | 6 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| MTN-SCAF | 2024-01-04 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042481 | 0080 | ESD Afspæringsventil DFF-LIT-340108 | Scaffold removal | 6 |  |  | 12 | 2 | 12 | 0 | APPR APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PPRT PRC SETC | DF /F /20/DFFA-LIT-340108 | LEVEL DP INDICATOR TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0011 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Build / unbuild Scaffolding. | 2 |  |  | 64 | 3 | 64 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| PRODTECH | 2024-01-01 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0030 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Isolate ESDV Hydralic | 2 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INLC | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0040 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Disconnect Controls and switches. | 2 |  |  | 12 | 1 | 12 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0041 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Fireguard | 2 |  |  | 35 | 1 | 35 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0050 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Rigging assisit. rig in/rig out | 2 |  |  | 16 | 2 | 16 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0070 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Rigging assisit. rig in/rig out | 2 |  |  | 16 | 2 | 16 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0090 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Connect controls and switches | 2 |  |  | 16 | 1 | 16 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0120 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Build / unbuild Scaffolding | 2 |  |  | 52 | 3 | 52 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0150 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Prep.for sandblasting of valve top. | 2 |  |  | 16 | 2 | 16 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0170 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Re-paint of valve | 2 |  |  | 12 | 1 | 12 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-ROPE | 2023-12-31 | 2020-12-24 | WDF | 4 | V | 4. Long | 2100043575 | 0180 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Final houskeeping | 2 |  |  | 12 | 1 | 12 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL CSER GMPS MANC PPRT PRC SETC | DF /G /34/DFGA-ESDV-380131 | WET GAS FROM HBB TO EP-3813 | DFG20MPH |  | INT | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0020 | Intern lækage på ventil HCV-380229 | Rigger preparation |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0030 | Intern lækage på ventil HCV-380229 | Rigging new valve to/on site |  |  |  | 10 | 2 | 10 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0040 | Intern lækage på ventil HCV-380229 | Prod prepare permit/isolation w flushing |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-03 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0050 | Intern lækage på ventil HCV-380229 | Rigging assistance |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0060 | Intern lækage på ventil HCV-380229 | Removal of old HCV-380229 |  |  |  | 3 | 2 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0070 | Intern lækage på ventil HCV-380229 | Install new HCV-380229 |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0080 | Intern lækage på ventil HCV-380229 | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0090 | Intern lækage på ventil HCV-380229 | Rigging old HCV Vlv from site to deck |  |  |  | 10 | 2 | 10 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-06 | 2021-05-11 | WDF | 3 | S | 3. Intermediate | 2100044421 | 0110 | Intern lækage på ventil HCV-380229 | Rigging equipment removal |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /23/DFFA-HCV-380229 | HAND CONTROL VALVE | DAB-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-30 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0010 | DFG PCV-570437A Dårlig integritet | Prepare Permit/Tools/Matr-fabrication | ID 70 |  | PRE | 12 | 1 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0020 | DFG PCV-570437A Dårlig integritet | Isolate PCV | ID 70 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-INST | 2024-01-02 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0030 | DFG PCV-570437A Dårlig integritet | Isolate pneumatic and controls | ID 70 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-03 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0040 | DFG PCV-570437A Dårlig integritet | Rigging assist. Rig in/out | ID 70 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0050 | DFG PCV-570437A Dårlig integritet | Demount Actuator | ID 70 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-04 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0060 | DFG PCV-570437A Dårlig integritet | Rigging assist. Rig in/out | ID 70 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-INST | 2024-01-06 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0080 | DFG PCV-570437A Dårlig integritet | Re-build tubing if any | ID 70 |  |  | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-INST | 2024-01-07 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0090 | DFG PCV-570437A Dårlig integritet | Connect Controls and pneumatic | ID 70 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-08 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0100 | DFG PCV-570437A Dårlig integritet | Callibration Positioner/functional test | ID 70 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-09 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0110 | DFG PCV-570437A Dårlig integritet | Deisolate PCV | ID 70 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-09 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0120 | DFG PCV-570437A Dårlig integritet | Housekeeping | ID 70 |  | POST | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2021-09-24 | WDF | 4 | S | 4. Long | 2100045353 | 0010 | Deluge HCV-030042 internal leak | Bulit scaffold repo |  |  |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /01/DFAA-HCV-030042 | LO - HAND CONTROL VALVE | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-09-24 | WDF | 4 | S | 4. Long | 2100045353 | 0020 | Deluge HCV-030042 internal leak | Isolate up & downstream HCV-030042 |  |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /01/DFAA-HCV-030042 | LO - HAND CONTROL VALVE | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-09-24 | WDF | 4 | S | 4. Long | 2100045353 | 0030 | Deluge HCV-030042 internal leak | Replace HCV-030042 |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /01/DFAA-HCV-030042 | LO - HAND CONTROL VALVE | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2021-09-24 | WDF | 4 | S | 4. Long | 2100045353 | 0040 | Deluge HCV-030042 internal leak | Assist MECH with rigging/instal of valve |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /01/DFAA-HCV-030042 | LO - HAND CONTROL VALVE | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-09-24 | WDF | 4 | S | 4. Long | 2100045353 | 0050 | Deluge HCV-030042 internal leak | Deisolate HCV-030042 and check for leaks |  |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /01/DFAA-HCV-030042 | LO - HAND CONTROL VALVE | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-09-24 | WDF | 4 | S | 4. Long | 2100045353 | 0060 | Deluge HCV-030042 internal leak | Remove scaffolding |  |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /01/DFAA-HCV-030042 | LO - HAND CONTROL VALVE | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2021-09-25 | WDF | 4 | S | 4. Long | 2100045354 | 0020 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. |  |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03017 | HAND CONTROL VALVE DELUGE SKID | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-09-25 | WDF | 4 | S | 4. Long | 2100045354 | 0030 | HCV-03017 internal leak us XCV-0328 Delu | Prod prepare permit/isolation |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03017 | HAND CONTROL VALVE DELUGE SKID | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-09-25 | WDF | 4 | S | 4. Long | 2100045354 | 0050 | HCV-03017 internal leak us XCV-0328 Delu | Replace 10" Butterfly valve |  |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03017 | HAND CONTROL VALVE DELUGE SKID | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-09-25 | WDF | 4 | S | 4. Long | 2100045354 | 0060 | HCV-03017 internal leak us XCV-0328 Delu | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03017 | HAND CONTROL VALVE DELUGE SKID | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-09-25 | WDF | 4 | S | 4. Long | 2100045354 | 0070 | HCV-03017 internal leak us XCV-0328 Delu | Housekeeping |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSD AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03017 | HAND CONTROL VALVE DELUGE SKID | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0020 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0025 | Both DFF-14 manifold Vlv's internal leak | Scaffold Step-up work PF + hard barrier |  |  |  | 18 | 3 | 18 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0030 | Both DFF-14 manifold Vlv's internal leak | Prod isolation/permit |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0040 | Both DFF-14 manifold Vlv's internal leak | Rigger assistance |  |  |  | 16 | 2 | 16 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0050 | Both DFF-14 manifold Vlv's internal leak | Valve removal |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0060 | Both DFF-14 manifold Vlv's internal leak | Valve installation w torqing |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0070 | Both DFF-14 manifold Vlv's internal leak | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0080 | Both DFF-14 manifold Vlv's internal leak | Housekeeping |  |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-05 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0090 | Both DFF-14 manifold Vlv's internal leak | Rigging equip removal |  |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-06 | 2022-02-14 | WDF | 4 | V | 4. Long | 2100046329 | 0100 | Both DFF-14 manifold Vlv's internal leak | Scaffold removal |  |  |  | 12 | 3 | 12 | 0 | APPR PMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF14-WATER-INJECTION | DFF14 WATER INJECTION | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0010 | 12" WIJ Vlv replacement DFB Topdeck | Rectify scaffold work PF |  |  |  | 32 | 4 | 32 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0020 | 12" WIJ Vlv replacement DFB Topdeck | Prepare lifting equipment |  |  |  | 10 | 2 | 10 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0030 | 12" WIJ Vlv replacement DFB Topdeck | Prepare Permit/Tools/Matr |  |  |  | 4 | 2 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0040 | 12" WIJ Vlv replacement DFB Topdeck | Prod isolation/permit |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-04 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0050 | 12" WIJ Vlv replacement DFB Topdeck | Rigger assistance |  |  |  | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-ROUS | 2024-01-06 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0055 | 12" WIJ Vlv replacement DFB Topdeck | Crane assistance |  |  |  | 8 | 2 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-07 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0060 | 12" WIJ Vlv replacement DFB Topdeck | 12" Spool removal |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-08 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0070 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv removal |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-09 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0080 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-09 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0090 | 12" WIJ Vlv replacement DFB Topdeck | 12" Spool installation w torquing |  |  |  | 4 | 2 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-10 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0100 | 12" WIJ Vlv replacement DFB Topdeck | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-11 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0110 | 12" WIJ Vlv replacement DFB Topdeck | Housekeeping |  |  |  | 2 | 2 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-11 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0120 | 12" WIJ Vlv replacement DFB Topdeck | Rigging equipment removal |  |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-12 | 2021-06-22 | WDF | 3 |  | 3. Intermediate | 2100046479 | 0130 | 12" WIJ Vlv replacement DFB Topdeck | Scaffold removal |  |  |  | 20 | 4 | 20 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /54/SYSTEM-54-MANUAL-VALVES | SYSTEM 54 MANUAL VALVES | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0010 | DFF HCV-030119 Intern leaking | Build N2 proection Boundary |  |  |  | 18 | 3 | 18 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0020 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0030 | DFF HCV-030119 Intern leaking | Prepare Permit/Tools/Matr |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0040 | DFF HCV-030119 Intern leaking | Production isolation/assistance |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0050 | DFF HCV-030119 Intern leaking | Carry out freezing job |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0060 | DFF HCV-030119 Intern leaking | Replace HCV 030119 |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0070 | DFF HCV-030119 Intern leaking | Removal of freezing kit |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0080 | DFF HCV-030119 Intern leaking | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0090 | DFF HCV-030119 Intern leaking | Removal of freezing kit from site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0100 | DFF HCV-030119 Intern leaking | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047712 | 0110 | DFF HCV-030119 Intern leaking | Protection Boundary removal |  |  |  | 12 | 3 | 12 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030119 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0010 | DFF-HCV-030120 internly leaking | Build N2 proection Boundary |  |  |  | 18 | 3 | 18 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0020 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0030 | DFF-HCV-030120 internly leaking | Prepare Permit/Tools/Matr |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0040 | DFF-HCV-030120 internly leaking | Production isolation/assistance |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0050 | DFF-HCV-030120 internly leaking | Carry out freezing job |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0060 | DFF-HCV-030120 internly leaking | Replace HCV 030120 |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0070 | DFF-HCV-030120 internly leaking | Removal of freezing kit |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0080 | DFF-HCV-030120 internly leaking | Production isolation/assistance |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0090 | DFF-HCV-030120 internly leaking | Removal of freezing kit from site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0100 | DFF-HCV-030120 internly leaking | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-05 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047713 | 0110 | DFF-HCV-030120 internly leaking | Protection Boundary removal |  |  |  | 12 | 3 | 12 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030120 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0010 | DFF-HCV-030121 internly leaking | Build N2 proection Boundary |  |  |  | 18 | 3 | 18 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0020 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0030 | DFF-HCV-030121 internly leaking | Prepare Permit/Tools/Matr |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0040 | DFF-HCV-030121 internly leaking | Production isolation/assistance |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0050 | DFF-HCV-030121 internly leaking | Carry out freezing job |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0060 | DFF-HCV-030121 internly leaking | Replace HCV 030121 |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0070 | DFF-HCV-030121 internly leaking | Removal of freezing kit |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0080 | DFF-HCV-030121 internly leaking | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0090 | DFF-HCV-030121 internly leaking | Removal of freezing kit from site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0100 | DFF-HCV-030121 internly leaking | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-05 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047714 | 0110 | DFF-HCV-030121 internly leaking | Protection Boundary removal |  |  |  | 12 | 3 | 12 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030121 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-10 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0010 | dff-hcv-030122 internly leaking | Build N2 proection Boundary |  |  |  | 18 | 3 | 18 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-11 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0020 | dff-hcv-030122 internly leaking | Prepare freezing kit on site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-11 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0030 | dff-hcv-030122 internly leaking | Prepare Permit/Tools/Matr |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-12 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0040 | dff-hcv-030122 internly leaking | Production isolation/assistance |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-12 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0050 | dff-hcv-030122 internly leaking | Carry out freezing job |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-13 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0060 | dff-hcv-030122 internly leaking | Replace HCV 030122 |  |  |  | 2 | 2 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-13 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0070 | dff-hcv-030122 internly leaking | Removal of freezing kit |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-13 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0080 | dff-hcv-030122 internly leaking | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-14 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0090 | dff-hcv-030122 internly leaking | Removal of freezing kit from site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-14 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0100 | dff-hcv-030122 internly leaking | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-14 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047715 | 0110 | dff-hcv-030122 internly leaking | Protection Boundary removal |  |  |  | 12 | 3 | 12 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030122 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0010 | DFF HCV-030169 internly leaking | Build N2 proection Boundary |  |  |  | 18 | 3 | 18 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0020 | DFF HCV-030169 internly leaking | Prepare freezing kit on site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0030 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0040 | DFF HCV-030169 internly leaking | Production isolation/assistance |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-02 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0050 | DFF HCV-030169 internly leaking | Carry out freezing job |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0060 | DFF HCV-030169 internly leaking | Replace HCV 030169 |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0070 | DFF HCV-030169 internly leaking | Removal of freezing kit |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0080 | DFF HCV-030169 internly leaking | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0090 | DFF HCV-030169 internly leaking | Removal of freezing kit from site |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0100 | DFF HCV-030169 internly leaking | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-05 | 2021-07-16 | WDF | 3 | S | 3. Intermediate | 2100047716 | 0110 | DFF HCV-030169 internly leaking | Protection Boundary removal |  |  |  | 12 | 3 | 12 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-030169 | LO - HAND CONTROL VALVE | DAN-FRYS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0010 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold | 5 |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0020 | DFB-1"HCV system 35 WI ext. leak | Isolate HCV | 5 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0030 | DFB-1"HCV system 35 WI ext. leak | Remove old Valve | 5 |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0040 | DFB-1"HCV system 35 WI ext. leak | Install new Valve | 5 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0050 | DFB-1"HCV system 35 WI ext. leak | De-isolate XCV | 5 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0060 | DFB-1"HCV system 35 WI ext. leak | Housekeeping | 5 |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2021-08-04 | WDF | 3 | V | 3. Intermediate | 2100048512 | 0070 | DFB-1"HCV system 35 WI ext. leak | Scaffold removal | 5 |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-ESDV-35790 | ESDV FOR WATER INJECTION | DAN-WI |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0010 | HCV-380337+bypass Vlv internal leaking | Scaffold Erection work platform | 2 |  |  | 48 | 4 | 48 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-03 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0020 | HCV-380337+bypass Vlv internal leaking | Rigger prepareness | 2 |  |  | 24 | 2 | 24 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-07 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0030 | HCV-380337+bypass Vlv internal leaking | Prepare permit/tools/matr | 2 |  |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-ROPE | 2024-01-06 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0035 | HCV-380337+bypass Vlv internal leaking | Lagger Assistance/insulation removal | 2 |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INT | MTN-MECH
| PRODTECH | 2024-01-07 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0040 | HCV-380337+bypass Vlv internal leaking | Prod prepare permit/isolations | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-08 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0050 | HCV-380337+bypass Vlv internal leaking | Rigger Assistance | 2 |  |  | 24 | 2 | 24 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-11 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0060 | HCV-380337+bypass Vlv internal leaking | HCV-380338 removal | 2 |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-12 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0070 | HCV-380337+bypass Vlv internal leaking | New HCV-380338 installation w torquing | 2 |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-13 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0080 | HCV-380337+bypass Vlv internal leaking | Bypass Vlv removal | 2 |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-14 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0090 | HCV-380337+bypass Vlv internal leaking | New Bypass Vlv installation w torquing | 2 |  |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| PRODTECH | 2024-01-14 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0100 | HCV-380337+bypass Vlv internal leaking | Prod deisolate w function/leak test | 2 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-15 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0110 | HCV-380337+bypass Vlv internal leaking | Housekeeping | 2 |  |  | 2 | 2 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-15 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0120 | HCV-380337+bypass Vlv internal leaking | Rigger equipment removal | 2 |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-ROPE | 2024-01-15 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0125 | HCV-380337+bypass Vlv internal leaking | Reinstate insulation | 2 |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| MTN-SCAF | 2024-01-16 | 2021-08-31 | WDF | 3 | S | 3. Intermediate | 2100049758 | 0130 | HCV-380337+bypass Vlv internal leaking | Scaffold removal | 2 |  |  | 36 | 4 | 36 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /34/DFFA-HCV-380338 | HAND CONTROL VALVE | DHDLPGAS |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-05-12 | WDF | 4 | V | 4. Long | 2100050704 | 0020 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2022-05-12 | WDF | 4 | V | 4. Long | 2100050704 | 0030 | Replace Corroded Valve WI Manifold DFF | Old Vlv removal |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2022-05-12 | WDF | 4 | V | 4. Long | 2100050704 | 0040 | Replace Corroded Valve WI Manifold DFF | New Vlv installation w torquing |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2022-05-12 | WDF | 4 | V | 4. Long | 2100050704 | 0050 | Replace Corroded Valve WI Manifold DFF | Prod deisolate w function/leak test |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2022-05-12 | WDF | 4 | V | 4. Long | 2100050704 | 0060 | Replace Corroded Valve WI Manifold DFF | Housekeeping |  |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2023-12-31 | 2021-09-25 | WDF | 3 | V | 3. Intermediate | 2100050783 | 0030 | Small oil leaks form emg. engine | Investigation of the leaks | 2 |  |  | 8 | 2 | 8 | 0 | APPR AWSC | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /05/DFCI-ESDG-1701 | EMERGENCY GENERATOR PACKAGE G-1701 | DFC-1701 |  | INLC | MTN-TURB
| MTN-ROPE | 2023-12-31 | 2021-08-06 | WDF | 3 |  | 3. Intermediate | 2100051102 | 0030 | ANOP Leak on line DFF-4"-WF-037015-AN P | ISOLATE-HT, REMO-INSU, INSPECT ALL | 6 |  |  | 12 | 3 | 12 | 0 | WREA WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /01/DFF-4-WF-003-7015-AN-T | 4 FIREWATER LINE | NOSD | 2022 FIRE WATER REP CLOSE ? | INLC | MTN-ROPE |  | 99000087
| MTN-ROPE | 2024-01-01 | 2021-08-06 | WDF | 3 |  | 3. Intermediate | 2100051102 | 0040 | ANOP Leak on line DFF-4"-WF-037015-AN P | CLEAN-OFF, WRAP | 2 |  |  | 6 | 3 | 6 | 0 | WREA WMAT AWDO AWSC RDBL RFRZ ROUT | WREA OPND | REL MANC PRC SETC | DF /F /01/DFF-4-WF-003-7015-AN-T | 4 FIREWATER LINE | NOSD | 2022 FIRE WATER REP CLOSE ? | INLC | MTN-ROPE |  | 99000087
| MTN-ROPE | 2024-01-02 | 2021-08-06 | WDF | 3 |  | 3. Intermediate | 2100051102 | 0050 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | 2 |  |  | 12 | 3 | 12 | 0 | WREA WMAT AWDO AWSC RDBL RFRZ ROUT | WREA OPND | REL MANC PRC SETC | DF /F /01/DFF-4-WF-003-7015-AN-T | 4 FIREWATER LINE | NOSD | 2022 FIRE WATER REP CLOSE ? | INLC | MTN-ROPE |  | 99000087
| MTN-ROPE | 2024-01-03 | 2021-08-06 | WDF | 3 |  | 3. Intermediate | 2100051102 | 0060 | ANOP Leak on line DFF-4"-WF-037015-AN P | ASSEMBLE-HT+TEST + REINSULATE | 2 |  |  | 12 | 3 | 12 | 0 | WREA WMAT AWDO AWSC RDBL RFRZ ROUT | WREA OPND | REL MANC PRC SETC | DF /F /01/DFF-4-WF-003-7015-AN-T | 4 FIREWATER LINE | NOSD | 2022 FIRE WATER REP CLOSE ? | INLC | MTN-ROPE |  | 99000087
| MTN-ROPE | 2024-01-04 | 2021-08-06 | WDF | 3 |  | 3. Intermediate | 2100051102 | 0070 | ANOP Leak on line DFF-4"-WF-037015-AN P | CLEAN-UP+COLOR-COTE+BACKLOAD | 2 |  |  | 3 | 3 | 3 | 0 | WREA WMAT AWDO AWSC RDBL RFRZ ROUT | WREA OPND | REL MANC PRC SETC | DF /F /01/DFF-4-WF-003-7015-AN-T | 4 FIREWATER LINE | NOSD | 2022 FIRE WATER REP CLOSE ? | INLC | MTN-ROPE |  | 99000087
| MTN-RIGG | 2024-01-01 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0030 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0040 | BDV-33010 DFE Prod.åbner ikke helt. | Demount old BDV |  |  |  | 3 | 1 | 3 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0050 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out |  |  |  | 4 | 1 | 4 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0060 | BDV-33010 DFE Prod.åbner ikke helt. | Mount new BDV |  |  |  | 4 | 1 | 4 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-05 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0070 | BDV-33010 DFE Prod.åbner ikke helt. | Rebuild tubing if necsessary |  |  |  | 2 | 1 | 2 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-05 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0080 | BDV-33010 DFE Prod.åbner ikke helt. | Deisolate Hydraulic and controls |  |  |  | 2 | 1 | 2 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-06 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0090 | BDV-33010 DFE Prod.åbner ikke helt. | Functional test |  |  |  | 2 | 1 | 2 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0100 | BDV-33010 DFE Prod.åbner ikke helt. | Deisolate BDV |  |  |  | 2 | 1 | 2 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-07 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0110 | BDV-33010 DFE Prod.åbner ikke helt. | Housekeeping |  |  |  | 3 | 1 | 3 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0040 | (DFB16)XCV-30410 & 30401 intern leaking | Rigging assist. Rig in/out |  |  |  | 8 | 1 | 8 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0050 | (DFB16)XCV-30410 & 30401 intern leaking | Demount XCV-30401 |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0060 | (DFB16)XCV-30410 & 30401 intern leaking | Mount new XCV-30401 |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0070 | (DFB16)XCV-30410 & 30401 intern leaking | Re-build tubing if nescassary |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-06 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0080 | (DFB16)XCV-30410 & 30401 intern leaking | Re-connect Controls/Switches |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0090 | (DFB16)XCV-30410 & 30401 intern leaking | Deisolate Hydraulic |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-07 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0110 | (DFB16)XCV-30410 & 30401 intern leaking | Housekeeping |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0130 | (DFB16)XCV-30410 & 30401 intern leaking | Isolate XCV-30410 |  |  |  | 5 | 1 | 5 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0140 | (DFB16)XCV-30410 & 30401 intern leaking | Isolate Hydraulic |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-01 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0150 | (DFB16)XCV-30410 & 30401 intern leaking | Demount Controls/Switches |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0160 | (DFB16)XCV-30410 & 30401 intern leaking | Rigging assist. Rig in/out |  |  |  | 8 | 1 | 8 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0170 | (DFB16)XCV-30410 & 30401 intern leaking | Demount XCV-30410 |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0180 | (DFB16)XCV-30410 & 30401 intern leaking | Mount new XCV-30410 |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-06 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0190 | (DFB16)XCV-30410 & 30401 intern leaking | Re-build tubing if nescassary |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-07 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0200 | (DFB16)XCV-30410 & 30401 intern leaking | Re-connect Controls/Switches |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-07 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0220 | (DFB16)XCV-30410 & 30401 intern leaking | Functional test |  |  |  | 1 | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-08 | 2021-09-06 | WDF | 3 | V | 3. Intermediate | 2100052620 | 0230 | (DFB16)XCV-30410 & 30401 intern leaking | Housekeeping |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-XCV-30410 | CHANGE-OVER WELL 16-TEST MANIF. XCV II | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2023-12-31 | 2021-11-20 | WDF | 3 | V | 3. Intermediate | 2100053134 | 0030 | intern leak in Block PT-30040 | Install new manifold | 6 |  |  | 6 | 1 | 6 | 0 | APPR SMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /10/DFEZ-PT-30040 | PRESSURE TRANSMITTER (PT-VII) (ESD) | DFE-O04 | SECE-CLJ003 | INLC | MTN-INST |  | 99000116
| MTN-MECH | 2024-01-01 | 2022-11-26 | WDF | 4 | S | 4. Long | 2100053493 | 0010 | Nozzle flange sealing face corro (HOLD) | Nozzle flange sealing face corrosion |  |  |  | 1 | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL NMAT PRC SETC | DF /C /51/DFCM-FT-5231 | COOLING WATER MEDIUM - SEAWATER FILTER | NOSD |  | INLC | VEN-MECH
| VEN-INST | 2024-01-01 | 2022-03-27 | WDF | 4 | V | 4. Long | 2100053641 | 0030 | Replace hydrau. tubing on DFA-A-3102A | Replace pipping |  |  |  | 12 | 1 | 12 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102A | WELLHEAD CONTROL PANEL 6 WELL EXTENTION | DFA-W13 | SECE TEAM | INLC | VEN-INST |  | 99000116
| PRODTECH | 2024-01-02 | 2022-03-27 | WDF | 4 | V | 4. Long | 2100053641 | 0040 | Replace hydrau. tubing on DFA-A-3102A | De-isolate |  |  |  | 1 | 2 | 1 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102A | WELLHEAD CONTROL PANEL 6 WELL EXTENTION | DFA-W13 | SECE TEAM | INLC | VEN-INST |  | 99000116
| VEN-INST | 2024-01-02 | 2022-03-27 | WDF | 4 | V | 4. Long | 2100053641 | 0050 | Replace hydrau. tubing on DFA-A-3102A | Test |  |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102A | WELLHEAD CONTROL PANEL 6 WELL EXTENTION | DFA-W13 | SECE TEAM | INLC | VEN-INST |  | 99000116
| MTN-SCAF | 2024-01-02 | 2022-03-27 | WDF | 4 | V | 4. Long | 2100053641 | 0080 | Replace hydrau. tubing on DFA-A-3102A | Remove scaffold |  |  |  | 6 | 2 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102A | WELLHEAD CONTROL PANEL 6 WELL EXTENTION | DFA-W13 | SECE TEAM | INLC | VEN-INST |  | 99000116
| MTN-RIGG | 2023-12-31 | 2022-04-09 | WDF | 4 |  | 4. Long | 2100053942 | 0010 | Change Check valve DFB-05 | Rigger Assistance | 7 |  |  | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFB05-WATER-INJECTION-LINE | DFB05 WATER INJECTION LINE | DFB-W05 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-04-09 | WDF | 4 |  | 4. Long | 2100053942 | 0040 | Change Check valve DFB-05 | Replace 4" Check Vlv | 7 |  |  | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFB05-WATER-INJECTION-LINE | DFB05 WATER INJECTION LINE | DFB-W05 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2022-04-09 | WDF | 4 |  | 4. Long | 2100053942 | 0050 | Change Check valve DFB-05 | Production Deisolate w leak/test | 7 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFB05-WATER-INJECTION-LINE | DFB05 WATER INJECTION LINE | DFB-W05 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-04-09 | WDF | 4 |  | 4. Long | 2100053942 | 0060 | Change Check valve DFB-05 | Housekeeping | 7 |  |  | 2 | 2 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFB05-WATER-INJECTION-LINE | DFB05 WATER INJECTION LINE | DFB-W05 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2021-12-10 | WDF | 3 | S | 3. Intermediate | 2100053995 | 0010 | DFC-FT5241 Noz sealing face corro (HOLD) | DFC-FT5241 Nozzle sealing face corrosion |  |  |  | 1 | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL NMAT PRC SETC | DF /C /51/DFCM-FT-5241 | COOLING WATER MEDIUM - SEAWATER FILTER | NOSD |  | INLC | VEN-MECH
| MTN-INST | 2023-12-31 | 2022-01-13 | WDF | 3 | V | 3. Intermediate | 2100055790 | 0020 | Falty positiner for BDV-330007 | Dismount ShutDown Valve (BDV, ESDV, SDV) | 6 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-BDV-330007 | HP MANIFOLD BLOWDOWN | DFGFLARE |  | INLC | MTN-INST
| MTN-INST | 2023-12-31 | 2022-01-13 | WDF | 3 | V | 3. Intermediate | 2100055791 | 0070 | DFA07 ESDV-45007 falty indication | Mount Instrument, position | 5 |  |  | 1 | 1 | 1 | 0 | APPR SMAT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45007 | EMERGENCY SHUTDOWN LIFT GAS MFD-07A | SIWL |  | INLC | MTN-INST
| MTN-MECH | 2024-01-01 | 2022-01-13 | WDF | 3 | V | 3. Intermediate | 2100055791 | 0071 | DFA07 ESDV-45007 falty indication | Adjust Position Switch | 5 |  |  | 2 | 1 | 2 | 0 | APPR SMAT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45007 | EMERGENCY SHUTDOWN LIFT GAS MFD-07A | SIWL |  | INLC | MTN-INST
| PRODTECH | 2024-01-01 | 2022-01-13 | WDF | 3 | V | 3. Intermediate | 2100055791 | 0080 | DFA07 ESDV-45007 falty indication | Deisolate & Leaktest Emergency Shutdown | 5 |  |  | 2 | 1 | 2 | 0 | APPR SMAT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45007 | EMERGENCY SHUTDOWN LIFT GAS MFD-07A | SIWL |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2021-10-22 | WDF | 3 | V | 3. Intermediate | 2100056156 | 0030 | Hydraulic seep in WH panel FP-3103 | Replace instrument valve | 4 |  | DUCSAT, post-WELLSAT DAB | 1 | 1 | 1 | 0 | APPR SMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DA /D /07/DD-PSH-30538 | SSSV-30538, WELL MD-02 | SIWL |  | INLC | MTN-INST
| PRODTECH | 2024-01-01 | 2021-10-22 | WDF | 3 | V | 3. Intermediate | 2100056156 | 0040 | Hydraulic seep in WH panel FP-3103 | Production deisolation w leak test | 4 |  | DUCSAT, post-WELLSAT DAB | 2 | 1 | 2 | 0 | APPR SMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DA /D /07/DD-PSH-30538 | SSSV-30538, WELL MD-02 | SIWL |  | INLC | MTN-INST
| MTN-RIGG | 2024-01-03 | 2021-12-03 | WDF | 3 | V | 3. Intermediate | 2100056840 | 0077 | Refurbished Winch to be installed LB2 an | Rigging Winch |  |  |  | 18 | 2 | 18 | 0 | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /G /02/DFGA-X-0702 | LIFEBOAT | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-07 | 2021-12-03 | WDF | 3 | V | 3. Intermediate | 2100056840 | 0110 | Refurbished Winch to be installed LB2 an | Loadtest LB1 (later by Verhoef) |  |  |  | 1 | 1 | 1 | 0 | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ ROUT | INIT OPND | REL PCNF GMPS MANC PRC SETC | DF /G /02/DFGA-X-0702 | LIFEBOAT | NOSD |  | INLC | MTN-MECH
| MTN-INST | 2024-01-01 | 2022-09-28 | WDF | 4 | S | 4. Long | 2100056882 | 0020 | Replace Manifold tubing and DBB for PI35 | Remove Manifold |  |  |  | 1 | 1 | 1 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /54/DFGA-PI-350465 | PRESSURE GAUGE | DFG-WI |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2022-09-28 | WDF | 4 | S | 4. Long | 2100056882 | 0030 | Replace Manifold tubing and DBB for PI35 | Replace Manifold |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /54/DFGA-PI-350465 | PRESSURE GAUGE | DFG-WI |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2022-09-28 | WDF | 4 | S | 4. Long | 2100056882 | 0031 | Replace Manifold tubing and DBB for PI35 | Replace Instr.pipe from manifold /PI |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /54/DFGA-PI-350465 | PRESSURE GAUGE | DFG-WI |  | INLC | MTN-INST
| MTN-INST | 2024-01-02 | 2022-09-28 | WDF | 4 | S | 4. Long | 2100056882 | 0040 | Replace Manifold tubing and DBB for PI35 | Alignment of Manifold |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /54/DFGA-PI-350465 | PRESSURE GAUGE | DFG-WI |  | INLC | MTN-INST
| PRODTECH | 2024-01-02 | 2022-09-28 | WDF | 4 | S | 4. Long | 2100056882 | 0050 | Replace Manifold tubing and DBB for PI35 | Deisolate and test Manifold |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /54/DFGA-PI-350465 | PRESSURE GAUGE | DFG-WI |  | INLC | MTN-INST
| MTN-MECH | 2023-12-31 | 2022-02-10 | WDF | 3 | V | 3. Intermediate | 2100057170 | 0020 | Rusten sov på ESDV | Replace and adjust Control panel (SDV) | 6 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /11/DFBA-ESDV-34081 | EMERGENCY SHUTDOWN VALVE | DFB-3550 |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2022-02-11 | WDF | 3 | I | 3. Intermediate | 2100057416 | 0010 | ½" welded WI HCV leaking at valve handle | Scaffold Errection/Step-up work PF | 6 |  |  | 18 | 3 | 18 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /E /55/DFE01-WATER-INJECTION-LINE | DFE01 WATER INJECTION LINE | DFE-W01 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-02-11 | WDF | 3 | I | 3. Intermediate | 2100057416 | 0040 | ½" welded WI HCV leaking at valve handle | Replace Spool w SDBB Vlv | 6 |  |  | 6 | 2 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /E /55/DFE01-WATER-INJECTION-LINE | DFE01 WATER INJECTION LINE | DFE-W01 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2022-02-11 | WDF | 3 | I | 3. Intermediate | 2100057416 | 0050 | ½" welded WI HCV leaking at valve handle | Production deisolation w leak test | 6 |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /E /55/DFE01-WATER-INJECTION-LINE | DFE01 WATER INJECTION LINE | DFE-W01 |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-10 | 2023-02-26 | WDF | 4 | I | 4. Long | 2100058383 | 0080 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Check isolation |  |  |  | 1 | 1 | 1 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /75/DFFA-P-3910 | METHANOL PUMP | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-10 | 2023-02-26 | WDF | 4 | I | 4. Long | 2100058383 | 0090 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Mech installation of pumpskid |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /75/DFFA-P-3910 | METHANOL PUMP | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-10 | 2023-02-26 | WDF | 4 | I | 4. Long | 2100058383 | 0100 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Electric install pumpskid |  |  |  | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /75/DFFA-P-3910 | METHANOL PUMP | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-10 | 2023-02-26 | WDF | 4 | I | 4. Long | 2100058383 | 0110 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance / rigout |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /75/DFFA-P-3910 | METHANOL PUMP | NOSD |  | INLC | MTN-MECH
| PRODTECH | 2024-01-12 | 2023-02-26 | WDF | 4 | I | 4. Long | 2100058383 | 0120 | DFFA-P-3910 METHANOL PUMP Onshore for ov | deisolate/test DFFA-P-3910 |  |  |  | 3 | 2 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /75/DFFA-P-3910 | METHANOL PUMP | NOSD |  | INLC | MTN-MECH
| MTN-ROPE | 2024-01-13 | 2023-02-26 | WDF | 4 | I | 4. Long | 2100058383 | 0130 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Remove hoist/rigger prep |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /75/DFFA-P-3910 | METHANOL PUMP | NOSD |  | INLC | MTN-MECH
| MTN-TELE | 2023-12-31 | 2022-01-25 | WDF | 3 | V | 3. Intermediate | 2100059454 | 0030 | Control voltage DFF 1907A | Assist Vendor | 5 |  | W35-36 | 6 | 1 | 6 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /06/DFFA-DP-1907 | UPS DISTRIBUTION BOARD | DFF-IPHP | GMC | INLC | MTN-ELEC
| PRODTECH | 2024-01-03 | 2022-01-25 | WDF | 3 | V | 3. Intermediate | 2100059454 | 0040 | Control voltage DFF 1907A | De-isolate above | 5 |  |  | 2 | 1 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /06/DFFA-DP-1907 | UPS DISTRIBUTION BOARD | DFF-IPHP | GMC | INLC | MTN-ELEC
| PRODTECH | 2023-12-31 | 2022-01-31 | WDF | 3 | V | 3. Intermediate | 2100059695 | 0030 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Production isolation |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /20/DFCI-LT-34014 | LEVEL TRANSMITTER (ESD) | DFCHPSEP |  | INLC | MTN-INST
| MTN-MECH | 2024-01-01 | 2022-01-31 | WDF | 3 | V | 3. Intermediate | 2100059695 | 0040 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Replace 2" valve |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /20/DFCI-LT-34014 | LEVEL TRANSMITTER (ESD) | DFCHPSEP |  | INLC | MTN-INST
| PRODTECH | 2024-01-02 | 2022-01-31 | WDF | 3 | V | 3. Intermediate | 2100059695 | 0050 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Production de-isolation w leaktest |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /20/DFCI-LT-34014 | LEVEL TRANSMITTER (ESD) | DFCHPSEP |  | INLC | MTN-INST
| MTN-LAGG | 2024-01-03 | 2022-01-31 | WDF | 3 | V | 3. Intermediate | 2100059695 | 0060 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Re-instate insulation |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /C /20/DFCI-LT-34014 | LEVEL TRANSMITTER (ESD) | DFCHPSEP |  | INLC | MTN-INST
| PRODTECH | 2024-01-01 | 2022-07-31 | WDF | 4 | S | 4. Long | 2100059771 | 0030 | DFFA-HCV-340004-U Internal leak | Production isolation |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-HCV-340004-U | HCV UPSTREAM PSV-340004 | DFFHPSEP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2022-07-31 | WDF | 4 | S | 4. Long | 2100059771 | 0040 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  |  | 14 | 2 | 14 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-HCV-340004-U | HCV UPSTREAM PSV-340004 | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-07-31 | WDF | 4 | S | 4. Long | 2100059771 | 0050 | DFFA-HCV-340004-U Internal leak | HCV-340004 removal |  |  |  | 6 | 2 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-HCV-340004-U | HCV UPSTREAM PSV-340004 | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-07-31 | WDF | 4 | S | 4. Long | 2100059771 | 0060 | DFFA-HCV-340004-U Internal leak | Install new HCV-340004 |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-HCV-340004-U | HCV UPSTREAM PSV-340004 | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2022-07-31 | WDF | 4 | S | 4. Long | 2100059771 | 0070 | DFFA-HCV-340004-U Internal leak | Production de-isolation w leaktest |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-HCV-340004-U | HCV UPSTREAM PSV-340004 | DFFHPSEP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2022-07-31 | WDF | 4 | S | 4. Long | 2100059771 | 0080 | DFFA-HCV-340004-U Internal leak | Rigging equipment removal |  |  |  | 8 | 2 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /10/DFFA-HCV-340004-U | HCV UPSTREAM PSV-340004 | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-08-17 | WDF | 4 |  | 4. Long | 2100060627 | 0010 | FF-31 Manifold Valves Internal leak | Isolate Manifold Valves |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF31-WATER-INJECTION-LINE | DFF31 WATER INJECTION LINE | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-08-17 | WDF | 4 |  | 4. Long | 2100060627 | 0040 | FF-31 Manifold Valves Internal leak | Demount "upper" HCV Valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF31-WATER-INJECTION-LINE | DFF31 WATER INJECTION LINE | DFF-WI |  | INLC | MTN-MECH | 2264077
| MTN-MECH | 2024-01-03 | 2022-08-17 | WDF | 4 |  | 4. Long | 2100060627 | 0050 | FF-31 Manifold Valves Internal leak | Demount "lower" HCV Valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF31-WATER-INJECTION-LINE | DFF31 WATER INJECTION LINE | DFF-WI |  | INLC | MTN-MECH | 2264077
| MTN-MECH | 2024-01-04 | 2022-08-17 | WDF | 4 |  | 4. Long | 2100060627 | 0070 | FF-31 Manifold Valves Internal leak | Mount new "lower" HCV Valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF31-WATER-INJECTION-LINE | DFF31 WATER INJECTION LINE | DFF-WI |  | INLC | MTN-MECH | 2264077
| MTN-MECH | 2024-01-06 | 2022-08-17 | WDF | 4 |  | 4. Long | 2100060627 | 0080 | FF-31 Manifold Valves Internal leak | Mount new "upper" HCV Valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF31-WATER-INJECTION-LINE | DFF31 WATER INJECTION LINE | DFF-WI |  | INLC | MTN-MECH | 2264077
| PRODTECH | 2024-01-07 | 2022-08-17 | WDF | 4 |  | 4. Long | 2100060627 | 0090 | FF-31 Manifold Valves Internal leak | De Isolate Manifold Valves |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF31-WATER-INJECTION-LINE | DFF31 WATER INJECTION LINE | DFF-WI |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0010 | DFB fire water valve LV-72 | Scaffold erection/Lifting Points |  |  |  | 18 | 2 | 18 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0020 | DFB fire water valve LV-72 | Prepare Rigging Equipment |  |  |  | 4 | 2 | 4 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0030 | DFB fire water valve LV-72 | Production isolation |  |  |  | 3 | 1 | 3 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0040 | DFB fire water valve LV-72 | Replace HCV | 7 |  |  | 4 | 1 | 4 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH | 2293414
| MTN-RIGG | 2024-01-03 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0050 | DFB fire water valve LV-72 | Rigger assistance |  |  |  | 8 | 2 | 8 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0060 | DFB fire water valve LV-72 | Production deisolation w leaktest |  |  |  | 2 | 1 | 2 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH
| MTN-SCAF | 2024-01-05 | 2022-09-17 | WDF | 4 | S | 4. Long | 2100062057 | 0070 | DFB fire water valve LV-72 | Scaffold removal |  |  |  | 8 | 1 | 8 | 0 | APPR APOG PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /01/DFBA-HCV-03805 | LO - HAND CONTROL VALVE | DFB-OIL |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-09-23 | WDF | 4 | V | 4. Long | 2100062451 | 0010 | DFB06 Manifold valve fails inflow test | Isolate HCV | 5 |  |  | 4 | 1 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-WI |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2022-09-23 | WDF | 4 | V | 4. Long | 2100062451 | 0030 | DFB06 Manifold valve fails inflow test | Rigging assist. Rig in/out | 5 |  |  | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-09-23 | WDF | 4 | V | 4. Long | 2100062451 | 0040 | DFB06 Manifold valve fails inflow test | Demount Old HCV | 5 |  |  | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-WI |  | INLC | MTN-MECH | 2267898
| MTN-RIGG | 2024-01-03 | 2022-09-23 | WDF | 4 | V | 4. Long | 2100062451 | 0050 | DFB06 Manifold valve fails inflow test | Rigging assist. Rig in/out | 5 |  |  | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-09-23 | WDF | 4 | V | 4. Long | 2100062451 | 0060 | DFB06 Manifold valve fails inflow test | Mount new HCV | 5 |  |  | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-WI |  | INLC | MTN-MECH | 2267898
| PRODTECH | 2024-01-05 | 2022-09-23 | WDF | 4 | V | 4. Long | 2100062451 | 0070 | DFB06 Manifold valve fails inflow test | Deisolate HCV | 5 |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-WI |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-09-20 | WDF | 4 | I | 4. Long | 2100062994 | 0010 | DFB-04 Pigtails missing on inst tubing F | Isolate Flow transmitter (Orifice Plate) | 7 |  | Hold Step on stock | 0.5 | 1 | 0.5 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /B /55/DFBA-FT-35025 | FLOW TRANSM. (FT-I) (SCADA) (METERING) | SIWL |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2022-09-20 | WDF | 4 | I | 4. Long | 2100062994 | 0020 | DFB-04 Pigtails missing on inst tubing F | Replace Flow transmitter tubing | 7 |  | Hold Step on stock | 2.5 | 1 | 2.5 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /B /55/DFBA-FT-35025 | FLOW TRANSM. (FT-I) (SCADA) (METERING) | SIWL |  | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2022-09-20 | WDF | 4 | I | 4. Long | 2100062994 | 0030 | DFB-04 Pigtails missing on inst tubing F | Deisolate and test Flow transmitter (Ori | 7 |  | Hold Step on stock | 0.5 | 1 | 0.5 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /B /55/DFBA-FT-35025 | FLOW TRANSM. (FT-I) (SCADA) (METERING) | SIWL |  | INLC | MTN-INST
| MTN-RIGG | 2024-01-01 | 2022-10-18 | WDF | 4 | V | 4. Long | 2100064010 | 0030 | DFF-11 man VLV gearbox and internal leak | Rigging assist. Rig in/out |  |  |  | 19 | 1 | 19 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2022-10-18 | WDF | 4 | V | 4. Long | 2100064010 | 0040 | DFF-11 man VLV gearbox and internal leak | Demount both HCV Valves |  |  |  | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-08 | 2022-10-18 | WDF | 4 | V | 4. Long | 2100064010 | 0050 | DFF-11 man VLV gearbox and internal leak | Remove gearbox and mount on lower Valve |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-09 | 2022-10-18 | WDF | 4 | V | 4. Long | 2100064010 | 0060 | DFF-11 man VLV gearbox and internal leak | Rigging assist. Rig in/out |  |  |  | 19 | 1 | 19 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-14 | 2022-10-18 | WDF | 4 | V | 4. Long | 2100064010 | 0070 | DFF-11 man VLV gearbox and internal leak | Mount new HCV Valves |  |  |  | 20 | 1 | 20 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-19 | 2022-10-18 | WDF | 4 | V | 4. Long | 2100064010 | 0080 | DFF-11 man VLV gearbox and internal leak | De Isolate Manifold Valves |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/WATER-INJECTION-MANIFOLD | WATER INJECTION MANIFOLD | DFF-WI |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-10-28 | WDF | 4 |  | 4. Long | 2100064529 | 0010 | Manifold HCVer intern utæt DFF-19 | Isolate Manifold Valve |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF19-WATER-INJECTION-LINE | DFF19 WATER INJECTION LINE | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-10-28 | WDF | 4 |  | 4. Long | 2100064529 | 0040 | Manifold HCVer intern utæt DFF-19 | Demount "lower" HCV Valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF19-WATER-INJECTION-LINE | DFF19 WATER INJECTION LINE | DAN-WI |  | INLC | MTN-MECH | 2297703
| MTN-MECH | 2024-01-02 | 2022-10-28 | WDF | 4 |  | 4. Long | 2100064529 | 0070 | Manifold HCVer intern utæt DFF-19 | Mount new "lower" HCV Valve |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF19-WATER-INJECTION-LINE | DFF19 WATER INJECTION LINE | DAN-WI |  | INLC | MTN-MECH | 2297703
| MTN-MECH | 2024-01-04 | 2022-10-28 | WDF | 4 |  | 4. Long | 2100064529 | 0080 | Manifold HCVer intern utæt DFF-19 | De Isolate Manifold Valves |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /55/DFF19-WATER-INJECTION-LINE | DFF19 WATER INJECTION LINE | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0005 | DFG Glycol High dP over exchanger 4147 | Insulation/cladding removal | ID 29 |  |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0007 | DFG Glycol High dP over exchanger 4147 | Prepare Lifting Equip. | ID 29 |  | PRE | 10 | 2 | 10 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0010 | DFG Glycol High dP over exchanger 4147 | Production isolation w Flushing | ID 29 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0020 | DFG Glycol High dP over exchanger 4147 | Rigger assistance | ID 29 |  |  | 24 | 2 | 24 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0030 | DFG Glycol High dP over exchanger 4147 | Replace Exchanger E-4147 | ID 29 |  |  | 24 | 2 | 24 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0040 | DFG Glycol High dP over exchanger 4147 | Removal rigging equipment | ID 29 |  | POST | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-06 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0050 | DFG Glycol High dP over exchanger 4147 | Production de-isolation w leaktest | ID 29 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-LAGG | 2024-01-06 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067223 | 0060 | DFG Glycol High dP over exchanger 4147 | Insulation/Cladding erection | ID 29 |  |  | 20 | 1 | 20 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4147 | GLYCOL/GLYCOL EXCHANGER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0010 | DFG Glycol High dP over exchanger 4148 | Insulation/cladding removal | ID 14 |  |  | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0020 | DFG Glycol High dP over exchanger 4148 | Prepare Rigger equipment | ID 14 |  | PRE | 10 | 2 | 10 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0030 | DFG Glycol High dP over exchanger 4148 | Production isolation w Flushing | ID 14 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0040 | DFG Glycol High dP over exchanger 4148 | Rigger assistance | ID 14 |  |  | 24 | 2 | 24 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0050 | DFG Glycol High dP over exchanger 4148 | Replace Exchanger E-4147 | ID 14 |  |  | 24 | 2 | 24 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0060 | DFG Glycol High dP over exchanger 4148 | Rigger equipment removal | ID 14 |  | POST | 6 | 2 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-06 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0070 | DFG Glycol High dP over exchanger 4148 | Production de-isolation w leaktest | ID 14 |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| MTN-LAGG | 2024-01-06 | 2022-12-16 | WDF | 4 | I | 4. Long | 2100067224 | 0080 | DFG Glycol High dP over exchanger 4148 | Reinstate insulation/cladding | ID 14 |  |  | 20 | 2 | 20 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /30/DFGA-E-4148 | GLYCOL PRE-HEATER | DFG-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-07-24 | WDF | 3 | V | 3. Intermediate | 2100067310 | 0040 | DFB-02 choke ZSC can not be activated | Deisolate and repeal inhibits Choke Valv |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /10/DFBA-CVA-30002 | CHOKE VALVE | DFB-O02 |  | INLC | MTN-INST
| MTN-MECH | 2023-12-31 | 2022-08-20 | WDF | 3 | V | 3. Intermediate | 2100067914 | 0010 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Small Step-up scaffold erection |  |  |  | 24 | 3 | 24 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-08-20 | WDF | 3 | V | 3. Intermediate | 2100067914 | 0020 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Production Isolation |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-08-20 | WDF | 3 | V | 3. Intermediate | 2100067914 | 0030 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Rigger assistance |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-08-20 | WDF | 3 | V | 3. Intermediate | 2100067914 | 0040 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Replace 2" Globe Valve |  |  |  | 8 | 1 | 8 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-04 | 2022-08-20 | WDF | 3 | V | 3. Intermediate | 2100067914 | 0050 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Production De-isolation w Leaktest |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-EP-3804 | 12" DAN B WATER PIG LAUNCHER | DAN-WI |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-09-25 | WDF | 3 | V | 3. Intermediate | 2100069195 | 0005 | DFE-04 WCV-30028 hydraulic piping | Isolate and Inhibit Valve |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /10/DFEZ-WCV-30028 | WING CONTROL VALVE (WCV/SOV-III) | DFE-O04 |  | INLC | MTN-INST
| MTN-INST | 2023-12-31 | 2022-09-25 | WDF | 3 | V | 3. Intermediate | 2100069195 | 0030 | DFE-04 WCV-30028 hydraulic piping | Remove Piping |  |  |  | 3 | 2 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /10/DFEZ-WCV-30028 | WING CONTROL VALVE (WCV/SOV-III) | DFE-O04 |  | INLC | MTN-INST
| MTN-INST | 2023-12-31 | 2022-09-25 | WDF | 3 | V | 3. Intermediate | 2100069195 | 0035 | DFE-04 WCV-30028 hydraulic piping | Reinstall Piping |  |  |  | 3 | 2 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /10/DFEZ-WCV-30028 | WING CONTROL VALVE (WCV/SOV-III) | DFE-O04 |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2022-09-25 | WDF | 3 | V | 3. Intermediate | 2100069195 | 0040 | DFE-04 WCV-30028 hydraulic piping | Adjust Valve |  |  |  | 0.5 | 1 | 0.5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /10/DFEZ-WCV-30028 | WING CONTROL VALVE (WCV/SOV-III) | DFE-O04 |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2022-09-25 | WDF | 3 | V | 3. Intermediate | 2100069195 | 0060 | DFE-04 WCV-30028 hydraulic piping | Deisolate Valve |  |  |  | 0.5 | 1 | 0.5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /10/DFEZ-WCV-30028 | WING CONTROL VALVE (WCV/SOV-III) | DFE-O04 |  | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2022-09-25 | WDF | 3 | V | 3. Intermediate | 2100069195 | 0070 | DFE-04 WCV-30028 hydraulic piping | Deisolate and repeal inhibits Valv |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /10/DFEZ-WCV-30028 | WING CONTROL VALVE (WCV/SOV-III) | DFE-O04 |  | INLC | MTN-INST
| MTN-SCAF | 2023-12-31 | 2022-09-29 | WDF | 3 | S | 3. Intermediate | 2100069357 | 0010 | DFFA-HCV-380016 internal leaking (EP-380 | Scaffold Erection/Assistance |  |  |  | 120 | 4 | 120 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-HCV-380016 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2022-09-29 | WDF | 3 | S | 3. Intermediate | 2100069357 | 0020 | DFFA-HCV-380016 internal leaking (EP-380 | Rigging preparation/Liftings assistance |  |  |  | 120 | 3 | 120 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-HCV-380016 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-09-29 | WDF | 3 | S | 3. Intermediate | 2100069357 | 0030 | DFFA-HCV-380016 internal leaking (EP-380 | Production isolation |  |  |  | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-HCV-380016 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-10 | 2022-09-29 | WDF | 3 | S | 3. Intermediate | 2100069357 | 0040 | DFFA-HCV-380016 internal leaking (EP-380 | Swap Actuator/Replace Valve |  |  |  | 100 | 3 | 100 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-HCV-380016 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH
| PRODTECH | 2024-01-18 | 2022-09-29 | WDF | 3 | S | 3. Intermediate | 2100069357 | 0050 | DFFA-HCV-380016 internal leaking (EP-380 | Production de-isolation w leaktest |  |  |  | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54/DFFA-HCV-380016 | HAND CONTROL VALVE | DAN-WI |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2025-05-30 | WDF | 4 | S | 4. Long | 2100069954 | 0010 | DFB-HCV-57314 | Isolate HCV |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /70/DFBA-HCV-57314-D | HCV DOWNSTREAM PSV-57314 | D-FLARE |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2025-05-30 | WDF | 4 | S | 4. Long | 2100069954 | 0030 | DFB-HCV-57314 | Rigging assist. Rig in/out |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /70/DFBA-HCV-57314-D | HCV DOWNSTREAM PSV-57314 | D-FLARE |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2025-05-30 | WDF | 4 | S | 4. Long | 2100069954 | 0040 | DFB-HCV-57314 | Demount HCV |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /70/DFBA-HCV-57314-D | HCV DOWNSTREAM PSV-57314 | D-FLARE |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2025-05-30 | WDF | 4 | S | 4. Long | 2100069954 | 0050 | DFB-HCV-57314 | Mount New HCV |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /70/DFBA-HCV-57314-D | HCV DOWNSTREAM PSV-57314 | D-FLARE |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2025-05-30 | WDF | 4 | S | 4. Long | 2100069954 | 0060 | DFB-HCV-57314 | De Isolate Manifold Valves |  |  |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /70/DFBA-HCV-57314-D | HCV DOWNSTREAM PSV-57314 | D-FLARE |  | INLC | MTN-MECH
| MTN-INST | 2023-12-31 | 2023-02-12 | WDF | 3 | V | 3. Intermediate | 2100073047 | 0030 | Leaking instrument valve PT-35219 | Replace manifold block and fittings for | 5 |  |  | 3 | 1 | 3 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-PT-35219 | PRESSURE TRANSMITTER (PT-X) (ESD) | SIWL |  | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2023-02-12 | WDF | 3 | V | 3. Intermediate | 2100073047 | 0040 | Leaking instrument valve PT-35219 | Deisolate Pressure transmitter | 5 |  |  | 0.5 | 1 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-PT-35219 | PRESSURE TRANSMITTER (PT-X) (ESD) | SIWL |  | INLC | MTN-INST
| MTN-INST | 2023-12-31 | 2023-02-12 | WDF | 3 | V | 3. Intermediate | 2100073047 | 0045 | Leaking instrument valve PT-35219 | Calibrate pressure transmitter and test | 5 |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-PT-35219 | PRESSURE TRANSMITTER (PT-X) (ESD) | SIWL |  | INLC | MTN-INST
| PRODTECH | 2024-01-01 | 2023-02-12 | WDF | 3 | V | 3. Intermediate | 2100073047 | 0050 | Leaking instrument valve PT-35219 | Repeal inhibit Pressure transmitter | 5 |  |  | 0.5 | 1 | 0.5 | 0 | APPR PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFBA-PT-35219 | PRESSURE TRANSMITTER (PT-X) (ESD) | SIWL |  | INLC | MTN-INST
| PRODTECH | 2024-04-06 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0010 | DFFW/78: Wire rope pulleys replacement | Isolate/de-isolate of crane DFFA-A-6102 |  |  |  | 4 | 1 | 4 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| MTN-ROPE | 2024-04-07 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0020 | DFFW/78: Wire rope pulleys replacement | Build/demol of scaffold/gallows |  |  |  | 240 | 3 | 240 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| MTN-ROPE | 2024-04-27 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0021 | DFFW/78: Wire rope pulleys replacement | Handling/lift of wire rope pulleys |  |  |  | 90 | 3 | 90 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| VEN-CRAN | 2024-04-27 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0030 | DFFW/78: Wire rope pulleys replacement | Replace BH wire rope pulleys in A-Frame |  |  |  | 60 | 2 | 60 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| VEN-CRAN | 2024-04-30 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0040 | DFFW/78: Wire rope pulleys replacement | Replace BH wire rope pulleys in boom |  |  |  | 60 | 2 | 60 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| VEN-CRAN | 2024-05-03 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0050 | DFFW/78: Wire rope pulleys replacement | Replace aux hoist wire rope pulleys |  |  |  | 48 | 2 | 48 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| VEN-CRAN | 2024-05-05 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0060 | DFFW/78: Wire rope pulleys replacement | Perform proof load test of crane |  |  |  | 24 | 2 | 24 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| MTN-ROUS | 2024-05-05 | 2025-09-22 | WDF | 4 | V | 4. Long | 2100076005 | 0070 | DFFW/78: Wire rope pulleys replacement | Operation of crane/assistance with test |  |  |  | 24 | 2 | 24 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /78/DFFA-A-6102 | CRANE - 60 T | NOSD |  | INLC | VEN-CRAN
| MTN-CRAN | 2024-06-07 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0010 | DFG/78 Main winch onshore for overhaul | Remove main hook and spool of wire |  |  |  | 22 | 2 | 22 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROUS | 2024-06-07 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0020 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  |  | 8 | 1 | 8 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-RIGG | 2024-06-07 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0030 | DFG/78 Main winch onshore for overhaul | Assist with hook and wire |  |  |  | 20 | 2 | 20 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| PRODTECH | 2024-06-10 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0040 | DFG/78 Main winch onshore for overhaul | Isolate/de-isolate crane |  |  |  | 2 | 1 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-06-10 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0050 | DFG/78 Main winch onshore for overhaul | Disconnect el & hydraulics |  |  |  | 28 | 2 | 28 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-06-14 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0060 | DFG/78 Main winch onshore for overhaul | Disconnect winch |  |  |  | 10 | 2 | 10 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-RIGG | 2024-06-14 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0070 | DFG/78 Main winch onshore for overhaul | Rigging of winch (down) |  |  |  | 75 | 3 | 75 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-06-20 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0080 | DFG/78 Main winch onshore for overhaul | Ensure safe upstart without main winch |  |  |  | 4 | 1 | 4 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-06-21 | 2025-10-23 | WDF | 4 | V | 4. Long | 2100077932 | 0090 | DFG/78 Main winch onshore for overhaul | Backload main winch for onshore overhaul |  |  |  | 2 | 1 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DF /G /78/DFGA-A-6140 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| PRODTECH | 2024-07-10 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0010 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-10 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0020 | DFA/78 Bolts for winch flanges+paint | Replace bolts on luffing winch |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-PAIN | 2024-07-10 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0030 | DFA/78 Bolts for winch flanges+paint | Clean/Paint area around luffing winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-11 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0040 | DFA/78 Bolts for winch flanges+paint | Replace bolts on main winch |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-PAIN | 2024-07-12 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0050 | DFA/78 Bolts for winch flanges+paint | Clean/Paint area around main winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROPE | 2024-07-12 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0060 | DFA/78 Bolts for winch flanges+paint | Assist with main winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-13 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0070 | DFA/78 Bolts for winch flanges+paint | Replace bolts on Aux winch |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-PAIN | 2024-07-14 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0080 | DFA/78 Bolts for winch flanges+paint | Clean/Paint area around Aux winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROPE | 2024-07-14 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0090 | DFA/78 Bolts for winch flanges+paint | Assist with Aux winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-15 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0100 | DFA/78 Bolts for winch flanges+paint | Proof loadtest in connection with 1Y PPM |  |  |  | 8 | 1 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROUS | 2024-07-15 | 2026-02-26 | WDF | 4 | V | 4. Long | 2100087412 | 0110 | DFA/78 Bolts for winch flanges+paint | Proof loadtest in connection with 1Y PPM |  |  |  | 8 | 1 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| PRODTECH | 2024-07-16 | 2026-03-04 | WDF | 4 | V | 4. Long | 2100087753 | 0010 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-16 | 2026-03-04 | WDF | 4 | V | 4. Long | 2100087753 | 0020 | DFFE/78 Wire sheave replacement | Replace all wire sheaves |  |  |  | 100 | 2 | 100 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-SCAF | 2024-07-29 | 2026-03-04 | WDF | 4 | V | 4. Long | 2100087753 | 0030 | DFFE/78 Wire sheave replacement | Build & remove scaffold |  |  |  | 120 | 3 | 120 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-RIGG | 2024-08-08 | 2026-03-04 | WDF | 4 | V | 4. Long | 2100087753 | 0040 | DFFE/78 Wire sheave replacement | Rigging of sheaves & secure wires |  |  |  | 70 | 2 | 70 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-08-17 | 2026-03-04 | WDF | 4 | V | 4. Long | 2100087753 | 0050 | DFFE/78 Wire sheave replacement | Proof load test of crane |  |  |  | 16 | 2 | 16 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROUS | 2024-08-19 | 2026-03-04 | WDF | 4 | V | 4. Long | 2100087753 | 0060 | DFFE/78 Wire sheave replacement | Proof load test of crane |  |  |  | 16 | 2 | 16 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /F /78/DFFA-A-6101 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| PRODTECH | 2024-07-20 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0010 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-20 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0020 | DFB/78 Bolts for winch flanges+paint | Replace bolts on luffing winch |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-PAIN | 2024-07-20 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0030 | DFB/78 Bolts for winch flanges+paint | Clean/Paint area around luffing winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-21 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0040 | DFB/78 Bolts for winch flanges+paint | Replace bolts on main winch |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-PAIN | 2024-07-22 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0050 | DFB/78 Bolts for winch flanges+paint | Clean/Paint area around main winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROPE | 2024-07-22 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0060 | DFB/78 Bolts for winch flanges+paint | Assist with main winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-23 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0070 | DFB/78 Bolts for winch flanges+paint | Replace bolts on Aux winch |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-PAIN | 2024-07-24 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0080 | DFB/78 Bolts for winch flanges+paint | Clean/Paint area around Aux winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROPE | 2024-07-24 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0090 | DFB/78 Bolts for winch flanges+paint | Assist with Aux winch |  |  |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-25 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0100 | DFB/78 Bolts for winch flanges+paint | Proof loadtest in connection with 1Y PPM |  |  |  | 8 | 1 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-07-25 | 2026-03-08 | WDF | 4 | V | 4. Long | 2100088070 | 0110 | DFB/78 Bolts for winch flanges+paint | Proof loadtest in connection with 1Y PPM |  |  |  | 8 | 1 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MACM PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-10 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0020 | DBB/78 Dynamic damper for winch Defect | Replace 2 ea accumulators and fill up N2 |  |  |  | 8 | 1 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-RIGG | 2024-01-10 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0030 | DBB/78 Dynamic damper for winch Defect | Assist with rigging of accumulators |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-12 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0040 | DBB/78 Dynamic damper for winch Defect | Replace cylinder kit |  |  |  | 4 | 1 | 4 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-RIGG | 2024-01-12 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0050 | DBB/78 Dynamic damper for winch Defect | Assist with rigging of cylinder if neede |  |  |  | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-CRAN | 2024-01-13 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0060 | DBB/78 Dynamic damper for winch Defect | Function test |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-ROUS | 2024-01-13 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0070 | DBB/78 Dynamic damper for winch Defect | function test |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-MECH | 2024-04-27 | 2026-10-14 | WDF | 4 | V | 4. Long | 2100092170 | 0010 | CHG2958908 - Incorrect batch number 9 | CHG2958908 - Incorrect batch number 9 |  |  |  | 1 | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL MACM PRC SETC | DA /B /01/DB-FT-0400 | INLINE FILTER | NE |  | INLC | MTN-MECH
| MTN-INST | 2024-06-30 | 2026-12-17 | WDF | 4 | V | 4. Long | 2100092321 | 0010 | Check flowline | Repair job |  |  |  | 20 | 2 | 20 | 0 | APPR SECE AWDO SCH RFRZ ROUT | APPR OPND | REL NMAT PRC SETC | DA /A /07/DA-PSLL-3A | PSLL ON FLOWLINE, HIGH-PILOT |  |  | INLC | MTN-INST
| VEN-MECH | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002913 | 0050 | DFF-Insulation assists FORCE 13522 | L3 Force inspection at 3 places |  |  | COMP | 9 | 1 | 9 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-6-WI-035-7103-GF-U | 6 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002913 | 0090 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING |  |  | COMP | 12 | 2 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-6-WI-035-7103-GF-U | 6 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002913 | 0100 | DFF-Insulation assists FORCE 13522 | REMOVE INSULATION |  |  | COMP | 12 | 1 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-6-WI-035-7103-GF-U | 6 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002913 | 0110 | DFF-Insulation assists FORCE 13522 | Bilfinger inspection |  |  | COMP | 18 | 2 | 18 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-6-WI-035-7103-GF-U | 6 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002913 | 0120 | DFF-Insulation assists FORCE 13522 | INSTALL INSULATION |  |  | COMP | 24 | 1 | 24 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-6-WI-035-7103-GF-U | 6 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002913 | 0130 | DFF-Insulation assists FORCE 13522 | REMOVE SCAFFOLDING |  |  | COMP | 6 | 2 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-6-WI-035-7103-GF-U | 6 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-MECH | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0050 | DFF-Insulation assists FORCE 13521 | L3 Force inspection at 4 places |  |  |  | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0090 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 2 | 12 | 2 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0100 | DFF-Insulation assists FORCE 13521 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 2 | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-ELEC | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0110 | DFF-Insulation assists FORCE 13521 | REMOVE HEATTRACING |  |  | 2022 WTW - PIPE INSP DFF 2 | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0120 | DFF-Insulation assists FORCE 13521 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 2 | 12 | 2 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-ELEC | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0130 | DFF-Insulation assists FORCE 13521 | INSTALL HEATTRACING |  |  | 2022 WTW - PIPE INSP DFF 2 | 24 | 1 | 24 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0140 | DFF-Insulation assists FORCE 13521 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 2 | 24 | 1 | 24 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002914 | 0150 | DFF-Insulation assists FORCE 13521 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 2 | 6 | 2 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /55/DFF-2-WI-035-7203-GF-T | 2 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-MECH | 2024-01-09 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002915 | 0050 | DFF-Insulation assists FORCE 15971 | L3 Force inspection at 2 places |  |  |  | 6 | 1 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /10/DFF-6-PHS-030-7041-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-09 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002915 | 0090 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 3 | 36 | 2 | 36 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /10/DFF-6-PHS-030-7041-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-09 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002915 | 0100 | DFF-Insulation assists FORCE 15971 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 3 | 12 | 1 | 12 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /10/DFF-6-PHS-030-7041-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-09 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002915 | 0110 | DFF-Insulation assists FORCE 15971 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 3 | 32 | 2 | 32 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /10/DFF-6-PHS-030-7041-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-09 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002915 | 0120 | DFF-Insulation assists FORCE 15971 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 3 | 16 | 1 | 16 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /10/DFF-6-PHS-030-7041-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-09 | 2019-12-11 | WGN | 3 |  | 3. Intermediate | 2200002915 | 0130 | DFF-Insulation assists FORCE 15971 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 3 | 24 | 2 | 24 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /10/DFF-6-PHS-030-7041-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| VEN-MECH | 2024-01-08 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002923 | 0040 | scaff/insulation FORCE: 15962 | L3 Force scan 15962 |  |  |  | 2 | 1 | 2 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7633-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-08 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002923 | 0070 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation |  |  | 2022 WTW - PIPE INSP DFF 4 | 96 | 4 | 96 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7633-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-LAGG | 2024-01-08 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002923 | 0080 | scaff/insulation FORCE: 15962 | Remove insulation |  |  | 2022 WTW - PIPE INSP DFF 4 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7633-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| VEN-INSP | 2024-01-08 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002923 | 0090 | scaff/insulation FORCE: 15962 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 4 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7633-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-LAGG | 2024-01-08 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002923 | 0100 | scaff/insulation FORCE: 15962 | Put back Insulation |  |  | 2022 WTW - PIPE INSP DFF 4 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7633-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-08 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002923 | 0110 | scaff/insulation FORCE: 15962 | Scaffold remove |  |  | 2022 WTW - PIPE INSP DFF 4 | 48 | 4 | 48 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7633-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| VEN-MECH | 2024-01-08 | 2019-10-16 | WGN | 3 |  | 3. Intermediate | 2200002955 | 0030 | Insulation assists FORCE 14191 | Inspection - Force |  |  |  | 168 | 2 | 168 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-10-16 | WGN | 3 |  | 3. Intermediate | 2200002955 | 0060 | Insulation assists FORCE 14191 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 1 | 12 | 1 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-08 | 2019-10-16 | WGN | 3 |  | 3. Intermediate | 2200002955 | 0070 | Insulation assists FORCE 14191 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 1 | 24 | 2 | 24 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-10-16 | WGN | 3 |  | 3. Intermediate | 2200002955 | 0080 | Insulation assists FORCE 14191 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 1 | 16 | 1 | 16 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-MECH | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003036 | 0040 | Isolation assists FORCE 9071 | L3 Force insp |  |  |  | 1 | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /51/DFF-16-WI-035-7001-AM-U | 16 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003036 | 0060 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 6 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /51/DFF-16-WI-035-7001-AM-U | 16 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003036 | 0070 | Isolation assists FORCE 9071 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 6 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /51/DFF-16-WI-035-7001-AM-U | 16 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003036 | 0080 | Isolation assists FORCE 9071 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 6 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /51/DFF-16-WI-035-7001-AM-U | 16 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003036 | 0090 | Isolation assists FORCE 9071 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 6 | 48 | 1 | 48 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /51/DFF-16-WI-035-7001-AM-U | 16 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003036 | 0100 | Isolation assists FORCE 9071 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 6 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /51/DFF-16-WI-035-7001-AM-U | 16 INJECTION WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-MECH | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003038 | 0040 | CMAT:Isolation assist to FORCE 14321 | L3 Force insp |  |  |  | 5 | 1 | 5 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /F /55/DFF-6-PHS-030-7032-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003038 | 0060 | CMAT:Isolation assist to FORCE 14321 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 7 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /F /55/DFF-6-PHS-030-7032-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003038 | 0070 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 7 | 6 | 1 | 6 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /F /55/DFF-6-PHS-030-7032-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003038 | 0080 | CMAT:Isolation assist to FORCE 14321 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 7 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /F /55/DFF-6-PHS-030-7032-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003038 | 0090 | CMAT:Isolation assist to FORCE 14321 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 7 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /F /55/DFF-6-PHS-030-7032-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003038 | 0100 | CMAT:Isolation assist to FORCE 14321 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 7 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /F /55/DFF-6-PHS-030-7032-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-LAGG
| PRODTECH | 2023-12-31 | 2019-01-11 | WGN | 4 | S | 4. Long | 2200003040 | 0010 | CMAT:Replace DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D |  |  |  | 48 | 1 | 48 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCI-HCV-33030-D | LO - HCV DOWNSTREAM PSV-33030 | D-FLARE |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-12 | 2019-01-11 | WGN | 4 | S | 4. Long | 2200003040 | 0015 | CMAT:Replace DFCI-HCV-33030-D | L3 Assist in replace DFCI-HCV-33030-D |  |  |  | 10 | 1 | 10 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCI-HCV-33030-D | LO - HCV DOWNSTREAM PSV-33030 | D-FLARE |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-14 | 2019-01-11 | WGN | 4 | S | 4. Long | 2200003040 | 0020 | CMAT:Replace DFCI-HCV-33030-D | L2 Replacement of DFCI-HCV-33030-D |  |  |  | 8 | 1 | 8 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCI-HCV-33030-D | LO - HCV DOWNSTREAM PSV-33030 | D-FLARE |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-16 | 2019-01-11 | WGN | 4 | S | 4. Long | 2200003040 | 0030 | CMAT:Replace DFCI-HCV-33030-D | L3 De-Isolation/test of DFCI-HCV-33030-D |  |  |  | 48 | 1 | 48 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10/DFCI-HCV-33030-D | LO - HCV DOWNSTREAM PSV-33030 | D-FLARE |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2018-08-11 | WGN | 3 | V | 3. Intermediate | 2200003041 | 0015 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in lifting out actuator |  |  |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-PCV-34027 | V-3402 TO L.P.COMPRESSOR SUCTION MANIF. | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-08-11 | WGN | 3 | V | 3. Intermediate | 2200003041 | 0025 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L2 Replace Actuator |  |  |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-PCV-34027 | V-3402 TO L.P.COMPRESSOR SUCTION MANIF. | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-04 | 2018-08-11 | WGN | 3 | V | 3. Intermediate | 2200003041 | 0026 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in putting in actuator |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-PCV-34027 | V-3402 TO L.P.COMPRESSOR SUCTION MANIF. | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-06 | 2018-08-11 | WGN | 3 | V | 3. Intermediate | 2200003041 | 0030 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 De-Safing of DFCI-PCV-34027 |  |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20/DFCI-PCV-34027 | V-3402 TO L.P.COMPRESSOR SUCTION MANIF. | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2017-11-24 | WGN | 4 | S | 4. Long | 2200003051 | 0010 | SMAT:DFCI-HCV-57120-U kan ikke opereres/ | HCV kan ikke opereres/defekt HCV |  |  |  | 24 | 2 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /70/DFCI-HCV-57120-U | LO - HCV UPSTREAM PSV-57120 | DFC-FUEL |  | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2023-12-31 | 2017-12-31 | WGN | 4 | V | 4. Long | 2200003053 | 0009 | SMAT:DA-06 Check valve replacement | L3 Mount chain block | 2 |  | Gorm E S/D ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DA /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | SIWL |  | INLC | PRODTECH |  | DK0500013008
| PRODTECH | 2024-01-01 | 2017-12-31 | WGN | 4 | V | 4. Long | 2200003053 | 0010 | SMAT:DA-06 Check valve replacement | L3 Safing of DA-06 Check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DA /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | SIWL |  | INLC | PRODTECH |  | DK0500013008
| MTN-MECH | 2024-01-02 | 2017-12-31 | WGN | 4 | V | 4. Long | 2200003053 | 0011 | SMAT:DA-06 Check valve replacement | L2 Replave DA-06 Check valve | 2 |  | Gorm E S/D ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DA /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | SIWL |  | INLC | PRODTECH |  | DK0500013008
| PRODTECH | 2024-01-04 | 2017-12-31 | WGN | 4 | V | 4. Long | 2200003053 | 0012 | SMAT:DA-06 Check valve replacement | L3 Desafing of DA-06 Check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DA /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | SIWL |  | INLC | PRODTECH |  | DK0500013008
| MTN-RIGG | 2024-01-05 | 2017-12-31 | WGN | 4 | V | 4. Long | 2200003053 | 0013 | SMAT:DA-06 Check valve replacement | L3 Remove chain block | 2 |  | Gorm E S/D ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DA /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | SIWL |  | INLC | PRODTECH |  | DK0500013008
| MTN-MECH | 2024-01-06 | 2017-12-31 | WGN | 4 | V | 4. Long | 2200003053 | 0020 | SMAT:DA-06 Check valve replacement | ER BLÅ JOBSEDDEL FJERNET? J/N/NA | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DA /A /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | SIWL |  | INLC | PRODTECH |  | DK0500013008
| MTN-MECH | 2023-12-31 | 2018-07-19 | WGN | 4 |  | 4. Long | 2200003054 | 0010 | PMAT:DE01 WI manif HCVr kan ikke lukkes/ | HCVér kan ikke lukkes/betjenes. | 2 |  |  | 24 | 2 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DE /A /55 | INJECTION WELLS/FLOW-LINES/MANIFOLDS | SIWL |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2019-05-04 | WGN | 4 | V | 4. Long | 2200003055 | 0020 | CMAT:DFC, replacement of checkvalve | Preparation for rigging | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFX-OIL |  | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2019-05-04 | WGN | 4 | V | 4. Long | 2200003055 | 0040 | CMAT:DFC, replacement of checkvalve | Rigging assistance for replacement of th | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6.7 | 1 | 6.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFX-OIL |  | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2019-05-04 | WGN | 4 | V | 4. Long | 2200003055 | 0070 | CMAT:DFC, replacement of checkvalve | Removal of rigging equipment | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | DFX-OIL |  | INLC | MTN-PIPF |  | DK0500013711
| MTN-MECH | 2023-12-31 | 2017-08-10 | WGN | 3 | V | 3. Intermediate | 2200003056 | 0020 | Slanger, rør og fittings efterspændes | Fittings, rør og slanger efterspændes i | 2 |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /34/DFEZ-ESDV-45092 | G.LIFT MAN'D FROM GASEXPORT (ESDV/SOV) | DFE-OIL |  | INLC | MTN-INST |  | DK0500013711
| PRODTECH | 2024-01-01 | 2017-08-10 | WGN | 3 | V | 3. Intermediate | 2200003056 | 0030 | Slanger, rør og fittings efterspændes | Desafing og leaktest | 2 |  |  | 0.1 | 1 | 0.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /34/DFEZ-ESDV-45092 | G.LIFT MAN'D FROM GASEXPORT (ESDV/SOV) | DFE-OIL |  | INLC | MTN-INST |  | DK0500013711
| VEN-MECH | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003061 | 0040 | Scaff Assist to Force 13236 | L3 Force insp |  |  |  | 1 | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /10/DFF-6-PHS-030-7061-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003061 | 0060 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 8 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /10/DFF-6-PHS-030-7061-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-SCAF
| VEN-INSP | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003061 | 0070 | Scaff Assist to Force 13236 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 8 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /10/DFF-6-PHS-030-7061-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-08 | 2019-03-27 | WGN | 3 |  | 3. Intermediate | 2200003061 | 0080 | Scaff Assist to Force 13236 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 8 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /10/DFF-6-PHS-030-7061-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2023-12-31 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0030 | CMAT: Oxyg scavenger leak from dearat DF | Prepare of Permit (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-01 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0040 | CMAT: Oxyg scavenger leak from dearat DF | L3 Prepare of Permit (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-SCAF | 2024-01-02 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0060 | CMAT: Oxyg scavenger leak from dearat DF | L3 Install scaff (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-04 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0070 | CMAT: Oxyg scavenger leak from dearat DF | L3 Demol insulation (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-04 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0080 | CMAT: Oxyg scavenger leak from dearat DF | L3 Demol heatracing (El) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 1 | 2.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-05 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0100 | CMAT: Oxyg scavenger leak from dearat DF | L3 Check Marerials (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| PRODTECH | 2024-01-05 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0110 | CMAT: Oxyg scavenger leak from dearat DF | L1 Isolate (Prod) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-08 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0120 | CMAT: Oxyg scavenger leak from dearat DF | L1 Demol spool (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 2 | 5.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-09 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0140 | CMAT: Oxyg scavenger leak from dearat DF | L1 LInspektion of Joint faces (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 0.7 | 1 | 0.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-09 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0150 | CMAT: Oxyg scavenger leak from dearat DF | L1 Install nye spool (weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| PRODTECH | 2024-01-09 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0160 | CMAT: Oxyg scavenger leak from dearat DF | L3 De-isolate (Prod) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-12 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0180 | CMAT: Oxyg scavenger leak from dearat DF | L3 Re-Install Heatracing and check (El) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-13 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0190 | CMAT: Oxyg scavenger leak from dearat DF | L3 Re-Install insulation (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-SCAF | 2024-01-14 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0200 | CMAT: Oxyg scavenger leak from dearat DF | L3 Demol scaff (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8 | 2 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-15 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0210 | CMAT: Oxyg scavenger leak from dearat DF | L3 Cleaning (Weld) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-SCAF | 2024-01-14 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0220 | CMAT: Oxyg scavenger leak from dearat DF | L3 Cleaning (Scaff) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-PIPF | 2024-01-15 | 2018-04-08 | WGN | 3 | V | 3. Intermediate | 2200003137 | 0230 | CMAT: Oxyg scavenger leak from dearat DF | L3 Cleaning (Lagger) | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /53/DFAA-V-3501 | DEAERATOR FOR WATER TREATMENT ON BRIDGE | DFE-3551 | 2024 | INLC | MTN-PIPF |  | DK0500014763
| MTN-INST | 2023-12-31 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0020 | Corroded Valtek Act FCV-45033 DFA | Isolate pneumatic and controls |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0030 | Corroded Valtek Act FCV-45033 DFA | Rigging assist. Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0040 | Corroded Valtek Act FCV-45033 DFA | Demount Actuator |  |  |  | 6 | 1 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0050 | Corroded Valtek Act FCV-45033 DFA | Rigging assist. Rig in/out |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0060 | Corroded Valtek Act FCV-45033 DFA | Mount new Actuator |  |  |  | 6 | 1 | 6 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-05 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0070 | Corroded Valtek Act FCV-45033 DFA | Re-build tubing if any |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-06 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0080 | Corroded Valtek Act FCV-45033 DFA | Connect Controls and pneumatic |  |  |  | 4 | 1 | 4 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-07 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0090 | Corroded Valtek Act FCV-45033 DFA | Callibration Positioner/functional test |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-07 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0100 | Corroded Valtek Act FCV-45033 DFA | Deisolate PCV |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-08 | 2019-02-18 | WGN | 4 | V | 4. Long | 2200003147 | 0110 | Corroded Valtek Act FCV-45033 DFA | Housekeeping |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-FCV-45033 | CHOKE VALVE | DFA-O15 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003149 | 0060 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 2 | 108 | 3 | 108 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /28/DFC-4-DP-050-0101-AD-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | CON-SCAF
| MTN-LAGG | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003149 | 0070 | CMAT:Scaff / Iso assists FORCE 13528 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 2 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /28/DFC-4-DP-050-0101-AD-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | CON-SCAF
| VEN-INSP | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003149 | 0080 | CMAT:Scaff / Iso assists FORCE 13528 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 2 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /28/DFC-4-DP-050-0101-AD-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | CON-SCAF
| MTN-LAGG | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003149 | 0090 | CMAT:Scaff / Iso assists FORCE 13528 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 2 | 48 | 1 | 48 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /28/DFC-4-DP-050-0101-AD-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003149 | 0100 | CMAT:Scaff / Iso assists FORCE 13528 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 2 | 72 | 3 | 72 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /28/DFC-4-DP-050-0101-AD-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | CON-SCAF
| VEN-MECH | 2024-01-10 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003150 | 0040 | Scaff / Iso assists FORCE 13515 | L3 Force insp |  |  |  | 5 | 1 | 5 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /53/DFG-26-WI-035-0009-AB-U | 26 INJECTION WATER LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-08 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003150 | 0060 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFG 1 | 60 | 3 | 60 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /53/DFG-26-WI-035-0009-AB-U | 26 INJECTION WATER LINE | NOSD |  | INLC | CON-SCAF
| MTN-LAGG | 2024-01-08 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003150 | 0070 | Scaff / Iso assists FORCE 13515 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFG 1 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /53/DFG-26-WI-035-0009-AB-U | 26 INJECTION WATER LINE | NOSD |  | INLC | CON-SCAF
| VEN-INSP | 2024-01-08 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003150 | 0080 | Scaff / Iso assists FORCE 13515 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFG 1 | 36 | 2 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /53/DFG-26-WI-035-0009-AB-U | 26 INJECTION WATER LINE | NOSD |  | INLC | CON-SCAF
| MTN-LAGG | 2024-01-08 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003150 | 0090 | Scaff / Iso assists FORCE 13515 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFG 1 | 90 | 2 | 90 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /53/DFG-26-WI-035-0009-AB-U | 26 INJECTION WATER LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-08 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003150 | 0100 | Scaff / Iso assists FORCE 13515 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFG 1 | 36 | 3 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /53/DFG-26-WI-035-0009-AB-U | 26 INJECTION WATER LINE | NOSD |  | INLC | CON-SCAF
| VEN-ELEC | 2023-12-31 | 2018-10-05 | WGN | 3 | V | 3. Intermediate | 2200003158 | 0020 | Cleaning of CPU and I/O cards SCADA | L3Cleaning of CPU and I/O cards SCADA | 2 |  |  | 15 | 1 | 15 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DA /B /04/DB-FP-2062 | FIELD PANEL SCADA RTU | DAB-OIL | DAM | INLC | MTN-TELE
| MTN-TELE | 2024-01-02 | 2018-10-05 | WGN | 3 | V | 3. Intermediate | 2200003158 | 0030 | Cleaning of CPU and I/O cards SCADA | L3 Desafing of DB-FP-2062 | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DA /B /04/DB-FP-2062 | FIELD PANEL SCADA RTU | DAB-OIL | DAM | INLC | MTN-TELE
| MTN-PIPF | 2024-01-02 | 2018-06-22 | WGN | 3 | V | 3. Intermediate | 2200003162 | 0020 | CMAT:DFF Efterfyldning af dual media fil | L3 Open the filter | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 36.2 | 2 | 36.2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3501 | DUAL MEDIA FILTER | DFF-3520 | DFF | INLC | MTN-PAIN
| MTN-SCAF | 2024-01-03 | 2018-06-22 | WGN | 3 | V | 3. Intermediate | 2200003162 | 0030 | CMAT:DFF Efterfyldning af dual media fil | L3 filling the filter | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 72.4 | 2 | 72.4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3501 | DUAL MEDIA FILTER | DFF-3520 | DFF | INLC | MTN-PAIN
| MTN-PIPF | 2024-01-13 | 2018-06-22 | WGN | 3 | V | 3. Intermediate | 2200003162 | 0040 | CMAT:DFF Efterfyldning af dual media fil | L3 Close the filter | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 36.2 | 2 | 36.2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3501 | DUAL MEDIA FILTER | DFF-3520 | DFF | INLC | MTN-PAIN
| PRODTECH | 2024-01-14 | 2018-06-22 | WGN | 3 | V | 3. Intermediate | 2200003162 | 0050 | CMAT:DFF Efterfyldning af dual media fil | L3 Desafing of DFFA-FT-3501 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3501 | DUAL MEDIA FILTER | DFF-3520 | DFF | INLC | MTN-PAIN
| PRODTECH | 2023-12-31 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003169 | 0010 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFF-04 |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290304 | LIFT GAS SHUTDOWN DFF-04 | DFF-O04 | DFF | INLC | PRODTECH
| PRODTECH | 2024-01-01 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003169 | 0020 | CMAT:ESDV / BDV-Udskifte def. manometre. | Udskift af manometer på DFFA-ESDV-290304 |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290304 | LIFT GAS SHUTDOWN DFF-04 | DFF-O04 | DFF | INLC | PRODTECH
| PRODTECH | 2024-01-02 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003169 | 0030 | CMAT:ESDV / BDV-Udskifte def. manometre. | Desafing |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290304 | LIFT GAS SHUTDOWN DFF-04 | DFF-O04 | DFF | INLC | PRODTECH
| MTN-MECH | 2023-12-31 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003170 | 0030 | CMAT:ESDV / BDV-Udskifte def. manometre. | Replace/Test DFFA-SOV-290306 | 2 |  |  | 6 | 2 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290306 | LIFT GAS SHUTDOWN DFF-06 | DFF-O06 | DFF | INLC | PRODTECH
| PRODTECH | 2024-01-01 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003170 | 0040 | CMAT:ESDV / BDV-Udskifte def. manometre. | Remove Inhibit DFFA-SOV-290306 | 2 |  |  | 1 | 2 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290306 | LIFT GAS SHUTDOWN DFF-06 | DFF-O06 | DFF | INLC | PRODTECH
| PRODTECH | 2024-01-01 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003170 | 0050 | CMAT:ESDV / BDV-Udskifte def. manometre. | De-Safing af DFF-06 | 2 |  |  | 3 | 2 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290306 | LIFT GAS SHUTDOWN DFF-06 | DFF-O06 | DFF | INLC | PRODTECH
| PRODTECH | 2023-12-31 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003171 | 0010 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFF-08 | 2 |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290308 | LIFT GAS SHUTDOWN DFF-08 | DFF-O08 | DFF | INLC | PRODTECH
| PRODTECH | 2024-01-01 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003171 | 0020 | CMAT:ESDV / BDV-Udskifte def. manometre. | Udskift af manometer på DFFA-ESDV-290308 | 2 |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290308 | LIFT GAS SHUTDOWN DFF-08 | DFF-O08 | DFF | INLC | PRODTECH
| PRODTECH | 2024-01-02 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003171 | 0030 | CMAT:ESDV / BDV-Udskifte def. manometre. | Desafing | 2 |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290308 | LIFT GAS SHUTDOWN DFF-08 | DFF-O08 | DFF | INLC | PRODTECH
| MTN-INST | 2023-12-31 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003182 | 0020 | CMAT:DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | 6 |  |  | 8 | 1 | 8 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /32/DFGA-ESDV-340016 | S/D VALVE | DFGHPSEP | DFGDEV | INLC | MTN-INST
| MTN-INST | 2024-01-02 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003182 | 0040 | CMAT:DFG Mount PRV on ESDV control panel | Test and documentation | 6 |  |  | 4 | 1 | 4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /32/DFGA-ESDV-340016 | S/D VALVE | DFGHPSEP | DFGDEV | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003183 | 0010 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-340003 | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /12/DFGA-ESDV-340003 | EMERGENCY SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | MTN-INST
| MTN-INST | 2024-01-01 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003183 | 0020 | DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | 2 |  |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /12/DFGA-ESDV-340003 | EMERGENCY SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | MTN-INST
| PRODTECH | 2024-01-03 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003183 | 0030 | DFG Mount PRV on ESDV control panel | Remove isolation |  |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /12/DFGA-ESDV-340003 | EMERGENCY SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | MTN-INST
| MTN-INST | 2024-01-04 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003183 | 0040 | DFG Mount PRV on ESDV control panel | Test and documentation |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /12/DFGA-ESDV-340003 | EMERGENCY SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003187 | 0010 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFG-HPSEP | 2 |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /20/DFGA-ESDV-340015 | SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | PRODTECH
| PRODTECH | 2024-01-02 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003187 | 0020 | CMAT:ESDV / BDV-Udskifte def. manometre. | Udskift af manometer på DFGA-ESDV-340015 | 2 |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /20/DFGA-ESDV-340015 | SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | PRODTECH
| PRODTECH | 2024-01-02 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003187 | 0021 | CMAT:ESDV / BDV-Udskifte def. manometre. | Udskift af manometer på DFGA-ESDV-340042 | 2 |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /20/DFGA-ESDV-340015 | SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | PRODTECH
| PRODTECH | 2024-01-03 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003187 | 0040 | CMAT:ESDV / BDV-Udskifte def. manometre. | Desafing |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /20/DFGA-ESDV-340015 | SHUTDOWN VALVE | DFGHPSEP | DFGDEV | INLC | PRODTECH
| PRODTECH | 2023-12-31 | 2019-01-14 | WGN | 4 | V | 4. Long | 2200003193 | 0010 | SMAT:ESDV / BDV-Udskifte def manometre(D | Safing af DAN FC LP Separator |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-ESDV-36113 | ACTUATED BALL CRUDE OIL BOOSTER PUMPS | DFCLPSEP | DFM30 | INLC | PRODTECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-01-14 | WGN | 4 | V | 4. Long | 2200003193 | 0020 | SMAT:ESDV / BDV-Udskifte def manometre(D | Udskift af manometer på DFCM-ESDV-36113 |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-ESDV-36113 | ACTUATED BALL CRUDE OIL BOOSTER PUMPS | DFCLPSEP | DFM30 | INLC | PRODTECH |  | 99000116
| PRODTECH | 2024-01-02 | 2019-01-14 | WGN | 4 | V | 4. Long | 2200003193 | 0030 | SMAT:ESDV / BDV-Udskifte def manometre(D | Desafing |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /23/DFCM-ESDV-36113 | ACTUATED BALL CRUDE OIL BOOSTER PUMPS | DFCLPSEP | DFM30 | INLC | PRODTECH |  | 99000116
| PRODTECH | 2023-12-31 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003197 | 0010 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFF-28 |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290328 | LIFT GAS SHUTDOWN DFF-28 | DFF-O28 | DWFF28 | INLC | PRODTECH
| PRODTECH | 2024-01-01 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003197 | 0020 | CMAT:ESDV / BDV-Udskifte def. manometre. | Udskift af manometer på DFFA-ESDV-290328 |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290328 | LIFT GAS SHUTDOWN DFF-28 | DFF-O28 | DWFF28 | INLC | PRODTECH
| PRODTECH | 2024-01-02 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003197 | 0030 | CMAT:ESDV / BDV-Udskifte def. manometre. | Desafing |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290328 | LIFT GAS SHUTDOWN DFF-28 | DFF-O28 | DWFF28 | INLC | PRODTECH
| PRODTECH | 2023-12-31 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003198 | 0010 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFF-29 |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290329 | LIFT GAS SHUTDOWN DFF-29 | DFF-O29 | DWFF29 | INLC | PRODTECH
| PRODTECH | 2024-01-01 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003198 | 0020 | CMAT:ESDV / BDV-Udskifte def. manometre. | Udskift af manometer på DFFA-ESDV-290329 |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290329 | LIFT GAS SHUTDOWN DFF-29 | DFF-O29 | DWFF29 | INLC | PRODTECH
| PRODTECH | 2024-01-02 | 2019-01-15 | WGN | 4 | V | 4. Long | 2200003198 | 0030 | CMAT:ESDV / BDV-Udskifte def. manometre. | Desafing |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /37/DFFA-ESDV-290329 | LIFT GAS SHUTDOWN DFF-29 | DFF-O29 | DWFF29 | INLC | PRODTECH
| MTN-INST | 2023-12-31 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003227 | 0020 | CMAT:DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | 2 |  |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /34/DFGA-ESDV-380140 | WET GAS FROM HBB (HIPPS) | DHDLPGAS | HN3DFG | INLC | MTN-INST
| PRODTECH | 2024-01-02 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003227 | 0030 | CMAT:DFG Mount PRV on ESDV control panel | Remove isolation | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /34/DFGA-ESDV-380140 | WET GAS FROM HBB (HIPPS) | DHDLPGAS | HN3DFG | INLC | MTN-INST
| MTN-INST | 2024-01-03 | 2018-03-29 | WGN | 3 | V | 3. Intermediate | 2200003227 | 0040 | CMAT:DFG Mount PRV on ESDV control panel | Test and documentation | 2 |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /34/DFGA-ESDV-380140 | WET GAS FROM HBB (HIPPS) | DHDLPGAS | HN3DFG | INLC | MTN-INST
| MTN-SCAF | 2024-01-09 | 2019-03-20 | WGN | 3 |  | 3. Intermediate | 2200003246 | 0010 | Scaff Assist to Force 5027 | L3 Create permit. | Pre Covid 2020 campaign |  |  | 32 | 1 | 58 | 26 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /28/DFF-3-DO-050-8101-AB-U | 3 OPEN DRAIN LINE | NOSD |  | INT | CON-SCAF
| VEN-MECH | 2024-01-09 | 2019-03-20 | WGN | 3 |  | 3. Intermediate | 2200003246 | 0040 | Scaff Assist to Force 5027 | L3 Force insp |  |  |  | 13 | 1 | 13 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /28/DFF-3-DO-050-8101-AB-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-09 | 2019-03-20 | WGN | 3 |  | 3. Intermediate | 2200003246 | 0060 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 10 | 36 | 3 | 36 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /28/DFF-3-DO-050-8101-AB-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | CON-SCAF
| VEN-INSP | 2024-01-09 | 2019-03-20 | WGN | 3 |  | 3. Intermediate | 2200003246 | 0070 | Scaff Assist to Force 5027 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 10 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /28/DFF-3-DO-050-8101-AB-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | CON-SCAF
| MTN-SCAF | 2024-01-09 | 2019-03-20 | WGN | 3 |  | 3. Intermediate | 2200003246 | 0080 | Scaff Assist to Force 5027 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 10 | 18 | 3 | 18 | 0 | APPR RDBL | APPR OPND | REL PCNF CSER MANC NMAT PRC SETC | DF /F /28/DFF-3-DO-050-8101-AB-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | CON-SCAF
| PRODTECH | 2023-12-31 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0020 | CMAT:Replacem. of valves during V-5012 P | L3 Safing of the valves (only if further | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-03 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0030 | CMAT:Replacem. of valves during V-5012 P | L3 Rigging assistance for replacement of | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 61 | 2 | 61 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-03 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0050 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of HCV-50082 | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-04 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0070 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of HCV-50080 | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-04 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0080 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of HCV-50084 | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-05 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0090 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of HCV-50085 | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-05 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0100 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of HCV-50086 | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-06 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0105 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of HCV-50012 | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-06 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0110 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of 2" vent valve | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-06 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0120 | CMAT:Replacem. of valves during V-5012 P | L2 Replacement of 2" valves (ball and ch | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 4.7 | 2 | 4.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-07 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003249 | 0130 | CMAT:Replacem. of valves during V-5012 P | L2 Desafing and leak test | 2 |  | 2022 Budget File - No ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /28/DFAA-V-5012 | WELLHEAD CLOSSED DRAINS VESSEL | DFA-OIL | TMM | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0020 | SMAT:Replacem valves during V-5022 PVI | L3 Safing of the valves (only if further | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-SCAF | 2024-01-03 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0030 | SMAT:Replacem valves during V-5022 PVI | L3 Rigging assistance for replacement of | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 61 | 2 | 61 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-03 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0050 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of HCV-50090 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-04 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0070 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of HCV-50088 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-04 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0080 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of HCV-50097 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-05 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0090 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of HCV-50096 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-05 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0100 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of 2" HCV-50092 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-05 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0105 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of 2" check valve | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 2 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-06 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0110 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of HCV-50094 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-PIPF | 2024-01-06 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0111 | SMAT:Replacem valves during V-5022 PVI | L2 Replacement of HCV-500014 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| PRODTECH | 2024-01-07 | 2018-09-12 | WGN | 3 | V | 3. Intermediate | 2200003250 | 0120 | SMAT:Replacem valves during V-5022 PVI | L2 Desafing and leak test | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 7 | 2 | 7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-V-5022 | WELLHEAD CLOSSED DRAINS VESSEL | DFB-OIL | TMM | INLC | MTN-PIPF
| MTN-SCAF | 2023-12-31 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0010 | CMAT:BOAT, Udskift af afspæringsventil f | Byg overbord stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 60.3 | 3 | 60.3 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-05 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0020 | CMAT:BOAT, Udskift af afspæringsventil f | Etablering overbord tryktelt | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 60.3 | 3 | 60.3 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| VEN-ELEC | 2024-01-10 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0030 | CMAT:BOAT, Udskift af afspæringsventil f | Install lys, byggestrøm, overtryk i telt | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 20.1 | 1 | 20.1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-15 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0050 | CMAT:BOAT, Udskift af afspæringsventil f | Utæt afspærrings HCV for ESDV-380014 sav | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-16 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0060 | CMAT:BOAT, Udskift af afspæringsventil f | Ny HCV svejses +100% NDT/Penetrant | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 40.2 | 1 | 40.2 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-PIPF | 2024-01-20 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0070 | CMAT:BOAT, Udskift af afspæringsventil f | Tryktest spool spec. ES | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| VEN-ELEC | 2024-01-23 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0090 | CMAT:BOAT, Udskift af afspæringsventil f | Demoll lys, byggestrøm, overtryk i telt | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 20.1 | 1 | 20.1 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-25 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0100 | CMAT:BOAT, Udskift af afspæringsventil f | Demoll overbord tryktelt | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 30.2 | 3 | 30.2 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-SCAF | 2024-01-28 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0110 | CMAT:BOAT, Udskift af afspæringsventil f | Demoll overbord stillads | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 30.2 | 3 | 30.2 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| MTN-LAGG | 2024-01-08 | 2021-03-28 | WGN | 3 |  | 3. Intermediate | 2200006293 | 0020 | Insulation assits FORCE 15879 | Remove insulation |  |  | 2022 WTW - PIPE INSP DFG 2 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL CSER MANC NMAT PRC SETC | DF /G /28/DFG-2-DOS-050-0170-AB-T | 2 OPEN DRAIN SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-ELEC | 2024-01-09 | 2021-03-28 | WGN | 3 |  | 3. Intermediate | 2200006293 | 0030 | Insulation assits FORCE 15879 | Remove heattracing |  |  | 2022 WTW - PIPE INSP DFG 2 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL CSER MANC NMAT PRC SETC | DF /G /28/DFG-2-DOS-050-0170-AB-T | 2 OPEN DRAIN SOUR LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-11 | 2021-03-28 | WGN | 3 |  | 3. Intermediate | 2200006293 | 0035 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFG 2 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL CSER MANC NMAT PRC SETC | DF /G /28/DFG-2-DOS-050-0170-AB-T | 2 OPEN DRAIN SOUR LINE | NOSD |  | INT | CON-LAGG
| MTN-ELEC | 2024-01-11 | 2021-03-28 | WGN | 3 |  | 3. Intermediate | 2200006293 | 0040 | Insulation assits FORCE 15879 | Reinstall heattracing+test |  |  | 2022 WTW - PIPE INSP DFG 2 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL CSER MANC NMAT PRC SETC | DF /G /28/DFG-2-DOS-050-0170-AB-T | 2 OPEN DRAIN SOUR LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-08 | 2021-05-23 | WGN | 3 |  | 3. Intermediate | 2200006799 | 0020 | scaffold assits FORCE 21768 | Build scaffolding |  |  | 2022 WTW - PIPE INSP DFC 3 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-2-DO-050-0802-B-U | 2 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2021-05-23 | WGN | 3 |  | 3. Intermediate | 2200006799 | 0022 | scaffold assits FORCE 21768 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 3 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-2-DO-050-0802-B-U | 2 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-10 | 2021-05-23 | WGN | 3 |  | 3. Intermediate | 2200006799 | 0030 | scaffold assits FORCE 21768 | Remove scaffolding |  |  | 2022 WTW - PIPE INSP DFC 3 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-2-DO-050-0802-B-U | 2 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009212 | 0020 | Insulation assits FORCE 16322 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFA 1 | 6 | 1 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /28/DFA-2-DPS-050-4051-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009212 | 0030 | Insulation assits FORCE 16322 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFA 1 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /28/DFA-2-DPS-050-4051-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009212 | 0035 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFA 1 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /28/DFA-2-DPS-050-4051-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-10 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009212 | 0040 | Insulation assits FORCE 16322 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFA 1 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /28/DFA-2-DPS-050-4051-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009212 | 0050 | Insulation assits FORCE 16322 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFA 1 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /28/DFA-2-DPS-050-4051-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009214 | 0020 | Insulation assist FORCE 16210 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFA 3 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /70/DFA-2-GFS-057-4023-BD-T | 2 FUEL GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-09 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009214 | 0030 | Insulation assist FORCE 16210 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFA 3 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /70/DFA-2-GFS-057-4023-BD-T | 2 FUEL GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-12 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009214 | 0035 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFA 3 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /70/DFA-2-GFS-057-4023-BD-T | 2 FUEL GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-12 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009214 | 0040 | Insulation assist FORCE 16210 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFA 3 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /70/DFA-2-GFS-057-4023-BD-T | 2 FUEL GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-16 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009214 | 0050 | Insulation assist FORCE 16210 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFA 3 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /70/DFA-2-GFS-057-4023-BD-T | 2 FUEL GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009215 | 0020 | Insulation assist bilfinger 20861 | INSTALL SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFB 1 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-PHS-038-0864-AB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009215 | 0030 | Insulation assist bilfinger 20861 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFB 1 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-PHS-038-0864-AB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-14 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009215 | 0035 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFB 1 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-PHS-038-0864-AB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-15 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009215 | 0040 | Insulation assist bilfinger 20861 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFB 1 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-PHS-038-0864-AB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-16 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009215 | 0050 | Insulation assist bilfinger 20861 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFB 1 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-PHS-038-0864-AB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009216 | 0020 | Insulation assist Bilfinger 20860 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFB 2 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-WOS-050-4135-AD-F | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-10 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009216 | 0025 | Insulation assist Bilfinger 20860 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFB 2 | 18 | 2 | 18 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-WOS-050-4135-AD-F | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009216 | 0030 | Insulation assist Bilfinger 20860 | MOUNT INSULATION |  |  | 2022 WTW - PIPE INSP DFB 2 | 36 | 1 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /27/DFB-6-WOS-050-4135-AD-F | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009217 | 0020 | Insulation assits FORCE 9547 | Remove Insulation |  |  | 2022 WTW - PIPE INSP DFB 3 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /28/DFB-3-DP-050-0902-B5-F | 3 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009217 | 0022 | Insulation assits FORCE 9547 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFB 3 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /28/DFB-3-DP-050-0902-B5-F | 3 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009217 | 0030 | Insulation assits FORCE 9547 | Reinstall insulation |  |  | 2022 WTW - PIPE INSP DFB 3 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /28/DFB-3-DP-050-0902-B5-F | 3 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009219 | 0020 | Insulation assist FORCE 16151 | BUILD SCAF |  |  | 2022 WTW - PIPE INSP DFB 5 | 2 | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /55/DFB-6-WI-035-9038-FC-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009219 | 0030 | Insulation assist FORCE 16151 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFB 5 | 6 | 1 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /55/DFB-6-WI-035-9038-FC-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009219 | 0035 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFB 5 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /55/DFB-6-WI-035-9038-FC-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009219 | 0040 | Insulation assist FORCE 16151 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFB 5 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /55/DFB-6-WI-035-9038-FC-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-10 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009219 | 0050 | Insulation assist FORCE 16151 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFB 5 | 2 | 2 | 2 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /55/DFB-6-WI-035-9038-FC-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0020 | Insulation assist FORCE 19002 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 4 | 48 | 4 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0030 | Insulation assist FORCE 19002 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 4 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-11 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0040 | Insulation assist FORCE 19002 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 4 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-14 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0045 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 4 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-15 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0050 | Insulation assist FORCE 19002 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 4 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-19 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0060 | Insulation assist FORCE 19002 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 4 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-20 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009220 | 0070 | Insulation assist FORCE 19002 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 4 | 36 | 4 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /01/DFC-3-WF-003-0047-A3-F | 3 FIREWATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009222 | 0020 | Insulation assist FORCE 20023 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 6 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | MTN-LAGG
| MTN-LAGG | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009222 | 0025 | Insulation assist FORCE 20023 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 6 | 3 | 2 | 3 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | MTN-LAGG
| MTN-LAGG | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009222 | 0030 | Insulation assist FORCE 20023 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 6 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-10-WOS-050-9031-AB-U | 10 PRODUCED WATER LINE | NOSD |  | INLC | MTN-LAGG
| MTN-SCAF | 2024-01-08 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0020 | Insulation assist bilfinger 19728 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 8 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0030 | Insulation assist bilfinger 19728 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 8 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-12 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0040 | Insulation assist bilfinger 19728 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 8 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0045 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 8 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0050 | Insulation assist bilfinger 19728 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 8 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-19 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0060 | Insulation assist bilfinger 19728 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 8 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-22 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009224 | 0070 | Insulation assist bilfinger 19728 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 8 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AD-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009225 | 0020 | Insulation assits FORCE 14246 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 9 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-6-WOS-050-9035-AB-U | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009225 | 0030 | Insulation assits FORCE 14246 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 9 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-6-WOS-050-9035-AB-U | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-11 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009225 | 0032 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 9 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-6-WOS-050-9035-AB-U | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-12 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009225 | 0040 | Insulation assits FORCE 14246 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 9 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-6-WOS-050-9035-AB-U | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-16 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009225 | 0050 | Insulation assits FORCE 14246 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 9 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-6-WOS-050-9035-AB-U | 6 PRODUCED WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0020 | Insulation assits FORCE 15245 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 11 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0030 | Insulation assits FORCE 15245 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 11 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-15 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0040 | Insulation assits FORCE 15245 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 11 | 1 | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-15 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0042 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 11 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-16 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0050 | Insulation assits FORCE 15245 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFC 11 | 2 | 1 | 2 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-17 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0060 | Insulation assits FORCE 15245 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 11 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-18 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009227 | 0070 | Insulation assits FORCE 15245 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 11 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-4-DP-050-0101-B5-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009228 | 0020 | Insulation assist Bilfinger 20808 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 12 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-8-DO-050-0556-AA-U | 8 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-08 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009228 | 0025 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 12 | 6 | 1 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-8-DO-050-0556-AA-U | 8 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-09 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009228 | 0030 | Insulation assist Bilfinger 20808 | REMOVE HEATTRACING |  |  | 2022 WTW - PIPE INSP DFC 12 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-8-DO-050-0556-AA-U | 8 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-10 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009228 | 0040 | Insulation assist Bilfinger 20808 | INSTALL HEATTRACING |  |  | 2022 WTW - PIPE INSP DFC 12 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-8-DO-050-0556-AA-U | 8 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009228 | 0050 | Insulation assist Bilfinger 20808 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 12 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-8-DO-050-0556-AA-U | 8 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0020 | Insulation assist bilfinger 20867 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFE 1 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0030 | Insulation assist bilfinger 20867 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFE 1 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-12 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0040 | Insulation assist bilfinger 20867 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFE 1 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0045 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFE 1 | 9 | 2 | 9 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0050 | Insulation assist bilfinger 20867 | INSTALL HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFE 1 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-19 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0060 | Insulation assist bilfinger 20867 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFE 1 | 36 | 1 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-23 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009229 | 0070 | Insulation assist bilfinger 20867 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFE 1 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /55/DFE-6-WI-035-5011-FE-U | 6 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009235 | 0020 | Insulation assist bilfinger 22075 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 16 | 6 | 1 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /27/DFF-3-DO-050-8071-AD-T | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-08 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009235 | 0022 | Insulation assist bilfinger 22075 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 16 | 3 | 2 | 3 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /27/DFF-3-DO-050-8071-AD-T | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-09 | WGN | 4 | S | 4. Long | 2200009235 | 0030 | Insulation assist bilfinger 22075 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 16 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /27/DFF-3-DO-050-8071-AD-T | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009236 | 0020 | Insulation assist bilfinger 20864 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 17 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7666-AB-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009236 | 0030 | Insulation assist bilfinger 20864 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 17 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7666-AB-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-12 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009236 | 0035 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 17 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7666-AB-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-12 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009236 | 0040 | Insulation assist bilfinger 20864 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 17 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7666-AB-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009236 | 0050 | Insulation assist bilfinger 20864 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 17 | 18 | 2 | 18 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-2-DPS-050-7666-AB-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009237 | 0020 | Insulation assist FORCE 19490 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 18 | 8 | 1 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8001-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009237 | 0030 | Insulation assist FORCE 19490 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFF 18 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8001-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-11 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009237 | 0035 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 18 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8001-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-12 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009237 | 0040 | Insulation assist FORCE 19490 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFF 18 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8001-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-16 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009237 | 0050 | Insulation assist FORCE 19490 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 18 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8001-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-07 | WGN | 4 | V | 4. Long | 2200009238 | 0020 | Insulation assist bilfinger 22392 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 19 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /32/DFF-16-GPS-044-7004-EB-U | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | MTN-LAGG
| MTN-LAGG | 2024-01-09 | 2022-07-07 | WGN | 4 | V | 4. Long | 2200009238 | 0022 | Insulation assist bilfinger 22392 | Bilfinger |  |  | 2022 WTW - PIPE INSP DFF 19 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /32/DFF-16-GPS-044-7004-EB-U | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | MTN-LAGG
| MTN-LAGG | 2024-01-09 | 2022-07-07 | WGN | 4 | V | 4. Long | 2200009238 | 0030 | Insulation assist bilfinger 22392 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 19 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /32/DFF-16-GPS-044-7004-EB-U | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | MTN-LAGG
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009240 | 0020 | Insulation assits FORCE 20654 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 21 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /54/DFF-16-WI-035-7003-AD-U | 16 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009240 | 0030 | Insulation assits FORCE 20654 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 21 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /54/DFF-16-WI-035-7003-AD-U | 16 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-15 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009240 | 0035 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 21 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /54/DFF-16-WI-035-7003-AD-U | 16 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-16 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009240 | 0040 | Insulation assits FORCE 20654 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 21 | 36 | 1 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /54/DFF-16-WI-035-7003-AD-U | 16 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-20 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009240 | 0050 | Insulation assits FORCE 20654 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 21 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /54/DFF-16-WI-035-7003-AD-U | 16 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009242 | 0020 | Insulation assist FORCE 14378 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 23 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7031-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009242 | 0030 | Insulation assist FORCE 14378 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 23 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7031-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-16 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009242 | 0032 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 23 | 18 | 2 | 18 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7031-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-17 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009242 | 0040 | Insulation assist FORCE 14378 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 23 | 48 | 1 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7031-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-22 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009242 | 0050 | Insulation assist FORCE 14378 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 23 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7031-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009243 | 0020 | Insulation assist bilfinger 21918 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 24 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7101-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009243 | 0022 | Insulation assist bilfinger 21918 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 24 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7101-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-09 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009243 | 0030 | Insulation assist bilfinger 21918 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 24 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7101-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009245 | 0020 | Insulation assist FORCE 15795 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 26 | 144 | 4 | 144 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7141-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INST
| MTN-LAGG | 2024-01-17 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009245 | 0030 | Insulation assist FORCE 15795 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 26 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7141-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INST
| VEN-INST | 2024-01-19 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009245 | 0035 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 26 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7141-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INST
| MTN-LAGG | 2024-01-20 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009245 | 0040 | Insulation assist FORCE 15795 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 26 | 36 | 1 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7141-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INST
| MTN-SCAF | 2024-01-23 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009245 | 0050 | Insulation assist FORCE 15795 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 26 | 96 | 4 | 96 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7141-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INST
| MTN-SCAF | 2024-01-08 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009248 | 0020 | Insulation assist bilfinger 21528 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 29 | 96 | 4 | 96 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7311-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009248 | 0030 | Insulation assist bilfinger 21528 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 29 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7311-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-16 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009248 | 0033 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 29 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7311-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-17 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009248 | 0040 | Insulation assist bilfinger 21528 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 29 | 48 | 1 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7311-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-22 | 2022-07-13 | WGN | 4 | V | 4. Long | 2200009248 | 0050 | Insulation assist bilfinger 21528 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 29 | 48 | 4 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /55/DFF-6-PHS-030-7311-GF-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0020 | Insulation assist bilfinger 20976 | Build Scaffolding |  |  | 2022 WTW - PIPE INSP DFG 3 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-11 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0030 | Insulation assist bilfinger 20976 | Remove heattracing |  |  | 2022 WTW - PIPE INSP DFG 3 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-14 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0040 | Insulation assist bilfinger 20976 | Remove insulation |  |  | 2022 WTW - PIPE INSP DFG 3 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-15 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0045 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFG 3 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-15 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0050 | Insulation assist bilfinger 20976 | Reinstall+test heattracing |  |  | 2022 WTW - PIPE INSP DFG 3 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-19 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0060 | Insulation assist bilfinger 20976 | Reinstall insulation |  |  | 2022 WTW - PIPE INSP DFG 3 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-22 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009252 | 0070 | Insulation assist bilfinger 20976 | Remove scaffolding |  |  | 2022 WTW - PIPE INSP DFG 3 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /11/DFG-6-GPS-034-0008-AB-T | 6 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-08 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009256 | 0020 | Insulation assist bilfinger 20975 | Remove insulation |  |  | 2022 WTW - PIPE INSP DFG 7 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /32/DFG-26-GPS-043-0009-DD-A | 26 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-10 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009256 | 0025 | Insulation assist bilfinger 20975 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFG 7 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /32/DFG-26-GPS-043-0009-DD-A | 26 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-11 | 2022-07-09 | WGN | 4 | V | 4. Long | 2200009256 | 0030 | Insulation assist bilfinger 20975 | Install insulation |  |  | 2022 WTW - PIPE INSP DFG 7 | 36 | 1 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /G /32/DFG-26-GPS-043-0009-DD-A | 26 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009353 | 0020 | FORCE assistance 20558 | SANDBLASTING |  |  | 2022 WTW - PIPE INSP DFA 4 | 20 | 2 | 20 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /10/DFA-6-PHS-030-4052-FE-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009353 | 0030 | FORCE assistance 20558 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFA 4 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /10/DFA-6-PHS-030-4052-FE-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-09 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009353 | 0040 | FORCE assistance 20558 | PRIME/MALE |  |  | 2022 WTW - PIPE INSP DFA 4 | 37 | 2 | 37 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /10/DFA-6-PHS-030-4052-FE-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009354 | 0012 | sandblasting assists FORCE 8757 | SANDBLASTNING |  |  | 2022 WTW - PIPE INSP DFA 5 | 20 | 2 | 20 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /12/DFA-6-PT-033-0612-C2-U | 6 TEST WELLHEAD LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009354 | 0018 | sandblasting assists FORCE 8757 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFA 5 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /12/DFA-6-PT-033-0612-C2-U | 6 TEST WELLHEAD LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009354 | 0020 | sandblasting assists FORCE 8757 | PAINT/PRIME |  |  | 2022 WTW - PIPE INSP DFA 5 | 37 | 2 | 37 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /12/DFA-6-PT-033-0612-C2-U | 6 TEST WELLHEAD LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009355 | 0020 | Paint assist FORCE 16266 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFA 6 | 20 | 2 | 20 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /54/DFA-12-WI-035-9012-AB-U | 12 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-10 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009355 | 0025 | Paint assist FORCE 16266 | SANDBLAST |  |  | 2022 WTW - PIPE INSP DFA 6 | 20 | 2 | 20 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /54/DFA-12-WI-035-9012-AB-U | 12 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-11 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009355 | 0027 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFA 6 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /54/DFA-12-WI-035-9012-AB-U | 12 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-12 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009355 | 0030 | Paint assist FORCE 16266 | PAINT/PRIME |  |  | 2022 WTW - PIPE INSP DFA 6 | 37 | 2 | 37 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /54/DFA-12-WI-035-9012-AB-U | 12 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-14 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009355 | 0040 | Paint assist FORCE 16266 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFA 6 | 10 | 2 | 10 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /54/DFA-12-WI-035-9012-AB-U | 12 INJECTION WATER LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009356 | 0020 | sandblasting assists FORCE 15634 | SANDBLASTNING |  |  | 2022 WTW - PIPE INSP DFB 6 | 33 | 2 | 33 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /31/DFB-10-PH-038-0855-C2-U | 10 HIGH PRESS WELL LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-09 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009356 | 0022 | sandblasting assists FORCE 15634 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFB 6 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /31/DFB-10-PH-038-0855-C2-U | 10 HIGH PRESS WELL LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-10 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009356 | 0030 | sandblasting assists FORCE 15634 | PRIME/PAINTING |  |  | 2022 WTW - PIPE INSP DFB 6 | 30 | 2 | 30 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /31/DFB-10-PH-038-0855-C2-U | 10 HIGH PRESS WELL LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 | S | 4. Long | 2200009357 | 0020 | Sandblasting assist FORCE 21054 | BUILD SCAFOLDING |  |  | 2022 WTW - PIPE INSP DFC 13 | 336 | 4 | 336 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-3-DO-050-0317-B-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INST
| MTN-PAIN | 2024-01-29 | 2022-07-08 | WGN | 4 | S | 4. Long | 2200009357 | 0030 | Sandblasting assist FORCE 21054 | SANDBLASTNING |  |  | 2022 WTW - PIPE INSP DFC 13 | 20 | 1 | 20 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-3-DO-050-0317-B-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INST
| VEN-INST | 2024-01-31 | 2022-07-08 | WGN | 4 | S | 4. Long | 2200009357 | 0032 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 13 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-3-DO-050-0317-B-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INST
| MTN-PAIN | 2024-01-31 | 2022-07-08 | WGN | 4 | S | 4. Long | 2200009357 | 0033 | Sandblasting assist FORCE 21054 | PRIME/PAINT |  |  | 2022 WTW - PIPE INSP DFC 13 | 37 | 1 | 37 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-3-DO-050-0317-B-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INST
| MTN-SCAF | 2024-02-04 | 2022-07-08 | WGN | 4 | S | 4. Long | 2200009357 | 0040 | Sandblasting assist FORCE 21054 | REMOVE SCAFFOLDIGN |  |  | 2022 WTW - PIPE INSP DFC 13 | 200 | 4 | 200 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /28/DFC-3-DO-050-0317-B-U | 3 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INST
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009358 | 0020 | sandblasting assists FORCE 19755 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 33 | 36 | 3 | 36 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /31/DFF-16-GPS-043-7003-DB-P | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-11 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009358 | 0030 | sandblasting assists FORCE 19755 | Sandblastning,prime |  |  | 2022 WTW - PIPE INSP DFF 33 | 20 | 1 | 20 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /31/DFF-16-GPS-043-7003-DB-P | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-13 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009358 | 0035 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 33 | 72 | 2 | 72 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /31/DFF-16-GPS-043-7003-DB-P | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-PAIN | 2024-01-16 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009358 | 0037 | sandblasting assists FORCE 19755 | prime,touch up |  |  | 2022 WTW - PIPE INSP DFF 33 | 37 | 1 | 37 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /31/DFF-16-GPS-043-7003-DB-P | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-20 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009358 | 0040 | sandblasting assists FORCE 19755 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 33 | 24 | 3 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /31/DFF-16-GPS-043-7003-DB-P | 16 PROCESS GAS SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009372 | 0020 | Scaff Assits FORCE 20683 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFB 7 | 48 | 2 | 48 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /10/DFB-6-PHS-030-4010-FB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-14 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009372 | 0025 | Scaff Assits FORCE 20683 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFB 7 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /10/DFB-6-PHS-030-4010-FB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-14 | 2022-07-08 | WGN | 4 |  | 4. Long | 2200009372 | 0030 | Scaff Assits FORCE 20683 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFB 7 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /10/DFB-6-PHS-030-4010-FB-U | 6 HIGH PRESS WELL SOUR LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0020 | Insulation assist FORCE 19492 | BUILD SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 34 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-MECH | 2024-01-08 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0025 | Insulation assist FORCE 19492 | Remove grating |  |  | 2022 WTW - PIPE INSP DFF 34 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-10 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0030 | Insulation assist FORCE 19492 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFF 34 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-11 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0040 | Insulation assist FORCE 19492 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFF 34 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| VEN-INSP | 2024-01-14 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0045 | Insulation assist FORCE 19492 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFF 34 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-ELEC | 2024-01-15 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0050 | Insulation assist FORCE 19492 | REMOVE HEAT TRACING |  |  | 2022 WTW - PIPE INSP DFF 34 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-LAGG | 2024-01-19 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0060 | Insulation assist FORCE 19492 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFF 34 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-MECH | 2024-01-21 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0065 | Insulation assist FORCE 19492 | Mounting grating |  |  | 2022 WTW - PIPE INSP DFF 34 | 8 | 2 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-22 | 2022-07-07 | WGN | 4 |  | 4. Long | 2200009373 | 0070 | Insulation assist FORCE 19492 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFF 34 | 3 | 2 | 3 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /28/DFF-4-DO-050-8015-AB-T | 4 OPEN DRAIN LINE | NOSD |  | INLC | VEN-INSP
| MTN-SCAF | 2024-01-08 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0020 | Insulation assist Bilfinger 19727 | INSTALL SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 14 | 24 | 2 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-11 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0030 | Insulation assist Bilfinger 19727 | REMOVE INSULATION |  |  | 2022 WTW - PIPE INSP DFC 14 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-ELEC | 2024-01-12 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0040 | Insulation assist Bilfinger 19727 | REMOVE HEATTRACING |  |  | 2022 WTW - PIPE INSP DFC 14 | 12 | 1 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| VEN-INSP | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0045 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 2022 WTW - PIPE INSP DFC 14 | 6 | 2 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-ELEC | 2024-01-15 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0050 | Insulation assist Bilfinger 19727 | INSTALL HEATTRACING |  |  | 2022 WTW - PIPE INSP DFC 14 | 16 | 1 | 16 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-LAGG | 2024-01-19 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0060 | Insulation assist Bilfinger 19727 | INSTALL INSULATION |  |  | 2022 WTW - PIPE INSP DFC 14 | 24 | 1 | 24 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-SCAF | 2024-01-22 | 2022-07-09 | WGN | 4 | I | 4. Long | 2200009396 | 0070 | Insulation assist Bilfinger 19727 | REMOVE SCAFFOLDING |  |  | 2022 WTW - PIPE INSP DFC 14 | 12 | 2 | 12 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /27/DFC-4-WOS-050-4099-AB-T | 4 PRODUCED WATER LINE | NOSD |  | INLC | CON-LAGG
| MTN-MECH | 2024-04-27 | 2026-10-14 | WGN | 4 | V | 4. Long | 2200014660 | 0010 | CHG2958908 - Incorrect batch number 4 | CHG2958908 - Incorrect batch number 4 |  |  |  | 2 | 1 | 2 | 0 | APPR WMAT RDBL | APPR OPND | REL MACM PRC SETC | DA /B /01/DB-FT-0400 | INLINE FILTER | NOSD |  | INLC | MTN-MECH
| VEN-COMM | 2024-07-01 | 2019-11-09 | WRO | 4 | V | 4. Long | 2300000926 | 0010 | ESD SW for DFBWID2 | ESD SW for DFBWID2 | 2020 Project |  |  | 36 | 1 | 36 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0208A | ESD PANEL | NE | DFBWID2 | INLC | MTN-TELE
| MTN-TELE | 2024-07-04 | 2019-11-09 | WRO | 4 | V | 4. Long | 2300000926 | 0020 | ESD SW for DFBWID2 | Telecom support | 2020 Project |  |  | 15 | 1 | 15 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0208A | ESD PANEL | NE | DFBWID2 | INLC | MTN-TELE
| VEN-COMM | 2024-07-01 | 2019-11-09 | WRO | 4 | V | 4. Long | 2300000927 | 0010 | F&G SW for DFBWID2 | F&G SW for DFBWID2 | 2020 Project |  |  | 24 | 1 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0108 | PANELER FOR FIRE AND GAS SYSTEM | NE | DFBWID2 | INLC | MTN-TELE
| MTN-TELE | 2024-07-03 | 2019-11-09 | WRO | 4 | V | 4. Long | 2300000927 | 0020 | F&G SW for DFBWID2 | Telecom support | 2020 Project |  |  | 10 | 0 | 10 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0108 | PANELER FOR FIRE AND GAS SYSTEM | NE | DFBWID2 | INLC | MTN-TELE
| VEN-COMM | 2024-04-03 | 2019-11-17 | WRO | 4 | V | 4. Long | 2300000931 | 0010 | F&G SW for DFDCOM | F&G SW for DFDCOM | 2 |  |  | 24 | 1 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/DFCI-FP-0136 | FIRE AND GAS PANEL | NE | DFDCOM | INLC | MTN-TELE
| MTN-TELE | 2024-04-05 | 2019-11-17 | WRO | 4 | V | 4. Long | 2300000931 | 0020 | F&G SW for DFDCOM | Telecom support | 2 |  | Gregor | 10 | 1 | 10 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/DFCI-FP-0136 | FIRE AND GAS PANEL | NE | DFDCOM | INLC | MTN-TELE
| MTN-TELE | 2024-05-16 | 2020-07-06 | WRO | 4 | V | 4. Long | 2300000939 | 0010 | Range change DFRODS1 DFF-FIT-500435 | Range change DFRODS1 FIT-500435 | 2 |  | E&C: DFRODS1 - Flow meter | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /04/DFFA-FP-2093 | SCADA RTU | DFFHPSEP | DFRODS1 | INLC | MTN-TELE |  | 99000002
| MTN-TELE | 2024-05-16 | 2020-07-06 | WRO | 4 | V | 4. Long | 2300000939 | 0020 | Range change DFRODS1 DFF-FIT-500435 | Telecom support | 2 |  | E&C: DFRODS1 - Flow meter | 3 | 0 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /04/DFFA-FP-2093 | SCADA RTU | DFFHPSEP | DFRODS1 | INLC | MTN-TELE |  | 99000002
| MTN-SCAF | 2025-01-18 | 2020-03-10 | WPM | C | V | Business Critical | 2400050237 | 0020 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 67 | 2 | 67 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-V-5019 | TEST SAND REMOVAL VESSEL | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-SCAF | 2025-01-27 | 2020-03-10 | WPM | C | V | Business Critical | 2400050237 | 0040 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 2 |  | ¦10/01/2022 Wrk. Ctr. Migration | 33.5 | 2 | 33.5 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-V-5019 | TEST SAND REMOVAL VESSEL | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-MECH | 2023-12-31 | 2020-05-07 | WPM | B | V | Safety & Env.Related | 2400051631 | 0010 | 1Y FW RINGMAIN INSTRUMENTER, ALLE PLTF | 1Y FW RINGMAIN INSTRUMENTER, ALLE PLTF | 5 |  |  | 8 | 1 | 8 | 0 | APPR CMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-02 | 2020-05-07 | WPM | B | V | Safety & Env.Related | 2400051631 | 0012 | 1Y FW RINGMAIN INSTRUMENTER, ALLE PLTF | 1Y FW RINGMAIN INSTRUMENTER, ALLE PLTF | 5 |  |  | 8 | 1 | 8 | 0 | APPR CMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2020-05-07 | WPM | B | V | Safety & Env.Related | 2400051631 | 0014 | 1Y FW RINGMAIN INSTRUMENTER, ALLE PLTF | De-isolation | 5 |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-06-15 | 2020-04-12 | WPM | C | V | Business Critical | 2400052075 | 0010 | 3Y PIG LAUNCHER DAN B, WI. | 3Y-DFFA-EP-3804 | 5 |  |  | 6.5 | 1 | 6.5 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /34 | TRANSFER | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-INST | 2024-06-16 | 2020-04-12 | WPM | C | V | Business Critical | 2400052075 | 0012 | 3Y PIG LAUNCHER DAN B, WI. | 3Y-DFFA-EP-3804 | 5 |  |  | 2 | 1 | 2 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /34 | TRANSFER | NOSD |  | INLC | MTN-MECH |  | 99000142
| VEN-MECH | 2024-04-01 | 2018-12-31 | WPM | D | V | Non Critical | 2400053825 | 0010 | 3Y, LUBE VLVS (DFC SYS-40) VENDOR | Kontrol af utaggede ventiler | 5 |  |  | 43 | 1 | 43 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /36 | GAS DISPOSAL (ACID GAS, FLARE, VENT) | NOSD |  | INLC | MTN-INST |  | 99000142
| VEN-MECH | 2023-12-31 | 2019-12-31 | WPM | D | V | Non Critical | 2400053837 | 0010 | 3Y LUBRICATE VALVES (DFF SYS-33) VENDOR | Kontrol af utaggede ventiler | 5 |  |  | 36 | 1 | 36 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /10 | PROD WELLS/FLOW/MANIF/PMPG/WELL METERING | NOSD |  | INLC | MTN-MECH |  | DK0500014380
| VEN-MECH | 2023-12-31 | 2020-01-01 | WPM | D | V | Non Critical | 2400053841 | 0010 | 3Y LUBRICATE VALVES (DFF SYS-03) VENDOR | Kontrol af utaggede ventiler | 5 |  |  | 43.5 | 1 | 43.5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT NTUP PRC SETC | DF /F /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD |  | INLC | MTN-MECH |  | DK0500014380
| VEN-MECH | 2023-12-31 | 2020-01-01 | WPM | D | V | Non Critical | 2400053858 | 0010 | 3Y LUBRICATE VALVES (DFF SYS-57) VENDOR | Kontrol af utaggede ventiler | 2 |  |  | 46.5 | 1 | 46.5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT NTUP PRC SETC | DF /F /71 | FUEL OIL/DIESEL OIL (INCL STORAGE/DIST) | NOSD |  | INLC | MTN-MECH |  | DK0500014382
| MTN-LAGG | 2024-01-15 | 2022-12-21 | WPM | C | V | Business Critical | 2400116269 | 0061 | NII Inspection DB-V-5001 | Genisolering og oprydning | 2 |  | WELLSAT, cancelled resource availability | 120 | 2 | 120 | 0 | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DA /B /28/DB-V-5001 | DRAIN VESSEL | NOSD | DANBPVI22 | INLC | MTN-PAIN
| MTN-PIPF | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0003 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI |  |  | 2022 WTW REGRET | 24 | 1 | 24 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-SCAF | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0010 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI |  |  | 2022 WTW REGRET | 105 | 1 | 105 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-LAGG | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0020 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI |  |  | 2022 WTW REGRET | 12 | 1 | 12 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-ELEC | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0030 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI |  |  | 2022 WTW REGRET | 15 | 1 | 15 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-PAIN | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0040 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI |  |  | 2022 WTW REGRET | 39 | 1 | 39 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-PIPF | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0050 | 6Y PVI Internal Inspection DFGA-V-3441. | EXCECUTION WORK ON PVI |  |  | 2022 WTW REGRET | 96 | 1 | 96 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-SCAF | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0060 | 6Y PVI Internal Inspection DFGA-V-3441. | EXCECUTION WORK ON PVI |  |  | 2022 WTW REGRET | 72 | 1 | 72 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-ELEC | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0080 | 6Y PVI Internal Inspection DFGA-V-3441. | EXCECUTION WORK ON PVI |  |  | 2022 WTW REGRET | 12 | 1 | 12 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-PAIN | 2024-01-08 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0090 | 6Y PVI Internal Inspection DFGA-V-3441. | EXCECUTION WORK ON PVI |  |  | 2022 WTW REGRET | 30 | 1 | 30 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| QAQCMECH | 2024-01-26 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0100 | 6Y PVI Internal Inspection DFGA-V-3441. | EXCECUTION WORK ON PVI |  |  | 2022 WTW REGRET | 18 | 1 | 18 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-PIPF | 2024-01-28 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0110 | 6Y PVI Internal Inspection DFGA-V-3441. | POST WORK AFTER PVI |  |  | 2022 WTW REGRET | 6 | 1 | 6 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-SCAF | 2024-01-28 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0120 | 6Y PVI Internal Inspection DFGA-V-3441. | POST WORK AFTER PVI |  |  | 2022 WTW REGRET | 48 | 1 | 48 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-LAGG | 2024-01-28 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0130 | 6Y PVI Internal Inspection DFGA-V-3441. | POST WORK AFTER PVI |  |  | 2022 WTW REGRET | 48 | 1 | 48 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-ELEC | 2024-02-09 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0140 | 6Y PVI Internal Inspection DFGA-V-3441. | POST WORK AFTER PVI |  |  | 2022 WTW REGRET | 18 | 1 | 18 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-PAIN | 2024-02-09 | 2022-12-21 | WPM | A | V | Assurance | 2400116297 | 0150 | 6Y PVI Internal Inspection DFGA-V-3441. | POST WORK AFTER PVI |  |  | 2022 WTW REGRET | 36 | 1 | 36 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /27/DFGA-V-3441 | SAND REMOVAL VESSEL, DEGASSER | NOSD | DANPVI22 | INLC | MTN-PAIN
| MTN-MECH | 2023-12-31 | 2021-08-18 | WPM | A | V | Assurance | 2400126337 | 0010 | 1Y GAS TIL TYRA EAST DFBA-EP-3805 | 1Y-DFBA-EP-3805 |  |  |  | 5 | 1 | 5 | 0 | APPR SECE AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2024-01-01 | 2021-08-18 | WPM | A | V | Assurance | 2400126337 | 0012 | 1Y GAS TIL TYRA EAST DFBA-EP-3805 | 1Y-DFBA-EP-3805 |  |  |  | 1.5 | 1 | 1.5 | 0 | APPR SECE AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-08-18 | WPM | A | V | Assurance | 2400126337 | 0014 | 1Y GAS TIL TYRA EAST DFBA-EP-3805 | DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR SECE AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /34/DFBA-EP-3805 | 12" TYRA GAS LINE SCRAPER LAUNCHER | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-10-20 | WPM | B | V | Safety & Env.Related | 2400126423 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFA-OIL) | REGISTRATION OF WORKING HOURS |  |  |  | 6 | 1 | 6 | 0 | APPR AWSD AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-10-20 | WPM | B | V | Safety & Env.Related | 2400126423 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFA-OIL) | DE-ISOLATION |  |  |  | 2 | 1 | 2 | 0 | APPR AWSD AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFA-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-11-03 | WPM | B | V | Safety & Env.Related | 2400126426 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFB-OIL) | REGISTRATION OF WORKING HOURS | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-11-03 | WPM | B | V | Safety & Env.Related | 2400126426 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFB-OIL) | DE-ISOLATION | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-12-04 | WPM | B | V | Safety & Env.Related | 2400126430 | 0020 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | REGISTRATION OF WORKING HOURS |  |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-12-04 | WPM | B | V | Safety & Env.Related | 2400126430 | 0040 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-12-11 | WPM | B | V | Safety & Env.Related | 2400126431 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFE-OIL) | REGISTRATION OF WORKING HOURS |  |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-12-11 | WPM | B | V | Safety & Env.Related | 2400126431 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFE-OIL) | DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2021-09-30 | WPM | B | V | Safety & Env.Related | 2400134483 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DAB-WI) | DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF PRT MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | NOSD |  | INLC | MTN-MECH
| MTN-ELEC | 2023-12-31 | 2021-11-19 | WPM | B | V | Safety & Env.Related | 2400151245 | 0010 | 3Y FUNC, VISUAL, EX INSP ESDV (DFC-FUEL9 | REGISTRATION OF WORKING HOURS | 5 |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-11-19 | WPM | B | V | Safety & Env.Related | 2400151245 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFC-FUEL9 | REGISTRATION OF WORKING HOURS | 5 |  |  | 9 | 1 | 9 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-FUEL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-11-19 | WPM | B | V | Safety & Env.Related | 2400151245 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFC-FUEL9 | DE-ISOLATION | 5 |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-FUEL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-11-26 | WPM | B | V | Safety & Env.Related | 2400157215 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFCLPSEP) | REGISTRATION OF WORKING HOURS | 5 |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-11-26 | WPM | B | V | Safety & Env.Related | 2400157215 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFCLPSEP) | DE-ISOLATION | 5 |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFCLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-ELEC | 2023-12-31 | 2021-11-30 | WPM | B | V | Safety & Env.Related | 2400157422 | 0010 | 3Y FUNC, VISUAL, EX INSP ESDV (DFC-TSEP) | REGISTRATION OF WORKING HOURS | 5 |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-11-30 | WPM | B | V | Safety & Env.Related | 2400157422 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFC-TSEP) | REGISTRATION OF WORKING HOURS | 5 |  |  | 9 | 1 | 9 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-11-30 | WPM | B | V | Safety & Env.Related | 2400157422 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFC-TSEP) | DE-ISOLATION | 5 |  |  | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2022-01-07 | WPM | B | V | Safety & Env.Related | 2400176974 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFFHPSEP) | REGISTRATION OF WORKING HOURS |  |  |  | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFFHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2022-01-07 | WPM | B | V | Safety & Env.Related | 2400176974 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFFHPSEP) | DE-ISOLATION |  |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFFHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2022-01-11 | WPM | B | V | Safety & Env.Related | 2400176975 | 0002 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-IPHP) | ISOLATION |  |  |  | 12 | 1 | 12 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-ELEC | 2024-01-03 | 2022-01-11 | WPM | B | V | Safety & Env.Related | 2400176975 | 0010 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-IPHP) | REGISTRATION OF WORKING HOURS |  |  |  | 12 | 1 | 12 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-06 | 2022-01-11 | WPM | B | V | Safety & Env.Related | 2400176975 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-IPHP) | REGISTRATION OF WORKING HOURS |  |  |  | 36 | 1 | 36 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-15 | 2022-01-11 | WPM | B | V | Safety & Env.Related | 2400176975 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-IPHP) | DE-ISOLATION |  |  |  | 12 | 1 | 12 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2022-01-15 | WPM | B | V | Safety & Env.Related | 2400176976 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFFLPSEP) | REGISTRATION OF WORKING HOURS |  |  |  | 6 | 1 | 6 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFFLPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2022-01-15 | WPM | B | V | Safety & Env.Related | 2400176976 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFFLPSEP) | DE-ISOLATION |  |  |  | 2 | 1 | 2 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFFLPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2022-01-19 | WPM | B | V | Safety & Env.Related | 2400176977 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-OIL) | REGISTRATION OF WORKING HOURS |  |  |  | 6 | 1 | 6 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2022-01-19 | WPM | B | V | Safety & Env.Related | 2400176977 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-OIL) | DE-ISOLATION |  |  |  | 2 | 1 | 2 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-ELEC | 2024-01-01 | 2022-02-03 | WPM | B | V | Safety & Env.Related | 2400176982 | 0010 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | REGISTRATION OF WORKING HOURS |  |  |  | 4 | 1 | 4 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2022-02-03 | WPM | B | V | Safety & Env.Related | 2400176982 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | REGISTRATION OF WORKING HOURS |  |  |  | 12 | 1 | 12 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2022-02-03 | WPM | B | V | Safety & Env.Related | 2400176982 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | DE-ISOLATION |  |  |  | 4 | 1 | 4 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFGHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2022-02-07 | WPM | B | V | Safety & Env.Related | 2400176984 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFX-LIFT) | REGISTRATION OF WORKING HOURS | 5 |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFX-LIFT |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-02-07 | WPM | B | V | Safety & Env.Related | 2400176984 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFX-LIFT) | DE-ISOLATION | 5 |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFX-LIFT |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-02-15 | WPM | B | V | Safety & Env.Related | 2400176986 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (D-GASTYE) | REGISTRATION OF WORKING HOURS | 2 |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /34/DFBA-ESDV-38097 | ESDV ON PIPELINE GAS TO TYRA EE FR DAN F | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2022-02-15 | WPM | B | V | Safety & Env.Related | 2400176986 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (D-GASTYE) | DE-ISOLATION | 2 |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /34/DFBA-ESDV-38097 | ESDV ON PIPELINE GAS TO TYRA EE FR DAN F | D-GASTYE |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2022-02-19 | WPM | B | V | Safety & Env.Related | 2400176987 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | REGISTRATION OF WORKING HOURS |  |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /34/DFFA-ESDV-380304 | S/D VALVE - PRODUCTION FROM HALFDAN S/D | DHDHPGAS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2022-02-19 | WPM | B | V | Safety & Env.Related | 2400176987 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /34/DFFA-ESDV-380304 | S/D VALVE - PRODUCTION FROM HALFDAN S/D | DHDHPGAS |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2022-02-23 | WPM | B | V | Safety & Env.Related | 2400176988 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDLPGAS) | REGISTRATION OF WORKING HOURS |  |  |  | 3 | 1 | 3 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DHDLPGAS |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2022-02-23 | WPM | B | V | Safety & Env.Related | 2400176988 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDLPGAS) | DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSD AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DHDLPGAS |  | INLC | MTN-MECH |  | 99000116
| MTN-ELEC | 2023-12-31 | 2022-02-28 | WPM | B | V | Safety & Env.Related | 2400176989 | 0010 | 3Y FUNC, VISUAL, EX INSP BDV (DFF-IPHP) | REGISTRATION OF WORKING HOURS | 2 |  |  | 3 | 1 | 3 | 0 | APPR SECE AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2022-02-28 | WPM | B | V | Safety & Env.Related | 2400176989 | 0020 | 3Y FUNC, VISUAL, EX INSP BDV (DFF-IPHP) | REGISTRATION OF WORKING HOURS | 2 |  |  | 9 | 1 | 9 | 0 | APPR SECE AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2022-02-28 | WPM | B | V | Safety & Env.Related | 2400176989 | 0040 | 3Y FUNC, VISUAL, EX INSP BDV (DFF-IPHP) | DE-ISOLATION |  |  |  | 3 | 1 | 3 | 0 | APPR SECE AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /30/DFFA-BDV-410521 | GLYCOL REBOILER V-4103 BLOWDOWN TO VENT | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2022-03-22 | WPM | A | V | Assurance | 2400190505 | 0002 | 1Y FIRE + GAS DETECTORS IN DFBA-A-3560 | ISOLATION | 3 |  |  | 5 | 1 | 5 | 0 | APPR SECE RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /B /03/FZ-27B | FIRE ZONE 27B W/I PUMP ENC | DFB-3560 |  | INLC | MTN-TELE
| MTN-TELE | 2024-01-01 | 2022-03-22 | WPM | A | V | Assurance | 2400190505 | 0010 | 1Y FIRE + GAS DETECTORS IN DFBA-A-3560 | TL-1Y FIRE + GAS DETECTORS IN DFBA-A-356 | 3 |  |  | 12 | 1 | 12 | 0 | APPR SECE RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /B /03/FZ-27B | FIRE ZONE 27B W/I PUMP ENC | DFB-3560 |  | INLC | MTN-TELE
| PRODTECH | 2024-01-04 | 2022-03-22 | WPM | A | V | Assurance | 2400190505 | 0012 | 1Y FIRE + GAS DETECTORS IN DFBA-A-3560 | DE-ISOLATION | 3 |  |  | 5 | 1 | 5 | 0 | APPR SECE RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /B /03/FZ-27B | FIRE ZONE 27B W/I PUMP ENC | DFB-3560 |  | INLC | MTN-TELE
| VEN-HVAC | 2023-12-31 | 2022-08-05 | WPM | C | I | Business Critical | 2400206493 | 0020 | 1Y HVAC SUPPLY CHECK DFBA-A-1224 | HVAC SUPPLY CHECK DFBA-A-1224 | 2 |  | materials on 2400128802 | 15 | 1 | 15 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /09/DFBA-A-1224 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| VEN-HVAC | 2024-01-01 | 2022-08-05 | WPM | C | I | Business Critical | 2400206493 | 0030 | 1Y HVAC SUPPLY CHECK DFBA-A-1224 | PERSONAL DE-ISOLATION | 2 |  | materials on 2400128802 | 1 | 1 | 1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /09/DFBA-A-1224 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| VEN-HVAC | 2024-01-01 | 2022-08-05 | WPM | C | I | Business Critical | 2400206493 | 0040 | 1Y HVAC SUPPLY CHECK DFBA-A-1224 | RETURN TO OPERATION | 2 |  | materials on 2400128802 | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /09/DFBA-A-1224 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| MTN-MECH | 2023-12-31 | 2022-09-17 | WPM | A | V | Assurance | 2400210900 | 0010 | 1Y FW HR/HYD/MONIT MAINT-DFG | FW HR/HYD/MONIT MAINT-DFG |  |  |  | 28 | 1 | 28 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /01/FW-HOSEREELS | FIREWATER HOSEREELS | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-09-17 | WPM | A | V | Assurance | 2400210900 | 0020 | 1Y FW HR/HYD/MONIT MAINT-DFG | FW HR/HYD/MONIT MAINT-DFG |  |  |  | 28 | 1 | 28 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /01/FW-HOSEREELS | FIREWATER HOSEREELS | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-10-04 | WPM | A | V | Assurance | 2400211608 | 0020 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | SDV LUBE/FUNC TEST - DFA/B/C/E |  |  |  | 45 | 1 | 45 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFX-LIFT |  | INLC | MTN-MECH
| MTN-INST | 2024-01-15 | 2022-10-04 | WPM | A | V | Assurance | 2400211608 | 0030 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | SDV LUBE/FUNC TEST - DFA/B/C/E |  |  |  | 1 | 1 | 1 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFX-LIFT |  | INLC | MTN-MECH
| PRODTECH | 2024-01-15 | 2022-10-04 | WPM | A | V | Assurance | 2400211608 | 0040 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | DE-ISOLATION BY PRODUCTION |  |  |  | 15 | 1 | 15 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFX-LIFT |  | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2022-10-06 | WPM | A | V | Assurance | 2400211611 | 0010 | 4Y FLARE SYSTEM MAINT-DFG | SCAFFOLDING CONSTRUCT |  |  |  | 25 | 1 | 25 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /36/FLARE-SYSTEM | FLARE SYSTEM | DFGFLARE |  | INLC | MTN-MECH
| PRODTECH | 2024-01-06 | 2022-10-06 | WPM | A | V | Assurance | 2400211611 | 0020 | 4Y FLARE SYSTEM MAINT-DFG | ISOLATION BY PRODUCTION |  |  |  | 2 | 1 | 2 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /36/FLARE-SYSTEM | FLARE SYSTEM | DFGFLARE |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-06 | 2022-10-06 | WPM | A | V | Assurance | 2400211611 | 0030 | 4Y FLARE SYSTEM MAINT-DFG | FLARE SYSTEM MAINT-DFG |  |  |  | 2 | 1 | 2 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /36/FLARE-SYSTEM | FLARE SYSTEM | DFGFLARE |  | INLC | MTN-MECH
| MTN-INST | 2024-01-07 | 2022-10-06 | WPM | A | V | Assurance | 2400211611 | 0040 | 4Y FLARE SYSTEM MAINT-DFG | FLARE SYSTEM MAINT-DFG |  |  |  | 5 | 1 | 5 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /36/FLARE-SYSTEM | FLARE SYSTEM | DFGFLARE |  | INLC | MTN-MECH
| PRODTECH | 2024-01-08 | 2022-10-06 | WPM | A | V | Assurance | 2400211611 | 0050 | 4Y FLARE SYSTEM MAINT-DFG | DE-ISOLATION BY PRODUCTION |  |  |  | 2 | 1 | 2 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /36/FLARE-SYSTEM | FLARE SYSTEM | DFGFLARE |  | INLC | MTN-MECH
| MTN-SCAF | 2024-01-09 | 2022-10-06 | WPM | A | V | Assurance | 2400211611 | 0060 | 4Y FLARE SYSTEM MAINT-DFG | SCAFFOLDING DE-CONSTRUCT |  |  |  | 25 | 1 | 25 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /G /36/FLARE-SYSTEM | FLARE SYSTEM | DFGFLARE |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-09-29 | WPM | B | V | Safety & Env.Related | 2400211620 | 0020 | 6M INSTRUMENT AIR SYSTEM MAINT - DFF | INSTRUMENT AIR SYSTEM MAINT - DFF |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM | NOSD |  | INLC | MTN-MECH
| VEN-ACCO | 2023-12-31 | 2022-10-01 | WPM | C | S | Business Critical | 2400211636 | 0010 | 6M GALLEY VENDOR MAINT DFC | GALLEY VENDOR MAINT DFC | 2 |  |  | 24 | 1 | 24 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT | NOSD |  | INLC | MTN-ELEC
| PRODTECH | 2023-12-31 | 2022-10-08 | WPM | A | V | Assurance | 2400211789 | 0010 | 1Y SDV LUBE/FUNC TEST - DFF | ISOLATION BY PRODUCTION |  |  | W51 | 13 | 1 | 13 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DAB-WI |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-10-08 | WPM | A | V | Assurance | 2400211789 | 0020 | 1Y SDV LUBE/FUNC TEST - DFF | SDV LUBE/FUNC TEST - DFF |  |  | W51 | 39 | 1 | 39 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DAB-WI |  | INLC | MTN-MECH
| PRODTECH | 2024-01-13 | 2022-10-08 | WPM | A | V | Assurance | 2400211789 | 0030 | 1Y SDV LUBE/FUNC TEST - DFF | DE-ISOLATION BY PRODUCTION |  |  | W51 | 13 | 1 | 13 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DAB-WI |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-09-28 | WPM | A | V | Assurance | 2400214281 | 0020 | 8KH SDV/BDV FUNC TEST WI DFFA-A-3520 | SDV FUNC TEST WI DFFA-A-3520 |  |  |  | 4.5 | 1 | 4.5 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /54/DFFA-A-3520 | WI PUMP UNIT | DFF-3520 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-09-28 | WPM | A | V | Assurance | 2400214281 | 0030 | 8KH SDV/BDV FUNC TEST WI DFFA-A-3520 | DE-ISOLATION BY PRODUCTION |  |  |  | 2 | 1 | 2 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /F /54/DFFA-A-3520 | WI PUMP UNIT | DFF-3520 |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2022-10-27 | WPM | C | S | Business Critical | 2400214328 | 0010 | 1Y SEWER TREAT VEND CLEANING DFCM-A-5101 | SEWER TREAT VEND CLEANING DFCM-A-5101 |  |  |  | 160 | 2 | 160 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /82/DFCM-A-5101 | SEWAGE TREATMENT UNIT | NOSD |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-06 | 2022-10-26 | WPM | D | I | Non Critical | 2400214329 | 0020 | 1Y STEAM CLEANER CHECK-DFFA-A-1110 | STEAM CLEANER CHECK-DFFA-A-1110 | 2 |  |  | 12 | 1 | 12 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /72/DFFA-A-1110 | HOT WATER CLEANER SKID | NOSD |  | INLC | MTN-INST
| PRODTECH | 2024-01-01 | 2022-11-03 | WPM | A | V | Assurance | 2400214776 | 0030 | 1Y SDV LUBE/FUNC TEST OIL - DFB | DE-ISOLATION BY PRODUCTION |  |  |  | 1 | 1 | 1 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFB-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-11-05 | WPM | A | V | Assurance | 2400214777 | 0020 | 1Y SDV LUBE/FUNC TEST OIL - DFA | SDV LUBE/FUNC TEST OIL - DFA | 3 |  |  | 6 | 1 | 6 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFA-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2022-11-05 | WPM | A | V | Assurance | 2400214777 | 0030 | 1Y SDV LUBE/FUNC TEST OIL - DFA | DE-ISOLATION BY PRODUCTION | 3 |  |  | 2 | 1 | 2 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFA-OIL |  | INLC | MTN-MECH
| MTN-ELEC | 2025-02-13 | 2022-11-19 | WPM | A | V | Assurance | 2400215388 | 0010 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-12532 | PERSONAL ISOLATION | 3 |  |  | 1 | 1 | 1 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /09/DFCC-A-12532 | AIR HANDLING UNIT - ACCOMMODATION | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2025-02-13 | 2022-11-19 | WPM | A | V | Assurance | 2400215388 | 0020 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-12532 | HVAC SUPPLY AHU CHECK DFCC-A-12532 | 3 |  |  | 12 | 1 | 12 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /09/DFCC-A-12532 | AIR HANDLING UNIT - ACCOMMODATION | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2025-02-16 | 2022-11-19 | WPM | A | V | Assurance | 2400215388 | 0030 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-12532 | PERSONAL DE-ISOLATION | 3 |  |  | 1 | 1 | 1 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /09/DFCC-A-12532 | AIR HANDLING UNIT - ACCOMMODATION | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2025-02-16 | 2022-11-19 | WPM | A | V | Assurance | 2400215388 | 0040 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-12532 | RETURN TO OPERATION | 3 |  |  | 2 | 1 | 2 | 0 | APPR SECE PMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /C /09/DFCC-A-12532 | AIR HANDLING UNIT - ACCOMMODATION | NOSD |  | INLC | MTN-ELEC
| VEN-HVAC | 2023-12-31 | 2022-11-23 | WPM | D | V | Non Critical | 2400215518 | 0010 | 3Y DUCT CLEAN VENDOR - DFC | DUCT CLEAN VENDOR - DFC | 2 |  |  | 180 | 1 | 180 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /09 | HVAC | NOSD |  | INLC | MTN-ELEC
| MTN-MECH | 2023-12-31 | 2022-12-04 | WPM | A | V | Assurance | 2400215979 | 0020 | 1Y SDV LUBE/FUNC TEST FUEL - DFC | SDV LUBE/FUNC TEST FUEL - DFC | 3 |  |  | 9 | 1 | 9 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-FUEL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2022-12-04 | WPM | A | V | Assurance | 2400215979 | 0030 | 1Y SDV LUBE/FUNC TEST FUEL - DFC | DE-ISOLATION BY PRODUCTION | 3 |  |  | 3 | 1 | 3 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-FUEL |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-12-07 | WPM | A | V | Assurance | 2400215980 | 0020 | 1Y SDV LUBE/FUNC TEST HPSEP - DFC | SDV LUBE/FUNC TEST HPSEP - DFC | 3 |  |  | 6 | 1 | 6 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFCHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2022-12-07 | WPM | A | V | Assurance | 2400215980 | 0030 | 1Y SDV LUBE/FUNC TEST HPSEP - DFC | DE-ISOLATION BY PRODUCTION | 3 |  |  | 2 | 1 | 2 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFCHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-12-11 | WPM | A | V | Assurance | 2400218580 | 0020 | 1Y SDV LUBE/FUNC TEST LPSEP - DFC | SDV LUBE/FUNC TEST LPSEP - DFC | 3 |  |  | 6 | 1 | 6 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFCLPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2022-12-11 | WPM | A | V | Assurance | 2400218580 | 0030 | 1Y SDV LUBE/FUNC TEST LPSEP - DFC | DE-ISOLATION BY PRODUCTION | 3 |  |  | 2 | 1 | 2 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFCLPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-12-11 | WPM | A | V | Assurance | 2400218581 | 0030 | 1Y SDV LUBE/FUNC TEST OIL - DFE | DE-ISOLATION BY PRODUCTION | 3 |  |  | 1 | 1 | 1 | 0 | APPR SECE AWSD AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFE-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-12-15 | WPM | A | V | Assurance | 2400219085 | 0020 | 1Y SDV LUBE/FUNC TEST TSEP - DFC | SDV LUBE/FUNC TEST TSEP - DFC |  |  |  | 9 | 1 | 9 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-TSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2022-12-15 | WPM | A | V | Assurance | 2400219085 | 0030 | 1Y SDV LUBE/FUNC TEST TSEP - DFC | DE-ISOLATION BY PRODUCTION |  |  |  | 3 | 1 | 3 | 0 | APPR SECE AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFC-TSEP |  | INLC | MTN-MECH
| VEN-HVAC | 2023-12-31 | 2023-01-23 | WPM | D | V | Non Critical | 2400221609 | 0010 | 3Y DUCT CLEAN LIVING QUARTERS VEND -DFC | DUCT CLEAN LIVING QUARTERS VEND -DFC |  |  |  | 180 | 1 | 180 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /09 | HVAC | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-30 | 2023-02-13 | WPM | A | V | Assurance | 2400230362 | 0020 | 1Y EMERGENCY LIGHTS TEST PROD - DFA | EMERGENCY LIGHTS TEST PROD - DFA |  |  |  | 12 | 1 | 12 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /62/EMERGENCY-LIGHTING | EMERGENCY LIGHTING | NOSD | GMC | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-02 | 2023-02-13 | WPM | A | V | Assurance | 2400230362 | 0030 | 1Y EMERGENCY LIGHTS TEST PROD - DFA | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /62/EMERGENCY-LIGHTING | EMERGENCY LIGHTING | NOSD | GMC | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-30 | 2023-02-13 | WPM | A | V | Assurance | 2400230363 | 0020 | 1Y EMERGENCY LIGHT TEST MEZZ.- DFA | EMERGENCY LIGHT TEST MEZZ.- DFA |  |  |  | 12 | 1 | 12 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /62/EMERGENCY-LIGHTING-MEZZ | EMERGENCY LIGHTING-MEZZANINE | NOSD | GMC | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-02 | 2023-02-13 | WPM | A | V | Assurance | 2400230363 | 0030 | 1Y EMERGENCY LIGHT TEST MEZZ.- DFA | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR SECE AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /A /62/EMERGENCY-LIGHTING-MEZZ | EMERGENCY LIGHTING-MEZZANINE | NOSD | GMC | INLC | MTN-ELEC
| VEN-MECH | 2023-12-31 | 2023-02-20 | WPM | D | S | Non Critical | 2400230510 | 0020 | 4Y COLD PROVISIONS DFCC-C-1301/2/3 VEND | COLD PROVISIONS DFCC-C-1301/2/3 VEND |  |  |  | 30 | 1 | 30 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT | NOSD |  | INLC | MTN-ELEC
| MTN-MECH | 2024-01-03 | 2023-02-20 | WPM | D | S | Non Critical | 2400230510 | 0030 | 4Y COLD PROVISIONS DFCC-C-1301/2/3 VEND | COLD PROVISIONS DFCC-C-1301/2/3 VEND |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-04 | 2023-02-20 | WPM | D | S | Non Critical | 2400230510 | 0040 | 4Y COLD PROVISIONS DFCC-C-1301/2/3 VEND | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-05 | 2023-02-20 | WPM | D | S | Non Critical | 2400230510 | 0050 | 4Y COLD PROVISIONS DFCC-C-1301/2/3 VEND | RETURN TO OPERATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/CATERING-EQUIPMENT | CATERING EQUIPMENT | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | I | Business Critical | 2400235569 | 0040 | 4Y 400V N-DP-MAINT-DFEZ-DP-1831 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /61/DFEZ-DP-1831 | LIGHTING DISTR.PANEL | NOSD |  | INLC | MTN-ELEC
| VEN-ELEC | 2023-12-30 | 2023-04-28 | WPM | C | I | Business Critical | 2400235572 | 0020 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | 380V UPS-DP-INSP-DFBA-DP-1834-01 |  |  |  | 20 | 1 | 20 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-DP-1834-A01 | M-56591 MOTOR OIL COOLER FAN 1 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | I | Business Critical | 2400235572 | 0030 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | 380V UPS-DP-INSP-DFBA-DP-1834-01 |  |  |  | 7 | 1 | 7 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-DP-1834-A01 | M-56591 MOTOR OIL COOLER FAN 1 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-03 | 2023-04-28 | WPM | C | I | Business Critical | 2400235572 | 0040 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-DP-1834-A01 | M-56591 MOTOR OIL COOLER FAN 1 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | D | I | Non Critical | 2400235573 | 0030 | 4Y 380V UPS-DP MAINT-DFBA-DP-1834-02 | 380V UPS-DP INSP-DFBA-DP-1834-02 |  |  |  | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-DP-1834-B04 | VENTILATION FAN DUTY M-57095 TURB. ENCL. | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | D | I | Non Critical | 2400235573 | 0040 | 4Y 380V UPS-DP MAINT-DFBA-DP-1834-02 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-DP-1834-B04 | VENTILATION FAN DUTY M-57095 TURB. ENCL. | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | C | V | Business Critical | 2400235583 | 0030 | 4Y 380V N-SWB-MAINT-DFBA-N-1830 | 380V N-SWB-INSP-DFBA-N-1830 |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830 | SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | V | Business Critical | 2400235583 | 0040 | 4Y 380V N-SWB-MAINT-DFBA-N-1830 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830 | SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| VEN-ELEC | 2023-12-30 | 2023-04-28 | WPM | C | I | Business Critical | 2400235584 | 0020 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | 380V N-SWB-INSP-DFBA-N-1830-02 |  |  |  | 21 | 1 | 21 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-02B1 | DEMULSIFIER PUMP PM-3925 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | I | Business Critical | 2400235584 | 0030 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | 380V N-SWB-INSP-DFBA-N-1830-02 |  |  |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-02B1 | DEMULSIFIER PUMP PM-3925 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | I | Business Critical | 2400235584 | 0040 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-02B1 | DEMULSIFIER PUMP PM-3925 | NOSD |  | INLC | MTN-ELEC
| VEN-ELEC | 2023-12-30 | 2023-04-28 | WPM | C | V | Business Critical | 2400235585 | 0020 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | 380V N-SWB-INSP-DFBA-N-1830-01 |  |  |  | 27 | 1 | 27 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-F102 | INVERSE TIME OVERCURRENT RELAY | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-02 | 2023-04-28 | WPM | C | V | Business Critical | 2400235585 | 0030 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | 380V N-SWB-INSP-DFBA-N-1830-01 |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-F102 | INVERSE TIME OVERCURRENT RELAY | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-02 | 2023-04-28 | WPM | C | V | Business Critical | 2400235585 | 0040 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-F102 | INVERSE TIME OVERCURRENT RELAY | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | C | I | Business Critical | 2400235586 | 0030 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-03 | 380V N-SWB-INSP-DFBA-N-1830-03 |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-03C1 | LIGHTING/SMALL POWER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | I | Business Critical | 2400235586 | 0040 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-03 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-03C1 | LIGHTING/SMALL POWER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | C | I | Business Critical | 2400235588 | 0040 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-05 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1830-05B1 | VACUUM PUMP PM-3520 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | A | V | Assurance | 2400235735 | 0030 | 4Y 380V E-SWB MAINT DFEZ-N-1804-01 | 380V E-SWB MAINT DFEZ-N-1804-01 |  |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /05/DFEZ-N-1804 | EMERGENCY SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| PRODTECH | 2024-01-01 | 2023-04-13 | WPM | A | V | Assurance | 2400235735 | 0040 | 4Y 380V E-SWB MAINT DFEZ-N-1804-01 | DE-ISOLATION BY PRODUCTION |  |  |  | 2 | 1 | 2 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /E /05/DFEZ-N-1804 | EMERGENCY SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | V | Business Critical | 2400235764 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-01 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-01A1 | EMERGENCY LIGHTING MODULE | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | V | Business Critical | 2400235765 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-02 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-02C1 | CP-0701 LIFEBOAT & DAVIT HOIST PANEL | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | I | Business Critical | 2400235766 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-03 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-03B1 | LIGHTING AND CTRL MODULE (SMALL POWER) | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | V | Business Critical | 2400235767 | 0030 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-04 | 380V N-SWB INSP-DFEZ-N-1803-04 |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-04H1 | EE FEEDER TO DFEZ-N-1804 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-13 | WPM | C | V | Business Critical | 2400235767 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-04 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-04H1 | EE FEEDER TO DFEZ-N-1804 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | I | Business Critical | 2400235768 | 0020 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-07 | 380V N-SWB MAINT-DFEZ-N-1803-07 |  |  |  | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-07B1 | PM-3141 WELLHEAD HYDR. PUMP DUTY | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | I | Business Critical | 2400235769 | 0030 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-08 | 380V N-SWB INSP-DFEZ-N-1803-08 |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-08B1 | PM-3911 BIOCIDE PUMP A | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-13 | WPM | C | I | Business Critical | 2400235769 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-08 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-08B1 | PM-3911 BIOCIDE PUMP A | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | I | Business Critical | 2400235770 | 0030 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-09 | 380V N-SWB INSP-DFEZ-N-1803-09 |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-09C1 | PM-3901 FERRIC-SULPHATE MIXER DAY TANK A | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-13 | WPM | C | I | Business Critical | 2400235770 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-09 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803-09C1 | PM-3901 FERRIC-SULPHATE MIXER DAY TANK A | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | V | Business Critical | 2400235771 | 0040 | 4Y 380V N-SWB MAINT-DFEZ-N-1803 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /61/DFEZ-N-1803 | L.V SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | V | Business Critical | 2400235793 | 0030 | 4Y 380V N-SWB MAINT-DFAA-N-1800 | 380V N-SWB INSP-DFAA-N-1800 |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800 | MAIN SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-13 | WPM | C | V | Business Critical | 2400235793 | 0040 | 4Y 380V N-SWB MAINT-DFAA-N-1800 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800 | MAIN SWITCHBOARD | NOSD |  | INLC | MTN-ELEC
| VEN-ELEC | 2023-12-30 | 2023-04-13 | WPM | B | I | Safety & Env.Related | 2400235795 | 0020 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | 380V N-SWB INSP-DFAA-N-1800-02 |  |  |  | 19 | 1 | 19 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800-C_11 | PM-3915 DEMULSIFIER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-13 | WPM | B | I | Safety & Env.Related | 2400235795 | 0030 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | 380V N-SWB INSP-DFAA-N-1800-02 |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800-C_11 | PM-3915 DEMULSIFIER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-02 | 2023-04-13 | WPM | B | I | Safety & Env.Related | 2400235795 | 0040 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800-C_11 | PM-3915 DEMULSIFIER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-13 | WPM | C | I | Business Critical | 2400235796 | 0030 | 4Y 380V N-SWB MAINT-DFAA-N-1800-03 | 380V N-SWB INSP-DFAA-N-1800-03 |  |  |  | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800-C_20 | DIST. PANEL MAIN LIGHT/SMALL POWER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-13 | WPM | C | I | Business Critical | 2400235796 | 0040 | 4Y 380V N-SWB MAINT-DFAA-N-1800-03 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /61/DFAA-N-1800-C_20 | DIST. PANEL MAIN LIGHT/SMALL POWER | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | C | I | Business Critical | 2400235798 | 0030 | 4Y 380V N-SWB MAINT-DFBA-N-1810-01 | 380V N-SWB INSP-DFBA-N-1810-01 |  |  |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1810-C_01 | DEMULSIFIER INJ. DFBA-PM-3921 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | I | Business Critical | 2400235798 | 0040 | 4Y 380V N-SWB MAINT-DFBA-N-1810-01 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1810-C_01 | DEMULSIFIER INJ. DFBA-PM-3921 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | C | I | Business Critical | 2400235799 | 0040 | 4Y 380V N-SWB MAINT-DFBA-N-1810-02 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1810-C_04 | POLY-ELECTROLYTE DFBA-PM-3525 | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-28 | WPM | C | I | Business Critical | 2400235802 | 0030 | 4Y 380V N-SWB MAINT-DFBA-N-1810-05 | 380V N-SWB INSP-DFBA-N-1810-05 |  |  |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1810-C_84 | PM-3532 ANTI-FOAM AGENT | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2023-04-28 | WPM | C | I | Business Critical | 2400235802 | 0040 | 4Y 380V N-SWB MAINT-DFBA-N-1810-05 | DE-ISOLATION ELECTRICAL |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /61/DFBA-N-1810-C_84 | PM-3532 ANTI-FOAM AGENT | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2023-12-31 | 2023-03-20 | WPM | D | V | Non Critical | 2400235817 | 0020 | 4Y COOL UNIT DFCC-A-1331 VENDOR | COOL UNIT DFCC-A-1331 VENDOR |  |  |  | 24 | 1 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/DFCC-A-1331 | COFFEE SHOP MODULE | NOSD |  | INLC | MTN-ELEC
| MTN-MECH | 2024-01-02 | 2023-03-20 | WPM | D | V | Non Critical | 2400235817 | 0030 | 4Y COOL UNIT DFCC-A-1331 VENDOR | COOL UNIT DFCC-A-1331 VENDOR |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/DFCC-A-1331 | COFFEE SHOP MODULE | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-04 | 2023-03-20 | WPM | D | V | Non Critical | 2400235817 | 0040 | 4Y COOL UNIT DFCC-A-1331 VENDOR | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/DFCC-A-1331 | COFFEE SHOP MODULE | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-04 | 2023-03-20 | WPM | D | V | Non Critical | 2400235817 | 0050 | 4Y COOL UNIT DFCC-A-1331 VENDOR | RETURN TO OPERATION |  |  |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82/DFCC-A-1331 | COFFEE SHOP MODULE | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2023-12-31 | 2023-03-24 | WPM | D |  | Non Critical | 2400235924 | 0020 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | HVAC COOL UNIT VEND DFCI-C-12803/903 |  |  |  | 30 | 1 | 30 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/HVAC-UTILITY | HVAC UTILITY | NOSD |  | INLC | MTN-ELEC
| MTN-MECH | 2024-01-03 | 2023-03-24 | WPM | D |  | Non Critical | 2400235924 | 0030 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | HVAC COOL UNIT VEND DFCI-C-12803/903 |  |  |  | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/HVAC-UTILITY | HVAC UTILITY | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-04 | 2023-03-24 | WPM | D |  | Non Critical | 2400235924 | 0040 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/HVAC-UTILITY | HVAC UTILITY | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-05 | 2023-03-24 | WPM | D |  | Non Critical | 2400235924 | 0050 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | RETURN TO OPERATION |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/HVAC-UTILITY | HVAC UTILITY | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2023-12-31 | 2023-03-23 | WPM | D | V | Non Critical | 2400235926 | 0020 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | HVAC COOL UNIT DFGA-1220/21/22 - VEND |  |  |  | 24 | 1 | 24 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /09/DFGA-A-1220 | UPS A ROOM SPLIT DX COOLER | NOSD |  | INLC | MTN-ELEC
| MTN-MECH | 2024-01-02 | 2023-03-23 | WPM | D | V | Non Critical | 2400235926 | 0030 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | HVAC COOL UNIT DFGA-1220/21/22 - VEND |  |  |  | 6 | 1 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /09/DFGA-A-1220 | UPS A ROOM SPLIT DX COOLER | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-04 | 2023-03-23 | WPM | D | V | Non Critical | 2400235926 | 0040 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /09/DFGA-A-1220 | UPS A ROOM SPLIT DX COOLER | NOSD |  | INLC | MTN-ELEC
| VEN-MECH | 2024-01-04 | 2023-03-23 | WPM | D | V | Non Critical | 2400235926 | 0050 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | RETURN TO OPERATION |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /09/DFGA-A-1220 | UPS A ROOM SPLIT DX COOLER | NOSD |  | INLC | MTN-ELEC
| MTN-INST | 2023-12-31 | 2023-03-29 | WPM | A | V | Assurance | 2400241128 | 0010 | 1Y COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 |  |  |  | 7 | 1 | 7 | 0 | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /C /07/DFCM-A-5408 | COMPRESSOR UNIT, FOR NITROGEN GENERATOR | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2023-03-29 | WPM | A | V | Assurance | 2400241128 | 0020 | 1Y COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 |  |  |  | 12 | 1 | 12 | 0 | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /C /07/DFCM-A-5408 | COMPRESSOR UNIT, FOR NITROGEN GENERATOR | NOSD |  | INLC | MTN-MECH
| VEN-MECH | 2024-01-04 | 2023-03-29 | WPM | A | V | Assurance | 2400241128 | 0030 | 1Y COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 |  |  |  | 24 | 1 | 24 | 0 | APPR SECE WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /C /07/DFCM-A-5408 | COMPRESSOR UNIT, FOR NITROGEN GENERATOR | NOSD |  | INLC | MTN-MECH
| VEN-MECH | 2023-12-31 | 2023-04-17 | WPM | D | I | Non Critical | 2400241706 | 0010 | 6M HVAC COOLING UNIT VENDOR DFFB-A-1252 | HVAC COOLING UNIT VENDOR DFFB-A-1252 |  |  |  | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /09/DFFB-A-1252 | LER HVAC COOLING UNIT | NOSD |  | INLC | MTN-ELEC | 2507003
| MTN-MECH | 2024-01-01 | 2023-04-17 | WPM | D | I | Non Critical | 2400241706 | 0020 | 6M HVAC COOLING UNIT VENDOR DFFB-A-1252 | HVAC COOLING UNIT VENDOR DFFB-A-1252 |  |  |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /09/DFFB-A-1252 | LER HVAC COOLING UNIT | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2023-12-31 | 2023-04-30 | WPM | C | I | Business Critical | 2400241889 | 0020 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | HVAC SUPPLY A-122 CHECK -DFCI |  |  |  | 8 | 1 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/A-1222 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-02 | 2023-04-30 | WPM | C | I | Business Critical | 2400241889 | 0030 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | HVAC EXHAUST A-122 CHECK -DFCI |  |  |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/A-1222 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| VEN-HVAC | 2024-01-03 | 2023-04-30 | WPM | C | I | Business Critical | 2400241889 | 0040 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | HVAC LAB HOODS A-122 CHECK-DFCI (VENDOR) |  |  |  | 12 | 1 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/A-1222 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-04 | 2023-04-30 | WPM | C | I | Business Critical | 2400241889 | 0050 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL DE-ISOLATION |  |  |  | 1 | 1 | 1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/A-1222 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-04 | 2023-04-30 | WPM | C | I | Business Critical | 2400241889 | 0060 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | RETURN TO OPERATION |  |  |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /09/A-1222 | HVAC UNIT | NOSD |  | INLC | MTN-ELEC
| MTN-INST | 2023-12-31 | 2023-05-16 | WPM | C | V | Business Critical | 2400244917 | 0010 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING |  |  |  | 26 | 1 | 26 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /70/METERING | METERING FUEL GAS | NOSD |  | INLC | MTN-INST
| PRODTECH | 2024-01-06 | 2023-05-16 | WPM | C | V | Business Critical | 2400244917 | 0020 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING |  |  |  | 2 | 1 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /70/METERING | METERING FUEL GAS | NOSD |  | INLC | MTN-INST
| MTN-MECH | 2024-01-07 | 2023-05-16 | WPM | C | V | Business Critical | 2400244917 | 0030 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING |  |  |  | 12 | 1 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /70/METERING | METERING FUEL GAS | NOSD |  | INLC | MTN-INST
| MTN-ROPE | 2024-01-10 | 2023-05-16 | WPM | C | V | Business Critical | 2400244917 | 0040 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING |  |  |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /70/METERING | METERING FUEL GAS | NOSD |  | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2018-06-22 | WGN | 3 | V | 3. Intermediate | 2200003162 | 0010 | CMAT:DFF Efterfyldning af dual media fil | L3 Safinng of DFFA-FT-3501 | 2 | ? after Minox PVI | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3501 | DUAL MEDIA FILTER | DFF-3520 | DFF | INLC | MTN-PAIN
| MTN-TELE | 2024-12-24 | 2023-01-24 | WRO | 3 | S | 3. Intermediate | 2300004051 | 0010 | IT0098 - Dan Telecom support August 2022 | IT0098 - Dan Telecom support August 2022 |  | +2300003932 | Vendor to be onboard | 30 | 1 | 36 | 6 | APPR PROK RDBL | APPR OPND | REL PCNF PRT MANC NMAT PRC SETC | DF /C /08/DFCI-DT-14-10-02 | TERMINAL |  | IT0098 | INLC | MTN-TELE
| PRODTECH | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0030 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Safing of the XCV | 2 | 17-08 DFF-OIL outage | ¦10/01/2022 Wrk. Ctr. Migration | 6.5 | 1 | 6.5 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2016-05-08 | WDF | 3 | V | 3. Intermediate | 2100024893 | 0110 | SMAT:@+DFF-29 OIL XCV-301329 til FF mani | Desafing and leak test | 2 | 17-08 DFF-OIL outage | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 1 | 6 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL PCNF PRT CSER MANC PRC SETC | DF /F /10/DFFA-XCV-301329 | WELL 29 TO DFF HP PROD. MANIFOLD | DFF-OIL | DF2532 | INLC | MTN-PIPF |  | 99000116
| VEN-COMM | 2024-04-03 | 2019-11-06 | WRO | 4 | V | 4. Long | 2300000954 | 0010 | SCADA SW for ENG469B | SCADA SW for ENG469B | 2020 Project | 2020 DATE TBC |  | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /04/DFBA-FP-2039 | RTU FOR PROCESS CONTROL SYSTEM (SCADA) | NE | ENG469B | INLC | MTN-TELE
| MTN-TELE | 2024-04-04 | 2019-11-06 | WRO | 4 | V | 4. Long | 2300000954 | 0020 | SCADA SW for ENG469B | Telecom support | 2020 Project | 2020 DATE TBC |  | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /04/DFBA-FP-2039 | RTU FOR PROCESS CONTROL SYSTEM (SCADA) | NE | ENG469B | INLC | MTN-TELE
| VEN-COMM | 2024-04-03 |  | WRO | 4 | V | 4. Long | 2300000955 | 0010 | ESD EW for ENG469B | ESD EW for ENG469B | 2020 Project | 2020 DATE TBC |  | 24 | 1 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0208 | ESD PANEL | NE | ENG469B | INLC | MTN-TELE
| MTN-TELE | 2024-04-05 |  | WRO | 4 | V | 4. Long | 2300000955 | 0020 | ESD EW for ENG469B | Telecom support | 2020 Project | 2020 DATE TBC |  | 10 | 1 | 10 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0208 | ESD PANEL | NE | ENG469B | INLC | MTN-TELE
| VEN-COMM | 2024-04-03 |  | WRO | 4 | V | 4. Long | 2300000956 | 0010 | F<(>&<)>G SW for ENG469B | F&G SE for ENG469B | 2020 Project | 2020 DATE TBC |  | 12 | 1 | 12 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0113 | RTU FOR FIRE & GAS SYSTEM | NE | ENG469B | INLC | MTN-TELE
| MTN-TELE | 2024-04-03 |  | WRO | 4 | V | 4. Long | 2300000956 | 0020 | F<(>&<)>G SW for ENG469B | Telecom support | 2020 Project | 2020 DATE TBC |  | 5 | 1 | 5 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/DFBA-FP-0113 | RTU FOR FIRE & GAS SYSTEM | NE | ENG469B | INLC | MTN-TELE
| MTN-RIGG | 2023-12-31 | 2021-08-04 | WDF | 4 | S | 4. Long | 2100042724 | 0040 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assistance | 2 | 3/6 No PO . Dec 21 |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440026-U | HCV UPSTREAM PSV-420026 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-08-04 | WDF | 4 | S | 4. Long | 2100042724 | 0050 | DFFA-HCV-440026-U defective/seized Gearb | Valve removal | 2 | 3/6 No PO . Dec 21 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440026-U | HCV UPSTREAM PSV-420026 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-08-04 | WDF | 4 | S | 4. Long | 2100042724 | 0060 | DFFA-HCV-440026-U defective/seized Gearb | Valve installation w bolt torquing | 2 | 3/6 No PO . Dec 21 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440026-U | HCV UPSTREAM PSV-420026 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-08-04 | WDF | 4 | S | 4. Long | 2100042724 | 0070 | DFFA-HCV-440026-U defective/seized Gearb | Prod deisolate w function/leak test | 2 | 3/6 No PO . Dec 21 |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440026-U | HCV UPSTREAM PSV-420026 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-08-04 | WDF | 4 | S | 4. Long | 2100042724 | 0080 | DFFA-HCV-440026-U defective/seized Gearb | Housekeeping/reinstate protection shield | 2 | 3/6 No PO . Dec 21 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440026-U | HCV UPSTREAM PSV-420026 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2021-08-04 | WDF | 4 | S | 4. Long | 2100042724 | 0090 | DFFA-HCV-440026-U defective/seized Gearb | Rigger equipment removal | 2 | 3/6 No PO . Dec 21 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440026-U | HCV UPSTREAM PSV-420026 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-12-05 | 2018-03-20 | WDF | 4 | I | 4. Long | 2100023750 | 0009 | CMAT:DFB WI xcv 35380 intern læk | L3 Build Scaffolding | 2 | 3560 being decomissioned | 3560 being decomissioned | 52 | 3 | 52 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-XCV-35380 | VENT FROM SEAWATER DUAL MEDIA FILTERS | DFB-3560 |  | INLC | MTN-MECH
| PRODTECH | 2024-12-09 | 2018-03-20 | WDF | 4 | I | 4. Long | 2100023750 | 0010 | CMAT:DFB WI xcv 35380 intern læk | L3 Safing of DFBA-XCV-35380 | 2 | 3560 being decomissioned | 3560 being decomissioned | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-XCV-35380 | VENT FROM SEAWATER DUAL MEDIA FILTERS | DFB-3560 |  | INLC | MTN-MECH
| MTN-MECH | 2024-12-10 | 2018-03-20 | WDF | 4 | I | 4. Long | 2100023750 | 0020 | CMAT:DFB WI xcv 35380 intern læk | L2 Replace DFBA-XCV-35380 | 2 | 3560 being decomissioned | 3560 being decomissioned | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-XCV-35380 | VENT FROM SEAWATER DUAL MEDIA FILTERS | DFB-3560 |  | INLC | MTN-MECH
| MTN-RIGG | 2024-12-13 | 2018-03-20 | WDF | 4 | I | 4. Long | 2100023750 | 0030 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | 2 | 3560 being decomissioned | 3560 being decomissioned | 26 | 2 | 26 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-XCV-35380 | VENT FROM SEAWATER DUAL MEDIA FILTERS | DFB-3560 |  | INLC | MTN-MECH
| PRODTECH | 2024-12-16 | 2018-03-20 | WDF | 4 | I | 4. Long | 2100023750 | 0040 | CMAT:DFB WI xcv 35380 intern læk | L3 Desafing DFBA-XCV-35380 | 2 | 3560 being decomissioned | 3560 being decomissioned | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-XCV-35380 | VENT FROM SEAWATER DUAL MEDIA FILTERS | DFB-3560 |  | INLC | MTN-MECH
| MTN-MECH | 2024-12-17 | 2018-03-20 | WDF | 4 | I | 4. Long | 2100023750 | 0050 | CMAT:DFB WI xcv 35380 intern læk | L3 Remove Scaffolding | 2 | 3560 being decomissioned | 3560 being decomissioned | 39 | 3 | 39 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /28/DFBA-XCV-35380 | VENT FROM SEAWATER DUAL MEDIA FILTERS | DFB-3560 |  | INLC | MTN-MECH
| VEN-ELEC | 2024-04-01 | 2019-07-20 | WPM | C |  | Business Critical | 2400054527 | 0010 | 3Y 3KV DFFA-N-1801B-04 Bus to buscoupler | DFF-18A24 PM-Code: | 2 | ABB/CAV PTW:135160 |  | 3.5 | 1 | 3.5 | 0 | APPR PROK AWSC | APPR OPND | REL MANC NMAT PRC SETC | DF /F /61/DFFA-N-1801 | MAIN HV 3 KV-SWITCHBOARD | DAN-OIL | CAVERION/ABB | INLC | MTN-ELEC |  | 99000142
| VEN-ELEC | 2024-04-01 | 2019-07-20 | WPM | C |  | Business Critical | 2400054527 | 0012 | 3Y 3KV DFFA-N-1801B-04 Bus to buscoupler | DFF-18A24 PM-Code: | 2 | ABB/CAV PTW:135160 |  | 24 | 1 | 24 | 0 | APPR PROK AWSC | APPR OPND | REL MANC NMAT PRC SETC | DF /F /61/DFFA-N-1801 | MAIN HV 3 KV-SWITCHBOARD | DAN-OIL | CAVERION/ABB | INLC | MTN-ELEC |  | 99000142
| PRODTECH | 2024-04-01 | 2019-07-20 | WPM | C |  | Business Critical | 2400054527 | 0005 | 3Y 3KV DFFA-N-1801B-04 Bus to buscoupler | Safing | 2 | Align end of nov Minox SD |  | 2 | 1 | 2 | 0 | APPR PROK AWSC | APPR OPND | REL MANC NMAT PRC SETC | DF /F /61/DFFA-N-1801 | MAIN HV 3 KV-SWITCHBOARD | DAN-OIL | CAVERION/ABB | INLC | MTN-ELEC |  | 99000142
| PRODTECH | 2024-04-04 | 2019-07-20 | WPM | C |  | Business Critical | 2400054527 | 0040 | 3Y 3KV DFFA-N-1801B-04 Bus to buscoupler | De-safing | 2 | Align end of nov Minox SD |  | 1 | 1 | 1 | 0 | APPR PROK AWSC | APPR OPND | REL MANC NMAT PRC SETC | DF /F /61/DFFA-N-1801 | MAIN HV 3 KV-SWITCHBOARD | DAN-OIL | CAVERION/ABB | INLC | MTN-ELEC |  | 99000142
| PRODTECH | 2024-01-07 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0020 | CMAT:Udskiftning af XCV-30664 DFB-02 | Desafing af XCV-30664 DFB-02 | 2 | aligned with oil outage | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-07 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0030 | CMAT:Udskiftning af XCV-30664 DFB-02 | Leak test | 2 | aligned with oil outage | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-INST | 2023-12-31 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0020 | DFF-29 Defekt aksel på Actuator FCV-2901 | Isolate pneumatic and controls |  | Awaiting loss approval |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0030 | DFF-29 Defekt aksel på Actuator FCV-2901 | Rigging assist. Rig in/out (If needed) |  | Awaiting loss approval |  | 1 | 1 | 1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0040 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator |  | Awaiting loss approval |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0050 | DFF-29 Defekt aksel på Actuator FCV-2901 | Rigging assist. Rig in/out (If needed) |  | Awaiting loss approval |  | 1 | 1 | 1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0060 | DFF-29 Defekt aksel på Actuator FCV-2901 | Mount new Actuator |  | Awaiting loss approval |  | 5 | 1 | 5 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-INST | 2024-01-03 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0070 | DFF-29 Defekt aksel på Actuator FCV-2901 | Re-build tubing if any |  | Awaiting loss approval |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-INST | 2024-01-04 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0080 | DFF-29 Defekt aksel på Actuator FCV-2901 | Connect Controls and pneumatic |  | Awaiting loss approval |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0090 | DFF-29 Defekt aksel på Actuator FCV-2901 | Callibration Positioner/functional test |  | Awaiting loss approval |  | 2 | 1 | 2 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-05 | 2022-01-16 | WDF | 3 | I | 3. Intermediate | 2100059079 | 0100 | DFF-29 Defekt aksel på Actuator FCV-2901 | Deisolate PCV |  | Awaiting loss approval |  | 1 | 1 | 1 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /37/DFFA-FCV-290129 | FLOW CONTROL VALVE -GAS LIFT TO WELL 29 | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0010 | DFB-03 lækage fra SOV for hyd-skuffe | Isolate system | 4 | Awaiting loss approval |  | 3 | 1 | 3 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0020 | DFB-03 lækage fra SOV for hyd-skuffe | Isolate hydraulic | 4 | Awaiting loss approval |  | 1 | 1 | 1 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0030 | DFB-03 lækage fra SOV for hyd-skuffe | Remove old solenoid Valve | 4 | Awaiting loss approval |  | 2 | 1 | 2 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0040 | DFB-03 lækage fra SOV for hyd-skuffe | Mount new model solenoid (Old Obselete) | 4 | Awaiting loss approval |  | 5 | 1 | 5 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0050 | DFB-03 lækage fra SOV for hyd-skuffe | M. bracket or simular probably nedded | 4 | Awaiting loss approval |  | 6 | 1 | 6 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-INST | 2024-01-04 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0060 | DFB-03 lækage fra SOV for hyd-skuffe | New tubing probably nedded to connect | 4 | Awaiting loss approval |  | 3 | 1 | 3 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-INST | 2024-01-05 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0070 | DFB-03 lækage fra SOV for hyd-skuffe | New cable probably nedded to connect | 4 | Awaiting loss approval |  | 2 | 1 | 2 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0080 | DFB-03 lækage fra SOV for hyd-skuffe | De-Isolate Hydraulic | 4 | Awaiting loss approval |  | 1 | 1 | 1 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-06 | 2022-01-20 | WDF | 3 | V | 3. Intermediate | 2100060714 | 0090 | DFB-03 lækage fra SOV for hyd-skuffe | De isolate System | 4 | Awaiting loss approval |  | 1 | 1 | 1 | 0 | APPR SMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /B /07/DFBA-A-3101 | WELLHEAD CTRL PANEL FOR 12 WELLS CTRL | SIWL |  | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0010 | Exchange 6" valve DFCM-HCV-504009 | L3 Prepare rigging equipment | 2 | before 22869 |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0020 | Exchange 6" valve DFCM-HCV-504009 | L3 Isolate equipment | 2 | before 22869 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0030 | Exchange 6" valve DFCM-HCV-504009 | L3 Loosen bolts on flanges | 2 | before 22869 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0040 | Exchange 6" valve DFCM-HCV-504009 | L3 Rig out of valve | 2 | before 22869 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0050 | Exchange 6" valve DFCM-HCV-504009 | L3 Rig in of valve | 2 | before 22869 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0060 | Exchange 6" valve DFCM-HCV-504009 | L2 Install new valve | 2 | before 22869 |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0070 | Exchange 6" valve DFCM-HCV-504009 | L3 Remove isolation | 2 | before 22869 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-05 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027723 | 0080 | Exchange 6" valve DFCM-HCV-504009 | L3 Remove lifting equipment | 2 | before 22869 |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504009 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0010 | Exchange 6" valve DFCM-HCV-504010 | L3 Prepare rigging equipment | 2 | before 22869 |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0020 | Exchange 6" valve DFCM-HCV-504010 | L3 Isolate equipment | 2 | before 22869 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0030 | Exchange 6" valve DFCM-HCV-504010 | L3 Loosen bolts on flanges | 2 | before 22869 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0040 | Exchange 6" valve DFCM-HCV-504010 | L3 Rig out of valve | 2 | before 22869 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0050 | Exchange 6" valve DFCM-HCV-504010 | L3 Rig in of valve | 2 | before 22869 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0060 | Exchange 6" valve DFCM-HCV-504010 | L2 Install new valve | 2 | before 22869 |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0070 | Exchange 6" valve DFCM-HCV-504010 | L3 Remove isolation | 2 | before 22869 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-05 | 2019-12-25 | WDF | 3 | S | 3. Intermediate | 2100027724 | 0080 | Exchange 6" valve DFCM-HCV-504010 | L3 Remove lifting equipment | 2 | before 22869 |  | 8 | 2 | 8 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-HCV-504010 | HAND CONTROL VALVE | DFC-TSEP | TMM902 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0020 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | 4 | BL-TEADFF-OIL SD required | Single block as depressurizing of test manifold is not possible | 3 | 1 | 3 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST | 372723
| MTN-INST | 2023-12-31 | 2019-09-28 | WDF | 3 | V | 3. Intermediate | 2100024623 | 0030 | DFFA-LG-440001 Replace of vent and drain | Changeout vent valve DFFA-LG-440001 | 6 | BL-TEAM |  | 7 | 1 | 7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-V-4401 | HP COMP SUCTION SCRUBBER | DFF-IPHP | SECE INST | INLC | VEN-INST | 329874 | 99000116
| MTN-INST | 2024-01-02 | 2019-09-28 | WDF | 3 | V | 3. Intermediate | 2100024623 | 0040 | DFFA-LG-440001 Replace of vent and drain | Changeout drain valve DFFA-LG-440001 | 6 | BL-TEAM |  | 7 | 1 | 7 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-V-4401 | HP COMP SUCTION SCRUBBER | DFF-IPHP | SECE INST | INLC | VEN-INST |  | 99000116
| PRODTECH | 2024-01-03 | 2019-09-28 | WDF | 3 | V | 3. Intermediate | 2100024623 | 0050 | DFFA-LG-440001 Replace of vent and drain | De-isolate/test DFFA-LG-440001 on V-4401 | 6 | BL-TEAM |  | 3 | 2 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-V-4401 | HP COMP SUCTION SCRUBBER | DFF-IPHP | SECE INST | INLC | VEN-INST |  | 99000116
| MTN-INST | 2024-01-01 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0030 | ESDV-330065 - Fail function test | Demount control and switches | 4 | BL-TEAM | Single block as depressurizing of test manifold is not possible | 2 | 1 | 2 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-MECH | 2024-01-02 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0040 | ESDV-330065 - Fail function test | Demount Valve/Actuator | 4 | BL-TEAM | Single block as depressurizing of test manifold is not possible | 5 | 1 | 5 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-MECH | 2024-01-03 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0050 | ESDV-330065 - Fail function test | Mount new Valve/Actuator | 4 | BL-TEAM | Single block as depressurizing of test manifold is not possible | 5 | 1 | 5 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-INST | 2024-01-04 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0060 | ESDV-330065 - Fail function test | Connect controls and switches | 4 | BL-TEAM | Single block as depressurizing of test manifold is not possible | 2 | 1 | 2 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-MECH | 2024-01-05 | 2020-11-03 | WDF | 3 |  | 3. Intermediate | 2100034740 | 0070 | ESDV-330065 - Fail function test | Deisolate hydralics | 4 | BL-TEAM | Single block as depressurizing of test manifold is not possible | 2 | 1 | 2 | 0 | APPR SECE CMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-OIL | SECE SOREN HVIRRING | INLC | MTN-INST
| MTN-ELEC | 2023-12-31 | 2022-01-25 | WDF | 3 | V | 3. Intermediate | 2100059454 | 0020 | Control voltage DFF 1907A | Troubleshoot and fix if possible | 5 | BL-TEAM |  | 12 | 1 | 12 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /06/DFFA-DP-1907 | UPS DISTRIBUTION BOARD | DFF-IPHP | GMC | INLC | MTN-ELEC
| VEN-INST | 2023-12-31 | 2020-01-18 | WDF | 3 | I | 3. Intermediate | 2100025415 | 0030 | DFBA-FT-35027 Disassemble and repack, va | L3 Disassemble and repack valve for tran | 2 | BL-TEAM W/2100036051 | W/2100036051, 2100025416 | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /B /55/DFBA-FT-35027 | FLOW TRANSM. (FT-I) (SCADA) (METERING) | DFB-W06 | SECE TEAM | INLC | VEN-INST | 353434 | 99000116
| PRODTECH | 2024-01-01 | 2020-01-18 | WDF | 3 | I | 3. Intermediate | 2100025415 | 0040 | DFBA-FT-35027 Disassemble and repack, va | L3 De-Isolation/leaktest DFBA-FT-35027 | 2 | BL-TEAM W/2100036051 | W/2100036051, 2100025416 | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /B /55/DFBA-FT-35027 | FLOW TRANSM. (FT-I) (SCADA) (METERING) | DFB-W06 | SECE TEAM | INLC | VEN-INST |  | 99000116
| MTN-MECH | 2024-04-01 | 2019-05-26 | WPM | D | V | Non Critical | 2400053802 | 0010 | 1Y ÅNDEDRÆTS-LUFTKOMP DFCI-C-5401 | Backload for rep/return DFCI-C-5401 | 5 | Check status with SR | Hold Step | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /07/DFCI-C-5401 | COMPRESSOR FOR BREATHING APPARATUS | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-INST | 2024-04-01 | 2019-05-26 | WPM | D | V | Non Critical | 2400053802 | 0012 | 1Y ÅNDEDRÆTS-LUFTKOMP DFCI-C-5401 | Backload for rep/return DFCI-C-5401 | 5 | Check status with SR | Hold Step | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /07/DFCI-C-5401 | COMPRESSOR FOR BREATHING APPARATUS | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-MECH | 2024-04-02 | 2019-05-26 | WPM | D | V | Non Critical | 2400053802 | 0020 | 1Y ÅNDEDRÆTS-LUFTKOMP DFCI-C-5401 | Re-install DFCI-C-5401 | 5 | Check status with SR | Hold Step | 6 | 1 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /07/DFCI-C-5401 | COMPRESSOR FOR BREATHING APPARATUS | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-INST | 2024-04-02 | 2019-05-26 | WPM | D | V | Non Critical | 2400053802 | 0030 | 1Y ÅNDEDRÆTS-LUFTKOMP DFCI-C-5401 | Re-install DFCI-C-5401 | 5 | Check status with SR | Hold Step | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /07/DFCI-C-5401 | COMPRESSOR FOR BREATHING APPARATUS | NOSD |  | INLC | MTN-MECH |  | 99000142
| VEN-MECH | 2024-01-09 | 2019-12-18 | WGN | 3 |  | 3. Intermediate | 2200002924 | 0040 | scaff/insulation FORCE: 15961 | L3 Force scan 15961 |  | CON-ELEC req'd - Hide | 2022 WTW - PIPE INSP DFF 5 | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /F /28/DFF-2-DPS-050-7569-AD-T | 2 CLOSED DRAIN SOUR LINE | NOSD |  | INLC | CON-SCAF
| VEN-MECH | 2024-01-09 | 2019-03-28 | WGN | 3 |  | 3. Intermediate | 2200003149 | 0040 | CMAT:Scaff / Iso assists FORCE 13528 | L3 Force insp |  | CON-ELEC req'd - Hide |  | 5 | 1 | 5 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /C /28/DFC-4-DP-050-0101-AD-T | 4 CLOSED DRAIN LINE | NOSD |  | INLC | CON-SCAF
| PRODTECH | 2023-12-31 | 2021-02-24 | WDF | 3 | V | 3. Intermediate | 2100040469 | 0020 | DFF_FCV440011A Leaking Gland Packing | Prod prepare permit/isolations w purging | 2 | Covered by TME1787 |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-FCV-440011A | FLOW CONTROL VALVE | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-02-24 | WDF | 3 | V | 3. Intermediate | 2100040469 | 0030 | DFF_FCV440011A Leaking Gland Packing | Gland packing replacement | 2 | Covered by TME1787 |  | 4 | 1 | 4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-FCV-440011A | FLOW CONTROL VALVE | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-TURB | 2024-01-02 | 2021-02-24 | WDF | 3 | V | 3. Intermediate | 2100040469 | 0040 | DFF_FCV440011A Leaking Gland Packing | Stroke/function test FCV valve | 2 | Covered by TME1787 |  | 4 | 1 | 4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-FCV-440011A | FLOW CONTROL VALVE | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-03 | 2021-02-24 | WDF | 3 | V | 3. Intermediate | 2100040469 | 0050 | DFF_FCV440011A Leaking Gland Packing | Prod deisolate w function/leak test | 2 | Covered by TME1787 |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-FCV-440011A | FLOW CONTROL VALVE | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2021-02-24 | WDF | 3 | V | 3. Intermediate | 2100040469 | 0060 | DFF_FCV440011A Leaking Gland Packing | Housekeeping/backload remainings | 2 | Covered by TME1787 |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /32/DFFA-FCV-440011A | FLOW CONTROL VALVE | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-TELE | 2024-02-14 | 2019-07-04 | WRO | 4 | V | 4. Long | 2300000959 | 0020 | SCADA SW for ENG469L Vacuum pump | Telecom support | 2 | date TBC | 2020 Project | 6 | 0 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /04/DFBA-FP-2002 | SCADA RTU | NE | ENG469L | INLC | MTN-TELE
| MTN-TELE | 2024-02-14 | 2019-07-05 | WRO | 4 | V | 4. Long | 2300000961 | 0020 | SCADA SW for ENG469M Polyelectric pumps | Telecom support | 2 | date TBC | 2020 Project | 6 | 0 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /04/DFBA-FP-2036 | SCADA RTU | NE | ENG469M | INLC | MTN-TELE
| MTN-TELE | 2024-02-14 | 2019-07-05 | WRO | 4 | V | 4. Long | 2300000964 | 0020 | SCADA SW for ENG469Q Catalyst pumps | Telecom support | 2 | date TBC | 2020 Project | 6 | 0 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /04/DFBA-FP-2036 | SCADA RTU | NE | ENG469Q | INLC | MTN-TELE
| MTN-MECH | 2024-01-05 | 2021-03-20 | WDF | 3 | V | 3. Intermediate | 2100044912 | 0070 | DFG PCV-570437A Dårlig integritet | Mount new Actuator | ID 70 | Del est. Dec-2022 |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /G /70/DFGA-PCV-570437A | PRESSURE CONTROL VALVE | DFG-3590 |  | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2017-07-13 | WDF | 4 | V | 4. Long | 2100025103 | 0050 | @+DFFA-FCV-360067 stem ekstern læk | Rigging assistance during removal of the |  | DFF-OIL outage |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-FCV-360067 | FLOW CONTROL VALVE | DFF-OIL | DFF | INLC | MTN-MECH |  | DK0500013711
| MTN-MECH | 2023-12-31 | 2017-07-13 | WDF | 4 | V | 4. Long | 2100025103 | 0070 | @+DFFA-FCV-360067 stem ekstern læk | Replacement of the stem packing |  | DFF-OIL outage |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-FCV-360067 | FLOW CONTROL VALVE | DFF-OIL | DFF | INLC | MTN-MECH |  | DK0500013711
| MTN-RIGG | 2023-12-31 | 2017-07-13 | WDF | 4 | V | 4. Long | 2100025103 | 0080 | @+DFFA-FCV-360067 stem ekstern læk | Rigging assistance during reinstallation |  | DFF-OIL outage |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-FCV-360067 | FLOW CONTROL VALVE | DFF-OIL | DFF | INLC | MTN-MECH |  | DK0500013711
| MTN-MECH | 2024-01-01 | 2017-07-13 | WDF | 4 | V | 4. Long | 2100025103 | 0090 | @+DFFA-FCV-360067 stem ekstern læk | Reinstallation of the actuator |  | DFF-OIL outage |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-FCV-360067 | FLOW CONTROL VALVE | DFF-OIL | DFF | INLC | MTN-MECH |  | DK0500013711
| MTN-MECH | 2024-01-01 | 2017-07-13 | WDF | 4 | V | 4. Long | 2100025103 | 0100 | @+DFFA-FCV-360067 stem ekstern læk | Reinstallation of the air supply and pos |  | DFF-OIL outage |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-FCV-360067 | FLOW CONTROL VALVE | DFF-OIL | DFF | INLC | MTN-MECH |  | DK0500013711
| PRODTECH | 2024-01-02 | 2017-07-13 | WDF | 4 | V | 4. Long | 2100025103 | 0110 | @+DFFA-FCV-360067 stem ekstern læk | Desafing and leak test |  | DFF-OIL outage |  | 0.1 | 1 | 0.1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-FCV-360067 | FLOW CONTROL VALVE | DFF-OIL | DFF | INLC | MTN-MECH |  | DK0500013711
| MTN-MECH | 2023-12-31 | 2018-03-22 | WGN | 3 | V | 3. Intermediate | 2200003013 | 0020 | DFA 05 Intern lækage i hydraulikskuf | L3 Replace Hydraulic drawer with spare | 4 | Drawer req. |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O05 |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2018-03-22 | WGN | 3 | V | 3. Intermediate | 2200003013 | 0030 | DFA 05 Intern lækage i hydraulikskuf | L3 Desafing of DFAA-A-3102 | 4 | Drawer req. |  | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O05 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-03-22 | WGN | 3 | V | 3. Intermediate | 2200003013 | 0035 | DFA 05 Intern lækage i hydraulikskuf | L3 Backload Drawer to JHO164 | 4 | Drawer req. |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O05 |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-03-22 | WGN | 3 | V | 3. Intermediate | 2200003013 | 0040 | DFA 05 Intern lækage i hydraulikskuf | L3 Rep drawer and return as spare | 4 | Drawer req. |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /A /07/DFAA-A-3102 | WELLHEAD CONTROL PANEL 12 WELLS CONTROL | DFA-O05 |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0010 | Alu JB on KRA06 CVA is heavily corroded | Rigging assistance pre work | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0020 | Alu JB on KRA06 CVA is heavily corroded | Isolate vavle | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-02 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0030 | Alu JB on KRA06 CVA is heavily corroded | changeout Choke | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 8 | 1 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0040 | Alu JB on KRA06 CVA is heavily corroded | Rigging assistance | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 8 | 1 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| MTN-INST | 2024-01-04 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0050 | Alu JB on KRA06 CVA is heavily corroded | instrument hookup and test | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0060 | Alu JB on KRA06 CVA is heavily corroded | de-isolate | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-05 | 2022-02-18 | WDF | 3 | V | 3. Intermediate | 2100060624 | 0070 | Alu JB on KRA06 CVA is heavily corroded | Rigging post work | 6 | DUCSAT next window, SIWL | DUCSAT next window, SIWL | 5 | 1 | 5 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | KR /A /10/KRA-CVA-30507 | HYDR. OPERATED CHOKE VALVE SLOT NO.3) | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-01-03 | WPM | B | V | Safety & Env.Related | 2400176973 | 0002 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-GEN) | ISOLATION | 5 | Duplicate w/2400202504 |  | 1 | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-GEN |  | INLC | MTN-MECH
| MTN-ELEC | 2023-12-31 | 2022-01-03 | WPM | B | V | Safety & Env.Related | 2400176973 | 0010 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-GEN) | REGISTRATION OF WORKING HOURS | 5 | Duplicate w/2400202504 |  | 1 | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-GEN |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2022-01-03 | WPM | B | V | Safety & Env.Related | 2400176973 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-GEN) | REGISTRATION OF WORKING HOURS | 5 | Duplicate w/2400202504 |  | 3 | 1 | 3 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-GEN |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-01-03 | WPM | B | V | Safety & Env.Related | 2400176973 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFF-GEN) | DE-ISOLATION | 5 | Duplicate w/2400202504 |  | 1 | 1 | 1 | 0 | APPR AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFF-GEN |  | INLC | MTN-MECH
| MTN-TELE | 2024-01-31 | 2021-06-24 | WGN | 3 | V | 3. Intermediate | 2200006515 | 0010 | ESD2 shutdown test ref EXP-407 DAB | ESD2 shutdown test ref EXP-407 DAB | 2 | Glycol SD |  | 0.5 | 1 | 0.5 | 0 | APPR AWSD AWSC | APPR OPND | REL MANC NMAT PRC SETC | DA /B /03/DB-FP-0220 | FIELD PANEL ESD | DAB-OIL |  | INLC | MTN-TELE
| MTN-TELE | 2024-12-31 | 2021-06-24 | WGN | 3 | V | 3. Intermediate | 2200006516 | 0010 | ESD2 shutdown test ref EXP-407 KRA | ESD2 shutdown test ref EXP-407 KRA | 2 | Glycol SD |  | 0.5 | 1 | 0.5 | 0 | APPR AWSD AWSC | APPR OPND | REL MANC NMAT PRC SETC | KR /A /04/KRA-FP-2269 | SCADA AND ESD RTU | KRA-OIL |  | INLC | MTN-TELE
| MTN-ROPE | 2023-12-31 | 2018-11-25 | WDF | 3 | I | 3. Intermediate | 2100023656 | 0009 | Replace valve handles DFEZ-P-5012 | Isolation | 2 | IOP | IOP - Wait prod? w/PVI 29/5 | 6 | 1 | 6 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /28/DFEZ-P-5012 | CLOSED DRAIN PUMP | DFE-OIL | SECE - MECH | INLC | MTN-MECH
| MTN-MECH | 2024-01-01 | 2018-11-25 | WDF | 3 | I | 3. Intermediate | 2100023656 | 0030 | Replace valve handles DFEZ-P-5012 | L2 Replace /test new valves as on P&ID | 2 | IOP | IOP - Wait prod? w/PVI 29/5 | 10 | 1 | 10 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /28/DFEZ-P-5012 | CLOSED DRAIN PUMP | DFE-OIL | SECE - MECH | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2018-11-25 | WDF | 3 | I | 3. Intermediate | 2100023656 | 0040 | Replace valve handles DFEZ-P-5012 | L2 Remove ihibit DFEZ-P-5012 | 2 | IOP | IOP - Wait prod? w/PVI 29/5 | 1 | 1 | 1 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /28/DFEZ-P-5012 | CLOSED DRAIN PUMP | DFE-OIL | SECE - MECH | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2018-11-25 | WDF | 3 | I | 3. Intermediate | 2100023656 | 0050 | Replace valve handles DFEZ-P-5012 | L3 De-Safing/test of DFEZ-P-5012 | 2 | IOP | IOP - Wait prod? w/PVI 29/5 | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /28/DFEZ-P-5012 | CLOSED DRAIN PUMP | DFE-OIL | SECE - MECH | INLC | MTN-MECH
| MTN-SCAF | 2023-12-31 | 2021-12-03 | WDF | 3 | V | 3. Intermediate | 2100056840 | 0075 | Refurbished Winch to be installed LB2 an | Scaffolding for access to winch up/down | 2 | IOP - RC | IOP + 2100024575 | 20 | 2 | 20 | 0 | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /G /02/DFGA-X-0702 | LIFEBOAT | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2021-12-03 | WDF | 3 | V | 3. Intermediate | 2100056840 | 0080 | Refurbished Winch to be installed LB2 an | Intall winch | 2 | IOP - RC | IOP + 2100024575 | 20 | 2 | 20 | 0 | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /G /02/DFGA-X-0702 | LIFEBOAT | NOSD |  | INLC | MTN-MECH
| PRODTECH | 2024-01-07 | 2021-12-03 | WDF | 3 | V | 3. Intermediate | 2100056840 | 0090 | Refurbished Winch to be installed LB2 an | De-isolate Lifeboat/HPU | 2 | IOP - RC | IOP + 2100024575 | 1 | 1 | 1 | 0 | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /G /02/DFGA-X-0702 | LIFEBOAT | NOSD |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-07 | 2021-12-03 | WDF | 3 | V | 3. Intermediate | 2100056840 | 0100 | Refurbished Winch to be installed LB2 an | Loadtest LB2 (later by Verhoef) | 2 | IOP - RC | IOP + 2100024575 | 1 | 1 | 1 | 0 | APPR SECE APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PRC SETC | DF /G /02/DFGA-X-0702 | LIFEBOAT | NOSD |  | INLC | MTN-MECH
| VEN-ACCO | 2023-12-30 | 2021-02-19 | WDF | 3 | S | 3. Intermediate | 2100044975 | 0070 | Sewage pipe at sauna blocket | Removal of old Sewage spool | 2 | Job done - CNF |  | 30 | 2 | 30 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /82/DFCM-A-5101 | SEWAGE TREATMENT UNIT | NOSD |  | INLC | VEN-ACCO
| VEN-ACCO | 2024-01-01 | 2021-02-19 | WDF | 3 | S | 3. Intermediate | 2100044975 | 0080 | Sewage pipe at sauna blocket | Prepare for new Blücher spool | 2 | Job done - CNF |  | 30 | 2 | 30 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /82/DFCM-A-5101 | SEWAGE TREATMENT UNIT | NOSD |  | INLC | VEN-ACCO
| VEN-ACCO | 2024-01-03 | 2021-02-19 | WDF | 3 | S | 3. Intermediate | 2100044975 | 0090 | Sewage pipe at sauna blocket | Installation of new spool | 2 | Job done - CNF |  | 30 | 2 | 30 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /82/DFCM-A-5101 | SEWAGE TREATMENT UNIT | NOSD |  | INLC | VEN-ACCO
| MTN-RIGG | 2023-12-31 | 2021-03-07 | WDF | 3 | S | 3. Intermediate | 2100044218 | 0040 | DFFA-HCV-440027-U defective/seized Gearb | Rigger Assistance | 2 | Mat eta 15/7 |  | 12 | 2 | 12 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440027-U | HCV UPSTREAM PSV-420027 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-03-07 | WDF | 3 | S | 3. Intermediate | 2100044218 | 0050 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | 2 | Mat eta 15/7 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440027-U | HCV UPSTREAM PSV-420027 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-03-07 | WDF | 3 | S | 3. Intermediate | 2100044218 | 0060 | DFFA-HCV-440027-U defective/seized Gearb | Valve installation w bolt torquing | 2 | Mat eta 15/7 |  | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440027-U | HCV UPSTREAM PSV-420027 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-03-07 | WDF | 3 | S | 3. Intermediate | 2100044218 | 0070 | DFFA-HCV-440027-U defective/seized Gearb | Prod deisolate w function/leak test | 2 | Mat eta 15/7 |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440027-U | HCV UPSTREAM PSV-420027 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2021-03-07 | WDF | 3 | S | 3. Intermediate | 2100044218 | 0080 | DFFA-HCV-440027-U defective/seized Gearb | Housekeeping/reinstate protection shield | 2 | Mat eta 15/7 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440027-U | HCV UPSTREAM PSV-420027 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-02 | 2021-03-07 | WDF | 3 | S | 3. Intermediate | 2100044218 | 0090 | DFFA-HCV-440027-U defective/seized Gearb | Rigger equipment removal | 2 | Mat eta 15/7 |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /31/DFFA-HCV-440027-U | HCV UPSTREAM PSV-420027 | DFF-IPHP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0010 | XCV-354164 air leakage on actuator | Rig-up scaffold for XCV-354164 | 2 | Mat eta 16/12 |  | 16 | 2 | 16 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-RIGG | 2024-01-02 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0020 | XCV-354164 air leakage on actuator | Rig-up hoist for XCV-354164 | 2 | Mat eta 16/12 |  | 8 | 2 | 8 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-INST | 2024-01-04 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0050 | XCV-354164 air leakage on actuator | Demoll air supply | 2 | Mat eta 16/12 |  | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-INST | 2024-01-06 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0080 | XCV-354164 air leakage on actuator | Re-install electric installation | 2 | Mat eta 16/12 |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| MTN-INST | 2024-01-06 | 2020-10-24 | WDF | 3 | V | 3. Intermediate | 2100038894 | 0090 | XCV-354164 air leakage on actuator | Re-install air supply | 2 | Mat eta 16/12 |  | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL CSER GMPS MANC PRC SETC | DF /F /51/DFFA-XCV-354164 | UNCLASSIFIED VALVE | DFF-3520 | DANXCV-2021 | INT | MTN-MECH
| PRODTECH | 2023-12-31 | 2020-08-10 | WDF | 4 | V | 4. Long | 2100023101 | 0010 | REplace 1" drainvalve. | Isolate equipment | 2 | Mat in WH/Jannik | 300B S/D | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2020-08-10 | WDF | 4 | V | 4. Long | 2100023101 | 0020 | REplace 1" drainvalve. | Exchange valve | 2 | Mat in WH/Jannik | 300B S/D | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2020-08-10 | WDF | 4 | V | 4. Long | 2100023101 | 0030 | REplace 1" drainvalve. | Remove isolation | 2 | Mat in WH/Jannik | 300B S/D | 6 | 2 | 6 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2024-01-03 | 2020-08-10 | WDF | 4 | V | 4. Long | 2100023101 | 0040 | REplace 1" drainvalve. | Remove hop up | 2 | Mat in WH/Jannik | 300B S/D | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DAN-WI |  | INLC | MTN-MECH |  | 99000116
| MTN-TURB | 2023-12-31 | 2021-06-01 | WDF | 3 | V | 3. Intermediate | 2100045551 | 0010 | LM-1600 Starter hose FX-308 replacement | Replace flexhose fx-308 | 2 | Mat not ordered |  | 5 | 1 | 5 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /54/DFFA-PT-3520 | POWER TURBINE | DFF-3520 |  | INLC | MTN-TURB
| PRODTECH | 2023-12-31 | 2020-12-08 | WDF | 3 | V | 3. Intermediate | 2100041176 | 0060 | ESDV-38169 failing inflow test DGS 63863 | Deisolate ESDV | 2 | Mat. req. |  | 4 | 1 | 4 | 0 | APPR SECE APOG WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF MANC PPRT PRC SETC | DF /A /12/DFAA-ESDV-38169 | SHUTDOWN VALVE, KRA INLET | KRA-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023869 | 0020 | SMAT:DFC Defekt HCV Upstrøms FE-50787 | Safing |  | Move way out of plan |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-07 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023869 | 0040 | SMAT:DFC Defekt HCV Upstrøms FE-50787 | Desafing |  | Move way out of plan |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023870 | 0010 | SMAT:DFC Defekt HCV Nedstrøms FE-50787 | Safing |  | Move way out of plan |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-07 | 2020-02-08 | WDF | 4 | V | 4. Long | 2100023870 | 0025 | SMAT:DFC Defekt HCV Nedstrøms FE-50787 | Desafing |  | Move way out of plan |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFC-TSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-08-22 | WDF | 3 | I | 3. Intermediate | 2100025102 | 0010 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Construction of scaffolding | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /28/DFFA-T-5052 | DRAINS CPI SEPARATOR | DFF-OIL | DFF | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-08-22 | WDF | 3 | I | 3. Intermediate | 2100025102 | 0070 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Demol of scaffolding | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /28/DFFA-T-5052 | DRAINS CPI SEPARATOR | DFF-OIL | DFF | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0010 | Udskiftning af 10" HCV v. EP-3803 | Construction of scaffolding | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0020 | Udskiftning af 10" HCV v. EP-3803 | Preparation for rigging | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 2 | 2.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0025 | Udskiftning af 10" HCV v. EP-3803 | Checking of the received materials | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 2 | 2.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| PRODTECH | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0030 | Udskiftning af 10" HCV v. EP-3803 | Safing of the HCV | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2024-01-01 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0040 | Udskiftning af 10" HCV v. EP-3803 | Rigging assistance for removal of the ol | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2024-01-01 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0045 | Udskiftning af 10" HCV v. EP-3803 | Removal of the old HCV | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2024-01-01 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0048 | Udskiftning af 10" HCV v. EP-3803 | Rigging assistance for installation of t | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2024-01-02 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0050 | Udskiftning af 10" HCV v. EP-3803 | Installation of the new HCV | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 2 | 8.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| PRODTECH | 2024-01-02 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0060 | Udskiftning af 10" HCV v. EP-3803 | Desafing and leak test | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0070 | Udskiftning af 10" HCV v. EP-3803 | Demol of scaffolding | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 17.4 | 2 | 17.4 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-SCAF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0080 | Udskiftning af 10" HCV v. EP-3803 | Clean-up | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 2 | 2.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PIPF | 2023-12-31 | 2016-07-18 | WDF | 3 | S | 3. Intermediate | 2100027732 | 0090 | Udskiftning af 10" HCV v. EP-3803 | Clean-up | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 2.7 | 2 | 2.7 | 0 | APPR WMAT AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /A /12/DFAA-HCV-380032 | HAND CONTROL VALVE | KRA-OIL | TMM902 | INLC | MTN-PIPF |  | DK0500013711
| MTN-PAIN | 2024-01-01 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0020 | DFF-20 FCV-290120 er rust beskadiget | Forberedelse + Permit | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-01 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0030 | DFF-20 FCV-290120 er rust beskadiget | Tilrigning | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-01 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0040 | DFF-20 FCV-290120 er rust beskadiget | Afskærmning med blå net | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| VEN-ELEC | 2024-01-02 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0044 | DFF-20 FCV-290120 er rust beskadiget | Løsnings Val Controls conv./Air supply | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-02 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0045 | DFF-20 FCV-290120 er rust beskadiget | Sandblæsning | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 6.7 | 1 | 6.7 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-03 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0050 | DFF-20 FCV-290120 er rust beskadiget | Afskærmning fjernes + oprydning | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-03 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0060 | DFF-20 FCV-290120 er rust beskadiget | Afdækning for maling | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PIPF | 2024-01-03 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0070 | DFF-20 FCV-290120 er rust beskadiget | Nye bolte monteres en af gangen | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-04 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0080 | DFF-20 FCV-290120 er rust beskadiget | Opmaling | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 12.1 | 1 | 12.1 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| VEN-ELEC | 2024-01-05 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0085 | DFF-20 FCV-290120 er rust beskadiget | Genetabler Val Controls conv/Air supply | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 5.4 | 1 | 5.4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| VEN-ELEC | 2024-01-06 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0086 | DFF-20 FCV-290120 er rust beskadiget | Funktionstest af flow control ventil | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 6.7 | 1 | 6.7 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-07 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0090 | DFF-20 FCV-290120 er rust beskadiget | Afdækning fjernes | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-07 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0100 | DFF-20 FCV-290120 er rust beskadiget | Blå net fjernes | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| PRODTECH | 2024-01-07 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0102 | DFF-20 FCV-290120 er rust beskadiget | Desafing af line/FCV-290120 | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 4 | 1 | 4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| MTN-PAIN | 2024-01-08 | 2018-02-28 | WGN | 3 | I | 3. Intermediate | 2200003251 | 0110 | DFF-20 FCV-290120 er rust beskadiget | Slut rengøring | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /F /37/DFFA-FCV-290120 | FLOW CONTROL VALVE -GAS LIFT TO WELL 20 | DFF-O20 | TMM | INLC | MTN-MECH
| PRODTECH | 2024-01-12 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0040 | CMAT:BOAT, Udskift af afspæringsventil f | Safing af hydraulik forsyningslinje til | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2024-01-20 | 2018-11-03 | WGN | 4 | V | 4. Long | 2200003252 | 0080 | CMAT:BOAT, Udskift af afspæringsventil f | Desafing og leaktest | 2 | Moved to 2022 | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR AWSD AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /03 | ESD AND FIRE & GAS | DAN-FRYS | TMM | INLC | MTN-PIPF |  | 99000116
| PRODTECH | 2023-12-31 | 2017-11-26 | WDF | 3 | V | 3. Intermediate | 2100025443 | 0010 | CMAT:DFC fuelgas udskift trim @ LCV-5769 | Safing af LVC-57690 - FG filter V-5705 |  | Moved-RPJ006 |  | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /70/DFCM-LCV-57690 | LEVEL CONTROL VALVE FUEL GAS FILTER | DFC-5705 | FETI | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2017-11-26 | WDF | 3 | V | 3. Intermediate | 2100025443 | 0020 | CMAT:DFC fuelgas udskift trim @ LCV-5769 | Udskiftning af trim - LCV-57690 |  | Moved-RPJ006 |  | 12 | 1 | 12 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /70/DFCM-LCV-57690 | LEVEL CONTROL VALVE FUEL GAS FILTER | DFC-5705 | FETI | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2017-11-26 | WDF | 3 | V | 3. Intermediate | 2100025443 | 0030 | CMAT:DFC fuelgas udskift trim @ LCV-5769 | Desafing |  | Moved-RPJ006 |  | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /C /70/DFCM-LCV-57690 | LEVEL CONTROL VALVE FUEL GAS FILTER | DFC-5705 | FETI | INLC | MTN-MECH |  | 99000116
| MTN-SCAF | 2023-12-31 | 2017-11-06 | WDF | 3 | V | 3. Intermediate | 2100027048 | 0004 | CMAT:Udskiftning af XCV-30664 DFB-02 | Opsætning af taljer | 2 | Moved-RPJ006 | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 1 | 8.7 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /B /10/DFBA-XCV-30664 | UNCLASSIFIED VALVE, MFB-02F | DFB-OIL | MFB02 | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-03-24 | WDF | 3 | S | 3. Intermediate | 2100042074 | 0030 | Internal leaking upstream HCV-035219 | replace HCV and deluge valve | 2 | OIM FW |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /01/DFFA-HCV-035219 | LO - HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2021-03-24 | WDF | 3 | S | 3. Intermediate | 2100042074 | 0040 | Internal leaking upstream HCV-035219 | Assist MECH with rigging of valve/spool | 2 | OIM FW |  | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /01/DFFA-HCV-035219 | LO - HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-03-24 | WDF | 3 | S | 3. Intermediate | 2100042074 | 0050 | Internal leaking upstream HCV-035219 | -Deisolate HCV by dry up freezeplug | 2 | OIM FW |  | 4 | 2 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /01/DFFA-HCV-035219 | LO - HAND CONTROL VALVE | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-07-24 | WDF | 4 | S | 4. Long | 2100042166 | 0020 | Deluge downstream valve HCV-035326 | Replace HCV-035326 and deluge valve | 2 | OIM FW |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /01/DFFA-HCV-035326 | LOCKED VALVE REGISTER | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2021-07-24 | WDF | 4 | S | 4. Long | 2100042166 | 0030 | Deluge downstream valve HCV-035326 | Assist MECH with rigging/mount of valve | 2 | OIM FW |  | 4 | 1 | 4 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /01/DFFA-HCV-035326 | LOCKED VALVE REGISTER | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2021-07-24 | WDF | 4 | S | 4. Long | 2100042166 | 0040 | Deluge downstream valve HCV-035326 | -Deisolate deluge valve and HCV-035326 | 2 | OIM FW |  | 2 | 1 | 2 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /F /01/DFFA-HCV-035326 | LOCKED VALVE REGISTER | DFF-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2019-03-09 | WDF | 3 | S | 3. Intermediate | 2100024044 | 0015 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | 2 | OIM FW INL |  | 18 | 1 | 18 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-035242 | LO - HAND CONTROL VALVE | DAN-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-04 | 2019-03-09 | WDF | 3 | S | 3. Intermediate | 2100024044 | 0020 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 Isolate valve | 2 | OIM FW INL |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-035242 | LO - HAND CONTROL VALVE | DAN-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-05 | 2019-03-09 | WDF | 3 | S | 3. Intermediate | 2100024044 | 0030 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L1 replace valve with new. | 2 | OIM FW INL |  | 10 | 2 | 10 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-035242 | LO - HAND CONTROL VALVE | DAN-OIL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-06 | 2019-03-09 | WDF | 3 | S | 3. Intermediate | 2100024044 | 0040 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 Deisolate valve. | 2 | OIM FW INL |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-035242 | LO - HAND CONTROL VALVE | DAN-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-07 | 2019-03-09 | WDF | 3 | S | 3. Intermediate | 2100024044 | 0045 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch off | 2 | OIM FW INL |  | 1 | 1 | 1 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-035242 | LO - HAND CONTROL VALVE | DAN-OIL |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-08 | 2019-03-09 | WDF | 3 | S | 3. Intermediate | 2100024044 | 0050 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 Clean up after work. | 2 | OIM FW INL |  | 2 | 2 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /01/DFFA-HCV-035242 | LO - HAND CONTROL VALVE | DAN-OIL |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0006 | DFC HCV-03067 LV05 Intern læk | Permit Vendor | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 13 | 1 | 13 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| PRODTECH | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0030 | DFC HCV-03067 LV05 Intern læk | Isolate DFC-HCV-03067 | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| VEN-MECH | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0035 | DFC HCV-03067 LV05 Intern læk | Erect freeze box & tray | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 2 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| VEN-MECH | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0056 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 16 | 2 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| PRODTECH | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0060 | DFC HCV-03067 LV05 Intern læk | De-isolate DFC-HCV-03067 | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| PRODTECH | 2024-01-08 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0020 | LV 24, DFCI-HCV-03349 Intern læk | Isolering af linje | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| PRODTECH | 2024-01-10 | 2015-08-13 | WDF | 3 | S | 3. Intermediate | 2100027694 | 0046 | LV 24, DFCI-HCV-03349 Intern læk | De-isolering | 2 | OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 3 | 1 | 3 | 0 | APPR PMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03349 | LO - HAND CONTROL VALVE | DAN-FRYS | TMM | INLC | MTN-MECH |  | DK0500013007
| MTN-RIGG | 2023-12-30 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0040 | DFF Replace Seawater pump P-5301 | L3 Set up of hoists for rigging | 2 | OIM/part of SD april 23 |  | 32 | 2 | 32 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-SCAF | 2023-12-30 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0041 | DFF Replace Seawater pump P-5301 | Build Barrier around hatches | 2 | OIM/part of SD april 23 |  | 20 | 2 | 20 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-ROUS | 2024-01-01 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0045 | DFF Replace Seawater pump P-5301 | Crane op - remove hatches | 2 | OIM/part of SD april 23 |  | 8 | 2 | 8 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-ROUS | 2024-01-09 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0065 | DFF Replace Seawater pump P-5301 | Crane assistance during removal | 2 | OIM/part of SD april 23 |  | 60 | 2 | 60 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-RIGG | 2024-01-01 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0070 | DFF Replace Seawater pump P-5301 | L3 Remove pump mechanically | 2 | OIM/part of SD april 23 |  | 90 | 3 | 90 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-RIGG | 2024-01-09 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0080 | DFF Replace Seawater pump P-5301 | L3 Rigger assistance for replacement | 2 | OIM/part of SD april 23 |  | 48 | 2 | 48 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-RIGG | 2024-01-09 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0100 | DFF Replace Seawater pump P-5301 | L3 Camera inspection of position tube | 2 | OIM/part of SD april 23 |  | 12 | 2 | 12 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-RIGG | 2024-01-09 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0105 | DFF Replace Seawater pump P-5301 | L3 Install pump | 2 | OIM/part of SD april 23 |  | 95 | 3 | 95 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| VEN-ELEC | 2024-01-09 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0120 | DFF Replace Seawater pump P-5301 | L3 Connect electrics | 2 | OIM/part of SD april 23 |  | 16 | 2 | 16 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| PRODTECH | 2024-01-10 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0130 | DFF Replace Seawater pump P-5301 | L3 De-isolate & function test | 2 | OIM/part of SD april 23 |  | 8 | 2 | 8 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-RIGG | 2024-01-11 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0140 | DFF Replace Seawater pump P-5301 | L3 Remove hoists | 2 | OIM/part of SD april 23 |  | 24 | 2 | 24 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| MTN-SCAF | 2024-01-11 | 2019-04-28 | WDF | 3 | V | 3. Intermediate | 2100027212 | 0150 | DFF Replace Seawater pump P-5301 | Install hatches, remove scaff | 2 | OIM/part of SD april 23 |  | 25 | 3 | 25 | 0 | APPR APOG WMAT AWSC RDBL | APPR OPND | REL PCNF PRT MANC PRC SETC | DF /F /50/DFFA-P-5301 | SEAWATER LIFT PUMP | DFF-3580 | RCEOOS | INLC | MTN-MECH
| PRODTECH | 2025-01-15 | 2020-03-10 | WPM | C | V | Business Critical | 2400050237 | 0010 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 2 | Parked 1/11 | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-V-5019 | TEST SAND REMOVAL VESSEL | NOSD |  | INLC | MTN-MECH |  | 99000142
| VEN-MECH | 2025-01-26 | 2020-03-10 | WPM | C | V | Business Critical | 2400050237 | 0030 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 2 | Parked 1/11 | OTS req. ¦10/01/2022 Wrk. Ctr. Migration | 48 | 4 | 48 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-V-5019 | TEST SAND REMOVAL VESSEL | NOSD |  | INLC | MTN-MECH |  | 99000142
| PRODTECH | 2025-01-31 | 2020-03-10 | WPM | C | V | Business Critical | 2400050237 | 0050 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 1Y HYDRO/SAND CYCONER DFFA-5017/18/19 | 4 | Parked 1/11 | ¦10/01/2022 Wrk. Ctr. Migration | 12 | 1 | 12 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /27/DFFA-V-5019 | TEST SAND REMOVAL VESSEL | NOSD |  | INLC | MTN-MECH |  | 99000142
| PRODTECH | 2024-01-01 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0020 | Install new actuator with switchbox(DAD) | L3 Isolate ZSO-38034 | 2 | pigging priority | DUCSAT, check MAT | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-01 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0030 | Install new actuator with switchbox(DAD) | L2 Dismantle elec. from act. switchbox | 2 | pigging priority | DUCSAT, check MAT | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-INST | 2024-01-02 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0040 | Install new actuator with switchbox(DAD) | L2 Dismantle hydraulic from actuator | 2 | pigging priority | DUCSAT, check MAT | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-MECH | 2024-01-02 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0050 | Install new actuator with switchbox(DAD) | L2 Remove old actuator | 2 | pigging priority | DUCSAT, check MAT | 8 | 2 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-ROUS | 2024-01-02 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0060 | Install new actuator with switchbox(DAD) | L2 Assist removing actuator | 2 | pigging priority | DUCSAT, check MAT | 4 | 1 | 4 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-MECH | 2024-01-03 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0070 | Install new actuator with switchbox(DAD) | L2 Install new actuator with switchbox | 2 | pigging priority | DUCSAT, check MAT | 8 | 2 | 8 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-ROUS | 2024-01-03 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0080 | Install new actuator with switchbox(DAD) | L2 Assist in installation new actu. | 2 | pigging priority | DUCSAT, check MAT | 4 | 1 | 4 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-INST | 2024-01-04 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0090 | Install new actuator with switchbox(DAD) | L2 Re-install hydraulic to actuator | 2 | pigging priority | DUCSAT, check MAT | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-ELEC | 2024-01-05 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0100 | Install new actuator with switchbox(DAD) | L2 Re-install elec. to actu. switchbox | 2 | pigging priority | DUCSAT, check MAT | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| QAQCMECH | 2024-01-05 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0110 | Install new actuator with switchbox(DAD) | L2 Test and QC | 2 | pigging priority | DUCSAT, check MAT | 2 | 1 | 2 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INT | MTN-ELEC
| PRODTECH | 2024-01-06 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0120 | Install new actuator with switchbox(DAD) | L3 De-Isolate ZSO-38034 | 2 | pigging priority | DUCSAT, check MAT | 3 | 1 | 3 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| MTN-ROUS | 2024-01-06 | 2018-06-19 | WDF | 3 | V | 3. Intermediate | 2100022793 | 0130 | Install new actuator with switchbox(DAD) | L3 Rig-down hoist and clean-up | 2 | pigging priority | DUCSAT, check MAT | 5 | 2 | 5 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DA /D /50/DD-ESDV-38034 | WATER INJ. RISER FRA DAN"F" SHUT DOWN | DAB-WI | @US37 | INLC | MTN-ELEC
| PRODTECH | 2023-12-31 | 2022-12-21 | WPM | C | V | Business Critical | 2400116269 | 0011 | NII Inspection DB-V-5001 | Isolering af Heat tracing | 2 | PM 30/06/2022 | POST WELLSAT/DUCSAT | 4 | 2 | 4 | 0 | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DA /B /28/DB-V-5001 | DRAIN VESSEL | NOSD | DANBPVI22 | INLC | MTN-PAIN
| MTN-LAGG | 2024-01-01 | 2022-12-21 | WPM | C | V | Business Critical | 2400116269 | 0021 | NII Inspection DB-V-5001 | Afmontering af Isolering | 2 | PM 30/06/2022 | POST WELLSAT/DUCSAT | 30 | 2 | 30 | 0 | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DA /B /28/DB-V-5001 | DRAIN VESSEL | NOSD | DANBPVI22 | INLC | MTN-PAIN
| MTN-ELEC | 2024-01-02 | 2022-12-21 | WPM | C | V | Business Critical | 2400116269 | 0031 | NII Inspection DB-V-5001 | Afmontering af Heat tracing | 2 | PM 30/06/2022 | POST WELLSAT/DUCSAT | 5 | 1 | 5 | 0 | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DA /B /28/DB-V-5001 | DRAIN VESSEL | NOSD | DANBPVI22 | INLC | MTN-PAIN
| VEN-INSP | 2024-01-04 | 2022-12-21 | WPM | C | V | Business Critical | 2400116269 | 0041 | NII Inspection DB-V-5001 | Scanning af behold Incl. Xray | 2 | PM 30/06/2022 | POST WELLSAT/DUCSAT | 144 | 2 | 144 | 0 | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DA /B /28/DB-V-5001 | DRAIN VESSEL | NOSD | DANBPVI22 | INLC | MTN-PAIN
| MTN-LAGG | 2024-01-11 | 2022-12-21 | WPM | C | V | Business Critical | 2400116269 | 0051 | NII Inspection DB-V-5001 | Brandvagt til Xray | 2 | PM 30/06/2022 | POST WELLSAT/DUCSAT | 36 | 1 | 36 | 0 | APPR SECE CMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DA /B /28/DB-V-5001 | DRAIN VESSEL | NOSD | DANBPVI22 | INLC | MTN-PAIN
| MTN-MECH | 2023-12-31 | 2017-01-12 | WDF | 3 | I | 3. Intermediate | 2100025040 | 0010 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | 2 | Possible Iso issue | Repair requiired on 2100022386 | 12 | 2 | 12 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-PDCV-500606 | PRESSURE DIFF. CONTROL VALVE | DFF-TSEP | DFF | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2022-07-08 | WPM | B | V | Safety & Env.Related | 2400202414 | 0010 | 1Y W-MIST NOZZLE A-0462 for IP/HP | 21.02.2013 | 2 | Pushed to late 22 | Last 1Y executed in jan.22 | 6 | 1 | 6 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /G /01/DFGA-A-0462 | WATER MIST SKID | DFF-IPHP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-02 | 2022-07-08 | WPM | B | V | Safety & Env.Related | 2400202414 | 0012 | 1Y W-MIST NOZZLE A-0462 for IP/HP | DE-ISOLATION | 2 | Pushed to late 22 | Last 1Y executed in jan.22 | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /G /01/DFGA-A-0462 | WATER MIST SKID | DFF-IPHP |  | INLC | MTN-MECH
| MTN-SCAF | 2024-01-02 | 2022-07-08 | WPM | B | V | Safety & Env.Related | 2400202414 | 0022 | 1Y W-MIST NOZZLE A-0462 for IP/HP | Build and remove scafffolding | 2 | Pushed to late 22 | Last 1Y executed in jan.22 | 14 | 1 | 14 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /G /01/DFGA-A-0462 | WATER MIST SKID | DFF-IPHP |  | INLC | MTN-MECH
| MTN-MECH | 2023-12-31 | 2019-08-08 | WDF | 1 | V | 1. Urgent | 2100022507 | 0010 | Cancel - Check of P-3551 outlet nozzle | Inspection of P-3551 outlet nozzle | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /E /54/DFEY-P-3551 | WI PUMP | DFE-3551 |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2023-12-31 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0030 | DFC Exp. P-3660, VOITH gear refurbisment | MAIN SCAF - Preparation and hanging up r | 2 | RCE |  | 24 | 2 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0040 | DFC Exp. P-3660, VOITH gear refurbisment | Safing Oil Export pump P-3660 | 2 | RCE |  | 1 | 1 | 6 | 5 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| VEN-MECH | 2024-01-03 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0050 | DFC Exp. P-3660, VOITH gear refurbisment | Dismanlted gear GEA-3660 from 3660 Pump | 2 | RCE |  | 20 | 1 | 20 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-05 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0060 | DFC Exp. P-3660, VOITH gear refurbisment | Elec demoll aux aux lube oil pump P-3661 | 2 | RCE |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-06 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0070 | DFC Exp. P-3660, VOITH gear refurbisment | Elec demoll oil heater E-3563 | 2 | RCE |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-INST | 2024-01-07 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0080 | DFC Exp. P-3660, VOITH gear refurbisment | Elec demoll instrument XE, ZSC, LSL, TE | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-01-09 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0090 | DFC Exp. P-3660, VOITH gear refurbisment | Demoll Working oil/lube oil pipeline | 2 | RCE |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-01-10 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0100 | DFC Exp. P-3660, VOITH gear refurbisment | Assist with out rigging of gears 16T/2 | 2 | RCE |  | 16 | 2 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-01-12 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0120 | DFC Exp. P-3660, VOITH gear refurbisment | Assist with in rigging of gears 16T/2 | 2 | RCE |  | 16 | 2 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| VEN-MECH | 2024-01-14 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0140 | DFC Exp. P-3660, VOITH gear refurbisment | Install Gear from Stock | 2 | RCE |  | 108 | 1 | 108 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-25 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0150 | DFC Exp. P-3660, VOITH gear refurbisment | Elec re-install aux lube oil pump P-3661 | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-27 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0160 | DFC Exp. P-3660, VOITH gear refurbisment | Elec re-install oil heater E-3663 | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-INST | 2024-01-29 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0170 | DFC Exp. P-3660, VOITH gear refurbisment | Tie-in local instruments XE, ZSC, LSL, T | 2 | RCE |  | 16 | 1 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-02-02 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0180 | DFC Exp. P-3660, VOITH gear refurbisment | Re-install Working oil/lube oil pipeline | 2 | RCE |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-02-03 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0190 | DFC Exp. P-3660, VOITH gear refurbisment | Gear, pump, motor coupling alignment | 2 | RCE |  | 48 | 2 | 48 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-02-09 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0200 | DFC Exp. P-3660, VOITH gear refurbisment | Function test | 2 | RCE |  | 24 | 2 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| PRODTECH | 2024-02-12 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0210 | DFC Exp. P-3660, VOITH gear refurbisment | Desafing Oil Export pump P-3660 | 2 | RCE |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-02-13 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0220 | DFC Exp. P-3660, VOITH gear refurbisment | Dismantling of rigging equipment 16T/2 | 2 | RCE |  | 16 | 2 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-02-15 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032039 | 0230 | DFC Exp. P-3660, VOITH gear refurbisment | Dismantling of overboard scaffolding 90T | 2 | RCE |  | 90 | 3 | 90 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3660 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0030 | DFC Exp. P-3650, VOITH gear refurbisment | Preparation and hanging up rig equipment | 2 | RCE |  | 24 | 2 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| PRODTECH | 2024-01-03 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0040 | DFC Exp. P-3650, VOITH gear refurbisment | Safing Oil Export pump P-3650 | 2 | RCE |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| VEN-MECH | 2024-01-04 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0050 | DFC Exp. P-3650, VOITH gear refurbisment | Dismanlted gear GEA-3670 from 3650 Pump | 2 | RCE |  | 20 | 1 | 20 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-06 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0060 | DFC Exp. P-3650, VOITH gear refurbisment | Elec demoll aux lube oil pump P-3651 | 2 | RCE |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-08 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0070 | DFC Exp. P-3650, VOITH gear refurbisment | Elec demoll oil heater E-3573 | 2 | RCE |  | 0 | 1 | 4 | 5 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-INST | 2024-01-08 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0080 | DFC Exp. P-3650, VOITH gear refurbisment | Elec demoll instrument XE, ZSC, LSL, TE | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-01-10 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0090 | DFC Exp. P-3650, VOITH gear refurbisment | Demoll Working oil/lube oil pipeline | 2 | RCE |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-01-10 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0100 | DFC Exp. P-3650, VOITH gear refurbisment | Assist with out rigging of gears | 2 | RCE |  | 16 | 2 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-01-12 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0120 | DFC Exp. P-3650, VOITH gear refurbisment | Assist with in rigging of gears | 2 | RCE |  | 16 | 2 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| VEN-MECH | 2024-01-14 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0140 | DFC Exp. P-3650, VOITH gear refurbisment | Install Gear from Stock | 2 | RCE |  | 108 | 1 | 108 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-25 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0150 | DFC Exp. P-3650, VOITH gear refurbisment | Elec re-install aux lube oil pump P-3651 | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-ELEC | 2024-01-27 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0160 | DFC Exp. P-3650, VOITH gear refurbisment | Elec re-install oil heater E-3653 | 2 | RCE |  | 8 | 1 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-INST | 2024-01-29 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0170 | DFC Exp. P-3650, VOITH gear refurbisment | Tie-in local instruments XE, ZSC, LSL, T | 2 | RCE |  | 16 | 1 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-02-02 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0180 | DFC Exp. P-3650, VOITH gear refurbisment | Re-install Working oil/lube oil pipeline | 2 | RCE |  | 4 | 1 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-02-03 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0190 | DFC Exp. P-3650, VOITH gear refurbisment | Gear, pump, motor coupling alignment | 2 | RCE |  | 48 | 2 | 48 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-MECH | 2024-02-09 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0200 | DFC Exp. P-3650, VOITH gear refurbisment | Function test | 2 | RCE |  | 24 | 2 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| PRODTECH | 2024-02-12 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0210 | DFC Exp. P-3650, VOITH gear refurbisment | Desafing Oil Export pump P-3650 | 2 | RCE |  | 6 | 1 | 6 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| MTN-RIGG | 2024-02-14 | 2020-07-05 | WDF | 3 | S | 3. Intermediate | 2100032040 | 0220 | DFC Exp. P-3650, VOITH gear refurbisment | Dismantling of rigging equipment | 2 | RCE |  | 16 | 2 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF MANC NMAT PRC SETC | DF /C /23/DFCM-GEA-3650 | GEAR/COUPLING BETWEEN ENERGR AND EXP PP | NOSD | RCE | INLC | MTN-MECH
| VEN-MECH | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0020 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor equipment for temp wrap | DAN-2022-FM-B | RCE | superceeded scope ?? ¦10/01/2022 Wrk. Ctr. Migration | 95.5 | 2 | 96 | 0.5 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| PRODTECH | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0190 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Prod - Desafeing and leaktest of 12" | DAN-2022-FM-B | RCE | superceeded scope ?? ¦10/01/2022 Wrk. Ctr. Migration | 2 | 1 | 2 | 0 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INLC | VEN-MECH
| MTN-SCAF | 2024-01-08 | 2020-12-07 | WDF | 3 |  | 3. Intermediate | 2100037152 | 0260 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Scaff - Remove scaffold inside/outside | DAN-2022-FM-B | RCE | superceeded scope ?? ¦10/01/2022 Wrk. Ctr. Migration | 22 | 2 | 30 | 8 | APPR CMAT AWDO RFRZ ROUT | APPR OPND | REL PCNF CSER GMPS MANC PPRT PRC SETC | DF /F /54/DFF-12-WI-035-9049-AB-U | 12 INJECTION WATER LINE | DFF-3520 | COMPLETED | INT | VEN-MECH
| MTN-MECH | 2024-01-02 | 2020-05-01 | WDF | 4 | V | 4. Long | 2100024676 | 0030 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Replace DFAA-ESDV-45092 |  | Req loss agreement |  | 24 | 2 | 24 | 0 | APPR PMAT AWDO RFRZ ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /A /37/DFAA-ESDV-45092 | GAS LIFT FROM GAS EXPORT MANIFOLD VIA FB | SIWL | AWSR AWZMOG | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-04-09 | WDF | 4 |  | 4. Long | 2100053942 | 0030 | Change Check valve DFB-05 | Production Isolation | 7 | Req loss approval |  | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /B /55/DFB05-WATER-INJECTION-LINE | DFB05 WATER INJECTION LINE | DFB-W05 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2022-02-11 | WDF | 3 | I | 3. Intermediate | 2100057416 | 0030 | ½" welded WI HCV leaking at valve handle | Production isolation | 6 | Req loss approval |  | 3 | 1 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /E /55/DFE01-WATER-INJECTION-LINE | DFE01 WATER INJECTION LINE | DFE-W01 |  | INLC | MTN-MECH
| PRODTECH | 2023-12-31 | 2022-09-28 | WDF | 4 | S | 4. Long | 2100056882 | 0010 | Replace Manifold tubing and DBB for PI35 | Isolate Manifold |  | Require loss agreement |  | 2 | 1 | 2 | 0 | APPR CMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /54/DFGA-PI-350465 | PRESSURE GAUGE | DFG-WI |  | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2019-09-09 | WDF | 3 | V | 3. Intermediate | 2100024572 | 0010 | CMAT:Trouble shooting filter sand | L3 Isolate equipment | 2 | S/D date TBC |  | 10 | 5 | 10 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3503 | FINE FILTER | DFF-3520 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-09-09 | WDF | 3 | V | 3. Intermediate | 2100024572 | 0020 | CMAT:Trouble shooting filter sand | L3 Remove manhole cover | 2 | S/D date TBC |  | 4 | 2 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3503 | FINE FILTER | DFF-3520 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-09-09 | WDF | 3 | V | 3. Intermediate | 2100024572 | 0030 | CMAT:Trouble shooting filter sand | L3 Trouble shoot according to WO text | 2 | S/D date TBC |  | 22 | 2 | 22 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3503 | FINE FILTER | DFF-3520 | AWSR | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-09-09 | WDF | 3 | V | 3. Intermediate | 2100024572 | 0040 | CMAT:Trouble shooting filter sand | L3 Install manhole cover |  | S/D date TBC |  | 4 | 2 | 4 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3503 | FINE FILTER | DFF-3520 | AWSR | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2019-09-09 | WDF | 3 | V | 3. Intermediate | 2100024572 | 0050 | CMAT:Trouble shooting filter sand | L3 Remove isolation |  | S/D date TBC |  | 10 | 2 | 10 | 0 | APPR AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DF /F /51/DFFA-FT-3503 | FINE FILTER | DFF-3520 | AWSR | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-09 | 2016-08-27 | WDF | 3 | S | 3. Intermediate | 2100027216 | 0090 | CMAT:Replacement of HCV-380115 | Desafing and leak test | 2 | SD 2018 | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR AWSC RDBL | APPR OPND | REL PCNF CSER MANC PRC SETC | DF /F /34/DFFA-HCV-380115 | HAND CONTROL VALVE | D-GASEXP | RCEOOS | INLC | MTN-PIPF |  | DK0500014340
| PRODTECH | 2023-12-31 | 2020-07-04 | WDF | 3 | V | 3. Intermediate | 2100033284 | 0010 | Replace DFCI-BDV-34057 (opens only 15 to | Isolate DFCI-BDV-34057 | 4 | SD/loss to be agreed |  | 8 | 1 | 8 | 0 | APPR SECE WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /C /20/DFCI-BDV-34057 | HP SEPARATOR, TO FLARE | DFCHPSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| MTN-INST | 2023-12-31 | 2022-02-09 | WDF | 4 | V | 4. Long | 2100051374 | 0020 | BDV-33010 DFE Prod.åbner ikke helt. | Isolate Hydraulic and controls |  | SD/loss to be agreed |  | 3 | 1 | 3 | 0 | APPR SECE PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /E /10/DFEZ-BDV-33010 | PRODUCTION MANIFOLD TO FLARE | DFE-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-06-15 | 2020-03-20 | WPM | B | V | Safety & Env.Related | 2400052544 | 0020 | 1Y FUNCT AND VISUAL INSP ESDV (DHDLPGAS) | ESDV VISUAL AND FUNCTIONAL CHECK | 3 | SD/loss to be agreed |  | 1 | 1 | 3 | 2 | APPR SECE AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF PRT MANC NMAT PRC SETC | DF /F /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DHDLPGAS |  | INLC | MTN-MECH |  | 99000142
| MTN-MECH | 2024-01-03 | 2022-06-01 | WPM | A | V | Assurance | 2400199791 | 0010 | 1Y FLAME ARRESTORS DFB/DFD | 24.01.2013 | 3 | SD/loss to be agreed |  | 5 | 0 | 5 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /D /36/DFDA-FLA-40071 | FLAME ARRESTOR FOR VENT STACK | DFDFLARE |  | INLC | MTN-INST
| PRODTECH | 2023-12-31 | 2022-10-04 | WPM | A | V | Assurance | 2400211608 | 0010 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | ISOLATION BY PRODUCTION |  | SD/Loss to be agreed |  | 15 | 1 | 15 | 0 | APPR SECE AWSD AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | DFX-LIFT |  | INLC | MTN-MECH
| MTN-ROPE | 2024-01-03 | 2021-04-01 | WDF | 3 | V | 3. Intermediate | 2100042480 | 0070 | ESD Afspæringsventil DFF-LIT-340102 | Rectify Insulation | 2 | See Revison code |  | 6 | 1 | 6 | 0 | APPR WMAT AWDO AWSC RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /F /20/DFFA-LIT-340102 | LEVEL DIFF. PRESSURE TRANSMITTER (ESD) | DFFLPSEP | SECE SOREN HVIRRING | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-04-01 | 2019-08-22 | WPM | C | V | Business Critical | 2400050819 | 0009 | 2Y POT WATER TREATMENT, DFC | Isolation | 5 | See text vendor req'd |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO ROUT | APPR OPND | REL MANC PRC SETC | DF /C /85 | SOFT WATER | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-MECH | 2024-04-01 | 2019-08-22 | WPM | C | V | Business Critical | 2400050819 | 0010 | 2Y POT WATER TREATMENT, DFC | VIGTIGT! DETTE CHECK UFØRES AF PRODUKTIO | 5 | See text vendor req'd |  | 24 | 1 | 24 | 0 | APPR WMAT AWDO ROUT | APPR OPND | REL MANC PRC SETC | DF /C /85 | SOFT WATER | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-INST | 2024-04-07 | 2019-08-22 | WPM | C | V | Business Critical | 2400050819 | 0012 | 2Y POT WATER TREATMENT, DFC | VIGTIGT! DETTE CHECK UFØRES AF PRODUKTIO | 5 | See text vendor req'd |  | 10 | 1 | 10 | 0 | APPR WMAT AWDO ROUT | APPR OPND | REL MANC PRC SETC | DF /C /85 | SOFT WATER | NOSD |  | INLC | MTN-MECH |  | 99000142
| PRODTECH | 2024-04-10 | 2019-08-22 | WPM | C | V | Business Critical | 2400050819 | 0014 | 2Y POT WATER TREATMENT, DFC | De-isolation | 5 | See text vendor req'd |  | 2 | 1 | 2 | 0 | APPR WMAT AWDO ROUT | APPR OPND | REL MANC PRC SETC | DF /C /85 | SOFT WATER | NOSD |  | INLC | MTN-MECH |  | 99000142
| MTN-CRAN | 2024-01-10 | 2026-03-18 | WDF | 4 | V | 4. Long | 2100088910 | 0010 | DBB/78 Dynamic damper for winch Defect | Isolation/deisolation of crane |  | TEST2 |  | 1 | 1 | 1 | 0 | APPR WMAT AWDO RDBL RFRZ ROUT | APPR OPND | REL MANC PRC SETC | DA /B /78/DB-JC-20 | CRANE - 8 T | NOSD |  | INLC | MTN-CRAN
| MTN-MECH | 2024-01-01 | 2020-05-05 | WDF | 3 | V | 3. Intermediate | 2100026509 | 0030 | DFG Lvl 2 Replace BDV 380137 | Replace BDV 380137 | 6 | V/v est. del =05-10-22 |  | 14 | 2 | 14 | 0 | APPR PMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /G /34/DFGA-BDV-380137 | BLOWDOWN VALVE | DFG20MPH | HN3DFG | INLC | MTN-MECH
| MTN-INST | 2023-12-31 | 2022-10-26 | WPM | D | I | Non Critical | 2400214329 | 0010 | 1Y STEAM CLEANER CHECK-DFFA-A-1110 | STEAM CLEANER CHECK-DFFA-A-1110 | 2 | vendor |  | 24 | 1 | 24 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /F /72/DFFA-A-1110 | HOT WATER CLEANER SKID | NOSD |  | INLC | MTN-INST
| MTN-MECH | 2024-01-01 | 2019-07-15 | WDF | 2 | V | 2. Short | 2100022869 | 0020 | DFC TEST W. LCV LEAK 30M3/h | demount valve | 1 | W? after 27723+27724 | W15-16 | 2 | 2 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-LCV-34001 | LCV - HYDROCYCLONE TEST OUTL TO DEGASSER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-01 | 2019-07-15 | WDF | 2 | V | 2. Short | 2100022869 | 0030 | DFC TEST W. LCV LEAK 30M3/h | rigg vlv out transport to workshop | 1 | W? after 27723+27724 | W15-16 | 5 | 2 | 5 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-LCV-34001 | LCV - HYDROCYCLONE TEST OUTL TO DEGASSER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2019-07-15 | WDF | 2 | V | 2. Short | 2100022869 | 0040 | DFC TEST W. LCV LEAK 30M3/h | change out component/soft kit test | 1 | W? after 27723+27724 | W15-16 | 12 | 2 | 12 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-LCV-34001 | LCV - HYDROCYCLONE TEST OUTL TO DEGASSER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-03 | 2019-07-15 | WDF | 2 | V | 2. Short | 2100022869 | 0050 | DFC TEST W. LCV LEAK 30M3/h | transport workshop to Wp and rigg in | 1 | W? after 27723+27724 | W15-16 | 5 | 1 | 5 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-LCV-34001 | LCV - HYDROCYCLONE TEST OUTL TO DEGASSER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-04 | 2019-07-15 | WDF | 2 | V | 2. Short | 2100022869 | 0060 | DFC TEST W. LCV LEAK 30M3/h | Mount vlv and doc | 1 | W? after 27723+27724 | W15-16 | 4 | 1 | 4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-LCV-34001 | LCV - HYDROCYCLONE TEST OUTL TO DEGASSER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-05 | 2019-07-15 | WDF | 2 | V | 2. Short | 2100022869 | 0070 | DFC TEST W. LCV LEAK 30M3/h | desafing | 1 | W? after 27723+27724 | W15-16 | 4 | 1 | 4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /27/DFCM-LCV-34001 | LCV - HYDROCYCLONE TEST OUTL TO DEGASSER | DFCHPSEP |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2017-01-30 | WDF | 3 | V | 3. Intermediate | 2100025290 | 0010 | Skift af ventiler ved FIT-500820 | Servicere FIT-500820 + skift af ventiler | 2 | W/200659082 |  | 30 | 2 | 30 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /27/DFGA-FE-500820 | ULTRASONIC FLOW METER (METERING) | DFG-IGF | DFGDEV | INLC | MTN-MECH |  | DK0500013007
| MTN-MECH | 2024-01-04 | 2017-01-30 | WDF | 3 | V | 3. Intermediate | 2100025290 | 0020 | Skift af ventiler ved FIT-500820 | Skifte ventiler (2 Stk.) | 2 | W/200659082 |  | 30 | 2 | 30 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /27/DFGA-FE-500820 | ULTRASONIC FLOW METER (METERING) | DFG-IGF | DFGDEV | INLC | MTN-MECH |  | DK0500013007
| MTN-MECH | 2024-01-08 | 2017-01-30 | WDF | 3 | V | 3. Intermediate | 2100025290 | 0030 | Skift af ventiler ved FIT-500820 | Servicere FIT-500820 (PPM) | 2 | W/200659082 |  | 8 | 1 | 8 | 0 | APPR WMAT AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /27/DFGA-FE-500820 | ULTRASONIC FLOW METER (METERING) | DFG-IGF | DFGDEV | INLC | MTN-MECH |  | DK0500013007
| MTN-INST | 2024-01-01 | 2021-06-18 | WDF | 3 | V | 3. Intermediate | 2100049116 | 0030 | DFE-04 liftgas FCV-45016 faulty | Troubleshooting FCV-45016 | 2 | W/23469 | W/23469 | 5 | 1 | 5 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /37/DFEZ-FCV-45016 | GAS LIFT 04 (FCV-XI) | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2021-06-18 | WDF | 3 | V | 3. Intermediate | 2100049116 | 0040 | DFE-04 liftgas FCV-45016 faulty | Production Assistance | 2 | W/23469 | W/23469 | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /37/DFEZ-FCV-45016 | GAS LIFT 04 (FCV-XI) | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-06-18 | WDF | 3 | V | 3. Intermediate | 2100049116 | 0050 | DFE-04 liftgas FCV-45016 faulty | Prod deisolate w function test | 2 | W/23469 | W/23469 | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /E /37/DFEZ-FCV-45016 | GAS LIFT 04 (FCV-XI) | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2018-05-26 | WDF | 3 | V | 3. Intermediate | 2100023469 | 0020 | DAN FE replace all 3 valves in gaslif | L2-safing of well no. 4 | 2 | W/49116 | W/49116 | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2018-05-26 | WDF | 3 | V | 3. Intermediate | 2100023469 | 0030 | DAN FE replace all 3 valves in gaslif | L3-Demount valves | 2 | W/49116 | W/49116 | 12 | 2 | 12 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-02 | 2018-05-26 | WDF | 3 | V | 3. Intermediate | 2100023469 | 0040 | DAN FE replace all 3 valves in gaslif | L2-install valves | 2 | W/49116 | W/49116 | 12 | 2 | 12 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-04 | 2018-05-26 | WDF | 3 | V | 3. Intermediate | 2100023469 | 0050 | DAN FE replace all 3 valves in gaslif | L3-desfaing of Well no. 4 | 2 | W/49116 | W/49116 | 3 | 1 | 3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-05 | 2018-05-26 | WDF | 3 | V | 3. Intermediate | 2100023469 | 0060 | DAN FE replace all 3 valves in gaslif | L3-test and documentation | 2 | W/49116 | W/49116 | 2 | 1 | 2 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /E /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFX-LIFT |  | INLC | MTN-MECH |  | 99000116
| VEN-MECH | 2023-12-31 | 2022-05-10 | WDF | 3 | V | 3. Intermediate | 2100061493 | 0020 | DFE-06 justering af ZT | Udskiftning af switchbox | 2 | w/SSSV test | 260722 Pr Step +6 weeks delivery | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /E /10/DFEZ-CVA-30006 | CHOKE VALVE | SIWL |  | INLC | VEN-MECH
| PRODTECH | 2024-01-14 | 2023-10-05 | WDF | 3 | V | 3. Intermediate | 2100088905 | 0010 | DFFA-PDIT-360033 Replace manifold and bo | Isolate PDT360033 manifold |  | W02-03 |  | 1 | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-PDIT-360033 | PRESSURE DIFF. INDIC. TRANSMITTER | NOSD | WP SAMIH | INLC | MTN-INST
| MTN-INST | 2024-01-14 | 2023-10-05 | WDF | 3 | V | 3. Intermediate | 2100088905 | 0020 | DFFA-PDIT-360033 Replace manifold and bo | Replace PDT360033 manifold & bolts |  | W02-03 |  | 4 | 2 | 4 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-PDIT-360033 | PRESSURE DIFF. INDIC. TRANSMITTER | NOSD | WP SAMIH | INLC | MTN-INST
| MTN-INST | 2024-01-14 | 2023-10-05 | WDF | 3 | V | 3. Intermediate | 2100088905 | 0030 | DFFA-PDIT-360033 Replace manifold and bo | Calibrate PDT360033 |  | W02-03 |  | 1 | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-PDIT-360033 | PRESSURE DIFF. INDIC. TRANSMITTER | NOSD | WP SAMIH | INLC | MTN-INST
| PRODTECH | 2024-01-15 | 2023-10-05 | WDF | 3 | V | 3. Intermediate | 2100088905 | 0040 | DFFA-PDIT-360033 Replace manifold and bo | De-isolate PDT360033 manifold |  | W02-03 |  | 1 | 1 | 1 | 0 | APPR WMAT RDBL | APPR OPND | REL MANC PRC SETC | DF /F /21/DFFA-PDIT-360033 | PRESSURE DIFF. INDIC. TRANSMITTER | NOSD | WP SAMIH | INLC | MTN-INST
| MTN-MECH | 2023-12-31 | 2019-09-28 | WDF | 3 | V | 3. Intermediate | 2100024622 | 0030 | DFFA-LG-410010 on V-4102 Replace of drai | Replace vent and drain valves on LG | 6 | W05-06 IOP | W05-06 IOP | 8 | 1 | 8 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /F /30/DFFA-V-4102 | GLYCOL CONTACTOR | DFF-IPHP | SECE - MECH | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2019-09-28 | WDF | 3 | V | 3. Intermediate | 2100024622 | 0040 | DFFA-LG-410010 on V-4102 Replace of drai | De-isolate/test DFFA-LG-410010 | 6 | W05-06 IOP | W05-06 IOP | 3 | 2 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /F /30/DFFA-V-4102 | GLYCOL CONTACTOR | DFF-IPHP | SECE - MECH | INLC | MTN-MECH
| MTN-RIGG | 2023-12-31 | 2019-04-29 | WDF | 4 | V | 4. Long | 2100022706 | 0015 | Replace Bypass HCV | Help remove old HCV |  | W05-06? IOP | W05-06 IOP | 12 | 1 | 12 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-MECH | 2024-01-03 | 2019-04-29 | WDF | 4 | V | 4. Long | 2100022706 | 0020 | Replace Bypass HCV | L2 Replace HCV |  | W05-06? IOP | W05-06 IOP | 16 | 1 | 16 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| MTN-RIGG | 2024-01-07 | 2019-04-29 | WDF | 4 | V | 4. Long | 2100022706 | 0025 | Replace Bypass HCV | Help putting in new HCV |  | W05-06? IOP | W05-06 IOP | 8 | 1 | 8 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| PRODTECH | 2024-01-09 | 2019-04-29 | WDF | 4 | V | 4. Long | 2100022706 | 0030 | Replace Bypass HCV | L3 De-Isolation/test HCV |  | W05-06? IOP | W05-06 IOP | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /F /20 | SEP/HEATING/COOLING (INCLUDING MANIFOLD) | DFFHPSEP |  | INLC | MTN-MECH
| VEN-ELEC | 2023-12-31 | 2020-02-20 | WDF | 3 | V | 3. Intermediate | 2100023221 | 0020 | CMAT:Change of defect RCD units | Replace RCD's and test installation | 2 | W16 Caverion | W16 Caverion | 50 | 2 | 50 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /05/DFGA-LP-1852 | EMERGENCY LIGHTING PANEL | DAN FG | CAVERION | INLC | MTN-ELEC |  | 99000116
| PRODTECH | 2024-01-03 | 2020-02-20 | WDF | 3 | V | 3. Intermediate | 2100023221 | 0030 | CMAT:Change of defect RCD units | De-isolate | 2 | W16 Caverion | W16 Caverion | 3 | 2 | 3 | 0 | APPR PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /G /05/DFGA-LP-1852 | EMERGENCY LIGHTING PANEL | DAN FG | CAVERION | INLC | MTN-ELEC |  | 99000116
| MTN-SCAF | 2023-12-31 | 2016-07-26 | WDF | 3 | V | 3. Intermediate | 2100027108 | 0070 | DFA-25, XCV 30537 fundet intern læk | Valve replaced with new, rigger | 2 | W18 Align with S/D | ¦10/01/2022 Wrk. Ctr. Migration | 13.4 | 2 | 13.4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /10/DFAA-XCV-30537 | CHANGE-OVER VALVE TO PRODUCTION MANIFOLD | DFA-OIL | PO ETA 21.12.2016 | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2023-12-31 | 2016-07-26 | WDF | 3 | V | 3. Intermediate | 2100027108 | 0080 | DFA-25, XCV 30537 fundet intern læk | Valve replaced with new, smede | 2 | W18 Align with S/D | ¦10/01/2022 Wrk. Ctr. Migration | 13.4 | 2 | 13.4 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /10/DFAA-XCV-30537 | CHANGE-OVER VALVE TO PRODUCTION MANIFOLD | DFA-OIL | PO ETA 21.12.2016 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-01 | 2016-07-26 | WDF | 3 | V | 3. Intermediate | 2100027108 | 0090 | DFA-25, XCV 30537 fundet intern læk | Desafing/leaktest | 2 | W18 Align with S/D | ¦10/01/2022 Wrk. Ctr. Migration | 0.1 | 1 | 0.1 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /10/DFAA-XCV-30537 | CHANGE-OVER VALVE TO PRODUCTION MANIFOLD | DFA-OIL | PO ETA 21.12.2016 | INLC | MTN-MECH |  | 99000116
| MTN-PIPF | 2023-12-31 | 2016-07-26 | WDF | 3 | V | 3. Intermediate | 2100027108 | 0110 | DFA-25, XCV 30537 fundet intern læk | TAGno Laves/påmonteres ventil Offshore | 2 | W18 Align with S/D | ¦10/01/2022 Wrk. Ctr. Migration | 1.3 | 1 | 1.3 | 0 | APPR SMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /A /10/DFAA-XCV-30537 | CHANGE-OVER VALVE TO PRODUCTION MANIFOLD | DFA-OIL | PO ETA 21.12.2016 | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2019-10-23 | WDF | 4 | V | 4. Long | 2100022631 | 0020 | Exchange actuator ESDV-34009 | L3 Isolate equipment | 2 | w18-19? |  | 4 | 2 | 4 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /11/DFCI-ESDV-34009 | V-3401 TO IP COMPRESSOR SUCTION MANIFOLD | DFC-TSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2019-10-23 | WDF | 4 | V | 4. Long | 2100022631 | 0030 | Exchange actuator ESDV-34009 | L3 dismantle actuator | 2 | w18-19? |  | 4 | 1 | 4 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /11/DFCI-ESDV-34009 | V-3401 TO IP COMPRESSOR SUCTION MANIFOLD | DFC-TSEP | SECE - MECH | INLC | VEN-MECH | 338134 | 99000116
| VEN-MECH | 2024-01-01 | 2019-10-23 | WDF | 4 | V | 4. Long | 2100022631 | 0040 | Exchange actuator ESDV-34009 | L3 Rig out & in of actuator | 2 | w18-19? |  | 4 | 2 | 4 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /11/DFCI-ESDV-34009 | V-3401 TO IP COMPRESSOR SUCTION MANIFOLD | DFC-TSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| VEN-MECH | 2024-01-01 | 2019-10-23 | WDF | 4 | V | 4. Long | 2100022631 | 0050 | Exchange actuator ESDV-34009 | L2 Install new actuator | 2 | w18-19? |  | 4 | 1 | 4 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /11/DFCI-ESDV-34009 | V-3401 TO IP COMPRESSOR SUCTION MANIFOLD | DFC-TSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-01-02 | 2019-10-23 | WDF | 4 | V | 4. Long | 2100022631 | 0060 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | 2 | w18-19? |  | 4 | 1 | 4 | 0 | APPR WMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /11/DFCI-ESDV-34009 | V-3401 TO IP COMPRESSOR SUCTION MANIFOLD | DFC-TSEP | SECE - MECH | INLC | VEN-MECH |  | 99000116
| PRODTECH | 2024-04-06 | 2019-12-04 | WDF | 3 | I | 3. Intermediate | 2100024998 | 0180 | Sisterpump 2100059456 DFFA-P-5001 expect | Isolate pump. |  | W23-24 | W23-24 | 5 | 1 | 5 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-P-5002 | LP HYDROCYCLONE PUMP | NOSD | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-04-06 | 2019-12-04 | WDF | 3 | I | 3. Intermediate | 2100024998 | 0190 | Sisterpump 2100059456 DFFA-P-5001 expect | Rigging of spool / pump |  | W23-24 | W23-24 | 12 | 2 | 12 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-P-5002 | LP HYDROCYCLONE PUMP | NOSD | DFF | INLC | MTN-MECH
| MTN-MECH | 2024-04-06 | 2019-12-04 | WDF | 3 | I | 3. Intermediate | 2100024998 | 0200 | Sisterpump 2100059456 DFFA-P-5001 expect | Reinstallation of pump / spool |  | W23-24 | W23-24 | 20 | 2 | 20 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-P-5002 | LP HYDROCYCLONE PUMP | NOSD | DFF | INLC | MTN-MECH
| MTN-RIGG | 2024-04-06 | 2019-12-04 | WDF | 3 | I | 3. Intermediate | 2100024998 | 0205 | Sisterpump 2100059456 DFFA-P-5001 expect | Move rigger equipment |  | W23-24 | W23-24 | 4 | 2 | 4 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-P-5002 | LP HYDROCYCLONE PUMP | NOSD | DFF | INLC | MTN-MECH
| MTN-MECH | 2024-04-06 | 2019-12-04 | WDF | 3 | I | 3. Intermediate | 2100024998 | 0210 | Sisterpump 2100059456 DFFA-P-5001 expect | Aligment |  | W23-24 | W23-24 | 8 | 2 | 8 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-P-5002 | LP HYDROCYCLONE PUMP | NOSD | DFF | INLC | MTN-MECH
| MTN-MECH | 2024-04-06 | 2019-12-04 | WDF | 3 | I | 3. Intermediate | 2100024998 | 0220 | Sisterpump 2100059456 DFFA-P-5001 expect | Deisolate pump |  | W23-24 | W23-24 | 5 | 1 | 5 | 0 | APPR PMAT SCH RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /F /27/DFFA-P-5002 | LP HYDROCYCLONE PUMP | NOSD | DFF | INLC | MTN-MECH
| MTN-SCAF | 2024-01-02 | 2016-06-14 | WDF | 3 | S | 3. Intermediate | 2100025337 | 0010 | DFC HCV-03067 LV05 Intern læk | Rig-up scaffold | 2 | W24-25 OIM FW INL | ¦10/01/2022 Wrk. Ctr. Migration | 36 | 3 | 36 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /C /01/DFCM-HCV-03067 | LO - HAND CONTROL VALVE | DAN-FRYS | DFGPRO | INLC | MTN-MECH |  | DK0500013007
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0042 | DGSP #650089 Temp Repair to 16 inch Line | Paint; Prep/Team/Gear/Barrier+POST |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 12 | 3 | 12 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH | DFB2223657
| MTN-ROPE | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0043 | DGSP #650089 Temp Repair to 16 inch Line | Paint; Clean, SB, Inspect, Waste | 2 | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 36 | 3 | 36 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH | DFB2179185
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0044 | DGSP #650089 Temp Repair to 16 inch Line | EMS PLAN-A; QC, WRAP, Clean-up |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 48 | 4 | 48 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0045 | DGSP #650089 Temp Repair to 16 inch Line | Paint; QC, Repaint, Waste |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 36 | 3 | 36 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| MTN-ROPE | 2024-02-05 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0050 | DGSP #650089 Temp Repair to 16 inch Line | Scaf; Take Tarp/Net Down | 2 | W26-27 IOP 1-12/7 | M5061, M5340/PR step | 30 | 3 | 40 | 10 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0051 | DGSP #650089 Temp Repair to 16 inch Line | Paint; Clean-Up+Backload |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 6 | 3 | 6 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0053 | DGSP #650089 Temp Repair to 16 inch Line | Prepare Materials - tools and hold TBT |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 24 | 3 | 24 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| MTN-ROPE | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0054 | DGSP #650089 Temp Repair to 16 inch Line | Rig up clamp |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 12 | 2 | 12 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0055 | DGSP #650089 Temp Repair to 16 inch Line | Install seal clamp |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 12 | 2 | 12 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0056 | DGSP #650089 Temp Repair to 16 inch Line | Torque clamp to spec |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 12 | 2 | 12 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0057 | DGSP #650089 Temp Repair to 16 inch Line | Inspect installation |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 2 | 1 | 2 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0061 | DGSP #650089 Temp Repair to 16 inch Line | EMS PLAN-B; CLAMP, Clean-up |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 48 | 4 | 48 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0071 | DGSP #650089 Temp Repair to 16 inch Line | Site Inspector; Scan or NDT |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 12 | 1 | 12 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| MTN-ROPE | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0091 | DGSP #650089 Temp Repair to 16 inch Line | Setup rigger equipment |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 0 | 3 | 9 | 91 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| VEN-MECH | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0101 | DGSP #650089 Temp Repair to 16 inch Line | Remove rigger equipment |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 9 | 3 | 9 | 0 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| MTN-ROPE | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0111 | DGSP #650089 Temp Repair to 16 inch Line | Prepare equipment on site |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 0 | 1 | 12 | 177 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| MTN-ROPE | 2024-01-08 | 2022-05-31 | WDF | 3 | V | 3. Intermediate | 2100066360 | 0121 | DGSP #650089 Temp Repair to 16 inch Line | Correcting PTW |  | W26-27 IOP 1-12/7 | W26-27 IOP 1-12/7 M5061, M5340 | 0 | 1 | 3 | 92 | APPR CMAT AWDO SCH RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /A /12/DFA-16-PHS-033-9009-BD-U | 16 HIGH PRESS WELL SOUR LINE | NOSD | COMPLETED CLAMP | INLC | VEN-MECH
| MTN-RIGG | 2024-01-01 | 2021-10-06 | WDF | 4 | V | 4. Long | 2100045747 | 0040 | All 3 valves on Bull head internal leak | Rigging assist. rig in/rig out. | 6 | W27-28 W/2100042352 | W27-28 | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-RIGG | 2024-01-04 | 2021-10-06 | WDF | 4 | V | 4. Long | 2100045747 | 0060 | All 3 valves on Bull head internal leak | Rig down hoist equipment | 6 | W27-28 W/2100042352 | W27-28 | 4 | 1 | 4 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2023-12-31 | 2020-06-23 | WDF | 3 | S | 3. Intermediate | 2100029105 | 0020 | DFA-03 def. ventil på WI manifold. | Prod isolation/permit | 7 | W27-28? | W27-28? | 3 | 1 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /A /75/DFAA-HCV-35054 | HAND CONTROL VALVE | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2021-10-06 | WDF | 4 | V | 4. Long | 2100045747 | 0020 | All 3 valves on Bull head internal leak | Isolate valves | 6 | W27-28? W/2100042352 | W27-28 | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2024-01-01 | 2021-10-06 | WDF | 4 | V | 4. Long | 2100045747 | 0030 | All 3 valves on Bull head internal leak | Changeout valves | 6 | W27-28? W/2100042352 | W27-28 | 6 | 1 | 6 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| PRODTECH | 2024-01-03 | 2021-10-06 | WDF | 4 | V | 4. Long | 2100045747 | 0050 | All 3 valves on Bull head internal leak | De-Isolate | 6 | W27-28? W/2100042352 | W27-28 | 3 | 1 | 3 | 0 | APPR CMAT AWSC RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /B /10 | EXTRACT WELLS/FLOW/MANIF/PMPG/WELL METER | DFB-OIL |  | INLC | MTN-MECH |  | 99000116
| MTN-MECH | 2023-12-31 | 2021-10-30 | WPM | B | V | Safety & Env.Related | 2400150889 | 0020 | 3Y FUNC, VISUAL, EX INSP ESDV (DFB-O02) | REGISTRATION OF WORKING HOURS | 2 | W36? IOP Align Nogat SD | W34 | 3 | 1 | 3 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | SIWL |  | INLC | MTN-MECH
| PRODTECH | 2024-01-01 | 2021-10-30 | WPM | B | V | Safety & Env.Related | 2400150889 | 0040 | 3Y FUNC, VISUAL, EX INSP ESDV (DFB-O02) | DE-ISOLATION | 2 | W36? IOP Align Nogat SD | W34 | 1 | 1 | 1 | 0 | APPR AWDO AWSC RDBL ROUT | APPR OPND | REL MANC NMAT PRC SETC | DF /B /03/SDV-VALVES | SHUTDOWN VALVES - OL - P6.3 | SIWL |  | INLC | MTN-MECH
| MTN-ROPE | 2023-12-30 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0090 | ANOCR DFB-R3007 External Corrosion | WORK; 15-INSPECT+Blast R3007 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 36 | 3 | 36 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-01 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0100 | ANOCR DFB-R3007 External Corrosion | WORK; 15-MIO-Primer close steel | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 12 | 3 | 12 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-02 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0110 | ANOCR DFB-R3007 External Corrosion | WORK; 15-Multi-Strength 600μ DFT | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 18 | 3 | 18 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-02 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0120 | ANOCR DFB-R3007 External Corrosion | POST; 15-De-rig SB & Rope EQ | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 6 | 3 | 6 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-02 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0130 | ANOCR DFB-R3007 External Corrosion | POST; Remount Grating & SCAF | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 14 | 3 | 14 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-02 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0140 | ANOCR DFB-R3007 External Corrosion | POST; Tidy-Up, Waste & Backload | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 8 | 3 | 9 | 1 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| MTN-ROPE | 2024-01-02 | 2020-06-17 | WDF | 4 | V | 4. Long | 2100023218 | 0150 | ANOCR DFB-R3007 External Corrosion | Correctiing PTW writting from onshore | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 4 | 1 | 7 | 3 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | INIT OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD |  | INLC | MTN-ROPE
| VEN-COMM | 2024-04-03 | 2019-11-17 | WRO | 4 | V | 4. Long | 2300000930 | 0010 | ESD SW for DFDCOM | ESD SW for DFDCOM | 2 | W49 ABB |  | 24 | 1 | 24 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/DFCI-FP-0204 | ESD PANEL | NE | DFDCOM | INLC | MTN-TELE
| MTN-TELE | 2024-01-18 | 2019-11-09 | WRO | 4 | V | 4. Long | 2300000925 | 0020 | SCADA SW for DFBWID2 | Telecom support | 2020 Project | W49? ABB support | Gregor | 10 | 1 | 10 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /B /04/DFBA-FP-2039 | RTU FOR PROCESS CONTROL SYSTEM (SCADA) | NE | DFBWID2 | INLC | CON-VEN
| MTN-TELE | 2024-04-05 | 2019-11-17 | WRO | 4 | V | 4. Long | 2300000930 | 0020 | ESD SW for DFDCOM | Telecom support | 2 | W49? ABB support | Gregor | 10 | 1 | 10 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /03/DFCI-FP-0204 | ESD PANEL | NE | DFDCOM | INLC | MTN-TELE
| VEN-COMM | 2024-04-03 | 2019-11-17 | WRO | 4 | V | 4. Long | 2300000929 | 0010 | SCADA SW for DFDCOM | SCADA SW for DFDCOM | 2 | W50 ABB |  | 24 | 1 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /04/DFCI-FP-2051 | SCADA RTU | NE | DFDCOM | INLC | MTN-TELE
| MTN-TELE | 2024-04-05 | 2019-11-17 | WRO | 4 | V | 4. Long | 2300000929 | 0020 | SCADA SW for DFDCOM | Telecom support | 2 | W50? ABB support | Gregor | 10 | 1 | 10 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /04/DFCI-FP-2051 | SCADA RTU | NE | DFDCOM | INLC | MTN-TELE
| MTN-MECH | 2023-12-30 | 2022-08-04 | WPM | A |  | Assurance | 2400206480 | 0010 | 1Y DEAERATOR MAINT - DFFB-A-3580 - DFF | DEAERATOR MAINT - DFFB-A-3560 - DFF | 2 | W51-52 IOP 01-01 / 15-01 | W51-52 DFF-3580, no loss - GR | 25 | 1 | 25 | 0 | APPR SECE SMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /53 | WATER TREAT (SULP REMOV/DE-OXYGENATION) | DFF-3580 |  | INLC | MTN-MECH
| MTN-INST | 2024-01-05 | 2022-08-04 | WPM | A |  | Assurance | 2400206480 | 0020 | 1Y DEAERATOR MAINT - DFFB-A-3580 - DFF | DEAERATOR MAINT - DFFB-A-3560 - DFF |  | W51-52 IOP 01-01 / 15-01 | W51-52 DFF-3580, no loss - GR | 18 | 1 | 18 | 0 | APPR SECE SMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /53 | WATER TREAT (SULP REMOV/DE-OXYGENATION) | DFF-3580 |  | INLC | MTN-MECH
| MTN-ELEC | 2024-01-10 | 2022-08-04 | WPM | A |  | Assurance | 2400206480 | 0030 | 1Y DEAERATOR MAINT - DFFB-A-3580 - DFF | DEAERATOR MAINT - DFFB-A-3560 - DFF |  | W51-52 IOP 01-01 / 15-01 | W51-52 DFF-3580, no loss - GR | 6 | 1 | 6 | 0 | APPR SECE SMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /53 | WATER TREAT (SULP REMOV/DE-OXYGENATION) | DFF-3580 |  | INLC | MTN-MECH
| VEN-INST | 2024-01-11 | 2022-08-04 | WPM | A |  | Assurance | 2400206480 | 0040 | 1Y DEAERATOR MAINT - DFFB-A-3580 - DFF | SERVICE OF MINOX ANALYZERS |  | W51-52 IOP 01-01 / 15-01 | W51-52 DFF-3580, no loss - GR | 24 | 1 | 24 | 0 | APPR SECE SMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /53 | WATER TREAT (SULP REMOV/DE-OXYGENATION) | DFF-3580 |  | INLC | MTN-MECH
| PRODTECH | 2024-01-14 | 2022-08-04 | WPM | A |  | Assurance | 2400206480 | 0050 | 1Y DEAERATOR MAINT - DFFB-A-3580 - DFF | DE-ISOLATION BY PRODUCTION |  | W51-52 IOP 01-01 / 15-01 | W51-52 DFF-3580, no loss - GR | 1 | 1 | 1 | 0 | APPR SECE SMAT AWDO AWSC RDBL ROUT | APPR OPND | REL GMPS MANC PRC SETC | DF /F /53 | WATER TREAT (SULP REMOV/DE-OXYGENATION) | DFF-3580 |  | INLC | MTN-MECH
| MTN-INST | 2024-01-01 | 2020-07-14 | WDF | 4 | S | 4. Long | 2100024610 | 0030 | CMAT:Replace of ball valve HCV 40119 | L2 Replace valve |  | well S/D reqd |  | 8 | 2 | 8 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /37/DFBA-HCV-40119 | LC - HAND CONTROL VALVE | DFB-O13 | AWSR | INLC | MTN-INST |  | 99000116
| MTN-INST | 2024-01-02 | 2020-07-14 | WDF | 4 | S | 4. Long | 2100024610 | 0040 | CMAT:Replace of ball valve HCV 40119 | L3 De-Isolate and test for leak |  | well S/D reqd |  | 2 | 1 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /B /37/DFBA-HCV-40119 | LC - HAND CONTROL VALVE | DFB-O13 | AWSR | INLC | MTN-INST |  | 99000116
23488.5