## Sheet1
Priority | System_Status | Order_Type | Priority_Original | Work_Center_Main | Order | Notification_No | Basic_Start_Date | Latest_Allowed_Finish_Date | Description_1 | Functional_Location | Description_2 | User_Status | Original_Latest_Allowed_Finish_Date | Revision | System_Condition | Maintenance_Plan | VIS | Material_Number | Priority_Type | Actual_Release_Date | Actual_Finish_Date | Description_3 | User_Status_All | Changed_On_Date | Plant_Section | Description_4 | Equipment | Created_On_Date | Created_On_Year | Basic_Finish_Date | Scheduled_Finish_Date | Scheduled_Start_Date | Actual_Start_Date | Leading_Order | Suporior_Order | Priority_Desc | Maintenance_Item | Original_Start_Date | Earliest_Start_Date | Maintenance_Plant | %Maint_Plan_Key | Priority_Original_Finish_Days | Priority_Original_Start_Days | Extraction_Date | System_Condition_Desc | Priority_Days | Activity | Work_Center | Short_Text | Opr_User_Status | Opr_System_Status | Material | Functional_Location_1 | System_Condition_1 | Work_Planned | Work_Actual | Activity_Type | Actual_Finish_Date_1 | Actual_Finish_Time | Actual_Start_Date_1 | Actual_Start_Time | Earliest_End_Date | Ealiest_Finish_Date | Equipment_1 | Work_Forecast | Latest_Finish_Date | Latest_Finish_Time | Latest_Start_Date | Latest_Start_Time | Location | Long_Text_Flag | Number | Long_Txt_Key | Unloading_Point | Week_Start | Week_Finish | Start_Time | Finish_Time
3 | REL GMPS MANC PPRT PRC SETC | WDF | 3 | MTN-ELEC | 2100038175 | 1100048202 | 16-01-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1850 | LIGHTING & SMALL POWER PANEL | APPR CMAT SCH RDBL | 05-05-2021 | NOSD | C |  | I |  | PM | 07-12-2021 |  |  | APPR CMAT SCH RDBL | 20-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 24-01-2023 | 24-01-2023 | 16-01-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 22-02-2023 | Equipment Shutdown | 180 | 10 | MTN-SCAF | Isolate accordingly | APPR OPND | REL |  | DF /G /61/DFGA-LP-1850 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 17-01-2023 | 09:36:00 |  | 0 | 17-01-2023 | 09:36:00 | 16-01-2023 | 09:36:00 | DFGA |  | 1 |  | W36 Caverion | 2100038175
3 | REL GMPS MANC PPRT PRC SETC | WDF | 3 | MTN-ELEC | 2100038175 | 1100048202 | 16-01-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1850 | LIGHTING & SMALL POWER PANEL | APPR CMAT SCH RDBL | 05-05-2021 | NOSD | C |  | I |  | PM | 07-12-2021 |  |  | APPR CMAT SCH RDBL | 20-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 24-01-2023 | 24-01-2023 | 16-01-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 22-02-2023 | Equipment Shutdown | 180 | 20 | MTN-MECH | Prove dead | APPR OPND | REL |  | DF /G /61/DFGA-LP-1850 | C | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 17-01-2023 | 15:36:00 |  | 0 | 17-01-2023 | 15:36:00 | 17-01-2023 | 09:36:00 | DFGA |  | 1 |  | W36 Caverion | 2100038175
3 | REL GMPS MANC PPRT PRC SETC | WDF | 3 | MTN-ELEC | 2100038175 | 1100048202 | 16-01-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1850 | LIGHTING & SMALL POWER PANEL | APPR CMAT SCH RDBL | 05-05-2021 | NOSD | C |  | I |  | PM | 07-12-2021 |  |  | APPR CMAT SCH RDBL | 20-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 24-01-2023 | 24-01-2023 | 16-01-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 22-02-2023 | Equipment Shutdown | 180 | 30 | MTN-ELEC | Change RCDs | APPR OPND | REL |  | DF /G /61/DFGA-LP-1850 | C | 12 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 23-01-2023 | 15:36:00 |  | 0 | 23-01-2023 | 15:36:00 | 17-01-2023 | 15:36:00 | DFGA |  | 1 |  | W36 Caverion | 2100038175
3 | REL GMPS MANC PPRT PRC SETC | WDF | 3 | MTN-ELEC | 2100038175 | 1100048202 | 16-01-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1850 | LIGHTING & SMALL POWER PANEL | APPR CMAT SCH RDBL | 05-05-2021 | NOSD | C |  | I |  | PM | 07-12-2021 |  |  | APPR CMAT SCH RDBL | 20-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 24-01-2023 | 24-01-2023 | 16-01-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 22-02-2023 | Equipment Shutdown | 180 | 40 | MTN-MECH | De-isolate and test | APPR OPND | REL |  | DF /G /61/DFGA-LP-1850 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 24-01-2023 | 15:36:00 |  | 0 | 24-01-2023 | 15:36:00 | 23-01-2023 | 15:36:00 | DFGA |  | 1 |  | W36 Caverion | 2100038175
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-ELEC | 2100038177 | 1100048205 | 13-02-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1853 | OUTDOOR LIGHTING PANEL | APPR SMAT SCH RDBL | 05-05-2021 | NOSD | C |  | S |  | PM | 07-12-2021 |  |  | APPR SMAT SCH RDBL | 03-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 21-02-2023 | 21-02-2023 | 13-02-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 07-02-2023 | Equipment Shutdown | 180 | 10 | MTN-MECH | Isolate accordingly | APPR OPND | REL |  | DF /G /61/DFGA-LP-1853 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 13-02-2023 | 19:00:00 |  | 0 | 13-02-2023 | 19:00:00 | 13-02-2023 | 07:00:00 | DFGA |  | 1 |  | W36 Caverion | 2100038177
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-ELEC | 2100038177 | 1100048205 | 13-02-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1853 | OUTDOOR LIGHTING PANEL | APPR SMAT SCH RDBL | 05-05-2021 | NOSD | C |  | S |  | PM | 07-12-2021 |  |  | APPR SMAT SCH RDBL | 03-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 21-02-2023 | 21-02-2023 | 13-02-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 07-02-2023 | Equipment Shutdown | 180 | 20 | MTN-ELEC | Prove dead | APPR OPND | REL |  | DF /G /61/DFGA-LP-1853 | C | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 14-02-2023 | 13:00:00 |  | 0 | 14-02-2023 | 13:00:00 | 14-02-2023 | 07:00:00 | DFGA |  | 1 |  | W36 Caverion | 2100038177
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-ELEC | 2100038177 | 1100048205 | 13-02-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1853 | OUTDOOR LIGHTING PANEL | APPR SMAT SCH RDBL | 05-05-2021 | NOSD | C |  | S |  | PM | 07-12-2021 |  |  | APPR SMAT SCH RDBL | 03-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 21-02-2023 | 21-02-2023 | 13-02-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 07-02-2023 | Equipment Shutdown | 180 | 30 | MTN-ELEC | Change RCDs | APPR OPND | REL |  | DF /G /61/DFGA-LP-1853 | C | 12 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 20-02-2023 | 13:00:00 |  | 0 | 20-02-2023 | 13:00:00 | 14-02-2023 | 13:00:00 | DFGA |  | 1 |  | W36 Caverion | 2100038177
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-ELEC | 2100038177 | 1100048205 | 13-02-2023 | 21-03-1944 | Replacement of RCDs | DF /G /61/DFGA-LP-1853 | OUTDOOR LIGHTING PANEL | APPR SMAT SCH RDBL | 05-05-2021 | NOSD | C |  | S |  | PM | 07-12-2021 |  |  | APPR SMAT SCH RDBL | 03-02-2023 | 18 |  |  | 10-09-2020 | 2020 | 21-02-2023 | 21-02-2023 | 13-02-2023 |  |  |  | 4. Long |  | 06-12-2020 | 06-12-2020 | DK40 | ¦¦¦ |  |  | 07-02-2023 | Equipment Shutdown | 180 | 40 | MTN-MECH | De-isolate and test | APPR OPND | REL |  | DF /G /61/DFGA-LP-1853 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 21-02-2023 | 13:00:00 |  | 0 | 21-02-2023 | 13:00:00 | 20-02-2023 | 13:00:00 | DFGA |  | 1 |  | W36 Caverion | 2100038177
1 | REL PRT MANC NMAT PRC SETC | WDF | 1 | MTN-MECH | 2100077077 | 1100101704 | 28-09-1944 | 09-09-1944 | DFFA-XCV-500712 INTERN LEAK | DF /F /27/DFFA-XCV-500712 | UNCLASSIFIED VALVE | APPR SCH RDBL | 14-12-2022 | DFFHPSEP | C |  | I |  | PM | 30-10-2022 |  |  | APPR SCH RDBL | 06-06-2023 | 33 |  |  | 30-10-2022 | 2022 | 05-01-2023 | 05-01-2023 | 28-09-1944 |  |  |  | 1. Urgent |  | 30-10-2022 | 30-10-2022 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 15 | 20 | MTN-MECH | Replace valve with new valve received | APPR OPND | REL |  | DF /F /27/DFFA-XCV-500712 |  | 12 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 05-01-2023 | 14:35:00 |  | 0 | 05-01-2023 | 14:35:00 | 02-01-2023 | 14:35:00 | DFFA |  | 2 |  | W45-46 Parked | 2100077077
3 | REL PRT MANC NMAT PRC SETC | WDF | 3 | MTN-MECH | 2100080794 | 1100106549 | 05-06-2023 | 14-01-1945 | Spring in checkvalve broken C-5450 | DF /G /07/DFGA-P-5450 | COOLING WATER CIRCULATION PUMP | APPR AWSC RDBL | 07-07-2023 | NOSD | A |  | I |  | PM | 27-01-2023 |  | COOLING WATER CIRCULATION PUMP | APPR AWSC SCH RDBL | 02-06-2023 | 54 |  | 30393852 | 10-01-2023 | 2023 | 06-06-2023 | 06-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 22-02-2023 | 22-02-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | No Shutdown Required | 180 | 10 | MTN-MECH | Spring in checkvalve broken C-5450 | APPR OPND | REL |  | DF /G /07/DFGA-P-5450 |  | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 06-06-2023 | 08:16:00 | 30393852 | 0 | 06-06-2023 | 08:16:00 | 05-06-2023 | 08:16:00 | DFGA |  | 1 |  | W23-24 | 2100080794
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 10 | MTN-MECH | Isolate XCV-355104 | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 05-06-2023 | 14:16:00 |  | 0 | 05-06-2023 | 14:16:00 | 05-06-2023 | 08:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 20 | MTN-SCAF | Isolate pneumatic and controls | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 05-06-2023 | 17:16:00 |  | 0 | 05-06-2023 | 17:16:00 | 05-06-2023 | 14:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 30 | MTN-RIGG | Rigging assist. rig in/rig out | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 06-06-2023 | 11:16:00 |  | 0 | 06-06-2023 | 11:16:00 | 05-06-2023 | 17:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 40 | MTN-MECH | Remove XCV | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 06-06-2023 | 17:16:00 |  | 0 | 06-06-2023 | 17:16:00 | 06-06-2023 | 11:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 50 | MTN-RIGG | Rigging assist. rig in/rig out | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 07-06-2023 | 11:16:00 |  | 0 | 07-06-2023 | 11:16:00 | 06-06-2023 | 17:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 60 | MTN-MECH | Install new XCV | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 07-06-2023 | 17:16:00 |  | 0 | 07-06-2023 | 17:16:00 | 07-06-2023 | 11:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 70 | MTN-MECH | Build new tubing if necessary | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 08-06-2023 | 11:16:00 |  | 0 | 08-06-2023 | 11:16:00 | 07-06-2023 | 17:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 80 | MTN-MECH | De Isolate pneumatic and controls | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 08-06-2023 | 14:16:00 |  | 0 | 08-06-2023 | 14:16:00 | 08-06-2023 | 11:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 90 | MTN-MECH | Functional test XCV-355104 | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 08-06-2023 | 14:16:00 |  | 0 | 08-06-2023 | 14:16:00 | 08-06-2023 | 11:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
3 | REL PRT GMPS MANC PRC SETC | WDF | 3 | MTN-MECH | 2100091182 | 1100120069 | 05-06-2023 | 18-11-2023 | FLM:DFF Minox filter XCV internal leak | DF /F /51/DFFB-XCV-355104 | FT-3551 BACKWASH | APPR CMAT SCH RDBL | 18-11-2023 | NE | C |  | I |  | PM | 22-05-2023 |  |  | APPR CMAT SCH RDBL | 12-06-2023 | 35 |  |  | 22-05-2023 | 2023 | 09-06-2023 | 09-06-2023 | 05-06-2023 |  |  |  | 3. Intermediate |  | 06-07-2023 | 06-07-2023 | DK40 | ¦¦¦ |  |  | 12-06-2023 | Equipment Shutdown | 180 | 100 | MTN-MECH | De Isolate XCV-355104 | APPR OPND | REL |  | DF /F /51/DFFB-XCV-355104 |  | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 09-06-2023 | 08:16:00 |  | 0 | 09-06-2023 | 08:16:00 | 08-06-2023 | 14:16:00 | DFFB |  | 1 |  | W23-24 | 2100091182
D | REL PRT MANC NMAT PRC SETC | WPM | D | MTN-INST | 2400070944 | 1400072112 | 13-02-2023 | 20-11-2020 | 1Y TRANSPORTABLE STIGER | DF /C /84 | WORKSHOP/WAREHOUSE | APPR SCH RDBL | 20-11-2020 | NOSD | A | DK600000874 | I |  | PP | 10-06-2020 |  |  | APPR SCH RDBL | 25-01-2023 |  |  |  | 08-06-2020 | 2020 | 17-02-2023 | 17-02-2023 | 13-02-2023 |  |  |  | Non Critical | 110051254 | 02-10-2020 | 16-08-2020 | DK40 | DK600000874 ¦¦¦ 110051254 |  |  | 07-02-2023 | No Shutdown Required |  | 10 | MTN-SCAF | 14.02.2013 | APPR OPND | REL |  | DF /C /84 | A | 12 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 17-02-2023 | 19:00:00 |  | 0 | 17-02-2023 | 19:00:00 | 13-02-2023 | 07:00:00 |  | X | 1 |  |  | 2400070944
A | REL PRT MANC NMAT PRC SETC | WPM | A | MTN-MECH | 2400206461 | 1400219794 | 28-09-1944 | 05-08-1944 | 1Y INERT GAS GEN UNIT MAINT-DFCI-A-0801 | DF /C /74/DFCI-A-0801 | NITROGEN CONTROL PANEL | APPR SECE AWDO SCH RDBL RFRZ ROUT | 01-09-2022 | NOSD | C | DKDF-0545 | V |  | PP | 15-07-1944 |  |  | APPR SECE AWDO SCH ROUT RDBL RFRZ | 19-12-2022 | 8 |  |  | 13-05-2022 | 2022 | 29-09-1944 | 29-09-1944 | 28-09-1944 |  |  |  | Assurance | 110074422 | 17-08-2022 | 02-08-2022 | DK40 | DKDF-0545 ¦¦¦ 110074422 |  |  | 21-12-2022 | Equipment Shutdown |  | 10 | MTN-MECH | INERT GAS GEN UNIT MAINT-DFCI-A-0801 | APPR OPND | REL |  | DF /C /74/DFCI-A-0801 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 03-01-2023 | 08:14:00 |  | 0 | 03-01-2023 | 08:14:00 | 02-01-2023 | 08:14:00 | DFCI | X | 1 |  | W49-50 | 2400206461
A | REL PRT MANC NMAT PRC SETC | WPM | A | MTN-ELEC | 2400210920 | 1400224473 | 05-06-2023 | 27-08-1944 | 1Y FIRE DAMPER CHECK - DFF | DF /F /09/FIRE-DAMPERS | FIRE DAMPERS | APPR SECE AWDO SCH RDBL RFRZ ROUT | 23-09-2022 | NOSD | A | DKDF-2002 | V |  | PP | 13-07-1944 |  |  | APPR SECE AWDO SCH ROUT RDBL RFRZ | 05-05-2023 | 12 |  |  | 25-05-2022 | 2022 | 07-06-2023 | 07-06-2023 | 05-06-2023 |  |  |  | Assurance | 110074254 | 08-09-2022 | 24-08-2022 | DK40 | DKDF-2002 ¦¦¦ 110074254 |  |  | 11-05-2023 | No Shutdown Required |  | 10 | MTN-MECH | FIRE DAMPER CHECK - DFF | APPR OPND | REL |  | DF /F /09/FIRE-DAMPERS | A | 8 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 07-06-2023 | 09:33:00 |  | 0 | 07-06-2023 | 09:33:00 | 05-06-2023 | 09:33:00 | DFFY | X | 1 |  | Moved to Jun SR Req | 2400210920
C | REL MANC NMAT PRC SETC | WPM | C | MTN-MECH | 2400211626 | 1400225181 | 24-04-2023 | 01-10-2022 | 6M WI BOOSTER PUMP MAINT DFFB-P-3570/71 | DF /F /54/DFFB-P-3570 | WI BOOSTER PUMP | APPR SCH RDBL | 01-10-2022 | NOSD | C | DKDF-0679 | I |  | PP | 25-07-2022 |  | WI BOOSTER PUMP | APPR SCH RDBL | 26-04-2023 | 35 |  | 30389091 | 07-06-2022 | 2022 | 25-04-2023 | 25-04-2023 | 24-04-2023 |  |  |  | Business Critical | 110075316 | 21-09-2022 | 12-09-2022 | DK40 | DKDF-0679 ¦¦¦ 110075316 |  |  | 11-05-2023 | Equipment Shutdown |  | 10 | MTN-MECH | WI BOOSTER PUMP MAINT DFFB-P-3570/71 | APPR OPND | REL |  | DF /F /54/DFFB-P-3570 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 25-04-2023 | 09:31:00 | 30389091 | 0 | 25-04-2023 | 09:31:00 | 24-04-2023 | 09:31:00 | DFFB | X | 1 |  | W17-18 | 2400211626
C | REL GMPS MANC PPRT PRC SETC | WPM | C | MTN-ELEC | 2400211798 | 1400225355 | 13-02-2023 | 12-10-2022 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | DF /C /61 | POWER DISTRIBUTION (HV, LV) | APPR CMAT AWSC RDBL | 12-10-2022 | NOSD | A | DKDF-2165 | V |  | PP | 19-10-2022 |  |  | APPR CMAT AWSC SCH RDBL | 28-01-2023 | 18 |  |  | 17-06-2022 | 2022 | 18-02-2023 | 18-02-2023 | 13-02-2023 |  |  |  | Business Critical | 110073297 | 06-10-2022 | 01-10-2022 | DK40 | DKDF-2165 ¦¦¦ 110073297 |  |  | 07-02-2023 | No Shutdown Required |  | 20 | MTN-ELEC | TEMP ELEC INSTALLATIONS CHECK - DFC | APPR OPND | REL |  | DF /C /61 | A | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 14-02-2023 | 13:00:00 |  | 0 | 14-02-2023 | 13:00:00 | 13-02-2023 | 07:00:00 | DFCY | X | 1 |  |  | 2400211798
C | REL GMPS MANC PPRT PRC SETC | WPM | C | MTN-ELEC | 2400211798 | 1400225355 | 13-02-2023 | 12-10-2022 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | DF /C /61 | POWER DISTRIBUTION (HV, LV) | APPR CMAT AWSC RDBL | 12-10-2022 | NOSD | A | DKDF-2165 | V |  | PP | 19-10-2022 |  |  | APPR CMAT AWSC SCH RDBL | 28-01-2023 | 18 |  |  | 17-06-2022 | 2022 | 18-02-2023 | 18-02-2023 | 13-02-2023 |  |  |  | Business Critical | 110073297 | 06-10-2022 | 01-10-2022 | DK40 | DKDF-2165 ¦¦¦ 110073297 |  |  | 07-02-2023 | No Shutdown Required |  | 30 | MTN-ELEC | TEMP ELEC INSTALLATIONS CHECK - DFC | APPR OPND | REL |  | DF /C /61 | A | 18 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 18-02-2023 | 19:00:00 |  | 0 | 18-02-2023 | 19:00:00 | 14-02-2023 | 13:00:00 | DFCY |  | 1 |  |  | 2400211798
A | REL PRT MANC NMAT PRC SETC | WPM | A | MTN-MECH | 2400215380 | 1400228951 | 27-03-2023 | 20-11-2022 | 3M EMER. GENERATOR INSPECT DFFA-A-1701 | DF /F /05/DFFA-A-1701 | EMERGENCY DIESEL GENERATOR | APPR SECE AWDO SCH RDBL RFRZ ROUT | 20-11-2022 | NOSD | A | DKDF-0619 | V |  | PP | 10-08-1944 |  |  | APPR SECE AWDO SCH ROUT RDBL RFRZ | 29-03-2023 | 17 |  |  | 22-07-2022 | 2022 | 28-03-2023 | 28-03-2023 | 27-03-2023 |  |  |  | Assurance | 110075103 | 15-11-2022 | 10-11-2022 | DK40 | DKDF-0619 ¦¦¦ 110075103 |  |  | 03-04-2023 | No Shutdown Required |  | 20 | MTN-MECH | EMER. GENERATOR INSPECT DFFA-A-1701 | APPR OPND | REL |  | DF /F /05/DFFA-A-1701 | A | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 28-03-2023 | 11:49:00 |  | 0 | 28-03-2023 | 11:49:00 | 27-03-2023 | 11:49:00 | DFFA | X | 1 |  | W13-14 | 2400215380
A | REL MANC NMAT PRC SETC | WPM | A | MTN-MECH | 2400215975 | 1400229568 | 13-02-2023 | 02-12-2022 | 3M FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | DF /C /01/FIREWATER-PUMPS | FIREWATER PUMPS | APPR SECE AWDO SCH RDBL RFRZ ROUT | 02-12-2022 | NOSD | A | DKDF-0049 | V |  | PP | 22-08-2022 |  |  | APPR SECE AWDO SCH ROUT RDBL RFRZ | 23-01-2023 |  |  |  | 08-08-2022 | 2022 | 14-02-2023 | 14-02-2023 | 13-02-2023 |  |  |  | Assurance | 110074801 | 27-11-2022 | 22-11-2022 | DK40 | DKDF-0049 ¦¦¦ 110074801 |  |  | 07-02-2023 | No Shutdown Required |  | 10 | MTN-MECH | FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | APPR OPND | REL |  | DF /C /01/FIREWATER-PUMPS | A | 12 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 14-02-2023 | 15:31:00 |  | 0 | 14-02-2023 | 15:31:00 | 13-02-2023 | 09:31:00 | DFCY | X | 2 |  | W51-52 | 2400215975
A | REL MANC NMAT PRC SETC | WPM | A | MTN-MECH | 2400232963 | 1400246798 | 05-06-2023 | 04-03-2023 | 3M FIREWATER PUMP PKG MAINT-DFGA-A-0351 | DF /G /01/DFGA-A-0351 | FIREWATER PUMP PACKAGE | APPR SECE AWDO SCH RDBL RFRZ ROUT | 04-03-2023 | NOSD | A | DKDF-0094 | V |  | PP | 14-11-2022 |  |  | APPR SECE AWDO SCH ROUT RDBL RFRZ | 02-06-2023 | 3 |  |  | 04-11-2022 | 2022 | 06-06-2023 | 06-06-2023 | 05-06-2023 |  |  |  | Assurance | 110074820 | 27-02-2023 | 22-02-2023 | DK40 | DKDF-0094 ¦¦¦ 110074820 |  |  | 12-06-2023 | No Shutdown Required |  | 10 | MTN-MECH | FIREWATER PUMP PKG MAINT-DFGA-A-0351 | APPR OPND | REL |  | DF /G /01/DFGA-A-0351 | A | 6 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 06-06-2023 | 14:16:00 |  | 0 | 06-06-2023 | 14:16:00 | 05-06-2023 | 08:16:00 | DFGA | X | 1 |  | W23-24 | 2400232963
B | REL NMAT PRC SETC | WPM | B | MTN-MECH | 2400241334 | 1400255268 | 25-03-2023 | 10-04-2023 | 4KH SDV/BDV LUB/MAINT WI DFFA-A-3520 | DF /F /54/DFFA-A-3520 | WI PUMP UNIT | APPR AWDO AWSC RDBL RFRZ ROUT | 10-04-2023 | DFF-3520 | A | DKDF-0162 | V |  | PP | 16-09-1944 |  |  | APPR AWDO AWSC SCH ROUT RDBL RFRZ | 14-03-2023 | 35 |  |  | 13-12-2022 | 2022 | 25-03-2023 | 25-03-2023 | 25-03-2023 |  |  |  | Safety & Env.Related | 110073845 | 02-04-2023 | 25-03-2023 | DK40 | DKDF-0162 ¦¦¦ 110073845 |  |  | 22-03-2023 | No Shutdown Required |  | 10 | MTN-MECH | SDV/BDV LUB/INSP WI DFFA-A-3520 | APPR OPND | REL |  | DF /F /54/DFFA-A-3520 | A | 2 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 25-03-2023 | 11:30:00 |  | 0 | 25-03-2023 | 11:30:00 | 25-03-2023 | 07:00:00 | DFFA | X | 1 |  | W11-12 IOP | 2400241334
C | REL MANC NMAT PRC SETC | unavailable | C | MTN-MECH | 2400211626 | 1400225181 | 24-04-2023 | 01-10-2022 | 6M WI BOOSTER PUMP MAINT DFFB-P-3570/71 | DF /F /54/DFFB-P-3570 | WI BOOSTER PUMP | APPR SCH RDBL | 01-10-2022 | NOSD | C | DKDF-0679 | I |  | PP | 25-07-2022 |  | WI BOOSTER PUMP | APPR SCH RDBL | 26-04-2023 | 35 |  | 30389091 | 07-06-2022 | 2022 | 25-04-2023 | 25-04-2023 | 24-04-2023 |  |  |  | Business Critical | 110075316 | 21-09-2022 | 12-09-2022 | DK40 | DKDF-0679 ¦¦¦ 110075316 |  |  | 11-05-2023 | Equipment Shutdown |  | 10 | MTN-MECH | WI BOOSTER PUMP MAINT DFFB-P-3570/71 | APPR OPND | REL |  | DF /F /54/DFFB-P-3570 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 25-04-2023 | 09:31:00 | 30389091 | 0 | 25-04-2023 | 09:31:00 | 24-04-2023 | 09:31:00 | DFFB | X | 1 |  | W17-18 | 2400211626 |  | 0 | 40
C | REL MANC NMAT PRC SETC | unavailable | C | MTN-MECH | 2400211626 | 1400225181 | 24-04-2023 | 01-10-2022 | 6M WI BOOSTER PUMP MAINT DFFB-P-3570/71 | DF /F /54/DFFB-P-3570 | WI BOOSTER PUMP | APPR SCH RDBL | 01-10-2022 | NOSD | C | DKDF-0679 | I |  | PP | 25-07-2022 |  | WI BOOSTER PUMP | APPR SCH RDBL | 26-04-2023 | 35 |  | 30389091 | 07-06-2022 | 2022 | 25-04-2023 | 25-04-2023 | 24-04-2023 |  |  |  | Business Critical | 110075316 | 21-09-2022 | 12-09-2022 | DK40 | DKDF-0679 ¦¦¦ 110075316 |  |  | 11-05-2023 | Equipment Shutdown |  | 10 | MTN-MECH | WI BOOSTER PUMP MAINT DFFB-P-3570/71 | APPR OPND | REL |  | DF /F /54/DFFB-P-3570 | C | 4 | 0 | AAINHR |  | 00:00:00 |  | 00:00:00 | 25-04-2023 | 09:31:00 | 30389091 | 0 | 25-04-2023 | 09:31:00 | 24-04-2023 | 09:31:00 | DFFB | X | 1 |  | W17-18 | 2400211626 |  | 20 | 60