## Sheet1
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400264133 | 1Y HPU FOR MFF1 SCRAMS MAINT - FP-3001 | Electrical isolation | AWSCSECE | AWSCSECE | 2 | 0 | W35-W36 | 2024-06-03 | 2024-06-06 | 2024-06-03 | 2024-06-03 | 2023-06-26 | 2023-07-26 | 10 | AWSCSECE | AWSCSECE | DF /F /07/DFFA-FP-3001 | Electrical isolation | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400264133 | 1Y HPU FOR MFF1 SCRAMS MAINT - FP-3001 | Electrical isolation | AWSCSECE | AWSCSECE | 4 | 0 | W35-W36 | 2024-06-03 | 2024-06-06 | 2024-06-03 | 2024-06-04 | 2023-06-26 | 2023-07-26 | 15 | AWSCSECE | AWSCSECE | DF /F /07/DFFA-FP-3001 | Electrical isolation | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400264133 | 1Y HPU FOR MFF1 SCRAMS MAINT - FP-3001 | Electrical isolation | AWSCSECE | AWSCSECE | 4 | 0 | W35-W36 | 2024-06-03 | 2024-06-06 | 2024-06-04 | 2024-06-05 | 2023-06-26 | 2023-07-26 | 20 | AWSCSECE | AWSCSECE | DF /F /07/DFFA-FP-3001 | Electrical isolation | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400264133 | 1Y HPU FOR MFF1 SCRAMS MAINT - FP-3001 | Electrical isolation | AWSCSECE | AWSCSECE | 1 | 0 | W35-W36 | 2024-06-03 | 2024-06-06 | 2024-06-05 | 2024-06-05 | 2023-06-26 | 2023-07-26 | 30 | AWSCSECE | AWSCSECE | DF /F /07/DFFA-FP-3001 | Electrical isolation | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400264133 | 1Y HPU FOR MFF1 SCRAMS MAINT - FP-3001 | Electrical isolation | AWSCSECE | AWSCSECE | 1 | 0 | W35-W36 | 2024-06-03 | 2024-06-06 | 2024-06-05 | 2024-06-05 | 2023-06-26 | 2023-07-26 | 40 | AWSCSECE | AWSCSECE | DF /F /07/DFFA-FP-3001 | Electrical isolation | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400264133 | 1Y HPU FOR MFF1 SCRAMS MAINT - FP-3001 | Electrical isolation | AWSCSECE | AWSCSECE | 2 | 0 | W35-W36 | 2024-06-03 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2023-06-26 | 2023-07-26 | 50 | AWSCSECE | AWSCSECE | DF /F /07/DFFA-FP-3001 | Electrical isolation | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400292158 | 6M FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | FW JOCKEY PUMP MAINT -DFCM-P-0308/09 |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-29 | 2023-12-18 | 10 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342418 | 6M BDV LUB/MAINT - DFA/B/E | BDV LUB/INSP - DFA/B/E |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-08-26 | 2024-09-11 | 10 |  |  | DF /A /70/BDV | BDV LUB/INSP - DFA/B/E | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100107867 | DFCI-AE-34052 WCM unstable | DFCI-AE-34052 investigation |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-03-28 | 2024-08-10 | 10 |  |  | DF /C /20/DFCI-AE-34052 | DFCI-AE-34052 investigation | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400325741 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59190 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59190 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /B /07/DFBA-FP-59190 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59190 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400306651 | 3M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-10 | 2024-02-20 | 10 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 3 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-01 | 2018-09-18 | 2018-10-28 | 10 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-02 | 2018-09-18 | 2018-10-28 | 20 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-02 | 2023-04-02 | 2018-09-18 | 2018-10-28 | 30 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 5.4000000000000003552713678785 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-02 | 2023-04-02 | 2018-09-18 | 2018-10-28 | 40 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-02 | 2023-04-03 | 2018-09-18 | 2018-10-28 | 45 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-03 | 2023-04-03 | 2018-09-18 | 2018-10-28 | 50 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 3 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-03 | 2023-04-04 | 2018-09-18 | 2018-10-28 | 60 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023592 | ANOP DAN FC, Bld. Flg with PSL-03446 at | Instr materials |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2018-09-18 | 2018-10-28 | 70 |  |  | DF /C /01/DFCC-V-0301 | Instr materials | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329525 | 1Y DIESEL HOSEREELS MAINT - DFF | DIESEL HOSEREELS MAINT - DFF |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-13 | 2024-06-18 | 10 |  |  | DF /F /71/DFFA-HOSU-570126 | DIESEL HOSEREELS MAINT - DFF | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044251 | DFC LEVEL 1. DFC-XCV-34308 fejl zsc/zso | Vendor to Troubleshoot on XCV-34308 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-03 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-34308 | Vendor to Troubleshoot on XCV-34308 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044251 | DFC LEVEL 1. DFC-XCV-34308 fejl zsc/zso | Vendor to Troubleshoot on XCV-34308 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-34308 | Vendor to Troubleshoot on XCV-34308 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053468 | DFA-Scale/Corr P-39222 Pulsation damper | Isolate DFAA-PD-39226 |  |  | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-31 | 2021-08-19 | 2021-09-28 | 20 |  |  | DF /F /75/DFFA-A-3954 | Isolate DFAA-PD-39226 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053468 | DFA-Scale/Corr P-39222 Pulsation damper | Isolate DFAA-PD-39226 |  |  | 30 | 0 | W29-W30 | 2024-07-29 | 2024-08-08 | 2024-07-31 | 2024-08-07 | 2021-08-19 | 2021-09-28 | 30 |  |  | DF /F /75/DFFA-A-3954 | Isolate DFAA-PD-39226 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053468 | DFA-Scale/Corr P-39222 Pulsation damper | Isolate DFAA-PD-39226 |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2021-08-19 | 2021-09-28 | 40 |  |  | DF /F /75/DFFA-A-3954 | Isolate DFAA-PD-39226 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085361 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-03-30 | 2023-08-12 | 10 |  |  | DF /C /05/DFCI-DP-1823 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085361 | Battery fault on emergency light | Change batteries |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-03-30 | 2023-08-12 | 20 |  |  | DF /C /05/DFCI-DP-1823 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085361 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-03-30 | 2023-08-12 | 30 |  |  | DF /C /05/DFCI-DP-1823 | Change batteries | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012455 | Wet units Job preperation dec. 2022 | Increase of PO 4500075986 |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-06 | 2023-05-21 | 10 |  |  | DF /C /82 | Increase of PO 4500075986 | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012455 | Wet units Job preperation dec. 2022 | Increase of PO 4500075986 |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-06 | 2023-05-21 | 20 |  |  | DF /C /82 | Increase of PO 4500075986 | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200012455 | Wet units Job preperation dec. 2022 | Increase of PO 4500075986 |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-06 | 2023-05-21 | 30 |  |  | DF /C /82 | Increase of PO 4500075986 | Unknown
B | NOSD | WPM | MTN-INST | MTN-INST | 2400206506 | 1Y DFCI-FT-50439 PROD WATER - METERING | Rigging ESDV 50447 | AWSC | AWSC | 6 | 0 | Empty | 2024-07-17 | 2024-07-22 | 2024-07-17 | 2024-07-18 | 2022-07-06 | 2022-08-05 | 10 | AWSC | AWSC | DF /C /20/DFCI-FT-50439 | Rigging ESDV 50447 | Unknown
B | NOSD | WPM | MTN-INST | PRODTECH | 2400206506 | 1Y DFCI-FT-50439 PROD WATER - METERING | Rigging ESDV 50447 | AWSC | AWSC | 12 | 0 | Empty | 2024-07-17 | 2024-07-22 | 2024-07-18 | 2024-07-21 | 2022-07-06 | 2022-08-05 | 20 | AWSC | AWSC | DF /C /20/DFCI-FT-50439 | Rigging ESDV 50447 | Unknown
B | NOSD | WPM | MTN-INST | MTN-SCAF | 2400206506 | 1Y DFCI-FT-50439 PROD WATER - METERING | Rigging ESDV 50447 | AWSC | AWSC | 4 | 0 | Empty | 2024-07-17 | 2024-07-22 | 2024-07-21 | 2024-07-22 | 2022-07-06 | 2022-08-05 | 30 | AWSC | AWSC | DF /C /20/DFCI-FT-50439 | Rigging ESDV 50447 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048085 | DFGA-A-0464 Repl. 6 pcs. N2 gas cylindre | Additinal materials | SCH | SCH | 2 | 0 | Empty | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-04-07 | 2021-05-17 | 10 | SCH | SCH | DF /G /01/DFGA-A-0464 | Additinal materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048085 | DFGA-A-0464 Repl. 6 pcs. N2 gas cylindre | Additinal materials | SCH | SCH | 12 | 0 | Empty | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-04-07 | 2021-05-17 | 20 | SCH | SCH | DF /G /01/DFGA-A-0464 | Additinal materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100048085 | DFGA-A-0464 Repl. 6 pcs. N2 gas cylindre | Additinal materials | SCH | SCH | 10 | 0 | Empty | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-04-07 | 2021-05-17 | 25 | SCH | SCH | DF /G /01/DFGA-A-0464 | Additinal materials | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048085 | DFGA-A-0464 Repl. 6 pcs. N2 gas cylindre | Additinal materials | SCH | SCH | 2 | 0 | Empty | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-04-07 | 2021-05-17 | 30 | SCH | SCH | DF /G /01/DFGA-A-0464 | Additinal materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048085 | DFGA-A-0464 Repl. 6 pcs. N2 gas cylindre | Additinal materials | SCH | SCH | 0 | 0 | Empty | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-04-07 | 2021-05-17 | 40 | SCH | SCH | DF /G /01/DFGA-A-0464 | Additinal materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048085 | DFGA-A-0464 Repl. 6 pcs. N2 gas cylindre | Additinal materials | SCH | SCH | 0 | 0 | Empty | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-04-07 | 2021-05-17 | 50 | SCH | SCH | DF /G /01/DFGA-A-0464 | Additinal materials | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269323 | 6M PRIME MOVER DFFA-MD-6102 | PRIME MOVER MAINTENANCE DFFA-MD-6102 |  |  | 15 | 0 | W23-W24 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2023-10-13 | 2023-10-29 | 20 |  |  | DF /F /78/DFFA-MD-6102 | PRIME MOVER MAINTENANCE DFFA-MD-6102 | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 2 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 3 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 4 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 5 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 3 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 10 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 60 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-20 | 2018-10-09 | 2019-03-08 | 20 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 16 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-20 | 2024-03-22 | 2018-10-09 | 2019-03-08 | 30 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 16 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-22 | 2024-03-23 | 2018-10-09 | 2019-03-08 | 40 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 4 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-23 | 2024-03-24 | 2018-10-09 | 2019-03-08 | 50 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 120 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-24 | 2024-04-08 | 2018-10-09 | 2019-03-08 | 60 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 16 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-04-08 | 2024-04-10 | 2018-10-09 | 2019-03-08 | 70 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-INSP | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 1 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2022-01-10 | 2022-01-10 | 2018-10-09 | 2019-03-08 | 72 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 40 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-17 | 2018-10-09 | 2019-03-08 | 75 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | INP-SITE | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 6 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-17 | 2024-03-17 | 2018-10-09 | 2019-03-08 | 80 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 80 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-17 | 2024-03-22 | 2018-10-09 | 2019-03-08 | 90 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 32 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-22 | 2024-03-26 | 2018-10-09 | 2019-03-08 | 100 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 16 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-26 | 2024-03-28 | 2018-10-09 | 2019-03-08 | 110 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 16 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-28 | 2024-03-29 | 2018-10-09 | 2019-03-08 | 120 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 12 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-29 | 2024-03-30 | 2018-10-09 | 2019-03-08 | 130 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 2 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-30 | 2024-03-31 | 2018-10-09 | 2019-03-08 | 135 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 24 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-31 | 2024-04-02 | 2018-10-09 | 2019-03-08 | 140 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2022-01-10 | 2022-01-10 | 2018-10-09 | 2019-03-08 | 150 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2022-01-10 | 2022-01-10 | 2018-10-09 | 2019-03-08 | 170 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 180 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 190 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 220 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 230 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024392 | FFSPR 1 pc 2" Nozzels must be replaced w | PO Bureau Veritas | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-04-10 | 2024-03-15 | 2024-03-15 | 2018-10-09 | 2019-03-08 | 240 | PCNF | PCNF | DF /B /36/DFB-18-FH-040-0847-B5-U | PO Bureau Veritas | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235762 | 4Y 24V UPS-DP F.TEST-DFCI-AS-14-31 | 24V UPS-DP F.TEST-DFCI-AS-14-31 | AWSC | AWSC | 20 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-20 | 2023-03-01 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /08/DFCI-AS-14-31 | 24V UPS-DP F.TEST-DFCI-AS-14-31 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088310 | Hose reel drum very rusty | Replace hosereel |  |  | 2 | 0 | Empty | 2024-06-14 | 2024-06-17 | 2024-06-14 | 2024-06-15 | 2023-05-14 | 2023-09-26 | 10 |  |  | DF /C /01/DFCI-HR-0374 | Replace hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088310 | Hose reel drum very rusty | Replace hosereel |  |  | 6 | 0 | Empty | 2024-06-14 | 2024-06-17 | 2024-06-15 | 2024-06-16 | 2023-05-14 | 2023-09-26 | 20 |  |  | DF /C /01/DFCI-HR-0374 | Replace hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088310 | Hose reel drum very rusty | Replace hosereel |  |  | 8 | 0 | Empty | 2024-06-14 | 2024-06-17 | 2024-06-15 | 2024-06-17 | 2023-05-14 | 2023-09-26 | 30 |  |  | DF /C /01/DFCI-HR-0374 | Replace hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088310 | Hose reel drum very rusty | Replace hosereel |  |  | 2 | 0 | Empty | 2024-06-14 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-14 | 2023-09-26 | 40 |  |  | DF /C /01/DFCI-HR-0374 | Replace hosereel | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 8 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-20 | 2023-06-04 | 10 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 36 | 36 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-20 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 20 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 24 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-24 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 30 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 18 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-27 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 40 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 18 | 10 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-22 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 50 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | VEN-MECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 36 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-31 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 55 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 16 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-31 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 60 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 8 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-31 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 70 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 36 | 17 | Empty | 2024-09-22 | 2024-09-27 | 2023-05-29 | 2023-05-31 | 2023-04-20 | 2023-06-04 | 80 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 8 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-20 | 2023-06-04 | 90 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 12 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-04-20 | 2023-06-04 | 100 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 12 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-27 | 2023-04-20 | 2023-06-04 | 110 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-20 | 2023-06-04 | 120 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-20 | 2023-06-04 | 130 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
2 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100089383 | Leak Exhaust on DFGA-GT-4302 | Increase of PO 4500093196 | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-20 | 2023-06-04 | 140 | PCNF | PCNF | DF /G /31/DFGA-A-4310 | Increase of PO 4500093196 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 10 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 20 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 24 | 24 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 30 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 12 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 31 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-06-02 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 40 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 4 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-06-02 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 50 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-03 | 2020-08-10 | 2020-09-19 | 60 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 70 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-06-05 | 2020-08-10 | 2020-09-19 | 80 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-09-28 | 2020-08-10 | 2020-09-19 | 90 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 12 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-11-14 | 2020-08-10 | 2020-09-19 | 100 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 8 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-05-27 | 2022-09-28 | 2020-08-10 | 2020-09-19 | 110 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 3 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2022-11-14 | 2022-11-14 | 2020-08-10 | 2020-09-19 | 120 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 4 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-03 | 2020-08-10 | 2020-09-19 | 130 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 4 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2024-07-04 | 2024-07-04 | 2020-08-10 | 2020-09-19 | 140 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100035817 | DFA/78: replace wiper relays in cabin | Order new parts from Liebherr | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-03 | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2020-08-10 | 2020-09-19 | 150 | PCNFSCH | PCNFSCH | DF /A /78/DFAA-X-6102 | Order new parts from Liebherr | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 3 | 0 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2020-09-14 | 2020-10-01 | 2019-06-09 | 2019-07-19 | 10 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 4 | 24 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2020-09-14 | 2020-10-01 | 2019-06-09 | 2019-07-19 | 20 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 4 | 24 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2020-09-14 | 2020-10-01 | 2019-06-09 | 2019-07-19 | 25 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 3 | 0 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2020-09-15 | 2020-10-01 | 2019-06-09 | 2019-07-19 | 30 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 0 | 0 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-09 | 2019-07-19 | 40 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 4 | 0 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-06-09 | 2019-07-19 | 50 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024973 | Replace suction strainer and hose P-3110 | L3 Isolation of DFFA-P-3110 | PCNF | PCNF | 0 | 0 | W38-39 SR Request | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-09 | 2019-07-19 | 60 | PCNF | PCNF | DF /F /07/DFFA-P-3110 | L3 Isolation of DFFA-P-3110 | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400215368 | 1Y FINE WTER SPRAY SKD MAINT-DFFB-A-0334 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 3 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-03 | 2024-07-03 | 2022-10-16 | 2022-11-15 | 10 | AWSCSECE | AWSCSECE | DF /F /01/DFFB-A-0334 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400215368 | 1Y FINE WTER SPRAY SKD MAINT-DFFB-A-0334 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 10 | 10 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-03 | 2024-07-06 | 2022-10-16 | 2022-11-15 | 20 | AWSCSECE | AWSCSECE | DF /F /01/DFFB-A-0334 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400215368 | 1Y FINE WTER SPRAY SKD MAINT-DFFB-A-0334 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 6 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-06 | 2024-07-07 | 2022-10-16 | 2022-11-15 | 30 | AWSCSECE | AWSCSECE | DF /F /01/DFFB-A-0334 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-INST | 2400215368 | 1Y FINE WTER SPRAY SKD MAINT-DFFB-A-0334 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 4 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-07 | 2024-07-08 | 2022-10-16 | 2022-11-15 | 40 | AWSCSECE | AWSCSECE | DF /F /01/DFFB-A-0334 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400215368 | 1Y FINE WTER SPRAY SKD MAINT-DFFB-A-0334 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 3 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-08 | 2024-07-09 | 2022-10-16 | 2022-11-15 | 50 | AWSCSECE | AWSCSECE | DF /F /01/DFFB-A-0334 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100085207 | DFC Switchboard incom N-1802 signal err | Faultfinding on signals |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-03-29 | 2023-08-11 | 10 |  |  | DF /C /61/DFCI-ET-18151 | Faultfinding on signals | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085207 | DFC Switchboard incom N-1802 signal err | Faultfinding on signals |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-03-29 | 2023-08-11 | 11 |  |  | DF /C /61/DFCI-ET-18151 | Faultfinding on signals | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100085207 | DFC Switchboard incom N-1802 signal err | Faultfinding on signals |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-03-29 | 2023-08-11 | 20 |  |  | DF /C /61/DFCI-ET-18151 | Faultfinding on signals | Unknown
3 | DFA-OIL | WDF | MTN-MECH | PRODTECH | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2020-12-16 | 2021-01-25 | 20 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-02 | 2020-12-16 | 2021-01-25 | 30 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-03 | 2020-12-16 | 2021-01-25 | 40 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-03 | 2025-01-03 | 2020-12-16 | 2021-01-25 | 50 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2025-01-04 | 2020-12-16 | 2021-01-25 | 60 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2025-01-05 | 2020-12-16 | 2021-01-25 | 70 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-06 | 2020-12-16 | 2021-01-25 | 80 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2025-01-07 | 2020-12-16 | 2021-01-25 | 90 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-07 | 2020-12-16 | 2021-01-25 | 100 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | PRODTECH | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-08 | 2020-12-16 | 2021-01-25 | 110 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
3 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100042149 | DFA mess dæk proces. XCV-33196 defekt | Demount Actuator | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-09 | 2020-12-16 | 2021-01-25 | 120 | AWSC | AWSC | DF /A /12/DFAA-XCV-33196 | Demount Actuator | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-02-11 | 2024-03-27 | 10 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-02-11 | 2024-03-27 | 20 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-02-11 | 2024-03-27 | 30 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-02-11 | 2024-03-27 | 40 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-02-11 | 2024-03-27 | 50 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-02-11 | 2024-03-27 | 60 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100107144 | DFE Test flow line ESDV stuck open. | Isolate ESDV | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-02-11 | 2024-03-27 | 70 | SECE | SECE | DF /E /10/DFEZ-ESDV-33055 | Isolate ESDV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100064830 | Closure Door Safety Warning Lock defect | Production Isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-06-05 | 2022-11-02 | 10 |  |  | DF /G /34/DFGA-EP-3813 | Production Isolation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100064830 | Closure Door Safety Warning Lock defect | Production Isolation |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-06-05 | 2022-11-02 | 20 |  |  | DF /G /34/DFGA-EP-3813 | Production Isolation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100064830 | Closure Door Safety Warning Lock defect | Production Isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-06-05 | 2022-11-02 | 30 |  |  | DF /G /34/DFGA-EP-3813 | Production Isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106577 | Dan F Light Check materials 2024 | Dan F Light Check materials 2024 |  |  | 0 | 0 | Empty | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2027-01-17 | 10 |  |  | DF /C /62/EMERGENCY-LIGHTING | Dan F Light Check materials 2024 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235753 | 1Y 380V UPS.SYST BATT & CHAR F.TEST-DFE | 380V UPS.SYST BATT & CHAR F.TEST-DFE | SECE | SECE | 8 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-06-19 | 2023-07-19 | 10 | SECE | SECE | DF /E /06/UPS-SYSTEMS | 380V UPS.SYST BATT & CHAR F.TEST-DFE | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040324 | DFAA-HCV-38100 DKDF0072 C-Out 2 Hyd Hose | Repl hydr hoses DFAA-HCV-38100 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-11-22 | 2021-02-20 | 10 |  |  | DF /A /12/DFAA-HCV-38100 | Repl hydr hoses DFAA-HCV-38100 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040324 | DFAA-HCV-38100 DKDF0072 C-Out 2 Hyd Hose | Repl hydr hoses DFAA-HCV-38100 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-11-22 | 2021-02-20 | 20 |  |  | DF /A /12/DFAA-HCV-38100 | Repl hydr hoses DFAA-HCV-38100 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040324 | DFAA-HCV-38100 DKDF0072 C-Out 2 Hyd Hose | Repl hydr hoses DFAA-HCV-38100 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2020-11-22 | 2021-02-20 | 30 |  |  | DF /A /12/DFAA-HCV-38100 | Repl hydr hoses DFAA-HCV-38100 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322246 | DFB-28-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100065946 | DFA-15 choke can't open fully up. | Troubleshoot on on choke not fully open |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-04-06 | 2022-04-26 | 10 |  |  | DF /A /10/DFAA-CVA-30303 | Troubleshoot on on choke not fully open | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000927 | F&G SW for DFBWID2 | F&G SW for DFBWID2 | AWSC | AWSC | 24 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-03 | 2019-06-12 | 2019-11-09 | 10 | AWSC | AWSC | DF /B /03/DFBA-FP-0108 | F&G SW for DFBWID2 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000927 | F&G SW for DFBWID2 | F&G SW for DFBWID2 | AWSC | AWSC | 10 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2019-06-12 | 2019-11-09 | 20 | AWSC | AWSC | DF /B /03/DFBA-FP-0108 | F&G SW for DFBWID2 | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000927 | F&G SW for DFBWID2 | F&G SW for DFBWID2 | AWSC | AWSC | 0 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2019-06-12 | 2019-11-09 | 30 | AWSC | AWSC | DF /B /03/DFBA-FP-0108 | F&G SW for DFBWID2 | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2016-03-29 | 2016-05-08 | 1 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2016-03-29 | 2016-05-08 | 2 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2016-03-29 | 2016-05-08 | 3 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2016-03-29 | 2016-05-08 | 10 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 1 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2016-03-29 | 2016-05-08 | 20 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 6.5 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2016-03-29 | 2016-05-08 | 30 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2016-03-29 | 2016-05-08 | 40 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2016-03-29 | 2016-05-08 | 50 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-04 | 2016-03-29 | 2016-05-08 | 60 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2016-03-29 | 2016-05-08 | 70 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-02 | 2016-03-29 | 2016-05-08 | 80 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2016-03-29 | 2016-05-08 | 90 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2016-03-29 | 2016-05-08 | 100 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2016-03-29 | 2016-05-08 | 110 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2016-03-29 | 2016-05-08 | 120 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100024893 | SMAT: DFF-29 OIL XCV-301329 til FF man | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2016-03-29 | 2016-05-08 | 130 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301329 | Prepare Permits Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003060 | Scaff Assist to Force 13625. | L3 Install scaff | PCNF | PCNF | 13 | 10 | Empty | 2021-10-23 | 2021-10-23 | 2019-09-14 | 2019-09-16 | 2018-12-28 | 2019-03-28 | 10 | PCNF | PCNF | DF /A /36/DFA-6-FHS-040-0646-B5-U | L3 Install scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003060 | Scaff Assist to Force 13625. | L3 Install scaff | PCNF | PCNF | 0.6999999999999999555910790147 | 0 | Empty | 2021-10-23 | 2021-10-23 | 2019-09-16 | 2019-09-16 | 2018-12-28 | 2019-03-28 | 20 | PCNF | PCNF | DF /A /36/DFA-6-FHS-040-0646-B5-U | L3 Install scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003060 | Scaff Assist to Force 13625. | L3 Install scaff | PCNF | PCNF | 72 | 72 | Empty | 2021-10-23 | 2021-10-23 | 2019-09-09 | 2019-09-16 | 2018-12-28 | 2019-03-28 | 30 | PCNF | PCNF | DF /A /36/DFA-6-FHS-040-0646-B5-U | L3 Install scaff | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003060 | Scaff Assist to Force 13625. | L3 Install scaff | PCNF | PCNF | 1 | 0 | Empty | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2021-10-23 | 2018-12-28 | 2019-03-28 | 40 | PCNF | PCNF | DF /A /36/DFA-6-FHS-040-0646-B5-U | L3 Install scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003060 | Scaff Assist to Force 13625. | L3 Install scaff | PCNF | PCNF | 17.399999999999998578914528472 | 21.5 | Empty | 2021-10-23 | 2021-10-23 | 2020-09-01 | 2020-10-24 | 2018-12-28 | 2019-03-28 | 50 | PCNF | PCNF | DF /A /36/DFA-6-FHS-040-0646-B5-U | L3 Install scaff | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400230378 | 2Y AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2023-01-02 | 2023-02-17 | 10 | SECE | SECE | DF /C /50/DFCM-P-5304 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400230378 | 2Y AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-01-02 | 2023-02-17 | 20 | SECE | SECE | DF /C /50/DFCM-P-5304 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230378 | 2Y AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-01-02 | 2023-02-17 | 30 | SECE | SECE | DF /C /50/DFCM-P-5304 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400230378 | 2Y AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2023-01-02 | 2023-02-17 | 40 | SECE | SECE | DF /C /50/DFCM-P-5304 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400230378 | 2Y AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-01-02 | 2023-02-17 | 50 | SECE | SECE | DF /C /50/DFCM-P-5304 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 8 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-17 | 2023-11-16 | 2024-03-30 | 10 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 0.5 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-17 | 2023-11-16 | 2024-03-30 | 20 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 0.5 | 3 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-17 | 2023-11-16 | 2024-03-30 | 30 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 2.5 | 12 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-17 | 2023-11-16 | 2024-03-30 | 40 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-17 | 2023-11-16 | 2024-03-30 | 50 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-16 | 2024-03-30 | 60 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-16 | 2024-03-30 | 70 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099156 | Faulty transmitter FT-350206 | Test with CCR, after start of P-3520 | PCNFSCH | PCNFSCH | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-16 | 2024-03-30 | 80 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-FT-350206 | Test with CCR, after start of P-3520 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329442 | 3Y DFBA-P-3550, TURBINE | TL-3Y DFBA-P-3550, TURBINE | AWSCSCHSECE | AWSCSCHSECE | 12 | 0 | W23-W24 | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2024-06-05 | 2024-04-11 | 2024-06-12 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /B /54/DFBA-PTU-3550 | TL-3Y DFBA-P-3550, TURBINE | Unknown
A | DFG-IPHP | WPM | MTN-TELE | PRODTECH | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 9 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-04 | 2024-07-06 | 2024-07-04 | 2024-09-22 | 10 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-TELE | MTN-TELE | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3.5 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-06 | 2024-07-07 | 2024-07-04 | 2024-09-22 | 20 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-TELE | MTN-TELE | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4.5 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-07 | 2024-07-08 | 2024-07-04 | 2024-09-22 | 30 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-TELE | MTN-TELE | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1.5 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-08 | 2024-07-08 | 2024-07-04 | 2024-09-22 | 40 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-TELE | MTN-TELE | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-08 | 2024-07-09 | 2024-07-04 | 2024-09-22 | 50 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-TELE | MTN-TELE | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-09 | 2024-07-10 | 2024-07-04 | 2024-09-22 | 60 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-TELE | PRODTECH | 2400344187 | 40KH F&G DET. CHECK-DFGA-A-4302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 9 | 0 | Empty | 2024-07-04 | 2024-07-12 | 2024-07-10 | 2024-07-12 | 2024-07-04 | 2024-09-22 | 70 | AWSCSECE | AWSCSECE | DF /G /03/FZ-332-GAS-COMP-TURBINE-ENCL | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112588 | DFFW/78 Glaas for fuel level indicator i | Replace fuel level indicator |  |  | 5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-06-27 | 2024-11-09 | 10 |  |  | DF /F /78/DFFA-A-6102 | Replace fuel level indicator | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400230500 | 1Y WELL CONT PANEL MAINT - DFFA-FP-3101 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 2 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2023-01-26 | 2023-02-25 | 10 | SCHSECE | SCHSECE | DF /F /07/DFFA-FP-3101 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400230500 | 1Y WELL CONT PANEL MAINT - DFFA-FP-3101 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 9 | 9 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-31 | 2023-01-26 | 2023-02-25 | 20 | SCHSECE | SCHSECE | DF /F /07/DFFA-FP-3101 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400230500 | 1Y WELL CONT PANEL MAINT - DFFA-FP-3101 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 6 | 6 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-31 | 2024-08-02 | 2023-01-26 | 2023-02-25 | 30 | SCHSECE | SCHSECE | DF /F /07/DFFA-FP-3101 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230500 | 1Y WELL CONT PANEL MAINT - DFFA-FP-3101 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 10 | 10 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-04 | 2023-01-26 | 2023-02-25 | 40 | SCHSECE | SCHSECE | DF /F /07/DFFA-FP-3101 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400230500 | 1Y WELL CONT PANEL MAINT - DFFA-FP-3101 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 2 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-01-26 | 2023-02-25 | 50 | SCHSECE | SCHSECE | DF /F /07/DFFA-FP-3101 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400337276 | 6M CRANE HOIST EQUIP, DFC | CRANE HOIST EQUIP, DFC |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-10-13 | 2024-11-01 | 10 |  |  | DF /C /78/DFC-LIFTING | CRANE HOIST EQUIP, DFC | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400241158 | 1Y ANTIFOULING UNIT A-5501 | ISOLATION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-07-29 | 2024-07-29 | 2023-02-19 | 2023-03-27 | 10 |  |  | DF /G /52/DFGA-A-5501 | ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241158 | 1Y ANTIFOULING UNIT A-5501 | ISOLATION |  |  | 16 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-07-29 | 2024-08-02 | 2023-02-19 | 2023-03-27 | 20 |  |  | DF /G /52/DFGA-A-5501 | ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400241158 | 1Y ANTIFOULING UNIT A-5501 | ISOLATION |  |  | 16 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-02 | 2024-08-06 | 2023-02-19 | 2023-03-27 | 30 |  |  | DF /G /52/DFGA-A-5501 | ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400241158 | 1Y ANTIFOULING UNIT A-5501 | ISOLATION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2023-02-19 | 2023-03-27 | 40 |  |  | DF /G /52/DFGA-A-5501 | ISOLATION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400321853 | DFG-12-PLS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /12/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235741 | 1Y 400V UPS.SYST F.TEST BATT & CHAR -DFF | 400V UPS.SYST F.TEST BATT & CHAR -DFF | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-06-28 | 2024-07-01 | 2024-06-28 | 2024-06-30 | 2023-06-14 | 2023-07-14 | 10 | AWSCSECE | AWSCSECE | DF /F /06/UPS-SYSTEMS | 400V UPS.SYST F.TEST BATT & CHAR -DFF | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235741 | 1Y 400V UPS.SYST F.TEST BATT & CHAR -DFF | 400V UPS.SYST F.TEST BATT & CHAR -DFF | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-06-28 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2023-06-14 | 2023-07-14 | 20 | AWSCSECE | AWSCSECE | DF /F /06/UPS-SYSTEMS | 400V UPS.SYST F.TEST BATT & CHAR -DFF | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259283 | 6M SDV LUB/MAINT TSEP - DFC | SDV LUB/INSP TSEP - DFC |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-30 | 2023-06-15 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP TSEP - DFC | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346573 | 6M WI BOOSTER PUMP MAINT DFFB-P-3570/71 | WI BOOSTER PUMP MAINT DFFB-P-3570/71 |  |  | 4 | 0 | Empty | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-10-01 | 10 |  |  | DF /F /54/DFFB-P-3570 | WI BOOSTER PUMP MAINT DFFB-P-3570/71 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 1 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2022-09-05 | 2022-09-16 | 2020-11-04 | 2021-04-03 | 10 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 2 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2022-09-05 | 2022-09-16 | 2020-11-04 | 2021-04-03 | 20 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 2 | 1 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2022-09-05 | 2022-09-05 | 2020-11-04 | 2021-04-03 | 30 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 1 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2022-09-05 | 2022-09-16 | 2020-11-04 | 2021-04-03 | 40 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 1 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2022-09-05 | 2022-09-16 | 2020-11-04 | 2021-04-03 | 50 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 4 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-16 | 2020-11-04 | 2021-04-03 | 60 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 24 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2024-09-16 | 2024-09-22 | 2020-11-04 | 2021-04-03 | 70 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100036460 | DFB/78 hose/cable transit corroded | Clean hose connections with steel brush | PCNF | PCNF | 50 | 0 | Q2-2023 | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2024-09-26 | 2020-11-04 | 2021-04-03 | 80 | PCNF | PCNF | DF /B /78/DFBA-X-6102 | Clean hose connections with steel brush | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100058030 | Water damage on cabin 414 | Water damage on cabin 414 |  |  | 0 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-11-06 | 2021-11-26 | 10 |  |  | DF /C /82 | Water damage on cabin 414 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-03-03 | 2022-07-31 | 10 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-03-03 | 2022-07-31 | 20 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-17 | 2022-03-03 | 2022-07-31 | 30 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 14 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-18 | 2022-03-03 | 2022-07-31 | 40 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-17 | 2022-03-03 | 2022-07-31 | 50 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-03-03 | 2022-07-31 | 60 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2022-03-03 | 2022-07-31 | 70 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2022-03-03 | 2022-07-31 | 80 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-15 | 2022-03-03 | 2022-07-31 | 90 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100059771 | DFFA-HCV-340004-U Internal leak | Rigger assistance |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-15 | 2022-03-03 | 2022-07-31 | 100 |  |  | DF /F /10/DFFA-HCV-340004-U | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100099831 | FA-05 THP PIT-30041 DBB int leak | ESD transmitter inhibition |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-26 | 2024-04-09 | 10 |  |  | DF /A /10/DFAA-PIT-30041 | ESD transmitter inhibition | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099831 | FA-05 THP PIT-30041 DBB int leak | ESD transmitter inhibition |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-26 | 2024-04-09 | 20 |  |  | DF /A /10/DFAA-PIT-30041 | ESD transmitter inhibition | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099831 | FA-05 THP PIT-30041 DBB int leak | ESD transmitter inhibition |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-26 | 2024-04-09 | 30 |  |  | DF /A /10/DFAA-PIT-30041 | ESD transmitter inhibition | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099831 | FA-05 THP PIT-30041 DBB int leak | ESD transmitter inhibition |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-26 | 2024-04-09 | 40 |  |  | DF /A /10/DFAA-PIT-30041 | ESD transmitter inhibition | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284288 | PSV Exchange - DFFA-PSV-570068 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /70/DFFA-PSV-570068 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284288 | PSV Exchange - DFFA-PSV-570068 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /70/DFFA-PSV-570068 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284288 | PSV Exchange - DFFA-PSV-570068 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /70/DFFA-PSV-570068 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284288 | PSV Exchange - DFFA-PSV-570068 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /70/DFFA-PSV-570068 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284288 | PSV Exchange - DFFA-PSV-570068 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /70/DFFA-PSV-570068 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284288 | PSV Exchange - DFFA-PSV-570068 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /70/DFFA-PSV-570068 | Isolation of PSV | Unknown
3 | DFDFLARE | WDF | MTN-INST | MTN-INST | 2100099204 | DFG-TT-400415 and 400416 Temp Transmt. | Isolate transmitter |  |  | 1 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-16 | 2024-03-30 | 10 |  |  | DF /G /36/DFGA-TIT-400415 | Isolate transmitter | Unknown
3 | DFDFLARE | WDF | MTN-INST | MTN-INST | 2100099204 | DFG-TT-400415 and 400416 Temp Transmt. | Isolate transmitter |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-16 | 2024-03-30 | 20 |  |  | DF /G /36/DFGA-TIT-400415 | Isolate transmitter | Unknown
3 | DFDFLARE | WDF | MTN-INST | MTN-INST | 2100099204 | DFG-TT-400415 and 400416 Temp Transmt. | Isolate transmitter |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-16 | 2024-03-30 | 30 |  |  | DF /G /36/DFGA-TIT-400415 | Isolate transmitter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 32 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-07-29 | 2024-08-02 | 2023-05-28 | 2025-11-13 | 10 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-02 | 2024-08-03 | 2023-05-28 | 2025-11-13 | 20 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 10 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-03 | 2024-08-04 | 2023-05-28 | 2025-11-13 | 30 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 10 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-04 | 2024-08-05 | 2023-05-28 | 2025-11-13 | 40 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-05 | 2024-08-06 | 2023-05-28 | 2025-11-13 | 50 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-06 | 2024-08-07 | 2023-05-28 | 2025-11-13 | 60 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-07 | 2024-08-07 | 2023-05-28 | 2025-11-13 | 70 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100078818 | Replace DFFA-HCV-030068 (DFF-LV-144 ring | Rig up for replacing DFFA-HCV-030068 |  |  | 16 | 0 | W29-W30 | 2024-07-29 | 2024-08-09 | 2024-08-07 | 2024-08-09 | 2023-05-28 | 2025-11-13 | 80 |  |  | DF /F /01/DFFA-HCV-030068 | Rig up for replacing DFFA-HCV-030068 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344044 | 1Y HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-09-18 | 10 | SECE | SECE | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344044 | 1Y HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | SECE | SECE | 4 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-20 | 2024-08-19 | 2024-09-18 | 20 | SECE | SECE | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344044 | 1Y HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | SECE | SECE | 9 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-20 | 2024-08-22 | 2024-08-19 | 2024-09-18 | 30 | SECE | SECE | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344044 | 1Y HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2024-08-19 | 2024-09-18 | 40 | SECE | SECE | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344044 | 1Y HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-19 | 2024-09-18 | 50 | SECE | SECE | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
2 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100086256 | HCV is broken and have intern leaks | Changeout valves | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2023-02-23 | 2023-04-09 | 10 | AWSC | AWSC | DF /F /27/DFFA-V-5001 | Changeout valves | Unknown
2 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100086256 | HCV is broken and have intern leaks | Changeout valves | AWSC | AWSC | 40 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-06 | 2023-02-23 | 2023-04-09 | 20 | AWSC | AWSC | DF /F /27/DFFA-V-5001 | Changeout valves | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400337677 | 1Y DFCI-FT-34012 PROD WATER - METERING | DFCI-FT-34012 PROD WATER - METERING | AWSC | AWSC | 6 | 0 | Empty | 2024-07-06 | 2024-07-07 | 2024-07-06 | 2024-07-07 | 2024-07-06 | 2024-08-22 | 10 | AWSC | AWSC | DF /C /27/DFCI-FT-34012 | DFCI-FT-34012 PROD WATER - METERING | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100064674 | DFF19 flowline drainvalve extern leaking | Isolate HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-03-30 | 2022-06-28 | 10 |  |  | DF /F /55 | Isolate HCV | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100064674 | DFF19 flowline drainvalve extern leaking | Isolate HCV |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-03-30 | 2022-06-28 | 20 |  |  | DF /F /55 | Isolate HCV | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064674 | DFF19 flowline drainvalve extern leaking | Isolate HCV |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-03-30 | 2022-06-28 | 30 |  |  | DF /F /55 | Isolate HCV | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100064674 | DFF19 flowline drainvalve extern leaking | Isolate HCV |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-03-30 | 2022-06-28 | 40 |  |  | DF /F /55 | Isolate HCV | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064674 | DFF19 flowline drainvalve extern leaking | Isolate HCV |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-03-30 | 2022-06-28 | 50 |  |  | DF /F /55 | Isolate HCV | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100064674 | DFF19 flowline drainvalve extern leaking | Isolate HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-03-30 | 2022-06-28 | 60 |  |  | DF /F /55 | Isolate HCV | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400337251 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-08-01 | 2024-08-12 | 1 |  |  | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-ROUS | 2400337251 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-08-01 | 2024-08-12 | 10 |  |  | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400337251 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-01 | 2024-08-12 | 12 |  |  | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 10 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 64 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-11 | 2020-12-19 | 2020-12-24 | 11 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 4 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 20 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 2 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-07 | 2024-06-07 | 2020-12-19 | 2020-12-24 | 30 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 12 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-08 | 2020-12-19 | 2020-12-24 | 40 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 35 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-14 | 2020-12-19 | 2020-12-24 | 41 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 3 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 42 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 16 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-07 | 2020-12-19 | 2020-12-24 | 50 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 5 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 60 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 16 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-07 | 2020-12-19 | 2020-12-24 | 70 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 5 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 80 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 16 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-09 | 2020-12-19 | 2020-12-24 | 90 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 3 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 91 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 2 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 100 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 4 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 110 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 52 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-10 | 2020-12-19 | 2020-12-24 | 120 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 130 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 140 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 16 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-07 | 2020-12-19 | 2020-12-24 | 150 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 8 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 160 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 12 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-08 | 2020-12-19 | 2020-12-24 | 170 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-ROPE | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 12 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-08 | 2020-12-19 | 2020-12-24 | 180 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 190 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 200 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 210 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100043575 | DGS: DFG 20" HP HALFDAN ESDV fails to cl | Increase of PO 4300019612 | AWSC | AWSC | 0 | 0 | Empty | 2024-06-06 | 2024-06-14 | 2024-06-06 | 2024-06-06 | 2020-12-19 | 2020-12-24 | 220 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380131 | Increase of PO 4300019612 | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-SCAF | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 25 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2024-12-30 | 2025-01-05 | 2023-10-30 | 2026-04-17 | 10 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 3 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-05 | 2025-01-06 | 2023-10-30 | 2026-04-17 | 20 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-RIGG | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 14 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-06 | 2025-01-09 | 2023-10-30 | 2026-04-17 | 30 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 14 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-02 | 2025-01-06 | 2023-10-30 | 2026-04-17 | 40 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-RIGG | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 14 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-06 | 2025-01-09 | 2023-10-30 | 2026-04-17 | 50 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 14 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-09 | 2025-01-13 | 2023-10-30 | 2026-04-17 | 60 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 2 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-13 | 2025-01-13 | 2023-10-30 | 2026-04-17 | 70 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 1 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-13 | 2025-01-13 | 2023-10-30 | 2026-04-17 | 80 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-SCAF | 2100089999 | HCV-330103 Internal Leak | De Isolate HCV´s |  |  | 12 | 0 | Empty | 2024-12-30 | 2025-01-16 | 2025-01-13 | 2025-01-16 | 2023-10-30 | 2026-04-17 | 90 |  |  | DF /C /10/DFCM-HCV-330103 | De Isolate HCV´s | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400325363 | 4Y NAV AID MAINT-DFA/DFB/DFC/DFD/DFE | NAV AID MAINT-DFA/DFB/DFC/DFD/DFE | SECE | SECE | 19 | 28 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-08-03 | 2024-03-13 | 2024-05-25 | 10 | SECE | SECE | DF /C /64/NAVAIDS | NAV AID MAINT-DFA/DFB/DFC/DFD/DFE | Unknown
A | NOSD | WPM | MTN-TELE | MTN-ELEC | 2400325363 | 4Y NAV AID MAINT-DFA/DFB/DFC/DFD/DFE | NAV AID MAINT-DFA/DFB/DFC/DFD/DFE | SECE | SECE | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-03-13 | 2024-05-25 | 20 | SECE | SECE | DF /C /64/NAVAIDS | NAV AID MAINT-DFA/DFB/DFC/DFD/DFE | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000907 | TME1600-Upgrade F&G CPU0113 to SG400 | TME1600 - Upgrade F&G CPU0113 to SG400 | PCNFSCH | PCNFSCH | 2 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2017-09-15 | 2017-10-05 | 10 | PCNFSCH | PCNFSCH | DF /C /03 | TME1600 - Upgrade F&G CPU0113 to SG400 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322283 | DFF-55-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 41 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /55/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DFF-O18 | WDF | MTN-INST | PRODTECH | 2100026481 | DFFA-PDT-291118 skift af block på dffa-p | L3 Isolation of DFFA-PDT-291118 | AWSC | AWSC | 3 | 0 | W47-W48 IOP 03-12 / 04-12 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2019-10-05 | 2019-10-25 | 10 | AWSC | AWSC | DF /F /37/DFFA-PDT-291118 | L3 Isolation of DFFA-PDT-291118 | Unknown
3 | DFF-O18 | WDF | MTN-INST | MTN-INST | 2100026481 | DFFA-PDT-291118 skift af block på dffa-p | L3 Isolation of DFFA-PDT-291118 | AWSC | AWSC | 4 | 0 | W47-W48 IOP 03-12 / 04-12 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-10-05 | 2019-10-25 | 20 | AWSC | AWSC | DF /F /37/DFFA-PDT-291118 | L3 Isolation of DFFA-PDT-291118 | Unknown
3 | DFF-O18 | WDF | MTN-INST | PRODTECH | 2100026481 | DFFA-PDT-291118 skift af block på dffa-p | L3 Isolation of DFFA-PDT-291118 | AWSC | AWSC | 3 | 0 | W47-W48 IOP 03-12 / 04-12 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2019-10-05 | 2019-10-25 | 30 | AWSC | AWSC | DF /F /37/DFFA-PDT-291118 | L3 Isolation of DFFA-PDT-291118 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235751 | 1Y 220V UPS.SYST BATT & CHAR F.TEST-DFC | 220V UPS.SYST BATT & CHAR F.TEST-DFC | SECE | SECE | 16 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-19 | 2023-08-02 | 2023-09-01 | 10 | SECE | SECE | DF /C /06/UPS-SYSTEMS | 220V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018131 | Replace Motor protection 1841-M107 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M107-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018131 | Replace Motor protection 1841-M107 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M107-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018131 | Replace Motor protection 1841-M107 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M107-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018131 | Replace Motor protection 1841-M107 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M107-02 | New mat num | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056492 | Repair HT-cable DFF module 2 | Change heattrace cable |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-01-23 | 2022-09-20 | 10 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Change heattrace cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056492 | Repair HT-cable DFF module 2 | Change heattrace cable |  |  | 3 | 0 | BL-TEAM | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-01-23 | 2022-09-20 | 20 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Change heattrace cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056492 | Repair HT-cable DFF module 2 | Change heattrace cable |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-01-23 | 2022-09-20 | 30 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Change heattrace cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056492 | Repair HT-cable DFF module 2 | Change heattrace cable |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-01-23 | 2022-09-20 | 40 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Change heattrace cable | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015381 | Replace LB4 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /C /02/DFCI-X-0704 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015381 | Replace LB4 coolant with GlysantinG30 | Isolate lifeboat |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /C /02/DFCI-X-0704 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015381 | Replace LB4 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /C /02/DFCI-X-0704 | Isolate lifeboat | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 10 | 4 | W23-W24 | 2024-07-04 | 2024-07-04 | 2023-08-09 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 10 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 3 | 7 | W23-W24 | 2024-07-04 | 2024-07-04 | 2023-08-10 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 20 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 15 | 28 | W23-W24 | 2024-07-04 | 2024-07-04 | 2023-08-11 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 30 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 10 | 0 | W23-W24 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 40 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 5 | 15 | W23-W24 | 2024-07-04 | 2024-07-04 | 2024-07-01 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 41 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 10 | 47 | W23-W24 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 50 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 5 | 4 | W23-W24 | 2024-07-04 | 2024-07-04 | 2024-07-02 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 60 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 70 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094026 | Noise from LP booster pump motor PM-3601 | Setup/de-rig rigg. equipment | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-08-09 | 2023-12-22 | 80 | PCNF | PCNF | DF /F /21/DFFA-PM-3601 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106302 | Firedamper DFF-FD-120150 feedback fail | Adjust DFFA-ZSC-120150 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-09 | 2024-07-22 | 10 |  |  | DF /F /03 | Adjust DFFA-ZSC-120150 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322257 | DFC-10-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 7 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /10/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263359 | 3M WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCH | SCH | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-07-01 | 2023-07-11 | 10 | SCH | SCH | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341920 | DFG_1Y_25537 INT STRUCT INSP - GVI | DFG_1Y_25537 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/EL_25537 (LIFE BOAT ACCESS) | DFG_1Y_25537 INT STRUCT INSP - GVI | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-RIGG | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 10 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-MECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-07-13 | 2021-08-22 | 11 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | PRODTECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 15 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-INST | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 20 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-MECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 25 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-RIGG | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 30 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-INST | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 35 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-RIGG | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 40 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-MECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 45 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-INST | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 50 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-INST | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 80 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | PRODTECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 90 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-RIGG | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 100 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-MECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 110 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
3 | DFA-O18 | WDF | MTN-MECH | MTN-MECH | 2100051783 | PMAT DFA-18 Choke ZT fault indication. | Replace Position Measurement Device | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-07-13 | 2021-08-22 | 120 | PCNFAWSC | PCNFAWSC | DF /A /10/DFAA-ZT-30306 | Replace Position Measurement Device | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235661 | 4Y 400V N-SWB MAINT DFCI-N-1802-R06 | 400V N-SWB INSP DFCI-N-1802-R06 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R06B | 400V N-SWB INSP DFCI-N-1802-R06 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235661 | 4Y 400V N-SWB MAINT DFCI-N-1802-R06 | 400V N-SWB INSP DFCI-N-1802-R06 | AWSC | AWSC | 19 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R06B | 400V N-SWB INSP DFCI-N-1802-R06 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235661 | 4Y 400V N-SWB MAINT DFCI-N-1802-R06 | 400V N-SWB INSP DFCI-N-1802-R06 | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R06B | 400V N-SWB INSP DFCI-N-1802-R06 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235661 | 4Y 400V N-SWB MAINT DFCI-N-1802-R06 | 400V N-SWB INSP DFCI-N-1802-R06 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R06B | 400V N-SWB INSP DFCI-N-1802-R06 | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325367 | 1YL-AUS TOOLS DFC | L-AUS TOOLS MAINTENANCE CHECK |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-08 | 2024-05-25 | 10 |  |  | DF /C /61 | L-AUS TOOLS MAINTENANCE CHECK | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400325367 | 1YL-AUS TOOLS DFC | L-AUS TOOLS MAINTENANCE CHECK |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-08 | 2024-05-25 | 20 |  |  | DF /C /61 | L-AUS TOOLS MAINTENANCE CHECK | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400330008 | 1Y WIRELINE OVERRIDE PANELS - DFF WH S | WIRELINE OVERRIDE PANELS-DFF WH S |  |  | 6.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-05-29 | 2024-06-28 | 10 |  |  | DF /F /07 | WIRELINE OVERRIDE PANELS-DFF WH S | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400330008 | 1Y WIRELINE OVERRIDE PANELS - DFF WH S | WIRELINE OVERRIDE PANELS-DFF WH S |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-05-29 | 2024-06-28 | 20 |  |  | DF /F /07 | WIRELINE OVERRIDE PANELS-DFF WH S | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300001878 | Genenal WO SCADA equipment | Genenal WO SCADA equipment |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-01 | 2021-11-28 | 10 |  |  | DF /F /20 | Genenal WO SCADA equipment | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 8 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-17 | 2021-02-19 | 2021-05-20 | 10 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-17 | 2024-09-18 | 2021-02-19 | 2021-05-20 | 20 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-18 | 2021-02-19 | 2021-05-20 | 30 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-19 | 2021-02-19 | 2021-05-20 | 40 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-19 | 2024-09-20 | 2021-02-19 | 2021-05-20 | 50 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-20 | 2021-02-19 | 2021-05-20 | 60 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-21 | 2021-02-19 | 2021-05-20 | 70 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-23 | 2021-02-19 | 2021-05-20 | 80 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 4 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2021-02-19 | 2021-05-20 | 90 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2021-02-19 | 2021-05-20 | 100 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-25 | 2021-02-19 | 2021-05-20 | 110 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2021-02-19 | 2021-05-20 | 120 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044950 | DFG PCV-530038 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-27 | 2021-02-19 | 2021-05-20 | 130 |  |  | DF /G /76/DFGA-PCV-530038 | Isolate PCV | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235620 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-8-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235620 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-8-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235620 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-8-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235620 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-8-5 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100099540 | DFF H2s P-3907 Change out PRV | Demount PRV and blind off |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-11-24 | 2024-04-07 | 10 |  |  | DF /F /75/DFFA-PRV-390570 | Demount PRV and blind off | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099540 | DFF H2s P-3907 Change out PRV | Demount PRV and blind off |  |  | 4 | 0 | W23-W24 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-11-24 | 2024-04-07 | 20 |  |  | DF /F /75/DFFA-PRV-390570 | Demount PRV and blind off | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099540 | DFF H2s P-3907 Change out PRV | Demount PRV and blind off |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2023-11-24 | 2024-04-07 | 30 |  |  | DF /F /75/DFFA-PRV-390570 | Demount PRV and blind off | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099540 | DFF H2s P-3907 Change out PRV | Demount PRV and blind off |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2023-11-24 | 2024-04-07 | 40 |  |  | DF /F /75/DFFA-PRV-390570 | Demount PRV and blind off | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100099540 | DFF H2s P-3907 Change out PRV | Demount PRV and blind off |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-11-24 | 2024-04-07 | 50 |  |  | DF /F /75/DFFA-PRV-390570 | Demount PRV and blind off | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098146 | Install bracket and sign for fire exting | Install bracket and sign for fire exting |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-13 | 2026-08-30 | 10 |  |  | DF /C /02/DFCC-EXP-0479 | Install bracket and sign for fire exting | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 2 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 10 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 2 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 20 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 24 | 5 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 30 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 5 | 12 | W23-W24 | 2024-07-15 | 2024-07-15 | 2023-05-16 | 2023-07-10 | 2023-06-03 | 2025-11-19 | 40 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 45 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 50 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 12 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 60 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 2 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 70 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 5 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 80 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 4 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 90 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012594 | Replace DFGA-PSV-430012B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 100 | PCNF | PCNF | DF /G /32/DFGA-PSV-430012B | Send PSV onshhore for service | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 20 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-06 | 2023-10-19 | 2024-03-02 | 10 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-13 | 2023-10-19 | 2024-03-02 | 20 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-14 | 2023-10-19 | 2024-03-02 | 30 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 6 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-14 | 2024-07-15 | 2023-10-19 | 2024-03-02 | 40 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 8 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 50 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 2 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 60 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 70 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 10 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-10-19 | 2024-03-02 | 80 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097604 | LB Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 0 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-05 | 2023-10-19 | 2024-03-02 | 90 | AWSC | AWSC | DF /E /02/DFEZ-X-0701 | Denso tape to cover greased thread | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400329521 | 3M UHF PORTABLE FIRE RADIOS -DFC | UHF PORTABLE FIRE RADIOS -DFC | SCHSECE | SCHSECE | 1 | 0 | W23-W24 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-22 | 10 | SCHSECE | SCHSECE | DF /C /08/EXTERNAL-COMMUNICATION | UHF PORTABLE FIRE RADIOS -DFC | Unknown
4 | DFB-3560 | WDF | MTN-INST | PRODTECH | 2100070241 | DFBA-SOV-57300 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 10 | SECE | SECE | DF /B /70/DFBA-ESDV-57300 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3560 | WDF | MTN-INST | MTN-INST | 2100070241 | DFBA-SOV-57300 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 20 | SECE | SECE | DF /B /70/DFBA-ESDV-57300 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3560 | WDF | MTN-INST | MTN-INST | 2100070241 | DFBA-SOV-57300 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 2 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 30 | SECE | SECE | DF /B /70/DFBA-ESDV-57300 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3560 | WDF | MTN-INST | MTN-INST | 2100070241 | DFBA-SOV-57300 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 40 | SECE | SECE | DF /B /70/DFBA-ESDV-57300 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3560 | WDF | MTN-INST | PRODTECH | 2100070241 | DFBA-SOV-57300 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 50 | SECE | SECE | DF /B /70/DFBA-ESDV-57300 | Isolate solenoid valve (SDV) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-07-31 | 2020-08-19 | 2020-11-17 | 10 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-07-29 | 2020-08-19 | 2020-11-17 | 11 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-07-30 | 2020-08-19 | 2020-11-17 | 20 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-30 | 2024-07-31 | 2020-08-19 | 2020-11-17 | 30 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-31 | 2024-07-31 | 2020-08-19 | 2020-11-17 | 40 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-31 | 2024-08-01 | 2020-08-19 | 2020-11-17 | 50 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-01 | 2024-08-02 | 2020-08-19 | 2020-11-17 | 60 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-02 | 2024-08-03 | 2020-08-19 | 2020-11-17 | 70 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-03 | 2024-08-03 | 2020-08-19 | 2020-11-17 | 80 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-03 | 2024-08-04 | 2020-08-19 | 2020-11-17 | 81 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-04 | 2024-08-05 | 2020-08-19 | 2020-11-17 | 90 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100035726 | 4 Floodlight have bad support - PDO | Remove old lights |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-05 | 2024-08-06 | 2020-08-19 | 2020-11-17 | 100 |  |  | DF /F /61 | Remove old lights | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040520 | DFGA-PD-553104 Ingen N2 på pulsationsdæm | Precharge / maintain pulsation damper ac |  |  | 1.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-11-17 | 2020-12-27 | 10 |  |  | DF /G /75/DFGA-PD-553104 | Precharge / maintain pulsation damper ac | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040520 | DFGA-PD-553104 Ingen N2 på pulsationsdæm | Precharge / maintain pulsation damper ac |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2020-11-17 | 2020-12-27 | 20 |  |  | DF /G /75/DFGA-PD-553104 | Precharge / maintain pulsation damper ac | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040520 | DFGA-PD-553104 Ingen N2 på pulsationsdæm | Precharge / maintain pulsation damper ac |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2020-11-17 | 2020-12-27 | 30 |  |  | DF /G /75/DFGA-PD-553104 | Precharge / maintain pulsation damper ac | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235611 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235611 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 |  |  | 11 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-18 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235611 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235611 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-19 | 380V N-SWB-INSP-DFFA-N-1802A-19 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263361 | 6M SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 |  |  | 4 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2023-06-21 | 2023-07-10 | 10 |  |  | DF /B /54/DFBA-P-3501 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | Unknown
C | NOSD | WPM | VEN-INSP | VEN-INSP | 2400116272 | 3M NOx in Exhaust, VENDOR, DFG | NOX CONCENTRATION IN GASTURBINES | AWSC | AWSC | 30 | 0 | W43 IOP 18-27/10 | 2023-01-16 | 2023-01-19 | 2023-01-16 | 2023-01-19 | 2021-03-19 | 2021-03-30 | 10 | AWSC | AWSC | DF /G /60/DFGA-GT-1640 | NOX CONCENTRATION IN GASTURBINES | Unknown
1 | Empty | WRO | VEN-INST | VEN-INST | 2300006718 | Dan Update Safety Monitor | operation_description_not_present |  |  | 0 | 0 | Empty | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-10-06 | 10 |  |  | DF /C /04 | operation_description_not_present | Unknown
1 | Empty | WRO | VEN-INST | MTN-TELE | 2300006718 | Dan Update Safety Monitor | operation_description_not_present |  |  | 0 | 0 | Empty | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 | 2023-10-06 | 20 |  |  | DF /C /04 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079507 | Defekt checkventil P-5052 | Defekt checkventil P-5052 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2023-06-13 | 10 |  |  | DF /F /28/DFFA-P-5052 | Defekt checkventil P-5052 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079507 | Defekt checkventil P-5052 | Defekt checkventil P-5052 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2023-06-13 | 20 |  |  | DF /F /28/DFFA-P-5052 | Defekt checkventil P-5052 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079507 | Defekt checkventil P-5052 | Defekt checkventil P-5052 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-01-29 | 2023-06-13 | 30 |  |  | DF /F /28/DFFA-P-5052 | Defekt checkventil P-5052 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079507 | Defekt checkventil P-5052 | Defekt checkventil P-5052 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-01-29 | 2023-06-13 | 40 |  |  | DF /F /28/DFFA-P-5052 | Defekt checkventil P-5052 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022645 | PM-3670 Montering af ny vibration probe. | Montering af ny vibration probe.XE-36741 | PCNF | PCNF | 4 | 4 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2019-09-30 | 2019-10-20 | 10 | PCNF | PCNF | DF /C /23/DFCM-XT-36741 | Montering af ny vibration probe.XE-36741 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022645 | PM-3670 Montering af ny vibration probe. | Montering af ny vibration probe.XE-36741 | PCNF | PCNF | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2019-09-30 | 2019-10-20 | 20 | PCNF | PCNF | DF /C /23/DFCM-XT-36741 | Montering af ny vibration probe.XE-36741 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024087 | DFG nøddiesel exhaust lækage | Drawing for spool DFG nøddiesel exhaust |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2018-12-18 | 2019-01-27 | 10 |  |  | DF /G /05/DFGA-A-1740 | Drawing for spool DFG nøddiesel exhaust | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024087 | DFG nøddiesel exhaust lækage | Drawing for spool DFG nøddiesel exhaust |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-12-18 | 2019-01-27 | 170 |  |  | DF /G /05/DFGA-A-1740 | Drawing for spool DFG nøddiesel exhaust | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025165 | DFGA-V-4040 DFG Flare drum defekt 2" HCV | L3 Isolation of DFGA-V-4040 DFG Flare dr |  |  | 3 | 0 | S/D Code missing | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2019-02-26 | 2021-02-15 | 10 |  |  | DF /G /36/DFGA-V-4040 | L3 Isolation of DFGA-V-4040 DFG Flare dr | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025165 | DFGA-V-4040 DFG Flare drum defekt 2" HCV | L3 Isolation of DFGA-V-4040 DFG Flare dr |  |  | 4 | 0 | S/D Code missing | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2019-02-26 | 2021-02-15 | 20 |  |  | DF /G /36/DFGA-V-4040 | L3 Isolation of DFGA-V-4040 DFG Flare dr | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025165 | DFGA-V-4040 DFG Flare drum defekt 2" HCV | L3 Isolation of DFGA-V-4040 DFG Flare dr |  |  | 3 | 0 | S/D Code missing | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2019-02-26 | 2021-02-15 | 30 |  |  | DF /G /36/DFGA-V-4040 | L3 Isolation of DFGA-V-4040 DFG Flare dr | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400241131 | 6M WELL HYD. PANEL MAINT - DFEZ-A-3102 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2023-03-26 | 2023-04-11 | 10 | SCH | SCH | DF /E /07/DFEZ-A-3102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241131 | 6M WELL HYD. PANEL MAINT - DFEZ-A-3102 | ISOLATION BY PRODUCTION | SCH | SCH | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2023-03-26 | 2023-04-11 | 20 | SCH | SCH | DF /E /07/DFEZ-A-3102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400241131 | 6M WELL HYD. PANEL MAINT - DFEZ-A-3102 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2023-03-26 | 2023-04-11 | 30 | SCH | SCH | DF /E /07/DFEZ-A-3102 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-01-17 | 2021-02-26 | 10 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-01-17 | 2021-02-26 | 20 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2021-01-17 | 2021-02-26 | 30 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2021-01-17 | 2021-02-26 | 40 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2021-01-17 | 2021-02-26 | 50 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2021-01-17 | 2021-02-26 | 60 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2021-01-17 | 2021-02-26 | 70 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100043863 | DFB-02 WCV switch problem | Order faulty component |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2021-01-17 | 2021-02-26 | 80 |  |  | DF /B /10/DFBA-WCV-30026 | Order faulty component | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300002016 | DK40 - Replaced by 2300004798 ONSUMABLE | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2021-04-03 | 2022-01-28 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100100120 | Deif skærm DFF-A-1610 kontrol panel | Assist with installation |  |  | 8 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-24 | 2023-12-01 | 2024-04-14 | 10 |  |  | DF /F /60/DFFA-FP-1610 | Assist with installation | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TURB | 2100100120 | Deif skærm DFF-A-1610 kontrol panel | Assist with installation |  |  | 4 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2023-12-01 | 2024-04-14 | 20 |  |  | DF /F /60/DFFA-FP-1610 | Assist with installation | Unknown
A | DFG-3590 | WPM | MTN-ELEC | MTN-ELEC | 2400235739 | 4Y 400V UPS-SWB F.TEST-DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSCSECE | AWSCSECE | DF /G /06/DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | Unknown
A | DFG-3590 | WPM | MTN-ELEC | MTN-ELEC | 2400235739 | 4Y 400V UPS-SWB F.TEST-DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | AWSCSECE | AWSCSECE | 14 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 20 | AWSCSECE | AWSCSECE | DF /G /06/DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | Unknown
A | DFG-3590 | WPM | MTN-ELEC | MTN-ELEC | 2400235739 | 4Y 400V UPS-SWB F.TEST-DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 30 | AWSCSECE | AWSCSECE | DF /G /06/DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | Unknown
A | DFG-3590 | WPM | MTN-ELEC | MTN-ELEC | 2400235739 | 4Y 400V UPS-SWB F.TEST-DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 40 | AWSCSECE | AWSCSECE | DF /G /06/DFGA-N-1941 | 400V UPS-SWB F.TEST-DFGA-N-1941 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100022376 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Isolate DFCI-SOV/ESDV-34020 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2019-09-05 | 2019-12-04 | 10 | AWSC | AWSC | DF /C /20/DFCI-ESDV-34020 | L3 Isolate DFCI-SOV/ESDV-34020 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022376 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Isolate DFCI-SOV/ESDV-34020 | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-02 | 2019-09-05 | 2019-12-04 | 20 | AWSC | AWSC | DF /C /20/DFCI-ESDV-34020 | L3 Isolate DFCI-SOV/ESDV-34020 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022376 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Isolate DFCI-SOV/ESDV-34020 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2019-09-05 | 2019-12-04 | 30 | AWSC | AWSC | DF /C /20/DFCI-ESDV-34020 | L3 Isolate DFCI-SOV/ESDV-34020 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100022376 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Isolate DFCI-SOV/ESDV-34020 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2019-09-05 | 2019-12-04 | 40 | AWSC | AWSC | DF /C /20/DFCI-ESDV-34020 | L3 Isolate DFCI-SOV/ESDV-34020 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022376 | DFCI-SOV/ESDV-34020 leaking hydraulics | L3 Isolate DFCI-SOV/ESDV-34020 | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2019-09-05 | 2019-12-04 | 50 | AWSC | AWSC | DF /C /20/DFCI-ESDV-34020 | L3 Isolate DFCI-SOV/ESDV-34020 | Unknown
2 | DFB-W07 | WDF | MTN-INST | PRODTECH | 2100087253 | DFB-07 Choke CVA-30007 ZT defect | Well shutdown |  |  | 2 | 2 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /B /55/DFBA-ZT-30007 | Well shutdown | Unknown
2 | DFB-W07 | WDF | MTN-INST | MTN-INST | 2100087253 | DFB-07 Choke CVA-30007 ZT defect | Well shutdown |  |  | 0.5 | 0.5 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /B /55/DFBA-ZT-30007 | Well shutdown | Unknown
2 | DFB-W07 | WDF | MTN-INST | MTN-INST | 2100087253 | DFB-07 Choke CVA-30007 ZT defect | Well shutdown |  |  | 2 | 2 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /B /55/DFBA-ZT-30007 | Well shutdown | Unknown
2 | DFB-W07 | WDF | MTN-INST | MTN-INST | 2100087253 | DFB-07 Choke CVA-30007 ZT defect | Well shutdown |  |  | 0.5 | 0.5 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /B /55/DFBA-ZT-30007 | Well shutdown | Unknown
2 | DFB-W07 | WDF | MTN-INST | MTN-INST | 2100087253 | DFB-07 Choke CVA-30007 ZT defect | Well shutdown |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 50 |  |  | DF /B /55/DFBA-ZT-30007 | Well shutdown | Unknown
2 | DFB-W07 | WDF | MTN-INST | PRODTECH | 2100087253 | DFB-07 Choke CVA-30007 ZT defect | Well shutdown |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 60 |  |  | DF /B /55/DFBA-ZT-30007 | Well shutdown | Unknown
2 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006658 | IT switch to CEA platform. | IT switch to CEA platform. |  |  | 0 | 0 | Empty | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-16 | 10 |  |  | DF /C | IT switch to CEA platform. | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000755 | MEDIC 01.01.19 TIL 31.12.19 | MEDIC 01.03.2020 TIL 31.12.2020 |  |  | 0 | 0 | Empty | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /C | MEDIC 01.03.2020 TIL 31.12.2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000755 | MEDIC 01.01.19 TIL 31.12.19 | MEDIC 01.03.2020 TIL 31.12.2020 |  |  | 0 | 0 | Empty | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF /C | MEDIC 01.03.2020 TIL 31.12.2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000755 | MEDIC 01.01.19 TIL 31.12.19 | MEDIC 01.03.2020 TIL 31.12.2020 |  |  | 0 | 0 | Empty | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2019-12-31 | 2019-12-31 | 30 |  |  | DF /C | MEDIC 01.03.2020 TIL 31.12.2020 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322316 | DFG-23-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /23/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400346575 | 1Y CHEM DISTR PANEL MAINT-DFFA-A-39705 | CHEM DISTR PANEL MAINT-DFFA-A-39705 |  |  | 16 | 0 | Empty | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-10-01 | 10 |  |  | DF /F /75/DFFA-A-39705 | CHEM DISTR PANEL MAINT-DFFA-A-39705 | Unknown
3 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100062838 | DFF level 1 well head syd,utæt 2" HCVèr | Remove both old HCV´s |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2022-03-03 | 2022-06-01 | 10 |  |  | DF /F /54/DFFA-EP-3804 | Remove both old HCV´s | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100062838 | DFF level 1 well head syd,utæt 2" HCVèr | Remove both old HCV´s |  |  | 2 | 2 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-02 | 2022-03-03 | 2022-06-01 | 20 |  |  | DF /F /54/DFFA-EP-3804 | Remove both old HCV´s | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100062838 | DFF level 1 well head syd,utæt 2" HCVèr | Remove both old HCV´s |  |  | 2 | 14.5 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-02 | 2022-03-03 | 2022-06-01 | 30 |  |  | DF /F /54/DFFA-EP-3804 | Remove both old HCV´s | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100062838 | DFF level 1 well head syd,utæt 2" HCVèr | Remove both old HCV´s |  |  | 2 | 2 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-03 | 2022-03-03 | 2022-06-01 | 40 |  |  | DF /F /54/DFFA-EP-3804 | Remove both old HCV´s | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100062838 | DFF level 1 well head syd,utæt 2" HCVèr | Remove both old HCV´s |  |  | 2 | 12.5 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-03 | 2024-07-03 | 2022-03-03 | 2022-06-01 | 50 |  |  | DF /F /54/DFFA-EP-3804 | Remove both old HCV´s | Unknown
3 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100062838 | DFF level 1 well head syd,utæt 2" HCVèr | Remove both old HCV´s |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2022-03-03 | 2022-06-01 | 60 |  |  | DF /F /54/DFFA-EP-3804 | Remove both old HCV´s | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235755 | 4Y 380V UPS-DP F.TEST DFBA-DP-1911/2/3 | 380V UPS-DP F.TEST DFBA-DP-1911/2/3 | AWSCSECE | AWSCSECE | 13 | 0 | Empty | 2024-07-24 | 2024-07-27 | 2024-07-24 | 2024-07-27 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /06/DISTRIBUTION-PANELS | 380V UPS-DP F.TEST DFBA-DP-1911/2/3 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235755 | 4Y 380V UPS-DP F.TEST DFBA-DP-1911/2/3 | 380V UPS-DP F.TEST DFBA-DP-1911/2/3 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /06/DISTRIBUTION-PANELS | 380V UPS-DP F.TEST DFBA-DP-1911/2/3 | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 13 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2022-05-31 | 2022-06-01 | 2018-12-28 | 2019-03-28 | 10 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 20.100000000000001421085471515 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 20 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 13.400000000000000355271367876 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-09 | 2024-01-10 | 2018-12-28 | 2019-03-28 | 30 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 5 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-10 | 2024-01-11 | 2018-12-28 | 2019-03-28 | 40 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 13.400000000000000355271367876 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-11 | 2024-01-12 | 2018-12-28 | 2019-03-28 | 45 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 13.400000000000000355271367876 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-12 | 2024-01-13 | 2018-12-28 | 2019-03-28 | 50 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 60 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-08 | 2024-01-12 | 2018-12-28 | 2019-03-28 | 60 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 48 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2018-12-28 | 2019-03-28 | 70 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 36 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 80 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 90 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-08 | 2024-01-12 | 2018-12-28 | 2019-03-28 | 90 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003150 | Scaff / Iso assists FORCE 13515 | BUILD SCAFFOLDING |  |  | 36 | 0 | Empty | 2022-05-31 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2018-12-28 | 2019-03-28 | 100 |  |  | DF /G /53/DFG-26-WI-035-0009-AB-U | BUILD SCAFFOLDING | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100068310 | DFFW/78 Replace operator seat | Isolation/deisolation of crane |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-15 | 2022-08-08 | 2023-01-05 | 10 |  |  | DF /F /78/DFFA-A-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100068310 | DFFW/78 Replace operator seat | Isolation/deisolation of crane |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-19 | 2022-08-08 | 2023-01-05 | 20 |  |  | DF /F /78/DFFA-A-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100068310 | DFFW/78 Replace operator seat | Isolation/deisolation of crane |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-19 | 2022-08-08 | 2023-01-05 | 30 |  |  | DF /F /78/DFFA-A-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100068310 | DFFW/78 Replace operator seat | Isolation/deisolation of crane |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2022-08-08 | 2023-01-05 | 40 |  |  | DF /F /78/DFFA-A-6102 | Isolation/deisolation of crane | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | PRODTECH | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 10 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-ELEC | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 20 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 6 | 9 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 30 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 40 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 4 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 50 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | PRODTECH | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 60 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 70 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100101567 | HP CMPR Journal Brg.Temp.SF TE-431065 | New Temp. converter | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-21 | 2024-05-04 | 80 | PCNF | PCNF | DF /F /31/DFFA-TE-431065 | New Temp. converter | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215517 | 1Y HVAC EXHAUST CHECK - DFC | HVAC EXHAUST DIRECT DRIVE CHECK - DFC |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2022-10-22 | 2022-11-21 | 10 |  |  | DF /C /09/DFCC-B-1207A | HVAC EXHAUST DIRECT DRIVE CHECK - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215517 | 1Y HVAC EXHAUST CHECK - DFC | HVAC EXHAUST DIRECT DRIVE CHECK - DFC |  |  | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2022-10-22 | 2022-11-21 | 20 |  |  | DF /C /09/DFCC-B-1207A | HVAC EXHAUST DIRECT DRIVE CHECK - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215517 | 1Y HVAC EXHAUST CHECK - DFC | HVAC EXHAUST DIRECT DRIVE CHECK - DFC |  |  | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2022-10-22 | 2022-11-21 | 30 |  |  | DF /C /09/DFCC-B-1207A | HVAC EXHAUST DIRECT DRIVE CHECK - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215517 | 1Y HVAC EXHAUST CHECK - DFC | HVAC EXHAUST DIRECT DRIVE CHECK - DFC |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2022-10-22 | 2022-11-21 | 40 |  |  | DF /C /09/DFCC-B-1207A | HVAC EXHAUST DIRECT DRIVE CHECK - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088046 | Replace Basket stretcher rusty hook | Replace feet rest and crowfoot lifting |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-10 | 2023-09-22 | 10 |  |  | DF /C /02/DFCC-STR-0650 | Replace feet rest and crowfoot lifting | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322274 | DFE-28-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 34 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235646 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L08A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235646 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L08 | ISOLATION ELECTRICAL | AWSC | AWSC | 19 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L08A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235646 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L08 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-28 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L08A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235646 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L08A1 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 0 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-08 | 2024-08-08 | 2024-06-08 | 2024-10-21 | 10 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 4 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-08 | 2024-08-08 | 2024-06-08 | 2024-10-21 | 15 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 1 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-08 | 2024-08-09 | 2024-06-08 | 2024-10-21 | 20 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 1 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-09 | 2024-08-09 | 2024-06-08 | 2024-10-21 | 30 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 3 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-09 | 2024-08-10 | 2024-06-08 | 2024-10-21 | 40 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 4 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-10 | 2024-08-11 | 2024-06-08 | 2024-10-21 | 70 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 48 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-11 | 2024-08-17 | 2024-06-08 | 2024-10-21 | 80 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 20 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-17 | 2024-08-22 | 2024-06-08 | 2024-10-21 | 90 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 2 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-06-08 | 2024-10-21 | 100 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111338 | DFF N2 membrane replacing | DFF N2 membrane replacing |  |  | 1 | 0 | Empty | 2024-08-08 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-06-08 | 2024-10-21 | 110 |  |  | DF /F /74/DFFA-A-0801 | DFF N2 membrane replacing | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 2 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2020-03-25 | 2020-06-23 | 10 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-03-25 | 2020-06-23 | 20 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 8 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-04 | 2020-03-25 | 2020-06-23 | 30 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2020-03-25 | 2020-06-23 | 40 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 1 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2020-03-25 | 2020-06-23 | 50 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2020-03-25 | 2020-06-23 | 60 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 5 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-03-25 | 2020-06-23 | 70 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 5 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-03-25 | 2020-06-23 | 80 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 5 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-03-25 | 2020-06-23 | 90 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 5 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2020-03-25 | 2020-06-23 | 100 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100029105 | DFA-03 def. ventil på WI manifold. | Prepare Permit/Tools/Matr | AWSC | AWSC | 2 | 0 | W41-42 | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-02 | 2020-03-25 | 2020-06-23 | 110 | AWSC | AWSC | DF /A /75/DFAA-HCV-35054 | Prepare Permit/Tools/Matr | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321272 | 1Y PRIME MOVER DFAA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-09-19 | 2024-09-19 | 2024-08-15 | 2024-09-14 | 10 | AWSC | AWSC | DF /A /78/DFAA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321272 | 1Y PRIME MOVER DFAA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 37 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-09-19 | 2024-09-28 | 2024-08-15 | 2024-09-14 | 20 | AWSC | AWSC | DF /A /78/DFAA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400321272 | 1Y PRIME MOVER DFAA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 9 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-09-28 | 2024-09-30 | 2024-08-15 | 2024-09-14 | 40 | AWSC | AWSC | DF /A /78/DFAA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321272 | 1Y PRIME MOVER DFAA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-08-15 | 2024-09-14 | 50 | AWSC | AWSC | DF /A /78/DFAA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
4 | DFGHPSEP | WGN | PRODTECH | PRODTECH | 2200003187 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFG-HPSEP | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2018-01-20 | 2019-01-15 | 10 | AWSC | AWSC | DF /G /20/DFGA-ESDV-340015 | Safing af DFG-HPSEP | Unknown
4 | DFGHPSEP | WGN | PRODTECH | PRODTECH | 2200003187 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFG-HPSEP | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2018-01-20 | 2019-01-15 | 20 | AWSC | AWSC | DF /G /20/DFGA-ESDV-340015 | Safing af DFG-HPSEP | Unknown
4 | DFGHPSEP | WGN | PRODTECH | PRODTECH | 2200003187 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFG-HPSEP | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2018-01-20 | 2019-01-15 | 21 | AWSC | AWSC | DF /G /20/DFGA-ESDV-340015 | Safing af DFG-HPSEP | Unknown
4 | DFGHPSEP | WGN | PRODTECH | PRODTECH | 2200003187 | CMAT:ESDV / BDV-Udskifte def. manometre. | Safing af DFG-HPSEP | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-05 | 2018-01-20 | 2019-01-15 | 40 | AWSC | AWSC | DF /G /20/DFGA-ESDV-340015 | Safing af DFG-HPSEP | Unknown
4 | DFB-OIL | WRO | MTN-TELE | MTN-TELE | 2300000901 | R8 Upgrade S400 I/O on RTU2039 | Upgrade S400 I/O on RTU2039 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-01-25 | 2019-01-20 | 10 |  |  | DF /B /04/DFBA-FP-2039 | Upgrade S400 I/O on RTU2039 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342419 | 6M BDV LUB/INSP IPHP - DFF | BDV LUB/MAINT IPHP - DFF |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-12 | 2024-08-28 | 10 |  |  | DF /F /30/BDV | BDV LUB/MAINT IPHP - DFF | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339285 | DFF_1Y_61000 INT STRUCT INSP - GVI | DFF_1Y_61000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_61000 (WL MODULE DECK) | DFF_1Y_61000 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344052 | 6M H2S SCAVENG PUMPS MAINT-DFGA-P-7640/1 | H2S SCAVENG PUMPS MAINT-DFGA-P-7640/1 |  |  | 1 | 0 | Empty | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-20 | 10 |  |  | DF /G /75/DFGA-A-7602 | H2S SCAVENG PUMPS MAINT-DFGA-P-7640/1 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055444 | Utæt PD SCALE INHIBITOR PUMP Skid | Isolate DFGA-PD-3988 |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-28 | 2021-12-07 | 2022-05-06 | 20 |  |  | DF /G /75/DFGA-A-3988 | Isolate DFGA-PD-3988 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055444 | Utæt PD SCALE INHIBITOR PUMP Skid | Isolate DFGA-PD-3988 |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-09-02 | 2021-12-07 | 2022-05-06 | 30 |  |  | DF /G /75/DFGA-A-3988 | Isolate DFGA-PD-3988 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055444 | Utæt PD SCALE INHIBITOR PUMP Skid | Isolate DFGA-PD-3988 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2021-12-07 | 2022-05-06 | 40 |  |  | DF /G /75/DFGA-A-3988 | Isolate DFGA-PD-3988 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100025159 | SMAT:DFGA-A-6140 Replacement of exhaust | L3 Deisolation of crane DFGA-A-6140 |  |  | 3 | 0 | W11 | 2023-04-03 | 2023-04-07 | 2023-04-03 | 2023-04-04 | 2019-03-27 | 2019-05-06 | 10 |  |  | DF /G /78/DFGA-A-6140 | L3 Deisolation of crane DFGA-A-6140 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025159 | SMAT:DFGA-A-6140 Replacement of exhaust | L3 Deisolation of crane DFGA-A-6140 |  |  | 24 | 0 | W11 | 2023-04-03 | 2023-04-07 | 2023-04-04 | 2023-04-05 | 2019-03-27 | 2019-05-06 | 20 |  |  | DF /G /78/DFGA-A-6140 | L3 Deisolation of crane DFGA-A-6140 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100025159 | SMAT:DFGA-A-6140 Replacement of exhaust | L3 Deisolation of crane DFGA-A-6140 |  |  | 6 | 0 | W11 | 2023-04-03 | 2023-04-07 | 2023-04-05 | 2023-04-06 | 2019-03-27 | 2019-05-06 | 25 |  |  | DF /G /78/DFGA-A-6140 | L3 Deisolation of crane DFGA-A-6140 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100025159 | SMAT:DFGA-A-6140 Replacement of exhaust | L3 Deisolation of crane DFGA-A-6140 |  |  | 3 | 0 | W11 | 2023-04-03 | 2023-04-07 | 2023-04-06 | 2023-04-07 | 2019-03-27 | 2019-05-06 | 30 |  |  | DF /G /78/DFGA-A-6140 | L3 Deisolation of crane DFGA-A-6140 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100025159 | SMAT:DFGA-A-6140 Replacement of exhaust | L3 Deisolation of crane DFGA-A-6140 |  |  | 1 | 0 | W11 | 2023-04-03 | 2023-04-07 | 2023-04-07 | 2023-04-07 | 2019-03-27 | 2019-05-06 | 40 |  |  | DF /G /78/DFGA-A-6140 | L3 Deisolation of crane DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400342421 | 1Y EXTINGUISHERS WITHOUT TAG NO, DAN F | CO2 EXTINGUISHERS, 2/5/10/20/45 KG | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-09-11 | 10 | SECE | SECE | DF /C /02/FIRE-FIGHTING-EQUIPMENT | CO2 EXTINGUISHERS, 2/5/10/20/45 KG | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344053 | 1Y SAND JET PUMP SKID MAINT-DFGA-P-5086 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-24 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-09-18 | 10 | SECE | SECE | DF /G /27/DFGA-P-5086 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344053 | 1Y SAND JET PUMP SKID MAINT-DFGA-P-5086 | ISOLATION BY PRODUCTION | SECE | SECE | 7 | 0 | Empty | 2024-08-19 | 2024-08-24 | 2024-08-19 | 2024-08-21 | 2024-08-19 | 2024-09-18 | 20 | SECE | SECE | DF /G /27/DFGA-P-5086 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344053 | 1Y SAND JET PUMP SKID MAINT-DFGA-P-5086 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2024-08-19 | 2024-08-24 | 2024-08-21 | 2024-08-22 | 2024-08-19 | 2024-09-18 | 30 | SECE | SECE | DF /G /27/DFGA-P-5086 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344053 | 1Y SAND JET PUMP SKID MAINT-DFGA-P-5086 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2024-08-19 | 2024-08-24 | 2024-08-22 | 2024-08-24 | 2024-08-19 | 2024-09-18 | 40 | SECE | SECE | DF /G /27/DFGA-P-5086 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344053 | 1Y SAND JET PUMP SKID MAINT-DFGA-P-5086 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-19 | 2024-09-18 | 50 | SECE | SECE | DF /G /27/DFGA-P-5086 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281430 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-10-01 | 2023-10-12 | 20 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281430 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2023-10-01 | 2023-10-12 | 30 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
3 | D-FLARE | WDF | MTN-INST | PRODTECH | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 0.5 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 97 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | D-FLARE | WDF | MTN-INST | MTN-INST | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 0.5 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 98 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | D-FLARE | WDF | MTN-INST | MTN-MECH | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 4 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 103 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | D-FLARE | WDF | MTN-INST | MTN-INST | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 3 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 199 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | D-FLARE | WDF | MTN-INST | MTN-INST | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 1 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 400 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | D-FLARE | WDF | MTN-INST | PRODTECH | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 0.5 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 402 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | D-FLARE | WDF | MTN-INST | MTN-INST | 2100046478 | Leak in transmitter or block and bleed | Restore insulation | AWSC | AWSC | 1 | 0 | BL-TEAM | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-24 | 2021-06-22 | 412 | AWSC | AWSC | DF /A /28/DFAA-PIT-50016 | Restore insulation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106935 | DFF HP-sep sandtrap XCV indication fault | XCV limit switches investigation |  |  | 2 | 12 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-22 | 2024-08-04 | 10 |  |  | DF /F /20/DFFA-XCV-340520 | XCV limit switches investigation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100025582 | SMAT:P-5302 Header tank LIT-52071 defect | P-5302 Header tank LIT-53071 defect |  |  | 16 | 4 | W03-04 | 2019-09-16 | 2023-10-20 | 2019-09-16 | 2023-10-20 | 2019-07-05 | 2019-07-10 | 10 |  |  | DF /C /50/DFCM-LIT-52071 | P-5302 Header tank LIT-53071 defect | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100025582 | SMAT:P-5302 Header tank LIT-52071 defect | P-5302 Header tank LIT-53071 defect |  |  | 0 | 0 | W03-04 | 2019-09-16 | 2023-10-20 | 2021-05-10 | 2023-10-20 | 2019-07-05 | 2019-07-10 | 20 |  |  | DF /C /50/DFCM-LIT-52071 | P-5302 Header tank LIT-53071 defect | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100025582 | SMAT:P-5302 Header tank LIT-52071 defect | P-5302 Header tank LIT-53071 defect |  |  | 0 | 0 | W03-04 | 2019-09-16 | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2019-07-05 | 2019-07-10 | 30 |  |  | DF /C /50/DFCM-LIT-52071 | P-5302 Header tank LIT-53071 defect | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100025582 | SMAT:P-5302 Header tank LIT-52071 defect | P-5302 Header tank LIT-53071 defect |  |  | 3 | 0 | W03-04 | 2019-09-16 | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2019-07-05 | 2019-07-10 | 40 |  |  | DF /C /50/DFCM-LIT-52071 | P-5302 Header tank LIT-53071 defect | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100025582 | SMAT:P-5302 Header tank LIT-52071 defect | P-5302 Header tank LIT-53071 defect |  |  | 1 | 0 | W03-04 | 2019-09-16 | 2023-10-20 | 2023-10-20 | 2023-10-20 | 2019-07-05 | 2019-07-10 | 50 |  |  | DF /C /50/DFCM-LIT-52071 | P-5302 Header tank LIT-53071 defect | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013900 | Ad-hoc assistance for production C2 | Ad-hoc assistance for production C2 | PCNF | PCNF | 0 | 20 | Empty | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-30 | 10 | PCNF | PCNF | DF /F | Ad-hoc assistance for production C2 | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013900 | Ad-hoc assistance for production C2 | Ad-hoc assistance for production C2 | PCNF | PCNF | 0 | 40 | Empty | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-30 | 20 | PCNF | PCNF | DF /F | Ad-hoc assistance for production C2 | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-RIGG | 2200013900 | Ad-hoc assistance for production C2 | Ad-hoc assistance for production C2 | PCNF | PCNF | 50 | 48 | Empty | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-30 | 30 | PCNF | PCNF | DF /F | Ad-hoc assistance for production C2 | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-MECH | 2200013900 | Ad-hoc assistance for production C2 | Ad-hoc assistance for production C2 | PCNF | PCNF | 100 | 86 | Empty | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-30 | 40 | PCNF | PCNF | DF /F | Ad-hoc assistance for production C2 | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013900 | Ad-hoc assistance for production C2 | Ad-hoc assistance for production C2 | PCNF | PCNF | 100 | 41 | Empty | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-30 | 50 | PCNF | PCNF | DF /F | Ad-hoc assistance for production C2 | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-LAGG | 2200013900 | Ad-hoc assistance for production C2 | Ad-hoc assistance for production C2 | PCNF | PCNF | 6 | 6 | Empty | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-03-16 | 2023-04-30 | 60 | PCNF | PCNF | DF /F | Ad-hoc assistance for production C2 | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 2 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2024-08-28 | 2021-01-26 | 2021-03-07 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 8 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2024-08-28 | 2021-01-26 | 2021-03-07 | 20 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 3 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2024-08-28 | 2021-01-26 | 2021-03-07 | 30 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 12 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2024-08-29 | 2021-01-26 | 2021-03-07 | 40 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 6 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-29 | 2024-08-29 | 2021-01-26 | 2021-03-07 | 50 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 6 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2024-08-29 | 2021-01-26 | 2021-03-07 | 60 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 3 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-29 | 2024-08-30 | 2021-01-26 | 2021-03-07 | 70 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 4 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-30 | 2024-08-30 | 2021-01-26 | 2021-03-07 | 80 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 4 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-30 | 2024-08-31 | 2021-01-26 | 2021-03-07 | 90 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044218 | DFFA-HCV-440027-U defective/seized Gearb | Valve removal | AWSCSCH | AWSCSCH | 0 | 0 | W37-38 | 2024-08-28 | 2024-08-31 | 2024-08-28 | 2024-08-28 | 2021-01-26 | 2021-03-07 | 100 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440027-U | Valve removal | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400350905 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-18 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 26 | 0 | Empty | 2024-08-07 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2024-08-07 | 2024-10-08 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-18 | ATEX EQUIPMENT INSPECTION | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100044303 | Stuck open valve on HP hot-recycle loop | Disconnect controls / pneumatic |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-01-17 | 2021-02-06 | 10 |  |  | DF /F /32/DFFA-FCV-440011B | Disconnect controls / pneumatic | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044303 | Stuck open valve on HP hot-recycle loop | Disconnect controls / pneumatic |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-01-17 | 2021-02-06 | 20 |  |  | DF /F /32/DFFA-FCV-440011B | Disconnect controls / pneumatic | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044303 | Stuck open valve on HP hot-recycle loop | Disconnect controls / pneumatic |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-01-17 | 2021-02-06 | 30 |  |  | DF /F /32/DFFA-FCV-440011B | Disconnect controls / pneumatic | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044303 | Stuck open valve on HP hot-recycle loop | Disconnect controls / pneumatic |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-01-17 | 2021-02-06 | 40 |  |  | DF /F /32/DFFA-FCV-440011B | Disconnect controls / pneumatic | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044303 | Stuck open valve on HP hot-recycle loop | Disconnect controls / pneumatic |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-01-17 | 2021-02-06 | 50 |  |  | DF /F /32/DFFA-FCV-440011B | Disconnect controls / pneumatic | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100044303 | Stuck open valve on HP hot-recycle loop | Disconnect controls / pneumatic |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-01-17 | 2021-02-06 | 60 |  |  | DF /F /32/DFFA-FCV-440011B | Disconnect controls / pneumatic | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200016266 | DAF Change certificate on Cisco IP phone | DAF Change certificate on Cisco IP phone |  |  | 5 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-30 | 2023-12-14 | 10 |  |  | DF /C /08 | DAF Change certificate on Cisco IP phone | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 15 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 2 | 22 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 50 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 60 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 70 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 7 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 80 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 90 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100087395 | GD-12702 signal fault. | Cable | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-29 | 2023-09-11 | 100 | PCNFSCHSECE | PCNFSCHSECE | DF /B /03/DFBA-GD-12702 | Cable | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400344034 | 6M PED CRANE CHECK VENDOR-DFCI-X-6101 | PED CRANE CHECK VENDOR-DFCI-X-6101 | AWSC | AWSC | 25 | 0 | Empty | 2024-11-21 | 2024-11-25 | 2024-11-21 | 2024-11-24 | 2024-11-21 | 2024-12-07 | 10 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | PED CRANE CHECK VENDOR-DFCI-X-6101 | Unknown
B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400344034 | 6M PED CRANE CHECK VENDOR-DFCI-X-6101 | PED CRANE CHECK VENDOR-DFCI-X-6101 | AWSC | AWSC | 6 | 0 | Empty | 2024-11-21 | 2024-11-25 | 2024-11-24 | 2024-11-24 | 2024-11-21 | 2024-12-07 | 20 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | PED CRANE CHECK VENDOR-DFCI-X-6101 | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400344034 | 6M PED CRANE CHECK VENDOR-DFCI-X-6101 | PED CRANE CHECK VENDOR-DFCI-X-6101 | AWSC | AWSC | 9 | 0 | Empty | 2024-11-21 | 2024-11-25 | 2024-11-24 | 2024-11-25 | 2024-11-21 | 2024-12-07 | 30 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | PED CRANE CHECK VENDOR-DFCI-X-6101 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 42 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-04 | 2021-01-30 | 2021-09-27 | 10 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-04 | 2025-01-07 | 2021-01-30 | 2021-09-27 | 20 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-07 | 2025-01-08 | 2021-01-30 | 2021-09-27 | 30 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-08 | 2025-01-08 | 2021-01-30 | 2021-09-27 | 40 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-09 | 2025-01-10 | 2021-01-30 | 2021-09-27 | 50 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-11 | 2025-01-12 | 2021-01-30 | 2021-09-27 | 60 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-INST | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-13 | 2025-01-13 | 2021-01-30 | 2021-09-27 | 70 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-14 | 2025-01-14 | 2021-01-30 | 2021-09-27 | 80 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-15 | 2025-01-16 | 2021-01-30 | 2021-09-27 | 90 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-16 | 2025-01-17 | 2021-01-30 | 2021-09-27 | 100 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-17 | 2025-01-17 | 2021-01-30 | 2021-09-27 | 110 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-17 | 2025-01-18 | 2021-01-30 | 2021-09-27 | 120 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100039360 | XCV-33082 intern læk | Prepare Rigging equip. | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-18 | 2025-01-20 | 2021-01-30 | 2021-09-27 | 130 | AWSC | AWSC | DF /C /12/DFCM-XCV-33082 | Prepare Rigging equip. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027440 | Mount new cables DFC | undersøgelser af kabler på DFC | PCNF | PCNF | 100 | 58 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2017-01-01 | 2017-04-01 | 10 | PCNF | PCNF | DF /C /6 | undersøgelser af kabler på DFC | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339041 | DFA_1Y_27050 INT STRUCT INSP - GVI | DFA_1Y_27050 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /86/EL_27050 (MEZZANINE DECK) | DFA_1Y_27050 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400342706 | DFA-12-PHS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 31 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /12/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400316060 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-13 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 39 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2024-03-04 | 2024-05-05 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-13 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018652 | Dishwasher extended wash time issue | Isolate equipment |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-07-11 | 2024-11-23 | 10 |  |  | DF /C /82/DFCC-X-13015 | Isolate equipment | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018652 | Dishwasher extended wash time issue | Isolate equipment |  |  | 1 | 1 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-07-11 | 2024-11-23 | 20 |  |  | DF /C /82/DFCC-X-13015 | Isolate equipment | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018652 | Dishwasher extended wash time issue | Isolate equipment |  |  | 3 | 8 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-07-11 | 2024-11-23 | 30 |  |  | DF /C /82/DFCC-X-13015 | Isolate equipment | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018652 | Dishwasher extended wash time issue | Isolate equipment |  |  | 1 | 1 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-11 | 2024-11-23 | 40 |  |  | DF /C /82/DFCC-X-13015 | Isolate equipment | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018652 | Dishwasher extended wash time issue | Isolate equipment |  |  | 1 | 1 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-11 | 2024-11-23 | 50 |  |  | DF /C /82/DFCC-X-13015 | Isolate equipment | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006535 | DF Design of permanent support | PO Rambøll |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-03-27 | 2021-06-25 | 10 |  |  | DF | PO Rambøll | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200006535 | DF Design of permanent support | PO Rambøll |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-03-27 | 2021-06-25 | 20 |  |  | DF | PO Rambøll | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200006535 | DF Design of permanent support | PO Rambøll |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2021-03-27 | 2021-06-25 | 30 |  |  | DF | PO Rambøll | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235732 | 4Y 380V E-SWB MAINT DFCI-N-1812-L04 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235732 | 4Y 380V E-SWB MAINT DFCI-N-1812-L04 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 4 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235732 | 4Y 380V E-SWB MAINT DFCI-N-1812-L04 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235732 | 4Y 380V E-SWB MAINT DFCI-N-1812-L04 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 0 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 35 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235732 | 4Y 380V E-SWB MAINT DFCI-N-1812-L04 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-03 | 2024-06-03 | 2023-06-03 | 2025-11-19 | 10 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-03 | 2024-06-04 | 2023-06-03 | 2025-11-19 | 20 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 5 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-04 | 2024-06-05 | 2023-06-03 | 2025-11-19 | 30 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 0 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-05 | 2024-06-05 | 2023-06-03 | 2025-11-19 | 40 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-05 | 2024-06-06 | 2023-06-03 | 2025-11-19 | 50 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 5 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-06 | 2024-06-07 | 2023-06-03 | 2025-11-19 | 60 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 4 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-07 | 2024-06-08 | 2023-06-03 | 2025-11-19 | 70 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 0 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-08 | 2024-06-08 | 2023-06-03 | 2025-11-19 | 80 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012639 | PSV - Calibration DFFA-PSV-570039 - PSV | new PSV | PCNFSECE | PCNFSECE | 8 | 4 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-08 | 2024-06-10 | 2023-06-03 | 2025-11-19 | 90 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570039 | new PSV | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235593 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-2 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-29 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-2 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235593 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-2 | ISOLATION ELECTRICAL |  |  | 42 | 0 | Empty | 2024-09-15 | 2024-09-29 | 2024-09-15 | 2024-09-26 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-2 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235593 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-2 | ISOLATION ELECTRICAL |  |  | 14 | 0 | Empty | 2024-09-15 | 2024-09-29 | 2024-09-26 | 2024-09-29 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-2 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235593 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-2 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-2 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284272 | PSV Calibration - DFFA-PSV-410553 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /30/DFFA-PSV-410553 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284272 | PSV Calibration - DFFA-PSV-410553 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /30/DFFA-PSV-410553 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284272 | PSV Calibration - DFFA-PSV-410553 | Prod Assist (breaking containment) | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /30/DFFA-PSV-410553 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284272 | PSV Calibration - DFFA-PSV-410553 | Prod Assist (breaking containment) | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /30/DFFA-PSV-410553 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284272 | PSV Calibration - DFFA-PSV-410553 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /30/DFFA-PSV-410553 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284272 | PSV Calibration - DFFA-PSV-410553 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /30/DFFA-PSV-410553 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322278 | DFF-28-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 296 | 0 | Empty | 2024-10-30 | 2024-12-14 | 2024-10-30 | 2024-12-13 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322255 | DFC-36-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241157 | 1Y WIRELINE OVERRIDE PANEL - DFB | WIRELINE OVERRIDE PANEL - DFB |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-28 | 2023-02-26 | 2023-04-03 | 10 |  |  | DF /B /07 | WIRELINE OVERRIDE PANEL - DFB | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400241157 | 1Y WIRELINE OVERRIDE PANEL - DFB | WIRELINE OVERRIDE PANEL - DFB |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-28 | 2024-08-30 | 2023-02-26 | 2023-04-03 | 20 |  |  | DF /B /07 | WIRELINE OVERRIDE PANEL - DFB | Unknown
3 | DAN-OIL | WRO | VEN-INST | VEN-INST | 2300004184 | Upgrade RTU2004 to AC450 | Upgrade RTU2004 to AC450 |  |  | 48 | 0 | Empty | 2023-02-14 | 2023-02-19 | 2023-02-14 | 2023-02-19 | 2022-11-19 | 2023-04-03 | 10 |  |  | DF /C /04/DFCI-FP-2004 | Upgrade RTU2004 to AC450 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098342 | DFFE/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2023-10-29 | 2024-03-12 | 10 |  |  | DF /F /78/DFFA-MD-6101 | Start up and top up if neccessery | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098342 | DFFE/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2023-10-29 | 2024-03-12 | 20 |  |  | DF /F /78/DFFA-MD-6101 | Start up and top up if neccessery | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100098342 | DFFE/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2023-10-29 | 2024-03-12 | 30 |  |  | DF /F /78/DFFA-MD-6101 | Start up and top up if neccessery | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098342 | DFFE/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2023-10-29 | 2024-03-12 | 40 |  |  | DF /F /78/DFFA-MD-6101 | Start up and top up if neccessery | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322302 | DFG-27-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 39 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235800 | 4Y 380V N-SWB MAINT-DFBA-N-1810-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_13 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235800 | 4Y 380V N-SWB MAINT-DFBA-N-1810-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_13 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235800 | 4Y 380V N-SWB MAINT-DFBA-N-1810-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-02-14 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_13 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235800 | 4Y 380V N-SWB MAINT-DFBA-N-1810-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-02-14 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_13 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 22 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 4 | Empty | 2024-05-19 | 2024-07-30 | 2024-05-20 | 2024-05-20 | 2024-10-12 | 2024-12-31 | 25 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 26 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 27 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284244 | PSV Calibration - DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-05-19 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /51/DFCM-PSV-52230 | DFCM-PSV-52230 Offshore from WS Måde | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009228 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /C /28/DFC-8-DO-050-0556-AA-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009228 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /C /28/DFC-8-DO-050-0556-AA-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009228 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-09 | 2022-02-09 | 2022-07-09 | 25 |  |  | DF /C /28/DFC-8-DO-050-0556-AA-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009228 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-09 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /C /28/DFC-8-DO-050-0556-AA-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009228 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-10 | 2024-01-14 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /C /28/DFC-8-DO-050-0556-AA-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009228 | Insulation assist Bilfinger 20808 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-14 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /C /28/DFC-8-DO-050-0556-AA-U | Bilfinger inspection | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339208 | DFE_1Y_20200 INT STRUCT INSP - GVI | DFE_1Y_20200 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /86/EL_20200 (ACCESS DECK) | DFE_1Y_20200 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WGN | MTN-TELE | VEN-ELEC | 2200015375 | DHG Obsolete DHNC racks | DHG Obsolete DHNC racks new |  |  | 0.5 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-21 | 2026-08-09 | 10 |  |  | DF /E /10/DFEZ-CP-3040 | DHG Obsolete DHNC racks new | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100075992 | DFFE: Replace of bolts and nuts for gang | Change corroded bolts, nuts & washers |  |  | 3 | 0 | Empty | 2023-05-06 | 2023-05-09 | 2023-05-06 | 2023-05-06 | 2022-11-22 | 2023-04-06 | 10 |  |  | DF /F /78/DFFA-A-6101 | Change corroded bolts, nuts & washers | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075992 | DFFE: Replace of bolts and nuts for gang | Change corroded bolts, nuts & washers |  |  | 36 | 0 | Empty | 2023-05-06 | 2023-05-09 | 2023-05-06 | 2023-05-09 | 2022-11-22 | 2023-04-06 | 20 |  |  | DF /F /78/DFFA-A-6101 | Change corroded bolts, nuts & washers | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100075992 | DFFE: Replace of bolts and nuts for gang | Change corroded bolts, nuts & washers |  |  | 8 | 0 | Empty | 2023-05-06 | 2023-05-09 | 2023-05-06 | 2023-05-08 | 2022-11-22 | 2023-04-06 | 30 |  |  | DF /F /78/DFFA-A-6101 | Change corroded bolts, nuts & washers | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346560 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0322 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0322 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346560 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0322 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0322 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346560 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0322 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0322 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346560 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0322 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0322 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346560 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0322 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0322 | ISOLATION BY PRODUCTION | Unknown
2 | NOSD | WDF | MTN-INST | MTN-TELE | 2100114201 | WH PB faulty on DFA-08 MCV | Fault finding on digital output |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-06-08 | 2024-07-23 | 10 |  |  | DF /A /55/DFAA-MCV-30044 | Fault finding on digital output | Unknown
2 | NOSD | WDF | MTN-INST | MTN-TELE | 2100114201 | WH PB faulty on DFA-08 MCV | Fault finding on digital output |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-06-08 | 2024-07-23 | 20 |  |  | DF /A /55/DFAA-MCV-30044 | Fault finding on digital output | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025059 | DFFA-XCV-570133 open drains caisson | L3 isolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2018-03-30 | 2018-06-28 | 10 |  |  | DF /F /70/DFFA-XCV-570133 | L3 isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025059 | DFFA-XCV-570133 open drains caisson | L3 isolate system |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2018-03-30 | 2018-06-28 | 20 |  |  | DF /F /70/DFFA-XCV-570133 | L3 isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025059 | DFFA-XCV-570133 open drains caisson | L3 isolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2018-03-30 | 2018-06-28 | 30 |  |  | DF /F /70/DFFA-XCV-570133 | L3 isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025059 | DFFA-XCV-570133 open drains caisson | L3 isolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2018-03-30 | 2018-06-28 | 40 |  |  | DF /F /70/DFFA-XCV-570133 | L3 isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025059 | DFFA-XCV-570133 open drains caisson | L3 isolate system |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2018-03-30 | 2018-06-28 | 50 |  |  | DF /F /70/DFFA-XCV-570133 | L3 isolate system | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 2 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2024-09-15 | 2024-09-15 | 2021-11-10 | 2022-04-09 | 10 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 2 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2024-09-15 | 2024-09-16 | 2021-11-10 | 2022-04-09 | 20 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 2 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2024-09-15 | 2024-09-16 | 2021-11-10 | 2022-04-09 | 30 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 4 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2024-09-16 | 2024-09-16 | 2021-11-10 | 2022-04-09 | 40 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 4 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2025-01-16 | 2025-01-17 | 2021-11-10 | 2022-04-09 | 50 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 5 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2025-01-17 | 2025-01-18 | 2021-11-10 | 2022-04-09 | 60 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 5 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2025-01-17 | 2025-01-18 | 2021-11-10 | 2022-04-09 | 70 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 2 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2025-01-18 | 2025-01-19 | 2021-11-10 | 2022-04-09 | 80 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053944 | Motor & pump 5038 cannot turn | Rig in overhauled motor and pump |  |  | 0 | 0 | Empty | 2024-09-15 | 2025-01-19 | 2024-09-15 | 2024-09-15 | 2021-11-10 | 2022-04-09 | 90 |  |  | DF /C /27/DFCM-PM-5038 | Rig in overhauled motor and pump | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200005952 | Replace outdated PLC's DFGA-A-1202 & 120 | PO Johnson Controls | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2020-12-30 | 2021-03-30 | 10 | AWSC | AWSC | DF /G /09/DFGA-A-1202 | PO Johnson Controls | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200005952 | Replace outdated PLC's DFGA-A-1202 & 120 | PO Johnson Controls | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2020-12-30 | 2021-03-30 | 20 | AWSC | AWSC | DF /G /09/DFGA-A-1202 | PO Johnson Controls | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200005952 | Replace outdated PLC's DFGA-A-1202 & 120 | PO Johnson Controls | AWSC | AWSC | 24 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2020-12-30 | 2021-03-30 | 30 | AWSC | AWSC | DF /G /09/DFGA-A-1202 | PO Johnson Controls | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200005952 | Replace outdated PLC's DFGA-A-1202 & 120 | PO Johnson Controls | AWSC | AWSC | 12 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-19 | 2020-12-30 | 2021-03-30 | 40 | AWSC | AWSC | DF /G /09/DFGA-A-1202 | PO Johnson Controls | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-HVAC | 2200005952 | Replace outdated PLC's DFGA-A-1202 & 120 | PO Johnson Controls | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2020-12-30 | 2021-03-30 | 50 | AWSC | AWSC | DF /G /09/DFGA-A-1202 | PO Johnson Controls | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200005952 | Replace outdated PLC's DFGA-A-1202 & 120 | PO Johnson Controls | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2020-12-30 | 2021-03-30 | 60 | AWSC | AWSC | DF /G /09/DFGA-A-1202 | PO Johnson Controls | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000962 | ESD SW for ENG469M Polyelectric pumps | ESD SW for ENG469M Polyelectric pumps | AWSC | AWSC | 12 | 0 | IOP date TBC | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 10 | AWSC | AWSC | DF /B /03/DFBA-FP-0208A | ESD SW for ENG469M Polyelectric pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000962 | ESD SW for ENG469M Polyelectric pumps | ESD SW for ENG469M Polyelectric pumps | AWSC | AWSC | 0 | 0 | IOP date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 20 | AWSC | AWSC | DF /B /03/DFBA-FP-0208A | ESD SW for ENG469M Polyelectric pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000962 | ESD SW for ENG469M Polyelectric pumps | ESD SW for ENG469M Polyelectric pumps | AWSC | AWSC | 0 | 0 | IOP date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 30 | AWSC | AWSC | DF /B /03/DFBA-FP-0208A | ESD SW for ENG469M Polyelectric pumps | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-PAIN | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 0 | Empty | 2023-01-02 | 2024-08-09 | 2023-01-02 | 2023-01-02 | 2022-08-09 | 2023-04-06 | 10 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 0 | Empty | 2023-01-02 | 2024-08-09 | 2022-06-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 20 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2022-07-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 30 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 52 | 54 | Empty | 2023-01-02 | 2024-08-09 | 2022-07-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 40 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 216 | 216 | Empty | 2023-01-02 | 2024-08-09 | 2022-07-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 50 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2022-08-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 60 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2022-08-24 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 70 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 36 | 36 | Empty | 2023-01-02 | 2024-08-09 | 2022-08-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 80 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 9 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2022-09-06 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 90 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2022-09-17 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 100 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 10 | Empty | 2023-01-02 | 2024-08-09 | 2022-10-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 110 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2022-10-14 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 120 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-02 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 130 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-03 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 140 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 9 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 150 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-08 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 160 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-17 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 170 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-18 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 180 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 26 | Empty | 2023-01-02 | 2024-08-09 | 2022-11-27 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 190 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 120 | 42 | Empty | 2023-01-02 | 2024-08-09 | 2022-12-10 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 200 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2022-12-16 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 210 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-01-02 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 220 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2023-01-10 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 230 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2023-01-18 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 240 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2023-01-27 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 250 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 20 | Empty | 2023-01-02 | 2024-08-09 | 2023-02-07 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 260 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-02-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 270 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | VEN-MECH | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 24 | 24 | Empty | 2023-01-02 | 2024-08-09 | 2023-02-20 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 280 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-02-26 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 290 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2023-02-26 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 300 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 20 | Empty | 2023-01-02 | 2024-08-09 | 2023-02-26 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 310 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-03-04 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 320 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 16 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2023-03-09 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 330 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-03-13 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 340 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2023-03-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 350 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-03-17 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 360 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-03-25 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 370 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2023-04-01 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 380 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-04-03 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 390 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 40 | 40 | Empty | 2023-01-02 | 2024-08-09 | 2023-04-21 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 400 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2023-05-01 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 410 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 24 | 24 | Empty | 2023-01-02 | 2024-08-09 | 2023-05-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 420 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 37 | 37 | Empty | 2023-01-02 | 2024-08-09 | 2023-05-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 430 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2023-06-01 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 440 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2023-06-07 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 450 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2023-07-16 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 460 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2023-07-19 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 470 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 480 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 9 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-06 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 490 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 21 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-06 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 500 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-09 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 510 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-13 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 520 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 24 | 24 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-17 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 530 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-21 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 540 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 10 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-21 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 550 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 5 | 5 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 560 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 40 | 40 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-24 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 570 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 20 | 38 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-24 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 580 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 72 | 72 | Empty | 2023-01-02 | 2024-08-09 | 2023-08-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 590 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 9 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2023-09-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 600 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-09-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 610 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 16 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2023-09-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 620 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-09-14 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 630 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2023-09-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 640 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-09-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 650 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2023-10-02 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 660 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2023-10-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 670 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-LAGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 24 | 24 | Empty | 2023-01-02 | 2024-08-09 | 2023-10-25 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 680 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 16 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2023-10-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 690 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 20 | 20 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-02 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 700 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 710 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 16 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 720 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 730 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 17 | 17 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 740 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 750 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 760 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 30 | 5 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-16 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 770 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 35 | 14 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-19 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 780 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-20 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 790 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 20 | 20 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-20 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 800 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 10 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-22 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 810 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 21 | 21 | Empty | 2023-01-02 | 2024-08-09 | 2023-11-26 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 820 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 42 | 42 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-11 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 830 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 50 | 50 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 840 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 10 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-16 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 850 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 24 | 24 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-17 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 860 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-24 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 870 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-24 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 880 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-25 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 890 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-27 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 900 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 910 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 920 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 930 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 5 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 940 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 30 | 32 | Empty | 2023-01-02 | 2024-08-09 | 2023-12-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 950 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 7 | 7 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-01 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 960 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 25 | 25 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-01 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 970 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 980 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-05 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 990 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-08 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1000 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-09 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1010 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 48 | 60 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1020 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-14 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1030 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-16 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1040 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-17 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1050 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 32 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-21 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1060 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-21 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1070 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 24 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1080 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 16 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1090 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1100 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 40 | 40 | Empty | 2023-01-02 | 2024-08-09 | 2024-01-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1110 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 22 | 22 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-02 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1120 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-04 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1130 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-LAGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1140 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 16 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-14 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1150 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 14 | 14 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1160 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1170 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1180 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 19 | 19 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1190 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-02-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1200 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-11 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1210 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 25 | 25 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-11 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1220 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 5 | 5 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-14 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1230 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-14 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1240 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 10 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-25 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1250 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 30 | 30 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-26 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1260 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 11 | 11 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-26 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1270 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-27 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1280 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 3 | 3 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1290 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 36 | 36 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-31 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1300 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-03-31 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1310 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-01 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1320 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 10 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-03 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1330 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 40 | 19 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-04 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1340 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 20 | 0 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-15 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1350 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 48 | 38 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-06 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1360 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-06 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1370 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 26 | 26 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-06 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1380 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-10 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1390 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 21 | 21 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-10 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1400 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-11 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1410 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1420 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-LAGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-12 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1430 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 36 | 36 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-20 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1440 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 85 | 85 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-20 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1450 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 31 | 31 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1460 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1470 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1480 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1490 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-28 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1500 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 9 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-29 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1510 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 9 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1520 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1530 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-RIGG | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1540 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1550 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 18 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1560 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1570 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-04-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1580 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-04 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1590 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-07 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1600 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 8 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-08 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1610 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 42 | 42 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-09 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1620 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 7 | 7 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-19 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1630 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 6 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-23 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1640 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 12 | 12 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-30 | 2024-06-01 | 2022-08-09 | 2023-04-06 | 1650 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ELEC | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-31 | 2024-07-22 | 2022-08-09 | 2023-04-06 | 1660 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ELEC | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 2 | 0 | Empty | 2023-01-02 | 2024-08-09 | 2024-05-31 | 2024-07-22 | 2022-08-09 | 2023-04-06 | 1670 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-01 | 2024-06-08 | 2022-08-09 | 2023-04-06 | 1680 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 9 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-08 | 2024-07-22 | 2022-08-09 | 2023-04-06 | 1690 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 6 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-08 | 2024-06-15 | 2022-08-09 | 2023-04-06 | 1700 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-15 | 2024-06-17 | 2022-08-09 | 2023-04-06 | 1710 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 28 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-17 | 2024-06-17 | 2022-08-09 | 2023-04-06 | 1720 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 8 | 5 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-17 | 2024-07-22 | 2022-08-09 | 2023-04-06 | 1730 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 4 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-17 | 2024-06-18 | 2022-08-09 | 2023-04-06 | 1740 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-18 | 2024-06-20 | 2022-08-09 | 2023-04-06 | 1750 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-18 | 2024-06-20 | 2022-08-09 | 2023-04-06 | 1760 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-18 | 2024-06-20 | 2022-08-09 | 2023-04-06 | 1770 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 16 | Empty | 2023-01-02 | 2024-08-09 | 2024-06-20 | 2024-07-10 | 2022-08-09 | 2023-04-06 | 1780 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 18 | Empty | 2023-01-02 | 2024-08-09 | 2024-07-10 | 2024-07-11 | 2022-08-09 | 2023-04-06 | 1790 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-07-11 | 2024-07-15 | 2022-08-09 | 2023-04-06 | 1800 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-PIPF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 2 | Empty | 2023-01-02 | 2024-08-09 | 2024-07-15 | 2024-07-15 | 2022-08-09 | 2023-04-06 | 1810 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 15 | 15 | Empty | 2023-01-02 | 2024-08-09 | 2024-07-15 | 2024-07-22 | 2022-08-09 | 2023-04-06 | 1820 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-SCAF | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 4 | Empty | 2023-01-02 | 2024-08-09 | 2024-07-22 | 2024-08-09 | 2022-08-09 | 2023-04-06 | 1830 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200010507 | ANOC MPM Ad Hoc Work Capture_Dan F | Rig pig DFG | PCNF | PCNF | 0 | 36 | Empty | 2023-01-02 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2022-08-09 | 2023-04-06 | 1840 | PCNF | PCNF | DF /A /86/FABRIC-MAINTENANCE | Rig pig DFG | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400244903 | 1Y HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 | HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-03-29 | 2023-05-15 | 10 |  |  | DF /C /09/DFCC-BM-1255 | HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400244903 | 1Y HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 | HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-03-29 | 2023-05-15 | 20 |  |  | DF /C /09/DFCC-BM-1255 | HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100022701 | CMAT:Exchange 2" HCV & CHK valve Interst | Line for missing Bolts | AWSC | AWSC | 12 | 0 | Empty | 2024-08-01 | 2024-08-06 | 2024-08-01 | 2024-08-02 | 2019-05-16 | 2019-06-05 | 10 | AWSC | AWSC | DF /F /20 | Line for missing Bolts | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022701 | CMAT:Exchange 2" HCV & CHK valve Interst | Line for missing Bolts | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-06 | 2024-08-02 | 2024-08-03 | 2019-05-16 | 2019-06-05 | 20 | AWSC | AWSC | DF /F /20 | Line for missing Bolts | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022701 | CMAT:Exchange 2" HCV & CHK valve Interst | Line for missing Bolts | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-06 | 2024-08-04 | 2024-08-05 | 2019-05-16 | 2019-06-05 | 30 | AWSC | AWSC | DF /F /20 | Line for missing Bolts | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100022701 | CMAT:Exchange 2" HCV & CHK valve Interst | Line for missing Bolts | AWSC | AWSC | 12 | 0 | Empty | 2024-08-01 | 2024-08-06 | 2024-08-05 | 2024-08-06 | 2019-05-16 | 2019-06-05 | 40 | AWSC | AWSC | DF /F /20 | Line for missing Bolts | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022701 | CMAT:Exchange 2" HCV & CHK valve Interst | Line for missing Bolts | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-06 | 2024-08-01 | 2024-08-01 | 2019-05-16 | 2019-06-05 | 50 | AWSC | AWSC | DF /F /20 | Line for missing Bolts | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-06 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 2 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 6 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-06 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 4 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-06 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 10 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 10 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-06 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 20 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-06 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 30 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-07 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 40 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 4 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-07 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 50 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-08 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 60 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 10 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-08 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 70 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2023-02-08 | 2023-07-03 | 2022-11-06 | 2023-03-21 | 80 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 1 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2022-11-06 | 2023-03-21 | 90 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075340 | DFFØ/78 Main wire re-spooling | Isolate-de-isolate | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2022-11-06 | 2023-03-21 | 100 | PCNF | PCNF | DF /F /78/DFFA-A-6101 | Isolate-de-isolate | Unknown
4 | DFE-3551 | WDF | INP-SITE | MTN-SCAF | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 16.100000000000001421085471515 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2023-12-31 | 2024-01-04 | 2019-06-30 | 2019-07-05 | 10 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
4 | DFE-3551 | WDF | INP-SITE | VEN-ELEC | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2024-01-04 | 2024-01-04 | 2019-06-30 | 2019-07-05 | 20 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
4 | DFE-3551 | WDF | INP-SITE | MTN-LAGG | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 4 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2024-01-04 | 2024-01-05 | 2019-06-30 | 2019-07-05 | 30 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
4 | DFE-3551 | WDF | INP-SITE | MTN-PAIN | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 8 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2024-01-05 | 2024-01-06 | 2019-06-30 | 2019-07-05 | 40 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
4 | DFE-3551 | WDF | INP-SITE | MTN-LAGG | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 8 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2024-01-06 | 2024-01-07 | 2019-06-30 | 2019-07-05 | 50 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
4 | DFE-3551 | WDF | INP-SITE | VEN-ELEC | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2024-01-07 | 2024-01-07 | 2019-06-30 | 2019-07-05 | 60 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
4 | DFE-3551 | WDF | INP-SITE | MTN-SCAF | 2100024401 | Leak on oxygen scav spool to DFE WI | Erection of scaffold |  |  | 8 | 0 | Empty | 2023-12-31 | 2024-01-09 | 2024-01-07 | 2024-01-09 | 2019-06-30 | 2019-07-05 | 70 |  |  | DF /A /75/DFA-1-WI-035-4141-AS-U | Erection of scaffold | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400352429 | 3M CRUDE OIL EXP. SKD MAINT-DFCM-A-3660 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3660 |  |  | 1 | 0 | Empty | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-26 | 10 |  |  | DF /C /23/DFCM-A-3660 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3660 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322300 | DFG-36-DOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100067923 | Change out DFFA-PRV-390580 | Isolate PRV |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2022-05-06 | 2022-05-11 | 10 |  |  | DF /F /75/DFFA-PRV-390580 | Isolate PRV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067923 | Change out DFFA-PRV-390580 | Isolate PRV |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2022-05-06 | 2022-05-11 | 20 |  |  | DF /F /75/DFFA-PRV-390580 | Isolate PRV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067923 | Change out DFFA-PRV-390580 | Isolate PRV |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2022-05-06 | 2022-05-11 | 30 |  |  | DF /F /75/DFFA-PRV-390580 | Isolate PRV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067923 | Change out DFFA-PRV-390580 | Isolate PRV |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2022-05-06 | 2022-05-11 | 40 |  |  | DF /F /75/DFFA-PRV-390580 | Isolate PRV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100067923 | Change out DFFA-PRV-390580 | Isolate PRV |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2022-05-06 | 2022-05-11 | 50 |  |  | DF /F /75/DFFA-PRV-390580 | Isolate PRV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048082 | DFFB-A-0334 Repl. 3 pcs. N2 gas cylindre | Rigging assistance |  |  | 3 | 3 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-04-07 | 2021-05-17 | 10 |  |  | DF /F /01/DFFB-A-0334 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048082 | DFFB-A-0334 Repl. 3 pcs. N2 gas cylindre | Rigging assistance |  |  | 10 | 10 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-04-07 | 2021-05-17 | 20 |  |  | DF /F /01/DFFB-A-0334 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100048082 | DFFB-A-0334 Repl. 3 pcs. N2 gas cylindre | Rigging assistance |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-04-07 | 2021-05-17 | 25 |  |  | DF /F /01/DFFB-A-0334 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048082 | DFFB-A-0334 Repl. 3 pcs. N2 gas cylindre | Rigging assistance |  |  | 3 | 3 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2021-04-07 | 2021-05-17 | 30 |  |  | DF /F /01/DFFB-A-0334 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048082 | DFFB-A-0334 Repl. 3 pcs. N2 gas cylindre | Rigging assistance |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 40 |  |  | DF /F /01/DFFB-A-0334 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048082 | DFFB-A-0334 Repl. 3 pcs. N2 gas cylindre | Rigging assistance |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 50 |  |  | DF /F /01/DFFB-A-0334 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 10 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 12 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2021-03-04 | 2023-06-18 | 2021-01-17 | 2021-02-26 | 20 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 20 | 95 | Empty | 2023-11-01 | 2023-11-01 | 2021-03-04 | 2023-06-18 | 2021-01-17 | 2021-02-26 | 30 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 8 | 54 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 40 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 48 | 36 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 50 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 4 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 60 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 8 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 70 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 12 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2021-03-04 | 2023-06-18 | 2021-01-17 | 2021-02-26 | 80 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 90 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 100 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 110 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 120 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 130 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 140 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 150 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 12 | 12 | Empty | 2023-11-01 | 2023-11-01 | 2023-05-07 | 2023-06-18 | 2021-01-17 | 2021-02-26 | 160 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100043885 | DFF P-3601 Mechanical seal rupture | Spares Order |  |  | 12 | 8 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2021-01-17 | 2021-02-26 | 170 |  |  | DF /F /21/DFFA-P-3601 | Spares Order | Unknown
D | NOSD | WPM | MTN-PAIN | MTN-SCAF | 2400346579 | 1Y TRANSPORTABLE LADDERS - DFC | TRANSPORTABLE LADDERS - DFC |  |  | 20 | 0 | Empty | 2024-08-16 | 2024-08-20 | 2024-08-16 | 2024-08-20 | 2024-08-16 | 2024-10-02 | 10 |  |  | DF /C /84 | TRANSPORTABLE LADDERS - DFC | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200003196 | DFE/78: Styrhjul gantry travel | Styrhjul gantry travel |  |  | 24 | 0 | W27-W28 | 2024-07-15 | 2024-07-21 | 2024-07-15 | 2024-07-21 | 2017-07-15 | 2018-07-10 | 10 |  |  | DF /E /78/DFEZ-X-6150 | Styrhjul gantry travel | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 29 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-02 | 2023-01-05 | 2021-01-20 | 2021-01-25 | 10 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 5 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-05 | 2023-01-06 | 2021-01-20 | 2021-01-25 | 20 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 6 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-06 | 2023-01-06 | 2021-01-20 | 2021-01-25 | 30 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 4 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-06 | 2023-01-07 | 2021-01-20 | 2021-01-25 | 40 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 23 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-07 | 2023-01-09 | 2021-01-20 | 2021-01-25 | 50 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 3 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-09 | 2023-01-09 | 2021-01-20 | 2021-01-25 | 60 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 2 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-09 | 2023-01-10 | 2021-01-20 | 2021-01-25 | 70 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 2 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-10 | 2023-01-10 | 2021-01-20 | 2021-01-25 | 80 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 11 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-10 | 2023-01-11 | 2021-01-20 | 2021-01-25 | 90 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 14 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-11 | 2023-01-12 | 2021-01-20 | 2021-01-25 | 100 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 2 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-12 | 2023-01-13 | 2021-01-20 | 2021-01-25 | 110 |  |  | DF /D | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002506 | DAF OCG NPT, 057-01 / TMP368 | Clean-up & housekeeping |  |  | 11 | 0 | Empty | 2023-01-02 | 2023-01-14 | 2023-01-13 | 2023-01-14 | 2021-01-20 | 2021-01-25 | 120 |  |  | DF /D | Clean-up & housekeeping | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076551 | DFAA-A-39230 small leak | Refit fitting with packing tape |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-17 | 2025-07-05 | 10 |  |  | DF /A /75/DFAA-XCV-392304 | Refit fitting with packing tape | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076551 | DFAA-A-39230 small leak | Refit fitting with packing tape |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-17 | 2025-07-05 | 20 |  |  | DF /A /75/DFAA-XCV-392304 | Refit fitting with packing tape | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076551 | DFAA-A-39230 small leak | Refit fitting with packing tape |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-17 | 2025-07-05 | 30 |  |  | DF /A /75/DFAA-XCV-392304 | Refit fitting with packing tape | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076551 | DFAA-A-39230 small leak | Refit fitting with packing tape |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-17 | 2025-07-05 | 40 |  |  | DF /A /75/DFAA-XCV-392304 | Refit fitting with packing tape | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100111615 | MIRQ DFG IPHP Water mist (main bank) | Troubleshooting |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-16 | 2024-09-28 | 10 |  |  | DF /G /01/DFGA-WIT-043328A | Troubleshooting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059081 | DFA-LC-5012 Change Emg. pushbutton | Prove dead | SCH | SCH | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2021-12-18 | 2022-03-18 | 10 | SCH | SCH | DF /A /28/DFAA-P-5012 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059081 | DFA-LC-5012 Change Emg. pushbutton | Prove dead | SCH | SCH | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2021-12-18 | 2022-03-18 | 20 | SCH | SCH | DF /A /28/DFAA-P-5012 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059081 | DFA-LC-5012 Change Emg. pushbutton | Prove dead | SCH | SCH | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2021-12-18 | 2022-03-18 | 30 | SCH | SCH | DF /A /28/DFAA-P-5012 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059081 | DFA-LC-5012 Change Emg. pushbutton | Prove dead | SCH | SCH | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2021-12-18 | 2022-03-18 | 40 | SCH | SCH | DF /A /28/DFAA-P-5012 | Prove dead | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044257 | DFC LEVEL 1 DFC-XCV50401 DEFEKT | Vendor to Troubleshoot on XCV-50401 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50401 | Vendor to Troubleshoot on XCV-50401 | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044257 | DFC LEVEL 1 DFC-XCV50401 DEFEKT | Vendor to Troubleshoot on XCV-50401 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50401 | Vendor to Troubleshoot on XCV-50401 | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 10 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 20 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 24 | 6 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 30 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 5 | 13 | W29-W30 | 2024-07-15 | 2024-07-15 | 2023-05-16 | 2023-07-10 | 2023-06-03 | 2025-11-19 | 40 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 45 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 50 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 60 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 70 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 5 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 80 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 90 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012602 | Repalce DFGA-PSV-440422B - PSV 2023 | Send PSV onshhore for service | PCNF | PCNF | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 100 | PCNF | PCNF | DF /G /32/DFGA-PSV-440422B | Send PSV onshhore for service | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-07 | 2024-06-07 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-07 | 2024-06-08 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 12 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-08 | 2024-06-11 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 8 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-11 | 2024-06-12 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 4 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-12 | 2024-06-13 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-13 | 2024-06-14 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 12 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-14 | 2024-06-15 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-15 | 2024-06-16 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-16 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-17 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-17 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-18 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-18 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-SCAF | 2400284308 | PSV Calibration - DFGA-PSV-440027A | Set up rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 8 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-18 | 2024-06-19 | 2024-10-19 | 2024-12-31 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-440027A | Set up rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047991 | BDV-570013 1" bypass Vlv handle corroded | Return data sheet back to onshore |  |  | 3 | 0 | W27-28 Sece Mech | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2021-04-23 | 2021-07-22 | 10 |  |  | DF /F /70/DFFA-BDV-570012 | Return data sheet back to onshore | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047991 | BDV-570013 1" bypass Vlv handle corroded | Return data sheet back to onshore |  |  | 1 | 0 | W27-28 Sece Mech | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2021-04-23 | 2021-07-22 | 20 |  |  | DF /F /70/DFFA-BDV-570012 | Return data sheet back to onshore | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100100864 | Minox drain/Eq spool demount/leak (INST- | Remove old tubing |  |  | 4 | 0 | Empty | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-03 | 2023-12-02 | 2024-04-15 | 10 |  |  | DF /F /51/DFFB-FT-3551 | Remove old tubing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100100864 | Minox drain/Eq spool demount/leak (INST- | Remove old tubing |  |  | 2 | 0 | Empty | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | 2023-12-02 | 2024-04-15 | 20 |  |  | DF /F /51/DFFB-FT-3551 | Remove old tubing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100100864 | Minox drain/Eq spool demount/leak (INST- | Remove old tubing |  |  | 10 | 0 | Empty | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-03 | 2023-12-02 | 2024-04-15 | 30 |  |  | DF /F /51/DFFB-FT-3551 | Remove old tubing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100100864 | Minox drain/Eq spool demount/leak (INST- | Remove old tubing |  |  | 1.5 | 0 | Empty | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | 2023-12-02 | 2024-04-15 | 40 |  |  | DF /F /51/DFFB-FT-3551 | Remove old tubing | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100100864 | Minox drain/Eq spool demount/leak (INST- | Remove old tubing |  |  | 2 | 0 | Empty | 2024-05-02 | 2024-05-03 | 2024-05-02 | 2024-05-02 | 2023-12-02 | 2024-04-15 | 50 |  |  | DF /F /51/DFFB-FT-3551 | Remove old tubing | Unknown
3 | NOSD | WDF | VEN-INST | MTN-TELE | 2100059136 | Missing communi. Compass server to VM | Observation - Vibration |  |  | 25 | 5 | Empty | 2024-04-24 | 2024-05-08 | 2022-03-28 | 2023-10-20 | 2021-12-18 | 2022-03-18 | 10 |  |  | DF /F /54/DFFA-FP-7201 | Observation - Vibration | Unknown
3 | NOSD | WDF | VEN-INST | MTN-TURB | 2100059136 | Missing communi. Compass server to VM | Observation - Vibration |  |  | 20 | 0 | Empty | 2024-04-24 | 2024-05-08 | 2022-04-07 | 2023-10-20 | 2021-12-18 | 2022-03-18 | 20 |  |  | DF /F /54/DFFA-FP-7201 | Observation - Vibration | Unknown
3 | NOSD | WDF | VEN-INST | VEN-INST | 2100059136 | Missing communi. Compass server to VM | Observation - Vibration |  |  | 20 | 0 | Empty | 2024-04-24 | 2024-05-08 | 2022-04-08 | 2023-10-20 | 2021-12-18 | 2022-03-18 | 30 |  |  | DF /F /54/DFFA-FP-7201 | Observation - Vibration | Unknown
3 | NOSD | WDF | VEN-INST | MTN-TELE | 2100059136 | Missing communi. Compass server to VM | Observation - Vibration |  |  | 20 | 0 | Empty | 2024-04-24 | 2024-05-08 | 2024-04-24 | 2024-04-28 | 2021-12-18 | 2022-03-18 | 40 |  |  | DF /F /54/DFFA-FP-7201 | Observation - Vibration | Unknown
3 | NOSD | WDF | VEN-INST | MTN-TURB | 2100059136 | Missing communi. Compass server to VM | Observation - Vibration |  |  | 25 | 0 | Empty | 2024-04-24 | 2024-05-08 | 2024-04-29 | 2024-05-05 | 2021-12-18 | 2022-03-18 | 50 |  |  | DF /F /54/DFFA-FP-7201 | Observation - Vibration | Unknown
3 | NOSD | WDF | VEN-INST | MTN-INST | 2100059136 | Missing communi. Compass server to VM | Observation - Vibration |  |  | 12.5 | 0 | Empty | 2024-04-24 | 2024-05-08 | 2024-05-05 | 2024-05-08 | 2021-12-18 | 2022-03-18 | 60 |  |  | DF /F /54/DFFA-FP-7201 | Observation - Vibration | Unknown
4 | NE | WDF | MTN-INST | WELLSUPV | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-08-11 | 2024-07-26 | 2024-07-26 | 2021-12-14 | 2022-05-13 | 10 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-INST | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-08-11 | 2024-07-26 | 2024-07-26 | 2021-12-14 | 2022-05-13 | 20 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 36 | 0 | Empty | 2024-07-26 | 2024-08-11 | 2024-07-26 | 2024-07-30 | 2021-12-14 | 2022-05-13 | 30 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-PIPF | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 48 | 28 | Empty | 2024-07-26 | 2024-08-11 | 2024-07-30 | 2024-08-04 | 2021-12-14 | 2022-05-13 | 40 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-ROPE | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 36 | 20 | Empty | 2024-07-26 | 2024-08-11 | 2024-08-04 | 2024-08-07 | 2021-12-14 | 2022-05-13 | 50 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | PRODTECH | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-08-11 | 2024-08-07 | 2024-08-07 | 2021-12-14 | 2022-05-13 | 60 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-PIPF | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 16 | 0 | Empty | 2024-07-26 | 2024-08-11 | 2024-08-07 | 2024-08-09 | 2021-12-14 | 2022-05-13 | 70 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055841 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 18 | 0 | Empty | 2024-07-26 | 2024-08-11 | 2024-08-09 | 2024-08-11 | 2021-12-14 | 2022-05-13 | 80 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0810-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076232 | HCV gear afmonteret | If not please fill in attached sketch so |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-11 | 2025-09-27 | 10 |  |  | DF /F /27/DFFA-XCV-500772 | If not please fill in attached sketch so | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076232 | HCV gear afmonteret | If not please fill in attached sketch so |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-04-11 | 2025-09-27 | 11 |  |  | DF /F /27/DFFA-XCV-500772 | If not please fill in attached sketch so | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076232 | HCV gear afmonteret | If not please fill in attached sketch so |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-11 | 2025-09-27 | 20 |  |  | DF /F /27/DFFA-XCV-500772 | If not please fill in attached sketch so | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100068153 | Replace TT-54185 | Isolate TT-54185 |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2022-06-08 | 2022-09-06 | 10 |  |  | DF /C /07/DFCM-A-5408 | Isolate TT-54185 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100068153 | Replace TT-54185 | Isolate TT-54185 |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2022-06-08 | 2022-09-06 | 20 |  |  | DF /C /07/DFCM-A-5408 | Isolate TT-54185 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100068153 | Replace TT-54185 | Isolate TT-54185 |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2022-06-08 | 2022-09-06 | 30 |  |  | DF /C /07/DFCM-A-5408 | Isolate TT-54185 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098920 | DFG P-5074 external leak in stuffing bo | DFG PM-5074 external leak in stuffing bo |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-11-13 | 2024-03-27 | 10 |  |  | DF /G /28/DFGA-P-5074 | DFG PM-5074 external leak in stuffing bo | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 10 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-01 | 2023-04-03 | 2021-04-21 | 2021-07-20 | 10 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-03 | 2023-04-03 | 2021-04-21 | 2021-07-20 | 20 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 20 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-04 | 2023-04-06 | 2021-04-21 | 2021-07-20 | 30 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 3 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-06 | 2023-04-07 | 2021-04-21 | 2021-07-20 | 40 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 10 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-07 | 2023-04-08 | 2021-04-21 | 2021-07-20 | 50 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 24 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-08 | 2023-04-11 | 2021-04-21 | 2021-07-20 | 60 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 64 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-11 | 2023-04-19 | 2021-04-21 | 2021-07-20 | 70 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 20 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-19 | 2023-04-21 | 2021-04-21 | 2021-07-20 | 80 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-22 | 2023-04-22 | 2021-04-21 | 2021-07-20 | 90 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 10 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-09 | 2023-06-10 | 2021-04-21 | 2021-07-20 | 100 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 64 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-10 | 2023-06-18 | 2021-04-21 | 2021-07-20 | 110 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 10 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-18 | 2023-06-19 | 2021-04-21 | 2021-07-20 | 120 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 10 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-20 | 2023-06-21 | 2021-04-21 | 2021-07-20 | 130 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 24 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-21 | 2023-06-24 | 2021-04-21 | 2021-07-20 | 140 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-24 | 2023-06-24 | 2021-04-21 | 2021-07-20 | 150 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 3 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-24 | 2023-06-25 | 2021-04-21 | 2021-07-20 | 160 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 14 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-06-25 | 2023-06-27 | 2021-04-21 | 2021-07-20 | 170 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100048141 | ANOP DFC-FT-5221 Corr nozzle flange seal | Ordering materials. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-06-27 | 2023-04-01 | 2023-04-01 | 2021-04-21 | 2021-07-20 | 180 |  |  | DF /C /51/DFCM-FT-5221 | Ordering materials. | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077100 | DFGA-PSV-570428A Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2022-11-10 | 2023-03-25 | 10 |  |  | DF /G /70/DFGA-PSV-570428A | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077100 | DFGA-PSV-570428A Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2022-11-10 | 2023-03-25 | 20 |  |  | DF /G /70/DFGA-PSV-570428A | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077100 | DFGA-PSV-570428A Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2022-11-10 | 2023-03-25 | 40 |  |  | DF /G /70/DFGA-PSV-570428A | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077100 | DFGA-PSV-570428A Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2022-11-10 | 2023-03-25 | 50 |  |  | DF /G /70/DFGA-PSV-570428A | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077100 | DFGA-PSV-570428A Misaligned flanges | Isolation of PSV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2022-11-10 | 2023-03-25 | 70 |  |  | DF /G /70/DFGA-PSV-570428A | Isolation of PSV | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 1 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-21 | 2024-06-21 | 2020-08-02 | 2020-12-30 | 10 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 1 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-21 | 2024-06-21 | 2020-08-02 | 2020-12-30 | 20 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-SCAF | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 24 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-21 | 2024-06-24 | 2020-08-02 | 2020-12-30 | 30 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 5 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-24 | 2024-06-25 | 2020-08-02 | 2020-12-30 | 40 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 5 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-24 | 2024-06-25 | 2020-08-02 | 2020-12-30 | 50 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 5 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-25 | 2024-06-26 | 2020-08-02 | 2020-12-30 | 60 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 6 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-27 | 2024-06-28 | 2020-08-02 | 2020-12-30 | 70 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 6 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-28 | 2024-06-29 | 2020-08-02 | 2020-12-30 | 80 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 6 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-30 | 2024-07-01 | 2020-08-02 | 2020-12-30 | 90 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-SCAF | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 20 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-07-01 | 2024-07-03 | 2020-08-02 | 2020-12-30 | 100 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 8 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-07-04 | 2024-07-05 | 2020-08-02 | 2020-12-30 | 110 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 8 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-07-06 | 2024-07-07 | 2020-08-02 | 2020-12-30 | 120 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 1 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2020-08-02 | 2020-12-30 | 130 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 1 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2020-08-02 | 2020-12-30 | 140 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200004178 | DFG/78: Replacement of swing beam in the | Ordre pillow block |  |  | 0 | 0 | Empty | 2024-06-21 | 2024-07-08 | 2024-06-21 | 2024-06-21 | 2020-08-02 | 2020-12-30 | 150 |  |  | DF /G /78/DFGA-A-6140 | Ordre pillow block | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100099374 | ANOCR DFC - Paint SW Stair Tower EL. 41. | Wash down, surface prep and coatings |  |  | 0 | 0 | Empty | 2024-05-15 | 2024-05-30 | 2024-05-15 | 2024-05-15 | 2024-04-03 | 2024-06-30 | 10 |  |  | DF /C /86/41000 - GRATINGS | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100099374 | ANOCR DFC - Paint SW Stair Tower EL. 41. | Wash down, surface prep and coatings |  |  | 12 | 0 | Empty | 2024-05-15 | 2024-05-30 | 2024-05-15 | 2024-05-16 | 2024-04-03 | 2024-06-30 | 15 |  |  | DF /C /86/41000 - GRATINGS | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100099374 | ANOCR DFC - Paint SW Stair Tower EL. 41. | Wash down, surface prep and coatings |  |  | 256 | 0 | Empty | 2024-05-15 | 2024-05-30 | 2024-05-16 | 2024-05-29 | 2024-04-03 | 2024-06-30 | 20 |  |  | DF /C /86/41000 - GRATINGS | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100099374 | ANOCR DFC - Paint SW Stair Tower EL. 41. | Wash down, surface prep and coatings |  |  | 12 | 0 | Empty | 2024-05-15 | 2024-05-30 | 2024-05-29 | 2024-05-30 | 2024-04-03 | 2024-06-30 | 40 |  |  | DF /C /86/41000 - GRATINGS | Wash down, surface prep and coatings | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269336 | 4Y SYS 28 DRAINS PUMPS MAINT-DFF | SYS 28 DRAINS PUMPS MAINT-DFF | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-06-07 | 2023-08-19 | 10 | SECE | SECE | DF /F /28/DFFA-T-5050 | SYS 28 DRAINS PUMPS MAINT-DFF | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400269336 | 4Y SYS 28 DRAINS PUMPS MAINT-DFF | SYS 28 DRAINS PUMPS MAINT-DFF | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-06-07 | 2023-08-19 | 20 | SECE | SECE | DF /F /28/DFFA-T-5050 | SYS 28 DRAINS PUMPS MAINT-DFF | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400269336 | 4Y SYS 28 DRAINS PUMPS MAINT-DFF | SYS 28 DRAINS PUMPS MAINT-DFF | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-06-07 | 2023-08-19 | 30 | SECE | SECE | DF /F /28/DFFA-T-5050 | SYS 28 DRAINS PUMPS MAINT-DFF | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000703 | MEDIC 01.01.18 TIL 31.12.18 | MEDIC 01.01.18 TIL 31.12.18 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2018-12-31 | 2018-12-31 | 10 |  |  | DF /C | MEDIC 01.01.18 TIL 31.12.18 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100074849 | DFB/78: Drain main fuel tank | Drain 10% of fuel tank located at slewbe |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-10-31 | 2023-03-15 | 10 |  |  | DF /B /78/DFBA-X-6102 | Drain 10% of fuel tank located at slewbe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074849 | DFB/78: Drain main fuel tank | Drain 10% of fuel tank located at slewbe |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-01 | 2022-10-31 | 2023-03-15 | 20 |  |  | DF /B /78/DFBA-X-6102 | Drain 10% of fuel tank located at slewbe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074849 | DFB/78: Drain main fuel tank | Drain 10% of fuel tank located at slewbe |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2022-10-31 | 2023-03-15 | 30 |  |  | DF /B /78/DFBA-X-6102 | Drain 10% of fuel tank located at slewbe | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400328734 | 3Y DFFA WATER INJECT - METERING | DFFA WATER INJECT - METERING | AWSC | AWSC | 0.5 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-03-24 | 2024-06-06 | 10 | AWSC | AWSC | DF /F /54/METERING | DFFA WATER INJECT - METERING | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241134 | 3M HYD POWER PACKAGE MAINT - DFFA-A-5901 | HYD POWER PACKAGE MAINT - DFFA-A-5901 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-28 | 2023-04-07 | 10 |  |  | DF /F /07/DFFA-A-5901 | HYD POWER PACKAGE MAINT - DFFA-A-5901 | Unknown
4 | DHDLPGAS | WDF | PRODTECH | MTN-SCAF | 2100026139 | Skift HCV-380326 (*NSD). | Bygning af stillads | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2025-01-01 | 2025-01-10 | 2025-01-01 | 2025-01-03 | 2014-03-31 | 2015-01-25 | 10 | AWSC | AWSC | DF /F /34/DFFA-HCV-380326 | Bygning af stillads | Unknown
4 | DHDLPGAS | WDF | PRODTECH | PRODTECH | 2100026139 | Skift HCV-380326 (*NSD). | Bygning af stillads | AWSC | AWSC | 5 | 0 | Empty | 2025-01-01 | 2025-01-10 | 2025-01-03 | 2025-01-04 | 2014-03-31 | 2015-01-25 | 20 | AWSC | AWSC | DF /F /34/DFFA-HCV-380326 | Bygning af stillads | Unknown
4 | DHDLPGAS | WDF | PRODTECH | VEN-ELEC | 2100026139 | Skift HCV-380326 (*NSD). | Bygning af stillads | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-10 | 2025-01-04 | 2025-01-05 | 2014-03-31 | 2015-01-25 | 30 | AWSC | AWSC | DF /F /34/DFFA-HCV-380326 | Bygning af stillads | Unknown
4 | DHDLPGAS | WDF | PRODTECH | MTN-PIPF | 2100026139 | Skift HCV-380326 (*NSD). | Bygning af stillads | AWSC | AWSC | 16.100000000000001421085471515 | 0 | Empty | 2025-01-01 | 2025-01-10 | 2025-01-05 | 2025-01-06 | 2014-03-31 | 2015-01-25 | 40 | AWSC | AWSC | DF /F /34/DFFA-HCV-380326 | Bygning af stillads | Unknown
4 | DHDLPGAS | WDF | PRODTECH | PRODTECH | 2100026139 | Skift HCV-380326 (*NSD). | Bygning af stillads | AWSC | AWSC | 5 | 0 | Empty | 2025-01-01 | 2025-01-10 | 2025-01-06 | 2025-01-07 | 2014-03-31 | 2015-01-25 | 50 | AWSC | AWSC | DF /F /34/DFFA-HCV-380326 | Bygning af stillads | Unknown
4 | DHDLPGAS | WDF | PRODTECH | MTN-SCAF | 2100026139 | Skift HCV-380326 (*NSD). | Bygning af stillads | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2025-01-01 | 2025-01-10 | 2025-01-07 | 2025-01-10 | 2014-03-31 | 2015-01-25 | 60 | AWSC | AWSC | DF /F /34/DFFA-HCV-380326 | Bygning af stillads | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346556 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346556 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346556 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346556 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346556 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346556 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | AWSCSECE | AWSCSECE | 0 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 50 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0325 | DELUGE SKID, SMOKE TEST-DFCI-X-0325 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058037 | Change Socketoutlet DFCI-WO-1818-4 | Replace SO |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-01-23 | 2022-06-22 | 10 |  |  | DF /C /61/DFCI-N-1802-L07F | Replace SO | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058037 | Change Socketoutlet DFCI-WO-1818-4 | Replace SO |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-01-23 | 2022-06-22 | 20 |  |  | DF /C /61/DFCI-N-1802-L07F | Replace SO | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058037 | Change Socketoutlet DFCI-WO-1818-4 | Replace SO |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-01-23 | 2022-06-22 | 30 |  |  | DF /C /61/DFCI-N-1802-L07F | Replace SO | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 0 | 0 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-08-19 | 10 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 9 | 2 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-06 | 2024-04-07 | 2024-04-06 | 2024-08-19 | 20 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 2 | 0 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-07 | 2024-04-07 | 2024-04-06 | 2024-08-19 | 30 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 9 | 4 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-07 | 2024-04-08 | 2024-04-06 | 2024-08-19 | 40 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 48 | 4 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-08 | 2024-04-12 | 2024-04-06 | 2024-08-19 | 50 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 48 | 12 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-12 | 2024-04-16 | 2024-04-06 | 2024-08-19 | 60 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 9 | 3 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-16 | 2024-04-16 | 2024-04-06 | 2024-08-19 | 70 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 2 | 0 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-16 | 2024-04-17 | 2024-04-06 | 2024-08-19 | 80 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 9 | 2 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 | 2024-04-06 | 2024-08-19 | 90 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100108168 | ANOPR: LOPC - Replace spool | Install rigging equipment | PCNF | PCNF | 6 | 4 | Empty | 2024-04-06 | 2024-04-17 | 2024-04-17 | 2024-04-17 | 2024-04-06 | 2024-08-19 | 100 | PCNF | PCNF | DF /C /82/DFC-3-SS-051-0004-B-U | Install rigging equipment | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241141 | 6M POT WATER TANK/ PUMP MAINT-A-1028/29 | POT WATER TANK/ PUMP MAINT-A-1028/29 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-09 | 2023-03-28 | 10 |  |  | DF /C /85/DFCM-A-1028 | POT WATER TANK/ PUMP MAINT-A-1028/29 | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100071670 | HCV-340065 kan ikke opperes, groet fast. | Rigging assist. Rig in/out |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-09-01 | 2023-01-14 | 10 |  |  | DF /G /32/DFGA-HCV-340065 | Rigging assist. Rig in/out | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100071670 | HCV-340065 kan ikke opperes, groet fast. | Rigging assist. Rig in/out |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2022-09-01 | 2023-01-14 | 20 |  |  | DF /G /32/DFGA-HCV-340065 | Rigging assist. Rig in/out | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100071670 | HCV-340065 kan ikke opperes, groet fast. | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2022-09-01 | 2023-01-14 | 30 |  |  | DF /G /32/DFGA-HCV-340065 | Rigging assist. Rig in/out | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100071670 | HCV-340065 kan ikke opperes, groet fast. | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2022-09-01 | 2023-01-14 | 40 |  |  | DF /G /32/DFGA-HCV-340065 | Rigging assist. Rig in/out | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100071670 | HCV-340065 kan ikke opperes, groet fast. | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2022-09-01 | 2023-01-14 | 50 |  |  | DF /G /32/DFGA-HCV-340065 | Rigging assist. Rig in/out | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235318 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-02-14 | 2023-03-16 | 10 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235318 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-15 | 2023-02-14 | 2023-03-16 | 20 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235318 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2023-02-14 | 2023-03-16 | 30 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235318 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-02-14 | 2023-03-16 | 40 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400329443 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | SCH | SCH | 0 | 0 | W33-W34 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-15 | 2024-06-01 | 2024-06-12 | 1 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-MECH | 2400329443 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | SCH | SCH | 4 | 0 | W33-W34 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2024-06-01 | 2024-06-12 | 10 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-MECH | 2400329443 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | SCH | SCH | 4 | 0 | W33-W34 | 2024-07-15 | 2024-07-17 | 2024-07-16 | 2024-07-17 | 2024-06-01 | 2024-06-12 | 12 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
2 | NOSD | WDF | MTN-INST | PRODTECH | 2100104497 | DFC Promac A-1027 Flowmeter U/S | Process isolation / de-isolation |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-12-31 | 2024-02-14 | 10 |  |  | DF /C /85/DFCM-FE-10284 | Process isolation / de-isolation | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100104497 | DFC Promac A-1027 Flowmeter U/S | Process isolation / de-isolation |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-12-31 | 2024-02-14 | 20 |  |  | DF /C /85/DFCM-FE-10284 | Process isolation / de-isolation | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2019-02-10 | 2019-03-22 | 2 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 3 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 4 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 5 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 4 | 16 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 10 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 16 | 16 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 20 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ELEC | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 8 | 12 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 30 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 24 | 24 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 40 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 36 | 36 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 50 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 3 | 3 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 60 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 3 | 30 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 70 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 75.700000000000002842170943015 | 76 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 80 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 40.20000000000000284217094303 | 56 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 90 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 24 | 39 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 100 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 80.40000000000000568434188606 | 24 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 110 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ELEC | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 20.100000000000001421085471515 | 108 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 120 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 50.29999999999999715782905694 | 3 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 130 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 4 | 10 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 140 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 30 | 59 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-04-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 150 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | WELLSUPV | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 160 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ELEC | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 2 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2022-01-17 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 169 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 80 | 132 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-08-16 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 170 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ELEC | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 2 | 7 | W23-W24 | 2024-06-03 | 2024-10-15 | 2022-01-17 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 172 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 100 | 30 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-10-14 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 180 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 9 | 9 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-10-14 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 190 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | VEN-ELEC | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-10-15 | 2021-11-22 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 200 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 210 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 220 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 230 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ROPE | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 240 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 250 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 260 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 18 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2023-01-02 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 270 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 54 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2023-01-02 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 280 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 36 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2023-01-02 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 290 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 18 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2023-01-02 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 300 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-ELEC | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 310 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 320 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 330 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 340 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 350 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 360 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 370 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 10 | 10 | W23-W24 | 2024-06-03 | 2024-10-15 | 2023-08-28 | 2024-03-24 | 2019-02-10 | 2019-03-22 | 380 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 390 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 400 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100025272 | Pump to be dismantled. DFG. | Additional material order | AWSCSCH | AWSCSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-10-15 | 2024-06-03 | 2024-06-03 | 2019-02-10 | 2019-03-22 | 410 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | Additional material order | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100063809 | Drawer switch defect DFEZ-N-1804-1C03 | Troubleshoot and fix if possible |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-02-27 | 2022-03-19 | 10 |  |  | DF /E /05/DFEZ-N-1804-01C3 | Troubleshoot and fix if possible | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100063809 | Drawer switch defect DFEZ-N-1804-1C03 | Troubleshoot and fix if possible |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-02-27 | 2022-03-19 | 20 |  |  | DF /E /05/DFEZ-N-1804-01C3 | Troubleshoot and fix if possible | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100063809 | Drawer switch defect DFEZ-N-1804-1C03 | Troubleshoot and fix if possible |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-27 | 2022-03-19 | 30 |  |  | DF /E /05/DFEZ-N-1804-01C3 | Troubleshoot and fix if possible | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 12 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-28 | 2024-07-29 | 2021-04-27 | 2021-09-24 | 10 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 1 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2021-04-27 | 2021-09-24 | 20 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 4 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2021-04-27 | 2021-09-24 | 30 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 4 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2021-04-27 | 2021-09-24 | 40 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 1 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2021-04-27 | 2021-09-24 | 50 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 4 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2021-04-27 | 2021-09-24 | 60 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 0 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-28 | 2024-07-28 | 2021-04-27 | 2021-09-24 | 70 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100045353 | Deluge HCV-030042 internal leak | reorder valve and bolts for lugs | AWSC | AWSC | 0 | 0 | Empty | 2024-07-28 | 2024-07-31 | 2024-07-28 | 2024-07-28 | 2021-04-27 | 2021-09-24 | 80 | AWSC | AWSC | DF /A /01/DFAA-HCV-030042 | reorder valve and bolts for lugs | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307836 | 1Y CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | SECE | SECE | 7 | 0 | W19-W20 | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-05-22 | 2024-02-08 | 2024-03-09 | 10 | SECE | SECE | DF /B /01/CO2-SNUFFING-SYSTEM | CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400307836 | 1Y CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | SECE | SECE | 6 | 0 | W19-W20 | 2024-05-20 | 2024-05-23 | 2024-05-22 | 2024-05-23 | 2024-02-08 | 2024-03-09 | 20 | SECE | SECE | DF /B /01/CO2-SNUFFING-SYSTEM | CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | Unknown
4 | DFF-O05 | WDF | MTN-MECH | PRODTECH | 2100023702 | SMAT:DFF 3'th ventil på bullheadline int | L3 Safing of Slot 5 | AWSCSCH | AWSCSCH | 3 | 0 | W37-38 | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-19 | 2018-05-13 | 2018-10-10 | 10 | AWSCSCH | AWSCSCH | DF /F /10 | L3 Safing of Slot 5 | Unknown
4 | DFF-O05 | WDF | MTN-MECH | MTN-SCAF | 2100023702 | SMAT:DFF 3'th ventil på bullheadline int | L3 Safing of Slot 5 | AWSCSCH | AWSCSCH | 17.399999999999998578914528472 | 0 | W37-38 | 2024-09-18 | 2024-09-25 | 2024-09-19 | 2024-09-23 | 2018-05-13 | 2018-10-10 | 15 | AWSCSCH | AWSCSCH | DF /F /10 | L3 Safing of Slot 5 | Unknown
4 | DFF-O05 | WDF | MTN-MECH | MTN-PIPF | 2100023702 | SMAT:DFF 3'th ventil på bullheadline int | L3 Safing of Slot 5 | AWSCSCH | AWSCSCH | 10.099999999999999644728632116 | 0 | W37-38 | 2024-09-18 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2018-05-13 | 2018-10-10 | 20 | AWSCSCH | AWSCSCH | DF /F /10 | L3 Safing of Slot 5 | Unknown
4 | DFF-O05 | WDF | MTN-MECH | PRODTECH | 2100023702 | SMAT:DFF 3'th ventil på bullheadline int | L3 Safing of Slot 5 | AWSCSCH | AWSCSCH | 3 | 0 | W37-38 | 2024-09-18 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2018-05-13 | 2018-10-10 | 30 | AWSCSCH | AWSCSCH | DF /F /10 | L3 Safing of Slot 5 | Unknown
3 | Empty | WRO | MTN-INST | MTN-TELE | 2300007604 | New range and ABB factor for DFB-FT-3503 | New range and ABB factor DFB-FT-35035 |  |  | 1 | 1 | Empty | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-02-23 | 2024-07-07 | 10 |  |  | DF /B /55/DFBA-FT-35035 | New range and ABB factor DFB-FT-35035 | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 2 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 10 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 2 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 20 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | MTN-MECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 5 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 30 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | MTN-MECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 0 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 40 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 2 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 50 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | MTN-MECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 5 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 60 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008954 | Recertify DFAA-PSV-33002 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 4 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 70 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33002 | Install re-certified PSV | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339280 | DFF_1Y_42600 INT STRUCT INSP - GVI | DFF_1Y_42600 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_42600 (ROOF DECK) | DFF_1Y_42600 INT STRUCT INSP - GVI | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094011 | Drain from cooler accomodation HVAC bloc | Drain from cooler accomodation HVAC bloc | SCH | SCH | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-07-01 | 2023-08-15 | 10 | SCH | SCH | DF /C /09/DFCC-A-12532 | Drain from cooler accomodation HVAC bloc | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094011 | Drain from cooler accomodation HVAC bloc | Drain from cooler accomodation HVAC bloc | SCH | SCH | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-07-01 | 2023-08-15 | 20 | SCH | SCH | DF /C /09/DFCC-A-12532 | Drain from cooler accomodation HVAC bloc | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 0 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-03 | 2022-05-03 | 2021-09-10 | 2021-09-15 | 10 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 56 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-03 | 2022-05-09 | 2021-09-10 | 2021-09-15 | 20 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 10 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-09 | 2022-05-10 | 2021-09-10 | 2021-09-15 | 30 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 11 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-10 | 2022-05-11 | 2021-09-10 | 2021-09-15 | 40 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 7 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-11 | 2022-05-12 | 2021-09-10 | 2021-09-15 | 50 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 45 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-12 | 2022-05-16 | 2021-09-10 | 2021-09-15 | 60 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 7 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-16 | 2022-05-17 | 2021-09-10 | 2021-09-15 | 70 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 5 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-17 | 2022-05-18 | 2021-09-10 | 2021-09-15 | 80 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 5 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-18 | 2022-05-18 | 2021-09-10 | 2021-09-15 | 90 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 23 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-18 | 2022-05-21 | 2021-09-10 | 2021-09-15 | 100 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 27 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-21 | 2022-05-23 | 2021-09-10 | 2021-09-15 | 110 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 5 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-23 | 2022-05-24 | 2021-09-10 | 2021-09-15 | 120 |  |  | DF | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003230 | DAF OCG NPT order - RM648S NSA/DFF | Meals & breaks |  |  | 23 | 0 | Empty | 2022-05-03 | 2022-05-26 | 2022-05-24 | 2022-05-26 | 2021-09-10 | 2021-09-15 | 130 |  |  | DF | Meals & breaks | Unknown
4 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001925 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL DFG INSTR SHOP 22.09.2020 | PCNF | PCNF | 0 | 1 | Empty | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2022-01-03 | 10 | PCNF | PCNF | DF /C | MATERIAL DFG INSTR SHOP 22.09.2020 | Unknown
4 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001925 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL DFG INSTR SHOP 22.09.2020 | PCNF | PCNF | 0 | 0 | Empty | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2022-01-03 | 20 | PCNF | PCNF | DF /C | MATERIAL DFG INSTR SHOP 22.09.2020 | Unknown
4 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001925 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL DFG INSTR SHOP 22.09.2020 | PCNF | PCNF | 0 | 0 | Empty | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2022-01-03 | 30 | PCNF | PCNF | DF /C | MATERIAL DFG INSTR SHOP 22.09.2020 | Unknown
4 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001925 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL DFG INSTR SHOP 22.09.2020 | PCNF | PCNF | 0 | 0 | Empty | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2021-03-09 | 2022-01-03 | 40 | PCNF | PCNF | DF /C | MATERIAL DFG INSTR SHOP 22.09.2020 | Unknown
A | DHDLPGAS | WPM | MTN-MECH | PRODTECH | 2400325546 | 1Y ESDV LEAK TEST DFFA-ESDV-380638 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 2 | Empty | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-07-05 | 5 | AWSCSECE | AWSCSECE | DF /F /34/DFFA-ESDV-380638 | ISOLATION BY PRODUCTION | Unknown
A | DHDLPGAS | WPM | MTN-MECH | PRODTECH | 2400325546 | 1Y ESDV LEAK TEST DFFA-ESDV-380638 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 4 | Empty | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-07-05 | 10 | AWSCSECE | AWSCSECE | DF /F /34/DFFA-ESDV-380638 | ISOLATION BY PRODUCTION | Unknown
A | DHDLPGAS | WPM | MTN-MECH | PRODTECH | 2400325546 | 1Y ESDV LEAK TEST DFFA-ESDV-380638 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 1 | Empty | 2024-06-05 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-05 | 2024-07-05 | 20 | AWSCSECE | AWSCSECE | DF /F /34/DFFA-ESDV-380638 | ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400330005 | 1Y NORM EQUIPMENT MAINT - DFC | NORM EQUIPMENT MAINT - DFC |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-05-13 | 2024-06-29 | 10 |  |  | DF /C /84 | NORM EQUIPMENT MAINT - DFC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 20 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-24 | 2021-11-19 | 2022-02-17 | 10 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | PRODTECH | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-25 | 2024-08-25 | 2021-11-19 | 2022-02-17 | 20 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-25 | 2024-08-26 | 2021-11-19 | 2022-02-17 | 30 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 16 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2021-11-19 | 2022-02-17 | 40 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 16 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-26 | 2021-11-19 | 2022-02-17 | 50 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 16 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-28 | 2021-11-19 | 2022-02-17 | 60 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 16 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-27 | 2021-11-19 | 2022-02-17 | 70 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 5 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-28 | 2021-11-19 | 2022-02-17 | 80 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | PRODTECH | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-29 | 2021-11-19 | 2022-02-17 | 90 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | WELLSUPV | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 4 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2021-11-19 | 2022-02-17 | 100 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-22 | 2021-11-19 | 2022-02-17 | 110 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
3 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100057546 | HCV int. leaking LG launch to Dan bravo | PO ISC |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-22 | 2021-11-19 | 2022-02-17 | 120 |  |  | DF /F /34/DFFA-HCV-380114 | PO ISC | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400330010 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-25 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-04-25 | 2024-06-26 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-25 | ATEX EQUIPMENT INSPECTION | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009215 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /B /27/DFB-6-PHS-038-0864-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009215 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-08 | 2024-01-13 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /B /27/DFB-6-PHS-038-0864-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009215 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-14 | 2024-01-14 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /B /27/DFB-6-PHS-038-0864-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009215 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-14 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 35 |  |  | DF /B /27/DFB-6-PHS-038-0864-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009215 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-15 | 2024-01-16 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /B /27/DFB-6-PHS-038-0864-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009215 | Insulation assist bilfinger 20861 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-16 | 2024-01-19 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /B /27/DFB-6-PHS-038-0864-AB-U | Bilfinger inspection | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-20 | 2022-06-03 | 2022-09-01 | 10 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-19 | 2022-06-03 | 2022-09-01 | 20 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-19 | 2022-06-03 | 2022-09-01 | 30 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 14 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-20 | 2024-09-23 | 2022-06-03 | 2022-09-01 | 40 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-23 | 2024-09-25 | 2022-06-03 | 2022-09-01 | 50 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-25 | 2024-09-27 | 2022-06-03 | 2022-09-01 | 60 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2022-06-03 | 2022-09-01 | 70 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067912 | HCV-340006-U internally leaking | Prepare matr/tools |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-28 | 2024-09-30 | 2022-06-03 | 2022-09-01 | 80 |  |  | DF /F /10/DFFA-HCV-340006-U | Prepare matr/tools | Unknown
3 | DFF-1751 | WDF | MTN-MECH | MTN-RIGG | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2020-01-01 | 2020-03-31 | 10 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | DFF-1751 | WDF | MTN-MECH | PRODTECH | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-19 | 2024-09-19 | 2020-01-01 | 2020-03-31 | 20 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | DFF-1751 | WDF | MTN-MECH | MTN-ELEC | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2020-01-01 | 2020-03-31 | 30 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | DFF-1751 | WDF | MTN-MECH | MTN-RIGG | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2020-01-01 | 2020-03-31 | 40 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | DFF-1751 | WDF | MTN-MECH | MTN-ELEC | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2020-01-01 | 2020-03-31 | 50 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | DFF-1751 | WDF | MTN-MECH | PRODTECH | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2020-01-01 | 2020-03-31 | 60 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | DFF-1751 | WDF | MTN-MECH | MTN-RIGG | 2100023333 | Exchange blower motor BM-1751B | Isolate equipment |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2020-01-01 | 2020-03-31 | 70 |  |  | DF /F /76/DFFA-BM-1751B | Isolate equipment | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 73 | 134 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-01 | 2022-04-01 | 2020-07-07 | 2020-08-16 | 10 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 13 | 65 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-01 | 2022-04-01 | 2020-07-07 | 2020-08-16 | 20 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 15 | 0 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-01 | 2022-04-03 | 2020-07-07 | 2020-08-16 | 30 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 10 | 37 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-03 | 2022-04-03 | 2020-07-07 | 2020-08-16 | 40 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 59 | 80 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-03 | 2022-04-03 | 2020-07-07 | 2020-08-16 | 50 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 9 | 78 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-03 | 2022-04-03 | 2020-07-07 | 2020-08-16 | 60 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 6 | 0 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-03 | 2022-04-03 | 2020-07-07 | 2020-08-16 | 70 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 6 | 0 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-03 | 2022-04-04 | 2020-07-07 | 2020-08-16 | 80 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 29 | 35.5 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2020-07-07 | 2020-08-16 | 90 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 35 | 15.5 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2020-07-07 | 2020-08-16 | 100 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 6 | 3.5 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2020-07-07 | 2020-08-16 | 110 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001731 | DAF OCG NPT order - 2700000176/DFRODS1 | Clean-up & housekeeping | PCNF | PCNF | 29 | 41.5 | Empty | 2022-04-01 | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2020-07-07 | 2020-08-16 | 120 | PCNF | PCNF | DF /F | Clean-up & housekeeping | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235713 | 4Y 380V E-SWB MAINT DFFA-N-1812-1A | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1812-1A | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235713 | 4Y 380V E-SWB MAINT DFFA-N-1812-1A | ISOLATION BY PRODUCTION | SCH | SCH | 6 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1812-1A | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235713 | 4Y 380V E-SWB MAINT DFFA-N-1812-1A | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1812-1A | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235713 | 4Y 380V E-SWB MAINT DFFA-N-1812-1A | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1812-1A | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400342425 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-11 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 28 | 0 | Empty | 2024-07-07 | 2024-07-08 | 2024-07-07 | 2024-07-08 | 2024-07-07 | 2024-09-07 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-11 | ATEX EQUIPMENT INSPECTION | Unknown
A | HD-DANLP | WPM | MTN-MECH | MTN-MECH | 2400235299 | 6M ESDV FUNC TEST DFFA-ESDV-380638 | ESDV FUNC TEST DFFA-ESDV-380638 | SECE | SECE | 1 | 0 | Empty | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2023-02-27 | 2023-03-15 | 10 | SECE | SECE | DF /F /34/DFFA-ESDV-380638 | ESDV FUNC TEST DFFA-ESDV-380638 | Unknown
A | HD-DANLP | WPM | MTN-MECH | MTN-INST | 2400235299 | 6M ESDV FUNC TEST DFFA-ESDV-380638 | ESDV FUNC TEST DFFA-ESDV-380638 | SECE | SECE | 1 | 0 | Empty | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2023-02-27 | 2023-03-15 | 20 | SECE | SECE | DF /F /34/DFFA-ESDV-380638 | ESDV FUNC TEST DFFA-ESDV-380638 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259296 | 1Y BUNKER HOSES/REELS MAINT - DAN-F | BUNKER HOSES/REELS MAINT - DAN-F |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-05-11 | 2023-06-16 | 10 |  |  | DF /C /71/DFCI-HOSB-5790 | BUNKER HOSES/REELS MAINT - DAN-F | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259296 | 1Y BUNKER HOSES/REELS MAINT - DAN-F | BUNKER HOSES/REELS MAINT - DAN-F |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-05-11 | 2023-06-16 | 20 |  |  | DF /C /71/DFCI-HOSB-5790 | BUNKER HOSES/REELS MAINT - DAN-F | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-07 | 2024-06-07 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-07 | 2024-06-08 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-08 | 2024-06-11 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 4 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-11 | 2024-06-12 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 4 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-12 | 2024-06-13 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-13 | 2024-06-14 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-14 | 2024-06-15 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-15 | 2024-06-16 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-16 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
A | DFG-IPHP | WPM | MTN-MECH | VEN-INSP | 2400291847 | PSV Exchange - DFGA-PSV-410462 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /30/DFGA-PSV-410462 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024960 | V-5003 Intern læk XCV Sandjeting | L3 Isolate actuator |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2019-03-27 | 2019-06-25 | 10 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024960 | V-5003 Intern læk XCV Sandjeting | L3 Isolate actuator |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2019-03-27 | 2019-06-25 | 20 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024960 | V-5003 Intern læk XCV Sandjeting | L3 Isolate actuator |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2019-03-27 | 2019-06-25 | 30 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024960 | V-5003 Intern læk XCV Sandjeting | L3 Isolate actuator |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2019-03-27 | 2019-06-25 | 40 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024960 | V-5003 Intern læk XCV Sandjeting | L3 Isolate actuator |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2019-03-27 | 2019-06-25 | 50 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024960 | V-5003 Intern læk XCV Sandjeting | L3 Isolate actuator |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2019-03-27 | 2019-06-25 | 60 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate actuator | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298669 | 6M WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-01-12 | 2024-01-28 | 10 |  |  | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235578 | 4Y 380V N-SWB-MAINT DFCC-N-1803-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-06-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235578 | 4Y 380V N-SWB-MAINT DFCC-N-1803-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-06-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235578 | 4Y 380V N-SWB-MAINT DFCC-N-1803-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-06-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235578 | 4Y 380V N-SWB-MAINT DFCC-N-1803-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-06-01 | ISOLATION ELECTRICAL | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100050704 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation | AWSC | AWSC | 2 | 4 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-03 | 2021-09-14 | 2022-05-12 | 10 | AWSC | AWSC | DF /F /55/WATER-INJECTION-MANIFOLD | Prod prepare permit/isolation | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100050704 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation | AWSC | AWSC | 3 | 0 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-04 | 2021-09-14 | 2022-05-12 | 20 | AWSC | AWSC | DF /F /55/WATER-INJECTION-MANIFOLD | Prod prepare permit/isolation | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100050704 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation | AWSC | AWSC | 3 | 4 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-04 | 2024-07-04 | 2021-09-14 | 2022-05-12 | 30 | AWSC | AWSC | DF /F /55/WATER-INJECTION-MANIFOLD | Prod prepare permit/isolation | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100050704 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation | AWSC | AWSC | 2 | 3 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-05 | 2024-07-05 | 2021-09-14 | 2022-05-12 | 40 | AWSC | AWSC | DF /F /55/WATER-INJECTION-MANIFOLD | Prod prepare permit/isolation | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100050704 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation | AWSC | AWSC | 3 | 0 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-05 | 2024-07-06 | 2021-09-14 | 2022-05-12 | 50 | AWSC | AWSC | DF /F /55/WATER-INJECTION-MANIFOLD | Prod prepare permit/isolation | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100050704 | Replace Corroded Valve WI Manifold DFF | Prod prepare permit/isolation | AWSC | AWSC | 1 | 1 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2021-09-14 | 2022-05-12 | 60 | AWSC | AWSC | DF /F /55/WATER-INJECTION-MANIFOLD | Prod prepare permit/isolation | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400235814 | 4Y 3KV N-SWB-MAINT-DFCI-N-1801 | PO SPT | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-29 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801 | PO SPT | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400235814 | 4Y 3KV N-SWB-MAINT-DFCI-N-1801 | PO SPT | AWSC | AWSC | 21 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2022-12-31 | 2023-03-29 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801 | PO SPT | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400235814 | 4Y 3KV N-SWB-MAINT-DFCI-N-1801 | PO SPT | AWSC | AWSC | 5 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801 | PO SPT | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400235814 | 4Y 3KV N-SWB-MAINT-DFCI-N-1801 | PO SPT | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801 | PO SPT | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400235814 | 4Y 3KV N-SWB-MAINT-DFCI-N-1801 | PO SPT | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 50 | AWSC | AWSC | DF /C /61/DFCI-N-1801 | PO SPT | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400235814 | 4Y 3KV N-SWB-MAINT-DFCI-N-1801 | PO SPT | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 60 | AWSC | AWSC | DF /C /61/DFCI-N-1801 | PO SPT | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339031 | DFB_1Y_JACKET ABOVE WATER INSPECTION | DFB_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/JACKET - L.A.T. TO EL 22000 | DFB_1Y_JACKET ABOVE WATER INSPECTION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322288 | DFF-74-GI-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /74/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-04-17 | 2021-07-16 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 70 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-06 | 2021-04-17 | 2021-07-16 | 80 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 90 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 100 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047714 | DFF-HCV-030121 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-04-17 | 2021-07-16 | 110 | AWSC | AWSC | DF /F /01/DFFA-HCV-030121 | Prepare freezing kit on site | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 1 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 30 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 40 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 50 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 1 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 60 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004798 | Replaced by 2300006748 | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2023-08-16 | 2026-02-01 | 70 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309003 | $1Y COOL UNIT DFCC-A-1331 VENDOR | PERSONAL DE-ISOLATION | AWSC | AWSC | 1 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-05 | 2024-10-05 | 2024-02-02 | 2024-03-20 | 10 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | PERSONAL DE-ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309003 | $1Y COOL UNIT DFCC-A-1331 VENDOR | PERSONAL DE-ISOLATION | AWSC | AWSC | 24 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-05 | 2024-10-07 | 2024-02-02 | 2024-03-20 | 20 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | PERSONAL DE-ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400309003 | $1Y COOL UNIT DFCC-A-1331 VENDOR | PERSONAL DE-ISOLATION | AWSC | AWSC | 6 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-07 | 2024-10-09 | 2024-02-02 | 2024-03-20 | 30 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | PERSONAL DE-ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309003 | $1Y COOL UNIT DFCC-A-1331 VENDOR | PERSONAL DE-ISOLATION | AWSC | AWSC | 1 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-02-02 | 2024-03-20 | 40 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | PERSONAL DE-ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309003 | $1Y COOL UNIT DFCC-A-1331 VENDOR | PERSONAL DE-ISOLATION | AWSC | AWSC | 1 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-02-02 | 2024-03-20 | 50 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | PERSONAL DE-ISOLATION | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100085041 | DFFW/78 DFFA-A-6102 Vest kran V08 Print | Replace V08 | SCH | SCH | 2 | 2 | W25-26 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-02-08 | 2023-03-25 | 10 | SCH | SCH | DF /F /78/DFFA-A-6102 | Replace V08 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100085041 | DFFW/78 DFFA-A-6102 Vest kran V08 Print | Replace V08 | SCH | SCH | 4 | 14 | W25-26 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-02-08 | 2023-03-25 | 20 | SCH | SCH | DF /F /78/DFFA-A-6102 | Replace V08 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085041 | DFFW/78 DFFA-A-6102 Vest kran V08 Print | Replace V08 | SCH | SCH | 2 | 0 | W25-26 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-02-08 | 2023-03-25 | 30 | SCH | SCH | DF /F /78/DFFA-A-6102 | Replace V08 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085041 | DFFW/78 DFFA-A-6102 Vest kran V08 Print | Replace V08 | SCH | SCH | 0 | 0 | W25-26 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-02-08 | 2023-03-25 | 40 | SCH | SCH | DF /F /78/DFFA-A-6102 | Replace V08 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085041 | DFFW/78 DFFA-A-6102 Vest kran V08 Print | Replace V08 | SCH | SCH | 0 | 0 | W25-26 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-06-22 | 2023-02-08 | 2023-03-25 | 50 | SCH | SCH | DF /F /78/DFFA-A-6102 | Replace V08 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339098 | DFC_1Y_54200 INT STRUCT INSP - GVI | DFC_1Y_54200 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_54200 (ACCOMMODATION L2) | DFC_1Y_54200 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325775 | 6M BOOSTER PUMP MAINT DFGA-P-3547/48 | BOOSTER PUMP MAINT DFGA-P-3547/48 |  |  | 4 | 0 | W17-W18 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2024-05-29 | 10 |  |  | DF /G /54/DFGA-P-3547 | BOOSTER PUMP MAINT DFGA-P-3547/48 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077772 | DFC LB2 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-09 | 2025-10-25 | 10 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077772 | DFC LB2 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 20 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077772 | DFC LB2 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 30 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077772 | DFC LB2 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 35 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100077772 | DFC LB2 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 40 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat in maintenance wires | Unknown
A | DFF-3580 | WPM | MTN-TURB | MTN-TURB | 2400336979 | 2.5KH TURBINE WASH DFFB-A-3580 COUNTER | TURBINE WASH DFFB-A-3580 COUNTER | AWSCSECE | AWSCSECE | 12 | 12 | W27-W28 | 2024-07-16 | 2024-07-19 | 2024-07-16 | 2024-07-19 | 2024-07-26 | 2024-08-11 | 10 | AWSCSECE | AWSCSECE | DF /F /54/DFFB-A-3580 | TURBINE WASH DFFB-A-3580 COUNTER | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088892 | Pressure regulating valve out of order | Replace hydrant | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-05-16 | 2023-09-28 | 10 | SECE | SECE | DF /C /01/DFCC-X-0369 | Replace hydrant | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088892 | Pressure regulating valve out of order | Replace hydrant | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-05-16 | 2023-09-28 | 20 | SECE | SECE | DF /C /01/DFCC-X-0369 | Replace hydrant | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088892 | Pressure regulating valve out of order | Replace hydrant | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-16 | 2023-09-28 | 30 | SECE | SECE | DF /C /01/DFCC-X-0369 | Replace hydrant | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100112700 | DHG metering issues DFA23 DFB21 | Replace DHNC cards |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2024-06-30 | 2024-11-12 | 10 |  |  | DF /E /10/DFEZ-CP-3040 | Replace DHNC cards | Unknown
3 | NOSD | WDF | MTN-TELE | VEN-INST | 2100112700 | DHG metering issues DFA23 DFB21 | Replace DHNC cards |  |  | 4 | 0 | Empty | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-06-30 | 2024-11-12 | 20 |  |  | DF /E /10/DFEZ-CP-3040 | Replace DHNC cards | Unknown
2 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100101522 | func. and Inflow test Kraka XCV | Inflow test DF /A /12/DFAA-XCV-38210 | AWSC | AWSC | 3 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2023-12-22 | 2024-05-05 | 10 | AWSC | AWSC | DF /A /12/DFAA-XCV-38210 | Inflow test DF /A /12/DFAA-XCV-38210 | Unknown
2 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100101522 | func. and Inflow test Kraka XCV | Inflow test DF /A /12/DFAA-XCV-38210 | AWSC | AWSC | 3 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-27 | 2023-12-22 | 2024-05-05 | 20 | AWSC | AWSC | DF /A /12/DFAA-XCV-38210 | Inflow test DF /A /12/DFAA-XCV-38210 | Unknown
2 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100101522 | func. and Inflow test Kraka XCV | Inflow test DF /A /12/DFAA-XCV-38210 | AWSC | AWSC | 3 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2023-12-22 | 2024-05-05 | 30 | AWSC | AWSC | DF /A /12/DFAA-XCV-38210 | Inflow test DF /A /12/DFAA-XCV-38210 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060722 | Filter S-3906 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-01-21 | 2022-04-21 | 10 |  |  | DF /F /75/DFFA-S-3906 | Isolation of system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100060722 | Filter S-3906 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-01-21 | 2022-04-21 | 20 |  |  | DF /F /75/DFFA-S-3906 | Isolation of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060722 | Filter S-3906 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-01-21 | 2022-04-21 | 30 |  |  | DF /F /75/DFFA-S-3906 | Isolation of system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100060722 | Filter S-3906 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-01-21 | 2022-04-21 | 40 |  |  | DF /F /75/DFFA-S-3906 | Isolation of system | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100025234 | ANOCR Clean and paint CD on DFG glycol | Set up equipment |  |  | 0 | 0 | Empty | 2023-04-03 | 2023-04-19 | 2023-04-03 | 2023-04-03 | 2019-05-20 | 2019-10-17 | 10 |  |  | DF /G /30/DFGA-A-4140 | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100025234 | ANOCR Clean and paint CD on DFG glycol | Set up equipment |  |  | 12 | 0 | Empty | 2023-04-03 | 2023-04-19 | 2023-04-03 | 2023-04-04 | 2019-05-20 | 2019-10-17 | 20 |  |  | DF /G /30/DFGA-A-4140 | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100025234 | ANOCR Clean and paint CD on DFG glycol | Set up equipment |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-19 | 2023-04-04 | 2023-04-04 | 2019-05-20 | 2019-10-17 | 30 |  |  | DF /G /30/DFGA-A-4140 | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100025234 | ANOCR Clean and paint CD on DFG glycol | Set up equipment |  |  | 160 | 0 | Empty | 2023-04-03 | 2023-04-19 | 2023-04-05 | 2023-04-18 | 2019-05-20 | 2019-10-17 | 40 |  |  | DF /G /30/DFGA-A-4140 | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100025234 | ANOCR Clean and paint CD on DFG glycol | Set up equipment |  |  | 12 | 0 | Empty | 2023-04-03 | 2023-04-19 | 2023-04-18 | 2023-04-19 | 2019-05-20 | 2019-10-17 | 50 |  |  | DF /G /30/DFGA-A-4140 | Set up equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104300 | DFFA-P-3510 gets S/D on vibrations | Isolation & safing of DFFA-P-3510 |  |  | 2 | 0 | W17-W18 | 2024-05-01 | 2024-05-06 | 2024-05-01 | 2024-05-02 | 2024-02-10 | 2024-06-24 | 10 |  |  | DF /F /54/DFFA-P-3510 | Isolation & safing of DFFA-P-3510 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-TURB | 2100104300 | DFFA-P-3510 gets S/D on vibrations | Isolation & safing of DFFA-P-3510 |  |  | 8 | 10 | W17-W18 | 2024-05-01 | 2024-05-06 | 2024-05-02 | 2024-05-04 | 2024-02-10 | 2024-06-24 | 20 |  |  | DF /F /54/DFFA-P-3510 | Isolation & safing of DFFA-P-3510 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-TELE | 2100104300 | DFFA-P-3510 gets S/D on vibrations | Isolation & safing of DFFA-P-3510 |  |  | 6 | 0 | W17-W18 | 2024-05-01 | 2024-05-06 | 2024-05-04 | 2024-05-05 | 2024-02-10 | 2024-06-24 | 30 |  |  | DF /F /54/DFFA-P-3510 | Isolation & safing of DFFA-P-3510 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104300 | DFFA-P-3510 gets S/D on vibrations | Isolation & safing of DFFA-P-3510 |  |  | 2 | 0 | W17-W18 | 2024-05-01 | 2024-05-06 | 2024-05-05 | 2024-05-06 | 2024-02-10 | 2024-06-24 | 40 |  |  | DF /F /54/DFFA-P-3510 | Isolation & safing of DFFA-P-3510 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084631 | DFG PBS-3952 Emg. Push botton stop fault | Isolate and prove dead |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-18 | 2023-07-31 | 10 |  |  | DF /G /75/DFGA-PM-3952 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084631 | DFG PBS-3952 Emg. Push botton stop fault | Isolate and prove dead |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-18 | 2023-07-31 | 20 |  |  | DF /G /75/DFGA-PM-3952 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084631 | DFG PBS-3952 Emg. Push botton stop fault | Isolate and prove dead |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-18 | 2023-07-31 | 30 |  |  | DF /G /75/DFGA-PM-3952 | Isolate and prove dead | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235645 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L07A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235645 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L07 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L07A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235645 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L07 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L07A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235645 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L07A | ISOLATION ELECTRICAL | Unknown
3 | DFF-O30 | WDF | MTN-MECH | MTN-MECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-17 | 2023-07-30 | 10 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
3 | DFF-O30 | WDF | MTN-MECH | PRODTECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-17 | 2023-07-30 | 11 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
3 | DFF-O30 | WDF | MTN-MECH | MTN-MECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-17 | 2023-07-30 | 20 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
3 | DFF-O30 | WDF | MTN-MECH | MTN-MECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-03-17 | 2023-07-30 | 30 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
3 | DFF-O30 | WDF | MTN-MECH | MTN-MECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-03-17 | 2023-07-30 | 40 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
3 | DFF-O30 | WDF | MTN-MECH | PRODTECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-17 | 2023-07-30 | 41 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
3 | DFF-O30 | WDF | MTN-MECH | MTN-MECH | 2100082299 | DFF30 LG FCV internal LEak | De-Isolate FCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-17 | 2023-07-30 | 50 |  |  | DF /F /37/DFFA-FCV-290130 | De-Isolate FCV | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088912 | Repair of floodlighting DFB | Repair of floodlighting DFB |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-10-07 | 2026-03-25 | 10 |  |  | DF /B /61/DFBA-N-1810-C_48 | Repair of floodlighting DFB | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100088912 | Repair of floodlighting DFB | Repair of floodlighting DFB |  |  | 18 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2023-10-07 | 2026-03-25 | 20 |  |  | DF /B /61/DFBA-N-1810-C_48 | Repair of floodlighting DFB | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088912 | Repair of floodlighting DFB | Repair of floodlighting DFB |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-10-07 | 2026-03-25 | 30 |  |  | DF /B /61/DFBA-N-1810-C_48 | Repair of floodlighting DFB | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009248 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-01-08 | 2022-02-13 | 2022-07-13 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7311-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009248 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 96 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-01-13 | 2022-02-13 | 2022-07-13 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7311-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009248 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-14 | 2024-01-16 | 2022-02-13 | 2022-07-13 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7311-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009248 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-16 | 2024-01-17 | 2022-02-13 | 2022-07-13 | 33 |  |  | DF /F /55/DFF-6-PHS-030-7311-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009248 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-17 | 2024-01-22 | 2022-02-13 | 2022-07-13 | 40 |  |  | DF /F /55/DFF-6-PHS-030-7311-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009248 | Insulation assist bilfinger 21528 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-22 | 2024-01-25 | 2022-02-13 | 2022-07-13 | 50 |  |  | DF /F /55/DFF-6-PHS-030-7311-GF-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101808 | DFF-20 PT-300920 fail reading in ccr. | Troubleshoot barrier replace if required |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-26 | 2024-05-09 | 10 |  |  | DF /F /10/DFFA-PIT-300920 | Troubleshoot barrier replace if required | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400302681 | 4Y SW FILT FEED PUMP MAINT P-3511/12/13 | SW FILT FEED PUMP MAINT P-3511/12/13 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-12-04 | 2024-02-15 | 10 | SECE | SECE | DF /C /54/DFCM-P-3511 | SW FILT FEED PUMP MAINT P-3511/12/13 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400302681 | 4Y SW FILT FEED PUMP MAINT P-3511/12/13 | SW FILT FEED PUMP MAINT P-3511/12/13 | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2023-12-04 | 2024-02-15 | 20 | SECE | SECE | DF /C /54/DFCM-P-3511 | SW FILT FEED PUMP MAINT P-3511/12/13 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302681 | 4Y SW FILT FEED PUMP MAINT P-3511/12/13 | SW FILT FEED PUMP MAINT P-3511/12/13 | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2023-12-04 | 2024-02-15 | 30 | SECE | SECE | DF /C /54/DFCM-P-3511 | SW FILT FEED PUMP MAINT P-3511/12/13 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400302681 | 4Y SW FILT FEED PUMP MAINT P-3511/12/13 | SW FILT FEED PUMP MAINT P-3511/12/13 | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2023-12-04 | 2024-02-15 | 40 | SECE | SECE | DF /C /54/DFCM-P-3511 | SW FILT FEED PUMP MAINT P-3511/12/13 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400302681 | 4Y SW FILT FEED PUMP MAINT P-3511/12/13 | SW FILT FEED PUMP MAINT P-3511/12/13 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-12-04 | 2024-02-15 | 50 | SECE | SECE | DF /C /54/DFCM-P-3511 | SW FILT FEED PUMP MAINT P-3511/12/13 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235635 | 4Y 380V N-SWB MAINT-DFFA-N-1803-4 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803-04 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235635 | 4Y 380V N-SWB MAINT-DFFA-N-1803-4 | ISOLATION ELECTRICAL | AWSC | AWSC | 23 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803-04 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235635 | 4Y 380V N-SWB MAINT-DFFA-N-1803-4 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-29 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803-04 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235635 | 4Y 380V N-SWB MAINT-DFFA-N-1803-4 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803-04 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200003177 | SMAT:Flow indikator def-Finding PPM- ch | Flow indikator def. - Finding PPM-check |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2016-08-22 | 2016-11-20 | 10 |  |  | DF /F /70/DFFA-HCV-570076 | Flow indikator def. - Finding PPM-check | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235636 | 4Y 380V N-SWB MAINT-DFFA-N-1803-5 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803-05 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235636 | 4Y 380V N-SWB MAINT-DFFA-N-1803-5 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 14 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803-05 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235636 | 4Y 380V N-SWB MAINT-DFFA-N-1803-5 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-26 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803-05 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235636 | 4Y 380V N-SWB MAINT-DFFA-N-1803-5 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803-05 | DE-ISOLATION ELECTRICAL | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009216 | Insulation assist Bilfinger 20860 | REMOVE INSULATION |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /B /27/DFB-6-WOS-050-4135-AD-F | REMOVE INSULATION | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009216 | Insulation assist Bilfinger 20860 | REMOVE INSULATION |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /B /27/DFB-6-WOS-050-4135-AD-F | REMOVE INSULATION | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009216 | Insulation assist Bilfinger 20860 | REMOVE INSULATION |  |  | 18 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-10 | 2024-01-11 | 2022-02-09 | 2022-07-09 | 25 |  |  | DF /B /27/DFB-6-WOS-050-4135-AD-F | REMOVE INSULATION | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009216 | Insulation assist Bilfinger 20860 | REMOVE INSULATION |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-11 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /B /27/DFB-6-WOS-050-4135-AD-F | REMOVE INSULATION | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 3 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-02-02 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 4 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-02-02 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 5 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-02-02 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 6 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 7 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 24 | Empty | 2022-03-20 | 2023-05-12 | 2022-02-01 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 8 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 9 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 10 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2022-05-23 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 11 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 112 | 153 | Empty | 2022-03-20 | 2023-05-12 | 2020-09-24 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 13 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 3 | Empty | 2022-03-20 | 2023-05-12 | 2020-10-20 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 14 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 35 | 131 | Empty | 2022-03-20 | 2023-05-12 | 2020-08-13 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 15 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 58 | 37 | Empty | 2022-03-20 | 2023-05-12 | 2020-09-29 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 20 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 12 | 12 | Empty | 2022-03-20 | 2023-05-12 | 2020-10-14 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 21 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 62 | 57 | Empty | 2022-03-20 | 2023-05-12 | 2020-09-29 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 30 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 24 | Empty | 2022-03-20 | 2023-05-12 | 2020-08-14 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 31 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 36 | 39 | Empty | 2022-03-20 | 2023-05-12 | 2020-10-25 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 32 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-02-02 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 33 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-02-02 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 34 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-02-02 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 35 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 36 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROUS | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 37 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 4 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-14 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 45 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 5 | Empty | 2022-03-20 | 2023-05-12 | 2022-06-07 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 47 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 12 | 12 | Empty | 2022-03-20 | 2023-05-12 | 2022-06-07 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 48 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 4 | Empty | 2022-03-20 | 2023-05-12 | 2022-06-07 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 49 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 60 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 50 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROUS | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 6 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 60 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 6 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 70 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 80 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 36 | 43 | Empty | 2022-03-20 | 2023-05-12 | 2021-03-18 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 90 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 16 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-21 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 100 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 36 | 43 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-21 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 110 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 16 | 14 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-21 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 120 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 12 | 14 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-21 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 130 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 10 | 30 | Empty | 2022-03-20 | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 140 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 20 | 30 | Empty | 2022-03-20 | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 150 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-ELEC | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 8 | 4 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-14 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 155 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 160 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 170 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 6 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-05-12 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 180 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 30 | 30 | Empty | 2022-03-20 | 2023-05-12 | 2022-03-21 | 2023-05-12 | 2019-12-21 | 2020-03-20 | 190 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 200 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 205 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 215 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 300 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 310 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 320 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100025009 | Pump and motor onshore for repair. New r | operation_description_not_present | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2022-03-20 | 2023-05-12 | 2023-04-26 | 2023-04-26 | 2019-12-21 | 2020-03-20 | 330 | AWSCSCH | AWSCSCH | DF /F /54/DFFA-PM-3510 | operation_description_not_present | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2021-05-06 | 2021-08-04 | 10 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2021-05-06 | 2021-08-04 | 20 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 1 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2021-05-06 | 2021-08-04 | 30 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2021-05-06 | 2021-08-04 | 40 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2021-05-06 | 2021-08-04 | 50 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2021-05-06 | 2021-08-04 | 60 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2021-05-06 | 2021-08-04 | 70 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100048512 | DFB-1"HCV system 35 WI ext. leak | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2021-05-06 | 2021-08-04 | 80 |  |  | DF /B /55/DFBA-ESDV-35790 | Build Scaffold | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235820 | 4Y 380V E-SWB MAINT DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235820 | 4Y 380V E-SWB MAINT DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | SCH | SCH | 6 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235820 | 4Y 380V E-SWB MAINT DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | SCH | SCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235820 | 4Y 380V E-SWB MAINT DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1812-01 | 380V E-SWB MAINT DFFA-N-1812-01 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235695 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR08-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235695 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR08 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR08-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235695 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR08 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR08-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235695 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR08-DA001 | ISOLATION ELECTRICAL | Unknown
2 | Empty | WDF | MTN-ELEC | MTN-TELE | 2100112051 | DFC P-0304 fail on trip spool drawer | Full AUS isolation | SECE | SECE | 6 | 6 | Empty | 2024-06-16 | 2024-06-16 | 2024-05-09 | 2024-05-09 | 2024-06-16 | 2024-10-29 | 10 | SECE | SECE | DF /C /01/DFCM-P-0304 | Full AUS isolation | Unknown
2 | Empty | WDF | MTN-ELEC | MTN-TELE | 2100112051 | DFC P-0304 fail on trip spool drawer | Full AUS isolation | SECE | SECE | 12 | 16 | Empty | 2024-06-16 | 2024-06-16 | 2024-05-09 | 2024-05-09 | 2024-06-16 | 2024-10-29 | 20 | SECE | SECE | DF /C /01/DFCM-P-0304 | Full AUS isolation | Unknown
2 | Empty | WDF | MTN-ELEC | MTN-ELEC | 2100112051 | DFC P-0304 fail on trip spool drawer | Full AUS isolation | SECE | SECE | 0 | 0 | Empty | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2024-10-29 | 30 | SECE | SECE | DF /C /01/DFCM-P-0304 | Full AUS isolation | Unknown
2 | Empty | WDF | MTN-ELEC | MTN-ELEC | 2100112051 | DFC P-0304 fail on trip spool drawer | Full AUS isolation | SECE | SECE | 0 | 0 | Empty | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2024-10-29 | 40 | SECE | SECE | DF /C /01/DFCM-P-0304 | Full AUS isolation | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235594 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-5 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-5-9 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235594 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-5 | ISOLATION ELECTRICAL |  |  | 7 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-5-9 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235594 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-5 | ISOLATION ELECTRICAL |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-5-9 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235594 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-5 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-5-9 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-23 | 2019-01-27 | 2019-02-16 | 10 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-23 | 2019-01-27 | 2019-02-16 | 20 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-24 | 2024-09-25 | 2019-01-27 | 2019-02-16 | 30 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-25 | 2024-09-26 | 2019-01-27 | 2019-02-16 | 40 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-26 | 2024-09-26 | 2019-01-27 | 2019-02-16 | 50 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2019-01-27 | 2019-02-16 | 60 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-28 | 2024-09-28 | 2019-01-27 | 2019-02-16 | 70 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2019-01-27 | 2019-02-16 | 80 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025335 | Exchange actuator & positioner. | L3 Prepare lifting equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2019-01-27 | 2019-02-16 | 90 | AWSC | AWSC | DF /G /50/DFGA-FCV-530530 | L3 Prepare lifting equipment | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 10 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 20 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-TURB | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 5 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 30 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 40 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 50 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 60 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-TURB | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 96 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 70 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 80 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 90 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 100 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 30 | 18 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 110 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 120 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 130 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 20 | 27 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 140 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 10 | 15 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 150 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 52 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 160 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 170 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ROPE | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 10 | 10 | Empty | 2024-09-16 | 2024-09-16 | 2024-04-15 | 2024-04-15 | 2023-05-01 | 2023-09-13 | 180 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100087404 | $P-3520 Pump Axial Float | Increase of PO 4300048068 | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-05-01 | 2023-09-13 | 190 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-P-3520 | Increase of PO 4300048068 | Unknown
D | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400241705 | 1Y SW STRAINER PKG MAINT-DFFA-A-5310 | SEAWAT STRAINER PKG MAINT-DFFA-A-5310 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-01 | 2023-04-17 | 10 |  |  | DF /F /51/DFFA-A-5310 | SEAWAT STRAINER PKG MAINT-DFFA-A-5310 | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241705 | 1Y SW STRAINER PKG MAINT-DFFA-A-5310 | SEAWAT STRAINER PKG MAINT-DFFA-A-5310 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-01 | 2023-04-17 | 20 |  |  | DF /F /51/DFFA-A-5310 | SEAWAT STRAINER PKG MAINT-DFFA-A-5310 | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-22 | 2021-04-25 | 2021-07-24 | 10 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-23 | 2021-04-25 | 2021-07-24 | 20 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 26 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-23 | 2024-08-26 | 2021-04-25 | 2021-07-24 | 30 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2021-04-25 | 2021-07-24 | 40 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-27 | 2021-04-25 | 2021-07-24 | 50 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-27 | 2021-04-25 | 2021-07-24 | 60 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-28 | 2021-04-25 | 2021-07-24 | 100 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048144 | DFCM-PSV-52211 Corroded sealing face | L3 Pre. Linewalk |  |  | 14 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-30 | 2021-04-25 | 2021-07-24 | 110 |  |  | DF /C /51/DFCM-PSV-52211 | L3 Pre. Linewalk | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235798 | 4Y 380V N-SWB MAINT-DFBA-N-1810-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235798 | 4Y 380V N-SWB MAINT-DFBA-N-1810-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235798 | 4Y 380V N-SWB MAINT-DFBA-N-1810-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235798 | 4Y 380V N-SWB MAINT-DFBA-N-1810-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-02-27 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 10 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 8 | 16 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 20 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 8 | 8 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-01 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 30 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 20 | 36 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-03 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 40 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 40 | 36 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-05 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 50 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 60 | 60 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-08 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 60 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 20 | 20 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-13 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 70 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 8 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 75 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 8 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 76 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 8 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 77 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 8 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 78 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 12 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 80 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 21 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-15 | 2019-04-01 | 2019-04-21 | 90 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 8 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-15 | 2023-03-15 | 2019-04-01 | 2019-04-21 | 100 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 110 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 120 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 130 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 140 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 150 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 0 | 0 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-14 | 2019-04-01 | 2019-04-21 | 160 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024393 | FFSPR Pin hole downstream LCV 500106. | Pin hole down strem LCV 500106 |  |  | 15 | 15 | Empty | 2023-03-14 | 2023-03-18 | 2023-03-14 | 2023-03-18 | 2019-04-01 | 2019-04-21 | 170 |  |  | DF /F /28/DFF-4-DPS-050-7508-AB-T | Pin hole down strem LCV 500106 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009355 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /A /54/DFA-12-WI-035-9012-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009355 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 20 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-08 | 2024-01-10 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /A /54/DFA-12-WI-035-9012-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009355 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 20 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-10 | 2024-01-11 | 2022-02-08 | 2022-07-08 | 25 |  |  | DF /A /54/DFA-12-WI-035-9012-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009355 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-11 | 2024-01-12 | 2022-02-08 | 2022-07-08 | 27 |  |  | DF /A /54/DFA-12-WI-035-9012-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009355 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 37 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-12 | 2024-01-14 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /A /54/DFA-12-WI-035-9012-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009355 | Paint assist FORCE 16266 | Bilfinger inspection |  |  | 10 | 0 | Empty | 2024-01-08 | 2024-01-15 | 2024-01-14 | 2024-01-15 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /A /54/DFA-12-WI-035-9012-AB-U | Bilfinger inspection | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 0 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-07-30 | 2024-07-30 | 2023-08-20 | 2024-01-02 | 10 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-07-30 | 2024-07-30 | 2023-08-20 | 2024-01-02 | 20 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 4 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-07-30 | 2024-07-31 | 2023-08-20 | 2024-01-02 | 30 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 4 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-07-31 | 2024-08-01 | 2023-08-20 | 2024-01-02 | 40 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 6 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-08-01 | 2024-08-03 | 2023-08-20 | 2024-01-02 | 50 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 6 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-08-03 | 2024-08-04 | 2023-08-20 | 2024-01-02 | 60 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100094214 | DFG-HCV-340059 Internal Leak. | Isolate HCV-340059 |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-08-20 | 2024-01-02 | 70 |  |  | DF /G /32/DFGA-HCV-340059 | Isolate HCV-340059 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263656 | 6M SDV LUB/MAINT TSEP - DFF | SDV LUB/INSP TSEP - DFF |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-07-07 | 2023-07-23 | 10 |  |  | DF /F /03/SDV-VALVES | SDV LUB/INSP TSEP - DFF | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339102 | DFC_1Y_67450 INT STRUCT INSP - GVI | DFC_1Y_67450 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_67450 (ACCOMOD. ROOF DECK) | DFC_1Y_67450 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-26 | 2023-04-11 | 2023-08-24 | 10 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-27 | 2023-04-11 | 2023-08-24 | 20 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-27 | 2024-08-28 | 2023-04-11 | 2023-08-24 | 29 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-08-29 | 2023-04-11 | 2023-08-24 | 30 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-29 | 2024-08-30 | 2023-04-11 | 2023-08-24 | 40 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-30 | 2024-08-30 | 2023-04-11 | 2023-08-24 | 50 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-30 | 2024-08-31 | 2023-04-11 | 2023-08-24 | 60 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-31 | 2024-09-01 | 2023-04-11 | 2023-08-24 | 70 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-01 | 2024-09-01 | 2023-04-11 | 2023-08-24 | 80 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-01 | 2024-09-01 | 2023-04-11 | 2023-08-24 | 90 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-01 | 2024-09-02 | 2023-04-11 | 2023-08-24 | 100 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100088066 | FLM ESDV-45092 DFE gaslift manifold fail | Isolate ESDV-45092 |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2023-04-11 | 2023-08-24 | 120 |  |  | DF /E /34/DFEZ-ESDV-45092 | Isolate ESDV-45092 | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300001076 | Firmware upgrade Saab GW DAF | Firmware upgrade Saab GW DAF,permits etc |  |  | 5 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2019-12-01 | 2019-12-06 | 10 |  |  | DF /C /08/DFCI-RL-140054 | Firmware upgrade Saab GW DAF,permits etc | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235697 | 4Y 380V E-SWB MAINT-DFBA-N-1811 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-24 | 2024-07-24 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1811 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235697 | 4Y 380V E-SWB MAINT-DFBA-N-1811 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 14 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-24 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1811 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235697 | 4Y 380V E-SWB MAINT-DFBA-N-1811 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2023-02-14 | 2023-04-28 | 30 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1811 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235697 | 4Y 380V E-SWB MAINT-DFBA-N-1811 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2023-02-14 | 2023-04-28 | 40 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1811 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 6 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 10 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 20 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 3 | 36 | Empty | 2024-07-29 | 2024-07-29 | 2022-10-27 | 2022-10-27 | 2019-08-07 | 2019-11-05 | 30 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 2 | 4 | Empty | 2024-07-29 | 2024-07-29 | 2022-10-27 | 2022-10-27 | 2019-08-07 | 2019-11-05 | 40 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 5 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 50 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 5 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 60 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 3 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 70 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 80 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 90 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025157 | Exchange pump & motor DFGA-P-3961 | L3 Remove mechanical connections | PCNF | PCNF | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-08-07 | 2019-11-05 | 100 | PCNF | PCNF | DF /G /75/DFGA-P-3961 | L3 Remove mechanical connections | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018147 | Replace Feeder protection 1841-M124 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M124-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018147 | Replace Feeder protection 1841-M124 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M124-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018147 | Replace Feeder protection 1841-M124 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M124-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018147 | Replace Feeder protection 1841-M124 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M124-02 | New mat num | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235627 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235627 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | AWSC | AWSC | 39 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-09-22 | 2024-10-01 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235627 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-10-02 | 2024-10-05 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235627 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-17 | 380V N-SWB INSP-DFFA-N-1802B-17 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095456 | Minox DFFB-A-1252 | Minox DFFB-A-1252 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 10 |  |  | DF /F /09/DFFB-A-1252 | Minox DFFB-A-1252 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095456 | Minox DFFB-A-1252 | Minox DFFB-A-1252 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 20 |  |  | DF /F /09/DFFB-A-1252 | Minox DFFB-A-1252 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095456 | Minox DFFB-A-1252 | Minox DFFB-A-1252 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-09 | 2024-01-22 | 30 |  |  | DF /F /09/DFFB-A-1252 | Minox DFFB-A-1252 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095456 | Minox DFFB-A-1252 | Minox DFFB-A-1252 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 40 |  |  | DF /F /09/DFFB-A-1252 | Minox DFFB-A-1252 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095456 | Minox DFFB-A-1252 | Minox DFFB-A-1252 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-09 | 2024-01-22 | 50 |  |  | DF /F /09/DFFB-A-1252 | Minox DFFB-A-1252 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235597 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-8 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-8-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235597 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-8 | ISOLATION ELECTRICAL |  |  | 35 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-24 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-8-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235597 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-8 | ISOLATION ELECTRICAL |  |  | 11 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-27 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-8-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235597 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-8 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-8-5 | ISOLATION ELECTRICAL | Unknown
C | DFF-3580 | WPM | MTN-INST | MTN-INST | 2400321283 | 3Y WATER INJ TURBINE PT-3580 - METERING | WATER INJ TURBINE PT-3580 - METERING | AWSC | AWSC | 1 | 0 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-02-28 | 2024-05-12 | 10 | AWSC | AWSC | DF /F /54/DFFB-A-3580 | WATER INJ TURBINE PT-3580 - METERING | Unknown
2 | DFA-W08 | WDF | MTN-MECH | PRODTECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 3 | 0 | Empty | 2024-01-15 | 2024-06-19 | 2023-01-24 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 10 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-RIGG | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 8 | 13 | Empty | 2024-01-15 | 2024-06-19 | 2023-01-25 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 20 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-MECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 15 | 112 | Empty | 2024-01-15 | 2024-06-19 | 2023-01-27 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 30 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-RIGG | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 4 | 4 | Empty | 2024-01-15 | 2024-06-19 | 2023-01-27 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 40 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-MECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 4 | 25 | Empty | 2024-01-15 | 2024-06-19 | 2023-01-30 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 50 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-MECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 4 | 12 | Empty | 2024-01-15 | 2024-06-19 | 2023-01-31 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 60 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-MECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 15 | 8 | Empty | 2024-01-15 | 2024-06-19 | 2023-02-01 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 70 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-RIGG | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 4 | 4 | Empty | 2024-01-15 | 2024-06-19 | 2023-02-01 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 80 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | PRODTECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 3 | 0 | Empty | 2024-01-15 | 2024-06-19 | 2023-02-05 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 90 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-RIGG | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 6 | 6 | Empty | 2024-01-15 | 2024-06-19 | 2023-02-06 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 100 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-SCAF | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 10 | 10 | Empty | 2024-01-15 | 2024-06-19 | 2023-03-13 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 110 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-MECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-01-15 | 2024-06-19 | 2024-01-15 | 2024-01-15 | 2023-01-24 | 2023-02-08 | 120 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-SCAF | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 5 | 5 | Empty | 2024-01-15 | 2024-06-19 | 2024-01-16 | 2024-06-19 | 2023-01-24 | 2023-02-08 | 130 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-INST | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 12 | 10 | Empty | 2024-01-15 | 2024-06-19 | 2024-01-15 | 2024-01-15 | 2023-01-24 | 2023-02-08 | 140 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
2 | DFA-W08 | WDF | MTN-MECH | MTN-MECH | 2100081660 | DFA08 CHOKE stock, home for rep<(>,<)> | line for extra mat. | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-01-15 | 2024-06-19 | 2024-01-15 | 2024-01-15 | 2023-01-24 | 2023-02-08 | 150 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-HCV-30008 | line for extra mat. | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 3 | 0 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 10 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 3 | 3 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 20 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 2 | 4 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 30 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 5 | 37 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 40 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 5 | 5 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 50 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 5 | 2 | Empty | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2021-11-17 | 2021-12-27 | 60 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 5 | 5 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 70 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 2 | 4 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 80 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 2 | 4 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-29 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 90 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 3 | 2 | Empty | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2021-11-17 | 2021-12-27 | 100 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 0 | 12 | Empty | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2021-11-17 | 2021-12-27 | 110 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 50 | 48 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-30 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 120 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058034 | PMAT Minox FT-3552 XCV-355204 kører dårl | open FT-3552 to check / change filters |  |  | 60 | 48 | Empty | 2023-02-13 | 2023-02-13 | 2022-03-30 | 2022-04-03 | 2021-11-17 | 2021-12-27 | 130 |  |  | DF /F /51/DFFB-XCV-355204 | open FT-3552 to check / change filters | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322297 | DFF-54-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /54/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | VEN-MECH | 2100025261 | S/D på PT backup overspeed. | Får S/D på PT backup overspeed | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 12 | W37-38 DFG SD J&K | 2024-09-25 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2016-12-24 | 2017-03-24 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-A-4302 | Får S/D på PT backup overspeed | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | VEN-MECH | 2100025261 | S/D på PT backup overspeed. | Får S/D på PT backup overspeed | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W37-38 DFG SD J&K | 2024-09-25 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2016-12-24 | 2017-03-24 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-A-4302 | Får S/D på PT backup overspeed | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100025261 | S/D på PT backup overspeed. | Får S/D på PT backup overspeed | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W37-38 DFG SD J&K | 2024-09-25 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2016-12-24 | 2017-03-24 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-A-4302 | Får S/D på PT backup overspeed | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | VEN-MECH | 2100025261 | S/D på PT backup overspeed. | Får S/D på PT backup overspeed | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W37-38 DFG SD J&K | 2024-09-25 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2016-12-24 | 2017-03-24 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-A-4302 | Får S/D på PT backup overspeed | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-15 | 2023-04-06 | 2025-09-22 | 10 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-17 | 2023-04-06 | 2025-09-22 | 20 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-17 | 2023-04-06 | 2025-09-22 | 30 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 14 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-17 | 2023-04-06 | 2025-09-22 | 40 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 10 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-17 | 2024-07-18 | 2023-04-06 | 2025-09-22 | 45 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-17 | 2024-07-19 | 2023-04-06 | 2025-09-22 | 50 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 26 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-19 | 2024-07-22 | 2023-04-06 | 2025-09-22 | 60 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-22 | 2024-07-22 | 2023-04-06 | 2025-09-22 | 70 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100076002 | DFCM: 10Y overhaul onshore. | Disconnect supply cables |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-22 | 2024-07-23 | 2023-04-06 | 2025-09-22 | 80 |  |  | DF /C /78/DFCM-X-6105 | Disconnect supply cables | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235596 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-7 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-7-1-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235596 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-7 | ISOLATION ELECTRICAL |  |  | 27 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-22 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-7-1-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235596 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-7 | ISOLATION ELECTRICAL |  |  | 9 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-7-1-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235596 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-7 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-7-1-1 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339099 | DFC_1Y_57350 INT STRUCT INSP - GVI | DFC_1Y_57350 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_57350 (ACCOMMODATION L3) | DFC_1Y_57350 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 0 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-17 | 2021-12-01 | 2022-01-06 | 1 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-18 | 2024-06-18 | 2021-12-01 | 2022-01-06 | 10 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | PRODTECH | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-18 | 2024-06-18 | 2021-12-01 | 2022-01-06 | 11 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | MTN-MECH | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 6 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-19 | 2024-06-20 | 2021-12-01 | 2022-01-06 | 12 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-20 | 2021-12-01 | 2022-01-06 | 20 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | MTN-SCAF | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-17 | 2021-12-01 | 2022-01-06 | 30 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | MTN-SCAF | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-21 | 2021-12-01 | 2022-01-06 | 40 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
C | NOSD | WPM | MTN-INST | PRODTECH | 2400176903 | 1Y FUELGAS METERING, FE-570222 | Build scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-20 | 2021-12-01 | 2022-01-06 | 50 | AWSC | AWSC | DF /F /70/DFFA-FIT-570222 | Build scaffolding | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-27 | 2023-03-29 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-30 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-31 | 2023-04-03 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-03 | 2023-04-03 | 2022-02-07 | 2022-07-07 | 42 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-03 | 2023-04-07 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 28 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-07 | 2023-04-10 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009230 | Insulation assists Bilfinger 22080(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-10 | 2023-04-12 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /F /27/DFF-2-DPS-050-8072-AD-T | Bilfinger inspection | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016994 | vegetable cutter Galley defective | vegetable cutter Galley defective |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-12-28 | 2024-02-11 | 10 |  |  | DF /C /82/CATERING-EQUIPMENT | vegetable cutter Galley defective | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100078736 | Change of complete FCV-290106. | Mount new FCV-290116 |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-10 | 2023-05-25 | 10 |  |  | DF /F /37/DFFA-FCV-290106 | Mount new FCV-290116 | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078736 | Change of complete FCV-290106. | Mount new FCV-290116 |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2023-01-10 | 2023-05-25 | 20 |  |  | DF /F /37/DFFA-FCV-290106 | Mount new FCV-290116 | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078736 | Change of complete FCV-290106. | Mount new FCV-290116 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2023-01-10 | 2023-05-25 | 30 |  |  | DF /F /37/DFFA-FCV-290106 | Mount new FCV-290116 | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078736 | Change of complete FCV-290106. | Mount new FCV-290116 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-01-10 | 2023-05-25 | 40 |  |  | DF /F /37/DFFA-FCV-290106 | Mount new FCV-290116 | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078736 | Change of complete FCV-290106. | Mount new FCV-290116 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-01-10 | 2023-05-25 | 50 |  |  | DF /F /37/DFFA-FCV-290106 | Mount new FCV-290116 | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100078736 | Change of complete FCV-290106. | Mount new FCV-290116 |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-10 | 2023-05-25 | 60 |  |  | DF /F /37/DFFA-FCV-290106 | Mount new FCV-290116 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040325 | DFAA-HCV-38101 DKDF0073 C-Out 2 Hyd Hose | Replace hydr hoses DFAA-HCV-38101 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-11-22 | 2021-02-20 | 10 |  |  | DF /A /12/DFAA-HCV-38101 | Replace hydr hoses DFAA-HCV-38101 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040325 | DFAA-HCV-38101 DKDF0073 C-Out 2 Hyd Hose | Replace hydr hoses DFAA-HCV-38101 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-11-22 | 2021-02-20 | 20 |  |  | DF /A /12/DFAA-HCV-38101 | Replace hydr hoses DFAA-HCV-38101 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040325 | DFAA-HCV-38101 DKDF0073 C-Out 2 Hyd Hose | Replace hydr hoses DFAA-HCV-38101 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2020-11-22 | 2021-02-20 | 30 |  |  | DF /A /12/DFAA-HCV-38101 | Replace hydr hoses DFAA-HCV-38101 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100060280 | FLMR DFG - Repl of gratings EL +42000 | DFG - Replacement of gratings EL +42000 |  |  | 0 | 0 | Empty | 2022-01-05 | 2022-01-07 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-04-05 | 10 |  |  | DF /G /86/42000 - GRATINGS | DFG - Replacement of gratings EL +42000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100060280 | FLMR DFG - Repl of gratings EL +42000 | DFG - Replacement of gratings EL +42000 |  |  | 3 | 0 | Empty | 2022-01-05 | 2022-01-07 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-04-05 | 20 |  |  | DF /G /86/42000 - GRATINGS | DFG - Replacement of gratings EL +42000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100060280 | FLMR DFG - Repl of gratings EL +42000 | DFG - Replacement of gratings EL +42000 |  |  | 1 | 0 | Empty | 2022-01-05 | 2022-01-07 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-04-05 | 30 |  |  | DF /G /86/42000 - GRATINGS | DFG - Replacement of gratings EL +42000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100060280 | FLMR DFG - Repl of gratings EL +42000 | DFG - Replacement of gratings EL +42000 |  |  | 12 | 0 | Empty | 2022-01-05 | 2022-01-07 | 2022-01-05 | 2022-01-06 | 2022-01-05 | 2022-04-05 | 40 |  |  | DF /G /86/42000 - GRATINGS | DFG - Replacement of gratings EL +42000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100060280 | FLMR DFG - Repl of gratings EL +42000 | DFG - Replacement of gratings EL +42000 |  |  | 12 | 0 | Empty | 2022-01-05 | 2022-01-07 | 2022-01-06 | 2022-01-06 | 2022-01-05 | 2022-04-05 | 50 |  |  | DF /G /86/42000 - GRATINGS | DFG - Replacement of gratings EL +42000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100060280 | FLMR DFG - Repl of gratings EL +42000 | DFG - Replacement of gratings EL +42000 |  |  | 1 | 0 | Empty | 2022-01-05 | 2022-01-07 | 2022-01-06 | 2022-01-07 | 2022-01-05 | 2022-04-05 | 60 |  |  | DF /G /86/42000 - GRATINGS | DFG - Replacement of gratings EL +42000 | Unknown
2 | DFF-O04 | WDF | MTN-MECH | MTN-MECH | 2100087707 | DFF-04 leak from liftgas check-valve | Remove valves and blind off. | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-22 | 2023-05-06 | 10 | PCNFSECE | PCNFSECE | DF /F /37/DFF-2-GPS-029-6904-FC-U | Remove valves and blind off. | Unknown
2 | DFF-O04 | WDF | MTN-MECH | MTN-MECH | 2100087707 | DFF-04 leak from liftgas check-valve | Remove valves and blind off. | PCNFSECE | PCNFSECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-22 | 2023-05-06 | 20 | PCNFSECE | PCNFSECE | DF /F /37/DFF-2-GPS-029-6904-FC-U | Remove valves and blind off. | Unknown
2 | DFF-O04 | WDF | MTN-MECH | MTN-MECH | 2100087707 | DFF-04 leak from liftgas check-valve | Remove valves and blind off. | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-22 | 2023-05-06 | 30 | PCNFSECE | PCNFSECE | DF /F /37/DFF-2-GPS-029-6904-FC-U | Remove valves and blind off. | Unknown
2 | DFF-O04 | WDF | MTN-MECH | MTN-RIGG | 2100087707 | DFF-04 leak from liftgas check-valve | Remove valves and blind off. | PCNFSECE | PCNFSECE | 6 | 36 | Empty | 2024-09-22 | 2024-09-23 | 2023-03-22 | 2023-05-22 | 2023-03-22 | 2023-05-06 | 40 | PCNFSECE | PCNFSECE | DF /F /37/DFF-2-GPS-029-6904-FC-U | Remove valves and blind off. | Unknown
2 | DFF-O04 | WDF | MTN-MECH | MTN-SCAF | 2100087707 | DFF-04 leak from liftgas check-valve | Remove valves and blind off. | PCNFSECE | PCNFSECE | 8 | 42 | Empty | 2024-09-22 | 2024-09-23 | 2023-03-22 | 2023-05-22 | 2023-03-22 | 2023-05-06 | 50 | PCNFSECE | PCNFSECE | DF /F /37/DFF-2-GPS-029-6904-FC-U | Remove valves and blind off. | Unknown
2 | DFF-O04 | WDF | MTN-MECH | MTN-MECH | 2100087707 | DFF-04 leak from liftgas check-valve | Remove valves and blind off. | PCNFSECE | PCNFSECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-22 | 2023-05-06 | 60 | PCNFSECE | PCNFSECE | DF /F /37/DFF-2-GPS-029-6904-FC-U | Remove valves and blind off. | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400220345 | 6M HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-12-22 | 2023-01-07 | 10 |  |  | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400220345 | 6M HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-12-22 | 2023-01-07 | 20 |  |  | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400220345 | 6M HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-12-22 | 2023-01-07 | 30 |  |  | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100089323 | DFA-15 LG ESDV-45027 ZSO faulty | Investigate ESDV-45027 ZSO |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-06-02 | 2023-10-15 | 10 |  |  | DF /A /37/DFAA-ESDV-45027 | Investigate ESDV-45027 ZSO | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087752 | Nød armatue 1812-10905-L2E | Nød armatue 1812-10905-L2E |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 10 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatue 1812-10905-L2E | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087752 | Nød armatue 1812-10905-L2E | Nød armatue 1812-10905-L2E |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 20 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatue 1812-10905-L2E | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087752 | Nød armatue 1812-10905-L2E | Nød armatue 1812-10905-L2E |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 30 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatue 1812-10905-L2E | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087752 | Nød armatue 1812-10905-L2E | Nød armatue 1812-10905-L2E |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 40 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatue 1812-10905-L2E | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2021-05-30 | 2021-10-27 | 10 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2021-05-30 | 2021-10-27 | 20 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2021-05-30 | 2021-10-27 | 30 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2021-05-30 | 2021-10-27 | 40 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2021-05-30 | 2021-10-27 | 50 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2021-05-30 | 2021-10-27 | 60 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100046902 | Extern leak from HCV-03811 valve (pinhol | Cladding/insulation removal |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2021-05-30 | 2021-10-27 | 70 |  |  | DF /B /01/DFBA-HCV-03811 | Cladding/insulation removal | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100031791 | Troubleshoot HT FG DP-1854 Q22 | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2020-08-16 | 2021-04-13 | 10 |  |  | DF /G /61/DFGA-DP-1854-22 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100031791 | Troubleshoot HT FG DP-1854 Q22 | Set personal isolation |  |  | 5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2020-08-16 | 2021-04-13 | 20 |  |  | DF /G /61/DFGA-DP-1854-22 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100031791 | Troubleshoot HT FG DP-1854 Q22 | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2020-08-16 | 2021-04-13 | 30 |  |  | DF /G /61/DFGA-DP-1854-22 | Set personal isolation | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-MECH | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 1457 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 10 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-SCAF | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 2802 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 20 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-ELEC | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 100 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 30 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-RIGG | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 0 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 40 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-PIPF | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 0 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 50 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-ROPE | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 0 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 60 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-INST | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 0 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 70 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-PAIN | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 647 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 80 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | PRODTECH | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 50 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 90 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | VEN-INSP | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 24 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 100 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
A | DFG-WI | WPM | VEN-INSP | MTN-LAGG | 2400292010 | PVI Major - DFGA-V-3540 | Scaffolding work | AWSC | AWSC | 122 | 0 | Empty | 2024-04-30 | 2024-12-31 | 2024-04-30 | 2024-12-31 | 2024-09-30 | 2024-12-30 | 110 | AWSC | AWSC | DF /G /54/DFGA-V-3540 | Scaffolding work | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400285952 | 6M PED CRANE CHECK VENDOR DFBA-X-6102 | order new whip hook | AWSC | AWSC | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2024-03-01 | 2024-03-17 | 10 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order new whip hook | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400285952 | 6M PED CRANE CHECK VENDOR DFBA-X-6102 | order new whip hook | AWSC | AWSC | 18 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-19 | 2024-03-01 | 2024-03-17 | 20 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order new whip hook | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400285952 | 6M PED CRANE CHECK VENDOR DFBA-X-6102 | order new whip hook | AWSC | AWSC | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2024-03-01 | 2024-03-17 | 30 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order new whip hook | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400285952 | 6M PED CRANE CHECK VENDOR DFBA-X-6102 | order new whip hook | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2024-03-01 | 2024-03-17 | 40 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order new whip hook | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096537 | Earth bonding broken DFCC-PM-0306 | Remove old |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-18 | 2024-01-31 | 10 |  |  | DF /C /01/DFCC-PM-0306 | Remove old | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096537 | Earth bonding broken DFCC-PM-0306 | Remove old |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-18 | 2024-01-31 | 20 |  |  | DF /C /01/DFCC-PM-0306 | Remove old | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096537 | Earth bonding broken DFCC-PM-0306 | Remove old |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-18 | 2024-01-31 | 30 |  |  | DF /C /01/DFCC-PM-0306 | Remove old | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096537 | Earth bonding broken DFCC-PM-0306 | Remove old |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-18 | 2024-01-31 | 40 |  |  | DF /C /01/DFCC-PM-0306 | Remove old | Unknown
A | DFG-3590 | WPM | MTN-TURB | MTN-TURB | 2400336980 | 2,5KH TURBINE WASH DFGA-A-3590 COUNTER | TURBINE WASH DFGA-A-3590 COUNTER | AWSCSECE | AWSCSECE | 12 | 0 | W29-W30 | 2024-07-21 | 2024-07-23 | 2024-07-21 | 2024-07-23 | 2024-07-21 | 2024-08-06 | 10 | AWSCSECE | AWSCSECE | DF /G /54/DFGA-A-3590 | TURBINE WASH DFGA-A-3590 COUNTER | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235605 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235605 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL |  |  | 13 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-18 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235605 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235605 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-11 | DE-ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058309 | DFAA-PSV-392323 interal leaking | Install certified PSV |  |  | 1.5 | 0 | RCE | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-11-20 | 2021-12-30 | 10 |  |  | DF /A /75/DFAA-PSV-392323 | Install certified PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100058309 | DFAA-PSV-392323 interal leaking | Install certified PSV |  |  | 1 | 0 | RCE | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-11-20 | 2021-12-30 | 20 |  |  | DF /A /75/DFAA-PSV-392323 | Install certified PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100058309 | DFAA-PSV-392323 interal leaking | Install certified PSV |  |  | 1 | 0 | RCE | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-11-20 | 2021-12-30 | 30 |  |  | DF /A /75/DFAA-PSV-392323 | Install certified PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058309 | DFAA-PSV-392323 interal leaking | Install certified PSV |  |  | 1.5 | 0 | RCE | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-11-20 | 2021-12-30 | 40 |  |  | DF /A /75/DFAA-PSV-392323 | Install certified PSV | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344325 | 6M FLARE SYSTEM MAINT-DFC | FLARE SYSTEM MAINT-DFC |  |  | 2 | 0 | Empty | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-28 | 10 |  |  | DF /C /36/FLARE-SYSTEM | FLARE SYSTEM MAINT-DFC | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059889 | Replace power cable DFB-L1810-43-L2H | Isolate light circuit |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-04-04 | 2022-11-30 | 10 |  |  | DF /B /61/DFBA-N-1810-C_43 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059889 | Replace power cable DFB-L1810-43-L2H | Isolate light circuit |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-04-04 | 2022-11-30 | 20 |  |  | DF /B /61/DFBA-N-1810-C_43 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059889 | Replace power cable DFB-L1810-43-L2H | Isolate light circuit |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2022-04-04 | 2022-11-30 | 30 |  |  | DF /B /61/DFBA-N-1810-C_43 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059889 | Replace power cable DFB-L1810-43-L2H | Isolate light circuit |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2022-04-04 | 2022-11-30 | 40 |  |  | DF /B /61/DFBA-N-1810-C_43 | Isolate light circuit | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200018523 | DFC Dauble acting posioner | DFC Dauble acting posioner |  |  | 0 | 0 | Empty | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-11-09 | 10 |  |  | DF /C /03/INSTRUMENTS | DFC Dauble acting posioner | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344326 | 6M COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | AWSC | AWSC | 8 | 0 | Empty | 2024-09-10 | 2024-09-17 | 2024-09-10 | 2024-09-11 | 2024-09-10 | 2024-09-29 | 10 | AWSC | AWSC | DF /C /07/DFCM-A-5408 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344326 | 6M COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | AWSC | AWSC | 17 | 0 | Empty | 2024-09-10 | 2024-09-17 | 2024-09-12 | 2024-09-16 | 2024-09-10 | 2024-09-29 | 20 | AWSC | AWSC | DF /C /07/DFCM-A-5408 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400344326 | 6M COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | AWSC | AWSC | 6 | 0 | Empty | 2024-09-10 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2024-09-10 | 2024-09-29 | 40 | AWSC | AWSC | DF /C /07/DFCM-A-5408 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241155 | 6M GALLEY VENDOR MAINT DFC | GALLEY VENDOR MAINT DFC | AWSC | AWSC | 24 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-27 | 2023-03-13 | 2023-04-01 | 10 | AWSC | AWSC | DF /C /82/CATERING-EQUIPMENT | GALLEY VENDOR MAINT DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235674 | 4Y 380V N-SWB MAINT-DFCI-N-1823-1 | 380V N-SWB INSP-DFCI-N-1823-1 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1823-01A1 | 380V N-SWB INSP-DFCI-N-1823-1 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235674 | 4Y 380V N-SWB MAINT-DFCI-N-1823-1 | 380V N-SWB INSP-DFCI-N-1823-1 | AWSC | AWSC | 19 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1823-01A1 | 380V N-SWB INSP-DFCI-N-1823-1 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235674 | 4Y 380V N-SWB MAINT-DFCI-N-1823-1 | 380V N-SWB INSP-DFCI-N-1823-1 | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1823-01A1 | 380V N-SWB INSP-DFCI-N-1823-1 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235674 | 4Y 380V N-SWB MAINT-DFCI-N-1823-1 | 380V N-SWB INSP-DFCI-N-1823-1 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1823-01A1 | 380V N-SWB INSP-DFCI-N-1823-1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2022-04-19 | 2022-05-29 | 10 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-16 | 2022-04-19 | 2022-05-29 | 20 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2022-04-19 | 2022-05-29 | 25 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2022-04-19 | 2022-05-29 | 30 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2022-04-19 | 2022-05-29 | 40 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2022-04-19 | 2022-05-29 | 50 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-04-19 | 2022-05-29 | 60 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-04-19 | 2022-05-29 | 70 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100066276 | DFF LP-sep sandtrap XCV actuator faulty. | Isolate Actuator pneumatic |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-04-19 | 2022-05-29 | 80 |  |  | DF /F /20/DFFA-XCV-340563 | Isolate Actuator pneumatic | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316004 | 4000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION & GREASING | AWSCSCH | AWSCSCH | 18 | 24 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-20 | 2024-06-24 | 2024-04-03 | 2024-04-19 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | VISUAL INSPECTION & GREASING | Unknown
4 | NE | WRO | UNKNOWN | WELLSUPV | 2300000721 | Backload af grise Dan | BACKLOAD GRISE DAN |  |  | 0 | 0 | Empty | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2010-01-01 | 2030-12-31 | 10 |  |  | DF | BACKLOAD GRISE DAN | Unknown
4 | NE | WRO | UNKNOWN | WELLSUPV | 2300000721 | Backload af grise Dan | BACKLOAD GRISE DAN |  |  | 0 | 0 | Empty | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2010-01-01 | 2030-12-31 | 20 |  |  | DF | BACKLOAD GRISE DAN | Unknown
4 | NE | WRO | UNKNOWN | WELLSUPV | 2300000721 | Backload af grise Dan | BACKLOAD GRISE DAN |  |  | 0 | 0 | Empty | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2010-01-01 | 2030-12-31 | 30 |  |  | DF | BACKLOAD GRISE DAN | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018146 | Replace Motor protection 1841-M123 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M123-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018146 | Replace Motor protection 1841-M123 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M123-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018146 | Replace Motor protection 1841-M123 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M123-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018146 | Replace Motor protection 1841-M123 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M123-02 | Isolation of Breaker section | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322253 | DFC-28-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 97 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004051 | IT0098 - Dan Telecom support August 2022 | IT0098 - Dan Telecom support August 2022 | PCNF | PCNF | 36 | 6 | W21-W22 | 2024-05-20 | 2024-05-28 | 2024-05-20 | 2024-05-28 | 2022-09-11 | 2023-01-24 | 10 | PCNF | PCNF | DF /C /08/DFCI-DT-14-10-02 | IT0098 - Dan Telecom support August 2022 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291800 | 6M BUNKER HOSES/REELS MAINT - DAN-F | BUNKER HOSES/REELS INSP - DAN-F |  |  | 5 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-27 | 2023-12-16 | 10 |  |  | DF /C /71/DFCI-HOSB-5790 | BUNKER HOSES/REELS INSP - DAN-F | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000963 | ESD SW for ENG469Q Catalyst pumps | ESD SW for ENG469Q Catalyst pumps | AWSC | AWSC | 12 | 0 | IOP date TBC | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 10 | AWSC | AWSC | DF /B /03/DFBA-FP-0208 | ESD SW for ENG469Q Catalyst pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000963 | ESD SW for ENG469Q Catalyst pumps | ESD SW for ENG469Q Catalyst pumps | AWSC | AWSC | 0 | 0 | IOP date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 20 | AWSC | AWSC | DF /B /03/DFBA-FP-0208 | ESD SW for ENG469Q Catalyst pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000963 | ESD SW for ENG469Q Catalyst pumps | ESD SW for ENG469Q Catalyst pumps | AWSC | AWSC | 0 | 0 | IOP date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 30 | AWSC | AWSC | DF /B /03/DFBA-FP-0208 | ESD SW for ENG469Q Catalyst pumps | Unknown
3 | NE | WRO | MTN-TURB | MTN-TURB | 2300000905 | Low temperature downstream DFF HP ASV | Low temperature downstream DFF HP ASV |  |  | 0 | 0 | W21-W22 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2017-03-27 | 2017-04-16 | 10 |  |  | DF /F /31/DFFA-TIT-440056 | Low temperature downstream DFF HP ASV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053493 | Nozzle flange sealing face corro (HOLD) | Nozzle flange sealing face corrosion |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-30 | 2022-11-26 | 10 |  |  | DF /C /51/DFCM-FT-5231 | Nozzle flange sealing face corrosion | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015378 | Replace LB1 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /C /02/DFCI-X-0701 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015378 | Replace LB1 coolant with GlysantinG30 | Isolate lifeboat |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /C /02/DFCI-X-0701 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015378 | Replace LB1 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /C /02/DFCI-X-0701 | Isolate lifeboat | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400315643 | 6M PROCESS CALIBR EQUIPMENT MAINT - DFC | PROCESS CALIBR EQUIPMENT MAINT - DFC |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-03-31 | 2024-04-19 | 10 |  |  | DF /C /84/DFCI-XE-80001 | PROCESS CALIBR EQUIPMENT MAINT - DFC | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286623 | 1Y HI-FOG SKID MAINT-DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | PCNFSECE | PCNFSECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2023-10-16 | 2023-11-15 | 10 | PCNFSECE | PCNFSECE | DF /E /01/DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286623 | 1Y HI-FOG SKID MAINT-DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | PCNFSECE | PCNFSECE | 10 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2023-10-16 | 2023-11-15 | 20 | PCNFSECE | PCNFSECE | DF /E /01/DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286623 | 1Y HI-FOG SKID MAINT-DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | PCNFSECE | PCNFSECE | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2023-10-16 | 2023-11-15 | 30 | PCNFSECE | PCNFSECE | DF /E /01/DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286623 | 1Y HI-FOG SKID MAINT-DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | PCNFSECE | PCNFSECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2023-10-16 | 2023-11-15 | 40 | PCNFSECE | PCNFSECE | DF /E /01/DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286623 | 1Y HI-FOG SKID MAINT-DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | PCNFSECE | PCNFSECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2023-10-16 | 2023-11-15 | 50 | PCNFSECE | PCNFSECE | DF /E /01/DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286623 | 1Y HI-FOG SKID MAINT-DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | PCNFSECE | PCNFSECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2023-10-16 | 2023-11-15 | 60 | PCNFSECE | PCNFSECE | DF /E /01/DFEZ-A-0440 | HI-FOG SKID MAINT-DFEZ-A-0440 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284287 | PSV Exchange - DFFA-PSV-570066 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /70/DFFA-PSV-570066 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284287 | PSV Exchange - DFFA-PSV-570066 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /70/DFFA-PSV-570066 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284287 | PSV Exchange - DFFA-PSV-570066 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /70/DFFA-PSV-570066 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284287 | PSV Exchange - DFFA-PSV-570066 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /70/DFFA-PSV-570066 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284287 | PSV Exchange - DFFA-PSV-570066 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /70/DFFA-PSV-570066 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284287 | PSV Exchange - DFFA-PSV-570066 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /70/DFFA-PSV-570066 | Isolation of PSV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2021-05-09 | 2021-10-06 | 10 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2021-05-09 | 2021-10-06 | 20 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2021-05-09 | 2021-10-06 | 30 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2021-05-09 | 2021-10-06 | 40 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-05 | 2021-05-09 | 2021-10-06 | 50 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2021-05-09 | 2021-10-06 | 60 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100045747 | FB-16 Bullhead valves int leak CHV+HCV | order bolts | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2021-05-09 | 2021-10-06 | 70 | AWSC | AWSC | DF /B /10 | order bolts | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329506 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W19-W20 | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-06-23 | 10 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400329506 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W19-W20 | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-06-23 | 20 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329506 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-05-24 | 2024-05-25 | 2024-05-24 | 2024-05-24 | 2024-05-24 | 2024-06-23 | 30 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329506 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W19-W20 | 2024-05-24 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2024-05-24 | 2024-06-23 | 40 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-O16 | WDF | MTN-MECH | MTN-RIGG | 2100078735 | Change complete FCV-290116 | Re-build tubing if any |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-11 | 2023-05-26 | 10 |  |  | DF /F /37/DFFA-FCV-290116 | Re-build tubing if any | Unknown
3 | DFF-O16 | WDF | MTN-MECH | MTN-MECH | 2100078735 | Change complete FCV-290116 | Re-build tubing if any |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2023-01-11 | 2023-05-26 | 20 |  |  | DF /F /37/DFFA-FCV-290116 | Re-build tubing if any | Unknown
3 | DFF-O16 | WDF | MTN-MECH | MTN-MECH | 2100078735 | Change complete FCV-290116 | Re-build tubing if any |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2023-01-11 | 2023-05-26 | 30 |  |  | DF /F /37/DFFA-FCV-290116 | Re-build tubing if any | Unknown
3 | DFF-O16 | WDF | MTN-MECH | MTN-MECH | 2100078735 | Change complete FCV-290116 | Re-build tubing if any |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-01-11 | 2023-05-26 | 40 |  |  | DF /F /37/DFFA-FCV-290116 | Re-build tubing if any | Unknown
3 | DFF-O16 | WDF | MTN-MECH | MTN-MECH | 2100078735 | Change complete FCV-290116 | Re-build tubing if any |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-01-11 | 2023-05-26 | 50 |  |  | DF /F /37/DFFA-FCV-290116 | Re-build tubing if any | Unknown
3 | DFF-O16 | WDF | MTN-MECH | PRODTECH | 2100078735 | Change complete FCV-290116 | Re-build tubing if any |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-11 | 2023-05-26 | 60 |  |  | DF /F /37/DFFA-FCV-290116 | Re-build tubing if any | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400269302 | ILI-PIGGING-LAUNCHING_P3002_10"_DFB-GOC | Setup/de-rig rigg. equipment | PCNFAWSCSECE | PCNFAWSCSECE | 24 | 5 | Empty | 2023-09-23 | 2023-09-26 | 2023-09-21 | 2023-09-23 | 2023-10-12 | 2023-12-31 | 10 | PCNFAWSCSECE | PCNFAWSCSECE | DF /B /23/DFBY-PL-673002 | Setup/de-rig rigg. equipment | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400269302 | ILI-PIGGING-LAUNCHING_P3002_10"_DFB-GOC | Setup/de-rig rigg. equipment | PCNFAWSCSECE | PCNFAWSCSECE | 48 | 0 | Empty | 2023-09-23 | 2023-09-26 | 2023-09-23 | 2023-09-26 | 2023-10-12 | 2023-12-31 | 20 | PCNFAWSCSECE | PCNFAWSCSECE | DF /B /23/DFBY-PL-673002 | Setup/de-rig rigg. equipment | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400269302 | ILI-PIGGING-LAUNCHING_P3002_10"_DFB-GOC | Setup/de-rig rigg. equipment | PCNFAWSCSECE | PCNFAWSCSECE | 3 | 3 | Empty | 2023-09-23 | 2023-09-26 | 2023-09-21 | 2023-09-23 | 2023-10-12 | 2023-12-31 | 30 | PCNFAWSCSECE | PCNFAWSCSECE | DF /B /23/DFBY-PL-673002 | Setup/de-rig rigg. equipment | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342420 | 6M BDV LUB/MAINT IPHP - DFG | BDV LUB/INSP IPHP - DFG |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-22 | 2024-09-07 | 10 |  |  | DF /G /31/DFGA-BDV-430013 | BDV LUB/INSP IPHP - DFG | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100104500 | No flow indication on FT-350302 | Erect and dismantle scaffold | SCH | SCH | 6 | 28 | W29-W30 | 2024-09-16 | 2024-09-17 | 2024-07-12 | 2024-07-16 | 2024-01-01 | 2024-02-15 | 10 | SCH | SCH | DF /F /54/DFFA-FT-350302 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100104500 | No flow indication on FT-350302 | Erect and dismantle scaffold | SCH | SCH | 0 | 20 | W29-W30 | 2024-09-16 | 2024-09-17 | 2024-07-13 | 2024-07-21 | 2024-01-01 | 2024-02-15 | 20 | SCH | SCH | DF /F /54/DFFA-FT-350302 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100104500 | No flow indication on FT-350302 | Erect and dismantle scaffold | SCH | SCH | 4 | 0 | W29-W30 | 2024-09-16 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2024-01-01 | 2024-02-15 | 30 | SCH | SCH | DF /F /54/DFFA-FT-350302 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071663 | Replace Emerg. Light Fixture LE-1811-2-L | Set personal isolation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-07-10 | 2022-10-08 | 10 |  |  | DF /B /62/EMERGENCY-LIGHTING-DFZ-BRIDGE | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071663 | Replace Emerg. Light Fixture LE-1811-2-L | Set personal isolation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-07-10 | 2022-10-08 | 20 |  |  | DF /B /62/EMERGENCY-LIGHTING-DFZ-BRIDGE | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071663 | Replace Emerg. Light Fixture LE-1811-2-L | Set personal isolation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2022-07-10 | 2022-10-08 | 30 |  |  | DF /B /62/EMERGENCY-LIGHTING-DFZ-BRIDGE | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071663 | Replace Emerg. Light Fixture LE-1811-2-L | Set personal isolation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-07-10 | 2022-10-08 | 40 |  |  | DF /B /62/EMERGENCY-LIGHTING-DFZ-BRIDGE | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071663 | Replace Emerg. Light Fixture LE-1811-2-L | Set personal isolation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-07-10 | 2022-10-08 | 50 |  |  | DF /B /62/EMERGENCY-LIGHTING-DFZ-BRIDGE | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071663 | Replace Emerg. Light Fixture LE-1811-2-L | Set personal isolation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-07-10 | 2022-10-08 | 60 |  |  | DF /B /62/EMERGENCY-LIGHTING-DFZ-BRIDGE | Set personal isolation | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000718 | DAFTEL BEST/BKLD SYS80 -START 01JUN2018 | DAFTEL SYS69 01.03.20 31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-06-01 | 2019-06-01 | 10 |  |  | DF /C /84 | DAFTEL SYS69 01.03.20 31.12.20 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000718 | DAFTEL BEST/BKLD SYS80 -START 01JUN2018 | DAFTEL SYS69 01.03.20 31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-06-01 | 2019-06-01 | 20 |  |  | DF /C /84 | DAFTEL SYS69 01.03.20 31.12.20 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000718 | DAFTEL BEST/BKLD SYS80 -START 01JUN2018 | DAFTEL SYS69 01.03.20 31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-06-01 | 2019-06-01 | 30 |  |  | DF /C /84 | DAFTEL SYS69 01.03.20 31.12.20 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000718 | DAFTEL BEST/BKLD SYS80 -START 01JUN2018 | DAFTEL SYS69 01.03.20 31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-06-01 | 2019-06-01 | 40 |  |  | DF /C /84 | DAFTEL SYS69 01.03.20 31.12.20 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000718 | DAFTEL BEST/BKLD SYS80 -START 01JUN2018 | DAFTEL SYS69 01.03.20 31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-06-01 | 2019-06-01 | 50 |  |  | DF /C /84 | DAFTEL SYS69 01.03.20 31.12.20 | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215393 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PO CONIXI |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2022-10-14 | 2022-11-19 | 10 |  |  | DF /C /09/DFCI-B-1212 | PO CONIXI | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215393 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PO CONIXI |  |  | 10 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 20 |  |  | DF /C /09/DFCI-B-1212 | PO CONIXI | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215393 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PO CONIXI |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 30 |  |  | DF /C /09/DFCI-B-1212 | PO CONIXI | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215393 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PO CONIXI |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 40 |  |  | DF /C /09/DFCI-B-1212 | PO CONIXI | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215393 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PO CONIXI |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 50 |  |  | DF /C /09/DFCI-B-1212 | PO CONIXI | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-03 | 2024-07-03 | 2021-03-10 | 2022-01-04 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-ELEC | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-03 | 2024-07-03 | 2021-03-10 | 2022-01-04 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-LAGG | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 3 | Empty | 2024-07-03 | 2024-07-10 | 2021-02-17 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | PRODTECH | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-03 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 20 | 19 | Empty | 2024-07-03 | 2024-07-10 | 2021-07-06 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-LAGG | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 5 | Empty | 2024-07-03 | 2024-07-10 | 2021-02-18 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-ELEC | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 1 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | PRODTECH | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-03 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | PRODTECH | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-04 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 5 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-04 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-MECH | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-04 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | PRODTECH | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-06 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 14 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-06 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-ELEC | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 1 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | PRODTECH | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-07 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 150 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-LAGG | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 9 | Empty | 2024-07-03 | 2024-07-10 | 2021-07-03 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 160 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 10 | 32 | Empty | 2024-07-03 | 2024-07-10 | 2021-04-01 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 170 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 180 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | WELLSUPV | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 190 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-PIPF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 200 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-RIGG | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 5 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 210 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
4 | DAN-WI | WGN | MTN-MECH | MTN-SCAF | 2200005008 | Exchange DFFA-PSV-350102 Level 3 | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 5 | Empty | 2024-07-03 | 2024-07-10 | 2024-07-10 | 2024-07-10 | 2021-03-10 | 2022-01-04 | 220 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PSV-350102 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105400 | sandjet pump DFCI-5044 can not start | De-Isolate Pump Circuit |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2024-01-15 | 2024-02-29 | 20 |  |  | DF /C /27/DFCI-P-5044 | De-Isolate Pump Circuit | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105400 | sandjet pump DFCI-5044 can not start | De-Isolate Pump Circuit |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2024-01-15 | 2024-02-29 | 30 |  |  | DF /C /27/DFCI-P-5044 | De-Isolate Pump Circuit | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105400 | sandjet pump DFCI-5044 can not start | De-Isolate Pump Circuit |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2024-01-15 | 2024-02-29 | 40 |  |  | DF /C /27/DFCI-P-5044 | De-Isolate Pump Circuit | Unknown
3 | NOSD | WDF | PRODTECH | PRODTECH | 2100029694 | Inflow of XCV to verify leakage amount | Inflow of XCV to verify leakage amount |  |  | 4 | 0 | W39-40 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2020-04-02 | 2020-07-01 | 10 |  |  | DF /G /34/DFGA-XCV-380134 | Inflow of XCV to verify leakage amount | Unknown
A | DFG-1740 | WPM | MTN-MECH | PRODTECH | 2400306665 | 6M EMER. GENERATOR INSPECT DFGA-A-1740 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2024-02-04 | 2024-02-20 | 10 | SECE | SECE | DF /G /05/DFGA-A-1740 | ISOLATION BY PRODUCTION | Unknown
A | DFG-1740 | WPM | MTN-MECH | MTN-MECH | 2400306665 | 6M EMER. GENERATOR INSPECT DFGA-A-1740 | ISOLATION BY PRODUCTION | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-19 | 2024-02-04 | 2024-02-20 | 20 | SECE | SECE | DF /G /05/DFGA-A-1740 | ISOLATION BY PRODUCTION | Unknown
A | DFG-1740 | WPM | MTN-MECH | MTN-ELEC | 2400306665 | 6M EMER. GENERATOR INSPECT DFGA-A-1740 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2024-02-04 | 2024-02-20 | 30 | SECE | SECE | DF /G /05/DFGA-A-1740 | ISOLATION BY PRODUCTION | Unknown
A | DFG-1740 | WPM | MTN-MECH | PRODTECH | 2400306665 | 6M EMER. GENERATOR INSPECT DFGA-A-1740 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2024-02-04 | 2024-02-20 | 40 | SECE | SECE | DF /G /05/DFGA-A-1740 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263354 | 6M SDV LUB/MAINT LPSEP - DFF | SDV LUB/INSP LPSEP - DFF |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-06-29 | 2023-07-15 | 10 |  |  | DF /F /03/SDV-VALVES | SDV LUB/INSP LPSEP - DFF | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-09-15 | 2024-09-17 | 2023-02-10 | 2023-03-27 | 10 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-09-17 | 2024-09-20 | 2023-02-10 | 2023-03-27 | 20 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-09-20 | 2024-09-21 | 2023-02-10 | 2023-03-27 | 30 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-09-21 | 2024-09-22 | 2023-02-10 | 2023-03-27 | 40 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 72 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-09-22 | 2024-10-01 | 2023-02-10 | 2023-03-27 | 50 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 72 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-10-01 | 2024-10-10 | 2023-02-10 | 2023-03-27 | 60 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-10-10 | 2024-10-10 | 2023-02-10 | 2023-03-27 | 70 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-10-10 | 2024-10-11 | 2023-02-10 | 2023-03-27 | 80 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 16 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-10-11 | 2024-10-13 | 2023-02-10 | 2023-03-27 | 90 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085079 | Change put plates - 2 bar DP on E-3602 | Scaffold erection |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-10-15 | 2024-10-13 | 2024-10-15 | 2023-02-10 | 2023-03-27 | 100 |  |  | DF /F /21/DFFA-E-3602 | Scaffold erection | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284255 | PSV Exchange - DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-10-30 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33059 | DFEZ-PSV-33059 Offshore from WS Måde | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101804 | DFF-FCV-500409 on OIW monitor failed | Troubleshoot flow control valve |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-27 | 2023-12-11 | 10 |  |  | DF /F /27/DFFA-FCV-500409 | Troubleshoot flow control valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060721 | Filter S-3905 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-01-21 | 2022-04-21 | 10 |  |  | DF /F /75/DFFA-S-3905 | Isolation of system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100060721 | Filter S-3905 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-01-21 | 2022-04-21 | 20 |  |  | DF /F /75/DFFA-S-3905 | Isolation of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060721 | Filter S-3905 corroded | Isolation of system |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-01-21 | 2022-04-21 | 30 |  |  | DF /F /75/DFFA-S-3905 | Isolation of system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100060721 | Filter S-3905 corroded | Isolation of system |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-01-21 | 2022-04-21 | 40 |  |  | DF /F /75/DFFA-S-3905 | Isolation of system | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241144 | 6M CHEM DIST PANEL MAINT -DFFA-A-39704 | CHEM DIST PANEL MAINT -DFFA-A-39704 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-03-13 | 2023-04-01 | 10 |  |  | DF /F /75/DFFA-A-39704 | CHEM DIST PANEL MAINT -DFFA-A-39704 | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100079687 | Change of defect battery in batterybank | Change of defect bat in batterybank LAUS |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-01-29 | 2023-06-13 | 9 |  |  | DF /G /06/DFGA-AE-1952B | Change of defect bat in batterybank LAUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100079687 | Change of defect battery in batterybank | Change of defect bat in batterybank LAUS |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-01-29 | 2023-06-13 | 10 |  |  | DF /G /06/DFGA-AE-1952B | Change of defect bat in batterybank LAUS | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100079687 | Change of defect battery in batterybank | Change of defect bat in batterybank LAUS |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-01-29 | 2023-06-13 | 11 |  |  | DF /G /06/DFGA-AE-1952B | Change of defect bat in batterybank LAUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100079687 | Change of defect battery in batterybank | Change of defect bat in batterybank LAUS |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-01-29 | 2023-06-13 | 20 |  |  | DF /G /06/DFGA-AE-1952B | Change of defect bat in batterybank LAUS | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059139 | Fault finding on lights DFG 1853 | Isolate light circuit |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-02-12 | 2022-07-12 | 10 |  |  | DF /G /61/DFGA-LP-1853-08 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059139 | Fault finding on lights DFG 1853 | Isolate light circuit |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-02-12 | 2022-07-12 | 20 |  |  | DF /G /61/DFGA-LP-1853-08 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059139 | Fault finding on lights DFG 1853 | Isolate light circuit |  |  | 6 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-03 | 2022-02-12 | 2022-07-12 | 30 |  |  | DF /G /61/DFGA-LP-1853-08 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059139 | Fault finding on lights DFG 1853 | Isolate light circuit |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-12 | 2022-07-12 | 40 |  |  | DF /G /61/DFGA-LP-1853-08 | Isolate light circuit | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059139 | Fault finding on lights DFG 1853 | Isolate light circuit |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-12 | 2022-07-12 | 50 |  |  | DF /G /61/DFGA-LP-1853-08 | Isolate light circuit | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235023 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-03-12 | 1 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235023 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-03-12 | 9 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235023 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-18 | 2023-03-02 | 2023-03-12 | 10 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400235023 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-21 | 2023-03-02 | 2023-03-12 | 12 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235023 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2023-03-02 | 2023-03-12 | 14 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024623 | DFFA-LG-440001 Replace of vent and drain | Replace of valves on level glass | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 10 | AWSC | AWSC | DF /F /32/DFFA-V-4401 | Replace of valves on level glass | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024623 | DFFA-LG-440001 Replace of vent and drain | Replace of valves on level glass | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 20 | AWSC | AWSC | DF /F /32/DFFA-V-4401 | Replace of valves on level glass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024623 | DFFA-LG-440001 Replace of vent and drain | Replace of valves on level glass | AWSC | AWSC | 7 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2019-06-30 | 2019-09-28 | 30 | AWSC | AWSC | DF /F /32/DFFA-V-4401 | Replace of valves on level glass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024623 | DFFA-LG-440001 Replace of vent and drain | Replace of valves on level glass | AWSC | AWSC | 7 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-05 | 2019-06-30 | 2019-09-28 | 40 | AWSC | AWSC | DF /F /32/DFFA-V-4401 | Replace of valves on level glass | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024623 | DFFA-LG-440001 Replace of vent and drain | Replace of valves on level glass | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2019-06-30 | 2019-09-28 | 50 | AWSC | AWSC | DF /F /32/DFFA-V-4401 | Replace of valves on level glass | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-28 | 2023-09-10 | 10 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-RIGG | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-28 | 2023-09-10 | 20 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-28 | 2023-09-10 | 30 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-RIGG | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-28 | 2023-09-10 | 40 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-04-28 | 2023-09-10 | 50 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-04-28 | 2023-09-10 | 60 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-28 | 2023-09-10 | 70 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-28 | 2023-09-10 | 80 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100087263 | DFC test sep flare HCV external leak | Isolate HCV-400037 (freeze plug) | PCNF | PCNF | 15 | 16 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-04-28 | 2023-09-10 | 90 | PCNF | PCNF | DF /C /11/DFCI-HCV-400037 | Isolate HCV-400037 (freeze plug) | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100094030 | DFA 400barHydr pump press problem | Mechanical Scope |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2023-08-08 | 2023-12-21 | 10 |  |  | DF /A /07/DFAA-P-3121 | Mechanical Scope | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094030 | DFA 400barHydr pump press problem | Mechanical Scope |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2023-08-08 | 2023-12-21 | 20 |  |  | DF /A /07/DFAA-P-3121 | Mechanical Scope | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100094030 | DFA 400barHydr pump press problem | Mechanical Scope |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2023-08-08 | 2023-12-21 | 30 |  |  | DF /A /07/DFAA-P-3121 | Mechanical Scope | Unknown
4 | DFG-3590 | WDF | MTN-MECH | VEN-INST | 2100104716 | Faulty power supply for B&K panel | Replace power supply for B&K panel |  |  | 6 | 6 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-02-01 | 2026-07-20 | 10 |  |  | DF /G /54/DFGA-A-3590 | Replace power supply for B&K panel | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000701 | GE SYST 61 | GE SYST 61 *01.01.18 TIL 31.12.18* |  |  | 0 | 0 | Empty | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2018-12-31 | 2018-12-31 | 10 |  |  | DF | GE SYST 61 *01.01.18 TIL 31.12.18* | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000701 | GE SYST 61 | GE SYST 61 *01.01.18 TIL 31.12.18* |  |  | 0 | 0 | Empty | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2018-12-31 | 2018-12-31 | 20 |  |  | DF | GE SYST 61 *01.01.18 TIL 31.12.18* | Unknown
A | DFF-1620 | WPM | MTN-TURB | PRODTECH | 2400230571 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620, | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 5 | 0 | W29-30 | 2023-07-17 | 2023-07-26 | 2023-07-17 | 2023-07-18 | 2023-01-27 | 2023-02-26 | 10 | SCHSECE | SCHSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-TURB | 2400230571 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620, | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 32 | 32 | W29-30 | 2023-07-17 | 2023-07-26 | 2023-07-18 | 2023-07-22 | 2023-01-27 | 2023-02-26 | 20 | SCHSECE | SCHSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-MECH | 2400230571 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620, | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 18 | 33 | W29-30 | 2023-07-17 | 2023-07-26 | 2023-07-22 | 2023-07-24 | 2023-01-27 | 2023-02-26 | 30 | SCHSECE | SCHSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | VEN-INST | 2400230571 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620, | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 18 | 0 | W29-30 | 2023-07-17 | 2023-07-26 | 2023-07-24 | 2023-07-25 | 2023-01-27 | 2023-02-26 | 40 | SCHSECE | SCHSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | PRODTECH | 2400230571 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620, | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 5 | 0 | W29-30 | 2023-07-17 | 2023-07-26 | 2023-07-25 | 2023-07-26 | 2023-01-27 | 2023-02-26 | 50 | SCHSECE | SCHSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-TURB | 2400230571 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620, | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 0 | 0 | W29-30 | 2023-07-17 | 2023-07-26 | 2023-07-26 | 2023-07-26 | 2023-01-27 | 2023-02-26 | 60 | SCHSECE | SCHSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-31 | 2021-02-07 | 2021-03-19 | 10 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-31 | 2024-08-01 | 2021-02-07 | 2021-03-19 | 20 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-01 | 2021-02-07 | 2021-03-19 | 30 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-02 | 2021-02-07 | 2021-03-19 | 40 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-03 | 2021-02-07 | 2021-03-19 | 50 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-03 | 2021-02-07 | 2021-03-19 | 60 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-04 | 2021-02-07 | 2021-03-19 | 70 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-06 | 2021-02-07 | 2021-03-19 | 80 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-06 | 2024-08-07 | 2021-02-07 | 2021-03-19 | 90 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-07 | 2021-02-07 | 2021-03-19 | 100 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-08 | 2021-02-07 | 2021-03-19 | 110 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2021-02-07 | 2021-03-19 | 120 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044850 | DFG LCV-440410 Dårlig integritet | Isolate LCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-10 | 2021-02-07 | 2021-03-19 | 130 |  |  | DF /G /32/DFGA-LCV-440410 | Isolate LCV | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 3 | 0 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 10 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 20 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 5 | 5 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 30 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 1 | 0 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 40 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 20 | 20 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 50 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 0 | 0 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 60 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 0 | 0 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 70 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100062056 | FCV 35791 Booster relay Replacment. | Isolate FCV-35791 | PCNFAWSC | PCNFAWSC | 0 | 0 | W27-W28 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2022-02-18 | 2022-05-19 | 80 | PCNFAWSC | PCNFAWSC | DF /B /55/DFBA-FCV-35791 | Isolate FCV-35791 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100112082 | DFBA-PIT-45207 isolation valve stucked | DFBA-PIT-45207 isolation valve stucked |  |  | 0 | 0 | Empty | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-06-14 | 2024-10-27 | 10 |  |  | DF /B /37/DFBA-PIT-45207 | DFBA-PIT-45207 isolation valve stucked | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100112082 | DFBA-PIT-45207 isolation valve stucked | DFBA-PIT-45207 isolation valve stucked |  |  | 1 | 0 | Empty | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-06-14 | 2024-10-27 | 20 |  |  | DF /B /37/DFBA-PIT-45207 | DFBA-PIT-45207 isolation valve stucked | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100112082 | DFBA-PIT-45207 isolation valve stucked | DFBA-PIT-45207 isolation valve stucked |  |  | 1 | 0 | Empty | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-06-14 | 2024-10-27 | 30 |  |  | DF /B /37/DFBA-PIT-45207 | DFBA-PIT-45207 isolation valve stucked | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100112082 | DFBA-PIT-45207 isolation valve stucked | DFBA-PIT-45207 isolation valve stucked |  |  | 1 | 0 | Empty | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-06-14 | 2024-10-27 | 40 |  |  | DF /B /37/DFBA-PIT-45207 | DFBA-PIT-45207 isolation valve stucked | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100052527 | DFC export meter Slave 2 | Inspect strainer, see LT |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2021-07-27 | 2021-09-05 | 10 |  |  | DF /C /26/DFCI-FE-37125 | Inspect strainer, see LT | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100052527 | DFC export meter Slave 2 | Inspect strainer, see LT |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-18 | 2021-07-27 | 2021-09-05 | 20 |  |  | DF /C /26/DFCI-FE-37125 | Inspect strainer, see LT | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100052527 | DFC export meter Slave 2 | Inspect strainer, see LT |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2021-07-27 | 2021-09-05 | 21 |  |  | DF /C /26/DFCI-FE-37125 | Inspect strainer, see LT | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100052527 | DFC export meter Slave 2 | Inspect strainer, see LT |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2021-07-27 | 2021-09-05 | 30 |  |  | DF /C /26/DFCI-FE-37125 | Inspect strainer, see LT | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235699 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235699 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 23 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235699 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-29 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235699 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF05-BA001 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-TELE | MTN-INST | 2100106041 | Wind sensor in DFA crane periodic error | Wind sensor in DFA crane periodic error |  |  | 0 | 0 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2027-01-06 | 10 |  |  | DF /A /78/DFAA-X-6102 | Wind sensor in DFA crane periodic error | Unknown
4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100106041 | Wind sensor in DFA crane periodic error | Wind sensor in DFA crane periodic error |  |  | 10 | 0 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-20 | 2024-07-23 | 2024-07-20 | 2027-01-06 | 20 |  |  | DF /A /78/DFAA-X-6102 | Wind sensor in DFA crane periodic error | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298225 | 4Y SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-10-29 | 2024-01-10 | 10 | SECE | SECE | DF /B /54/DFBA-P-3501 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400298225 | 4Y SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2023-10-29 | 2024-01-10 | 20 | SECE | SECE | DF /B /54/DFBA-P-3501 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298225 | 4Y SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SECE | SECE | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2023-10-29 | 2024-01-10 | 30 | SECE | SECE | DF /B /54/DFBA-P-3501 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298225 | 4Y SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-10-29 | 2024-01-10 | 40 | SECE | SECE | DF /B /54/DFBA-P-3501 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298225 | 4Y SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2023-10-29 | 2024-01-10 | 50 | SECE | SECE | DF /B /54/DFBA-P-3501 | SW BOOSTER PUMP MAINT DFBA-P-3501/02 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-05-21 | 2024-05-21 | 2024-10-12 | 2024-12-31 | 22 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-05-21 | 2024-05-21 | 2024-10-12 | 2024-12-31 | 23 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 25 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 26 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284290 | PSV Calibration - DFFA-PSV-390520 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-390520 | Remove PSV and Install blinds | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 52.29999999999999715782905694 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-01 | 2025-01-05 | 2018-07-06 | 2018-07-26 | 5 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 52.29999999999999715782905694 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-05 | 2025-01-09 | 2018-07-06 | 2018-07-26 | 10 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-09 | 2025-01-10 | 2018-07-06 | 2018-07-26 | 20 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | PRODTECH | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-10 | 2025-01-10 | 2018-07-06 | 2018-07-26 | 30 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-10 | 2025-01-11 | 2018-07-06 | 2018-07-26 | 40 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-11 | 2025-01-12 | 2018-07-06 | 2018-07-26 | 50 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-12 | 2025-01-13 | 2018-07-06 | 2018-07-26 | 55 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-13 | 2025-01-14 | 2018-07-06 | 2018-07-26 | 60 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | PRODTECH | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-14 | 2025-01-14 | 2018-07-06 | 2018-07-26 | 70 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PAIN | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-14 | 2025-01-15 | 2018-07-06 | 2018-07-26 | 75 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | QAQCPAIN | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-15 | 2025-01-15 | 2018-07-06 | 2018-07-26 | 76 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-15 | 2025-01-16 | 2018-07-06 | 2018-07-26 | 80 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-16 | 2025-01-18 | 2018-07-06 | 2018-07-26 | 90 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-PIPF | 2100025039 | CMAT:Demol of flare valve, level glass a | L3 Erection of scaffolding | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2025-01-01 | 2025-01-19 | 2025-01-18 | 2025-01-19 | 2018-07-06 | 2018-07-26 | 100 | AWSC | AWSC | DF /F /32/DFFA-LG-340126 | L3 Erection of scaffolding | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329515 | 1Y BUNKER HOSES/REELS MAINT - DAN-F | BUNKER HOSES/REELS MAINT - DAN-F |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2024-05-11 | 2024-06-16 | 10 |  |  | DF /C /71/DFCI-HOSB-5790 | BUNKER HOSES/REELS MAINT - DAN-F | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 6 | 6 | W32-33 | 2024-07-30 | 2024-07-31 | 2020-08-05 | 2020-11-12 | 2019-08-28 | 2020-08-22 | 9 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 1 | 1 | W32-33 | 2024-07-30 | 2024-07-31 | 2020-08-05 | 2020-11-12 | 2019-08-28 | 2020-08-22 | 10 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 12 | 12 | W32-33 | 2024-07-30 | 2024-07-31 | 2020-08-05 | 2020-11-12 | 2019-08-28 | 2020-08-22 | 20 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 1 | 1 | W32-33 | 2024-07-30 | 2024-07-31 | 2020-08-05 | 2020-11-12 | 2019-08-28 | 2020-08-22 | 21 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 2 | 2 | W32-33 | 2024-07-30 | 2024-07-31 | 2020-08-05 | 2020-11-12 | 2019-08-28 | 2020-08-22 | 30 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 1 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2019-08-28 | 2020-08-22 | 40 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 20 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2019-08-28 | 2020-08-22 | 50 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 5 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2019-08-28 | 2020-08-22 | 51 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 1 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2019-08-28 | 2020-08-22 | 60 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 1 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2019-08-28 | 2020-08-22 | 70 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 0 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2019-08-28 | 2020-08-22 | 80 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-INSP | 2100022407 | DFE/78: Overhaul door for engine room | Preparation and permit | PCNF | PCNF | 0 | 0 | W32-33 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2019-08-28 | 2020-08-22 | 90 | PCNF | PCNF | DF /E /78/DFEZ-X-6150 | Preparation and permit | Unknown
A | DFC-FUEL | WPM | MTN-MECH | PRODTECH | 2400215979 | 1Y SDV LUBE/FUNC TEST FUEL - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2022-11-04 | 2022-12-04 | 10 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFC-FUEL | WPM | MTN-MECH | MTN-MECH | 2400215979 | 1Y SDV LUBE/FUNC TEST FUEL - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 9 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2022-11-04 | 2022-12-04 | 20 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFC-FUEL | WPM | MTN-MECH | PRODTECH | 2400215979 | 1Y SDV LUBE/FUNC TEST FUEL - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2022-11-04 | 2022-12-04 | 30 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329518 | 6M DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG |  |  | 2 | 0 | Empty | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-21 | 10 |  |  | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339037 | DFA_1Y_22000 INT STRUCT INSP - GVI | DFA_1Y_22000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /86/EL_22000 (CELLAR DECK) | DFA_1Y_22000 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 2 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-17 | 2024-09-17 | 2024-06-17 | 2024-10-30 | 10 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 2 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-17 | 2024-09-18 | 2024-06-17 | 2024-10-30 | 50 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 8 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-18 | 2024-09-20 | 2024-06-17 | 2024-10-30 | 60 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 8 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-18 | 2024-09-20 | 2024-06-17 | 2024-10-30 | 70 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 3 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-20 | 2024-09-20 | 2024-06-17 | 2024-10-30 | 80 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 5 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-20 | 2024-09-22 | 2024-06-17 | 2024-10-30 | 90 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 5 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-20 | 2024-09-22 | 2024-06-17 | 2024-10-30 | 100 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 3 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2024-06-17 | 2024-10-30 | 110 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 2 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2024-06-17 | 2024-10-30 | 120 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 2 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2024-06-17 | 2024-10-30 | 130 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112090 | ESDV-33086 hydr. leak from actuator | Isolate ESDV |  |  | 2 | 0 | Empty | 2024-09-17 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2024-06-17 | 2024-10-30 | 140 |  |  | DF /B /10/DFBA-ESDV-33086 | Isolate ESDV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328721 | 1Y FIRE DOORS TEST - DFE | FIRE DOORS TEST- DFE | SECE | SECE | 9 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-06-05 | 10 | SECE | SECE | DF /E /02/FIRE-DOORS | FIRE DOORS TEST- DFE | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-SCAF | 2100114785 | DFFA-UV-124606 in fault | Build scaffold | PCNFSECE | PCNFSECE | 6 | 6 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-19 | 2024-08-19 | 2024-06-19 | 2024-08-03 | 10 | PCNFSECE | PCNFSECE | DF /F /03/DFFA-UV-124606 | Build scaffold | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100114785 | DFFA-UV-124606 in fault | Build scaffold | PCNFSECE | PCNFSECE | 6 | 50 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-19 | 2024-08-21 | 2024-06-19 | 2024-08-03 | 20 | PCNFSECE | PCNFSECE | DF /F /03/DFFA-UV-124606 | Build scaffold | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-SCAF | 2100114785 | DFFA-UV-124606 in fault | Build scaffold | PCNFSECE | PCNFSECE | 2 | 2 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-19 | 2024-08-19 | 2024-06-19 | 2024-08-03 | 30 | PCNFSECE | PCNFSECE | DF /F /03/DFFA-UV-124606 | Build scaffold | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-20 | 2024-05-20 | 2023-10-05 | 2024-02-17 | 10 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-20 | 2024-05-21 | 2023-10-05 | 2024-02-17 | 20 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-21 | 2024-05-22 | 2023-10-05 | 2024-02-17 | 30 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-22 | 2024-05-23 | 2023-10-05 | 2024-02-17 | 40 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-23 | 2024-05-24 | 2023-10-05 | 2024-02-17 | 50 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-24 | 2024-05-25 | 2023-10-05 | 2024-02-17 | 60 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096533 | No N2 pressure on accumulator bottle | Rigging assist. Rig in/out |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-25 | 2024-05-25 | 2024-05-25 | 2023-10-05 | 2024-02-17 | 70 |  |  | DF /F /07/DFFA-V-3102B | Rigging assist. Rig in/out | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235651 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R16 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R16B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235651 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R16 | ISOLATION ELECTRICAL | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R16B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235651 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R16 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R16B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235651 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R16 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R16B | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 10 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 20 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 30 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 6 | 19 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 40 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 2 | 19 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 60 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 70 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 80 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 90 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 8 | 5 | W25-W26 | 2024-07-01 | 2024-07-01 | 2022-06-20 | 2023-06-01 | 2021-09-18 | 2021-10-28 | 110 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 0 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 333 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055110 | DFF HP Hydro cyclon XCV reject failure | Isolate pneumatic and controls | PCNF | PCNF | 0 | 0 | W25-W26 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2021-09-18 | 2021-10-28 | 334 | PCNF | PCNF | DF /F /27/DFFA-XCV-500761 | Isolate pneumatic and controls | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400241130 | 2Y INSTR AIR SYSTEM MAINT - DFCM-A-5401 | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | SECE | SECE | 4 | 4 | W19-W20 | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2023-02-11 | 2023-03-29 | 10 | SECE | SECE | DF /C /07/INSTRUMENT-AIR-SYSTEM | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400241130 | 2Y INSTR AIR SYSTEM MAINT - DFCM-A-5401 | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | SECE | SECE | 13 | 13 | W19-W20 | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-19 | 2023-02-11 | 2023-03-29 | 20 | SECE | SECE | DF /C /07/INSTRUMENT-AIR-SYSTEM | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241130 | 2Y INSTR AIR SYSTEM MAINT - DFCM-A-5401 | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | SECE | SECE | 12 | 12 | W19-W20 | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-22 | 2023-02-11 | 2023-03-29 | 30 | SECE | SECE | DF /C /07/INSTRUMENT-AIR-SYSTEM | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300000750 | DAF Switchboard materials 2019 | DAF Switchboard materials 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /F | DAF Switchboard materials 2019 | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400281913 | 6M SW STRAINER PKG MAINT-DFFA-A-5310 | SEAWAT STRAINER PKG MAINT-DFFA-A-5310 |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-09-22 | 2023-10-17 | 10 |  |  | DF /F /51/DFFA-A-5310 | SEAWAT STRAINER PKG MAINT-DFFA-A-5310 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235049 | 2Y SEAWATER FILTER PKG MAINT-DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-13 | 2023-03-09 | 20 |  |  | DF /G /51/DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235049 | 2Y SEAWATER FILTER PKG MAINT-DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-13 | 2023-03-09 | 30 |  |  | DF /G /51/DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100086712 | DFB/78 Replace all outside hoses | Replace all outside hoses |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2023-08-30 | 2026-02-15 | 10 |  |  | DF /B /78/DFBA-X-6102 | Replace all outside hoses | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100086712 | DFB/78 Replace all outside hoses | Replace all outside hoses |  |  | 24 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-08-04 | 2023-08-30 | 2026-02-15 | 20 |  |  | DF /B /78/DFBA-X-6102 | Replace all outside hoses | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100086712 | DFB/78 Replace all outside hoses | Replace all outside hoses |  |  | 24 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-08-04 | 2023-08-30 | 2026-02-15 | 30 |  |  | DF /B /78/DFBA-X-6102 | Replace all outside hoses | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100086712 | DFB/78 Replace all outside hoses | Replace all outside hoses |  |  | 8 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2023-08-30 | 2026-02-15 | 40 |  |  | DF /B /78/DFBA-X-6102 | Replace all outside hoses | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100086712 | DFB/78 Replace all outside hoses | Replace all outside hoses |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-08-30 | 2026-02-15 | 50 |  |  | DF /B /78/DFBA-X-6102 | Replace all outside hoses | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100086712 | DFB/78 Replace all outside hoses | Replace all outside hoses |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2023-08-30 | 2026-02-15 | 60 |  |  | DF /B /78/DFBA-X-6102 | Replace all outside hoses | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322640 | 6M POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-04-29 | 2024-05-18 | 10 |  |  | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 3 | 1 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 10 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 3 | 4 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 20 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 2 | 1 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 30 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 16 | 140 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 40 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 30 | 30 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-10-15 | 2023-10-24 | 2023-01-26 | 2023-06-10 | 50 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 12 | 15 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-10-15 | 2023-10-24 | 2023-01-26 | 2023-06-10 | 60 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 6 | 20 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 65 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 3 | 0 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 70 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 9 | 9 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-11-23 | 2023-11-23 | 2023-01-26 | 2023-06-10 | 80 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100079500 | DFG: Oil leak from Hydraulic oil cooler | Fill up cooling water to correct level |  |  | 10 | 10 | W47-48 | 2023-10-14 | 2023-11-23 | 2023-10-24 | 2023-10-24 | 2023-01-26 | 2023-06-10 | 90 |  |  | DF /G /78/DFGA-A-6140 | Fill up cooling water to correct level | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 2 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 2 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 6 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 1 | 1 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 25 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 27 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 5 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 4 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284226 | PSV Calibration - DFAA-PSV-392223 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /A /75/DFAA-PSV-392223 | Remove PSV and Install blinds | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 26 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-08-22 | 2024-08-28 | 2023-09-14 | 2024-01-27 | 30 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-08-28 | 2024-08-29 | 2023-09-14 | 2024-01-27 | 40 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-08-29 | 2024-08-29 | 2023-09-14 | 2024-01-27 | 50 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-08-29 | 2024-08-31 | 2023-09-14 | 2024-01-27 | 60 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-08-31 | 2024-09-01 | 2023-09-14 | 2024-01-27 | 70 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-09-01 | 2024-09-02 | 2023-09-14 | 2024-01-27 | 100 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-09-02 | 2024-09-02 | 2023-09-14 | 2024-01-27 | 110 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-09-02 | 2024-09-03 | 2023-09-14 | 2024-01-27 | 115 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-09-03 | 2024-09-03 | 2023-09-14 | 2024-01-27 | 116 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100096129 | PSV Calibration - DFCI-PSV-57120 Intern | Check PSV flanges & alignment | SECE | SECE | 13 | 0 | W33-W34 | 2024-08-22 | 2024-09-06 | 2024-09-03 | 2024-09-06 | 2023-09-14 | 2024-01-27 | 120 | SECE | SECE | DF /C /70/DFCI-PSV-57120 | Check PSV flanges & alignment | Unknown
4 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200003749 | Replace Socket Outlet 230 volt | Set isolation |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2020-06-23 | 2020-11-20 | 10 |  |  | DF /A /61 | Set isolation | Unknown
4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200003749 | Replace Socket Outlet 230 volt | Set isolation |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2020-06-23 | 2020-11-20 | 20 |  |  | DF /A /61 | Set isolation | Unknown
4 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200003749 | Replace Socket Outlet 230 volt | Set isolation |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2020-06-23 | 2020-11-20 | 30 |  |  | DF /A /61 | Set isolation | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 12 | 6 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 10 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 3 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 20 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 8 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 25 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 10 | 6 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 30 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 6 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 40 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 1 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 50 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 3 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 60 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 8 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 65 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 10 | 9 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 70 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 6 | 1 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 80 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 1 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 90 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 3 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-21 | 2023-11-21 | 2021-05-21 | 2022-01-16 | 100 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 8 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 105 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 10 | 6 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 110 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 6 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 120 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 1 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 130 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 3 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 140 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 8 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 145 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 10 | 6 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 150 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 6 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 160 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 1 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 170 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 3 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 180 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 8 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 185 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 10 | 6 | W47-48 | 2023-11-20 | 2023-11-21 | 2022-10-04 | 2023-11-19 | 2021-05-21 | 2022-01-16 | 190 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 6 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 200 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 1 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 210 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045003 | Wrong material in PRV for deluge A-0340 | Production deisolation w leak test | SCH | SCH | 0 | 0 | W47-48 | 2023-11-20 | 2023-11-21 | 2023-11-20 | 2023-11-20 | 2021-05-21 | 2022-01-16 | 220 | SCH | SCH | DF /G /01/DFGA-A-0340 | Production deisolation w leak test | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100042379 | Replace socketoutlet DFFA-SO-0394 | Isolate accordingly |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-03-30 | 2021-11-25 | 10 |  |  | DF /F /61/DFFA-DP-1802A-2-F10 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100042379 | Replace socketoutlet DFFA-SO-0394 | Isolate accordingly |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-03-30 | 2021-11-25 | 20 |  |  | DF /F /61/DFFA-DP-1802A-2-F10 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100042379 | Replace socketoutlet DFFA-SO-0394 | Isolate accordingly |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-03-30 | 2021-11-25 | 30 |  |  | DF /F /61/DFFA-DP-1802A-2-F10 | Isolate accordingly | Unknown
4 | D-FLARE | WGN | MTN-TELE | VEN-ELEC | 2200004704 | DFGA-CP-0247 HIPPS AI Card replacement | PO Yokogawa | PCNFAWSC | PCNFAWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-11-24 | 2021-04-23 | 10 | PCNFAWSC | PCNFAWSC | DF /G /03/DFGA-CP-0247 | PO Yokogawa | Unknown
4 | D-FLARE | WGN | MTN-TELE | MTN-ELEC | 2200004704 | DFGA-CP-0247 HIPPS AI Card replacement | PO Yokogawa | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-11-24 | 2021-04-23 | 20 | PCNFAWSC | PCNFAWSC | DF /G /03/DFGA-CP-0247 | PO Yokogawa | Unknown
4 | D-FLARE | WGN | MTN-TELE | MTN-ELEC | 2200004704 | DFGA-CP-0247 HIPPS AI Card replacement | PO Yokogawa | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-11-24 | 2021-04-23 | 30 | PCNFAWSC | PCNFAWSC | DF /G /03/DFGA-CP-0247 | PO Yokogawa | Unknown
4 | D-FLARE | WGN | MTN-TELE | MTN-TELE | 2200004704 | DFGA-CP-0247 HIPPS AI Card replacement | PO Yokogawa | PCNFAWSC | PCNFAWSC | 6 | 5 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-11-24 | 2021-04-23 | 40 | PCNFAWSC | PCNFAWSC | DF /G /03/DFGA-CP-0247 | PO Yokogawa | Unknown
4 | D-FLARE | WGN | MTN-TELE | MTN-INST | 2200004704 | DFGA-CP-0247 HIPPS AI Card replacement | PO Yokogawa | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-11-24 | 2021-04-23 | 50 | PCNFAWSC | PCNFAWSC | DF /G /03/DFGA-CP-0247 | PO Yokogawa | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 24 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-17 | 2024-07-20 | 2024-10-30 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 5 | 5 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 2 | 2 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2024-10-30 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 12 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 80 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-25 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 90 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 100 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 110 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400291845 | PSV Calibration - DFFA-PSV-400011A | Remove PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 120 | AWSC | AWSC | DF /F /27/DFFA-PSV-400011A | Remove PSV | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400344386 | PIGGING, P3010 12" DFF-DAD WI 2W | P3010_DFF-DAD | AWSC | AWSC | 4 | 0 | Empty | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-20 | 2024-09-26 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673010 | P3010_DFF-DAD | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235687 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235687 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 19 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235687 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235687 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235687 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF05 | ISOLATION ELECTRICAL | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-05-30 | 2023-08-26 | 50 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF05-BA001 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-07-29 | 2024-07-29 | 2020-09-04 | 2020-12-03 | 10 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-07-29 | 2024-07-30 | 2020-09-04 | 2020-12-03 | 20 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-07-29 | 2024-07-31 | 2020-09-04 | 2020-12-03 | 30 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-07-31 | 2024-07-31 | 2020-09-04 | 2020-12-03 | 40 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-09-04 | 2024-09-04 | 2020-09-04 | 2020-12-03 | 50 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-09-04 | 2024-09-05 | 2020-09-04 | 2020-12-03 | 60 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036421 | LG M-fold DDB-HPLP-29006 to DFF34 leakin | Production Assistance if necessary |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-09-06 | 2024-09-05 | 2024-09-06 | 2020-09-04 | 2020-12-03 | 70 |  |  | DF /F /37/DFFA-FCV-290134 | Production Assistance if necessary | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2021-04-28 | 2021-09-25 | 10 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2021-04-28 | 2021-09-25 | 20 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2021-04-28 | 2021-09-25 | 30 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2021-04-28 | 2021-09-25 | 40 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2021-04-28 | 2021-09-25 | 50 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2021-04-28 | 2021-09-25 | 60 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100045354 | HCV-03017 internal leak us XCV-0328 Delu | Prepare Rigging equip. | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2021-04-28 | 2021-09-25 | 70 | AWSC | AWSC | DF /B /01/DFBA-HCV-03017 | Prepare Rigging equip. | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100111608 | DFB/78 Buzzer and aux slowly function | Isolate/De-isolate crane |  |  | 1 | 0 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-03 | 2024-06-13 | 2024-10-26 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolate/De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100111608 | DFB/78 Buzzer and aux slowly function | Isolate/De-isolate crane |  |  | 5 | 0 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-04 | 2024-06-13 | 2024-10-26 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolate/De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100111608 | DFB/78 Buzzer and aux slowly function | Isolate/De-isolate crane |  |  | 3 | 0 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-04 | 2024-07-05 | 2024-06-13 | 2024-10-26 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolate/De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100111608 | DFB/78 Buzzer and aux slowly function | Isolate/De-isolate crane |  |  | 3 | 0 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-04 | 2024-07-05 | 2024-06-13 | 2024-10-26 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolate/De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100111608 | DFB/78 Buzzer and aux slowly function | Isolate/De-isolate crane |  |  | 8 | 0 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-04 | 2024-07-05 | 2024-06-13 | 2024-10-26 | 50 |  |  | DF /B /78/DFBA-X-6102 | Isolate/De-isolate crane | Unknown
3 | DFC-TSEP | WDF | MTN-INST | PRODTECH | 2100055900 | Replace hyd sup/ret hoses with inst tubi | Replace hoses with 904L tubing |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-10-16 | 2022-01-14 | 10 |  |  | DF /C /11/DFCI-ESDV-34009 | Replace hoses with 904L tubing | Unknown
3 | DFC-TSEP | WDF | MTN-INST | MTN-INST | 2100055900 | Replace hyd sup/ret hoses with inst tubi | Replace hoses with 904L tubing |  |  | 8 | 0 | BL-TEAM | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2021-10-16 | 2022-01-14 | 20 |  |  | DF /C /11/DFCI-ESDV-34009 | Replace hoses with 904L tubing | Unknown
3 | DFC-TSEP | WDF | MTN-INST | PRODTECH | 2100055900 | Replace hyd sup/ret hoses with inst tubi | Replace hoses with 904L tubing |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-10-16 | 2022-01-14 | 30 |  |  | DF /C /11/DFCI-ESDV-34009 | Replace hoses with 904L tubing | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-MECH | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 207 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2024-10-01 | 2024-11-21 | 2024-10-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-SCAF | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 264 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2024-11-21 | 2025-01-26 | 2024-10-01 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-ELEC | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 127 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-01-26 | 2025-02-27 | 2024-10-01 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-RIGG | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-02-27 | 2025-02-27 | 2024-10-01 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-PIPF | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-02-27 | 2025-02-27 | 2024-10-01 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-ROPE | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-02-27 | 2025-02-27 | 2024-10-01 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-INST | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-02-27 | 2025-02-27 | 2024-10-01 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-PAIN | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 107 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-02-27 | 2025-03-10 | 2024-10-01 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | PRODTECH | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 30 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-03-10 | 2025-03-18 | 2024-10-01 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | VEN-INSP | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-03-18 | 2025-03-19 | 2024-10-01 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | MTN-INST | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 36 | 12 | Empty | 2024-10-01 | 2025-03-28 | 2025-03-19 | 2025-03-28 | 2024-10-01 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
A | DFE-OIL | WPM | VEN-INSP | VEN-INSP | 2400291981 | PVI Major - DFEZ-V-5012 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-01 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2024-10-01 | 2024-12-31 | 120 | AWSCSECE | AWSCSECE | DF /E /28/DFEZ-V-5012 | Assist FMC with instrumentation tasks | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053472 | Replace lighting DFA -1801-5-L1A | Replace Lighting |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 10 |  |  | DF /A /62 | Replace Lighting | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053472 | Replace lighting DFA -1801-5-L1A | Replace Lighting |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 20 |  |  | DF /A /62 | Replace Lighting | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053472 | Replace lighting DFA -1801-5-L1A | Replace Lighting |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-31 | 2022-03-30 | 30 |  |  | DF /A /62 | Replace Lighting | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100034326 | DFA/78: paint slewing bearing | build scaffolding |  |  | 1 | 0 | Empty | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2024-03-28 | 2020-09-22 | 2021-02-19 | 10 |  |  | DF /A /78/DFAA-X-6102 | build scaffolding | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100034326 | DFA/78: paint slewing bearing | build scaffolding |  |  | 8 | 0 | Empty | 2024-03-28 | 2024-04-02 | 2024-03-28 | 2024-03-30 | 2020-09-22 | 2021-02-19 | 20 |  |  | DF /A /78/DFAA-X-6102 | build scaffolding | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100034326 | DFA/78: paint slewing bearing | build scaffolding |  |  | 24 | 0 | Empty | 2024-03-28 | 2024-04-02 | 2024-03-30 | 2024-04-01 | 2020-09-22 | 2021-02-19 | 30 |  |  | DF /A /78/DFAA-X-6102 | build scaffolding | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100034326 | DFA/78: paint slewing bearing | build scaffolding |  |  | 1 | 0 | Empty | 2024-03-28 | 2024-04-02 | 2024-04-01 | 2024-04-02 | 2020-09-22 | 2021-02-19 | 40 |  |  | DF /A /78/DFAA-X-6102 | build scaffolding | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018127 | Replace Feeder protection 1841-M103 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M103-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018127 | Replace Feeder protection 1841-M103 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M103-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018127 | Replace Feeder protection 1841-M103 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M103-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018127 | Replace Feeder protection 1841-M103 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M103-02 | New mat num | Unknown
3 | DFA-OIL | WDF | MTN-INST | PRODTECH | 2100093856 | DFA-18 LG Ft external leaking | Transmitter isolation |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2023-12-25 | 10 |  |  | DF /A /37/DFAA-FT-45054 | Transmitter isolation | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100093856 | DFA-18 LG Ft external leaking | Transmitter isolation |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2023-12-25 | 20 |  |  | DF /A /37/DFAA-FT-45054 | Transmitter isolation | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100093856 | DFA-18 LG Ft external leaking | Transmitter isolation |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-08-12 | 2023-12-25 | 30 |  |  | DF /A /37/DFAA-FT-45054 | Transmitter isolation | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100093856 | DFA-18 LG Ft external leaking | Transmitter isolation |  |  | 1.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-08-12 | 2023-12-25 | 40 |  |  | DF /A /37/DFAA-FT-45054 | Transmitter isolation | Unknown
3 | DFA-OIL | WDF | MTN-INST | PRODTECH | 2100093856 | DFA-18 LG Ft external leaking | Transmitter isolation |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-08-12 | 2023-12-25 | 50 |  |  | DF /A /37/DFAA-FT-45054 | Transmitter isolation | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328717 | 6M SDV LUB/MAINT HPSEP - DFC | SDV LUB/INSP HPSEP - DFC |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-22 | 2024-06-07 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP HPSEP - DFC | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 10 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 11 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 21 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 31 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 41 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 51 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 61 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 71 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 81 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 91 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 101 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 111 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 121 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 131 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 141 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 151 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000658 | DK46 BUR CAMPAIGN OCG MATR ORDER 2020/21 | DK46 BUR CAMPAIGN OCG MATR ORDER 202 |  |  | 0 | 0 | Empty | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2020-01-01 | 2020-12-31 | 161 |  |  | DF /F | DK46 BUR CAMPAIGN OCG MATR ORDER 202 | Unknown
D | NOSD | WPM | MTN-INST | PRODLABO | 2400222517 | 1Y PORT DEWPOINT HYGROMETER CALIB - DFC | PORT DEWPOINT HYGROMETER CALIB - DFC |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-14 | 2023-01-30 | 10 |  |  | DF /C /84/TEST-EQUIPMENT | PORT DEWPOINT HYGROMETER CALIB - DFC | Unknown
D | DAB-WI | WPM | PRODTECH | PRODTECH | 2400337394 | PIGGING, P3010 12" DFF-DAD WI 2W | P3010_DFF-DAD | AWSC | AWSC | 4 | 0 | Empty | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-09 | 2024-08-15 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673010 | P3010_DFF-DAD | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018130 | Replace Motor protection 1841-M106 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M106-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018130 | Replace Motor protection 1841-M106 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M106-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018130 | Replace Motor protection 1841-M106 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M106-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018130 | Replace Motor protection 1841-M106 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M106-02 | New mat num | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339085 | DFC_1Y_JACKET ABOVE WATER INSPECTION | DFC_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/JACKET - L.A.T. TO EL 22000 | DFC_1Y_JACKET ABOVE WATER INSPECTION | Unknown
D | NOSD | WPM | MTN-MECH | PRODTECH | 2400221199 | 1Y HYPOCHLOR INJECT. SKID MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2022-11-30 | 2023-01-16 | 10 |  |  | DF /G /75/DFGA-A-55300 | ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400221199 | 1Y HYPOCHLOR INJECT. SKID MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2022-11-30 | 2023-01-16 | 20 |  |  | DF /G /75/DFGA-A-55300 | ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400221199 | 1Y HYPOCHLOR INJECT. SKID MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2022-11-30 | 2023-01-16 | 30 |  |  | DF /G /75/DFGA-A-55300 | ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-MECH | PRODTECH | 2400221199 | 1Y HYPOCHLOR INJECT. SKID MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-11-30 | 2023-01-16 | 40 |  |  | DF /G /75/DFGA-A-55300 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | PRODTECH | 2400334411 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620 | Boroscope inspection | AWSCSECE | AWSCSECE | 5 | 0 | W29-W30 | 2024-07-19 | 2024-08-01 | 2024-07-19 | 2024-07-20 | 2024-06-10 | 2024-07-10 | 10 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | Boroscope inspection | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-TURB | 2400334411 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620 | Boroscope inspection | AWSCSECE | AWSCSECE | 32 | 0 | W29-W30 | 2024-07-19 | 2024-08-01 | 2024-07-20 | 2024-07-24 | 2024-06-10 | 2024-07-10 | 20 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | Boroscope inspection | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-ELEC | 2400334411 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620 | Boroscope inspection | AWSCSECE | AWSCSECE | 18 | 0 | W29-W30 | 2024-07-19 | 2024-08-01 | 2024-07-24 | 2024-07-26 | 2024-06-10 | 2024-07-10 | 30 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | Boroscope inspection | Unknown
A | DFF-1620 | WPM | MTN-TURB | VEN-INST | 2400334411 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620 | Boroscope inspection | AWSCSECE | AWSCSECE | 18 | 0 | W29-W30 | 2024-07-19 | 2024-08-01 | 2024-07-26 | 2024-07-27 | 2024-06-10 | 2024-07-10 | 40 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | Boroscope inspection | Unknown
A | DFF-1620 | WPM | MTN-TURB | PRODTECH | 2400334411 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620 | Boroscope inspection | AWSCSECE | AWSCSECE | 5 | 0 | W29-W30 | 2024-07-19 | 2024-08-01 | 2024-07-27 | 2024-07-28 | 2024-06-10 | 2024-07-10 | 50 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | Boroscope inspection | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-TURB | 2400334411 | 8KH MAIN GEN. SERVICE, COUNTER-A-1620 | Boroscope inspection | AWSCSECE | AWSCSECE | 16 | 0 | W29-W30 | 2024-07-19 | 2024-08-01 | 2024-07-28 | 2024-08-01 | 2024-06-10 | 2024-07-10 | 60 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | Boroscope inspection | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322238 | DFB-36-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400316059 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-12 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 35 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2024-02-27 | 2024-04-29 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-12 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400352438 | 18M IR GAS DETECTORS CHECK - DFF | IR GAS DETECTORS CHECK | SECE | SECE | 105.5 | 0 | W39-W40 | 2024-09-23 | 2024-10-19 | 2024-09-23 | 2024-10-19 | 2024-09-23 | 2024-10-23 | 10 | SECE | SECE | DF /F /03/FGS-DETECTORS | IR GAS DETECTORS CHECK | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400290938 | 6M INST AIR SYSTEM MAINT- DFGA-A-5453/54 | INST AIR SYSTEM MAINT- DFGA-A-5453/54 |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-11-11 | 2023-11-30 | 10 |  |  | DF /G /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYSTEM MAINT- DFGA-A-5453/54 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400290938 | 6M INST AIR SYSTEM MAINT- DFGA-A-5453/54 | INST AIR SYSTEM MAINT- DFGA-A-5453/54 |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-11-11 | 2023-11-30 | 20 |  |  | DF /G /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYSTEM MAINT- DFGA-A-5453/54 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053474 | Replace floodlight DFA 1800-32-L3C | Replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-30 | 2022-03-29 | 10 |  |  | DF /A /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053474 | Replace floodlight DFA 1800-32-L3C | Replace floodlight |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-30 | 2022-03-29 | 20 |  |  | DF /A /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053474 | Replace floodlight DFA 1800-32-L3C | Replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 30 |  |  | DF /A /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058592 | Defect DFEZ-FI-57002 | Replace Flow gauge |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-02-06 | 2022-07-06 | 10 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058592 | Defect DFEZ-FI-57002 | Replace Flow gauge |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-02-06 | 2022-07-06 | 20 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058592 | Defect DFEZ-FI-57002 | Replace Flow gauge |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-06 | 2022-07-06 | 30 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100057912 | Troubleshoot Rotationsensor BM-1228A/B | Troubleshoot and fix or replace |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-11-15 | 2021-12-25 | 10 |  |  | DF /C /09/DFCI-BM-1228A | Troubleshoot and fix or replace | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057912 | Troubleshoot Rotationsensor BM-1228A/B | Troubleshoot and fix or replace |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-11-15 | 2021-12-25 | 20 |  |  | DF /C /09/DFCI-BM-1228A | Troubleshoot and fix or replace | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100057912 | Troubleshoot Rotationsensor BM-1228A/B | Troubleshoot and fix or replace |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-11-15 | 2021-12-25 | 30 |  |  | DF /C /09/DFCI-BM-1228A | Troubleshoot and fix or replace | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316051 | 6M WELL CONT PANEL MAINT - DFFA-FP-3102 | WELL CONT PANEL MAINT - DFFA-FP-3102 | SCH | SCH | 4 | 0 | W21-W22 | 2024-05-28 | 2024-05-29 | 2024-05-28 | 2024-05-29 | 2024-04-18 | 2024-05-04 | 10 | SCH | SCH | DF /F /07/DFFA-FP-3102 | WELL CONT PANEL MAINT - DFFA-FP-3102 | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235926 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL ISOLATION | AWSC | AWSC | 1 | 1 | W17-W18 | 2024-04-26 | 2024-04-30 | 2024-04-26 | 2024-04-26 | 2022-11-26 | 2023-03-23 | 10 | AWSC | AWSC | DF /G /09/DFGA-A-1220 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235926 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL ISOLATION | AWSC | AWSC | 24 | 24 | W17-W18 | 2024-04-26 | 2024-04-30 | 2024-04-26 | 2024-04-28 | 2022-11-26 | 2023-03-23 | 20 | AWSC | AWSC | DF /G /09/DFGA-A-1220 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400235926 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL ISOLATION | AWSC | AWSC | 6 | 6 | W17-W18 | 2024-04-26 | 2024-04-30 | 2024-04-28 | 2024-04-30 | 2022-11-26 | 2023-03-23 | 30 | AWSC | AWSC | DF /G /09/DFGA-A-1220 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235926 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL ISOLATION | AWSC | AWSC | 1 | 1 | W17-W18 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2022-11-26 | 2023-03-23 | 40 | AWSC | AWSC | DF /G /09/DFGA-A-1220 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235926 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL ISOLATION | AWSC | AWSC | 2 | 2 | W17-W18 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2022-11-26 | 2023-03-23 | 50 | AWSC | AWSC | DF /G /09/DFGA-A-1220 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235926 | 4Y HVAC COOL UNIT DFGA-1220/21/22 - VEND | PERSONAL ISOLATION | AWSC | AWSC | 0 | 0 | W17-W18 | 2024-04-26 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2022-11-26 | 2023-03-23 | 60 | AWSC | AWSC | DF /G /09/DFGA-A-1220 | PERSONAL ISOLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040880 | Re attach HT JB to pipe. 1802-20405-L2F | Install HT JB to pipe |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2020-12-03 | 2021-03-03 | 10 |  |  | DF /F /61 | Install HT JB to pipe | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040880 | Re attach HT JB to pipe. 1802-20405-L2F | Install HT JB to pipe |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2020-12-03 | 2021-03-03 | 20 |  |  | DF /F /61 | Install HT JB to pipe | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040880 | Re attach HT JB to pipe. 1802-20405-L2F | Install HT JB to pipe |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2020-12-03 | 2021-03-03 | 30 |  |  | DF /F /61 | Install HT JB to pipe | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235908 | 6M WELLH CONT PANEL MAINT - DFFA-FP-3103 | WELLH CONT PANEL MAINT - DFFA-FP-3103 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-06 | 2023-03-22 | 10 |  |  | DF /F /07/DFFA-FP-3103 | WELLH CONT PANEL MAINT - DFFA-FP-3103 | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044256 | DFC level 1. XCV-50400 Sidder fast | Vendor to Troubleshoot on XCV-50400 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50400 | Vendor to Troubleshoot on XCV-50400 | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044256 | DFC level 1. XCV-50400 Sidder fast | Vendor to Troubleshoot on XCV-50400 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50400 | Vendor to Troubleshoot on XCV-50400 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400215378 | 1Y POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2022-10-19 | 2022-11-18 | 10 | SECE | SECE | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400215378 | 1Y POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | SECE | SECE | 7 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-17 | 2022-10-19 | 2022-11-18 | 20 | SECE | SECE | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400215378 | 1Y POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | SECE | SECE | 5 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2022-10-19 | 2022-11-18 | 30 | SECE | SECE | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400215378 | 1Y POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-10-19 | 2022-11-18 | 40 | SECE | SECE | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400215378 | 1Y POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2022-10-19 | 2022-11-18 | 50 | SECE | SECE | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097347 | DFGA-HRF-3301 HOSE TO BE REPLACED | replace firehose and repair tube | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-03-01 | 2026-08-18 | 10 | SECE | SECE | DF /G /01/DFGA-HRF-03301 | replace firehose and repair tube | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097347 | DFGA-HRF-3301 HOSE TO BE REPLACED | replace firehose and repair tube | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-03-01 | 2026-08-18 | 20 | SECE | SECE | DF /G /01/DFGA-HRF-03301 | replace firehose and repair tube | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097347 | DFGA-HRF-3301 HOSE TO BE REPLACED | replace firehose and repair tube | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-03-01 | 2026-08-18 | 30 | SECE | SECE | DF /G /01/DFGA-HRF-03301 | replace firehose and repair tube | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 10 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 20 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 8 | 3 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 30 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 40 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 5 | 3 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 50 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 60 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-06-30 | 2019-09-28 | 70 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-06-30 | 2019-09-28 | 75 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-06-30 | 2019-09-28 | 80 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-06-30 | 2019-09-28 | 85 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-06-30 | 2019-09-28 | 90 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2019-06-30 | 2019-09-28 | 100 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024627 | DFFA-LG-410581 Replace of level glass. | Replace of valves on levelglass | PCNFAWSC | PCNFAWSC | 1.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2019-06-30 | 2019-09-28 | 110 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-LG-410581 | Replace of valves on levelglass | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088063 | Nødlys DFF Roof | Nødlys DFF Roof |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-08 | 2023-09-20 | 10 |  |  | DF /F /05/DFFA-N-1813 | Nødlys DFF Roof | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088063 | Nødlys DFF Roof | Nødlys DFF Roof |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-08 | 2023-09-20 | 20 |  |  | DF /F /05/DFFA-N-1813 | Nødlys DFF Roof | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088063 | Nødlys DFF Roof | Nødlys DFF Roof |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-08 | 2023-09-20 | 30 |  |  | DF /F /05/DFFA-N-1813 | Nødlys DFF Roof | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088063 | Nødlys DFF Roof | Nødlys DFF Roof |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-08 | 2023-09-20 | 40 |  |  | DF /F /05/DFFA-N-1813 | Nødlys DFF Roof | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400351958 | 1Y DOWNHOLE GAUGE SYSTEM - DFF | DOWNHOLE GAUGE SYSTEM MAINT - DFF |  |  | 6 | 0 | W37-W38 | 2024-09-09 | 2024-09-10 | 2024-09-09 | 2024-09-10 | 2024-09-09 | 2024-10-15 | 10 |  |  | DF /F /10/CONTROL-PANELS | DOWNHOLE GAUGE SYSTEM MAINT - DFF | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 6 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 10 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 20 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 2 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 30 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 2 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 40 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 8 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 50 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 60 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 3 | 8 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 70 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 80 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 2 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 90 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 100 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100041605 | DFF - XCV-354127 air leakage on actuator | De-isolate XCV-354127 | PCNFAWSC | PCNFAWSC | 5 | 0 | W49-50 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-09-23 | 2020-10-13 | 110 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-XCV-354127 | De-isolate XCV-354127 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400285956 | 3M HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | Take oil sample | SCH | SCH | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-02 | 2023-11-12 | 10 | SCH | SCH | DF /B /07/DFBA-A-5903 | Take oil sample | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400285956 | 3M HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | Take oil sample | SCH | SCH | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-02 | 2023-11-12 | 20 | SCH | SCH | DF /B /07/DFBA-A-5903 | Take oil sample | Unknown
4 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100053824 | SDBB for PIT-290540 internal leak | Isolate Pressure transmitter | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-11-05 | 2022-04-04 | 10 | AWSC | AWSC | DF /F /37/DFFA-PIT-290540 | Isolate Pressure transmitter | Unknown
4 | DFX-LIFT | WDF | MTN-MECH | MTN-MECH | 2100053824 | SDBB for PIT-290540 internal leak | Isolate Pressure transmitter | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-11-05 | 2022-04-04 | 20 | AWSC | AWSC | DF /F /37/DFFA-PIT-290540 | Isolate Pressure transmitter | Unknown
4 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100053824 | SDBB for PIT-290540 internal leak | Isolate Pressure transmitter | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-11-05 | 2022-04-04 | 30 | AWSC | AWSC | DF /F /37/DFFA-PIT-290540 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100111610 | DFF-UV-121705 defekt | Replace DFF-UV-121705 | SCHSECE | SCHSECE | 8 | 8 | W19-W20 | 2024-05-09 | 2024-05-10 | 2024-05-09 | 2024-05-10 | 2024-06-11 | 2024-10-24 | 10 | SCHSECE | SCHSECE | DF /F /03/DFFA-UV-121705 | Replace DFF-UV-121705 | Unknown
4 | Empty | WRO | MTN-SAT | MTN-SAT | 2300003118 | DUCSAT DO NOT USE Use 2300003373 | DUCSAT CONSUM DAN SAT |  |  | 0 | 0 | Empty | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-01-26 | 2022-11-22 | 10 |  |  | DF /F | DUCSAT CONSUM DAN SAT | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341921 | DFG_1Y_29000 INT STRUCT INSP - GVI | DFG_1Y_29000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/EL_29000 (LEVEL2) | DFG_1Y_29000 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235629 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-19 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-19 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235629 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-19 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-19 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235629 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-19 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-19 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235629 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-19 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-19 | ISOLATION ELECTRICAL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300002629 | DK40 - CONSUMABLE PROD - OCEAN TEAM | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 0 | 0 | Empty | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-06 | 10 |  |  | DF /C /75 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300002629 | DK40 - CONSUMABLE PROD - OCEAN TEAM | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 0 | 0 | Empty | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2022-06-06 | 20 |  |  | DF /C /75 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100040810 | Broken earth tag on MAC | Installation of the earthinhg tag |  |  | 0.5 | 6 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-12-02 | 2021-03-02 | 10 |  |  | DF /C /03/DFCM-MAC-13061B | Installation of the earthinhg tag | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100040810 | Broken earth tag on MAC | Installation of the earthinhg tag |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-12-02 | 2021-03-02 | 20 |  |  | DF /C /03/DFCM-MAC-13061B | Installation of the earthinhg tag | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100040810 | Broken earth tag on MAC | Installation of the earthinhg tag |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2020-12-02 | 2021-03-02 | 30 |  |  | DF /C /03/DFCM-MAC-13061B | Installation of the earthinhg tag | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284133 | 6M PRIME MOVER DFAA-MD-6102 | PRIME MOVER MAINTENANCE DFAA-MD-6102 |  |  | 16 | 0 | W23-W24 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2024-02-27 | 2024-03-14 | 10 |  |  | DF /A /78/DFAA-MD-6102 | PRIME MOVER MAINTENANCE DFAA-MD-6102 | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100074254 | Fusible loop på lev 1 taber tryk | Remove rope access |  |  | 10 | 0 | W51-52 | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-14 | 2022-09-07 | 2022-10-22 | 10 |  |  | DF /G /03/FUSIBLE-PLUG-LOOPS | Remove rope access | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100074254 | Fusible loop på lev 1 taber tryk | Remove rope access |  |  | 18 | 0 | W51-52 | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-16 | 2022-09-07 | 2022-10-22 | 20 |  |  | DF /G /03/FUSIBLE-PLUG-LOOPS | Remove rope access | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100074254 | Fusible loop på lev 1 taber tryk | Remove rope access |  |  | 2 | 0 | W51-52 | 2023-02-13 | 2023-02-16 | 2023-02-16 | 2023-02-16 | 2022-09-07 | 2022-10-22 | 30 |  |  | DF /G /03/FUSIBLE-PLUG-LOOPS | Remove rope access | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100074254 | Fusible loop på lev 1 taber tryk | Remove rope access |  |  | 6 | 0 | W51-52 | 2023-02-13 | 2023-02-16 | 2023-02-16 | 2023-02-16 | 2022-09-07 | 2022-10-22 | 40 |  |  | DF /G /03/FUSIBLE-PLUG-LOOPS | Remove rope access | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | MTN-INST | 2100049116 | DFE-04 liftgas FCV-45016 faulty | Prod isolation/permit | AWSCSCH | AWSCSCH | 1 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2024-04-08 | 2021-05-09 | 2021-06-18 | 10 | AWSCSCH | AWSCSCH | DF /E /37/DFEZ-FCV-45016 | Prod isolation/permit | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100049116 | DFE-04 liftgas FCV-45016 faulty | Prod isolation/permit | AWSCSCH | AWSCSCH | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-08 | 2024-04-08 | 2021-05-09 | 2021-06-18 | 20 | AWSCSCH | AWSCSCH | DF /E /37/DFEZ-FCV-45016 | Prod isolation/permit | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | MTN-INST | 2100049116 | DFE-04 liftgas FCV-45016 faulty | Prod isolation/permit | AWSCSCH | AWSCSCH | 5 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-09 | 2024-04-10 | 2021-05-09 | 2021-06-18 | 30 | AWSCSCH | AWSCSCH | DF /E /37/DFEZ-FCV-45016 | Prod isolation/permit | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100049116 | DFE-04 liftgas FCV-45016 faulty | Prod isolation/permit | AWSCSCH | AWSCSCH | 3 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-10 | 2024-04-10 | 2021-05-09 | 2021-06-18 | 40 | AWSCSCH | AWSCSCH | DF /E /37/DFEZ-FCV-45016 | Prod isolation/permit | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100049116 | DFE-04 liftgas FCV-45016 faulty | Prod isolation/permit | AWSCSCH | AWSCSCH | 2 | 0 | W15-W16 | 2024-04-08 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2021-05-09 | 2021-06-18 | 50 | AWSCSCH | AWSCSCH | DF /E /37/DFEZ-FCV-45016 | Prod isolation/permit | Unknown
D | NOSD | WPM | PRODLABO | PRODLABO | 2400298183 | 3M SAMPLING OF OiW CORRELATIONS | TL-3M SAMPLING OF OIW CORRELATIONS |  |  | 6 | 0 | Empty | 2024-01-01 | 2024-01-02 | 2024-01-01 | 2024-01-02 | 2023-12-31 | 2024-01-15 | 10 |  |  | DF /F /27/DFFA-A-5064 | TL-3M SAMPLING OF OIW CORRELATIONS | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000717 | DAFTEL PROD.BETALT -START 01JUN2018 | DAFTEL PROD.BETALT -START 01JUN2018 |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-06-01 | 10 |  |  | DF | DAFTEL PROD.BETALT -START 01JUN2018 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000717 | DAFTEL PROD.BETALT -START 01JUN2018 | DAFTEL PROD.BETALT -START 01JUN2018 |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-06-01 | 20 |  |  | DF | DAFTEL PROD.BETALT -START 01JUN2018 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322269 | DFC-11-WO-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /11/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027404 | HT cable disconnected in JB-1800-59-L | L2 Safing of JB-1800-59-L3B | PCNF | PCNF | 2 | 2 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2018-12-10 | 2019-05-09 | 10 | PCNF | PCNF | DF /A /61/DFAA-N-1800 | L2 Safing of JB-1800-59-L3B | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027404 | HT cable disconnected in JB-1800-59-L | L2 Safing of JB-1800-59-L3B | PCNF | PCNF | 10 | 108 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2018-12-10 | 2019-05-09 | 20 | PCNF | PCNF | DF /A /61/DFAA-N-1800 | L2 Safing of JB-1800-59-L3B | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027404 | HT cable disconnected in JB-1800-59-L | L2 Safing of JB-1800-59-L3B | PCNF | PCNF | 2 | 2 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2018-12-10 | 2019-05-09 | 30 | PCNF | PCNF | DF /A /61/DFAA-N-1800 | L2 Safing of JB-1800-59-L3B | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235760 | 4Y 380V UPS-DP F.TEST DFCC-DP-1933A/B | 380V UPS-DP F.TEST DFCC-DP-1933A/B | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /06/DFCI-DP-1933A | 380V UPS-DP F.TEST DFCC-DP-1933A/B | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | MTN-RIGG | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2020-01-01 | 2020-03-31 | 10 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | PRODTECH | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-19 | 2024-09-19 | 2020-01-01 | 2020-03-31 | 20 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | MTN-ELEC | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2020-01-01 | 2020-03-31 | 30 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | MTN-RIGG | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2020-01-01 | 2020-03-31 | 40 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | MTN-ELEC | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2020-01-01 | 2020-03-31 | 50 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | PRODTECH | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2020-01-01 | 2020-03-31 | 60 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
3 | DFF-1751 | WDF | MTN-ELEC | MTN-RIGG | 2100023334 | Exchange blower motor BM-1751A. | Build gantry, arrange chain block |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2020-01-01 | 2020-03-31 | 70 |  |  | DF /F /76/DFFA-BM-1751A | Build gantry, arrange chain block | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235690 | 4Y 00V N-SWB MAINT-DFGA-N-1842A-AR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235690 | 4Y 00V N-SWB MAINT-DFGA-N-1842A-AR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235690 | 4Y 00V N-SWB MAINT-DFGA-N-1842A-AR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235690 | 4Y 00V N-SWB MAINT-DFGA-N-1842A-AR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR03-01 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076003 | DFE/78: Replace JB X3 | Assist with replacement |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-15 | 2023-04-02 | 2025-09-18 | 10 |  |  | DF /E /78/DFEZ-X-6150 | Assist with replacement | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100076003 | DFE/78: Replace JB X3 | Assist with replacement |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-19 | 2023-04-02 | 2025-09-18 | 20 |  |  | DF /E /78/DFEZ-X-6150 | Assist with replacement | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100076003 | DFE/78: Replace JB X3 | Assist with replacement |  |  | 10 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-18 | 2023-04-02 | 2025-09-18 | 22 |  |  | DF /E /78/DFEZ-X-6150 | Assist with replacement | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076003 | DFE/78: Replace JB X3 | Assist with replacement |  |  | 28 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-19 | 2023-04-02 | 2025-09-18 | 30 |  |  | DF /E /78/DFEZ-X-6150 | Assist with replacement | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100076003 | DFE/78: Replace JB X3 | Assist with replacement |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2023-04-02 | 2025-09-18 | 40 |  |  | DF /E /78/DFEZ-X-6150 | Assist with replacement | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100076003 | DFE/78: Replace JB X3 | Assist with replacement |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2023-04-02 | 2025-09-18 | 50 |  |  | DF /E /78/DFEZ-X-6150 | Assist with replacement | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235566 | 4Y 400V E-DP-MAINT-DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /05/DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235566 | 4Y 400V E-DP-MAINT-DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /05/DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235566 | 4Y 400V E-DP-MAINT-DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /05/DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235566 | 4Y 400V E-DP-MAINT-DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-01-30 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /05/DFEZ-DP-1832 | DE-ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 8 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 20 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 20 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 30 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 20 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 40 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 4 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 50 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 8 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 60 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 10 | 10 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 70 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 30 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 80 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 30 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 90 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 100 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 30 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-10-31 | 2024-11-03 | 2021-07-30 | 2021-08-19 | 110 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-11-03 | 2024-11-04 | 2021-07-30 | 2021-08-19 | 120 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 30 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-11-03 | 2024-11-06 | 2021-07-30 | 2021-08-19 | 130 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 4 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-11-06 | 2024-11-06 | 2021-07-30 | 2021-08-19 | 140 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 20 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 150 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 160 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 170 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 180 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053019 | DFG Hazz dræn pumpe 5042 | Install temporary pump MN 1200285 | PCNFSCH | PCNFSCH | 12 | 0 | W29-W30 | 2024-07-29 | 2024-11-06 | 2024-07-29 | 2024-07-29 | 2021-07-30 | 2021-08-19 | 190 | PCNFSCH | PCNFSCH | DF /G /28/DFGA-P-5042 | Install temporary pump MN 1200285 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235825 | 4Y 380V E-SWB MAINT DFFA-N-1812-06 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFA-N-1812-06 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235825 | 4Y 380V E-SWB MAINT DFFA-N-1812-06 | ISOLATION BY PRODUCTION |  |  | 27 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-22 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFA-N-1812-06 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235825 | 4Y 380V E-SWB MAINT DFFA-N-1812-06 | ISOLATION BY PRODUCTION |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFA-N-1812-06 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235825 | 4Y 380V E-SWB MAINT DFFA-N-1812-06 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFA-N-1812-06 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344042 | 1Y SYS 28 DRAINS PUMPS MAINT-DFG | SYS 28 DRAINS PUMPS MAINT-DFG | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-09-18 | 10 | SECE | SECE | DF /G /28/DFGA-T-5040 | SYS 28 DRAINS PUMPS MAINT-DFG | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344042 | 1Y SYS 28 DRAINS PUMPS MAINT-DFG | SYS 28 DRAINS PUMPS MAINT-DFG | SECE | SECE | 21 | 0 | Empty | 2024-08-19 | 2024-08-31 | 2024-08-19 | 2024-08-24 | 2024-08-19 | 2024-09-18 | 20 | SECE | SECE | DF /G /28/DFGA-T-5040 | SYS 28 DRAINS PUMPS MAINT-DFG | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344042 | 1Y SYS 28 DRAINS PUMPS MAINT-DFG | SYS 28 DRAINS PUMPS MAINT-DFG | SECE | SECE | 15 | 0 | Empty | 2024-08-19 | 2024-08-31 | 2024-08-24 | 2024-08-28 | 2024-08-19 | 2024-09-18 | 30 | SECE | SECE | DF /G /28/DFGA-T-5040 | SYS 28 DRAINS PUMPS MAINT-DFG | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344042 | 1Y SYS 28 DRAINS PUMPS MAINT-DFG | SYS 28 DRAINS PUMPS MAINT-DFG | SECE | SECE | 9 | 0 | Empty | 2024-08-19 | 2024-08-31 | 2024-08-28 | 2024-08-30 | 2024-08-19 | 2024-09-18 | 40 | SECE | SECE | DF /G /28/DFGA-T-5040 | SYS 28 DRAINS PUMPS MAINT-DFG | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344042 | 1Y SYS 28 DRAINS PUMPS MAINT-DFG | SYS 28 DRAINS PUMPS MAINT-DFG | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-31 | 2024-08-30 | 2024-08-31 | 2024-08-19 | 2024-09-18 | 50 | SECE | SECE | DF /G /28/DFGA-T-5040 | SYS 28 DRAINS PUMPS MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2021-05-09 | 2021-06-18 | 8 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2021-05-09 | 2021-06-18 | 10 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-23 | 2024-09-23 | 2021-05-09 | 2021-06-18 | 20 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 18 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-23 | 2024-09-25 | 2021-05-09 | 2021-06-18 | 30 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 80 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-23 | 2024-10-03 | 2021-05-09 | 2021-06-18 | 31 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2021-05-09 | 2021-06-18 | 40 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2021-05-09 | 2021-06-18 | 50 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100049169 | DFB/78: Replace overpressure fan | Rigging/scaffold assistance |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2021-05-09 | 2021-06-18 | 60 |  |  | DF /B /78/DFBA-X-6102 | Rigging/scaffold assistance | Unknown
B | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215394 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | PERSONAL ISOLATION |  |  | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2022-10-20 | 2022-11-19 | 10 |  |  | DF /C /09/A-1211 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215394 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | PERSONAL ISOLATION |  |  | 12 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2022-10-20 | 2022-11-19 | 20 |  |  | DF /C /09/A-1211 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215394 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | PERSONAL ISOLATION |  |  | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-20 | 2022-11-19 | 30 |  |  | DF /C /09/A-1211 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215394 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | PERSONAL ISOLATION |  |  | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-20 | 2022-11-19 | 40 |  |  | DF /C /09/A-1211 | PERSONAL ISOLATION | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018132 | Replace Feeder protection 1841-M108 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M108-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018132 | Replace Feeder protection 1841-M108 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M108-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018132 | Replace Feeder protection 1841-M108 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M108-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018132 | Replace Feeder protection 1841-M108 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M108-02 | New mat num | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076000 | DFB: Bracket for wood protection in boom | Replace worn/corroded brackets |  |  | 2 | 0 | Empty | 2023-04-06 | 2023-04-09 | 2023-04-06 | 2023-04-06 | 2023-04-06 | 2025-09-22 | 10 |  |  | DF /B /78/DFBA-X-6102 | Replace worn/corroded brackets | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100076000 | DFB: Bracket for wood protection in boom | Replace worn/corroded brackets |  |  | 39 | 0 | Empty | 2023-04-06 | 2023-04-09 | 2023-04-06 | 2023-04-09 | 2023-04-06 | 2025-09-22 | 20 |  |  | DF /B /78/DFBA-X-6102 | Replace worn/corroded brackets | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076000 | DFB: Bracket for wood protection in boom | Replace worn/corroded brackets |  |  | 7 | 0 | Empty | 2023-04-06 | 2023-04-09 | 2023-04-06 | 2023-04-08 | 2023-04-06 | 2025-09-22 | 30 |  |  | DF /B /78/DFBA-X-6102 | Replace worn/corroded brackets | Unknown
3 | DFF-OIL | WDF | MTN-INST | PRODTECH | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 3 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2020-08-05 | 2020-11-03 | 10 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-MECH | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 3 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-23 | 2020-08-05 | 2020-11-03 | 20 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-INST | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 2 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-23 | 2020-08-05 | 2020-11-03 | 30 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-RIGG | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 5 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-28 | 2024-09-29 | 2020-08-05 | 2020-11-03 | 35 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-MECH | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 5 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-24 | 2024-09-25 | 2020-08-05 | 2020-11-03 | 40 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-RIGG | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 5 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2020-08-05 | 2020-11-03 | 45 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-MECH | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 5 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-25 | 2024-09-26 | 2020-08-05 | 2020-11-03 | 50 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-INST | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 2 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-26 | 2024-09-26 | 2020-08-05 | 2020-11-03 | 60 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | MTN-MECH | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 2 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-27 | 2024-09-27 | 2020-08-05 | 2020-11-03 | 70 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | DFF-OIL | WDF | MTN-INST | PRODTECH | 2100034740 | ESDV-330065 - Fail function test | Isolate ESDV Hydralic | SECE | SECE | 3 | 0 | BL-TEADFF-OIL SD required | 2024-09-22 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2020-08-05 | 2020-11-03 | 80 | SECE | SECE | DF /F /03/SDV-VALVES | Isolate ESDV Hydralic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104881 | FLM DFG Closed drain pump/motor faulty | Rigging assistance |  |  | 0 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-02-16 | 2024-06-30 | 10 |  |  | DF /G /28/DFGA-P-5077 | Rigging assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100104881 | FLM DFG Closed drain pump/motor faulty | Rigging assistance |  |  | 8 | 8 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-18 | 2024-02-16 | 2024-06-30 | 20 |  |  | DF /G /28/DFGA-P-5077 | Rigging assistance | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400298233 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-01-01 | 2024-01-12 | 20 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400298233 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-01-01 | 2024-01-12 | 30 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018129 | Replace Motor protection 1841-M105 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M105-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018129 | Replace Motor protection 1841-M105 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M105-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018129 | Replace Motor protection 1841-M105 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M105-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018129 | Replace Motor protection 1841-M105 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M105-02 | New mat num | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-10-31 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-03 | 2024-11-04 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-04 | 2024-11-04 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-04 | 2024-11-05 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-05 | 2024-11-07 | 2024-10-30 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-07 | 2024-11-07 | 2024-10-30 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-07 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-09 | 2024-11-09 | 2024-10-30 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-09 | 2024-11-09 | 2024-10-30 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-10 | 2024-11-10 | 2024-10-30 | 2024-12-31 | 120 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284246 | PSV Calibration - DFCI-PSV-57121 | Scaffolding | AWSCSECE | AWSCSECE | 10 | 0 | Empty | 2024-10-30 | 2024-11-11 | 2024-11-10 | 2024-11-11 | 2024-10-30 | 2024-12-31 | 130 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57121 | Scaffolding | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100023101 | P-3580 1" discharge drainvalve int leak | Isolate equipment | PCNFAWSC | PCNFAWSC | 3 | 10 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-03 | 2020-03-13 | 2020-08-10 | 5 | PCNFAWSC | PCNFAWSC | DF /F /54 | Isolate equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100023101 | P-3580 1" discharge drainvalve int leak | Isolate equipment | PCNFAWSC | PCNFAWSC | 6 | 0 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-04 | 2020-03-13 | 2020-08-10 | 10 | PCNFAWSC | PCNFAWSC | DF /F /54 | Isolate equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100023101 | P-3580 1" discharge drainvalve int leak | Isolate equipment | PCNFAWSC | PCNFAWSC | 6 | 18 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-04 | 2024-07-05 | 2020-03-13 | 2020-08-10 | 20 | PCNFAWSC | PCNFAWSC | DF /F /54 | Isolate equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100023101 | P-3580 1" discharge drainvalve int leak | Isolate equipment | PCNFAWSC | PCNFAWSC | 6 | 0 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-05 | 2024-07-05 | 2020-03-13 | 2020-08-10 | 30 | PCNFAWSC | PCNFAWSC | DF /F /54 | Isolate equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100023101 | P-3580 1" discharge drainvalve int leak | Isolate equipment | PCNFAWSC | PCNFAWSC | 3 | 0 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-05 | 2024-07-06 | 2020-03-13 | 2020-08-10 | 40 | PCNFAWSC | PCNFAWSC | DF /F /54 | Isolate equipment | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 0 | 6 | Empty | 2024-09-15 | 2024-10-31 | 2022-01-11 | 2022-01-16 | 2022-01-11 | 2022-01-16 | 10 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 20 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-SCAF | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 30 | 60 | Empty | 2024-09-15 | 2024-10-31 | 2022-01-15 | 2022-01-16 | 2022-01-11 | 2022-01-16 | 25 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 0 | 60 | Empty | 2024-09-15 | 2024-10-31 | 2022-01-16 | 2022-01-16 | 2022-01-11 | 2022-01-16 | 26 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 24 | 10 | Empty | 2024-09-15 | 2024-10-31 | 2022-01-13 | 2022-01-16 | 2022-01-11 | 2022-01-16 | 30 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-INST | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 12 | 10 | Empty | 2024-09-15 | 2024-10-31 | 2022-01-15 | 2022-01-16 | 2022-01-11 | 2022-01-16 | 40 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 50 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 51 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 60 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 61 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 71 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-15 | 2022-01-11 | 2022-01-16 | 81 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-15 | 2024-09-16 | 2022-01-11 | 2022-01-16 | 101 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-SCAF | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 60 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-09-16 | 2024-10-01 | 2022-01-11 | 2022-01-16 | 111 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 60 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-10-01 | 2024-10-16 | 2022-01-11 | 2022-01-16 | 121 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 10 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-10-16 | 2024-10-19 | 2022-01-11 | 2022-01-16 | 131 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 20 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-10-19 | 2024-10-24 | 2022-01-11 | 2022-01-16 | 141 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 20 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-10-24 | 2024-10-29 | 2022-01-11 | 2022-01-16 | 151 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 4 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-10-29 | 2024-10-30 | 2022-01-11 | 2022-01-16 | 161 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
2 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100061407 | DFG SW 16" bypass HCV stem pack damaged | Demount 2 bl. flange | PCNF | PCNF | 4 | 0 | Empty | 2024-09-15 | 2024-10-31 | 2024-10-30 | 2024-10-31 | 2022-01-11 | 2022-01-16 | 171 | PCNF | PCNF | DF /G /51/DFGA-TCV-530459B | Demount 2 bl. flange | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100057177 | ANOPR: Utility & Instrument Air Batch-01 | SCFM 9V corrosion to DFB-1"-AU-54853-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-01-08 | 2022-06-07 | 10 |  |  | DF /B /07/DFB-1-AU-054-0853-A1-U | SCFM 9V corrosion to DFB-1"-AU-54853-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100057177 | ANOPR: Utility & Instrument Air Batch-01 | SCFM 9V corrosion to DFB-1"-AU-54853-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-01-08 | 2022-06-07 | 20 |  |  | DF /B /07/DFB-1-AU-054-0853-A1-U | SCFM 9V corrosion to DFB-1"-AU-54853-A1 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235846 | 4Y 400V E-SWB MAINT DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235846 | 4Y 400V E-SWB MAINT DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235846 | 4Y 400V E-SWB MAINT DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235846 | 4Y 400V E-SWB MAINT DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A08 | ISOLATION BY PRODUCTION | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2020-03-18 | 2020-08-15 | 10 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2020-03-18 | 2020-08-15 | 20 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2020-03-18 | 2020-08-15 | 30 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2020-03-18 | 2020-08-15 | 40 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2020-03-18 | 2020-08-15 | 50 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2020-03-18 | 2020-08-15 | 60 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2020-03-18 | 2020-08-15 | 70 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-06 | 2020-03-18 | 2020-08-15 | 80 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2020-03-18 | 2020-08-15 | 90 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2020-03-18 | 2020-08-15 | 100 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100023195 | Exchange manifold valves for DFF-10 | Prepare rigging equipment | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2020-03-18 | 2020-08-15 | 110 | AWSC | AWSC | DF /F /54 | Prepare rigging equipment | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200010681 | køb af nye Lænestole til læsestuer Dan F | køb af nye Lænestole til læsestuer Dan F |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-12-26 | 2022-02-04 | 10 |  |  | DF /C /09/ACCOMMODATION-LEVEL-2 | køb af nye Lænestole til læsestuer Dan F | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 10 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-17 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 20 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 30 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-19 | 2021-02-18 | 2021-05-19 | 40 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-19 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 50 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 60 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-21 | 2021-02-18 | 2021-05-19 | 70 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-23 | 2021-02-18 | 2021-05-19 | 80 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 90 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 100 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 110 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 120 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044917 | DFG PDCV-500662 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-27 | 2021-02-18 | 2021-05-19 | 130 |  |  | DF /G /27/DFGA-PDCV-500662 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-24 | 2024-03-07 | 10 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-24 | 2024-03-07 | 20 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-24 | 2024-03-07 | 30 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-24 | 2024-03-07 | 40 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-24 | 2024-03-07 | 50 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-24 | 2024-03-07 | 60 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-24 | 2024-03-07 | 70 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097869 | Instal cable to Floodlight M1903B-27-L1E | Sitevisit - TBT. |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-24 | 2024-03-07 | 80 |  |  | DF /C /06/DFCI-DP-1903B | Sitevisit - TBT. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071669 | Håndtag på gear / ventil tæret væk | Mount new handwheel |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-08-28 | 2023-01-10 | 10 |  |  | DF /G /31/DFGA-HCV-440039 | Mount new handwheel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071669 | Håndtag på gear / ventil tæret væk | Mount new handwheel |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-08-28 | 2023-01-10 | 20 |  |  | DF /G /31/DFGA-HCV-440039 | Mount new handwheel | Unknown
2 | Empty | WDF | MTN-INST | MTN-MECH | 2100112075 | DFBA-X-0318 SOV12100/12500 fail open | DFBA-X-0318 SOV12100/12500 fail open |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2024-05-03 | 2024-06-17 | 10 |  |  | DF /B /03/DFBA-SOV-12100 | DFBA-X-0318 SOV12100/12500 fail open | Unknown
2 | Empty | WDF | MTN-INST | PRODTECH | 2100112075 | DFBA-X-0318 SOV12100/12500 fail open | DFBA-X-0318 SOV12100/12500 fail open |  |  | 1 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2024-05-03 | 2024-06-17 | 20 |  |  | DF /B /03/DFBA-SOV-12100 | DFBA-X-0318 SOV12100/12500 fail open | Unknown
2 | Empty | WDF | MTN-INST | MTN-INST | 2100112075 | DFBA-X-0318 SOV12100/12500 fail open | DFBA-X-0318 SOV12100/12500 fail open |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2024-05-03 | 2024-06-17 | 30 |  |  | DF /B /03/DFBA-SOV-12100 | DFBA-X-0318 SOV12100/12500 fail open | Unknown
2 | Empty | WDF | MTN-INST | PRODTECH | 2100112075 | DFBA-X-0318 SOV12100/12500 fail open | DFBA-X-0318 SOV12100/12500 fail open |  |  | 1 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-05-03 | 2024-06-17 | 40 |  |  | DF /B /03/DFBA-SOV-12100 | DFBA-X-0318 SOV12100/12500 fail open | Unknown
2 | Empty | WDF | MTN-INST | MTN-INST | 2100112075 | DFBA-X-0318 SOV12100/12500 fail open | DFBA-X-0318 SOV12100/12500 fail open |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2024-05-03 | 2024-06-17 | 50 |  |  | DF /B /03/DFBA-SOV-12100 | DFBA-X-0318 SOV12100/12500 fail open | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 9 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-21 | 2024-06-22 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-21 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 51 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-21 | 2024-06-22 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-21 | 2024-06-22 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-21 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-22 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-22 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284303 | PSV Calibration - DFGA-PSV-410405B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410405B | Backload PSV to Norspie Workshop | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200012429 | Flush eq. test KWV(WI) til KWV(Producer) | Flush eq. test KWV(WI) til KWV(Producer) |  |  | 0 | 0 | Empty | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2025-10-31 | 10 |  |  | DF /F /9 | Flush eq. test KWV(WI) til KWV(Producer) | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100114761 | DFF IP/HP antisurge valve | Change positioner | PCNF | PCNF | 12 | 14 | Empty | 2024-07-03 | 2024-07-03 | 2024-06-18 | 2024-06-25 | 2024-06-18 | 2024-08-02 | 10 | PCNF | PCNF | DF /F /32/DFFA-FCV-440011A | Change positioner | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100114761 | DFF IP/HP antisurge valve | Change positioner | PCNF | PCNF | 0 | 54 | Empty | 2024-07-03 | 2024-07-03 | 2024-06-18 | 2024-06-25 | 2024-06-18 | 2024-08-02 | 20 | PCNF | PCNF | DF /F /32/DFFA-FCV-440011A | Change positioner | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100114761 | DFF IP/HP antisurge valve | Change positioner | PCNF | PCNF | 0 | 20 | Empty | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2024-06-18 | 2024-08-02 | 30 | PCNF | PCNF | DF /F /32/DFFA-FCV-440011A | Change positioner | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322311 | DFG-28-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025274 | Specialist to clean pipe for sand. | L3 Isolate Pipe. | AWSC | AWSC | 6 | 0 | W23-W24 | 2024-06-03 | 2024-06-09 | 2024-06-03 | 2024-06-04 | 2019-02-10 | 2019-03-02 | 20 | AWSC | AWSC | DF /G /27/DFGA-XCV-340413 | L3 Isolate Pipe. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025274 | Specialist to clean pipe for sand. | L3 Isolate Pipe. | AWSC | AWSC | 26 | 0 | W23-W24 | 2024-06-03 | 2024-06-09 | 2024-06-04 | 2024-06-07 | 2019-02-10 | 2019-03-02 | 30 | AWSC | AWSC | DF /G /27/DFGA-XCV-340413 | L3 Isolate Pipe. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025274 | Specialist to clean pipe for sand. | L3 Isolate Pipe. | AWSC | AWSC | 6 | 0 | W23-W24 | 2024-06-03 | 2024-06-09 | 2024-06-07 | 2024-06-09 | 2019-02-10 | 2019-03-02 | 40 | AWSC | AWSC | DF /G /27/DFGA-XCV-340413 | L3 Isolate Pipe. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025274 | Specialist to clean pipe for sand. | L3 Isolate Pipe. | AWSC | AWSC | 2 | 0 | W23-W24 | 2024-06-03 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2019-02-10 | 2019-03-02 | 50 | AWSC | AWSC | DF /G /27/DFGA-XCV-340413 | L3 Isolate Pipe. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106758 | DFB HCV-360003 Missing Handle | If yes remove old "hub" |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-03-19 | 2024-08-01 | 10 |  |  | DF /B /23/DFBA-HCV-360003 | If yes remove old "hub" | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106758 | DFB HCV-360003 Missing Handle | If yes remove old "hub" |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-03-19 | 2024-08-01 | 20 |  |  | DF /B /23/DFBA-HCV-360003 | If yes remove old "hub" | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106758 | DFB HCV-360003 Missing Handle | If yes remove old "hub" |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-03-19 | 2024-08-01 | 30 |  |  | DF /B /23/DFBA-HCV-360003 | If yes remove old "hub" | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 10 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 20 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 30 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 40 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 50 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 60 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 70 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 80 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 90 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006211 | PVI Service material Dan F 2021 | Pieter M ATEX Dehumidifier |  |  | 0 | 0 | Empty | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-02-03 | 2021-03-15 | 100 |  |  | DF /C /11/DFCI-V-3401 | Pieter M ATEX Dehumidifier | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-06-21 | 2025-12-07 | 10 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-06-21 | 2025-12-07 | 20 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2023-06-21 | 2025-12-07 | 30 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-23 | 2023-06-21 | 2025-12-07 | 40 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-24 | 2023-06-21 | 2025-12-07 | 50 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-24 | 2024-09-25 | 2023-06-21 | 2025-12-07 | 60 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-26 | 2023-06-21 | 2025-12-07 | 70 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2023-06-21 | 2025-12-07 | 80 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-27 | 2023-06-21 | 2025-12-07 | 90 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-27 | 2023-06-21 | 2025-12-07 | 100 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2023-06-21 | 2025-12-07 | 110 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-06-21 | 2025-12-07 | 120 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-06-21 | 2025-12-07 | 130 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080289 | DP-1854 heat trace to circut Q7 defect | DP-1854 heat trace to circut Q7 defect | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-06-21 | 2025-12-07 | 140 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-07 | DP-1854 heat trace to circut Q7 defect | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088072 | Lifebuoy rope cabinet-cap broken | Replace broken caps |  |  | 5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-22 | 2026-03-10 | 10 |  |  | DF /C /02/DFCM-LBS-0606 | Replace broken caps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085357 | DFA-11 defekt håndtag. | DFA-11 Replace damaged Handwheel |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-01 | 2023-08-14 | 10 |  |  | DF /A /55/DFAA-HCV-350311 | DFA-11 Replace damaged Handwheel | Unknown
4 | DFB-O10 | WDF | MTN-INST | PRODTECH | 2100046328 | Invertere ZSO og ZSC på DFB10 WCV | Replace wiring | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 10 | AWSC | AWSC | DF /B /10/DFBA-WCV-30034 | Replace wiring | Unknown
4 | DFB-O10 | WDF | MTN-INST | MTN-INST | 2100046328 | Invertere ZSO og ZSC på DFB10 WCV | Replace wiring | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 12 | AWSC | AWSC | DF /B /10/DFBA-WCV-30034 | Replace wiring | Unknown
4 | DFB-O10 | WDF | MTN-INST | MTN-INST | 2100046328 | Invertere ZSO og ZSC på DFB10 WCV | Replace wiring | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 20 | AWSC | AWSC | DF /B /10/DFBA-WCV-30034 | Replace wiring | Unknown
4 | DFB-O10 | WDF | MTN-INST | PRODTECH | 2100046328 | Invertere ZSO og ZSC på DFB10 WCV | Replace wiring | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 30 | AWSC | AWSC | DF /B /10/DFBA-WCV-30034 | Replace wiring | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232985 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-03 | Additional Materials | AWSC | AWSC | 1 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-12-01 | 2023-02-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-03 | Additional Materials | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232985 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-03 | Additional Materials | AWSC | AWSC | 11 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-03 | Additional Materials | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232985 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-03 | Additional Materials | AWSC | AWSC | 3 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-03 | Additional Materials | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232985 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-03 | Additional Materials | AWSC | AWSC | 1 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-12-01 | 2023-02-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-03 | Additional Materials | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400232985 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-03 | Additional Materials | AWSC | AWSC | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-12-01 | 2023-02-27 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-03 | Additional Materials | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400232985 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-03 | Additional Materials | AWSC | AWSC | 0 | 0 | W49-50 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-12-01 | 2023-02-27 | 60 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-03 | Additional Materials | Unknown
3 | DFB-W05 | WDF | MTN-MECH | PRODTECH | 2100023406 | DFB-05, 400 bars anlæg, Defekt PRV | De-isolate drawer for well DFB-05 | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2019-11-29 | 2019-12-19 | 10 | AWSC | AWSC | DF /B /07/DFBA-PRV-30118 | De-isolate drawer for well DFB-05 | Unknown
3 | DFB-W05 | WDF | MTN-MECH | MTN-MECH | 2100023406 | DFB-05, 400 bars anlæg, Defekt PRV | De-isolate drawer for well DFB-05 | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2019-11-29 | 2019-12-19 | 20 | AWSC | AWSC | DF /B /07/DFBA-PRV-30118 | De-isolate drawer for well DFB-05 | Unknown
3 | DFB-W05 | WDF | MTN-MECH | PRODTECH | 2100023406 | DFB-05, 400 bars anlæg, Defekt PRV | De-isolate drawer for well DFB-05 | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2019-11-29 | 2019-12-19 | 30 | AWSC | AWSC | DF /B /07/DFBA-PRV-30118 | De-isolate drawer for well DFB-05 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241119 | 6M SDV LUB/MAINT- DFG | SDV LUB/MAINT- DFG |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-03-27 | 2023-04-12 | 10 |  |  | DF /G /03/SDV-VALVES | SDV LUB/MAINT- DFG | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342411 | 6M SEAWATER FILTER PKG MAINT-DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-21 | 2024-09-09 | 10 |  |  | DF /G /51/DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 | Unknown
3 | DAN-WI | WDF | MTN-INST | PRODTECH | 2100074991 | Defekt DBB ventil for PIT-350913 | Isolate and Inhibit Pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-05 | 2023-03-20 | 10 |  |  | DF /G /54/DFGA-PIT-350913 | Isolate and Inhibit Pressure transmitter | Unknown
3 | DAN-WI | WDF | MTN-INST | MTN-INST | 2100074991 | Defekt DBB ventil for PIT-350913 | Isolate and Inhibit Pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-05 | 2023-03-20 | 20 |  |  | DF /G /54/DFGA-PIT-350913 | Isolate and Inhibit Pressure transmitter | Unknown
3 | DAN-WI | WDF | MTN-INST | MTN-MECH | 2100074991 | Defekt DBB ventil for PIT-350913 | Isolate and Inhibit Pressure transmitter |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-05 | 2023-03-20 | 30 |  |  | DF /G /54/DFGA-PIT-350913 | Isolate and Inhibit Pressure transmitter | Unknown
3 | DAN-WI | WDF | MTN-INST | MTN-INST | 2100074991 | Defekt DBB ventil for PIT-350913 | Isolate and Inhibit Pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-05 | 2023-03-20 | 40 |  |  | DF /G /54/DFGA-PIT-350913 | Isolate and Inhibit Pressure transmitter | Unknown
3 | DAN-WI | WDF | MTN-INST | PRODTECH | 2100074991 | Defekt DBB ventil for PIT-350913 | Isolate and Inhibit Pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-05 | 2023-03-20 | 50 |  |  | DF /G /54/DFGA-PIT-350913 | Isolate and Inhibit Pressure transmitter | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100098376 | Helifuel System SOV's to be replaced | additional SOV | PCNF | PCNF | 8 | 12 | Empty | 2024-10-15 | 2024-10-15 | 2024-01-08 | 2024-06-29 | 2023-09-11 | 2023-10-26 | 10 | PCNF | PCNF | DF /C /81/DFCI-P-5601 | additional SOV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100098376 | Helifuel System SOV's to be replaced | additional SOV | PCNF | PCNF | 8 | 8 | Empty | 2024-10-15 | 2024-10-15 | 2024-06-29 | 2024-06-29 | 2023-09-11 | 2023-10-26 | 20 | PCNF | PCNF | DF /C /81/DFCI-P-5601 | additional SOV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100098376 | Helifuel System SOV's to be replaced | additional SOV | PCNF | PCNF | 8 | 8 | Empty | 2024-10-15 | 2024-10-15 | 2024-06-29 | 2024-06-29 | 2023-09-11 | 2023-10-26 | 30 | PCNF | PCNF | DF /C /81/DFCI-P-5601 | additional SOV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098376 | Helifuel System SOV's to be replaced | additional SOV | PCNF | PCNF | 0 | 0 | Empty | 2024-10-15 | 2024-10-15 | 2024-06-29 | 2024-06-29 | 2023-09-11 | 2023-10-26 | 40 | PCNF | PCNF | DF /C /81/DFCI-P-5601 | additional SOV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098376 | Helifuel System SOV's to be replaced | additional SOV | PCNF | PCNF | 0 | 0 | Empty | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2023-09-11 | 2023-10-26 | 50 | PCNF | PCNF | DF /C /81/DFCI-P-5601 | additional SOV | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322639 | 3M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-06 | 2024-05-16 | 10 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
4 | NOSD | WDF | MTN-PAIN | PRODTECH | 2100034408 | DFA/78 Paint corroded connection flanges | Clean area around connection flanges for |  |  | 1 | 0 | 260722 Need more prep. | 2023-12-11 | 2023-12-13 | 2023-12-11 | 2023-12-11 | 2020-09-23 | 2021-02-20 | 10 |  |  | DF /A /78/DFAA-X-6102 | Clean area around connection flanges for | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-CRAN | 2100034408 | DFA/78 Paint corroded connection flanges | Clean area around connection flanges for |  |  | 14 | 0 | 260722 Need more prep. | 2023-12-11 | 2023-12-13 | 2023-12-11 | 2023-12-13 | 2020-09-23 | 2021-02-20 | 20 |  |  | DF /A /78/DFAA-X-6102 | Clean area around connection flanges for | Unknown
4 | NOSD | WDF | MTN-PAIN | PRODTECH | 2100034408 | DFA/78 Paint corroded connection flanges | Clean area around connection flanges for |  |  | 1 | 0 | 260722 Need more prep. | 2023-12-11 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2020-09-23 | 2021-02-20 | 30 |  |  | DF /A /78/DFAA-X-6102 | Clean area around connection flanges for | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088055 | Replace basket stretcher rusty hook | Basket stretcher rusty hook |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-10 | 2023-09-22 | 10 |  |  | DF /C /02/DFCI-STR-0640 | Basket stretcher rusty hook | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2022-04-21 | 2022-05-31 | 10 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2022-04-21 | 2022-05-31 | 20 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 5 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2022-04-21 | 2022-05-31 | 30 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2022-04-21 | 2022-05-31 | 40 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 3 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2022-04-21 | 2022-05-31 | 50 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2022-04-21 | 2022-05-31 | 60 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100066358 | DFG: Replace cam switch main hoist | Find and check spareparts/tools |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2022-04-21 | 2022-05-31 | 70 |  |  | DF /G /78/DFGA-A-6140 | Find and check spareparts/tools | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300001995 | BACKLOAD AF INSTRUMENTS FOR RE-CAL. | Materials from Element Metech |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-03-28 | 2022-01-22 | 10 |  |  | DF /C /84 | Materials from Element Metech | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300001995 | BACKLOAD AF INSTRUMENTS FOR RE-CAL. | Materials from Element Metech |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-03-28 | 2022-01-22 | 20 |  |  | DF /C /84 | Materials from Element Metech | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300001995 | BACKLOAD AF INSTRUMENTS FOR RE-CAL. | Materials from Element Metech |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-03-28 | 2022-01-22 | 30 |  |  | DF /C /84 | Materials from Element Metech | Unknown
3 | DFF-OIL | WRO | MTN-TELE | VEN-INST | 2300004286 | DanF - RTU2091/3/4 Power Replacement | DanF - RTU2091/3/4 Power Replacement |  |  | 100 | 0 | Empty | 2024-08-22 | 2024-09-01 | 2024-08-22 | 2024-09-01 | 2023-01-06 | 2023-05-21 | 10 |  |  | DF /F /04/DFFA-FP-2093 | DanF - RTU2091/3/4 Power Replacement | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400309005 | 1Y BDV LUBE/FUNC TEST - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 13 | 0 | W21-W22 | 2024-05-20 | 2024-06-06 | 2024-05-20 | 2024-05-23 | 2024-02-18 | 2024-03-19 | 10 | SECE | SECE | DF /F /70/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400309005 | 1Y BDV LUBE/FUNC TEST - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 43 | 0 | W21-W22 | 2024-05-20 | 2024-06-06 | 2024-05-23 | 2024-06-03 | 2024-02-18 | 2024-03-19 | 20 | SECE | SECE | DF /F /70/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400309005 | 1Y BDV LUBE/FUNC TEST - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 13 | 0 | W21-W22 | 2024-05-20 | 2024-06-06 | 2024-06-03 | 2024-06-06 | 2024-02-18 | 2024-03-19 | 30 | SECE | SECE | DF /F /70/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400342401 | 1Y DRAG REDUCING INJ SYS MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-09-09 | 10 | SECE | SECE | DF /C /75/DFCI-A-3968 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342401 | 1Y DRAG REDUCING INJ SYS MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-10 | 2024-08-12 | 2024-08-10 | 2024-09-09 | 20 | SECE | SECE | DF /C /75/DFCI-A-3968 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400342401 | 1Y DRAG REDUCING INJ SYS MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2024-08-10 | 2024-09-09 | 30 | SECE | SECE | DF /C /75/DFCI-A-3968 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400342401 | 1Y DRAG REDUCING INJ SYS MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-08-10 | 2024-09-09 | 40 | SECE | SECE | DF /C /75/DFCI-A-3968 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400342401 | 1Y DRAG REDUCING INJ SYS MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-10 | 2024-09-09 | 50 | SECE | SECE | DF /C /75/DFCI-A-3968 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100105893 | I/P converter is internal leaking | Isolate / de-isolate positioner |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2024-03-06 | 2024-07-19 | 10 |  |  | DF /G /30/DFGA-TY-410451 | Isolate / de-isolate positioner | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105893 | I/P converter is internal leaking | Isolate / de-isolate positioner |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2024-03-06 | 2024-07-19 | 20 |  |  | DF /G /30/DFGA-TY-410451 | Isolate / de-isolate positioner | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-01 | 2025-01-02 | 2018-11-16 | 2019-04-15 | 10 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-01 | 2025-01-03 | 2018-11-16 | 2019-04-15 | 20 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-01 | 2025-01-02 | 2018-11-16 | 2019-04-15 | 30 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-03 | 2025-01-05 | 2018-11-16 | 2019-04-15 | 40 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-05 | 2025-01-07 | 2018-11-16 | 2019-04-15 | 50 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-07 | 2025-01-07 | 2018-11-16 | 2019-04-15 | 60 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-07 | 2025-01-08 | 2018-11-16 | 2019-04-15 | 70 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-08 | 2025-01-10 | 2018-11-16 | 2019-04-15 | 80 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-10 | 2025-01-11 | 2018-11-16 | 2019-04-15 | 90 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-10 | 2025-01-11 | 2018-11-16 | 2019-04-15 | 100 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-11 | 2025-01-12 | 2018-11-16 | 2019-04-15 | 110 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-12 | 2025-01-13 | 2018-11-16 | 2019-04-15 | 120 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100026132 | Exchange ESDV-441327. | L3 Pre permit & linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-15 | 2025-01-12 | 2025-01-15 | 2018-11-16 | 2019-04-15 | 130 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441327 | L3 Pre permit & linewalk | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337657 | 3M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-10 | 2024-08-20 | 10 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400244917 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING | AWSC | AWSC | 26 | 0 | W33-W34 | 2024-08-14 | 2024-08-25 | 2024-08-14 | 2024-08-21 | 2023-03-03 | 2023-05-16 | 10 | AWSC | AWSC | DF /G /70/METERING | DFGA FUELGAS - METERING | Unknown
C | NOSD | WPM | MTN-INST | PRODTECH | 2400244917 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING | AWSC | AWSC | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-25 | 2024-08-21 | 2024-08-21 | 2023-03-03 | 2023-05-16 | 20 | AWSC | AWSC | DF /G /70/METERING | DFGA FUELGAS - METERING | Unknown
C | NOSD | WPM | MTN-INST | MTN-MECH | 2400244917 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING | AWSC | AWSC | 12 | 0 | W33-W34 | 2024-08-14 | 2024-08-25 | 2024-08-21 | 2024-08-24 | 2023-03-03 | 2023-05-16 | 30 | AWSC | AWSC | DF /G /70/METERING | DFGA FUELGAS - METERING | Unknown
C | NOSD | WPM | MTN-INST | MTN-ROPE | 2400244917 | 3Y DFGA FUELGAS - METERING | DFGA FUELGAS - METERING | AWSC | AWSC | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2023-03-03 | 2023-05-16 | 40 | AWSC | AWSC | DF /G /70/METERING | DFGA FUELGAS - METERING | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321274 | 1Y PRIME MOVER DFBA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-09-19 | 2024-09-19 | 2024-08-18 | 2024-09-17 | 10 | AWSC | AWSC | DF /B /78/DFBA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321274 | 1Y PRIME MOVER DFBA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 38 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-09-19 | 2024-09-28 | 2024-08-18 | 2024-09-17 | 20 | AWSC | AWSC | DF /B /78/DFBA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400321274 | 1Y PRIME MOVER DFBA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 10 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-09-29 | 2024-10-01 | 2024-08-18 | 2024-09-17 | 30 | AWSC | AWSC | DF /B /78/DFBA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321274 | 1Y PRIME MOVER DFBA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-19 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-08-18 | 2024-09-17 | 40 | AWSC | AWSC | DF /B /78/DFBA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100028061 | Exchange PRV-300135 in FP-3103 | DFFA-PRV-300135 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-08 | 2020-05-04 | 2022-04-24 | 10 |  |  | DF /F /07/DFFA-PRV-300135 | DFFA-PRV-300135 Offshore from WS Måde | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100028061 | Exchange PRV-300135 in FP-3103 | DFFA-PRV-300135 Offshore from WS Måde |  |  | 4 | 0 | Empty | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-09 | 2020-05-04 | 2022-04-24 | 20 |  |  | DF /F /07/DFFA-PRV-300135 | DFFA-PRV-300135 Offshore from WS Måde | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100028061 | Exchange PRV-300135 in FP-3103 | DFFA-PRV-300135 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-04-08 | 2024-04-09 | 2024-04-09 | 2024-04-09 | 2020-05-04 | 2022-04-24 | 30 |  |  | DF /F /07/DFFA-PRV-300135 | DFFA-PRV-300135 Offshore from WS Måde | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100028061 | Exchange PRV-300135 in FP-3103 | DFFA-PRV-300135 Offshore from WS Måde |  |  | 0 | 0 | Empty | 2024-04-08 | 2024-04-09 | 2024-04-08 | 2024-04-08 | 2020-05-04 | 2022-04-24 | 40 |  |  | DF /F /07/DFFA-PRV-300135 | DFFA-PRV-300135 Offshore from WS Måde | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 14 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-10 | 2024-08-12 | 2023-04-14 | 2023-08-27 | 5 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | PRODTECH | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-12 | 2024-08-12 | 2023-04-14 | 2023-08-27 | 10 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-12 | 2024-08-13 | 2023-04-14 | 2023-08-27 | 20 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-MECH | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 28 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-13 | 2024-08-20 | 2023-04-14 | 2023-08-27 | 30 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 14 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-20 | 2024-08-21 | 2023-04-14 | 2023-08-27 | 35 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 6 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-21 | 2024-08-23 | 2023-04-14 | 2023-08-27 | 40 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 16 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-23 | 2024-08-27 | 2023-04-14 | 2023-08-27 | 50 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 6 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-27 | 2024-08-28 | 2023-04-14 | 2023-08-27 | 60 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-28 | 2024-08-29 | 2023-04-14 | 2023-08-27 | 70 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | PRODTECH | 2100086707 | LubeOil Seep Cpl.-Gbx.Probe XE-430267 | Remove coupling & guard incl. mark-up |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2023-04-14 | 2023-08-27 | 80 |  |  | DF /G /31/DFGA-GEA-4302 | Remove coupling & guard incl. mark-up | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009353 | FORCE assistance 20558 | PRIME/MALE |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /A /10/DFA-6-PHS-030-4052-FE-U | PRIME/MALE | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009353 | FORCE assistance 20558 | PRIME/MALE |  |  | 20 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-09 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /A /10/DFA-6-PHS-030-4052-FE-U | PRIME/MALE | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009353 | FORCE assistance 20558 | PRIME/MALE |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-09 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /A /10/DFA-6-PHS-030-4052-FE-U | PRIME/MALE | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009353 | FORCE assistance 20558 | PRIME/MALE |  |  | 37 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-11 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /A /10/DFA-6-PHS-030-4052-FE-U | PRIME/MALE | Unknown
3 | NOSD | WGN | MTN-INST | VEN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 0 | 0 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2022-09-01 | 2022-11-14 | 2021-12-12 | 2022-01-21 | 10 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 12 | 0 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2022-09-01 | 2022-11-14 | 2021-12-12 | 2022-01-21 | 20 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 4 | 9 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2022-08-29 | 2022-11-14 | 2021-12-12 | 2022-01-21 | 30 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 40 | 9 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2022-08-15 | 2022-11-14 | 2021-12-12 | 2022-01-21 | 40 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 7 | 9 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-12 | 2022-01-21 | 50 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 7 | 9 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-12 | 2022-01-21 | 60 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200009086 | Inspection of transmitter bolts on Dan F | Creating permits | PCNF | PCNF | 2 | 9 | SR BL-TEAM | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-12 | 2022-01-21 | 70 | PCNF | PCNF | DF /F /34 | Creating permits | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100064928 | DFAA-HCV-38100 hydraulic hoses expired | Production isolation |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-03-25 | 2022-05-04 | 10 |  |  | DF /A /12/DFAA-HCV-38100 | Production isolation | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100064928 | DFAA-HCV-38100 hydraulic hoses expired | Production isolation |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-03-25 | 2022-05-04 | 20 |  |  | DF /A /12/DFAA-HCV-38100 | Production isolation | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100064928 | DFAA-HCV-38100 hydraulic hoses expired | Production isolation |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-03-25 | 2022-05-04 | 30 |  |  | DF /A /12/DFAA-HCV-38100 | Production isolation | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100064928 | DFAA-HCV-38100 hydraulic hoses expired | Production isolation |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2022-03-25 | 2022-05-04 | 40 |  |  | DF /A /12/DFAA-HCV-38100 | Production isolation | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2020-04-06 | 2020-09-03 | 10 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | PRODTECH | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2020-04-06 | 2020-09-03 | 20 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2020-04-06 | 2020-09-03 | 30 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2020-04-06 | 2020-09-03 | 40 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2020-04-06 | 2020-09-03 | 50 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2020-04-06 | 2020-09-03 | 60 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2020-04-06 | 2020-09-03 | 70 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | PRODTECH | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2020-04-06 | 2020-09-03 | 80 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100023108 | DFA-18 Production XCV-30336 intern læk. | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2020-04-06 | 2020-09-03 | 90 | AWSC | AWSC | DF /A /10/DFAA-XCV-30336 | Prepare rigging equipment | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400350903 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 6 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-12 | 10 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111242 | New lifevest needed DFC | Replace lifevest | SECE | SECE | 1 | 1 | Empty | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-12-02 | 10 | SECE | SECE | DF /C /02/DFCI-LVS-0625 | Replace lifevest | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-MECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 0 | 86 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 10 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-MECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 0 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 20 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-MECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 0 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 30 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-RIGG | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 5 | 6 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-01-08 | 2024-02-08 | 2023-03-23 | 2023-08-05 | 40 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | PRODTECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 2 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 45 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-MECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 5 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 50 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-RIGG | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 10 | 27 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-01-11 | 2024-02-08 | 2023-03-23 | 2023-08-05 | 60 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-MECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 3 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 70 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-MECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 4 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 80 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | PRODTECH | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 2 | 0 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-23 | 2023-08-05 | 90 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-RIGG | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 5 | 5 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-01-12 | 2024-02-08 | 2023-03-23 | 2023-08-05 | 100 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | DFB-W14 | WDF | MTN-MECH | MTN-SCAF | 2100084868 | DFB-14 Choke broken | Rigging prework | PCNF | PCNF | 5 | 5 | W47-48 | 2024-07-29 | 2024-07-29 | 2024-01-08 | 2024-02-08 | 2023-03-23 | 2023-08-05 | 110 | PCNF | PCNF | DF /B /55/DFBA-CVA-30013 | Rigging prework | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2020-09-25 | 2020-09-25 | 2018-12-27 | 2019-03-27 | 10 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2020-09-30 | 2020-12-11 | 2018-12-27 | 2019-03-27 | 20 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-03-27 | 30 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 1 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-03-27 | 40 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-03-27 | 50 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2018-12-27 | 2019-03-27 | 60 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2018-12-27 | 2019-03-27 | 70 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-03-27 | 80 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 48 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-13 | 2018-12-27 | 2019-03-27 | 90 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003036 | Isolation assists FORCE 9071 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2018-12-27 | 2019-03-27 | 100 | PCNF | PCNF | DF /F /51/DFF-16-WI-035-7001-AM-U | BUILD SCAFFOLDING | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-01-31 | 2023-01-31 | 2019-01-29 | 2021-01-18 | 10 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 48.20000000000000284217094303 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-01-31 | 2023-02-04 | 2019-01-29 | 2021-01-18 | 20 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 16.100000000000001421085471515 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-04 | 2023-02-06 | 2019-01-29 | 2021-01-18 | 30 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 36 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-06 | 2023-02-09 | 2019-01-29 | 2021-01-18 | 40 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 8 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-09 | 2023-02-10 | 2019-01-29 | 2021-01-18 | 50 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 8 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-10 | 2023-02-11 | 2019-01-29 | 2021-01-18 | 60 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-11 | 2023-02-12 | 2019-01-29 | 2021-01-18 | 70 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 16.100000000000001421085471515 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-12 | 2023-02-14 | 2019-01-29 | 2021-01-18 | 80 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 36 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-14 | 2023-02-17 | 2019-01-29 | 2021-01-18 | 90 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003167 | DFF/78: Demol Platform on DFF east crane | L3 Safe Crane and areal below the crane. |  |  | 24.100000000000001421085471515 | 0 | Empty | 2023-01-31 | 2023-02-19 | 2023-02-17 | 2023-02-19 | 2019-01-29 | 2021-01-18 | 100 |  |  | DF /F /78/DFFA-A-6101 | L3 Safe Crane and areal below the crane. | Unknown
3 | DFX-OIL | WGN | MTN-TELE | MTN-TELE | 2200006511 | ESD2 shutdown test ref. EXP-407 DAF | ESD2 shutdown test ref. EXP-07 DAF | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-03-26 | 2021-06-24 | 10 | AWSC | AWSC | DF /C /03/DFCI-FP-0202 | ESD2 shutdown test ref. EXP-07 DAF | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400321278 | 1Y WELLHEAD CONTROL PANELS MAINT - DFB | WELLHEAD CONTROL PANELS MAINT - DFB | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-11 | 2024-10-05 | 2024-10-05 | 2024-04-11 | 2024-05-11 | 10 | SECE | SECE | DF /B /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT - DFB | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400321278 | 1Y WELLHEAD CONTROL PANELS MAINT - DFB | WELLHEAD CONTROL PANELS MAINT - DFB | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-11 | 2024-10-05 | 2024-10-05 | 2024-04-11 | 2024-05-11 | 20 | SECE | SECE | DF /B /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT - DFB | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400321278 | 1Y WELLHEAD CONTROL PANELS MAINT - DFB | WELLHEAD CONTROL PANELS MAINT - DFB | SECE | SECE | 14 | 0 | Empty | 2024-10-05 | 2024-10-11 | 2024-10-06 | 2024-10-09 | 2024-04-11 | 2024-05-11 | 30 | SECE | SECE | DF /B /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT - DFB | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321278 | 1Y WELLHEAD CONTROL PANELS MAINT - DFB | WELLHEAD CONTROL PANELS MAINT - DFB | SECE | SECE | 5 | 0 | Empty | 2024-10-05 | 2024-10-11 | 2024-10-09 | 2024-10-10 | 2024-04-11 | 2024-05-11 | 40 | SECE | SECE | DF /B /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT - DFB | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400321278 | 1Y WELLHEAD CONTROL PANELS MAINT - DFB | WELLHEAD CONTROL PANELS MAINT - DFB | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-11 | 2024-10-10 | 2024-10-11 | 2024-04-11 | 2024-05-11 | 50 | SECE | SECE | DF /B /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT - DFB | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018142 | Replace Motor protection 1841-M119 | Exchange of protection relay |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M119-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018142 | Replace Motor protection 1841-M119 | Exchange of protection relay |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M119-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018142 | Replace Motor protection 1841-M119 | Exchange of protection relay |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M119-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018142 | Replace Motor protection 1841-M119 | Exchange of protection relay |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M119-02 | Exchange of protection relay | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235914 | 1Y WAT CLARIFIER INJ PUMPS MAINT-3954/5 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-02-24 | 2023-03-26 | 10 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235914 | 1Y WAT CLARIFIER INJ PUMPS MAINT-3954/5 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-02-24 | 2023-03-26 | 20 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235914 | 1Y WAT CLARIFIER INJ PUMPS MAINT-3954/5 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-02-24 | 2023-03-26 | 30 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400235914 | 1Y WAT CLARIFIER INJ PUMPS MAINT-3954/5 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-02-24 | 2023-03-26 | 40 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235914 | 1Y WAT CLARIFIER INJ PUMPS MAINT-3954/5 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-02-24 | 2023-03-26 | 50 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235715 | 4Y 380V E-SWB MAINT-DFCC-N-1813 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235715 | 4Y 380V E-SWB MAINT-DFCC-N-1813 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 7 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235715 | 4Y 380V E-SWB MAINT-DFCC-N-1813 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235715 | 4Y 380V E-SWB MAINT-DFCC-N-1813 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241147 | 6M CHEM DISTR PANEL MAINT-DFFA-A-39709 | CHEM DISTR PANEL MAINT-DFFA-A-39709 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-03-13 | 2023-04-01 | 10 |  |  | DF /F /75/DFFA-A-39709 | CHEM DISTR PANEL MAINT-DFFA-A-39709 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 0 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-19 | 2024-04-25 | 2024-06-09 | 10 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 3 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-19 | 2024-04-25 | 2024-06-09 | 20 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 1 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-19 | 2024-08-19 | 2024-04-25 | 2024-06-09 | 30 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 3 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-20 | 2024-08-20 | 2024-04-25 | 2024-06-09 | 35 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 3 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-20 | 2024-08-21 | 2024-04-25 | 2024-06-09 | 40 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 1 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-21 | 2024-08-21 | 2024-04-25 | 2024-06-09 | 50 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-21 | 2024-08-22 | 2024-04-25 | 2024-06-09 | 60 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 3 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-22 | 2024-08-22 | 2024-04-25 | 2024-06-09 | 70 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111331 | Findings from 1Y check DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | SECE | SECE | 2 | 0 | Empty | 2024-08-19 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-04-25 | 2024-06-09 | 80 | SECE | SECE | DF /F /01/DFFA-A-0401 | Findings from 1Y check DFFA-A-0401 | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 30 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 40 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 50 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 60 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 70 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 80 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 90 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 100 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 110 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 120 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 130 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 140 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 150 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 160 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 170 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 180 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 190 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 200 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 210 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 220 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 230 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 240 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 250 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 260 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 270 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 280 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 290 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 300 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 310 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 320 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 330 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 340 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 350 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 360 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001474 | 001176912 001176912 | DK40- CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2020-09-09 | 2021-07-06 | 370 |  |  | DF /F | DK40- CONSUMABLE PRODTECH | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342400 | 3M LIFE-SAVING AND SAFETY EQ MAINT - DFG | LIFE-SAVING AND SAFETY EQ INSP - DFG | SECE | SECE | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-09-05 | 10 | SECE | SECE | DF /G /02/LIFE-SAVING-EQUIPMENT | LIFE-SAVING AND SAFETY EQ INSP - DFG | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 0 | 18 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 10 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 20 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 18 | 18 | Empty | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-09-14 | 2022-12-13 | 2023-01-27 | 30 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 40 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 12 | 7 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 50 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 12 | 15 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 60 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 70 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
2 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079419 | DFF Glycol Duplexfilter external leaking | Additional material | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-12-13 | 2023-01-27 | 80 | PCNF | PCNF | DF /F /30/DFFA-FIL-41041 | Additional material | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2022-11-01 | 2023-01-28 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 27 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2022-11-01 | 2023-01-28 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2022-11-01 | 2023-01-28 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2022-11-01 | 2023-01-28 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2022-11-01 | 2023-01-28 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2022-11-01 | 2023-01-28 | 60 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400221594 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A | ISOLATION ELECTRICAL | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2022-11-01 | 2023-01-28 | 70 | AWSC | AWSC | DF /F /61/DFFA-N-1801A | ISOLATION ELECTRICAL | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-MECH | 2200018264 | Install noise reduction panels DFC | Electrical assistance during installatio |  |  | 100 | 0 | W33-W34 | 2024-08-14 | 2024-09-02 | 2024-08-14 | 2024-08-27 | 2024-04-18 | 2024-06-02 | 20 |  |  | DF /C /84 | Electrical assistance during installatio | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018264 | Install noise reduction panels DFC | Electrical assistance during installatio |  |  | 50 | 0 | W33-W34 | 2024-08-14 | 2024-09-02 | 2024-08-27 | 2024-09-02 | 2024-04-18 | 2024-06-02 | 30 |  |  | DF /C /84 | Electrical assistance during installatio | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235657 | 4Y 400V N-SWB MAINT DFCI-N-1802-R10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R10A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235657 | 4Y 400V N-SWB MAINT DFCI-N-1802-R10 | ISOLATION ELECTRICAL | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R10A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235657 | 4Y 400V N-SWB MAINT DFCI-N-1802-R10 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R10A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235657 | 4Y 400V N-SWB MAINT DFCI-N-1802-R10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R10A | ISOLATION ELECTRICAL | Unknown
3 | DFGHPSEP | WGN | MTN-INST | PRODTECH | 2200003182 | CMAT:DFG Mount PRV on ESDV control panel | Line for missing materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2017-12-29 | 2018-03-29 | 10 | AWSC | AWSC | DF /G /32/DFGA-ESDV-340016 | Line for missing materials | Unknown
3 | DFGHPSEP | WGN | MTN-INST | MTN-INST | 2200003182 | CMAT:DFG Mount PRV on ESDV control panel | Line for missing materials | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2017-12-29 | 2018-03-29 | 20 | AWSC | AWSC | DF /G /32/DFGA-ESDV-340016 | Line for missing materials | Unknown
3 | DFGHPSEP | WGN | MTN-INST | PRODTECH | 2200003182 | CMAT:DFG Mount PRV on ESDV control panel | Line for missing materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-03 | 2017-12-29 | 2018-03-29 | 30 | AWSC | AWSC | DF /G /32/DFGA-ESDV-340016 | Line for missing materials | Unknown
3 | DFGHPSEP | WGN | MTN-INST | MTN-INST | 2200003182 | CMAT:DFG Mount PRV on ESDV control panel | Line for missing materials | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2017-12-29 | 2018-03-29 | 40 | AWSC | AWSC | DF /G /32/DFGA-ESDV-340016 | Line for missing materials | Unknown
3 | DFGHPSEP | WGN | MTN-INST | MTN-INST | 2200003182 | CMAT:DFG Mount PRV on ESDV control panel | Line for missing materials | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2017-12-29 | 2018-03-29 | 50 | AWSC | AWSC | DF /G /32/DFGA-ESDV-340016 | Line for missing materials | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001990 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL EL MUEHLHAN 2300001990 19.10.20 |  |  | 0 | 0 | Empty | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-11-23 | 10 |  |  | DF /C | MATERIAL EL MUEHLHAN 2300001990 19.10.20 | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001990 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL EL MUEHLHAN 2300001990 19.10.20 |  |  | 0 | 0 | Empty | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-11-23 | 20 |  |  | DF /C | MATERIAL EL MUEHLHAN 2300001990 19.10.20 | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001990 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL EL MUEHLHAN 2300001990 19.10.20 |  |  | 0 | 0 | Empty | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-11-23 | 30 |  |  | DF /C | MATERIAL EL MUEHLHAN 2300001990 19.10.20 | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001990 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL EL MUEHLHAN 2300001990 19.10.20 |  |  | 0 | 0 | Empty | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-11-23 | 40 |  |  | DF /C | MATERIAL EL MUEHLHAN 2300001990 19.10.20 | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001990 | DK40 EL/INST MATERIAL ORDER 2020 | MATERIAL EL MUEHLHAN 2300001990 19.10.20 |  |  | 0 | 0 | Empty | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-10-14 | 2020-11-23 | 50 |  |  | DF /C | MATERIAL EL MUEHLHAN 2300001990 19.10.20 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269623 | 1Y PROD WTR HP/LP SKD TEST-DFFA-A-5001 | PROD WTR HP/LP SKD TEST-DFFA-A-5001 |  |  | 18 | 0 | W23-W24 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2023-07-18 | 2023-08-23 | 10 |  |  | DF /F /27/DFFA-A-5001 | PROD WTR HP/LP SKD TEST-DFFA-A-5001 | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2021-06-19 | 2022-02-14 | 10 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-06-19 | 2022-02-14 | 20 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-03 | 2021-06-19 | 2022-02-14 | 25 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-06-19 | 2022-02-14 | 30 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-05 | 2021-06-19 | 2022-02-14 | 40 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-06-19 | 2022-02-14 | 50 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2021-06-19 | 2022-02-14 | 60 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2021-06-19 | 2022-02-14 | 70 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-06 | 2021-06-19 | 2022-02-14 | 80 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-06-19 | 2022-02-14 | 90 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100046329 | Both DFF-14 manifold Vlv's internal leak | Prepare rigging equipment | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-06-19 | 2022-02-14 | 100 | AWSC | AWSC | DF /F /55/DFF14-WATER-INJECTION | Prepare rigging equipment | Unknown
3 | DFB-3560 | WDF | MTN-INST | PRODTECH | 2100027601 | SMAT:Udskiftning af trim i PCV-57309 | Udskiftning af PCV trim | AWSC | AWSC | 2 | 0 | 3560 being decomissioned | 2024-09-18 | 2024-09-24 | 2024-09-18 | 2024-09-18 | 2017-09-01 | 2017-09-21 | 10 | AWSC | AWSC | DF /B /70/DFBA-PCV-57309 | Udskiftning af PCV trim | Unknown
3 | DFB-3560 | WDF | MTN-INST | MTN-INST | 2100027601 | SMAT:Udskiftning af trim i PCV-57309 | Udskiftning af PCV trim | AWSC | AWSC | 5 | 0 | 3560 being decomissioned | 2024-09-18 | 2024-09-24 | 2024-09-18 | 2024-09-20 | 2017-09-01 | 2017-09-21 | 20 | AWSC | AWSC | DF /B /70/DFBA-PCV-57309 | Udskiftning af PCV trim | Unknown
3 | DFB-3560 | WDF | MTN-INST | MTN-MECH | 2100027601 | SMAT:Udskiftning af trim i PCV-57309 | Udskiftning af PCV trim | AWSC | AWSC | 10 | 0 | 3560 being decomissioned | 2024-09-18 | 2024-09-24 | 2024-09-20 | 2024-09-22 | 2017-09-01 | 2017-09-21 | 30 | AWSC | AWSC | DF /B /70/DFBA-PCV-57309 | Udskiftning af PCV trim | Unknown
3 | DFB-3560 | WDF | MTN-INST | MTN-INST | 2100027601 | SMAT:Udskiftning af trim i PCV-57309 | Udskiftning af PCV trim | AWSC | AWSC | 5 | 0 | 3560 being decomissioned | 2024-09-18 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2017-09-01 | 2017-09-21 | 40 | AWSC | AWSC | DF /B /70/DFBA-PCV-57309 | Udskiftning af PCV trim | Unknown
3 | DFB-3560 | WDF | MTN-INST | PRODTECH | 2100027601 | SMAT:Udskiftning af trim i PCV-57309 | Udskiftning af PCV trim | AWSC | AWSC | 2 | 0 | 3560 being decomissioned | 2024-09-18 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2017-09-01 | 2017-09-21 | 50 | AWSC | AWSC | DF /B /70/DFBA-PCV-57309 | Udskiftning af PCV trim | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053482 | Replace floodlight DFC1805-15-L31A | Replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 10 |  |  | DF /C /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053482 | Replace floodlight DFC1805-15-L31A | Replace floodlight |  |  | 9 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-31 | 2022-03-30 | 20 |  |  | DF /C /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053482 | Replace floodlight DFC1805-15-L31A | Replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-10-31 | 2022-03-30 | 30 |  |  | DF /C /62 | Replace floodlight | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 10 |  |  | DF /C | Ladder | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 21 |  |  | DF /C | Ladder | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 31 |  |  | DF /C | Ladder | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 41 |  |  | DF /C | Ladder | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 51 |  |  | DF /C | Ladder | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 61 |  |  | DF /C | Ladder | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000659 | DK46 BUR PROD MATERIAL ORDER 2020 | Ladder |  |  | 0 | 0 | Empty | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-07-31 | 2020-01-01 | 2020-12-31 | 71 |  |  | DF /C | Ladder | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 93 | 1.5 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-04 | 2023-04-13 | 2021-03-24 | 2021-03-29 | 10 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 16 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-13 | 2023-04-15 | 2021-03-24 | 2021-03-29 | 20 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 19 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-15 | 2023-04-17 | 2021-03-24 | 2021-03-29 | 30 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 12 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-17 | 2023-04-18 | 2021-03-24 | 2021-03-29 | 40 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 74 | 3.5 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-18 | 2023-04-25 | 2021-03-24 | 2021-03-29 | 50 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 11 | 3 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-25 | 2023-04-25 | 2021-03-24 | 2021-03-29 | 60 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 7 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-25 | 2023-04-26 | 2021-03-24 | 2021-03-29 | 70 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 7 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-26 | 2023-04-26 | 2021-03-24 | 2021-03-29 | 80 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 37 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-26 | 2023-04-30 | 2021-03-24 | 2021-03-29 | 90 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 44 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-04-30 | 2023-05-05 | 2021-03-24 | 2021-03-29 | 100 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 7 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-05-05 | 2023-05-06 | 2021-03-24 | 2021-03-29 | 110 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002820 | DAF OCG NPT order -ENG469F-SPENT H2S SCA | Planned drills & meetings | PCNF | PCNF | 37 | 0 | Empty | 2023-04-04 | 2023-05-10 | 2023-05-06 | 2023-05-10 | 2021-03-24 | 2021-03-29 | 120 | PCNF | PCNF | DF /G | Planned drills & meetings | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100055728 | ANOP Misaligned WI pipe support | Aligne WI pipe support. |  |  | 35 | 0 | Empty | 2024-03-15 | 2024-03-17 | 2024-03-15 | 2024-03-17 | 2021-10-07 | 2022-01-05 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Aligne WI pipe support. | Unknown
A | DFG-3590 | WPM | MTN-MECH | PRODTECH | 2400214994 | 8KH SDV/BDV FUNC TEST WI DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | AWSCSECE | AWSCSECE | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-19 | 2024-07-16 | 2024-07-16 | 2022-10-14 | 2022-11-13 | 10 | AWSCSECE | AWSCSECE | DF /G /54/DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-MECH | 2400214994 | 8KH SDV/BDV FUNC TEST WI DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | AWSCSECE | AWSCSECE | 8.5 | 6 | W29-W30 | 2024-07-16 | 2024-07-19 | 2024-07-16 | 2024-07-18 | 2022-10-14 | 2022-11-13 | 20 | AWSCSECE | AWSCSECE | DF /G /54/DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-INST | 2400214994 | 8KH SDV/BDV FUNC TEST WI DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | AWSCSECE | AWSCSECE | 1 | 0 | W29-W30 | 2024-07-16 | 2024-07-19 | 2024-07-18 | 2024-07-19 | 2022-10-14 | 2022-11-13 | 30 | AWSCSECE | AWSCSECE | DF /G /54/DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | Unknown
A | DFG-3590 | WPM | MTN-MECH | PRODTECH | 2400214994 | 8KH SDV/BDV FUNC TEST WI DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | AWSCSECE | AWSCSECE | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2022-10-14 | 2022-11-13 | 40 | AWSCSECE | AWSCSECE | DF /G /54/DFGA-A-3590 | SDV/BDV FUNC TEST WI DFGA-A-3590 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100079745 | Fail on DFF HVAC | Trouble shoot SSL-120511 |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-02-03 | 2023-06-18 | 10 |  |  | DF /F /09/DFFA-SSL-120511 | Trouble shoot SSL-120511 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100079745 | Fail on DFF HVAC | Trouble shoot SSL-120511 |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-02-03 | 2023-06-18 | 20 |  |  | DF /F /09/DFFA-SSL-120511 | Trouble shoot SSL-120511 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100079745 | Fail on DFF HVAC | Trouble shoot SSL-120511 |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-02-03 | 2023-06-18 | 30 |  |  | DF /F /09/DFFA-SSL-120511 | Trouble shoot SSL-120511 | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400259873 | 6M PORTABLE INSTRUMENTS CALIBR - DFG | Pressure calibrators requested by site |  |  | 6 | 6 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2023-06-03 | 2023-06-28 | 10 |  |  | DF /G /84 | Pressure calibrators requested by site | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400259873 | 6M PORTABLE INSTRUMENTS CALIBR - DFG | Pressure calibrators requested by site |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2023-06-03 | 2023-06-28 | 20 |  |  | DF /G /84 | Pressure calibrators requested by site | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100062487 | Fault finding on HT DP-1830-Q9 | Isolate accordingly and prove dead |  |  | 12 | 0 | W27-W28 | 2024-07-01 | 2024-07-06 | 2024-07-01 | 2024-07-02 | 2022-02-26 | 2022-05-27 | 10 |  |  | DF /C /61/DFCI-DP-1830 | Isolate accordingly and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100062487 | Fault finding on HT DP-1830-Q9 | Isolate accordingly and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-06 | 2024-07-02 | 2024-07-03 | 2022-02-26 | 2022-05-27 | 20 |  |  | DF /C /61/DFCI-DP-1830 | Isolate accordingly and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100062487 | Fault finding on HT DP-1830-Q9 | Isolate accordingly and prove dead |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-06 | 2024-07-03 | 2024-07-05 | 2022-02-26 | 2022-05-27 | 30 |  |  | DF /C /61/DFCI-DP-1830 | Isolate accordingly and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100062487 | Fault finding on HT DP-1830-Q9 | Isolate accordingly and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-06 | 2024-07-05 | 2024-07-05 | 2022-02-26 | 2022-05-27 | 40 |  |  | DF /C /61/DFCI-DP-1830 | Isolate accordingly and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100062487 | Fault finding on HT DP-1830-Q9 | Isolate accordingly and prove dead |  |  | 12 | 0 | W27-W28 | 2024-07-01 | 2024-07-06 | 2024-07-05 | 2024-07-06 | 2022-02-26 | 2022-05-27 | 50 |  |  | DF /C /61/DFCI-DP-1830 | Isolate accordingly and prove dead | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400281429 | 3M SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-09-29 | 2023-10-10 | 10 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400281429 | 3M SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2023-09-29 | 2023-10-10 | 12 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2021-03-07 | 2021-08-04 | 10 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-17 | 2021-03-07 | 2021-08-04 | 20 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-17 | 2021-03-07 | 2021-08-04 | 30 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-18 | 2021-03-07 | 2021-08-04 | 40 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-20 | 2021-03-07 | 2021-08-04 | 50 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2021-03-07 | 2021-08-04 | 60 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-20 | 2021-03-07 | 2021-08-04 | 70 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2021-03-07 | 2021-08-04 | 80 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100042725 | HCV-380138-D hard to operate | Scaffold Asistance Lifting point |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2021-03-07 | 2021-08-04 | 90 |  |  | DF /G /11/DFGA-HCV-380138-D | Scaffold Asistance Lifting point | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009214 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /A /70/DFA-2-GFS-057-4023-BD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009214 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-08 | 2024-01-09 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /A /70/DFA-2-GFS-057-4023-BD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009214 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-09 | 2024-01-12 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /A /70/DFA-2-GFS-057-4023-BD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009214 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-12 | 2024-01-12 | 2022-02-07 | 2022-07-07 | 35 |  |  | DF /A /70/DFA-2-GFS-057-4023-BD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009214 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-12 | 2024-01-16 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /A /70/DFA-2-GFS-057-4023-BD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009214 | Insulation assist FORCE 16210 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-19 | 2024-01-16 | 2024-01-19 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /A /70/DFA-2-GFS-057-4023-BD-T | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100088905 | DFFA-PDIT-360033 Replace manifold and bo | additional mat as agreed wirth purchase |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-23 | 2023-10-05 | 10 |  |  | DF /F /21/DFFA-PDIT-360033 | additional mat as agreed wirth purchase | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100088905 | DFFA-PDIT-360033 Replace manifold and bo | additional mat as agreed wirth purchase |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-23 | 2023-10-05 | 20 |  |  | DF /F /21/DFFA-PDIT-360033 | additional mat as agreed wirth purchase | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100088905 | DFFA-PDIT-360033 Replace manifold and bo | additional mat as agreed wirth purchase |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-23 | 2023-10-05 | 30 |  |  | DF /F /21/DFFA-PDIT-360033 | additional mat as agreed wirth purchase | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100088905 | DFFA-PDIT-360033 Replace manifold and bo | additional mat as agreed wirth purchase |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-23 | 2023-10-05 | 40 |  |  | DF /F /21/DFFA-PDIT-360033 | additional mat as agreed wirth purchase | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100088905 | DFFA-PDIT-360033 Replace manifold and bo | additional mat as agreed wirth purchase |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-23 | 2023-10-05 | 50 |  |  | DF /F /21/DFFA-PDIT-360033 | additional mat as agreed wirth purchase | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-20 | 2024-06-21 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-21 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 6 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 10 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-27 | 2024-06-28 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-28 | 2024-06-29 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-29 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-30 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-30 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284248 | PSV Calibration - DFCI-PSV-57131 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 10 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCI-PSV-57131 | Scaffolding | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 10 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 20 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 30 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 40 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 50 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 60 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 70 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000655 | DK40 LAGGER MATERIAL ORDER 2020/21 | DK46 LAGGER MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2021-05-11 | 2020-01-01 | 2020-12-31 | 80 |  |  | DF /C | DK46 LAGGER MATERIAL ORDER 2020 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400321730 | DFA-55-PHS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /55/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 8 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-28 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 5 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-INST | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 0.5 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-28 | 2023-06-28 | 2023-03-28 | 2025-09-13 | 10 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-INST | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 2 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-28 | 2023-06-28 | 2023-03-28 | 2025-09-13 | 20 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-MECH | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 4 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-28 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 40 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | WELLSUPV | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 4 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 50 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-INST | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 2 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 60 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-INST | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 0.5 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 70 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-INST | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 1 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 80 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
4 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100075418 | Corroded support for DFGA-FIT-390622 | Dismount transmitter from a stand |  |  | 4 | 0 | Empty | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-06-29 | 2023-03-28 | 2025-09-13 | 90 |  |  | DF /G /75/DFGA-FIT-390622 | Dismount transmitter from a stand | Unknown
A | DFC-1620 | WPM | MTN-TURB | MTN-TURB | 2400301993 | 9M DFCI-G-1620 CHECK, SOLAR TURBINES | Visual inspection |  |  | 12 | 12 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-04 | 2024-01-17 | 2024-02-02 | 24 |  |  | DF /C /60/DFCI-G-1620 | Visual inspection | Unknown
3 | DFB-W06 | WDF | MTN-INST | PRODTECH | 2100025415 | DFBA-FT-35027 Disassemble and repack, va | L3 Isolation of DFBA-FT-35027 | AWSC | AWSC | 3 | 0 | BL-TEAM W/2100036051 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2019-10-20 | 2020-01-18 | 10 | AWSC | AWSC | DF /B /55/DFBA-FT-35027 | L3 Isolation of DFBA-FT-35027 | Unknown
3 | DFB-W06 | WDF | MTN-INST | MTN-INST | 2100025415 | DFBA-FT-35027 Disassemble and repack, va | L3 Isolation of DFBA-FT-35027 | AWSC | AWSC | 4 | 0 | BL-TEAM W/2100036051 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-10-20 | 2020-01-18 | 30 | AWSC | AWSC | DF /B /55/DFBA-FT-35027 | L3 Isolation of DFBA-FT-35027 | Unknown
3 | DFB-W06 | WDF | MTN-INST | PRODTECH | 2100025415 | DFBA-FT-35027 Disassemble and repack, va | L3 Isolation of DFBA-FT-35027 | AWSC | AWSC | 3 | 0 | BL-TEAM W/2100036051 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2019-10-20 | 2020-01-18 | 40 | AWSC | AWSC | DF /B /55/DFBA-FT-35027 | L3 Isolation of DFBA-FT-35027 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235791 | 4Y 380V HT-DP MAINT-DFCI-DP-1832 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1832 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235791 | 4Y 380V HT-DP MAINT-DFCI-DP-1832 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1832 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235791 | 4Y 380V HT-DP MAINT-DFCI-DP-1832 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1832 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235791 | 4Y 380V HT-DP MAINT-DFCI-DP-1832 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1832 | ISOLATION ELECTRICAL | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200013535 | Contingency vlvs for LG's on DFCM-V-5002 | Contingency vlvs for LG's on DFCM-V-5002 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-02-09 | 2023-03-26 | 10 |  |  | DF /C /28/DFCM-V-5002 | Contingency vlvs for LG's on DFCM-V-5002 | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344049 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3951 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-15 | 2024-08-26 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-20 | 10 |  |  | DF /F /75/DFFA-A-3951 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344049 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3951 | ISOLATION BY PRODUCTION |  |  | 30 | 0 | Empty | 2024-08-15 | 2024-08-26 | 2024-08-15 | 2024-08-22 | 2024-08-15 | 2024-09-20 | 20 |  |  | DF /F /75/DFFA-A-3951 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344049 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3951 | ISOLATION BY PRODUCTION |  |  | 15 | 0 | Empty | 2024-08-15 | 2024-08-26 | 2024-08-22 | 2024-08-26 | 2024-08-15 | 2024-09-20 | 30 |  |  | DF /F /75/DFFA-A-3951 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344049 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3951 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-15 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-15 | 2024-09-20 | 40 |  |  | DF /F /75/DFFA-A-3951 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-07-29 | 2024-07-29 | 2024-10-16 | 2027-04-04 | 10 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 30 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-07-29 | 2024-08-05 | 2024-10-16 | 2027-04-04 | 20 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-05 | 2024-08-06 | 2024-10-16 | 2027-04-04 | 30 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 20 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-06 | 2024-08-11 | 2024-10-16 | 2027-04-04 | 40 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-06 | 2024-08-07 | 2024-10-16 | 2027-04-04 | 50 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-07 | 2024-08-08 | 2024-10-16 | 2027-04-04 | 51 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-08 | 2024-08-08 | 2024-10-16 | 2027-04-04 | 60 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-08 | 2024-08-08 | 2024-10-16 | 2027-04-04 | 70 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 20 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-08 | 2024-08-13 | 2024-10-16 | 2027-04-04 | 80 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-13 | 2024-08-15 | 2024-10-16 | 2027-04-04 | 90 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-14 | 2024-08-15 | 2024-10-16 | 2027-04-04 | 100 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-14 | 2024-08-15 | 2024-10-16 | 2027-04-04 | 110 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110984 | Actuator has Ri8Q external corrosion. | Messure Valve topworks and fill in sketc |  |  | 20 | 0 | W27-W28 | 2024-07-29 | 2024-08-20 | 2024-08-15 | 2024-08-20 | 2024-10-16 | 2027-04-04 | 120 |  |  | DF /F /54/DFFB-XCV-357002 | Messure Valve topworks and fill in sketc | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100099956 | DFE/78 Switch between telescope and swin | Function test and leak test |  |  | 1 | 6 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2023-11-29 | 2024-04-12 | 10 |  |  | DF /E /78/DFEZ-X-6150 | Function test and leak test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100099956 | DFE/78 Switch between telescope and swin | Function test and leak test |  |  | 6 | 20 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2023-11-29 | 2024-04-12 | 20 |  |  | DF /E /78/DFEZ-X-6150 | Function test and leak test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100099956 | DFE/78 Switch between telescope and swin | Function test and leak test |  |  | 6 | 8 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2023-11-29 | 2024-04-12 | 30 |  |  | DF /E /78/DFEZ-X-6150 | Function test and leak test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100099956 | DFE/78 Switch between telescope and swin | Function test and leak test |  |  | 2 | 5 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2023-11-29 | 2024-04-12 | 40 |  |  | DF /E /78/DFEZ-X-6150 | Function test and leak test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100099956 | DFE/78 Switch between telescope and swin | Function test and leak test |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2023-11-29 | 2024-04-12 | 50 |  |  | DF /E /78/DFEZ-X-6150 | Function test and leak test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100099956 | DFE/78 Switch between telescope and swin | Function test and leak test |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2023-11-29 | 2024-04-12 | 60 |  |  | DF /E /78/DFEZ-X-6150 | Function test and leak test | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 3 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-07 | 2024-06-08 | 2019-09-30 | 2020-02-27 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-08 | 2024-06-09 | 2019-09-30 | 2020-02-27 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-09 | 2024-06-09 | 2019-09-30 | 2020-02-27 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 2 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-09 | 2024-06-10 | 2019-09-30 | 2020-02-27 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-10 | 2024-06-11 | 2019-09-30 | 2020-02-27 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 2 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-11 | 2024-06-12 | 2019-09-30 | 2020-02-27 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-12 | 2024-06-12 | 2019-09-30 | 2020-02-27 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-12 | 2024-06-13 | 2019-09-30 | 2020-02-27 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
4 | DFGHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022353 | Replace stem gasket DFGA-LCV-340022. | Prepare rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-14 | 2024-06-13 | 2024-06-14 | 2019-09-30 | 2020-02-27 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /20/DFGA-LCV-340022 | Prepare rigging equipment | Unknown
1 | NE | WRO | MTN-TELE | MTN-TELE | 2300004264 | IT0098 - Dan F telecom support to instal | IT0098 - Dan F telecom support to instal | SCH | SCH | 84 | 0 | W15-W16 | 2024-10-05 | 2024-10-25 | 2024-10-05 | 2024-10-25 | 2022-11-08 | 2022-11-23 | 10 | SCH | SCH | DF /C /08/DFCI-DT-14-10-02 | IT0098 - Dan F telecom support to instal | Unknown
A | DAN-OIL | WPM | MTN-MECH | PRODTECH | 2400325536 | 1Y ESDV LEAK TEST-DFBA-ESDV-38091 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-11-17 | 2024-11-18 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2024-12-17 | 10 | AWSCSECE | AWSCSECE | DF /B /23/DFBA-ESDV-38091 | ISOLATION BY PRODUCTION | Unknown
A | DAN-OIL | WPM | MTN-MECH | PRODTECH | 2400325536 | 1Y ESDV LEAK TEST-DFBA-ESDV-38091 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-11-17 | 2024-11-18 | 2024-11-17 | 2024-11-18 | 2024-11-17 | 2024-12-17 | 20 | AWSCSECE | AWSCSECE | DF /B /23/DFBA-ESDV-38091 | ISOLATION BY PRODUCTION | Unknown
A | DAN-OIL | WPM | MTN-MECH | PRODTECH | 2400325536 | 1Y ESDV LEAK TEST-DFBA-ESDV-38091 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-11-17 | 2024-11-18 | 2024-11-18 | 2024-11-18 | 2024-11-17 | 2024-12-17 | 30 | AWSCSECE | AWSCSECE | DF /B /23/DFBA-ESDV-38091 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100056490 | Pumpe P-3928 tripper ved start | Faultfinding trip of PM-3928 at start | PCNFSCH | PCNFSCH | 15 | 35 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-28 | 2022-05-27 | 20 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3928 | Faultfinding trip of PM-3928 at start | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100056490 | Pumpe P-3928 tripper ved start | Faultfinding trip of PM-3928 at start | PCNFSCH | PCNFSCH | 0 | 4 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-28 | 2022-05-27 | 30 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3928 | Faultfinding trip of PM-3928 at start | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056490 | Pumpe P-3928 tripper ved start | Faultfinding trip of PM-3928 at start | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-28 | 2022-05-27 | 40 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3928 | Faultfinding trip of PM-3928 at start | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056490 | Pumpe P-3928 tripper ved start | Faultfinding trip of PM-3928 at start | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-12-28 | 2022-05-27 | 50 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3928 | Faultfinding trip of PM-3928 at start | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342428 | 1Y CATALYTIC GAS DETECTORS - DFC LVL 2 | CATALYTIC GAS DETECTORS CHECK | SECE | SECE | 35 | 0 | W33-W34 | 2024-08-12 | 2024-08-21 | 2024-08-12 | 2024-08-21 | 2024-07-29 | 2024-08-28 | 10 | SECE | SECE | DF /C /03/FGS-DETECTORS | CATALYTIC GAS DETECTORS CHECK | Unknown
2 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100113532 | DFG Air comp LCP-5451 short circuit | Demount Socket from Panel |  |  | 0 | 71 | Empty | 2024-06-21 | 2024-06-22 | 2024-06-21 | 2024-06-21 | 2024-05-31 | 2024-07-15 | 10 |  |  | DF /G /05/DFGA-N-1843-A03-JA001 | Demount Socket from Panel | Unknown
2 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100113532 | DFG Air comp LCP-5451 short circuit | Demount Socket from Panel |  |  | 0 | 0 | Empty | 2024-06-21 | 2024-06-22 | 2024-06-21 | 2024-06-21 | 2024-05-31 | 2024-07-15 | 20 |  |  | DF /G /05/DFGA-N-1843-A03-JA001 | Demount Socket from Panel | Unknown
2 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100113532 | DFG Air comp LCP-5451 short circuit | Demount Socket from Panel |  |  | 3 | 0 | Empty | 2024-06-21 | 2024-06-22 | 2024-06-21 | 2024-06-22 | 2024-05-31 | 2024-07-15 | 30 |  |  | DF /G /05/DFGA-N-1843-A03-JA001 | Demount Socket from Panel | Unknown
2 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100113532 | DFG Air comp LCP-5451 short circuit | Demount Socket from Panel |  |  | 3 | 11 | Empty | 2024-06-21 | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-05-31 | 2024-07-15 | 40 |  |  | DF /G /05/DFGA-N-1843-A03-JA001 | Demount Socket from Panel | Unknown
2 | NOSD | WDF | VEN-ELEC | VEN-ELEC | 2100113532 | DFG Air comp LCP-5451 short circuit | Demount Socket from Panel |  |  | 3 | 12 | Empty | 2024-06-21 | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-05-31 | 2024-07-15 | 50 |  |  | DF /G /05/DFGA-N-1843-A03-JA001 | Demount Socket from Panel | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339050 | DFB_1Y_37300 INT STRUCT INSP - GVI | DFB_1Y_37300 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_37300 (CHEMICAL TANK SKID) | DFB_1Y_37300 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-16 | 2019-07-12 | 2019-08-21 | 10 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-16 | 2024-09-16 | 2019-07-12 | 2019-08-21 | 20 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-16 | 2024-09-17 | 2019-07-12 | 2019-08-21 | 30 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-17 | 2024-09-17 | 2019-07-12 | 2019-08-21 | 40 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-17 | 2024-09-18 | 2019-07-12 | 2019-08-21 | 50 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-18 | 2024-09-19 | 2019-07-12 | 2019-08-21 | 60 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-20 | 2019-07-12 | 2019-08-21 | 70 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-20 | 2024-09-20 | 2019-07-12 | 2019-08-21 | 80 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-20 | 2024-09-21 | 2019-07-12 | 2019-08-21 | 90 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2024-09-21 | 2019-07-12 | 2019-08-21 | 100 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2024-09-22 | 2019-07-12 | 2019-08-21 | 110 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2019-07-12 | 2019-08-21 | 120 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024612 | LCV-410492 Lækage v. stempel | Isolate LCV-410492 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2019-07-12 | 2019-08-21 | 130 |  |  | DF /G /30/DFGA-LCV-410492 | Isolate LCV-410492 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-21 | 2024-06-24 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-24 | 2024-06-25 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 10 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-26 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-27 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-28 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-28 | 2024-06-29 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284252 | PSV Calibration - DFCM-PSV-57665 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /70/DFCM-PSV-57665 | Rigging assist (remove) | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100023940 | Change out needle valve on 300bar | L3 deisolate system | AWSC | AWSC | 5 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-03-06 | 2019-04-15 | 10 | AWSC | AWSC | DF /A /07/DFAA-A-3102 | L3 deisolate system | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100023940 | Change out needle valve on 300bar | L3 deisolate system | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2019-03-06 | 2019-04-15 | 20 | AWSC | AWSC | DF /A /07/DFAA-A-3102 | L3 deisolate system | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100023940 | Change out needle valve on 300bar | L3 deisolate system | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2019-03-06 | 2019-04-15 | 30 | AWSC | AWSC | DF /A /07/DFAA-A-3102 | L3 deisolate system | Unknown
3 | DFA-OIL | WDF | MTN-INST | MTN-INST | 2100023940 | Change out needle valve on 300bar | L3 deisolate system | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2019-03-06 | 2019-04-15 | 40 | AWSC | AWSC | DF /A /07/DFAA-A-3102 | L3 deisolate system | Unknown
3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000920 | DAFDEH-HW Scope-DFFA-FP-2039 | method statement |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2018-07-22 | 2018-10-20 | 10 |  |  | DF /B /04/DFBA-FP-2039 | method statement | Unknown
3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000920 | DAFDEH-HW Scope-DFFA-FP-2039 | method statement |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2018-07-22 | 2018-10-20 | 20 |  |  | DF /B /04/DFBA-FP-2039 | method statement | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101250 | Replace PCV-570004 | Replace PCV-570004 |  |  | 3 | 0 | Empty | 2024-09-30 | 2024-10-02 | 2024-09-30 | 2024-09-30 | 2023-12-19 | 2024-10-01 | 10 |  |  | DF /G /30/DFG-1-GFS-057-0011-AB-U | Replace PCV-570004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101250 | Replace PCV-570004 | Replace PCV-570004 |  |  | 3 | 0 | Empty | 2024-09-30 | 2024-10-02 | 2024-09-30 | 2024-10-01 | 2023-12-19 | 2024-10-01 | 20 |  |  | DF /G /30/DFG-1-GFS-057-0011-AB-U | Replace PCV-570004 | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101250 | Replace PCV-570004 | Replace PCV-570004 |  |  | 3 | 0 | Empty | 2024-09-30 | 2024-10-02 | 2024-10-01 | 2024-10-02 | 2023-12-19 | 2024-10-01 | 30 |  |  | DF /G /30/DFG-1-GFS-057-0011-AB-U | Replace PCV-570004 | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005110 | DK40 - REPLACED BY 230008271 | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 0 | 0 | Empty | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2026-03-01 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005110 | DK40 - REPLACED BY 230008271 | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 1 | 0 | Empty | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2026-03-01 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005110 | DK40 - REPLACED BY 230008271 | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 1 | 0 | Empty | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2026-03-01 | 30 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005110 | DK40 - REPLACED BY 230008271 | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 1 | 0 | Empty | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2026-03-01 | 40 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005110 | DK40 - REPLACED BY 230008271 | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 0 | 0 | Empty | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2026-03-01 | 50 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300005110 | DK40 - REPLACED BY 230008271 | DK40 - CONSUMABLE PROD - CHEMICALS |  |  | 0 | 0 | Empty | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2023-09-13 | 2026-03-01 | 60 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - CHEMICALS | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-07 | 2024-06-07 | 2024-10-12 | 2024-12-31 | 10 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-07 | 2024-06-08 | 2024-10-12 | 2024-12-31 | 20 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 5 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-08 | 2024-06-09 | 2024-10-12 | 2024-12-31 | 30 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-09 | 2024-06-10 | 2024-10-12 | 2024-12-31 | 40 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-10 | 2024-06-11 | 2024-10-12 | 2024-12-31 | 50 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-11 | 2024-06-11 | 2024-10-12 | 2024-12-31 | 60 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 5 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-11 | 2024-06-12 | 2024-10-12 | 2024-12-31 | 70 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-12 | 2024-06-13 | 2024-10-12 | 2024-12-31 | 80 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-10-12 | 2024-12-31 | 90 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-10-12 | 2024-12-31 | 100 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284307 | PSV Calibration - DFGA-PSV-431102 | new psv | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-10-12 | 2024-12-31 | 110 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-PSV-431102 | new psv | Unknown
C | NOSD | WPM | MTN-MECH | VEN-MECH | 2400329520 | 1Y SW FILTERS & BLOWERS MAINT - DFE | SW FILTERS & BLOWERS MAINT - DFE | AWSC | AWSC | 2 | 0 | Empty | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-06-23 | 10 | AWSC | AWSC | DF /E /51/DFEY-FT-3511 | SW FILTERS & BLOWERS MAINT - DFE | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329520 | 1Y SW FILTERS & BLOWERS MAINT - DFE | SW FILTERS & BLOWERS MAINT - DFE | AWSC | AWSC | 2 | 0 | Empty | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-06-23 | 20 | AWSC | AWSC | DF /E /51/DFEY-FT-3511 | SW FILTERS & BLOWERS MAINT - DFE | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284301 | PSV Exchange - DFGA-PSV-500742 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /28/DFGA-PSV-500742 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284301 | PSV Exchange - DFGA-PSV-500742 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /28/DFGA-PSV-500742 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284301 | PSV Exchange - DFGA-PSV-500742 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /28/DFGA-PSV-500742 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284301 | PSV Exchange - DFGA-PSV-500742 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /28/DFGA-PSV-500742 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284301 | PSV Exchange - DFGA-PSV-500742 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /28/DFGA-PSV-500742 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284301 | PSV Exchange - DFGA-PSV-500742 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /28/DFGA-PSV-500742 | Isolation of PSV | Unknown
D | NOSD | WPM | PRODLABO | PRODLABO | 2400298184 | 3M SAMPLING OF OiW CORRELATIONS | SAMPLE OF OiW CORRELATION DFF,DFG,DFC |  |  | 1 | 0 | Empty | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2024-01-01 | 2023-12-31 | 2024-01-15 | 10 |  |  | DF /G /27/DFGA-AT-500600 | SAMPLE OF OiW CORRELATION DFF,DFG,DFC | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | VEN-MECH | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-01 | 2018-06-13 | 2018-06-18 | 2 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | VEN-MECH | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-01 | 2018-06-13 | 2018-06-18 | 3 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | VEN-MECH | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-01 | 2018-06-13 | 2018-06-18 | 4 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-SCAF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-01 | 2018-06-13 | 2018-06-18 | 10 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 6 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-01 | 2018-06-13 | 2018-06-18 | 15 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-SCAF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 35.39999999999999857891452847 | 26 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-01 | 2018-06-13 | 2018-06-18 | 20 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-RIGG | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 26.800000000000000710542735752 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-01 | 2023-04-08 | 2018-06-13 | 2018-06-18 | 30 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-08 | 2023-04-09 | 2018-06-13 | 2018-06-18 | 31 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-09 | 2023-04-10 | 2018-06-13 | 2018-06-18 | 32 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-10 | 2023-04-10 | 2018-06-13 | 2018-06-18 | 33 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-10 | 2023-04-11 | 2018-06-13 | 2018-06-18 | 34 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PIPF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 33.5 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-11 | 2023-04-13 | 2018-06-13 | 2018-06-18 | 40 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-SCAF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 17.399999999999998578914528472 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-13 | 2023-04-15 | 2018-06-13 | 2018-06-18 | 50 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-SCAF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-15 | 2023-04-18 | 2018-06-13 | 2018-06-18 | 60 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-ELEC | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 4 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-18 | 2023-04-19 | 2018-06-13 | 2018-06-18 | 70 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-RIGG | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 16 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-19 | 2023-04-21 | 2018-06-13 | 2018-06-18 | 80 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PIPF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 32 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-21 | 2023-04-23 | 2018-06-13 | 2018-06-18 | 90 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PIPF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 16 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-23 | 2023-04-24 | 2018-06-13 | 2018-06-18 | 100 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-RIGG | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-24 | 2023-04-26 | 2018-06-13 | 2018-06-18 | 110 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PIPF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 16 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-26 | 2023-04-27 | 2018-06-13 | 2018-06-18 | 120 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-27 | 2023-04-27 | 2018-06-13 | 2018-06-18 | 138 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PAIN | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-27 | 2023-04-27 | 2018-06-13 | 2018-06-18 | 139 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-PIPF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 6 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-27 | 2023-04-27 | 2018-06-13 | 2018-06-18 | 200 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | VEN-ELEC | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 4 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-27 | 2023-04-27 | 2018-06-13 | 2018-06-18 | 220 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-SCAF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 24 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-27 | 2023-04-29 | 2018-06-13 | 2018-06-18 | 240 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-SCAF | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-29 | 2023-04-29 | 2018-06-13 | 2018-06-18 | 260 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-ROPE | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-29 | 2023-04-29 | 2018-06-13 | 2018-06-18 | 270 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
4 | DFF-3520 | WDF | MTN-PIPF | MTN-ROPE | 2100024418 | FFSPR Replace 10" discharge to sea | Byg stillads i området for montage clamp | PCNF | PCNF | 0 | 0 | Empty | 2023-04-01 | 2023-04-29 | 2023-04-29 | 2023-04-29 | 2018-06-13 | 2018-06-18 | 280 | PCNF | PCNF | DF /F /54/DFF-10-WI-035-7003-AB-F | Byg stillads i området for montage clamp | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400315823 | 3M CRUDE OIL EXP. SKD MAINT-DFCM-A-3670 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3670 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-11 | 2024-04-22 | 10 |  |  | DF /C /23/DFCM-A-3670 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3670 | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400291656 | 1Y DFF FUELGAS TRANSMITTER - METERING | DFF FUELGAS TRANSMITTER - METERING | AWSC | AWSC | 4 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-11-04 | 2023-12-10 | 10 | AWSC | AWSC | DF /F /70/METERING | DFF FUELGAS TRANSMITTER - METERING | Unknown
2 | NOSD | WDF | VEN-INSP | VEN-INSP | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-07 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 10 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | WELLSUPV | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 30 | 30 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-06 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 20 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | WELLSUPV | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 75 | 88 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-05 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 30 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | WELLSUPV | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 45 | 0 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-11 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 40 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | WELLSUPV | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 30 | 6 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-13 | 2022-04-29 | 2021-08-07 | 2021-08-12 | 50 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | WELLSUPV | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 60 | 67 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-07 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 60 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | VEN-INSP | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 80 | 70 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-11 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 70 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | WELLSUPV | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 60 | 0 | Empty | 2023-01-16 | 2023-01-17 | 2021-08-17 | 2021-08-17 | 2021-08-07 | 2021-08-12 | 80 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | VEN-INSP | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 45 | 0 | Empty | 2023-01-16 | 2023-01-17 | 2023-01-16 | 2023-01-17 | 2021-08-07 | 2021-08-12 | 90 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
2 | NOSD | WDF | VEN-INSP | VEN-INSP | 2100053557 | SCFM 9E corrosion DFA-16"-PHS-339009-BD | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2023-01-16 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-08-07 | 2021-08-12 | 100 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | operation_description_not_present | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 32 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-01 | 2025-01-02 | 2021-03-24 | 2021-06-22 | 10 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-03 | 2025-01-04 | 2021-03-24 | 2021-06-22 | 20 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-04 | 2025-01-04 | 2021-03-24 | 2021-06-22 | 30 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-04 | 2025-01-05 | 2021-03-24 | 2021-06-22 | 40 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-05 | 2025-01-07 | 2021-03-24 | 2021-06-22 | 50 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-ROUS | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-07 | 2025-01-08 | 2021-03-24 | 2021-06-22 | 55 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-08 | 2025-01-09 | 2021-03-24 | 2021-06-22 | 60 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-09 | 2025-01-09 | 2021-03-24 | 2021-06-22 | 70 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-10 | 2025-01-10 | 2021-03-24 | 2021-06-22 | 80 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-10 | 2025-01-11 | 2021-03-24 | 2021-06-22 | 90 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-11 | 2025-01-11 | 2021-03-24 | 2021-06-22 | 100 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-12 | 2025-01-12 | 2021-03-24 | 2021-06-22 | 110 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-12 | 2025-01-12 | 2021-03-24 | 2021-06-22 | 120 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100046479 | 12" WIJ Vlv replacement DFB Topdeck | 12" 1500# Vlv installation w torqing | AWSC | AWSC | 20 | 0 | Empty | 2025-01-01 | 2025-01-14 | 2025-01-13 | 2025-01-14 | 2021-03-24 | 2021-06-22 | 130 | AWSC | AWSC | DF /B /54/SYSTEM-54-MANUAL-VALVES | 12" 1500# Vlv installation w torqing | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 0 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-11-19 | 2023-11-19 | 2023-11-19 | 2026-05-07 | 10 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | VEN-INSP | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 14 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-11-19 | 2023-11-20 | 2023-11-19 | 2026-05-07 | 20 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 8 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-11-20 | 2023-11-21 | 2023-11-19 | 2026-05-07 | 30 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-SCAF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 144 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-11-21 | 2023-12-03 | 2023-11-19 | 2026-05-07 | 40 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-RIGG | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 12 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-03 | 2023-12-04 | 2023-11-19 | 2026-05-07 | 50 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | PRODTECH | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 4 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-04 | 2023-12-05 | 2023-11-19 | 2026-05-07 | 60 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 12 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-05 | 2023-12-05 | 2023-11-19 | 2026-05-07 | 70 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-RIGG | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 12 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-05 | 2023-12-07 | 2023-11-19 | 2026-05-07 | 80 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | INP-SITE | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 4 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-07 | 2023-12-07 | 2023-11-19 | 2026-05-07 | 90 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-RIGG | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 12 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-07 | 2023-12-09 | 2023-11-19 | 2026-05-07 | 100 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 12 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-09 | 2023-12-09 | 2023-11-19 | 2026-05-07 | 110 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 8 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-09 | 2023-12-10 | 2023-11-19 | 2026-05-07 | 120 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
2 | DAN-OIL | WDF | MTN-PIPF | MTN-SCAF | 2100093354 | SYNPR: Perforated open drain DFF | Prepare work area |  |  | 72 | 0 | Empty | 2023-11-19 | 2023-12-16 | 2023-12-10 | 2023-12-16 | 2023-11-19 | 2026-05-07 | 130 |  |  | DF /F /28/DFF-4-DO-050-8016-AD-U | Prepare work area | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 1 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 20 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 1 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 40 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 1 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 60 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 0.5 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 80 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 0.5 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 95 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 0.5 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 96 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 0.5 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 97 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100040143 | Bypass for deluge XV-032993 intern leak | replace HCV valve | AWSC | AWSC | 0.5 | 0 | Freeze Job | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2020-11-19 | 2021-02-17 | 98 | AWSC | AWSC | DF /G /01/DFGA-XV-032993 | replace HCV valve | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-04-17 | 2021-07-16 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 70 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-06 | 2021-04-17 | 2021-07-16 | 80 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 90 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 100 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047716 | DFF HCV-030169 internly leaking | Prepare Permit/Tools/Matr | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-04-17 | 2021-07-16 | 110 | AWSC | AWSC | DF /F /01/DFFA-HCV-030169 | Prepare Permit/Tools/Matr | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322644 | 2Y 110VDC UPS.SYST BATT&CHAR F.TEST-DFC | PO - Vendor UPS | AWSCSCHSECE | AWSCSCHSECE | 20 | 0 | W25-W26 | 2024-06-28 | 2024-07-02 | 2024-06-28 | 2024-07-02 | 2024-04-01 | 2024-05-17 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /06/UPS-SYSTEM-3 | PO - Vendor UPS | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322644 | 2Y 110VDC UPS.SYST BATT&CHAR F.TEST-DFC | PO - Vendor UPS | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W25-W26 | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-04-01 | 2024-05-17 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /06/UPS-SYSTEM-3 | PO - Vendor UPS | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322644 | 2Y 110VDC UPS.SYST BATT&CHAR F.TEST-DFC | PO - Vendor UPS | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W25-W26 | 2024-06-28 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-04-01 | 2024-05-17 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /06/UPS-SYSTEM-3 | PO - Vendor UPS | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012832 | Follow up on lubrication on pumps | Follow up, lubricat on pumps & air comps |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-02-03 | 2023-06-18 | 10 |  |  | DF /F /9 | Follow up, lubricat on pumps & air comps | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400290948 | 1Y HVAC EXHAUST CHECK - DFC | PERSONAL ISOLATION |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-10-22 | 2023-11-21 | 10 |  |  | DF /C /09/DFCC-B-1207A | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400290948 | 1Y HVAC EXHAUST CHECK - DFC | PERSONAL ISOLATION |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2023-10-22 | 2023-11-21 | 20 |  |  | DF /C /09/DFCC-B-1207A | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400290948 | 1Y HVAC EXHAUST CHECK - DFC | PERSONAL ISOLATION |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-10-22 | 2023-11-21 | 30 |  |  | DF /C /09/DFCC-B-1207A | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400290948 | 1Y HVAC EXHAUST CHECK - DFC | PERSONAL ISOLATION |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-10-22 | 2023-11-21 | 40 |  |  | DF /C /09/DFCC-B-1207A | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329501 | 1Y EMERGENCY LIGHTS L1 TEST - DFG | PERSONAL ISOLATION | SCHSECE | SCHSECE | 1 | 3 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-17 | 2024-05-20 | 2024-06-19 | 10 | SCHSECE | SCHSECE | DF /G /62/EMERGENCY-LIGHTING | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329501 | 1Y EMERGENCY LIGHTS L1 TEST - DFG | PERSONAL ISOLATION | SCHSECE | SCHSECE | 12 | 38 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-20 | 2024-05-20 | 2024-06-19 | 20 | SCHSECE | SCHSECE | DF /G /62/EMERGENCY-LIGHTING | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400329501 | 1Y EMERGENCY LIGHTS L1 TEST - DFG | PERSONAL ISOLATION | SCHSECE | SCHSECE | 1 | 3 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-05-20 | 2024-06-19 | 30 | SCHSECE | SCHSECE | DF /G /62/EMERGENCY-LIGHTING | PERSONAL ISOLATION | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053642 | Replace light DFF1802-7504-L1N | Replace light fixture |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-11-01 | 2022-03-31 | 10 |  |  | DF /F /62 | Replace light fixture | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053642 | Replace light DFF1802-7504-L1N | Replace light fixture |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-11-01 | 2022-03-31 | 20 |  |  | DF /F /62 | Replace light fixture | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053642 | Replace light DFF1802-7504-L1N | Replace light fixture |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-11-01 | 2022-03-31 | 30 |  |  | DF /F /62 | Replace light fixture | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 15 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-18 | 2024-09-20 | 2019-06-03 | 2019-09-01 | 10 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 4 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-18 | 2024-09-19 | 2019-06-03 | 2019-09-01 | 15 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | WELLSUPV | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 4 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-18 | 2024-09-18 | 2019-06-03 | 2019-09-01 | 16 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 16 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-18 | 2024-09-20 | 2019-06-03 | 2019-09-01 | 20 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 24 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-20 | 2024-09-22 | 2019-06-03 | 2019-09-01 | 30 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 16 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2019-06-03 | 2019-09-01 | 40 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 2 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2019-06-03 | 2019-09-01 | 50 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | WELLSUPV | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 5 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2019-06-03 | 2019-09-01 | 52 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 3 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2019-06-03 | 2019-09-01 | 55 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100022680 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | AWSC | AWSC | 4 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2019-06-03 | 2019-09-01 | 60 | AWSC | AWSC | DF /G /31 | Remove lifting arrangement | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 13 | 3 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-31 | 2020-09-10 | 2018-12-27 | 2019-03-27 | 10 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 40.20000000000000284217094303 | 49 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-24 | 2020-12-09 | 2018-12-27 | 2019-03-27 | 30 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 13.400000000000000355271367876 | 10 | Empty | 2026-01-01 | 2026-01-01 | 2020-09-11 | 2020-09-16 | 2018-12-27 | 2019-03-27 | 35 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 5 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-27 | 2019-03-27 | 40 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 0.6999999999999999555910790147 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-27 | 2019-03-27 | 45 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 13.400000000000000355271367876 | 46.5 | Empty | 2026-01-01 | 2026-01-01 | 2020-11-08 | 2020-12-27 | 2018-12-27 | 2019-03-27 | 50 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 0.6999999999999999555910790147 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-27 | 2019-03-27 | 60 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 26.800000000000000710542735752 | 8 | Empty | 2026-01-01 | 2026-01-01 | 2020-11-11 | 2021-02-06 | 2018-12-27 | 2019-03-27 | 70 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003032 | Scaff / Iso assists FORCE 13346 | L3 Create permit. | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-27 | 2019-03-27 | 80 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AD-T | L3 Create permit. | Unknown
3 | DFG-1740 | WDF | MTN-MECH | PRODTECH | 2100097611 | Jacket heater left side defective | Repalce jacket heater left side - Mech |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2023-10-20 | 2024-03-03 | 10 |  |  | DF /G /05/DFGA-GM-1740 | Repalce jacket heater left side - Mech | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-MECH | 2100097611 | Jacket heater left side defective | Repalce jacket heater left side - Mech |  |  | 8 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2023-10-20 | 2024-03-03 | 20 |  |  | DF /G /05/DFGA-GM-1740 | Repalce jacket heater left side - Mech | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-ELEC | 2100097611 | Jacket heater left side defective | Repalce jacket heater left side - Mech |  |  | 8 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-02 | 2023-10-20 | 2024-03-03 | 30 |  |  | DF /G /05/DFGA-GM-1740 | Repalce jacket heater left side - Mech | Unknown
3 | DFG-1740 | WDF | MTN-MECH | PRODTECH | 2100097611 | Jacket heater left side defective | Repalce jacket heater left side - Mech |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2023-10-20 | 2024-03-03 | 40 |  |  | DF /G /05/DFGA-GM-1740 | Repalce jacket heater left side - Mech | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057551 | FLMR DFB - Replacement Handrail EL. 22.0 | DFB - Replacement Handrail EL. 22.000 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 10 |  |  | DF /B /86/22000 - HANDRAILS | DFB - Replacement Handrail EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057551 | FLMR DFB - Replacement Handrail EL. 22.0 | DFB - Replacement Handrail EL. 22.000 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 20 |  |  | DF /B /86/22000 - HANDRAILS | DFB - Replacement Handrail EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057551 | FLMR DFB - Replacement Handrail EL. 22.0 | DFB - Replacement Handrail EL. 22.000 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 30 |  |  | DF /B /86/22000 - HANDRAILS | DFB - Replacement Handrail EL. 22.000 | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400246005 | ILI-PIGGING-LAUNCHING_P3004_12"_DFB-TEE | PRODUCTION_PIG-LAUNCHING | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2023-10-12 | 2023-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /23/DFBY-PL-673004 | PRODUCTION_PIG-LAUNCHING | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400246005 | ILI-PIGGING-LAUNCHING_P3004_12"_DFB-TEE | PRODUCTION_PIG-LAUNCHING | AWSCSECE | AWSCSECE | 48 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-06 | 2023-10-12 | 2023-12-31 | 20 | AWSCSECE | AWSCSECE | DF /B /23/DFBY-PL-673004 | PRODUCTION_PIG-LAUNCHING | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284275 | PSV Exchange - DFFA-PSV-431128 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-12-05 | 2024-12-08 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431128 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284275 | PSV Exchange - DFFA-PSV-431128 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-12-05 | 2024-12-08 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431128 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284275 | PSV Exchange - DFFA-PSV-431128 | Isolation of PSV | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-12-05 | 2024-12-08 | 2024-12-06 | 2024-12-07 | 2024-10-19 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431128 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284275 | PSV Exchange - DFFA-PSV-431128 | Isolation of PSV | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-05 | 2024-12-08 | 2024-12-07 | 2024-12-07 | 2024-10-19 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431128 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284275 | PSV Exchange - DFFA-PSV-431128 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-12-05 | 2024-12-08 | 2024-12-07 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431128 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284275 | PSV Exchange - DFFA-PSV-431128 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-12-05 | 2024-12-08 | 2024-12-08 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431128 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100038111 | ANOP DFF-PSV-380021 defect spool | PO Densiq |  |  | 240 | 0 | Empty | 2023-04-01 | 2023-06-02 | 2023-04-01 | 2023-05-30 | 2020-09-19 | 2020-10-09 | 10 |  |  | DF /F /54/DFFA-PSV-380021 | PO Densiq | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100038111 | ANOP DFF-PSV-380021 defect spool | PO Densiq |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-06-02 | 2023-05-30 | 2023-05-30 | 2020-09-19 | 2020-10-09 | 20 |  |  | DF /F /54/DFFA-PSV-380021 | PO Densiq | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100038111 | ANOP DFF-PSV-380021 defect spool | PO Densiq |  |  | 30 | 0 | Empty | 2023-04-01 | 2023-06-02 | 2023-05-31 | 2023-06-02 | 2020-09-19 | 2020-10-09 | 30 |  |  | DF /F /54/DFFA-PSV-380021 | PO Densiq | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100038111 | ANOP DFF-PSV-380021 defect spool | PO Densiq |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-06-02 | 2023-06-02 | 2023-06-02 | 2020-09-19 | 2020-10-09 | 40 |  |  | DF /F /54/DFFA-PSV-380021 | PO Densiq | Unknown
A | NOSD | WPM | VEN-INSP | MTN-MECH | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 447 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2024-09-01 | 2024-12-21 | 2024-10-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 454 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2024-12-21 | 2025-04-14 | 2024-10-01 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 132 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-04-14 | 2025-05-17 | 2024-10-01 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-05-17 | 2025-05-17 | 2024-10-01 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PIPF | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-05-17 | 2025-05-17 | 2024-10-01 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-05-17 | 2025-05-17 | 2024-10-01 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-05-17 | 2025-05-17 | 2024-10-01 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PAIN | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 252 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-05-17 | 2025-06-12 | 2024-10-01 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 50 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-06-12 | 2025-06-25 | 2024-10-01 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-06-25 | 2025-06-27 | 2024-10-01 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-06-27 | 2025-06-28 | 2024-10-01 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-06-28 | 2025-06-29 | 2024-10-01 | 2024-12-31 | 120 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400298038 | PVI Major - DFGA-V-5072 | Assist FMC with instrumentation tasks | AWSCSECE | AWSCSECE | 74 | 0 | Empty | 2024-09-01 | 2025-07-18 | 2025-06-29 | 2025-07-18 | 2024-10-01 | 2024-12-31 | 130 | AWSCSECE | AWSCSECE | DF /G /28/DFGA-V-5072 | Assist FMC with instrumentation tasks | Unknown
4 | DFG-IPHP | WDF | MTN-INST | PRODTECH | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 0.5 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 10 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | PRODTECH | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 20 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 30 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-MECH | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 1.5 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 40 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-MECH | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 45 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-MECH | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 1.5 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 50 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 60 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 70 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 80 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
4 | DFG-IPHP | WDF | MTN-INST | PRODTECH | 2100065962 | Replace 1" Needle Valve on PGS line. | Inhibit Diff Pressure Transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-07-25 | 2023-03-22 | 90 |  |  | DF /G /32/DFG-30-GPS-043-0007-DD-A | Inhibit Diff Pressure Transmitter | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003050 | SMAT:DFCI-HCV-57121-U kan ikke opereres/ | ER BLÅ JOBSEDDEL FJERNET? J/N/NA |  |  | 24 | 0 | W23-W24 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-08-04 | 2017-04-18 | 2017-05-28 | 10 |  |  | DF /C /70/DFCI-HCV-57121-U | ER BLÅ JOBSEDDEL FJERNET? J/N/NA | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003050 | SMAT:DFCI-HCV-57121-U kan ikke opereres/ | ER BLÅ JOBSEDDEL FJERNET? J/N/NA |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-08-04 | 2024-08-04 | 2024-08-04 | 2017-04-18 | 2017-05-28 | 20 |  |  | DF /C /70/DFCI-HCV-57121-U | ER BLÅ JOBSEDDEL FJERNET? J/N/NA | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259858 | 1Y PIG RECEIVER MAINT-DFFA-EP-3802 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-17 | 2024-06-17 | 2023-06-01 | 2023-07-01 | 10 | SECE | SECE | DF /F /23/DFFA-EP-3802 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259858 | 1Y PIG RECEIVER MAINT-DFFA-EP-3802 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-17 | 2024-06-18 | 2023-06-01 | 2023-07-01 | 20 | SECE | SECE | DF /F /23/DFFA-EP-3802 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400259858 | 1Y PIG RECEIVER MAINT-DFFA-EP-3802 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-18 | 2024-06-19 | 2023-06-01 | 2023-07-01 | 30 | SECE | SECE | DF /F /23/DFFA-EP-3802 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259858 | 1Y PIG RECEIVER MAINT-DFFA-EP-3802 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2023-06-01 | 2023-07-01 | 40 | SECE | SECE | DF /F /23/DFFA-EP-3802 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 3 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-06-17 | 2024-06-18 | 2021-02-18 | 2021-07-18 | 10 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 4 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-06-19 | 2024-06-20 | 2021-02-18 | 2021-07-18 | 20 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 3 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-06-20 | 2024-06-20 | 2021-02-18 | 2021-07-18 | 30 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 3 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-06-20 | 2024-06-20 | 2021-02-18 | 2021-07-18 | 40 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 5 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-06-20 | 2024-06-21 | 2021-02-18 | 2021-07-18 | 50 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 5 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-06-21 | 2024-06-22 | 2021-02-18 | 2021-07-18 | 60 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 5 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2021-02-18 | 2021-07-18 | 70 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 5 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2021-02-18 | 2021-07-18 | 80 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 3 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2021-02-18 | 2021-07-18 | 90 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 3 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2021-02-18 | 2021-07-18 | 100 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 2 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2021-02-18 | 2021-07-18 | 110 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 2 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2021-02-18 | 2021-07-18 | 120 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100042169 | Defect elmotor and coupling | Isolate accordingly | SCH | SCH | 3 | 0 | W25-W26 | 2024-06-17 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2021-02-18 | 2021-07-18 | 130 | SCH | SCH | DF /G /27/DFGA-PM-5087 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2018-05-13 | 2018-08-11 | 10 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2018-05-13 | 2018-08-11 | 20 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 26 | 2 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-18 | 2018-05-13 | 2018-08-11 | 30 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2018-05-13 | 2018-08-11 | 50 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2018-05-13 | 2018-08-11 | 60 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2018-05-13 | 2018-08-11 | 70 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023914 | Actuator and SOV to be changed. DFEZ-XCV | Order of new SOV | PCNF | PCNF | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2018-05-13 | 2018-08-11 | 80 | PCNF | PCNF | DF /E /10/DFEZ-XCV-30351 | Order of new SOV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 32 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-13 | 2023-02-20 | 2020-05-27 | 2020-08-25 | 5 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-21 | 2023-02-21 | 2020-05-27 | 2020-08-25 | 10 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-22 | 2023-02-22 | 2020-05-27 | 2020-08-25 | 20 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 2 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-23 | 2023-02-23 | 2020-05-27 | 2020-08-25 | 30 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-23 | 2023-02-24 | 2020-05-27 | 2020-08-25 | 40 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 2 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-24 | 2023-02-24 | 2020-05-27 | 2020-08-25 | 50 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-25 | 2023-02-25 | 2020-05-27 | 2020-08-25 | 60 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 2 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-26 | 2023-02-26 | 2020-05-27 | 2020-08-25 | 70 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100031703 | Replace DFFA-HCV-030066 (stuck) | Order bolts in correct lenght |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-26 | 2023-02-26 | 2023-02-26 | 2020-05-27 | 2020-08-25 | 80 |  |  | DF /F /01/DFFA-HCV-030066 | Order bolts in correct lenght | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100027356 | Replace heat tracing DFFA-HTJB-1802-6914 | L3 Erect scaffold for replacing HT |  |  | 60 | 0 | W27-W28 | 2024-07-01 | 2024-08-15 | 2024-07-01 | 2024-07-16 | 2018-11-22 | 2019-01-01 | 10 |  |  | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027356 | Replace heat tracing DFFA-HTJB-1802-6914 | L3 Erect scaffold for replacing HT |  |  | 26.800000000000000710542735752 | 0 | W27-W28 | 2024-07-01 | 2024-08-15 | 2024-07-16 | 2024-07-22 | 2018-11-22 | 2019-01-01 | 15 |  |  | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027356 | Replace heat tracing DFFA-HTJB-1802-6914 | L3 Erect scaffold for replacing HT |  |  | 50 | 0 | W27-W28 | 2024-07-01 | 2024-08-15 | 2024-07-22 | 2024-08-04 | 2018-11-22 | 2019-01-01 | 20 |  |  | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027356 | Replace heat tracing DFFA-HTJB-1802-6914 | L3 Erect scaffold for replacing HT |  |  | 13.400000000000000355271367876 | 0 | W27-W28 | 2024-07-01 | 2024-08-15 | 2024-08-04 | 2024-08-07 | 2018-11-22 | 2019-01-01 | 25 |  |  | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100027356 | Replace heat tracing DFFA-HTJB-1802-6914 | L3 Erect scaffold for replacing HT |  |  | 30 | 0 | W27-W28 | 2024-07-01 | 2024-08-15 | 2024-08-07 | 2024-08-15 | 2018-11-22 | 2019-01-01 | 30 |  |  | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100035088 | Maintenance Follow-up DFGA-FI-570016 | Update MEL |  |  | 1 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2020-10-06 | 2021-03-05 | 97 |  |  | DF /G /70/DFG-PURGEGAS-1 | Update MEL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035088 | Maintenance Follow-up DFGA-FI-570016 | Update MEL |  |  | 1 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2020-10-06 | 2021-03-05 | 500 |  |  | DF /G /70/DFG-PURGEGAS-1 | Update MEL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035088 | Maintenance Follow-up DFGA-FI-570016 | Update MEL |  |  | 2 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2020-10-06 | 2021-03-05 | 503 |  |  | DF /G /70/DFG-PURGEGAS-1 | Update MEL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035088 | Maintenance Follow-up DFGA-FI-570016 | Update MEL |  |  | 1 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2020-10-06 | 2021-03-05 | 802 |  |  | DF /G /70/DFG-PURGEGAS-1 | Update MEL | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100035088 | Maintenance Follow-up DFGA-FI-570016 | Update MEL |  |  | 0.5 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2020-10-06 | 2021-03-05 | 804 |  |  | DF /G /70/DFG-PURGEGAS-1 | Update MEL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100035088 | Maintenance Follow-up DFGA-FI-570016 | Update MEL |  |  | 0 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2020-10-06 | 2021-03-05 | 814 |  |  | DF /G /70/DFG-PURGEGAS-1 | Update MEL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-07-29 | 2024-07-29 | 2018-10-01 | 2018-11-10 | 5 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 24 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-07-29 | 2024-08-01 | 2018-10-01 | 2018-11-10 | 10 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-01 | 2024-08-02 | 2018-10-01 | 2018-11-10 | 20 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-02 | 2024-08-02 | 2018-10-01 | 2018-11-10 | 30 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-02 | 2024-08-03 | 2018-10-01 | 2018-11-10 | 35 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-03 | 2024-08-03 | 2018-10-01 | 2018-11-10 | 40 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | QAQCMECH | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-03 | 2024-08-03 | 2018-10-01 | 2018-11-10 | 50 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-03 | 2024-08-04 | 2018-10-01 | 2018-11-10 | 60 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-04 | 2024-08-05 | 2018-10-01 | 2018-11-10 | 70 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 18 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-05 | 2024-08-07 | 2018-10-01 | 2018-11-10 | 80 |  |  | DF /F /10 | L3 Check material | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024092 | CMAT:DAN FF, Level 2 Wellhead, Support D | L3 Check material |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2018-10-01 | 2018-11-10 | 90 |  |  | DF /F /10 | L3 Check material | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339097 | DFC_1Y_50700 INT STRUCT INSP - GVI | DFC_1Y_50700 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_50700 (ACCOMMODATION L1) | DFC_1Y_50700 INT STRUCT INSP - GVI | Unknown
3 | DAN-OIL | WGN | MTN-ELEC | PRODTECH | 2200010146 | Overhaul ABB HVCB breaker FAF | De-isolate accordingly and test |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-04-08 | 2022-07-07 | 10 |  |  | DF /F /61/DFFA-N-1801B-03-01 | De-isolate accordingly and test | Unknown
3 | DAN-OIL | WGN | MTN-ELEC | VEN-ELEC | 2200010146 | Overhaul ABB HVCB breaker FAF | De-isolate accordingly and test |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-04-08 | 2022-07-07 | 20 |  |  | DF /F /61/DFFA-N-1801B-03-01 | De-isolate accordingly and test | Unknown
3 | DAN-OIL | WGN | MTN-ELEC | PRODTECH | 2200010146 | Overhaul ABB HVCB breaker FAF | De-isolate accordingly and test |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2022-04-08 | 2022-07-07 | 30 |  |  | DF /F /61/DFFA-N-1801B-03-01 | De-isolate accordingly and test | Unknown
3 | DFG-1740 | WGN | MTN-MECH | PRODTECH | 2200016095 | Cooling water replacement DFGA-A-1740 | Replacement of cooling water |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2023-11-25 | 2024-04-08 | 10 |  |  | DF /G /05/DFGA-A-1740 | Replacement of cooling water | Unknown
3 | DFG-1740 | WGN | MTN-MECH | MTN-MECH | 2200016095 | Cooling water replacement DFGA-A-1740 | Replacement of cooling water |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2023-11-25 | 2024-04-08 | 20 |  |  | DF /G /05/DFGA-A-1740 | Replacement of cooling water | Unknown
3 | DFG-1740 | WGN | MTN-MECH | PRODTECH | 2200016095 | Cooling water replacement DFGA-A-1740 | Replacement of cooling water |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2023-11-25 | 2024-04-08 | 30 |  |  | DF /G /05/DFGA-A-1740 | Replacement of cooling water | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000960 | ESD SW for ENG469L-Vacuum Pump | Method statement | AWSC | AWSC | 24 | 0 | IOP date TBC | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-20 | 2019-02-04 | 2019-07-04 | 10 | AWSC | AWSC | DF /B /03/DFBA-FP-0208 | Method statement | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000960 | ESD SW for ENG469L-Vacuum Pump | Method statement | AWSC | AWSC | 0 | 0 | IOP date TBC | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2019-02-04 | 2019-07-04 | 20 | AWSC | AWSC | DF /B /03/DFBA-FP-0208 | Method statement | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000960 | ESD SW for ENG469L-Vacuum Pump | Method statement | AWSC | AWSC | 0 | 0 | IOP date TBC | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2019-02-04 | 2019-07-04 | 30 | AWSC | AWSC | DF /B /03/DFBA-FP-0208 | Method statement | Unknown
A | NOSD | WPM | VEN-INSP | MTN-MECH | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-03 | 2024-05-03 | 2024-10-19 | 2024-12-31 | 10 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 100 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-03 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 20 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 30 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 40 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PIPF | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 50 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 60 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 70 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PAIN | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 80 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 90 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400292003 | PVI Intermediate - DFGA-V-4140 | Scaffolding work | SECE | SECE | 12 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-28 | 2024-05-29 | 2024-10-19 | 2024-12-31 | 100 | SECE | SECE | DF /G /30/DFGA-V-4140 | Scaffolding work | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-TELE | 2400346578 | 1Y FIRE DAMPER CHECK - DFA | FIRE DAMPER CHECK - DFA | SECE | SECE | 8 | 0 | W35-W36 | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2024-09-02 | 2024-10-02 | 10 | SECE | SECE | DF /A /09/FIRE-DAMPERS | FIRE DAMPER CHECK - DFA | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-01 | 2024-07-03 | 2018-08-01 | 2018-12-29 | 10 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-03 | 2024-07-05 | 2018-08-01 | 2018-12-29 | 20 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-05 | 2024-07-07 | 2018-08-01 | 2018-12-29 | 30 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-07 | 2024-07-09 | 2018-08-01 | 2018-12-29 | 40 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-09 | 2024-07-11 | 2018-08-01 | 2018-12-29 | 50 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-11 | 2024-07-13 | 2018-08-01 | 2018-12-29 | 60 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-13 | 2024-07-15 | 2018-08-01 | 2018-12-29 | 70 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-15 | 2024-07-17 | 2018-08-01 | 2018-12-29 | 80 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-17 | 2024-07-19 | 2018-08-01 | 2018-12-29 | 90 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-19 | 2024-07-21 | 2018-08-01 | 2018-12-29 | 100 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100027389 | DFF Roof LER transits | DFF-ROOF-003 A2 |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-23 | 2024-07-21 | 2024-07-23 | 2018-08-01 | 2018-12-29 | 110 |  |  | DF /F /6 | DFF-ROOF-003 A2 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308514 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-09-03 | 2024-09-09 | 2024-09-03 | 2024-09-03 | 2024-03-02 | 2024-03-12 | 1 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308514 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-09-03 | 2024-09-09 | 2024-09-03 | 2024-09-03 | 2024-03-02 | 2024-03-12 | 9 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308514 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-09-03 | 2024-09-09 | 2024-09-03 | 2024-09-06 | 2024-03-02 | 2024-03-12 | 10 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400308514 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-09-03 | 2024-09-09 | 2024-09-06 | 2024-09-09 | 2024-03-02 | 2024-03-12 | 12 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308514 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-09-03 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-03-02 | 2024-03-12 | 14 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
4 | DFA-OIL | WDF | MTN-MECH | PRODTECH | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-15 | 2024-09-16 | 2021-02-02 | 2021-09-30 | 10 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 0 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-16 | 2024-09-16 | 2021-02-02 | 2021-09-30 | 20 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-16 | 2024-09-16 | 2021-02-02 | 2021-09-30 | 30 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-16 | 2024-09-20 | 2021-02-02 | 2021-09-30 | 40 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-20 | 2024-09-22 | 2021-02-02 | 2021-09-30 | 50 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-22 | 2024-09-25 | 2021-02-02 | 2021-09-30 | 60 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-25 | 2024-09-27 | 2021-02-02 | 2021-09-30 | 70 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-INST | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2021-02-02 | 2021-09-30 | 80 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-28 | 2024-09-28 | 2021-02-02 | 2021-09-30 | 90 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | PRODTECH | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-28 | 2024-09-29 | 2021-02-02 | 2021-09-30 | 100 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 0 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-29 | 2024-09-29 | 2021-02-02 | 2021-09-30 | 110 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 5 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2021-02-02 | 2021-09-30 | 120 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
4 | DFA-OIL | WDF | MTN-MECH | MTN-MECH | 2100039473 | ESDV-33015 Intern læk | Build Scaffold | SECE | SECE | 0 | 0 | Empty | 2024-09-15 | 2024-09-30 | 2024-09-15 | 2024-09-15 | 2021-02-02 | 2021-09-30 | 130 | SECE | SECE | DF /C /12/DFCI-ESDV-33015 | Build Scaffold | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235628 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-18 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-18 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235628 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-18 | ISOLATION ELECTRICAL | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-18 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235628 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-18 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-18 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235628 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-18 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-18 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339092 | DFC_1Y_31600 INT STRUCT INSP - GVI | DFC_1Y_31600 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_31600 (ACCESS PLATFORM) | DFC_1Y_31600 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400315638 | 1Y TEST SEPERATOR INST MAINT DFBA-V-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-17 | 2024-06-17 | 2024-03-20 | 2024-04-19 | 10 | SECE | SECE | DF /B /11/DFBA-V-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | MTN-INST | 2400315638 | 1Y TEST SEPERATOR INST MAINT DFBA-V-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-17 | 2024-06-19 | 2024-03-20 | 2024-04-19 | 20 | SECE | SECE | DF /B /11/DFBA-V-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400315638 | 1Y TEST SEPERATOR INST MAINT DFBA-V-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W27-W28 | 2024-06-17 | 2024-06-19 | 2024-06-19 | 2024-06-19 | 2024-03-20 | 2024-04-19 | 30 | SECE | SECE | DF /B /11/DFBA-V-3801 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012623 | PSV Exchange - DFBA-PSV-33003 - PSV 2023 | DFBA-PSV-33003 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /B /10/DFBA-PSV-33003 | DFBA-PSV-33003 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012623 | PSV Exchange - DFBA-PSV-33003 - PSV 2023 | DFBA-PSV-33003 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /B /10/DFBA-PSV-33003 | DFBA-PSV-33003 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012623 | PSV Exchange - DFBA-PSV-33003 - PSV 2023 | DFBA-PSV-33003 Offshore from WS Måde |  |  | 5 | 24 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /B /10/DFBA-PSV-33003 | DFBA-PSV-33003 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012623 | PSV Exchange - DFBA-PSV-33003 - PSV 2023 | DFBA-PSV-33003 Offshore from WS Måde |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /B /10/DFBA-PSV-33003 | DFBA-PSV-33003 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012623 | PSV Exchange - DFBA-PSV-33003 - PSV 2023 | DFBA-PSV-33003 Offshore from WS Måde |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /B /10/DFBA-PSV-33003 | DFBA-PSV-33003 Offshore from WS Måde | Unknown
3 | NOSD | WDF | MTN-TURB | PRODTECH | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 10 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | VEN-MECH | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 20 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 20 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 5 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 30 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-RIGG | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 10 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 40 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-MECH | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 50 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-MECH | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 60 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-12-02 | 2023-04-16 | 70 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-ROPE | 2100076414 | Comp main lube oil pump 4305 change. | Replacement of pump | PCNF | PCNF | 4 | 4 | W27-W28 | 2024-07-01 | 2024-07-01 | 2023-05-07 | 2023-07-01 | 2022-12-02 | 2023-04-16 | 80 | PCNF | PCNF | DF /G /31/DFGA-PM-4305 | Replacement of pump | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400281087 | 1Y GAS LIFT INST/VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 5 | W27-W28 | 2024-07-03 | 2024-07-12 | 2024-07-03 | 2024-07-04 | 2023-09-03 | 2023-10-03 | 10 | SECE | SECE | DF /A /37/LIFT-GAS-MANIFOLD | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | MTN-INST | 2400281087 | 1Y GAS LIFT INST/VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 27 | 27 | W27-W28 | 2024-07-03 | 2024-07-12 | 2024-07-04 | 2024-07-10 | 2023-09-03 | 2023-10-03 | 20 | SECE | SECE | DF /A /37/LIFT-GAS-MANIFOLD | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400281087 | 1Y GAS LIFT INST/VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 5 | W27-W28 | 2024-07-03 | 2024-07-12 | 2024-07-11 | 2024-07-12 | 2023-09-03 | 2023-10-03 | 30 | SECE | SECE | DF /A /37/LIFT-GAS-MANIFOLD | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-LAGG | WELLSUPV | 2100027611 | ANOP SMATinstall Foamglas potable wat | L3-Check materials | AWSC | AWSC | 2 | 2 | Empty | 2023-12-31 | 2024-01-02 | 2018-04-05 | 2018-09-10 | 2018-03-26 | 2018-04-15 | 10 | AWSC | AWSC | DF /A /85/P-G | L3-Check materials | Unknown
3 | NOSD | WDF | MTN-LAGG | WELLSUPV | 2100027611 | ANOP SMATinstall Foamglas potable wat | L3-Check materials | AWSC | AWSC | 232.90000000000000568434188602 | 218.5 | Empty | 2023-12-31 | 2024-01-02 | 2018-04-05 | 2018-09-10 | 2018-03-26 | 2018-04-15 | 20 | AWSC | AWSC | DF /A /85/P-G | L3-Check materials | Unknown
3 | NOSD | WDF | MTN-LAGG | WELLSUPV | 2100027611 | ANOP SMATinstall Foamglas potable wat | L3-Check materials | AWSC | AWSC | 33.5 | 0 | Empty | 2023-12-31 | 2024-01-02 | 2018-09-01 | 2018-09-10 | 2018-03-26 | 2018-04-15 | 30 | AWSC | AWSC | DF /A /85/P-G | L3-Check materials | Unknown
3 | NOSD | WDF | MTN-LAGG | WELLSUPV | 2100027611 | ANOP SMATinstall Foamglas potable wat | L3-Check materials | AWSC | AWSC | 24 | 24 | Empty | 2023-12-31 | 2024-01-02 | 2018-04-05 | 2018-09-10 | 2018-03-26 | 2018-04-15 | 40 | AWSC | AWSC | DF /A /85/P-G | L3-Check materials | Unknown
3 | NOSD | WDF | MTN-LAGG | MTN-LAGG | 2100027611 | ANOP SMATinstall Foamglas potable wat | L3-Check materials | AWSC | AWSC | 33.5 | 16 | Empty | 2023-12-31 | 2024-01-02 | 2023-12-31 | 2024-01-02 | 2018-03-26 | 2018-04-15 | 50 | AWSC | AWSC | DF /A /85/P-G | L3-Check materials | Unknown
3 | NOSD | WDF | MTN-LAGG | MTN-SCAF | 2100027611 | ANOP SMATinstall Foamglas potable wat | L3-Check materials | AWSC | AWSC | 167.09999999999999431565811387 | 19 | Empty | 2023-12-31 | 2024-01-02 | 2024-01-02 | 2024-01-02 | 2018-03-26 | 2018-04-15 | 60 | AWSC | AWSC | DF /A /85/P-G | L3-Check materials | Unknown
3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 18.399999999999998578914528472 | 10 | W45-46 | 2024-09-15 | 2024-10-03 | 2018-12-31 | 2022-11-04 | 2019-01-01 | 2019-01-06 | 10 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | WELLSUPV | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 44.5 | 44.5 | W45-46 | 2024-09-15 | 2024-10-03 | 2018-12-30 | 2022-11-04 | 2019-01-01 | 2019-01-06 | 20 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 12 | 10 | W45-46 | 2024-09-15 | 2024-10-03 | 2022-10-31 | 2022-11-04 | 2019-01-01 | 2019-01-06 | 30 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 12 | 36 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-15 | 2024-09-15 | 2019-01-01 | 2019-01-06 | 40 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 10 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-15 | 2024-09-17 | 2019-01-01 | 2019-01-06 | 50 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 10 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-17 | 2024-09-20 | 2019-01-01 | 2019-01-06 | 60 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 4 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-20 | 2024-09-21 | 2019-01-01 | 2019-01-06 | 70 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 3 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-21 | 2024-09-22 | 2019-01-01 | 2019-01-06 | 80 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 14 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-22 | 2024-09-25 | 2019-01-01 | 2019-01-06 | 90 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 8 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-25 | 2024-09-27 | 2019-01-01 | 2019-01-06 | 100 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 6 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-27 | 2024-09-29 | 2019-01-01 | 2019-01-06 | 110 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 3 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-29 | 2024-09-29 | 2019-01-01 | 2019-01-06 | 120 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 2 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-29 | 2024-09-30 | 2019-01-01 | 2019-01-06 | 130 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 4 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-09-30 | 2024-10-01 | 2019-01-01 | 2019-01-06 | 140 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 8 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-10-01 | 2024-10-03 | 2019-01-01 | 2019-01-06 | 150 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100024061 | DFC hcv-36034 defekt. | Stillads for adgang til ventil | PCNF | PCNF | 0 | 0 | W45-46 | 2024-09-15 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2019-01-01 | 2019-01-06 | 160 | PCNF | PCNF | DF /C /20/DFCI-HCV-36034 | Stillads for adgang til ventil | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263655 | 6M SDV LUB/MAINT OIL - DFF-DFC | SDV LUB/INSP OIL - DFF-DFC |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-07-03 | 2023-07-19 | 10 |  |  | DF /F /03/SDV-VALVES | SDV LUB/INSP OIL - DFF-DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235682 | 4Y 400V N-SWB MAINT-DFGA-N-1842A | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235682 | 4Y 400V N-SWB MAINT-DFGA-N-1842A | ISOLATION ELECTRICAL | AWSC | AWSC | 35 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-30 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235682 | 4Y 400V N-SWB MAINT-DFGA-N-1842A | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-01 | 2024-10-03 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235682 | 4Y 400V N-SWB MAINT-DFGA-N-1842A | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241148 | 1Y SYS 51 CONTROL VALVES MAINT-DAN FB | SYS 51 CONTROL VALVES MAINT-DAN FB |  |  | 12 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-29 | 2023-02-24 | 2023-04-01 | 10 |  |  | DF /B /51/INSTRUMENTS | SYS 51 CONTROL VALVES MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400241148 | 1Y SYS 51 CONTROL VALVES MAINT-DAN FB | SYS 51 CONTROL VALVES MAINT-DAN FB |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2023-02-24 | 2023-04-01 | 20 |  |  | DF /B /51/INSTRUMENTS | SYS 51 CONTROL VALVES MAINT-DAN FB | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400316055 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-04-21 | 2024-05-01 | 10 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400316055 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 12 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-04-21 | 2024-05-01 | 20 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400316055 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-04-21 | 2024-05-01 | 30 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-ROPE | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 3 | 1 | Empty | 2024-05-14 | 2024-05-14 | 2023-09-17 | 2023-11-22 | 2023-09-17 | 2024-01-30 | 10 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-ROUS | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 1 | 12 | Empty | 2024-05-14 | 2024-05-14 | 2023-09-18 | 2023-11-22 | 2023-09-17 | 2024-01-30 | 20 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-LAGG | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 24 | 0 | Empty | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2023-09-17 | 2024-01-30 | 30 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-SCAF | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2023-09-17 | 2024-01-30 | 40 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-ROUS | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2023-09-17 | 2024-01-30 | 50 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-ROUS | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2023-09-17 | 2024-01-30 | 60 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
2 | NOSD | WDF | MTN-ROUS | MTN-ROUS | 2100096109 | Safety Shower DFAA-EMS-0601 | Add matr. Valve/Erection matr | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2023-09-17 | 2024-01-30 | 70 | PCNFAWSC | PCNFAWSC | DF /A /02/DFAA-EMS-0601 | Add matr. Valve/Erection matr | Unknown
3 | NE | WRO | MTN-TELE | VEN-INST | 2300007176 | TFUIESD Network change ONB5 and TEH | TFUIESD Network change ONB5 and THE | SCH | SCH | 24 | 24 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-05 | 2024-01-06 | 2024-05-20 | 10 | SCH | SCH | DF /C /03/ESD-SYSTEM | TFUIESD Network change ONB5 and THE | Unknown
3 | NE | WRO | MTN-TELE | MTN-INST | 2300007176 | TFUIESD Network change ONB5 and TEH | TFUIESD Network change ONB5 and THE | SCH | SCH | 0 | 24 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2024-01-06 | 2024-05-20 | 20 | SCH | SCH | DF /C /03/ESD-SYSTEM | TFUIESD Network change ONB5 and THE | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200017667 | FLM Syn.672065 LT drain vlv insp - DF | Inspect Level Transmitters on DFB |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-29 | 2024-07-29 | 2024-04-01 | 2024-08-14 | 10 |  |  | DF /F /37/INSTRUMENTS | Inspect Level Transmitters on DFB | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200017667 | FLM Syn.672065 LT drain vlv insp - DF | Inspect Level Transmitters on DFB |  |  | 7 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-29 | 2024-07-31 | 2024-04-01 | 2024-08-14 | 20 |  |  | DF /F /37/INSTRUMENTS | Inspect Level Transmitters on DFB | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200017667 | FLM Syn.672065 LT drain vlv insp - DF | Inspect Level Transmitters on DFB |  |  | 17.5 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-31 | 2024-08-04 | 2024-04-01 | 2024-08-14 | 30 |  |  | DF /F /37/INSTRUMENTS | Inspect Level Transmitters on DFB | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200017667 | FLM Syn.672065 LT drain vlv insp - DF | Inspect Level Transmitters on DFB |  |  | 17 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-04 | 2024-08-09 | 2024-04-01 | 2024-08-14 | 40 |  |  | DF /F /37/INSTRUMENTS | Inspect Level Transmitters on DFB | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 10 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 20 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 30 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 4 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 40 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 50 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-05-18 | 2024-07-02 | 60 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-05-18 | 2024-07-02 | 70 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-05-18 | 2024-07-02 | 80 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-05-18 | 2024-07-02 | 90 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112902 | DFFA-PSV-393504 leaking from tell tail h | Install re-certified PSV |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-05-18 | 2024-07-02 | 100 |  |  | DF /F /75/DFFA-PSV-393504 | Install re-certified PSV | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300004391 | DO NOT USE - RReplaced by 2300008213 | DK40 - CONSUMABLE PROD - SAFETY EQ |  |  | 0 | 0 | Empty | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2025-12-13 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - SAFETY EQ | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322272 | DFC-20-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 7 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /20/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097392 | DFG-P-5076 Check valve defekt | Replace defect check valve |  |  | 2 | 0 | Empty | 2023-10-15 | 2023-10-18 | 2023-10-15 | 2023-10-15 | 2023-10-15 | 2024-02-27 | 10 |  |  | DF /G /28/DFGA-P-5076 | Replace defect check valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100097392 | DFG-P-5076 Check valve defekt | Replace defect check valve |  |  | 2 | 0 | Empty | 2023-10-15 | 2023-10-18 | 2023-10-15 | 2023-10-15 | 2023-10-15 | 2024-02-27 | 20 |  |  | DF /G /28/DFGA-P-5076 | Replace defect check valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097392 | DFG-P-5076 Check valve defekt | Replace defect check valve |  |  | 8 | 0 | Empty | 2023-10-15 | 2023-10-18 | 2023-10-15 | 2023-10-17 | 2023-10-15 | 2024-02-27 | 30 |  |  | DF /G /28/DFGA-P-5076 | Replace defect check valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100097392 | DFG-P-5076 Check valve defekt | Replace defect check valve |  |  | 3 | 0 | Empty | 2023-10-15 | 2023-10-18 | 2023-10-17 | 2023-10-18 | 2023-10-15 | 2024-02-27 | 40 |  |  | DF /G /28/DFGA-P-5076 | Replace defect check valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097392 | DFG-P-5076 Check valve defekt | Replace defect check valve |  |  | 3 | 0 | Empty | 2023-10-15 | 2023-10-18 | 2023-10-15 | 2023-10-15 | 2023-10-15 | 2024-02-27 | 50 |  |  | DF /G /28/DFGA-P-5076 | Replace defect check valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 0 | 8 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 10 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 5 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 20 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 3 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 30 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 16 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 40 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 50 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 60 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 70 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 1 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-01-31 | 2022-06-30 | 80 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 8 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-01-31 | 2022-06-30 | 90 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 5 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-01-31 | 2022-06-30 | 100 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 8 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-01-31 | 2022-06-30 | 110 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 3 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-01-31 | 2022-06-30 | 120 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 3 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-01-31 | 2022-06-30 | 130 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 140 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058315 | DFFA-P-3903 Kemikalieunit skal renoveres | Rigger assistance Survey/prep hoist etc | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2025-01-03 | 2024-10-05 | 2024-10-05 | 2022-01-31 | 2022-06-30 | 150 | PCNF | PCNF | DF /F /75/DFFA-P-3903 | Rigger assistance Survey/prep hoist etc | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100092312 | DFGA-A-4302. Defective HCV | Change HCV |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-07-23 | 2023-12-05 | 10 |  |  | DF /G /31/DFGA-S-4308B | Change HCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100092312 | DFGA-A-4302. Defective HCV | Change HCV |  |  | 4 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2023-07-23 | 2023-12-05 | 20 |  |  | DF /G /31/DFGA-S-4308B | Change HCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100092312 | DFGA-A-4302. Defective HCV | Change HCV |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-07-23 | 2023-12-05 | 30 |  |  | DF /G /31/DFGA-S-4308B | Change HCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100092312 | DFGA-A-4302. Defective HCV | Change HCV |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2023-07-23 | 2023-12-05 | 40 |  |  | DF /G /31/DFGA-S-4308B | Change HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-02-12 | 2020-05-12 | 5 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-02-12 | 2020-05-12 | 10 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 15 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 20 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 30 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-02-12 | 2020-05-12 | 40 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 50 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 60 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025194 | DFGA-LG-410493 changeout of LG and HCV's | Isolate DFGA-LG-410493 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 70 |  |  | DF /G /30/DFGA-LG-410493 | Isolate DFGA-LG-410493 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100067487 | DFFA-P-3932 no pump pressure (giver ikke | Return of pump | PCNFSCH | PCNFSCH | 2 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-05-15 | 2022-06-24 | 20 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3932 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067487 | DFFA-P-3932 no pump pressure (giver ikke | Return of pump | PCNFSCH | PCNFSCH | 15 | 42 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-05-15 | 2022-06-24 | 30 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3932 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100067487 | DFFA-P-3932 no pump pressure (giver ikke | Return of pump | PCNFSCH | PCNFSCH | 2 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-05-15 | 2022-06-24 | 40 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3932 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100067487 | DFFA-P-3932 no pump pressure (giver ikke | Return of pump | PCNFSCH | PCNFSCH | 0 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-05-15 | 2022-06-24 | 50 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3932 | Return of pump | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400306672 | 1Y SYS 51 CTRL VALVES/INST MAINT-DAN FG | SYS 51 CTRL VALVES/INST MAINT-DAN FG |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-01-18 | 2024-02-23 | 10 |  |  | DF /G /51/INSTRUMENTS | SYS 51 CTRL VALVES/INST MAINT-DAN FG | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400306672 | 1Y SYS 51 CTRL VALVES/INST MAINT-DAN FG | SYS 51 CTRL VALVES/INST MAINT-DAN FG |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-01-18 | 2024-02-23 | 20 |  |  | DF /G /51/INSTRUMENTS | SYS 51 CTRL VALVES/INST MAINT-DAN FG | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 2 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2021-01-01 | 2021-04-01 | 10 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 16 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-01 | 2024-08-02 | 2021-01-01 | 2021-04-01 | 20 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 2 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-03 | 2024-08-03 | 2021-01-01 | 2021-04-01 | 30 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-03 | 2024-08-04 | 2021-01-01 | 2021-04-01 | 40 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-04 | 2024-08-04 | 2021-01-01 | 2021-04-01 | 50 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-05 | 2024-08-05 | 2021-01-01 | 2021-04-01 | 60 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-LAGG | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-05 | 2024-08-06 | 2021-01-01 | 2021-04-01 | 70 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 12 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2021-01-01 | 2021-04-01 | 80 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100042479 | ESD Isolation Vlv DFF-LIT-340038 Interna | Scaffold Work PF erection | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2021-01-01 | 2021-04-01 | 90 | AWSC | AWSC | DF /F /20/DFFA-LIT-340038 | Scaffold Work PF erection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097600 | DFA/78 Aircon and Blower not working | Trouble shooting - Cabin aircon/blower |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-19 | 2024-03-02 | 10 |  |  | DF /A /78/DFAA-X-6102 | Trouble shooting - Cabin aircon/blower | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100097600 | DFA/78 Aircon and Blower not working | Trouble shooting - Cabin aircon/blower |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-19 | 2024-03-02 | 20 |  |  | DF /A /78/DFAA-X-6102 | Trouble shooting - Cabin aircon/blower | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROUS | 2100097600 | DFA/78 Aircon and Blower not working | Trouble shooting - Cabin aircon/blower |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-19 | 2024-03-02 | 30 |  |  | DF /A /78/DFAA-X-6102 | Trouble shooting - Cabin aircon/blower | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029881 | FB-01 lækker i hydraulk skuffe til MCV | Safing of hydraulic drawer | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2020-03-23 | 2020-05-02 | 10 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Safing of hydraulic drawer | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029881 | FB-01 lækker i hydraulk skuffe til MCV | Safing of hydraulic drawer | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2020-03-23 | 2020-05-02 | 20 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Safing of hydraulic drawer | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029881 | FB-01 lækker i hydraulk skuffe til MCV | Safing of hydraulic drawer | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2020-03-23 | 2020-05-02 | 25 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Safing of hydraulic drawer | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029881 | FB-01 lækker i hydraulk skuffe til MCV | Safing of hydraulic drawer | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2020-03-23 | 2020-05-02 | 30 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Safing of hydraulic drawer | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235684 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235684 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235684 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235684 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF02-01 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025581 | SMAT:B-1234A-flow vagt defekt. | Isolate motor guard and motor |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2019-01-21 | 2020-01-16 | 10 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate motor guard and motor | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025581 | SMAT:B-1234A-flow vagt defekt. | Isolate motor guard and motor |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2019-01-21 | 2020-01-16 | 20 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate motor guard and motor | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025581 | SMAT:B-1234A-flow vagt defekt. | Isolate motor guard and motor |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2019-01-21 | 2020-01-16 | 30 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate motor guard and motor | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025581 | SMAT:B-1234A-flow vagt defekt. | Isolate motor guard and motor |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2019-01-21 | 2020-01-16 | 40 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate motor guard and motor | Unknown
3 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 2 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-05 | 2024-10-05 | 2021-10-07 | 2022-01-05 | 10 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 3 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-05 | 2024-10-05 | 2021-10-07 | 2022-01-05 | 20 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-RIGG | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 16 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-05 | 2024-10-07 | 2021-10-07 | 2022-01-05 | 25 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 5 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-07 | 2024-10-08 | 2021-10-07 | 2022-01-05 | 30 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 8 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-08 | 2024-10-09 | 2021-10-07 | 2022-01-05 | 35 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-TURB | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 12 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-09 | 2024-10-12 | 2021-10-07 | 2022-01-05 | 40 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-TURB | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 12 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-12 | 2024-10-15 | 2021-10-07 | 2022-01-05 | 50 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 8 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-15 | 2024-10-16 | 2021-10-07 | 2022-01-05 | 55 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 5 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-16 | 2024-10-17 | 2021-10-07 | 2022-01-05 | 60 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 3 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-17 | 2024-10-17 | 2021-10-07 | 2022-01-05 | 70 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 2 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-17 | 2024-10-17 | 2021-10-07 | 2022-01-05 | 80 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056039 | Leak from seal on booster P-3571 | Isolation & safing of DFFB-P-3571 |  |  | 2 | 0 | W15-W16 | 2024-10-05 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2021-10-07 | 2022-01-05 | 90 |  |  | DF /F /54/DFFB-P-3571 | Isolation & safing of DFFB-P-3571 | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-24 | 2026-01-09 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-24 | 2026-01-09 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-24 | 2026-01-09 | 30 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-07-24 | 2026-01-09 | 40 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-24 | 2026-01-09 | 50 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-24 | 2026-01-09 | 60 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300004552 | DK40 - REPLACED BY 2300008442 | DK40 - CONSUMABLE MTN - MECH |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-24 | 2026-01-09 | 70 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - MECH | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339101 | DFC_1Y_63650 INT STRUCT INSP - GVI | DFC_1Y_63650 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_63650 (ACCOMMODATION L5) | DFC_1Y_63650 INT STRUCT INSP - GVI | Unknown
2 | DFB-W11 | WDF | MTN-INST | MTN-INST | 2100092306 | FB-11 Hydraulic drawer missing. | Reinstall FB-11 Hydraulic drawer |  |  | 8 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2023-06-09 | 2023-07-24 | 10 |  |  | DF /B /07/DFBA-A-3101 | Reinstall FB-11 Hydraulic drawer | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-SCAF | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-17 | 2021-10-27 | 2022-03-26 | 10 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-MECH | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2021-10-27 | 2022-03-26 | 20 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-LAGG | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2021-10-27 | 2022-03-26 | 30 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | PRODTECH | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-18 | 2021-10-27 | 2022-03-26 | 40 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-MECH | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-18 | 2021-10-27 | 2022-03-26 | 50 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2021-10-27 | 2022-03-26 | 60 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | PRODTECH | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2021-10-27 | 2022-03-26 | 70 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-LAGG | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2021-10-27 | 2022-03-26 | 80 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
4 | DFG-IPHP | WDF | MTN-INST | MTN-SCAF | 2100053308 | Isolation valve on upper leg seized | Prepare matr/tools/permit |  |  | 15 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2021-10-27 | 2022-03-26 | 90 |  |  | DF /G /30/DFGA-LIT-410402 | Prepare matr/tools/permit | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 5 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 4 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284257 | PSV Exchange - DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | AWSC | AWSC | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602A | DFEZ-PSV-39602A Offshore from WS Måde | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400245680 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 0 | Empty | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-20 | 2023-05-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344333 | 6M WAT CLARIFIER INJ PUMPS MAINT-3954/5 | WAT CLARIFIER INJ PUMPS MAINT-3954/5 |  |  | 1 | 0 | Empty | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-26 | 10 |  |  | DF /G /75/DFGA-A-3940 | WAT CLARIFIER INJ PUMPS MAINT-3954/5 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 60.29999999999999715782905694 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-01 | 2024-07-08 | 2017-10-18 | 2018-01-16 | 10 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-08 | 2024-07-09 | 2017-10-18 | 2018-01-16 | 20 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 20.100000000000001421085471515 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-09 | 2024-07-11 | 2017-10-18 | 2018-01-16 | 30 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 75 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-11 | 2024-07-20 | 2017-10-18 | 2018-01-16 | 40 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 50.29999999999999715782905694 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-20 | 2024-07-23 | 2017-10-18 | 2018-01-16 | 50 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-23 | 2024-07-23 | 2017-10-18 | 2018-01-16 | 60 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 20.100000000000001421085471515 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-23 | 2024-07-25 | 2017-10-18 | 2018-01-16 | 70 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027368 | Skift af HT kbl DFGA-HTJB-1854-001 | Safing af HT kabel |  |  | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2017-10-18 | 2018-01-16 | 80 |  |  | DF /G /61/DFGA-DP-1854-19 | Safing af HT kabel | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105409 | DFE-06 Flowline Temp faulty indication | Replace Temp. element |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-28 | 2024-07-12 | 10 |  |  | DF /E /10/DFEZ-TE-30018 | Replace Temp. element | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105409 | DFE-06 Flowline Temp faulty indication | Replace Temp. element |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-28 | 2024-07-12 | 20 |  |  | DF /E /10/DFEZ-TE-30018 | Replace Temp. element | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105409 | DFE-06 Flowline Temp faulty indication | Replace Temp. element |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-28 | 2024-07-12 | 30 |  |  | DF /E /10/DFEZ-TE-30018 | Replace Temp. element | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 2 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 10 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 2 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 20 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | MTN-MECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 5 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 30 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | MTN-MECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 0 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 40 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 2 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 50 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | MTN-MECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 5 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 60 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
4 | DFA-OIL | WGN | MTN-MECH | PRODTECH | 2200008956 | Recertify DFAA-PSV-33004 - 2022 | Install re-certified PSV | PCNFSCH | PCNFSCH | 4 | 0 | 24-W01-02 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 70 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33004 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235757 | 4Y 380V UPS-DP F.TEST DFAA-DP-1901/2/3 | 380V UPS-DP F.TEST DFAA-DP-1901/2/3 | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-07-24 | 2024-07-27 | 2024-07-24 | 2024-07-26 | 2023-01-30 | 2023-04-13 | 10 | AWSCSECE | AWSCSECE | DF /A /06/DISTRIBUTION-PANELS | 380V UPS-DP F.TEST DFAA-DP-1901/2/3 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235757 | 4Y 380V UPS-DP F.TEST DFAA-DP-1901/2/3 | 380V UPS-DP F.TEST DFAA-DP-1901/2/3 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2023-01-30 | 2023-04-13 | 20 | AWSCSECE | AWSCSECE | DF /A /06/DISTRIBUTION-PANELS | 380V UPS-DP F.TEST DFAA-DP-1901/2/3 | Unknown
A | DFG-1640 | WPM | MTN-TURB | MTN-TURB | 2400342644 | 2KH TURBINE WASH, COUNTER-DFGA-A-1640 | TURBINE WASH, COUNTER-DFGA-A-1640 | AWSC | AWSC | 8 | 12 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2024-07-24 | 2024-08-03 | 10 | AWSC | AWSC | DF /G /60/DFGA-A-1640 | TURBINE WASH, COUNTER-DFGA-A-1640 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400298674 | 6M HPU FOR MFF1 SCRAMS MAINT - FP-3001 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2024-01-10 | 2024-01-26 | 10 |  |  | DF /F /07/DFFA-FP-3001 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298674 | 6M HPU FOR MFF1 SCRAMS MAINT - FP-3001 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-01-10 | 2024-01-26 | 20 |  |  | DF /F /07/DFFA-FP-3001 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400298674 | 6M HPU FOR MFF1 SCRAMS MAINT - FP-3001 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-01-10 | 2024-01-26 | 30 |  |  | DF /F /07/DFFA-FP-3001 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-MECH | PRODTECH | 2400230572 | 8KH BDV/SDV MAINT, COUNTER-A-1620 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2023-01-27 | 2023-02-26 | 10 | AWSC | AWSC | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-MECH | MTN-MECH | 2400230572 | 8KH BDV/SDV MAINT, COUNTER-A-1620 | ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 4 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-18 | 2023-01-27 | 2023-02-26 | 20 | AWSC | AWSC | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-MECH | PRODTECH | 2400230572 | 8KH BDV/SDV MAINT, COUNTER-A-1620 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2023-01-27 | 2023-02-26 | 30 | AWSC | AWSC | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058382 | Replace defect JB til HT 1802-20402-L2F | Prove dead |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-02-23 | 2022-10-21 | 10 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058382 | Replace defect JB til HT 1802-20402-L2F | Prove dead |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-02-23 | 2022-10-21 | 20 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058382 | Replace defect JB til HT 1802-20402-L2F | Prove dead |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2022-02-23 | 2022-10-21 | 30 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100058382 | Replace defect JB til HT 1802-20402-L2F | Prove dead |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-02 | 2022-02-23 | 2022-10-21 | 40 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058382 | Replace defect JB til HT 1802-20402-L2F | Prove dead |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-02 | 2022-02-23 | 2022-10-21 | 50 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058382 | Replace defect JB til HT 1802-20402-L2F | Prove dead |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2022-02-23 | 2022-10-21 | 60 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Prove dead | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235619 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-7-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235619 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-7-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235619 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-7-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235619 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-7-5 | ISOLATION ELECTRICAL | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400337747 | PIGGING, P3014 16" DFF-HDA WI 2W | P3014_DFF-HDA | AWSC | AWSC | 4 | 0 | Empty | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-18 | 2024-08-24 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673014 | P3014_DFF-HDA | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322276 | DFF-28-CB-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100063035 | DFE: Hoses in Cabin Observation card | Isolate De-isolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-08-03 | 2023-05-30 | 10 |  |  | DF /E /78/DFEZ-X-6150 | Isolate De-isolate crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100063035 | DFE: Hoses in Cabin Observation card | Isolate De-isolate crane |  |  | 5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-08-03 | 2023-05-30 | 20 |  |  | DF /E /78/DFEZ-X-6150 | Isolate De-isolate crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100063035 | DFE: Hoses in Cabin Observation card | Isolate De-isolate crane |  |  | 5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-08-03 | 2023-05-30 | 30 |  |  | DF /E /78/DFEZ-X-6150 | Isolate De-isolate crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100063035 | DFE: Hoses in Cabin Observation card | Isolate De-isolate crane |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-08-03 | 2023-05-30 | 40 |  |  | DF /E /78/DFEZ-X-6150 | Isolate De-isolate crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100063035 | DFE: Hoses in Cabin Observation card | Isolate De-isolate crane |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-08-03 | 2023-05-30 | 50 |  |  | DF /E /78/DFEZ-X-6150 | Isolate De-isolate crane | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-SCAF | 2100025282 | Exhaust ducting repairs | Install scaffolding | AWSC | AWSC | 32.20000000000000284217094303 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2025-01-05 | 2018-12-01 | 2018-12-21 | 10 | AWSC | AWSC | DF /G /54/DFGA-A-3590 | Install scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-PIPF | 2100025282 | Exhaust ducting repairs | Install scaffolding | AWSC | AWSC | 48.20000000000000284217094303 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2025-01-08 | 2018-12-01 | 2018-12-21 | 20 | AWSC | AWSC | DF /G /54/DFGA-A-3590 | Install scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-SCAF | 2100025282 | Exhaust ducting repairs | Install scaffolding | AWSC | AWSC | 32.20000000000000284217094303 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-08 | 2025-01-12 | 2018-12-01 | 2018-12-21 | 30 | AWSC | AWSC | DF /G /54/DFGA-A-3590 | Install scaffolding | Unknown
3 | DFA-W10 | WDF | MTN-INST | PRODTECH | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-04 | 2023-05-19 | 10 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-04 | 2023-05-19 | 20 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-MECH | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-04 | 2023-05-19 | 30 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-MECH | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 2.5 | 2.5 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-04 | 2023-05-19 | 40 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 2.5 | 2.5 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-04 | 2023-05-19 | 50 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-MECH | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-04 | 2023-05-19 | 60 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-04 | 2023-05-19 | 70 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
3 | DFA-W10 | WDF | MTN-INST | PRODTECH | 2100078301 | DFA-10 PSH-30010 ESD sssv defect | Replace Hydraulic drawer |  |  | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-04 | 2023-05-19 | 80 |  |  | DF /A /07/DFAA-PSH-30010 | Replace Hydraulic drawer | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298234 | 1Y WIRELINE OVERRIDE - DFE | WIRELINE OVERRIDE PANELS - DFE |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2023-11-27 | 2024-01-13 | 10 |  |  | DF /E /07 | WIRELINE OVERRIDE PANELS - DFE | Unknown
D | NOSD | WPM | MTN-MECH | PRODTECH | 2400298234 | 1Y WIRELINE OVERRIDE - DFE | WIRELINE OVERRIDE PANELS - DFE |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2023-11-27 | 2024-01-13 | 20 |  |  | DF /E /07 | WIRELINE OVERRIDE PANELS - DFE | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-09-30 | 2023-02-12 | 10 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-09-30 | 2023-02-12 | 20 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-09-30 | 2023-02-12 | 30 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 1 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-09-30 | 2023-02-12 | 40 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 4 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2022-09-30 | 2023-02-12 | 50 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 1 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2022-09-30 | 2023-02-12 | 60 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073125 | Change PM-3958 EMG stop button/contact | Additional materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-09-30 | 2023-02-12 | 70 |  |  | DF /F /75/DFFA-PM-3958 | Additional materials | Unknown
3 | DFA-W01 | WDF | MTN-INST | MTN-INST | 2100105403 | DFA-01 Choke ZT defekt | Isolate / de-isolate ZT |  |  | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2024-02-28 | 2024-07-12 | 10 |  |  | DF /A /55/DFAA-ZT-30001 | Isolate / de-isolate ZT | Unknown
3 | DFA-W01 | WDF | MTN-INST | MTN-INST | 2100105403 | DFA-01 Choke ZT defekt | Isolate / de-isolate ZT |  |  | 6 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2024-02-28 | 2024-07-12 | 20 |  |  | DF /A /55/DFAA-ZT-30001 | Isolate / de-isolate ZT | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009247 | Insulation assist bilfinger 21504(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-11 | 2023-03-27 | 2023-03-27 | 2022-02-13 | 2022-07-13 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009247 | Insulation assist bilfinger 21504(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-11 | 2023-03-27 | 2023-04-01 | 2022-02-13 | 2022-07-13 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009247 | Insulation assist bilfinger 21504(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-11 | 2023-04-02 | 2023-04-04 | 2022-02-13 | 2022-07-13 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009247 | Insulation assist bilfinger 21504(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-11 | 2023-04-04 | 2023-04-05 | 2022-02-13 | 2022-07-13 | 33 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009247 | Insulation assist bilfinger 21504(COMP) | Bilfinger inspection |  |  | 36 | 0 | Empty | 2023-03-27 | 2023-04-11 | 2023-04-05 | 2023-04-08 | 2022-02-13 | 2022-07-13 | 40 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009247 | Insulation assist bilfinger 21504(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-11 | 2023-04-08 | 2023-04-11 | 2022-02-13 | 2022-07-13 | 50 |  |  | DF /F /55/DFF-6-PHS-030-7271-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012621 | Replace DFAA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) |  |  | 2 | 2 | Empty | 2024-02-01 | 2024-02-04 | 2024-02-01 | 2024-02-01 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /A /07/DFAA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012621 | Replace DFAA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) |  |  | 2 | 2 | Empty | 2024-02-01 | 2024-02-04 | 2024-02-01 | 2024-02-02 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /A /07/DFAA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012621 | Replace DFAA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) |  |  | 5 | 5 | Empty | 2024-02-01 | 2024-02-04 | 2024-02-02 | 2024-02-03 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /A /07/DFAA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012621 | Replace DFAA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) |  |  | 4 | 4 | Empty | 2024-02-01 | 2024-02-04 | 2024-02-03 | 2024-02-04 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /A /07/DFAA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012621 | Replace DFAA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-04 | 2024-02-04 | 2024-02-04 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /A /07/DFAA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011642 | DFG FFLB1 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2023-02-14 | 2025-08-02 | 10 |  |  | DF /G /02/DFGA-X-0701 | Replace hydraulic hoses | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011642 | DFG FFLB1 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-14 | 2023-02-14 | 2025-08-02 | 20 |  |  | DF /G /02/DFGA-X-0701 | Replace hydraulic hoses | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200011642 | DFG FFLB1 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 18 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-14 | 2023-02-14 | 2025-08-02 | 30 |  |  | DF /G /02/DFGA-X-0701 | Replace hydraulic hoses | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011642 | DFG FFLB1 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-02-14 | 2025-08-02 | 40 |  |  | DF /G /02/DFGA-X-0701 | Replace hydraulic hoses | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100042525 | DFA test manifold BDV indication fault | troubleshot/rep valve feedback signals |  |  | 0 | 0 | W31-W32 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2020-12-23 | 2021-02-01 | 10 |  |  | DF /A /10/DFAA-BDV-33097 | troubleshot/rep valve feedback signals | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042525 | DFA test manifold BDV indication fault | troubleshot/rep valve feedback signals |  |  | 2 | 0 | W31-W32 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2020-12-23 | 2021-02-01 | 20 |  |  | DF /A /10/DFAA-BDV-33097 | troubleshot/rep valve feedback signals | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316048 | 6M SDV LUB/MAINT OIL - DFA | SDV LUB/INSP OIL - DFA |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-19 | 2024-05-05 | 10 |  |  | DF /A /03/SDV-VALVES | SDV LUB/INSP OIL - DFA | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 8.699999999999999289457264236 | 4.5 | Empty | 2020-11-01 | 2024-01-10 | 2020-10-05 | 2020-10-10 | 2018-12-28 | 2019-03-28 | 10 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 13.400000000000000355271367876 | 6 | Empty | 2020-11-01 | 2024-01-10 | 2020-10-06 | 2020-10-10 | 2018-12-28 | 2019-03-28 | 20 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 5 | 0 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2018-12-28 | 2019-03-28 | 40 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 6.700000000000000177635683938 | 9.5 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2018-12-28 | 2019-03-28 | 50 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 6 | 0 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-09 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 60 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 6 | 0 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-09 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 70 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 12 | 0 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-09 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 80 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 12 | 0 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-09 | 2024-01-10 | 2018-12-28 | 2019-03-28 | 90 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003038 | CMAT:Isolation assist to FORCE 14321 | REMOVE INSULATION | PCNF | PCNF | 6 | 0 | Empty | 2020-11-01 | 2024-01-10 | 2024-01-09 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 100 | PCNF | PCNF | DF /F /55/DFF-6-PHS-030-7032-GF-U | REMOVE INSULATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344062 | 3Y FIRE DAMPER CHECK LEVEL 3 - DFG | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2024-07-23 | 2024-09-23 | 10 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344062 | 3Y FIRE DAMPER CHECK LEVEL 3 - DFG | PERSONAL ISOLATION | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 20 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344062 | 3Y FIRE DAMPER CHECK LEVEL 3 - DFG | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 30 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344062 | 3Y FIRE DAMPER CHECK LEVEL 3 - DFG | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 40 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 6 | Empty | 2024-10-12 | 2024-12-11 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 22 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 25 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 26 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 27 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284293 | PSV Calibration - DFFA-PSV-393304 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-10-12 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /75/DFFA-PSV-393304 | Remove PSV and Install blinds | Unknown
3 | NOSD | WGN | VEN-INST | VEN-INST | 2200009663 | Modif Compass Vib db for export to PI | Support start/ stop gens, downloads |  |  | 1 | 0 | Empty | 2023-02-13 | 2023-02-19 | 2023-02-13 | 2023-02-13 | 2022-02-17 | 2022-05-18 | 10 |  |  | DF /F /54/DFFA-FP-7201 | Support start/ stop gens, downloads | Unknown
3 | NOSD | WGN | VEN-INST | VEN-INST | 2200009663 | Modif Compass Vib db for export to PI | Support start/ stop gens, downloads |  |  | 25 | 0 | Empty | 2023-02-13 | 2023-02-19 | 2023-02-13 | 2023-02-15 | 2022-02-17 | 2022-05-18 | 20 |  |  | DF /F /54/DFFA-FP-7201 | Support start/ stop gens, downloads | Unknown
3 | NOSD | WGN | VEN-INST | VEN-INST | 2200009663 | Modif Compass Vib db for export to PI | Support start/ stop gens, downloads |  |  | 10 | 0 | Empty | 2023-02-13 | 2023-02-19 | 2023-02-15 | 2023-02-16 | 2022-02-17 | 2022-05-18 | 30 |  |  | DF /F /54/DFFA-FP-7201 | Support start/ stop gens, downloads | Unknown
3 | NOSD | WGN | VEN-INST | VEN-INST | 2200009663 | Modif Compass Vib db for export to PI | Support start/ stop gens, downloads |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-19 | 2023-02-16 | 2023-02-17 | 2022-02-17 | 2022-05-18 | 40 |  |  | DF /F /54/DFFA-FP-7201 | Support start/ stop gens, downloads | Unknown
3 | NOSD | WGN | VEN-INST | MTN-TURB | 2200009663 | Modif Compass Vib db for export to PI | Support start/ stop gens, downloads |  |  | 10 | 0 | Empty | 2023-02-13 | 2023-02-19 | 2023-02-17 | 2023-02-19 | 2022-02-17 | 2022-05-18 | 50 |  |  | DF /F /54/DFFA-FP-7201 | Support start/ stop gens, downloads | Unknown
C | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400285945 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-07-14 | 2024-07-12 | 2024-07-12 | 2023-11-03 | 2023-11-08 | 1 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400285945 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-07-12 | 2024-07-14 | 2024-07-12 | 2024-07-14 | 2023-11-03 | 2023-11-08 | 10 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100053022 | LG-34006 on Test Sep clean change light | Replace backlight |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2021-08-18 | 2021-11-16 | 10 |  |  | DF /C /11/DFCI-LG-34006 | Replace backlight | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053022 | LG-34006 on Test Sep clean change light | Replace backlight |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2021-08-18 | 2021-11-16 | 20 |  |  | DF /C /11/DFCI-LG-34006 | Replace backlight | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100053022 | LG-34006 on Test Sep clean change light | Replace backlight |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2021-08-18 | 2021-11-16 | 30 |  |  | DF /C /11/DFCI-LG-34006 | Replace backlight | Unknown
D | NOSD | WPM | MTN-TURB | MTN-TURB | 2400337634 | 1M DFGA-GT-4302 Silencer Thermography | SAFETY INFORMATION |  |  | 0 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-18 | 1 |  |  | DF /G /31/DFGA-GT-4302 | SAFETY INFORMATION | Unknown
D | NOSD | WPM | MTN-TURB | MTN-TURB | 2400337634 | 1M DFGA-GT-4302 Silencer Thermography | SAFETY INFORMATION |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-18 | 10 |  |  | DF /G /31/DFGA-GT-4302 | SAFETY INFORMATION | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400245864 | 3Y DFE LIFT GAS - METERING | DFE LIFT GAS - METERING | AWSC | AWSC | 3 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-03-14 | 2023-05-27 | 10 | AWSC | AWSC | DF /E /37/GAS-LIFT-METERING | DFE LIFT GAS - METERING | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011639 | Commissioning of DFCM-P-5304 after re-lo | Commissioning of DFCM-P-5304 after re-lo | PCNFSCH | PCNFSCH | 12 | 4 | W47-48 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-08-17 | 2022-10-01 | 10 | PCNFSCH | PCNFSCH | DF /C /50/DFCM-P-5304 | Commissioning of DFCM-P-5304 after re-lo | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100036815 | Replace 1828-6-L3AA DFC 4 mezz | Set personal isolation |  |  | 0.2999999999999999888977697536 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2020-11-10 | 2021-04-09 | 10 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100036815 | Replace 1828-6-L3AA DFC 4 mezz | Set personal isolation |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2020-11-10 | 2021-04-09 | 20 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100036815 | Replace 1828-6-L3AA DFC 4 mezz | Set personal isolation |  |  | 0.2000000000000000111022302462 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-27 | 2020-11-10 | 2021-04-09 | 30 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100036815 | Replace 1828-6-L3AA DFC 4 mezz | Set personal isolation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2020-11-10 | 2021-04-09 | 40 |  |  | DF /C /62 | Set personal isolation | Unknown
3 | NOSD | WDF | PRODTECH | PRODTECH | 2100112039 | DFF V-5014 liner replacement | DFF V-5014 liner replacement | SECE | SECE | 0 | 24 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-10-30 | 10 | SECE | SECE | DF /F /27/DFFA-V-5014 | DFF V-5014 liner replacement | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344050 | 6M CHEM INJ PUMP SKID MAINT-DFFA-A-3961 | CHEM INJ PUMP SKID MAINT-DFFA-A-3961 |  |  | 3 | 0 | Empty | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-09-19 | 10 |  |  | DF /F /75/DFFA-A-3961 | CHEM INJ PUMP SKID MAINT-DFFA-A-3961 | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300007087 | DK40 - CONSUMABLE MTN - INST | DK40 - CONSUMABLE MTN - INST |  |  | 0 | 0 | Empty | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2026-10-28 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - INST | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258807 | 6M SDV LUB/MAINT FUEL - DFC | SDV LUB/INSP FUEL - DFC |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-19 | 2023-06-04 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP FUEL - DFC | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088913 | Repair of floodlighting DFB | Faultfinding. |  |  | 0 | 0 | W25-W26 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-10-07 | 2026-03-25 | 10 |  |  | DF /B /61/DFBA-N-1810-C_57 | Faultfinding. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100088913 | Repair of floodlighting DFB | Faultfinding. |  |  | 6 | 0 | W25-W26 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-10-07 | 2026-03-25 | 20 |  |  | DF /B /61/DFBA-N-1810-C_57 | Faultfinding. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088913 | Repair of floodlighting DFB | Faultfinding. |  |  | 6 | 0 | W25-W26 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2023-10-07 | 2026-03-25 | 30 |  |  | DF /B /61/DFBA-N-1810-C_57 | Faultfinding. | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298220 | 3M WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCH | SCH | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-01-01 | 2024-01-11 | 10 | SCH | SCH | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097394 | FF HP sep water outlet FT-340508 broken | Function test flowmeter |  |  | 5 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-10-16 | 2024-02-28 | 10 |  |  | DF /F /27/DFFA-FT-340508 | Function test flowmeter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097394 | FF HP sep water outlet FT-340508 broken | Function test flowmeter |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-10-16 | 2024-02-28 | 20 |  |  | DF /F /27/DFFA-FT-340508 | Function test flowmeter | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400199513 | 2M POT WATER TREATMENT, DFC | ISOLATION |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-05-21 | 2022-06-01 | 9 |  |  | DF /C /85/DFCM-A-1037 | ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400199513 | 2M POT WATER TREATMENT, DFC | ISOLATION |  |  | 14 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2022-05-21 | 2022-06-01 | 10 |  |  | DF /C /85/DFCM-A-1037 | ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400199513 | 2M POT WATER TREATMENT, DFC | ISOLATION |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2022-05-21 | 2022-06-01 | 12 |  |  | DF /C /85/DFCM-A-1037 | ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400199513 | 2M POT WATER TREATMENT, DFC | ISOLATION |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-07-31 | 2022-05-21 | 2022-06-01 | 14 |  |  | DF /C /85/DFCM-A-1037 | ISOLATION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284243 | PSV Exchange - DFCM-PSV-50331 | Install re-certified PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /27/DFCM-PSV-50331 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284243 | PSV Exchange - DFCM-PSV-50331 | Install re-certified PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /27/DFCM-PSV-50331 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284243 | PSV Exchange - DFCM-PSV-50331 | Install re-certified PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /27/DFCM-PSV-50331 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284243 | PSV Exchange - DFCM-PSV-50331 | Install re-certified PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /27/DFCM-PSV-50331 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284243 | PSV Exchange - DFCM-PSV-50331 | Install re-certified PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /27/DFCM-PSV-50331 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284243 | PSV Exchange - DFCM-PSV-50331 | Install re-certified PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /27/DFCM-PSV-50331 | Install re-certified PSV | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342413 | 2Y 24VDC UPS SYSTEM F.TEST-DFC | 24VDC UPS SYSTEM F.TEST-DFC | AWSCSECE | AWSCSECE | 16 | 0 | Empty | 2024-07-17 | 2024-07-20 | 2024-07-17 | 2024-07-20 | 2024-07-17 | 2024-09-01 | 10 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 24VDC UPS SYSTEM F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342413 | 2Y 24VDC UPS SYSTEM F.TEST-DFC | 24VDC UPS SYSTEM F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-17 | 2024-09-01 | 20 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 24VDC UPS SYSTEM F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342413 | 2Y 24VDC UPS SYSTEM F.TEST-DFC | 24VDC UPS SYSTEM F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-17 | 2024-09-01 | 30 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 24VDC UPS SYSTEM F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342413 | 2Y 24VDC UPS SYSTEM F.TEST-DFC | 24VDC UPS SYSTEM F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-17 | 2024-09-01 | 40 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 24VDC UPS SYSTEM F.TEST-DFC | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100049482 | Replace 4 pcs. defect lighting DFC leve | Set personal isolation |  |  | 0.5 | 0 | W51-52? | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2021-07-23 | 2021-12-20 | 10 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100049482 | Replace 4 pcs. defect lighting DFC leve | Set personal isolation |  |  | 6 | 0 | W51-52? | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-14 | 2021-07-23 | 2021-12-20 | 20 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100049482 | Replace 4 pcs. defect lighting DFC leve | Set personal isolation |  |  | 0.5 | 0 | W51-52? | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2021-07-23 | 2021-12-20 | 30 |  |  | DF /C /62 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100037072 | Broken/rusty bleed valve for DFFA-PSV-41 | operation_description_not_present |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2020-09-07 | 2020-10-17 | 10 |  |  | DF /F /30/DFFA-PSV-410521 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100037072 | Broken/rusty bleed valve for DFFA-PSV-41 | operation_description_not_present |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2020-09-07 | 2020-10-17 | 20 |  |  | DF /F /30/DFFA-PSV-410521 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037072 | Broken/rusty bleed valve for DFFA-PSV-41 | operation_description_not_present |  |  | 8 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2020-09-07 | 2020-10-17 | 30 |  |  | DF /F /30/DFFA-PSV-410521 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100037072 | Broken/rusty bleed valve for DFFA-PSV-41 | operation_description_not_present |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2020-09-07 | 2020-10-17 | 40 |  |  | DF /F /30/DFFA-PSV-410521 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100037072 | Broken/rusty bleed valve for DFFA-PSV-41 | operation_description_not_present |  |  | 5 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2020-09-07 | 2020-10-17 | 50 |  |  | DF /F /30/DFFA-PSV-410521 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100037072 | Broken/rusty bleed valve for DFFA-PSV-41 | operation_description_not_present |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2020-09-07 | 2020-10-17 | 60 |  |  | DF /F /30/DFFA-PSV-410521 | operation_description_not_present | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400221608 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B | PO Caverion | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-11-01 | 2023-01-28 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801B | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400221608 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B | PO Caverion | AWSC | AWSC | 22 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2022-11-01 | 2023-01-28 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801B | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400221608 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B | PO Caverion | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2022-11-01 | 2023-01-28 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801B | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400221608 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B | PO Caverion | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2022-11-01 | 2023-01-28 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801B | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400221608 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B | PO Caverion | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2022-11-01 | 2023-01-28 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801B | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400221608 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B | PO Caverion | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2022-11-01 | 2023-01-28 | 60 | AWSC | AWSC | DF /F /61/DFFA-N-1801B | PO Caverion | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 24 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-17 | 2023-07-30 | 10 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 1 | 16 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-17 | 2023-07-30 | 20 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-17 | 2023-07-30 | 30 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-17 | 2023-07-30 | 40 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-17 | 2023-07-30 | 50 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-17 | 2023-07-30 | 60 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100082296 | DFG XCV-500625 defektive SOV | Additional hours spend |  |  | 8 | 10 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-17 | 2023-07-30 | 70 |  |  | DF /G /27/DFGA-XCV-500625 | Additional hours spend | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400342407 | 1Y CORR INHIB PMP SKID MAINT-DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2024-08-02 | 2024-09-01 | 10 | SECE | SECE | DF /F /75/DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342407 | 1Y CORR INHIB PMP SKID MAINT-DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | SECE | SECE | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-28 | 2024-08-02 | 2024-09-01 | 20 | SECE | SECE | DF /F /75/DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400342407 | 1Y CORR INHIB PMP SKID MAINT-DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | SECE | SECE | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-28 | 2024-08-29 | 2024-08-02 | 2024-09-01 | 30 | SECE | SECE | DF /F /75/DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400342407 | 1Y CORR INHIB PMP SKID MAINT-DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-02 | 2024-09-01 | 40 | SECE | SECE | DF /F /75/DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400342407 | 1Y CORR INHIB PMP SKID MAINT-DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-02 | 2024-09-01 | 50 | SECE | SECE | DF /F /75/DFFA-A-3942 | CORR INHIB PMP SKID MAINT-DFFA-A-3942 | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300007985 | DK40 - CONSUMABLE PROD - LAB | DTU Sampling for PW Management |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 10 |  |  | DF /C /75 | DTU Sampling for PW Management | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300007985 | DK40 - CONSUMABLE PROD - LAB | DTU Sampling for PW Management |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 20 |  |  | DF /C /75 | DTU Sampling for PW Management | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300007985 | DK40 - CONSUMABLE PROD - LAB | DTU Sampling for PW Management |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 30 |  |  | DF /C /75 | DTU Sampling for PW Management | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300007985 | DK40 - CONSUMABLE PROD - LAB | DTU Sampling for PW Management |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 40 |  |  | DF /C /75 | DTU Sampling for PW Management | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300007985 | DK40 - CONSUMABLE PROD - LAB | DTU Sampling for PW Management |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2027-02-12 | 50 |  |  | DF /C /75 | DTU Sampling for PW Management | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400222495 | 1Y SDV LUBE/FUNC TEST IPHP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-09-22 | 2024-09-24 | 2023-01-06 | 2023-02-05 | 10 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400222495 | 1Y SDV LUBE/FUNC TEST IPHP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 36 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-09-25 | 2024-10-03 | 2023-01-06 | 2023-02-05 | 20 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-INST | 2400222495 | 1Y SDV LUBE/FUNC TEST IPHP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-10-04 | 2024-10-04 | 2023-01-06 | 2023-02-05 | 30 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400222495 | 1Y SDV LUBE/FUNC TEST IPHP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-10-04 | 2024-10-07 | 2023-01-06 | 2023-02-05 | 40 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
C | NE | WPM | MTN-MECH | MTN-MECH | 2400298186 | 1Y RENS AF HEATER/EXCHANGER | 09.10.2012 |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-12-15 | 2024-01-20 | 10 |  |  | DF /F /53/DFFB-E-3565 | 09.10.2012 | Unknown
C | NE | WPM | MTN-MECH | MTN-MECH | 2400298186 | 1Y RENS AF HEATER/EXCHANGER | 09.10.2012 |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-12-15 | 2024-01-20 | 20 |  |  | DF /F /53/DFFB-E-3565 | 09.10.2012 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-SCAF | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 10 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-05-25 | 2024-05-28 | 2023-06-14 | 2023-10-27 | 10 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 3 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-05-27 | 2024-05-28 | 2023-06-14 | 2023-10-27 | 20 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 6 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-05-28 | 2024-05-29 | 2023-06-14 | 2023-10-27 | 30 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 6 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-05-31 | 2023-06-14 | 2023-10-27 | 40 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 6 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-05-29 | 2024-05-31 | 2023-06-14 | 2023-10-27 | 50 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 6 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-05-31 | 2024-06-01 | 2023-06-14 | 2023-10-27 | 60 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 2 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-06-01 | 2024-06-02 | 2023-06-14 | 2023-10-27 | 70 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-SCAF | 2100089992 | FA-01 WI Manifold valves internal leak. | Isolate HCV-350312 |  |  | 4 | 0 | Empty | 2024-05-25 | 2024-06-02 | 2024-06-01 | 2024-06-02 | 2023-06-14 | 2023-10-27 | 80 |  |  | DF /A /55/DFAA-HCV-350312 | Isolate HCV-350312 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259290 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2023-05-15 | 2023-06-14 | 10 | SECE | SECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259290 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W19-W20 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2023-05-15 | 2023-06-14 | 20 | SECE | SECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259290 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W19-W20 | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2023-05-15 | 2023-06-14 | 30 | SECE | SECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400259290 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W19-W20 | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2023-05-15 | 2023-06-14 | 40 | SECE | SECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259290 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-05-15 | 2023-06-14 | 50 | SECE | SECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 3 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 10 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 3 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 20 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 3 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 30 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 40 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 50 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 70 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 80 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 90 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 0 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2023-08-05 | 2023-12-25 | 2023-07-26 | 2023-12-08 | 100 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 3 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 110 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 3 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 120 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 5 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 130 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 3 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 140 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 4 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 150 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 12 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 160 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 170 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 6 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 180 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 190 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 0 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 200 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 0 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 210 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 3 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-27 | 2023-07-26 | 2023-12-08 | 220 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-27 | 2024-03-28 | 2023-07-26 | 2023-12-08 | 230 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-28 | 2024-03-28 | 2023-07-26 | 2023-12-08 | 240 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-28 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 250 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 260 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-28 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 270 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 5 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-28 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 280 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 290 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 1 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 300 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093114 | Spent scav. level xcv-350475 intern leak | Line for new Actuator | SCH | SCH | 2 | 0 | Empty | 2024-03-27 | 2024-03-29 | 2024-03-29 | 2024-03-29 | 2023-07-26 | 2023-12-08 | 310 | SCH | SCH | DF /G /27/DFGA-XCV-350475 | Line for new Actuator | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400329517 | 1Y DEAERATOR INST MAINT DFGA-V-3540 | DEAERATOR INST MAINT DFGA-V-3540 | SECE | SECE | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-05-22 | 2024-06-21 | 10 | SECE | SECE | DF /G /54/DFGA-V-3540 | DEAERATOR INST MAINT DFGA-V-3540 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235745 | 4Y 380/220V UPS-DB F.TEST-DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /06/DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235745 | 4Y 380/220V UPS-DB F.TEST-DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | SECE | SECE | 12 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /06/DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235745 | 4Y 380/220V UPS-DB F.TEST-DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /06/DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235745 | 4Y 380/220V UPS-DB F.TEST-DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /06/DFFA-DP-1904 | 380/220V UPS-DB F.TEST-DFFA-DP-1904 | Unknown
4 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100042168 | Deluge. Broken upstream HCV-033558 | Replace HCV-033306 | AWSC | AWSC | 2 | 0 | Empty | 2026-05-15 | 2026-05-17 | 2026-05-15 | 2026-05-16 | 2021-02-24 | 2021-07-24 | 10 | AWSC | AWSC | DF /G /01/DFGA-HCV-033558 | Replace HCV-033306 | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100042168 | Deluge. Broken upstream HCV-033558 | Replace HCV-033306 | AWSC | AWSC | 4 | 0 | Empty | 2026-05-15 | 2026-05-17 | 2026-05-16 | 2026-05-17 | 2021-02-24 | 2021-07-24 | 20 | AWSC | AWSC | DF /G /01/DFGA-HCV-033558 | Replace HCV-033306 | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-RIGG | 2100042168 | Deluge. Broken upstream HCV-033558 | Replace HCV-033306 | AWSC | AWSC | 4 | 0 | Empty | 2026-05-15 | 2026-05-17 | 2026-05-16 | 2026-05-17 | 2021-02-24 | 2021-07-24 | 30 | AWSC | AWSC | DF /G /01/DFGA-HCV-033558 | Replace HCV-033306 | Unknown
4 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100042168 | Deluge. Broken upstream HCV-033558 | Replace HCV-033306 | AWSC | AWSC | 2 | 0 | Empty | 2026-05-15 | 2026-05-17 | 2026-05-17 | 2026-05-17 | 2021-02-24 | 2021-07-24 | 40 | AWSC | AWSC | DF /G /01/DFGA-HCV-033558 | Replace HCV-033306 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337660 | 6M WELL CONT PANEL MAINT - DFFA-FP-3101 | WELL CONT PANEL MAINT - DFFA-FP-3101 |  |  | 4 | 0 | Empty | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-08-25 | 10 |  |  | DF /F /07/DFFA-FP-3101 | WELL CONT PANEL MAINT - DFFA-FP-3101 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329524 | 1Y PROD WTR HP/LP SKD TEST-DFFA-A-5005 | PROD WTR HP/LP SKD TEST-DFFA-A-5005 | SECE | SECE | 20 | 15 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-08-03 | 2024-05-15 | 2024-06-14 | 10 | SECE | SECE | DF /F /27/DFFA-A-5005 | PROD WTR HP/LP SKD TEST-DFFA-A-5005 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346555 | 1Y DELUGE SKIDS, SMOKE TEST-DFA | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /A /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346555 | 1Y DELUGE SKIDS, SMOKE TEST-DFA | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /A /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346555 | 1Y DELUGE SKIDS, SMOKE TEST-DFA | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /A /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346555 | 1Y DELUGE SKIDS, SMOKE TEST-DFA | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-17 | 2024-08-18 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /A /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346555 | 1Y DELUGE SKIDS, SMOKE TEST-DFA | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-18 | 2024-08-18 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /A /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100067535 | Replace HMI Screen CP-3950 | Prepare permit, spot materials | PCNF | PCNF | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-05-01 | 2022-05-21 | 10 | PCNF | PCNF | DF /G /54/DFGA-A-3590 | Prepare permit, spot materials | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100067535 | Replace HMI Screen CP-3950 | Prepare permit, spot materials | PCNF | PCNF | 2 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-05-01 | 2022-05-21 | 20 | PCNF | PCNF | DF /G /54/DFGA-A-3590 | Prepare permit, spot materials | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100067535 | Replace HMI Screen CP-3950 | Prepare permit, spot materials | PCNF | PCNF | 4 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-05-01 | 2022-05-21 | 30 | PCNF | PCNF | DF /G /54/DFGA-A-3590 | Prepare permit, spot materials | Unknown
3 | NOSD | WDF | MTN-TURB | VEN-MECH | 2100067535 | Replace HMI Screen CP-3950 | Prepare permit, spot materials | PCNF | PCNF | 4 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-05-01 | 2022-05-21 | 40 | PCNF | PCNF | DF /G /54/DFGA-A-3590 | Prepare permit, spot materials | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100067535 | Replace HMI Screen CP-3950 | Prepare permit, spot materials | PCNF | PCNF | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-05-01 | 2022-05-21 | 50 | PCNF | PCNF | DF /G /54/DFGA-A-3590 | Prepare permit, spot materials | Unknown
4 | DFGFLARE | WDF | MTN-MECH | PRODTECH | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-03-11 | 2022-11-06 | 10 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | MTN-SCAF | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 7 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-17 | 2022-03-11 | 2022-11-06 | 20 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | MTN-MECH | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-18 | 2022-03-11 | 2022-11-06 | 30 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | MTN-MECH | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-03-11 | 2022-11-06 | 40 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | MTN-MECH | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2022-03-11 | 2022-11-06 | 50 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | MTN-MECH | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2022-03-11 | 2022-11-06 | 60 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | PRODTECH | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2022-03-11 | 2022-11-06 | 70 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
4 | DFGFLARE | WDF | MTN-MECH | MTN-SCAF | 2100058718 | Isolation HCV på V-4001 sidder fast | Build Scaffold |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2022-03-11 | 2022-11-06 | 80 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Build Scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-07-15 | 2024-07-15 | 2020-09-09 | 2020-12-08 | 10 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 16 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-07-15 | 2024-07-17 | 2020-09-09 | 2020-12-08 | 20 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 16 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-07-17 | 2024-07-19 | 2020-09-09 | 2020-12-08 | 30 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-07-19 | 2024-07-19 | 2020-09-09 | 2020-12-08 | 40 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-07-19 | 2024-07-20 | 2020-09-09 | 2020-12-08 | 50 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-09-20 | 2024-09-20 | 2020-09-09 | 2020-12-08 | 60 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-09-20 | 2024-09-20 | 2020-09-09 | 2020-12-08 | 70 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 16 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-09-20 | 2024-09-22 | 2020-09-09 | 2020-12-08 | 80 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 14 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2020-09-09 | 2020-12-08 | 90 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2020-09-09 | 2020-12-08 | 100 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036665 | DFCI/78: Onsh. overhaul Corroded A/C uni | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2020-09-09 | 2020-12-08 | 110 |  |  | DF /C /78/DFCI-X-6101 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100092669 | RESET PB DFFA-PB-021353 NEED TO REPLACE | Replace pushbutton and test |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-07-26 | 2023-12-08 | 10 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100092669 | RESET PB DFFA-PB-021353 NEED TO REPLACE | Replace pushbutton and test |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-07-26 | 2023-12-08 | 20 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100092669 | RESET PB DFFA-PB-021353 NEED TO REPLACE | Replace pushbutton and test |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-07-26 | 2023-12-08 | 30 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400221602 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-11-01 | 2023-01-28 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221602 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 12 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-11-01 | 2023-01-28 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221602 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2022-11-01 | 2023-01-28 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400221602 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2022-11-01 | 2023-01-28 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400221602 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-11-01 | 2023-01-28 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235604 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-10 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235604 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-10 | ISOLATION ELECTRICAL |  |  | 23 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-21 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235604 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-10 | ISOLATION ELECTRICAL |  |  | 7 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2024-09-23 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235604 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-10 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-10 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235311 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-02 | 3KV E-SWB MAINT-DFCI-N-1811-02 | AWSCSECE | AWSCSECE | 10 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-02 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235311 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-02 | 3KV E-SWB MAINT-DFCI-N-1811-02 | AWSCSECE | AWSCSECE | 5 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-02 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235311 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-02 | 3KV E-SWB MAINT-DFCI-N-1811-02 | AWSCSECE | AWSCSECE | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-02 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235311 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-02 | 3KV E-SWB MAINT-DFCI-N-1811-02 | AWSCSECE | AWSCSECE | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-02 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235311 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-02 | 3KV E-SWB MAINT-DFCI-N-1811-02 | AWSCSECE | AWSCSECE | 0.1000000000000000055511151231 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 50 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-02 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235311 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-02 | 3KV E-SWB MAINT-DFCI-N-1811-02 | AWSCSECE | AWSCSECE | 0 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 60 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-02 | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400316046 | 6M TRAVERSE CRANE CHECK-DFCM-X-6105 | Isolation electrical | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-04-15 | 2024-05-01 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /78/DFCM-X-6105 | Isolation electrical | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400316046 | 6M TRAVERSE CRANE CHECK-DFCM-X-6105 | Isolation electrical | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-04-15 | 2024-05-01 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /78/DFCM-X-6105 | Isolation electrical | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-SCAF | 2400316046 | 6M TRAVERSE CRANE CHECK-DFCM-X-6105 | Isolation electrical | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 14 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-04-15 | 2024-05-01 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /78/DFCM-X-6105 | Isolation electrical | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400316046 | 6M TRAVERSE CRANE CHECK-DFCM-X-6105 | Isolation electrical | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 2 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-04-15 | 2024-05-01 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /78/DFCM-X-6105 | Isolation electrical | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400316046 | 6M TRAVERSE CRANE CHECK-DFCM-X-6105 | Isolation electrical | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-04-15 | 2024-05-01 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /78/DFCM-X-6105 | Isolation electrical | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100086858 | KRA-10 ZT on choke needs adjust | Adjust position transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 10 |  |  | DF /A /10/DFAA-ZT-30007 | Adjust position transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086858 | KRA-10 ZT on choke needs adjust | Adjust position transmitter |  |  | 2.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 20 |  |  | DF /A /10/DFAA-ZT-30007 | Adjust position transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100086858 | KRA-10 ZT on choke needs adjust | Adjust position transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 30 |  |  | DF /A /10/DFAA-ZT-30007 | Adjust position transmitter | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055329 | Change Floodlight DFG | Additional materials |  |  | 0.5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-05 | 2022-05-04 | 10 |  |  | DF /G /62 | Additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055329 | Change Floodlight DFG | Additional materials |  |  | 4 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-05 | 2022-05-04 | 20 |  |  | DF /G /62 | Additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055329 | Change Floodlight DFG | Additional materials |  |  | 0.5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-12-05 | 2022-05-04 | 30 |  |  | DF /G /62 | Additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055329 | Change Floodlight DFG | Additional materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-05 | 2022-05-04 | 40 |  |  | DF /G /62 | Additional materials | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235683 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF01 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF01-FA001 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235683 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF01 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF01-FA001 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235683 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF01 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF01-FA001 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235683 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF01 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF01-FA001 | 400V N-SWB INSP-DFGA-N-1842A-AF01 | Unknown
4 | D-FLARE | WGN | MTN-MECH | PRODTECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-05-06 | 2024-05-06 | 2022-03-28 | 2022-11-23 | 10 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | PRODTECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-05-06 | 2024-05-06 | 2022-03-28 | 2022-11-23 | 20 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-RIGG | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 24 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-05-06 | 2024-05-08 | 2022-03-28 | 2022-11-23 | 30 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-MECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 5 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-05-09 | 2024-05-10 | 2022-03-28 | 2022-11-23 | 40 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-MECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 0 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-05-10 | 2024-05-10 | 2022-03-28 | 2022-11-23 | 50 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-RIGG | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 12 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-07-09 | 2024-07-10 | 2022-03-28 | 2022-11-23 | 60 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | PRODTECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-07-10 | 2024-07-11 | 2022-03-28 | 2022-11-23 | 70 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-MECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 5 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-07-09 | 2024-07-10 | 2022-03-28 | 2022-11-23 | 80 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
4 | D-FLARE | WGN | MTN-MECH | PRODTECH | 2200008895 | PSV Calibration - DFCI-PSV-33030 - 2022 | Rigging Assist (Install) | SCHSECE | SCHSECE | 4 | 0 | W19-W20 | 2024-05-06 | 2024-07-11 | 2024-07-09 | 2024-07-10 | 2022-03-28 | 2022-11-23 | 90 | SCHSECE | SCHSECE | DF /C /10/DFCI-PSV-33030 | Rigging Assist (Install) | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328723 | 6M SW BOOSTER PUMP MAINT DFAA-P-3506/07 | SW BOOSTER PUMP MAINT DFAA-P-3506/07 |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-16 | 2024-06-04 | 10 |  |  | DF /A /54/DFAA-P-3506 | SW BOOSTER PUMP MAINT DFAA-P-3506/07 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098344 | DFG/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-10-29 | 2024-03-12 | 10 |  |  | DF /G /78/DFGA-MD-6140 | Drain coolant & refill with new type | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098344 | DFG/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-10-29 | 2024-03-12 | 20 |  |  | DF /G /78/DFGA-MD-6140 | Drain coolant & refill with new type | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100098344 | DFG/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-10-29 | 2024-03-12 | 30 |  |  | DF /G /78/DFGA-MD-6140 | Drain coolant & refill with new type | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098344 | DFG/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-10-29 | 2024-03-12 | 40 |  |  | DF /G /78/DFGA-MD-6140 | Drain coolant & refill with new type | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298229 | 1Y SYS 51 CONTROL VALVES MAINT-DAN FE | SYS 51 CONTROL VALVES MAINT-DAN FE |  |  | 17 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-26 | 2024-08-30 | 2023-12-09 | 2024-01-14 | 10 |  |  | DF /E /51/INSTRUMENTS | SYS 51 CONTROL VALVES MAINT-DAN FE | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400298229 | 1Y SYS 51 CONTROL VALVES MAINT-DAN FE | SYS 51 CONTROL VALVES MAINT-DAN FE |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-30 | 2024-09-01 | 2023-12-09 | 2024-01-14 | 20 |  |  | DF /E /51/INSTRUMENTS | SYS 51 CONTROL VALVES MAINT-DAN FE | Unknown
B | DFG-3590 | WPM | MTN-INST | MTN-INST | 2400291807 | 1Y DFGA-FIT-570036 - METERING | DFGA-FIT-570036 - METERING | AWSCSCH | AWSCSCH | 6 | 0 | W13-W14 | 2024-06-03 | 2024-06-07 | 2024-06-03 | 2024-06-04 | 2023-11-16 | 2023-12-16 | 10 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-FE-570036 | DFGA-FIT-570036 - METERING | Unknown
B | DFG-3590 | WPM | MTN-INST | PRODTECH | 2400291807 | 1Y DFGA-FIT-570036 - METERING | DFGA-FIT-570036 - METERING | AWSCSCH | AWSCSCH | 2 | 0 | W13-W14 | 2024-06-03 | 2024-06-07 | 2024-06-04 | 2024-06-04 | 2023-11-16 | 2023-12-16 | 20 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-FE-570036 | DFGA-FIT-570036 - METERING | Unknown
B | DFG-3590 | WPM | MTN-INST | MTN-MECH | 2400291807 | 1Y DFGA-FIT-570036 - METERING | DFGA-FIT-570036 - METERING | AWSCSCH | AWSCSCH | 6 | 0 | W13-W14 | 2024-06-03 | 2024-06-07 | 2024-06-05 | 2024-06-06 | 2023-11-16 | 2023-12-16 | 30 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-FE-570036 | DFGA-FIT-570036 - METERING | Unknown
B | DFG-3590 | WPM | MTN-INST | MTN-RIGG | 2400291807 | 1Y DFGA-FIT-570036 - METERING | DFGA-FIT-570036 - METERING | AWSCSCH | AWSCSCH | 6 | 0 | W13-W14 | 2024-06-03 | 2024-06-07 | 2024-06-06 | 2024-06-07 | 2023-11-16 | 2023-12-16 | 40 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-FE-570036 | DFGA-FIT-570036 - METERING | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 12 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-14 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 10 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 12 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-14 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 20 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 0 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-10 | 2022-03-18 | 2022-04-07 | 30 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-15 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 40 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 2 | 24 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-16 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 50 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-RIGG | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 4 | 30 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-16 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 55 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 4 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-17 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 60 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-10 | 2022-03-18 | 2022-04-07 | 70 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-RIGG | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 4 | 4 | W39-40 | 2024-11-10 | 2024-11-19 | 2023-02-19 | 2023-10-06 | 2022-03-18 | 2022-04-07 | 75 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 4 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-10 | 2022-03-18 | 2022-04-07 | 80 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 1 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-10 | 2022-03-18 | 2022-04-07 | 90 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 2 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-10 | 2022-03-18 | 2022-04-07 | 100 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 2 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-10 | 2022-03-18 | 2022-04-07 | 110 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-10 | 2024-11-11 | 2022-03-18 | 2022-04-07 | 120 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 4 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-11 | 2024-11-12 | 2022-03-18 | 2022-04-07 | 130 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 4 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-12 | 2024-11-13 | 2022-03-18 | 2022-04-07 | 140 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 8 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-13 | 2024-11-15 | 2022-03-18 | 2022-04-07 | 150 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 8 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-15 | 2024-11-17 | 2022-03-18 | 2022-04-07 | 160 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-17 | 2024-11-17 | 2022-03-18 | 2022-04-07 | 170 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 2 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-17 | 2024-11-18 | 2022-03-18 | 2022-04-07 | 180 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100064889 | DFF-ESDV-340554 stock open | Troubleshoot Switchbox/controlpanel | PCNF | PCNF | 3 | 0 | W39-40 | 2024-11-10 | 2024-11-19 | 2024-11-18 | 2024-11-19 | 2022-03-18 | 2022-04-07 | 190 | PCNF | PCNF | DF /F /20/DFFA-ESDV-340554 | Troubleshoot Switchbox/controlpanel | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-11 | 2024-01-13 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-14 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 45 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-19 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-19 | 2024-01-22 | 2022-02-09 | 2022-07-09 | 60 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009252 | Insulation assist bilfinger 20976 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-22 | 2024-01-23 | 2022-02-09 | 2022-07-09 | 70 |  |  | DF /G /11/DFG-6-GPS-034-0008-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 0 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2021-12-08 | 2022-05-07 | 10 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 0 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2021-12-08 | 2022-05-07 | 20 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 0 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-06 | 2021-12-08 | 2022-05-07 | 30 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 60 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-06 | 2023-11-09 | 2021-12-08 | 2022-05-07 | 40 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 0 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-09 | 2023-11-09 | 2021-12-08 | 2022-05-07 | 50 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 16 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-09 | 2023-11-10 | 2021-12-08 | 2022-05-07 | 60 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100055793 | ANOPR: Utility & Instrument Air Batch-02 | Plant air spools SCFM 9V corrosion |  |  | 0 | 0 | Empty | 2023-11-06 | 2023-11-10 | 2023-11-10 | 2023-11-10 | 2021-12-08 | 2022-05-07 | 70 |  |  | DF /A /07/DFA-1-AU-054-0653-A1-U | Plant air spools SCFM 9V corrosion | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400285959 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-10-08 | 2023-11-07 | 10 |  |  | DF /F /54/DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400285959 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-10-08 | 2023-11-07 | 20 |  |  | DF /F /54/DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400285959 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION |  |  | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-10-08 | 2023-11-07 | 30 |  |  | DF /F /54/DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400285959 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-10-08 | 2023-11-07 | 40 |  |  | DF /F /54/DFFA-EP-3807 | DE-ISOLATION BY PRODUCTION | Unknown
3 | DFF-W03 | WDF | MTN-MECH | PRODTECH | 2100029430 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3101 | Install new SSSV Pilot Valve | AWSCSCH | AWSCSCH | 2 | 0 | W21-W22 | 2024-05-28 | 2024-05-30 | 2024-05-28 | 2024-05-29 | 2020-03-22 | 2020-05-01 | 10 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3101 | Install new SSSV Pilot Valve | Unknown
3 | DFF-W03 | WDF | MTN-MECH | MTN-MECH | 2100029430 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3101 | Install new SSSV Pilot Valve | AWSCSCH | AWSCSCH | 3 | 0 | W21-W22 | 2024-05-28 | 2024-05-30 | 2024-05-29 | 2024-05-29 | 2020-03-22 | 2020-05-01 | 20 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3101 | Install new SSSV Pilot Valve | Unknown
3 | DFF-W03 | WDF | MTN-MECH | MTN-MECH | 2100029430 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3101 | Install new SSSV Pilot Valve | AWSCSCH | AWSCSCH | 1 | 0 | W21-W22 | 2024-05-28 | 2024-05-30 | 2024-05-29 | 2024-05-30 | 2020-03-22 | 2020-05-01 | 25 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3101 | Install new SSSV Pilot Valve | Unknown
3 | DFF-W03 | WDF | MTN-MECH | PRODTECH | 2100029430 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3101 | Install new SSSV Pilot Valve | AWSCSCH | AWSCSCH | 2 | 0 | W21-W22 | 2024-05-28 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2020-03-22 | 2020-05-01 | 30 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3101 | Install new SSSV Pilot Valve | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100114624 | DFF Degasser LT deviation Scada & ESD | Calibrate Level transmitter | SECE | SECE | 0 | 4 | W29-W30 | 2024-07-14 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-06-17 | 2024-08-01 | 10 | SECE | SECE | DF /F /27/DFFA-LIT-500412 | Calibrate Level transmitter | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100114624 | DFF Degasser LT deviation Scada & ESD | Calibrate Level transmitter | SECE | SECE | 4 | 16 | W29-W30 | 2024-07-14 | 2024-07-29 | 2024-07-15 | 2024-07-15 | 2024-06-17 | 2024-08-01 | 20 | SECE | SECE | DF /F /27/DFFA-LIT-500412 | Calibrate Level transmitter | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058591 | Defect DFCI-FI-57791 | Replace Flow gauge |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-02-06 | 2022-07-06 | 10 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058591 | Defect DFCI-FI-57791 | Replace Flow gauge |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-02-06 | 2022-07-06 | 20 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058591 | Defect DFCI-FI-57791 | Replace Flow gauge |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-02-06 | 2022-07-06 | 30 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
B | NOSD | WPM | MTN-TELE | MTN-TELE | 2400344343 | 18M ULTRASONIC GAS DETECTORS CHECK - DFG | ULTRASONIC GAS DETECTORS CHECK |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-08-11 | 2024-09-26 | 10 |  |  | DF /G /03/FGS-DETECTORS | ULTRASONIC GAS DETECTORS CHECK | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337273 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL DE-ISOLATION |  |  | 1 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-08-17 | 10 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337273 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL DE-ISOLATION |  |  | 8 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-18 | 2024-07-20 | 2024-07-18 | 2024-08-17 | 20 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337273 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL DE-ISOLATION |  |  | 3 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-20 | 2024-07-20 | 2024-07-18 | 2024-08-17 | 30 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337273 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL DE-ISOLATION |  |  | 1 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-18 | 2024-08-17 | 40 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337273 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL DE-ISOLATION |  |  | 2 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-18 | 2024-08-17 | 50 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL DE-ISOLATION | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316005 | 4000H COMPRESSOR SKID, COUNTER | DATA & OIL SAMPLING AND GREASING | AWSCSCH | AWSCSCH | 20 | 20 | W25-W26 | 2024-06-20 | 2024-06-25 | 2024-06-20 | 2024-06-25 | 2024-04-03 | 2024-04-19 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | DATA & OIL SAMPLING AND GREASING | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 2 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-08-05 | 2024-08-05 | 2024-08-18 | 2024-09-17 | 10 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 144 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-08-05 | 2024-08-23 | 2024-08-18 | 2024-09-17 | 20 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 12 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-08-23 | 2024-08-26 | 2024-08-18 | 2024-09-17 | 30 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 2 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-08-26 | 2024-08-26 | 2024-08-18 | 2024-09-17 | 50 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 24 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-08-27 | 2024-09-01 | 2024-08-18 | 2024-09-17 | 60 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 12 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-09-02 | 2024-09-04 | 2024-08-18 | 2024-09-17 | 80 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 16 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-09-05 | 2024-09-08 | 2024-08-18 | 2024-09-17 | 90 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321273 | 1Y PED CRANE CHECK VENDOR DFBA-X-6102 | order rothe erde test kit | AWSC | AWSC | 0 | 0 | Empty | 2024-08-05 | 2024-09-08 | 2024-09-08 | 2024-09-08 | 2024-08-18 | 2024-09-17 | 100 | AWSC | AWSC | DF /B /78/DFBA-X-6102 | order rothe erde test kit | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235852 | 4Y 400V E-SWB MAINT DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235852 | 4Y 400V E-SWB MAINT DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235852 | 4Y 400V E-SWB MAINT DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235852 | 4Y 400V E-SWB MAINT DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A15 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2022-12-18 | 2023-05-02 | 10 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 2 | 2 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2022-12-18 | 2023-05-02 | 20 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 10 | 16 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-17 | 2022-12-18 | 2023-05-02 | 25 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 12 | 20 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-18 | 2022-12-18 | 2023-05-02 | 30 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 2 | 2 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-18 | 2024-07-19 | 2022-12-18 | 2023-05-02 | 40 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 8 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2022-12-18 | 2023-05-02 | 60 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078006 | Replace 6pcs. N2 cylinders DFGA-A-0461 | Rigging assistance and Gallow |  |  | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2022-12-18 | 2023-05-02 | 70 |  |  | DF /G /01/DFGA-A-0461 | Rigging assistance and Gallow | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100040411 | Replace 32A socketoutlet WO 1811 | Repair cable |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2021-01-22 | 2021-06-21 | 10 |  |  | DF /G /61/DFGA-N-1842A-AF01-JA001 | Repair cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040411 | Replace 32A socketoutlet WO 1811 | Repair cable |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2021-01-22 | 2021-06-21 | 20 |  |  | DF /G /61/DFGA-N-1842A-AF01-JA001 | Repair cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040411 | Replace 32A socketoutlet WO 1811 | Repair cable |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2021-01-22 | 2021-06-21 | 30 |  |  | DF /G /61/DFGA-N-1842A-AF01-JA001 | Repair cable | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100040411 | Replace 32A socketoutlet WO 1811 | Repair cable |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2021-01-22 | 2021-06-21 | 40 |  |  | DF /G /61/DFGA-N-1842A-AF01-JA001 | Repair cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040411 | Replace 32A socketoutlet WO 1811 | Repair cable |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2021-01-22 | 2021-06-21 | 50 |  |  | DF /G /61/DFGA-N-1842A-AF01-JA001 | Repair cable | Unknown
4 | Empty | WRO | MTN-CRAN | MTN-CRAN | 2300001861 | DK40 - CONSUMABLE MTN - CRAN (CRANE) | DK40 - CONSUMABLE MTN - CRAN (CRANE) |  |  | 0 | 0 | Empty | 2021-01-23 | 2021-01-23 | 2021-01-23 | 2021-01-23 | 2021-01-23 | 2021-11-19 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - CRAN (CRANE) | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235903 | 6M GANTRY CRANE CHECK VENDR-DFEZ-X-6150 | Assist | AWSC | AWSC | 24 | 0 | Empty | 2024-06-03 | 2024-06-07 | 2024-06-03 | 2024-06-05 | 2023-03-10 | 2023-03-26 | 10 | AWSC | AWSC | DF /E /78/DFEZ-X-6150 | Assist | Unknown
B | NOSD | WPM | MTN-MECH | MTN-CRAN | 2400235903 | 6M GANTRY CRANE CHECK VENDR-DFEZ-X-6150 | Assist | AWSC | AWSC | 6 | 0 | Empty | 2024-06-03 | 2024-06-07 | 2024-06-06 | 2024-06-07 | 2023-03-10 | 2023-03-26 | 20 | AWSC | AWSC | DF /E /78/DFEZ-X-6150 | Assist | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100096746 | ANOCR DFB-DFC Bridge - Paint Prim. Str. | De-rig equipment | PCNF | PCNF | 0 | 0 | Empty | 2024-02-20 | 2024-03-14 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2025-12-31 | 10 | PCNF | PCNF | DF /C /86/BRIDGE-DFB-DFC | De-rig equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100096746 | ANOCR DFB-DFC Bridge - Paint Prim. Str. | De-rig equipment | PCNF | PCNF | 15 | 55 | Empty | 2024-02-20 | 2024-03-14 | 2024-02-20 | 2024-02-21 | 2024-02-20 | 2025-12-31 | 20 | PCNF | PCNF | DF /C /86/BRIDGE-DFB-DFC | De-rig equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100096746 | ANOCR DFB-DFC Bridge - Paint Prim. Str. | De-rig equipment | PCNF | PCNF | 15 | 5 | Empty | 2024-02-20 | 2024-03-14 | 2024-02-21 | 2024-02-22 | 2024-02-20 | 2025-12-31 | 30 | PCNF | PCNF | DF /C /86/BRIDGE-DFB-DFC | De-rig equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100096746 | ANOCR DFB-DFC Bridge - Paint Prim. Str. | De-rig equipment | PCNF | PCNF | 387 | 418 | Empty | 2024-02-20 | 2024-03-14 | 2024-02-22 | 2024-03-13 | 2024-02-20 | 2025-12-31 | 40 | PCNF | PCNF | DF /C /86/BRIDGE-DFB-DFC | De-rig equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100096746 | ANOCR DFB-DFC Bridge - Paint Prim. Str. | De-rig equipment | PCNF | PCNF | 15 | 6 | Empty | 2024-02-20 | 2024-03-14 | 2024-03-13 | 2024-03-14 | 2024-02-20 | 2025-12-31 | 50 | PCNF | PCNF | DF /C /86/BRIDGE-DFB-DFC | De-rig equipment | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004029 | Replaced by 2300004391 | DK40 - CONSUMABLE PROD - SAFETY EQ |  |  | 0 | 0 | Empty | 2023-01-04 | 2023-01-04 | 2023-01-04 | 2023-01-04 | 2023-01-04 | 2025-06-22 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - SAFETY EQ | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100081335 | HT faultfinding DP-1829A-C11 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-02 | 2023-07-15 | 10 |  |  | DF /C /61/DFCI-DP-1829A-K2-11 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100081335 | HT faultfinding DP-1829A-C11 | Isolate and prove dead |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-02 | 2023-07-15 | 20 |  |  | DF /C /61/DFCI-DP-1829A-K2-11 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100081335 | HT faultfinding DP-1829A-C11 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-02 | 2023-07-15 | 30 |  |  | DF /C /61/DFCI-DP-1829A-K2-11 | Isolate and prove dead | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343680 | 1Y WIRELINE OVERRIDE PANELS - DFA | WIRELINE OVERRIDE PANELS - DFA |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-08-14 | 2024-09-13 | 10 |  |  | DF /A /07 | WIRELINE OVERRIDE PANELS - DFA | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400343680 | 1Y WIRELINE OVERRIDE PANELS - DFA | WIRELINE OVERRIDE PANELS - DFA |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-08-14 | 2024-09-13 | 20 |  |  | DF /A /07 | WIRELINE OVERRIDE PANELS - DFA | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030534 | Adjust DFGA-XCV-340037 ZSC/O (DFG HP-sep | Adjust DFGA-XCV-340037 ZSC/O |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-04-12 | 2020-05-22 | 10 |  |  | DF /G /27/DFGA-XCV-340037 | Adjust DFGA-XCV-340037 ZSC/O | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100030534 | Adjust DFGA-XCV-340037 ZSC/O (DFG HP-sep | Adjust DFGA-XCV-340037 ZSC/O |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2020-04-12 | 2020-05-22 | 20 |  |  | DF /G /27/DFGA-XCV-340037 | Adjust DFGA-XCV-340037 ZSC/O | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235650 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L12 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L12B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235650 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L12 | ISOLATION ELECTRICAL | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L12B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235650 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L12 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L12B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235650 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L12 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L12B | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322252 | DFC-75-CM-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000930 | ESD SW for DFDCOM | ESD SW for DFDCOM | AWSC | AWSC | 24 | 0 | W49 ABB | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-07 | 2019-06-20 | 2019-11-17 | 10 | AWSC | AWSC | DF /C /03/DFCI-FP-0204 | ESD SW for DFDCOM | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000930 | ESD SW for DFDCOM | ESD SW for DFDCOM | AWSC | AWSC | 10 | 0 | W49 ABB | 2024-10-05 | 2024-10-10 | 2024-10-07 | 2024-10-10 | 2019-06-20 | 2019-11-17 | 20 | AWSC | AWSC | DF /C /03/DFCI-FP-0204 | ESD SW for DFDCOM | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000930 | ESD SW for DFDCOM | ESD SW for DFDCOM | AWSC | AWSC | 0 | 0 | W49 ABB | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2019-06-20 | 2019-11-17 | 30 | AWSC | AWSC | DF /C /03/DFCI-FP-0204 | ESD SW for DFDCOM | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241149 | 1Y WI FILT & BLOWERS MAINT-DFFA-A-3501 | WI FILT & BLOWERS MAINT-DFFA-A-3501 |  |  | 24 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-08-04 | 2023-02-27 | 2023-03-29 | 20 |  |  | DF /F /51/DFFA-A-3501 | WI FILT & BLOWERS MAINT-DFFA-A-3501 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400241149 | 1Y WI FILT & BLOWERS MAINT-DFFA-A-3501 | WI FILT & BLOWERS MAINT-DFFA-A-3501 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-02-27 | 2023-03-29 | 30 |  |  | DF /F /51/DFFA-A-3501 | WI FILT & BLOWERS MAINT-DFFA-A-3501 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015382 | Replace DFE LB coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /E /02/DFEZ-X-0701 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015382 | Replace DFE LB coolant with GlysantinG30 | Isolate lifeboat |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /E /02/DFEZ-X-0701 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015382 | Replace DFE LB coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /E /02/DFEZ-X-0701 | Isolate lifeboat | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003200 | CMAT:ESDV / BDV-Udskifte def manometre. | Safing af ESDV-33077 | SCH | SCH | 2 | 0 | W45-46 | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2023-11-06 | 2018-01-19 | 2019-01-14 | 10 | SCH | SCH | DF /B /55/DFBA-ESDV-35790 | Safing af ESDV-33077 | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003200 | CMAT:ESDV / BDV-Udskifte def manometre. | Safing af ESDV-33077 | SCH | SCH | 2 | 0 | W45-46 | 2023-11-06 | 2023-11-07 | 2023-11-06 | 2023-11-07 | 2018-01-19 | 2019-01-14 | 20 | SCH | SCH | DF /B /55/DFBA-ESDV-35790 | Safing af ESDV-33077 | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003200 | CMAT:ESDV / BDV-Udskifte def manometre. | Safing af ESDV-33077 | SCH | SCH | 2 | 0 | W45-46 | 2023-11-06 | 2023-11-07 | 2023-11-07 | 2023-11-07 | 2018-01-19 | 2019-01-14 | 30 | SCH | SCH | DF /B /55/DFBA-ESDV-35790 | Safing af ESDV-33077 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339275 | DFF_1Y_33000 INT STRUCT INSP - GVI | DFF_1Y_33000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_33000 (MEZZ DECK) | DFF_1Y_33000 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-26 | 2021-10-29 | 2022-03-28 | 10 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-26 | 2021-10-29 | 2022-03-28 | 20 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-28 | 2021-10-29 | 2022-03-28 | 30 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 24 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-28 | 2024-08-30 | 2021-10-29 | 2022-03-28 | 40 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-30 | 2024-08-31 | 2021-10-29 | 2022-03-28 | 50 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2021-10-29 | 2022-03-28 | 60 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053893 | HT replace 1854-0041-L2A | Remove insulation |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-26 | 2021-10-29 | 2022-03-28 | 70 |  |  | DF /G /61/DFGA-DP-1854-41 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081338 | Transmitterhus er defekt dfga-ft-550022 | Isolate Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 10 |  |  | DF /G /52/DFGA-FT-550022 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081338 | Transmitterhus er defekt dfga-ft-550022 | Isolate Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 20 |  |  | DF /G /52/DFGA-FT-550022 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100081338 | Transmitterhus er defekt dfga-ft-550022 | Isolate Flow meter |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 30 |  |  | DF /G /52/DFGA-FT-550022 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081338 | Transmitterhus er defekt dfga-ft-550022 | Isolate Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 40 |  |  | DF /G /52/DFGA-FT-550022 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081338 | Transmitterhus er defekt dfga-ft-550022 | Isolate Flow meter |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 50 |  |  | DF /G /52/DFGA-FT-550022 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081338 | Transmitterhus er defekt dfga-ft-550022 | Isolate Flow meter |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 60 |  |  | DF /G /52/DFGA-FT-550022 | Isolate Flow meter | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400302021 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-01-22 | 2024-02-01 | 10 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400302021 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 12 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-01-22 | 2024-02-01 | 20 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400302021 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-01-22 | 2024-02-01 | 30 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077766 | FB-08 LG manifoldvalve externally leak | PO Grønbech |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-29 | 2022-11-10 | 2022-12-25 | 10 |  |  | DF /B /37 | PO Grønbech | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077766 | FB-08 LG manifoldvalve externally leak | PO Grønbech |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-29 | 2022-11-10 | 2022-12-25 | 20 |  |  | DF /B /37 | PO Grønbech | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077766 | FB-08 LG manifoldvalve externally leak | PO Grønbech |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-29 | 2022-11-10 | 2022-12-25 | 30 |  |  | DF /B /37 | PO Grønbech | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077766 | FB-08 LG manifoldvalve externally leak | PO Grønbech |  |  | 50 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-08-10 | 2022-11-10 | 2022-12-25 | 40 |  |  | DF /B /37 | PO Grønbech | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 27 | 1 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-16 | 2023-02-16 | 2021-03-24 | 2021-03-29 | 10 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 5 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-16 | 2023-02-16 | 2021-03-24 | 2021-03-29 | 20 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 5 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-16 | 2023-02-17 | 2021-03-24 | 2021-03-29 | 30 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 4 | 1 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-17 | 2023-02-17 | 2021-03-24 | 2021-03-29 | 40 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 21 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-17 | 2023-02-19 | 2021-03-24 | 2021-03-29 | 50 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 3 | 7.5 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-19 | 2023-02-19 | 2021-03-24 | 2021-03-29 | 60 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 2 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-19 | 2023-02-19 | 2021-03-24 | 2021-03-29 | 70 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 2 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-19 | 2023-02-19 | 2021-03-24 | 2021-03-29 | 80 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 11 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-19 | 2023-02-20 | 2021-03-24 | 2021-03-29 | 90 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 13 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-20 | 2023-02-22 | 2021-03-24 | 2021-03-29 | 100 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 2 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-22 | 2023-02-22 | 2021-03-24 | 2021-03-29 | 110 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002818 | DAF OCG NPT order - ENG469C-CORROSION IN | Shuttling | PCNF | PCNF | 11 | 0 | Empty | 2023-02-16 | 2023-02-23 | 2023-02-22 | 2023-02-23 | 2021-03-24 | 2021-03-29 | 120 | PCNF | PCNF | DF /F | Shuttling | Unknown
3 | SIWL | WDF | MTN-INST | PRODTECH | 2100030499 | DFB22 har extern leak på skuffe | Change out and backload drawer |  |  | 2 | 0 | Materials? | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-04-03 | 2020-07-02 | 10 |  |  | DF /B /07/DFBA-A-3101B | Change out and backload drawer | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100030499 | DFB22 har extern leak på skuffe | Change out and backload drawer |  |  | 5 | 0 | Materials? | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2020-04-03 | 2020-07-02 | 20 |  |  | DF /B /07/DFBA-A-3101B | Change out and backload drawer | Unknown
3 | SIWL | WDF | MTN-INST | PRODTECH | 2100030499 | DFB22 har extern leak på skuffe | Change out and backload drawer |  |  | 2 | 0 | Materials? | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2020-04-03 | 2020-07-02 | 30 |  |  | DF /B /07/DFBA-A-3101B | Change out and backload drawer | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241159 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-04-01 | 2023-04-12 | 20 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241159 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2023-04-01 | 2023-04-12 | 30 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235312 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-04 | 3KV E-SWB MAINT-DFCI-N-1811-04 | AWSCSCHSECE | AWSCSCHSECE | 12 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-04 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235312 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-04 | 3KV E-SWB MAINT-DFCI-N-1811-04 | AWSCSCHSECE | AWSCSCHSECE | 5 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-04 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235312 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-04 | 3KV E-SWB MAINT-DFCI-N-1811-04 | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-04 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235312 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-04 | 3KV E-SWB MAINT-DFCI-N-1811-04 | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-14 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-04 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235312 | 4Y 3KV E-SWB MAINT-DFCI-N-1811-04 | 3KV E-SWB MAINT-DFCI-N-1811-04 | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2022-12-31 | 2023-03-14 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1811 | 3KV E-SWB MAINT-DFCI-N-1811-04 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057926 | FLMR DFB - Repl. Handrail EL. 27.050 | DFB - Replacement Handrail EL. 27.050 |  |  | 0 | 0 | Empty | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-06-23 | 10 |  |  | DF /B /86/27050 - HANDRAILS | DFB - Replacement Handrail EL. 27.050 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057926 | FLMR DFB - Repl. Handrail EL. 27.050 | DFB - Replacement Handrail EL. 27.050 |  |  | 2 | 0 | Empty | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-06-23 | 20 |  |  | DF /B /86/27050 - HANDRAILS | DFB - Replacement Handrail EL. 27.050 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057926 | FLMR DFB - Repl. Handrail EL. 27.050 | DFB - Replacement Handrail EL. 27.050 |  |  | 0 | 0 | Empty | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-06-23 | 30 |  |  | DF /B /86/27050 - HANDRAILS | DFB - Replacement Handrail EL. 27.050 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057926 | FLMR DFB - Repl. Handrail EL. 27.050 | DFB - Replacement Handrail EL. 27.050 |  |  | 0 | 0 | Empty | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-06-23 | 40 |  |  | DF /B /86/27050 - HANDRAILS | DFB - Replacement Handrail EL. 27.050 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077077 | DFFA-XCV-500712 INTERN LEAK | DFFA-XCV-500712 INTERN LEAK |  |  | 0 | 0 | W33-W34 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2022-10-30 | 2022-12-14 | 10 |  |  | DF /F /27/DFFA-XCV-500712 | DFFA-XCV-500712 INTERN LEAK | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077077 | DFFA-XCV-500712 INTERN LEAK | DFFA-XCV-500712 INTERN LEAK |  |  | 24 | 0 | W33-W34 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-18 | 2022-10-30 | 2022-12-14 | 20 |  |  | DF /F /27/DFFA-XCV-500712 | DFFA-XCV-500712 INTERN LEAK | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100073420 | DFB/78 Replace wire rope guards in boom | Build/remove scaffolding |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-15 | 2023-02-12 | 2025-07-31 | 10 |  |  | DF /B /78/DFBA-X-6102 | Build/remove scaffolding | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100073420 | DFB/78 Replace wire rope guards in boom | Build/remove scaffolding |  |  | 24 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-16 | 2024-07-21 | 2023-02-12 | 2025-07-31 | 20 |  |  | DF /B /78/DFBA-X-6102 | Build/remove scaffolding | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100073420 | DFB/78 Replace wire rope guards in boom | Build/remove scaffolding |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-16 | 2024-07-19 | 2023-02-12 | 2025-07-31 | 30 |  |  | DF /B /78/DFBA-X-6102 | Build/remove scaffolding | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100073420 | DFB/78 Replace wire rope guards in boom | Build/remove scaffolding |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-19 | 2024-07-23 | 2023-02-12 | 2025-07-31 | 40 |  |  | DF /B /78/DFBA-X-6102 | Build/remove scaffolding | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-20 | 2022-06-03 | 2022-09-01 | 10 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-19 | 2022-06-03 | 2022-09-01 | 20 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-19 | 2022-06-03 | 2022-09-01 | 30 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 14 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-20 | 2024-09-23 | 2022-06-03 | 2022-09-01 | 40 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-23 | 2024-09-25 | 2022-06-03 | 2022-09-01 | 50 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-25 | 2024-09-27 | 2022-06-03 | 2022-09-01 | 60 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2022-06-03 | 2022-09-01 | 70 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067913 | HCV-340008-U Internally leaking | Rigger assistance |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-28 | 2024-09-30 | 2022-06-03 | 2022-09-01 | 80 |  |  | DF /F /10/DFFA-HCV-340008-U | Rigger assistance | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322312 | DFG-36-GI-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400329523 | 3M PORTABLE RADIO MAINT-DFC | PORTABLE RADIO MAINT-DFC | SCHSECE | SCHSECE | 3 | 0 | W23-W24 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-22 | 10 | SCHSECE | SCHSECE | DF /C /08/EXTERNAL-COMMUNICATION | PORTABLE RADIO MAINT-DFC | Unknown
3 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 10 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 20 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 40 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 50 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 100.5 | 125.5 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 55 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-LAGG | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 8 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 60 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 20 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-05-02 | 2020-01-23 | 2020-03-03 | 65 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 24 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-02 | 2023-05-07 | 2020-01-23 | 2020-03-03 | 68 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 120 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-07 | 2023-05-13 | 2020-01-23 | 2020-03-03 | 70 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 64 | 11 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-13 | 2023-05-13 | 2020-01-23 | 2020-03-03 | 80 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 60.29999999999999715782905694 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-13 | 2023-05-16 | 2020-01-23 | 2020-03-03 | 90 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 234.5 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-16 | 2023-05-29 | 2020-01-23 | 2020-03-03 | 100 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | VEN-ELEC | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 26 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-16 | 2023-05-16 | 2020-01-23 | 2020-03-03 | 110 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 20 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-16 | 2023-05-16 | 2020-01-23 | 2020-03-03 | 120 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 30 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-16 | 2023-05-17 | 2020-01-23 | 2020-03-03 | 130 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 26 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-16 | 2023-05-18 | 2020-01-23 | 2020-03-03 | 140 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 20 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-17 | 2023-05-17 | 2020-01-23 | 2020-03-03 | 150 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 24 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-17 | 2023-05-18 | 2020-01-23 | 2020-03-03 | 160 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 20 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-17 | 2023-05-18 | 2020-01-23 | 2020-03-03 | 170 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 12 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-18 | 2023-05-20 | 2020-01-23 | 2020-03-03 | 180 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 12 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-20 | 2023-05-23 | 2020-01-23 | 2020-03-03 | 185 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 24 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-23 | 2023-05-25 | 2020-01-23 | 2020-03-03 | 190 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 24 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-23 | 2023-05-23 | 2020-01-23 | 2020-03-03 | 200 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 52 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-23 | 2023-05-25 | 2020-01-23 | 2020-03-03 | 210 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 52 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-23 | 2023-05-29 | 2020-01-23 | 2020-03-03 | 220 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-LAGG | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 12 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-29 | 2023-05-29 | 2020-01-23 | 2020-03-03 | 230 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | VEN-ELEC | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 16 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-29 | 2023-05-29 | 2020-01-23 | 2020-03-03 | 240 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-PAIN | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 60 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-29 | 2023-05-31 | 2020-01-23 | 2020-03-03 | 250 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-31 | 2023-05-31 | 2020-01-23 | 2020-03-03 | 260 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 140 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-05-31 | 2023-06-08 | 2020-01-23 | 2020-03-03 | 270 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 280 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 290 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 300 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 310 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 320 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | WELLSUPV | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 0 | 0 | Empty | 2023-04-28 | 2023-06-08 | 2023-04-28 | 2023-04-28 | 2020-01-23 | 2020-03-03 | 330 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
3 | DFX-OIL | WDF | MTN-MECH | MTN-ROPE | 2100023165 | DGSPR 622415 DFC. Replacement of 24in Mu | 1:1 Replacement of 24in Multiphase line | AWSC | AWSC | 36 | 36 | Empty | 2023-04-28 | 2023-06-08 | 2023-03-25 | 2023-03-25 | 2020-01-23 | 2020-03-03 | 340 | AWSC | AWSC | DF /C /12/DFC-24-PHS-034-6511-AB-U | 1:1 Replacement of 24in Multiphase line | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400302678 | 6M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-01-31 | 2024-02-16 | 10 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302678 | 6M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-01-31 | 2024-02-16 | 20 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400302678 | 6M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-01-31 | 2024-02-16 | 30 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2021-12-27 | 2021-12-30 | 2021-04-10 | 2021-07-09 | 10 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 2 | 10 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-10 | 2021-07-09 | 20 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 2 | 6 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-10 | 2021-07-09 | 30 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-10 | 2021-07-09 | 40 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-10 | 2021-07-09 | 50 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-04-10 | 2021-07-09 | 60 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-04-10 | 2021-07-09 | 70 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-10 | 2021-07-09 | 80 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100047437 | Replace flange motor PM-5141 | Replace motor | PCNF | PCNF | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-10 | 2021-07-09 | 90 | PCNF | PCNF | DF /G /82/DFGA-PM-5141 | Replace motor | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322308 | DFG-51-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /51/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085204 | LYS amature defective Upper walkway DFC- | Change light fixtures |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-03-28 | 2023-08-10 | 10 |  |  | DF /B /05/DFBA-N-1811 | Change light fixtures | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085204 | LYS amature defective Upper walkway DFC- | Change light fixtures |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-03-28 | 2023-08-10 | 20 |  |  | DF /B /05/DFBA-N-1811 | Change light fixtures | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085204 | LYS amature defective Upper walkway DFC- | Change light fixtures |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-03-28 | 2023-08-10 | 30 |  |  | DF /B /05/DFBA-N-1811 | Change light fixtures | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339090 | DFC_1Y_22000 INT STRUCT INSP - GVI | DFC_1Y_22000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_22000 (L1 CELLAR DECK) | DFC_1Y_22000 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 8.699999999999999289457264236 | 6 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2020-09-05 | 2020-11-10 | 2019-05-11 | 2019-08-09 | 10 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 120.59999999999999431565811388 | 3.5 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2021-01-03 | 2021-01-07 | 2019-05-11 | 2019-08-09 | 20 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 17.399999999999998578914528472 | 15.5 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2020-09-16 | 2020-10-23 | 2019-05-11 | 2019-08-09 | 30 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 1 | 0 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2021-01-03 | 2021-01-03 | 2019-05-11 | 2019-08-09 | 40 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 17.399999999999998578914528472 | 33 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2020-11-04 | 2020-12-27 | 2019-05-11 | 2019-08-09 | 50 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 80.40000000000000568434188606 | 0 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2022-04-17 | 2022-04-20 | 2019-05-11 | 2019-08-09 | 60 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003136 | Insulation assists FORCE 9323 | L3 build scaff | PCNF | PCNF | 0 | 0 | CNF - to be closed | 2021-01-03 | 2022-04-20 | 2021-01-03 | 2021-01-03 | 2019-05-11 | 2019-08-09 | 70 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7666-AB-T | L3 build scaff | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339091 | DFC_1Y_29000 INT STRUCT INSP - GVI | DFC_1Y_29000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_29000 (LEVEL2) | DFC_1Y_29000 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 1 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-09-18 | 2024-09-18 | 2018-02-19 | 2018-03-31 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 40 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-09-18 | 2024-09-23 | 2018-02-19 | 2018-03-31 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 40 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-09-23 | 2024-09-28 | 2018-02-19 | 2018-03-31 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 1 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-09-28 | 2024-09-28 | 2018-02-19 | 2018-03-31 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 1 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-11-28 | 2024-11-29 | 2018-02-19 | 2018-03-31 | 50 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 40 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-11-29 | 2024-12-04 | 2018-02-19 | 2018-03-31 | 60 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-CRAN | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 1 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2018-02-19 | 2018-03-31 | 70 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-ROPE | 2200003138 | DFB/78: Clean and paint handrail around | Isolate crane |  |  | 0 | 0 | Q2 2023 | 2024-09-18 | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2018-02-19 | 2018-03-31 | 80 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400351962 | 1Y IRIDIUM PORTABLE SATELLITE TELEPHONE | TL-1Y IRIDIUM PORTABLE SATELLITE TELEPHO | SECE | SECE | 3 | 0 | W37-W38 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-10-16 | 10 | SECE | SECE | DF /C /08/EXTERNAL-COMMUNICATION | TL-1Y IRIDIUM PORTABLE SATELLITE TELEPHO | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078485 | periodic fail disturbance on bypass line | PO Coromatic |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-01-08 | 2023-05-23 | 10 |  |  | DF /C /06/DFCI-AE-19211 | PO Coromatic | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078485 | periodic fail disturbance on bypass line | PO Coromatic |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-01-08 | 2023-05-23 | 20 |  |  | DF /C /06/DFCI-AE-19211 | PO Coromatic | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078485 | periodic fail disturbance on bypass line | PO Coromatic |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 2023-01-08 | 2023-05-23 | 30 |  |  | DF /C /06/DFCI-AE-19211 | PO Coromatic | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100064929 | DFAA-HCV-38101 hydraulic hoses expired | Production isolation |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-03-25 | 2022-05-04 | 10 |  |  | DF /A /12/DFAA-HCV-38101 | Production isolation | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100064929 | DFAA-HCV-38101 hydraulic hoses expired | Production isolation |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-03-25 | 2022-05-04 | 20 |  |  | DF /A /12/DFAA-HCV-38101 | Production isolation | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100064929 | DFAA-HCV-38101 hydraulic hoses expired | Production isolation |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-03-25 | 2022-05-04 | 30 |  |  | DF /A /12/DFAA-HCV-38101 | Production isolation | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 0 | 0 | Empty | 2023-04-29 | 2023-05-08 | 2023-04-29 | 2023-04-29 | 2023-04-29 | 2023-12-31 | 10 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 16 | 15 | Empty | 2023-04-29 | 2023-05-08 | 2023-04-29 | 2023-05-01 | 2023-04-29 | 2023-12-31 | 15 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 9 | 0 | Empty | 2023-04-29 | 2023-05-08 | 2023-05-01 | 2023-05-01 | 2023-04-29 | 2023-12-31 | 20 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 36 | 6 | Empty | 2023-04-29 | 2023-05-08 | 2023-05-01 | 2023-05-03 | 2023-04-29 | 2023-12-31 | 30 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 16 | 0 | Empty | 2023-04-29 | 2023-05-08 | 2023-05-03 | 2023-05-05 | 2023-04-29 | 2023-12-31 | 35 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 36 | 0 | Empty | 2023-04-29 | 2023-05-08 | 2023-05-05 | 2023-05-06 | 2023-04-29 | 2023-12-31 | 40 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 16 | 0 | Empty | 2023-04-29 | 2023-05-08 | 2023-05-06 | 2023-05-08 | 2023-04-29 | 2023-12-31 | 45 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077159 | SYNSR-667006 - Replace Handrail ST002 EL | DFA - Replace Handrail ST002 EL. 22.000 | PCNF | PCNF | 9 | 0 | Empty | 2023-04-29 | 2023-05-08 | 2023-05-08 | 2023-05-08 | 2023-04-29 | 2023-12-31 | 50 | PCNF | PCNF | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST002 EL. 22.000 | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-ROPE | 2100025286 | SMAT:HCV nedtsrøms FG fuel heater int læ | Line for missing materials | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2025-01-03 | 2016-01-26 | 2016-02-15 | 2 | AWSC | AWSC | DF /G /70/DFGA-XE-5742 | Line for missing materials | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-ROPE | 2100025286 | SMAT:HCV nedtsrøms FG fuel heater int læ | Line for missing materials | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-03 | 2025-01-05 | 2016-01-26 | 2016-02-15 | 3 | AWSC | AWSC | DF /G /70/DFGA-XE-5742 | Line for missing materials | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-ROPE | 2100025286 | SMAT:HCV nedtsrøms FG fuel heater int læ | Line for missing materials | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2025-01-10 | 2016-01-26 | 2016-02-15 | 5 | AWSC | AWSC | DF /G /70/DFGA-XE-5742 | Line for missing materials | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-ROPE | 2100025286 | SMAT:HCV nedtsrøms FG fuel heater int læ | Line for missing materials | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-10 | 2025-01-12 | 2016-01-26 | 2016-02-15 | 10 | AWSC | AWSC | DF /G /70/DFGA-XE-5742 | Line for missing materials | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100025286 | SMAT:HCV nedtsrøms FG fuel heater int læ | Line for missing materials | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-12 | 2025-01-12 | 2016-01-26 | 2016-02-15 | 20 | AWSC | AWSC | DF /G /70/DFGA-XE-5742 | Line for missing materials | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235709 | 4Y 380V E-SWB MAINT-DFBA-N-1831 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-24 | 2024-07-24 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235709 | 4Y 380V E-SWB MAINT-DFBA-N-1831 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 16 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-24 | 2024-07-26 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235709 | 4Y 380V E-SWB MAINT-DFBA-N-1831 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2023-02-14 | 2023-04-28 | 30 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235709 | 4Y 380V E-SWB MAINT-DFBA-N-1831 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2023-02-14 | 2023-04-28 | 40 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 8 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2022-11-16 | 2022-11-23 | 2021-11-21 | 2021-12-11 | 5 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | VEN-INSP | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 12 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2022-11-16 | 2022-11-23 | 2021-11-21 | 2021-12-11 | 10 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 8 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2022-11-16 | 2022-11-23 | 2021-11-21 | 2021-12-11 | 20 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 40 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2024-07-30 | 2024-07-30 | 2021-11-21 | 2021-12-11 | 30 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-LAGG | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 192 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2024-07-30 | 2024-08-01 | 2021-11-21 | 2021-12-11 | 40 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-LAGG | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 504 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2024-08-02 | 2024-08-13 | 2021-11-21 | 2021-12-11 | 50 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 3 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2024-08-01 | 2024-08-02 | 2021-11-21 | 2021-12-11 | 60 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 24 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2021-11-21 | 2021-12-11 | 70 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100058710 | DFF IP/HP Damaged Cladding on Exhaust | Insulation inspection & measurement | PCNF | PCNF | 0 | 0 | CHF | 2024-07-30 | 2024-08-13 | 2024-07-30 | 2024-07-30 | 2021-11-21 | 2021-12-11 | 80 | PCNF | PCNF | DF /F /31/DFFA-CT-4301 | Insulation inspection & measurement | Unknown
3 | NOSD | WGN | MTN-ROUS | VEN-MECH | 2200015625 | Replace diaphragm in DFC LB4 | Replace diaphragm in DFC LB4 | SCHSECE | SCHSECE | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-10-19 | 2024-03-02 | 10 | SCHSECE | SCHSECE | DF /C /02/DFCI-X-0704 | Replace diaphragm in DFC LB4 | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235570 | 4Y 400V N-DP-MAINT-DFFA-DP-18872 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-02 | 2023-06-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-DP-18872 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235570 | 4Y 400V N-DP-MAINT-DFFA-DP-18872 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-02 | 2023-06-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-DP-18872 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235570 | 4Y 400V N-DP-MAINT-DFFA-DP-18872 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-02 | 2023-06-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-DP-18872 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235570 | 4Y 400V N-DP-MAINT-DFFA-DP-18872 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-02 | 2023-06-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-DP-18872 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100112083 | HI-FOG DFCI-A-0410 PSL-04110 leaking | Isolate PSL | SECE | SECE | 1 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-06-18 | 2024-10-31 | 10 | SECE | SECE | DF /C /01/DFCI-PSL-04110 | Isolate PSL | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100112083 | HI-FOG DFCI-A-0410 PSL-04110 leaking | Isolate PSL | SECE | SECE | 3 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-06-18 | 2024-10-31 | 20 | SECE | SECE | DF /C /01/DFCI-PSL-04110 | Isolate PSL | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100112083 | HI-FOG DFCI-A-0410 PSL-04110 leaking | Isolate PSL | SECE | SECE | 1 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-06-18 | 2024-10-31 | 30 | SECE | SECE | DF /C /01/DFCI-PSL-04110 | Isolate PSL | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-SCAF | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-12-04 | 2019-05-03 | 10 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | PRODTECH | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2018-12-04 | 2019-05-03 | 20 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-MECH | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2018-12-04 | 2019-05-03 | 30 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-ELEC | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2018-12-04 | 2019-05-03 | 40 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-SCAF | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2018-12-04 | 2019-05-03 | 50 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-MECH | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2018-12-04 | 2019-05-03 | 60 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-ELEC | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2018-12-04 | 2019-05-03 | 70 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | PRODTECH | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-05 | 2018-12-04 | 2019-05-03 | 80 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
4 | DFF-COOL | WDF | MTN-MECH | MTN-SCAF | 2100025077 | Replace DFFA-ESDV-570071 | L3 Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2018-12-04 | 2019-05-03 | 90 | AWSC | AWSC | DF /F /70/DFFA-ESDV-570071 | L3 Prepare rigging equipment | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400293991 | ILI-PIGGING-RECEIVING_P3004_12"_DFB-TEE | PRODUCTION_PIG-RECEIVING | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2023-06-18 | 2023-09-06 | 10 | AWSC | AWSC | DF /B /23/DFBY-PL-673004 | PRODUCTION_PIG-RECEIVING | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400293991 | ILI-PIGGING-RECEIVING_P3004_12"_DFB-TEE | PRODUCTION_PIG-RECEIVING | AWSC | AWSC | 96 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-07 | 2023-06-18 | 2023-09-06 | 20 | AWSC | AWSC | DF /B /23/DFBY-PL-673004 | PRODUCTION_PIG-RECEIVING | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 10 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 20 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-01 | 2024-07-02 | 2021-10-31 | 2022-03-30 | 30 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-02 | 2024-07-02 | 2021-10-31 | 2022-03-30 | 40 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-02 | 2024-07-03 | 2021-10-31 | 2022-03-30 | 50 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-03 | 2024-07-03 | 2021-10-31 | 2022-03-30 | 60 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-03 | 2024-07-03 | 2021-10-31 | 2022-03-30 | 70 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-03 | 2024-07-04 | 2021-10-31 | 2022-03-30 | 80 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-04 | 2024-07-04 | 2021-10-31 | 2022-03-30 | 90 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-04 | 2024-07-04 | 2021-10-31 | 2022-03-30 | 100 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-04 | 2024-07-05 | 2021-10-31 | 2022-03-30 | 110 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2021-10-31 | 2022-03-30 | 120 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053475 | Replace defect lightings DFD flarebridge | Replace Lighting 1810-77-L1E |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-05 | 2024-07-05 | 2024-07-05 | 2021-10-31 | 2022-03-30 | 130 |  |  | DF /B /62 | Replace Lighting 1810-77-L1E | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2020-12-07 | 2021-05-06 | 10 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2020-12-07 | 2021-05-06 | 11 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2020-12-07 | 2021-05-06 | 20 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 18 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 30 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 40 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 50 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 60 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 70 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 80 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 90 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-12-07 | 2021-05-06 | 100 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038735 | DFG/78: Corroded rope guards whip winch | Replace aux winch rope guards |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2020-12-07 | 2021-05-06 | 110 |  |  | DF /G /78/DFGA-A-6140 | Replace aux winch rope guards | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400281428 | 3M SMOKE CABINS AIR FILT.REPLACE -DFC/G | SMOKE CABINS AIR FILT.REPLACE -DFC/G |  |  | 4 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2023-09-27 | 2023-10-12 | 10 |  |  | DF /C /82/DFCC-A-1332 | SMOKE CABINS AIR FILT.REPLACE -DFC/G | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096122 | MCB found defect | Isolate Drawer |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-16 | 2024-01-29 | 20 |  |  | DF /F /61/DFFA-N-1801B-10 | Isolate Drawer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096122 | MCB found defect | Isolate Drawer |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-16 | 2024-01-29 | 30 |  |  | DF /F /61/DFFA-N-1801B-10 | Isolate Drawer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096122 | MCB found defect | Isolate Drawer |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-16 | 2024-01-29 | 40 |  |  | DF /F /61/DFFA-N-1801B-10 | Isolate Drawer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096122 | MCB found defect | Isolate Drawer |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-16 | 2024-01-29 | 50 |  |  | DF /F /61/DFFA-N-1801B-10 | Isolate Drawer | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100111614 | MIRQ 3590 water mist (reserve bank) | MIRQ 3590 water mist (reserve bank) |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-16 | 2024-09-28 | 10 |  |  | DF /G /01/DFGA-WIT-043318B | MIRQ 3590 water mist (reserve bank) | Unknown
3 | DFE-OIL | WDF | MTN-INST | MTN-INST | 2100101414 | DFE-01 PT30025 Malfunktion | Isolate replace and calibrate PT |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-12-17 | 2024-04-30 | 10 |  |  | DF /E /55/DFEZ-PT-30025 | Isolate replace and calibrate PT | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235307 | 1Y ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2023-02-17 | 2023-03-19 | 10 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235307 | 1Y ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-02-17 | 2023-03-19 | 20 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235307 | 1Y ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2023-02-17 | 2023-03-19 | 30 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400235307 | 1Y ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-02-17 | 2023-03-19 | 40 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235307 | 1Y ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-02-17 | 2023-03-19 | 50 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049170 | FLMR Corroded steps | Corroded steps | SECE | SECE | 0 | 0 | Empty | 2021-05-09 | 2021-05-11 | 2021-05-09 | 2021-05-09 | 2021-05-09 | 2021-06-18 | 10 | SECE | SECE | DF /C /86/22000 - STAIRS | Corroded steps | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049170 | FLMR Corroded steps | Corroded steps | SECE | SECE | 3 | 3 | Empty | 2021-05-09 | 2021-05-11 | 2021-05-09 | 2021-05-09 | 2021-05-09 | 2021-06-18 | 20 | SECE | SECE | DF /C /86/22000 - STAIRS | Corroded steps | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049170 | FLMR Corroded steps | Corroded steps | SECE | SECE | 1 | 3 | Empty | 2021-05-09 | 2021-05-11 | 2021-05-09 | 2021-05-09 | 2021-05-09 | 2021-06-18 | 30 | SECE | SECE | DF /C /86/22000 - STAIRS | Corroded steps | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049170 | FLMR Corroded steps | Corroded steps | SECE | SECE | 30 | 30 | Empty | 2021-05-09 | 2021-05-11 | 2021-05-09 | 2021-05-11 | 2021-05-09 | 2021-06-18 | 40 | SECE | SECE | DF /C /86/22000 - STAIRS | Corroded steps | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337272 | 6M AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | AUX. SW LIFT PUMP MAINT-DFCM-P-5304 |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-29 | 2024-08-17 | 10 |  |  | DF /C /50/DFCM-P-5304 | AUX. SW LIFT PUMP MAINT-DFCM-P-5304 | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-07-15 | 2024-07-15 | 2020-11-08 | 2021-04-07 | 9 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-07-15 | 2024-07-15 | 2020-11-08 | 2021-04-07 | 10 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 50 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-07-15 | 2024-07-21 | 2020-11-08 | 2021-04-07 | 20 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-07-21 | 2024-07-22 | 2020-11-08 | 2021-04-07 | 30 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 50 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-07-22 | 2024-07-28 | 2020-11-08 | 2021-04-07 | 40 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 50 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-07-28 | 2024-08-04 | 2020-11-08 | 2021-04-07 | 45 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-08-04 | 2024-08-04 | 2020-11-08 | 2021-04-07 | 50 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-04 | 2024-10-04 | 2020-11-08 | 2021-04-07 | 60 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-04 | 2024-10-04 | 2020-11-08 | 2021-04-07 | 70 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 50 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-04 | 2024-10-10 | 2020-11-08 | 2021-04-07 | 80 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 50 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-10 | 2024-10-17 | 2020-11-08 | 2021-04-07 | 90 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-17 | 2024-10-17 | 2020-11-08 | 2021-04-07 | 100 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 50 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-17 | 2024-10-24 | 2020-11-08 | 2021-04-07 | 110 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-24 | 2024-10-24 | 2020-11-08 | 2021-04-07 | 120 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 8 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-24 | 2024-10-25 | 2020-11-08 | 2021-04-07 | 130 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036670 | DFCI/78: change out main winch f. overha | De-isolate Crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2020-11-08 | 2021-04-07 | 140 |  |  | DF /C /78/DFCI-X-6101 | De-isolate Crane | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400344341 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-16 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 26 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-09-29 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-16 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100040993 | DFFA-V-3402 PVI Contingency valves | DFFA-V-3402 PVI Contingency valves |  |  | 0 | 0 | Empty | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2021-01-04 | 10 |  |  | DF /F /20/DFFA-V-3402 | DFFA-V-3402 PVI Contingency valves | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100040993 | DFFA-V-3402 PVI Contingency valves | DFFA-V-3402 PVI Contingency valves |  |  | 0 | 0 | Empty | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2021-01-04 | 20 |  |  | DF /F /20/DFFA-V-3402 | DFFA-V-3402 PVI Contingency valves | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 12 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-13 | 2023-02-14 | 2021-12-23 | 2022-05-22 | 10 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ROPE | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-14 | 2023-02-14 | 2021-12-23 | 2022-05-22 | 20 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 3 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-14 | 2023-02-14 | 2021-12-23 | 2022-05-22 | 30 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ROPE | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 24 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-14 | 2023-02-17 | 2021-12-23 | 2022-05-22 | 40 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ROPE | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 24 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-14 | 2023-02-17 | 2021-12-23 | 2022-05-22 | 50 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 3 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-17 | 2023-02-17 | 2021-12-23 | 2022-05-22 | 60 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ROPE | 2100056268 | XCV-380605 intern læk | Replace valve - MPM |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-18 | 2023-02-18 | 2021-12-23 | 2022-05-22 | 70 |  |  | DF /F /54/DFFA-XCV-380605 | Replace valve - MPM | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046907 | Checkventil ved DFFA-HCV-500224 Intern l | De-Isolate/Test DFFA-HCV-500224 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-05-30 | 2021-10-27 | 10 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | De-Isolate/Test DFFA-HCV-500224 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046907 | Checkventil ved DFFA-HCV-500224 Intern l | De-Isolate/Test DFFA-HCV-500224 |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-05-30 | 2021-10-27 | 20 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | De-Isolate/Test DFFA-HCV-500224 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046907 | Checkventil ved DFFA-HCV-500224 Intern l | De-Isolate/Test DFFA-HCV-500224 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-05-30 | 2021-10-27 | 30 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | De-Isolate/Test DFFA-HCV-500224 | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052623 | ANOP Leak on line DFG-2"-WS-530135-AM-T | Setup/de-rig rope eq. | PCNF | PCNF | 0 | 0 | Empty | 2021-08-04 | 2021-08-14 | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-11-02 | 10 | PCNF | PCNF | DF /G /85/DFG-2-WS-053-0135-AM-T | Setup/de-rig rope eq. | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052623 | ANOP Leak on line DFG-2"-WS-530135-AM-T | Setup/de-rig rope eq. | PCNF | PCNF | 4 | 4 | Empty | 2021-08-04 | 2021-08-14 | 2021-08-04 | 2021-08-05 | 2021-08-04 | 2021-11-02 | 20 | PCNF | PCNF | DF /G /85/DFG-2-WS-053-0135-AM-T | Setup/de-rig rope eq. | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052623 | ANOP Leak on line DFG-2"-WS-530135-AM-T | Setup/de-rig rope eq. | PCNF | PCNF | 8 | 8 | Empty | 2021-08-04 | 2021-08-14 | 2021-08-05 | 2021-08-07 | 2021-08-04 | 2021-11-02 | 30 | PCNF | PCNF | DF /G /85/DFG-2-WS-053-0135-AM-T | Setup/de-rig rope eq. | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052623 | ANOP Leak on line DFG-2"-WS-530135-AM-T | Setup/de-rig rope eq. | PCNF | PCNF | 8 | 8 | Empty | 2021-08-04 | 2021-08-14 | 2021-08-07 | 2021-08-09 | 2021-08-04 | 2021-11-02 | 40 | PCNF | PCNF | DF /G /85/DFG-2-WS-053-0135-AM-T | Setup/de-rig rope eq. | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052623 | ANOP Leak on line DFG-2"-WS-530135-AM-T | Setup/de-rig rope eq. | PCNF | PCNF | 18 | 18 | Empty | 2021-08-04 | 2021-08-14 | 2021-08-09 | 2021-08-14 | 2021-08-04 | 2021-11-02 | 50 | PCNF | PCNF | DF /G /85/DFG-2-WS-053-0135-AM-T | Setup/de-rig rope eq. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100093624 | DFC Closed drain vessel LT-50744 | De-isolation and calib check |  |  | 0.5 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-08-05 | 2023-12-18 | 10 |  |  | DF /C /28/DFCI-LT-50744 | De-isolation and calib check | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100093624 | DFC Closed drain vessel LT-50744 | De-isolation and calib check |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-08-05 | 2023-12-18 | 20 |  |  | DF /C /28/DFCI-LT-50744 | De-isolation and calib check | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100093624 | DFC Closed drain vessel LT-50744 | De-isolation and calib check |  |  | 1.5 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-08-05 | 2023-12-18 | 30 |  |  | DF /C /28/DFCI-LT-50744 | De-isolation and calib check | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085208 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2023-03-27 | 2023-08-09 | 10 |  |  | DF /F /05/DFFA-DP-1813 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085208 | Battery fault on emergency light | Change batteries |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-03-27 | 2023-08-09 | 20 |  |  | DF /F /05/DFFA-DP-1813 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100085208 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-03-27 | 2023-08-09 | 30 |  |  | DF /F /05/DFFA-DP-1813 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085208 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2023-03-27 | 2023-08-09 | 40 |  |  | DF /F /05/DFFA-DP-1813 | Change batteries | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200015929 | 1 stk Access Point til DAF | 1 stk Access Point til DAF |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-10-02 | 2023-11-16 | 10 |  |  | DF /C /08 | 1 stk Access Point til DAF | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341925 | DFG_1Y_FLARE INT STRUCT INSP - GVI | DFG_1Y_FLARE INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/FLARE TOWER | DFG_1Y_FLARE INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100095435 | Establishment of earthing ball points | Establishment of earthing ball points |  |  | 10 | 0 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2023-09-07 | 2024-01-20 | 10 |  |  | DF /C /61/DFCI-N-1801 | Establishment of earthing ball points | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023910 | 1Y CHEMICAL INJECTION LEVEL 2 Nord | Isolate P-3906 |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-17 | 2019-10-31 | 2020-03-29 | 20 |  |  | DF /F /75 | Isolate P-3906 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023910 | 1Y CHEMICAL INJECTION LEVEL 2 Nord | Isolate P-3906 |  |  | 40 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-17 | 2024-09-22 | 2019-10-31 | 2020-03-29 | 30 |  |  | DF /F /75 | Isolate P-3906 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023910 | 1Y CHEMICAL INJECTION LEVEL 2 Nord | Isolate P-3906 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2019-10-31 | 2020-03-29 | 40 |  |  | DF /F /75 | Isolate P-3906 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 2 | 2 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-06 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 10 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-13 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 20 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-14 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 25 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 4 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-14 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 30 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 8 | 8 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-07 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 40 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 2 | 2 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-08 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 50 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-13 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 60 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 2 | 2 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-09 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 70 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-05-22 | 2021-06-11 | 80 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-05-22 | 2021-06-11 | 90 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-05-22 | 2021-06-11 | 95 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 8 | W49-50 | 2024-07-29 | 2024-08-01 | 2021-12-15 | 2021-12-15 | 2021-05-22 | 2021-06-11 | 100 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 8 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-05-22 | 2021-06-11 | 110 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 4 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2021-05-22 | 2021-06-11 | 120 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 3 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2021-05-22 | 2021-06-11 | 130 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 1 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2021-05-22 | 2021-06-11 | 140 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 0 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-05-22 | 2021-06-11 | 150 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 0 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-05-22 | 2021-06-11 | 160 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050194 | Defective Hydaulic accumulator in FP3101 | Prod prepare permit/isolations | PCNF | PCNF | 0 | 0 | W49-50 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-05-22 | 2021-06-11 | 170 | PCNF | PCNF | DF /F /07/DFFA-V-3101F | Prod prepare permit/isolations | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-03 | 2022-03-28 | 2022-11-23 | 10 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-03 | 2022-03-28 | 2022-11-23 | 20 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-RIGG | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 24 | 24 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-04 | 2024-07-06 | 2022-03-28 | 2022-11-23 | 30 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 5 | 4 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-07 | 2024-07-08 | 2022-03-28 | 2022-11-23 | 40 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 0 | 4 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-08 | 2024-07-08 | 2022-03-28 | 2022-11-23 | 50 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-RIGG | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 12 | 16 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-08 | 2024-07-09 | 2022-03-28 | 2022-11-23 | 60 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-09 | 2024-07-10 | 2022-03-28 | 2022-11-23 | 70 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 5 | 4 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-10 | 2024-07-11 | 2022-03-28 | 2022-11-23 | 80 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-11 | 2024-07-12 | 2022-03-28 | 2022-11-23 | 90 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-ELEC | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-12 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 100 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-LAGG | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 110 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 0 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 120 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008920 | Exchange DFFA-PSV-351034 - PSV 2023 | DFFA-PSV-351034 Offshore from WS Måde | SCH | SCH | 0 | 4 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 130 | SCH | SCH | DF /F /54/DFFA-PSV-351034 | DFFA-PSV-351034 Offshore from WS Måde | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 0 | 0 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 10 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 0 | 0 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 20 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-SCAF | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 0 | 81 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 30 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PIPF | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 96 | 88 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 40 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-ROPE | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 0 | 229 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 50 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PIPF | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 16 | 0 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 60 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-SCAF | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 0 | 0 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 70 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100056163 | DGSPR: Utility & Instrument Air Batch-01 | Instrument air spools SCFM 8T corrosion | PCNF | PCNF | 0 | 0 | Empty | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2021-12-14 | 2022-05-13 | 80 | PCNF | PCNF | DF /A /07/DFA-1-AI-054-0606-AG-U | Instrument air spools SCFM 8T corrosion | Unknown
3 | DFA-W13 | WDF | MTN-INST | PRODTECH | 2100073336 | Replace ZT on DFA-13 choke | SD well/Inhibit Position Measurement Dev |  |  | 1 | 0 | W49-50 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-12 | 2023-01-25 | 10 |  |  | DF /A /55/DFAA-ZT-30301 | SD well/Inhibit Position Measurement Dev | Unknown
3 | DFA-W13 | WDF | MTN-INST | MTN-INST | 2100073336 | Replace ZT on DFA-13 choke | SD well/Inhibit Position Measurement Dev |  |  | 2 | 0 | W49-50 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-12 | 2023-01-25 | 20 |  |  | DF /A /55/DFAA-ZT-30301 | SD well/Inhibit Position Measurement Dev | Unknown
3 | DFA-W13 | WDF | MTN-INST | MTN-INST | 2100073336 | Replace ZT on DFA-13 choke | SD well/Inhibit Position Measurement Dev |  |  | 2 | 0 | W49-50 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-12 | 2023-01-25 | 30 |  |  | DF /A /55/DFAA-ZT-30301 | SD well/Inhibit Position Measurement Dev | Unknown
3 | DFA-W13 | WDF | MTN-INST | MTN-INST | 2100073336 | Replace ZT on DFA-13 choke | SD well/Inhibit Position Measurement Dev |  |  | 2 | 0 | W49-50 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-12 | 2023-01-25 | 40 |  |  | DF /A /55/DFAA-ZT-30301 | SD well/Inhibit Position Measurement Dev | Unknown
3 | DFA-W13 | WDF | MTN-INST | PRODTECH | 2100073336 | Replace ZT on DFA-13 choke | SD well/Inhibit Position Measurement Dev |  |  | 1 | 0 | W49-50 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-12 | 2023-01-25 | 50 |  |  | DF /A /55/DFAA-ZT-30301 | SD well/Inhibit Position Measurement Dev | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 13 | 13 | Empty | 2024-01-08 | 2024-01-09 | 2019-09-10 | 2020-08-24 | 2018-12-27 | 2019-03-27 | 10 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 0.6999999999999999555910790147 | 0 | Empty | 2024-01-08 | 2024-01-09 | 2019-09-14 | 2020-08-24 | 2018-12-27 | 2019-03-27 | 20 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 15 | 26.5 | Empty | 2024-01-08 | 2024-01-09 | 2019-09-10 | 2021-02-14 | 2018-12-27 | 2019-03-27 | 30 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 1 | 0 | Empty | 2024-01-08 | 2024-01-09 | 2024-01-08 | 2024-01-08 | 2018-12-27 | 2019-03-27 | 40 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 6.700000000000000177635683938 | 0 | Empty | 2024-01-08 | 2024-01-09 | 2020-08-24 | 2020-12-13 | 2018-12-27 | 2019-03-27 | 50 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-09 | 2024-01-08 | 2024-01-09 | 2018-12-27 | 2019-03-27 | 60 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-09 | 2024-01-08 | 2024-01-09 | 2018-12-27 | 2019-03-27 | 70 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003061 | Scaff Assist to Force 13236 | BUILD SCAFFOLDING | PCNF | PCNF | 6 | 0 | Empty | 2024-01-08 | 2024-01-09 | 2024-01-08 | 2024-01-09 | 2018-12-27 | 2019-03-27 | 80 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7061-GF-U | BUILD SCAFFOLDING | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-20 | 2024-06-21 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-21 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 12 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-27 | 2024-06-28 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-28 | 2024-06-29 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-29 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-30 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-06-30 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284229 | PSV Calibration - DFBA-PSV-38185 | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 10 | 0 | W25-W26 | 2024-06-20 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /11/DFBA-PSV-38185 | Scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094024 | Skuffe 1820 tripper ved brug af WO-1822 | Skuffe 1820 tripper ved brug af WO-1822 |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-13 | 2023-12-26 | 10 |  |  | DF /G /61/DFGA-N-1842A-AR06-FA001 | Skuffe 1820 tripper ved brug af WO-1822 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000785 | DK46 SCAFF MATERIAL ORDER 2019 | DK46 SCAFF MATERIAL ORDER 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-01-01 | 2019-12-31 | 10 |  |  | DF /F | DK46 SCAFF MATERIAL ORDER 2019 | Unknown
A | DFG-FUEL | WPM | MTN-MECH | PRODTECH | 2400222493 | 1Y SDV LUBE/FUNC TEST FUEL GAS - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-01-02 | 2023-02-01 | 10 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFG-FUEL | WPM | MTN-MECH | MTN-MECH | 2400222493 | 1Y SDV LUBE/FUNC TEST FUEL GAS - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-02 | 2023-02-01 | 20 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFG-FUEL | WPM | MTN-MECH | PRODTECH | 2400222493 | 1Y SDV LUBE/FUNC TEST FUEL GAS - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-02 | 2023-02-01 | 30 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DAB-OIL | WPM | MTN-MECH | PRODTECH | 2400325545 | 1Y ESDV LEAK TEST-DFFA-ESDV-380201 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-11-17 | 2024-11-18 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2024-12-17 | 10 | AWSCSECE | AWSCSECE | DF /F /23/DFFA-ESDV-380201 | ISOLATION BY PRODUCTION | Unknown
A | DAB-OIL | WPM | MTN-MECH | PRODTECH | 2400325545 | 1Y ESDV LEAK TEST-DFFA-ESDV-380201 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-11-17 | 2024-11-18 | 2024-11-17 | 2024-11-18 | 2024-11-17 | 2024-12-17 | 20 | AWSCSECE | AWSCSECE | DF /F /23/DFFA-ESDV-380201 | ISOLATION BY PRODUCTION | Unknown
A | DAB-OIL | WPM | MTN-MECH | PRODTECH | 2400325545 | 1Y ESDV LEAK TEST-DFFA-ESDV-380201 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-11-17 | 2024-11-18 | 2024-11-18 | 2024-11-18 | 2024-11-17 | 2024-12-17 | 30 | AWSCSECE | AWSCSECE | DF /F /23/DFFA-ESDV-380201 | ISOLATION BY PRODUCTION | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100086255 | FIRE DAMPER FD-12333 åbner ikke | FIRE DAMPER FD-12333 åbner ikke | PCNFSCHSECE | PCNFSCHSECE | 24 | 28 | W21-W22 | 2024-05-20 | 2024-05-20 | 2023-06-19 | 2023-12-28 | 2023-02-21 | 2023-04-07 | 5 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12333 | FIRE DAMPER FD-12333 åbner ikke | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086255 | FIRE DAMPER FD-12333 åbner ikke | FIRE DAMPER FD-12333 åbner ikke | PCNFSCHSECE | PCNFSCHSECE | 0 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-02-21 | 2023-04-07 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12333 | FIRE DAMPER FD-12333 åbner ikke | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086255 | FIRE DAMPER FD-12333 åbner ikke | FIRE DAMPER FD-12333 åbner ikke | PCNFSCHSECE | PCNFSCHSECE | 24 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-02-21 | 2023-04-07 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12333 | FIRE DAMPER FD-12333 åbner ikke | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100086255 | FIRE DAMPER FD-12333 åbner ikke | FIRE DAMPER FD-12333 åbner ikke | PCNFSCHSECE | PCNFSCHSECE | 6 | 9 | W21-W22 | 2024-05-20 | 2024-05-20 | 2023-06-27 | 2023-12-28 | 2023-02-21 | 2023-04-07 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12333 | FIRE DAMPER FD-12333 åbner ikke | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100086255 | FIRE DAMPER FD-12333 åbner ikke | FIRE DAMPER FD-12333 åbner ikke | PCNFSCHSECE | PCNFSCHSECE | 0 | 16 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-02-21 | 2023-04-07 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12333 | FIRE DAMPER FD-12333 åbner ikke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 20 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-06 | 2023-10-19 | 2024-03-02 | 10 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-13 | 2023-10-19 | 2024-03-02 | 20 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-14 | 2023-10-19 | 2024-03-02 | 30 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 6 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-14 | 2024-07-15 | 2023-10-19 | 2024-03-02 | 40 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 8 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 50 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 2 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 60 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 70 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 10 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-10-19 | 2024-03-02 | 80 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097602 | LB4 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 0 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-05 | 2023-10-19 | 2024-03-02 | 90 | AWSC | AWSC | DF /C /02/DFCI-X-0704 | Denso tape to cover greased thread | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100107143 | S 41010 defekt filterhus på V-4101 | Replace Filter House |  |  | 3 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2024-02-04 | 2024-03-20 | 10 |  |  | DF /F /30/DFFA-S-41010 | Replace Filter House | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100107143 | S 41010 defekt filterhus på V-4101 | Replace Filter House |  |  | 3 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2024-02-04 | 2024-03-20 | 20 |  |  | DF /F /30/DFFA-S-41010 | Replace Filter House | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100107143 | S 41010 defekt filterhus på V-4101 | Replace Filter House |  |  | 3 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2024-02-04 | 2024-03-20 | 30 |  |  | DF /F /30/DFFA-S-41010 | Replace Filter House | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400337268 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 2 | 0 | Empty | 2024-07-08 | 2024-07-25 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-08-13 | 10 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337268 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 47.5 | 0 | Empty | 2024-07-08 | 2024-07-25 | 2024-07-08 | 2024-07-20 | 2024-07-08 | 2024-08-13 | 20 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337268 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 20 | 0 | Empty | 2024-07-08 | 2024-07-25 | 2024-07-20 | 2024-07-25 | 2024-07-08 | 2024-08-13 | 30 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400337268 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 2 | 0 | Empty | 2024-07-08 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-08 | 2024-08-13 | 40 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2022-10-25 | 2022-10-25 | 2020-07-14 | 2020-08-23 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | VEN-MECH | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2022-10-25 | 2022-10-25 | 2020-07-14 | 2020-08-23 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | VEN-MECH | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2022-10-25 | 2022-10-25 | 2020-07-14 | 2020-08-23 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | VEN-MECH | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 20 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | PRODTECH | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-LAGG | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 10 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-RIGG | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-RIGG | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 150 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-RIGG | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 160 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 170 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-RIGG | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 180 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-LAGG | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 16 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2020-07-14 | 2020-08-23 | 190 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
3 | DFG-1640 | WDF | MTN-TURB | PRODTECH | 2100034402 | Leak in exhaust inside generator room | Nytech: Insulation on the muffler bottom | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W45-46 IOP | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-03 | 2020-07-14 | 2020-08-23 | 200 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /60/DFGA-A-1640 | Nytech: Insulation on the muffler bottom | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339213 | DFE_1Y_FIRE AND BLAST-WALLS INSP | DFE_1Y_FIRE AND BLAST-WALLS INSP | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /02/FIRE AND BLAST-WALLS | DFE_1Y_FIRE AND BLAST-WALLS INSP | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322298 | DFG-27-DOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-21 | 2024-06-24 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-24 | 2024-06-25 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 16 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-26 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-27 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-28 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-28 | 2024-06-29 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284265 | PSV Calibration - DFFA-PSV-340122 | De-isolation and leak test | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /20/DFFA-PSV-340122 | De-isolation and leak test | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400307847 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-2 | ATEX EQUIPMENT INSPECTION | PCNFAWSCSECE | PCNFAWSCSECE | 32 | 8 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-01-06 | 2024-03-08 | 10 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /63/ATEX-EARTH-AREA-2 | ATEX EQUIPMENT INSPECTION | Unknown
B | DFG-IPHP | WPM | MTN-TURB | MTN-TURB | 2400344184 | 4000H COMPRESSOR SKID, COUNTER | DATA & OIL SAMPLING AND GREASING | AWSC | AWSC | 20 | 0 | Empty | 2024-12-01 | 2024-12-05 | 2024-12-01 | 2024-12-05 | 2024-09-06 | 2024-09-22 | 10 | AWSC | AWSC | DF /G /31/DFGA-A-4302 | DATA & OIL SAMPLING AND GREASING | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400329531 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-23 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 32 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-04-19 | 2024-06-20 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-23 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100060719 | DFF-29 Downhole Scale inj FCV faulty | Replace DFFA-FCV-390063 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-01-09 | 2022-02-18 | 10 |  |  | DF /F /75/DFFA-FCV-390063 | Replace DFFA-FCV-390063 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060719 | DFF-29 Downhole Scale inj FCV faulty | Replace DFFA-FCV-390063 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-01-09 | 2022-02-18 | 20 |  |  | DF /F /75/DFFA-FCV-390063 | Replace DFFA-FCV-390063 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100060719 | DFF-29 Downhole Scale inj FCV faulty | Replace DFFA-FCV-390063 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-01-09 | 2022-02-18 | 30 |  |  | DF /F /75/DFFA-FCV-390063 | Replace DFFA-FCV-390063 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322224 | DFA-75-CB-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-17 | 2024-05-22 | 2024-07-06 | 10 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 2 | 2 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-17 | 2024-05-22 | 2024-07-06 | 20 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 12 | 39 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-20 | 2024-05-22 | 2024-07-06 | 30 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 2 | 2 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-21 | 2024-05-22 | 2024-07-06 | 40 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 1 | 10 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-05-22 | 2024-07-06 | 50 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-05-22 | 2024-07-06 | 60 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-05-22 | 2024-07-06 | 70 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100113253 | DFFA-C-1202 Freon leak on Hot gas line | DFFA-C-1202 Freon leak on Hot gas line | SCH | SCH | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-21 | 2024-06-21 | 2024-05-22 | 2024-07-06 | 80 | SCH | SCH | DF /F /09/DFFA-C-1202 | DFFA-C-1202 Freon leak on Hot gas line | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339140 | DFD_1Y_FLARE INT STRUCT INSP - GVI | DFD_1Y_FLARE INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /D /86/FLARE TOWER | DFD_1Y_FLARE INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2019-02-06 | 2019-05-07 | 10 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-16 | 2019-02-06 | 2019-05-07 | 20 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-17 | 2019-02-06 | 2019-05-07 | 30 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-17 | 2019-02-06 | 2019-05-07 | 40 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-18 | 2019-02-06 | 2019-05-07 | 50 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-18 | 2019-02-06 | 2019-05-07 | 60 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-19 | 2019-02-06 | 2019-05-07 | 70 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-20 | 2019-02-06 | 2019-05-07 | 80 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-20 | 2024-09-21 | 2019-02-06 | 2019-05-07 | 90 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-21 | 2019-02-06 | 2019-05-07 | 100 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 9 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-23 | 2019-02-06 | 2019-05-07 | 110 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2019-02-06 | 2019-05-07 | 120 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2019-02-06 | 2019-05-07 | 130 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025324 | Changeout PM-3956 + A<(>&<)>B pumps | L3 Isolate PM-3956 + A&B pumps |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2019-02-06 | 2019-05-07 | 140 |  |  | DF /F /75/DFFA-A-3954 | L3 Isolate PM-3956 + A&B pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025113 | Fabricate consol and fasten DFFA-XCV-301 | L3 Fabricate consol and fasten DFFA-XCV- |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2019-04-17 | 2019-07-16 | 10 |  |  | DF /F /10/DFFA-XCV-301313 | L3 Fabricate consol and fasten DFFA-XCV- | Unknown
2 | DFG-SW | WDF | MTN-PIPF | VEN-MECH | 2100100579 | SYNPR: Replacement of spool on 2" Nozzle | Build scaffolding lifting frame | PCNF | PCNF | 0 | 0 | Empty | 2023-10-25 | 2023-10-30 | 2023-10-25 | 2023-10-25 | 2023-10-25 | 2023-12-09 | 10 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0050-AM-U | Build scaffolding lifting frame | Unknown
2 | DFG-SW | WDF | MTN-PIPF | MTN-SCAF | 2100100579 | SYNPR: Replacement of spool on 2" Nozzle | Build scaffolding lifting frame | PCNF | PCNF | 16 | 16 | Empty | 2023-10-25 | 2023-10-30 | 2023-10-25 | 2023-10-27 | 2023-10-25 | 2023-12-09 | 20 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0050-AM-U | Build scaffolding lifting frame | Unknown
2 | DFG-SW | WDF | MTN-PIPF | MTN-RIGG | 2100100579 | SYNPR: Replacement of spool on 2" Nozzle | Build scaffolding lifting frame | PCNF | PCNF | 8 | 8 | Empty | 2023-10-25 | 2023-10-30 | 2023-10-27 | 2023-10-28 | 2023-10-25 | 2023-12-09 | 30 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0050-AM-U | Build scaffolding lifting frame | Unknown
2 | DFG-SW | WDF | MTN-PIPF | MTN-RIGG | 2100100579 | SYNPR: Replacement of spool on 2" Nozzle | Build scaffolding lifting frame | PCNF | PCNF | 8 | 8 | Empty | 2023-10-25 | 2023-10-30 | 2023-10-28 | 2023-10-29 | 2023-10-25 | 2023-12-09 | 40 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0050-AM-U | Build scaffolding lifting frame | Unknown
2 | DFG-SW | WDF | MTN-PIPF | MTN-SCAF | 2100100579 | SYNPR: Replacement of spool on 2" Nozzle | Build scaffolding lifting frame | PCNF | PCNF | 8 | 8 | Empty | 2023-10-25 | 2023-10-30 | 2023-10-29 | 2023-10-30 | 2023-10-25 | 2023-12-09 | 50 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0050-AM-U | Build scaffolding lifting frame | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064120 | FLM SYNSR-667006 DFF - Replacement of ha | DFF - Replacement of handrails EL +18000 |  |  | 0 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2022-05-23 | 2022-10-20 | 10 |  |  | DF /F /86/22000 - HANDRAILS | DFF - Replacement of handrails EL +18000 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064120 | FLM SYNSR-667006 DFF - Replacement of ha | DFF - Replacement of handrails EL +18000 |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2022-05-23 | 2022-10-20 | 20 |  |  | DF /F /86/22000 - HANDRAILS | DFF - Replacement of handrails EL +18000 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064120 | FLM SYNSR-667006 DFF - Replacement of ha | DFF - Replacement of handrails EL +18000 |  |  | 0 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2022-05-23 | 2022-10-20 | 30 |  |  | DF /F /86/22000 - HANDRAILS | DFF - Replacement of handrails EL +18000 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064120 | FLM SYNSR-667006 DFF - Replacement of ha | DFF - Replacement of handrails EL +18000 |  |  | 0 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2022-05-23 | 2022-10-20 | 40 |  |  | DF /F /86/22000 - HANDRAILS | DFF - Replacement of handrails EL +18000 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400215375 | 6M HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-11-04 | 2022-11-20 | 10 |  |  | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400215375 | 6M HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-11-04 | 2022-11-20 | 20 |  |  | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400215375 | 6M HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-11-04 | 2022-11-20 | 30 |  |  | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-21 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-21 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 10 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-28 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-28 | 2024-06-29 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284264 | PSV Calibration - DFFA-PSV-340320 | Isolation of PSV | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /11/DFFA-PSV-340320 | Isolation of PSV | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009358 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /F /31/DFF-16-GPS-043-7003-DB-P | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009358 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-08 | 2024-01-10 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /F /31/DFF-16-GPS-043-7003-DB-P | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009358 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 20 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-11 | 2024-01-13 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /F /31/DFF-16-GPS-043-7003-DB-P | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009358 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 72 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-13 | 2024-01-16 | 2022-02-08 | 2022-07-08 | 35 |  |  | DF /F /31/DFF-16-GPS-043-7003-DB-P | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009358 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 37 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-16 | 2024-01-20 | 2022-02-08 | 2022-07-08 | 37 |  |  | DF /F /31/DFF-16-GPS-043-7003-DB-P | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009358 | sandblasting assists FORCE 19755 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-20 | 2024-01-22 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /F /31/DFF-16-GPS-043-7003-DB-P | Bilfinger inspection | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322241 | DFB-55-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 7 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /55/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 10 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 20 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 30 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 40 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 50 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 60 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 70 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 80 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
3 | DFF-1620 | WDF | MTN-MECH | MTN-MECH | 2100100865 | Carry out FM on Corroded Actuator Body | Isolate Hydraulics | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-12-13 | 2024-04-26 | 90 | SECE | SECE | DF /F /60/DFFA-BDV-570052 | Isolate Hydraulics | Unknown
4 | NOSD | WGN | MTN-TELE | MTN-TELE | 2200006005 | General IT - DAF Telecom | General IT - DAF Telecom | PCNFSCH | PCNFSCH | 200 | 320 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2021-06-08 | 2022-04-04 | 10 | PCNFSCH | PCNFSCH | DF /C /08 | General IT - DAF Telecom | Unknown
A | NOSD | WPM | MTN-INST | VEN-INST | 2400292177 | 3Y DFFA-V-3403 WCM- METERING (VENDOR) | DFFA-V-3403 WCM- METERING (VENDOR) | AWSCSECE | AWSCSECE | 13 | 0 | Empty | 2024-06-22 | 2024-06-28 | 2024-06-22 | 2024-06-23 | 2023-10-22 | 2023-12-23 | 10 | AWSCSECE | AWSCSECE | DF /F /11/METERING | DFFA-V-3403 WCM- METERING (VENDOR) | Unknown
A | NOSD | WPM | MTN-INST | MTN-INST | 2400292177 | 3Y DFFA-V-3403 WCM- METERING (VENDOR) | DFFA-V-3403 WCM- METERING (VENDOR) | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-06-22 | 2024-06-28 | 2024-06-23 | 2024-06-24 | 2023-10-22 | 2023-12-23 | 20 | AWSCSECE | AWSCSECE | DF /F /11/METERING | DFFA-V-3403 WCM- METERING (VENDOR) | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400292177 | 3Y DFFA-V-3403 WCM- METERING (VENDOR) | DFFA-V-3403 WCM- METERING (VENDOR) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-06-22 | 2024-06-28 | 2024-06-24 | 2024-06-25 | 2023-10-22 | 2023-12-23 | 30 | AWSCSECE | AWSCSECE | DF /F /11/METERING | DFFA-V-3403 WCM- METERING (VENDOR) | Unknown
A | NOSD | WPM | MTN-INST | MTN-RIGG | 2400292177 | 3Y DFFA-V-3403 WCM- METERING (VENDOR) | DFFA-V-3403 WCM- METERING (VENDOR) | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-06-22 | 2024-06-28 | 2024-06-25 | 2024-06-26 | 2023-10-22 | 2023-12-23 | 40 | AWSCSECE | AWSCSECE | DF /F /11/METERING | DFFA-V-3403 WCM- METERING (VENDOR) | Unknown
A | NOSD | WPM | MTN-INST | MTN-MECH | 2400292177 | 3Y DFFA-V-3403 WCM- METERING (VENDOR) | DFFA-V-3403 WCM- METERING (VENDOR) | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-06-22 | 2024-06-28 | 2024-06-26 | 2024-06-28 | 2023-10-22 | 2023-12-23 | 50 | AWSCSECE | AWSCSECE | DF /F /11/METERING | DFFA-V-3403 WCM- METERING (VENDOR) | Unknown
A | NOSD | WPM | MTN-INST | MTN-ELEC | 2400292177 | 3Y DFFA-V-3403 WCM- METERING (VENDOR) | DFFA-V-3403 WCM- METERING (VENDOR) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-06-22 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2023-10-22 | 2023-12-23 | 60 | AWSCSECE | AWSCSECE | DF /F /11/METERING | DFFA-V-3403 WCM- METERING (VENDOR) | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400302334 | 1Y PRIME MOVER DFFA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-06-10 | 2024-06-17 | 2024-06-10 | 2024-06-10 | 2024-03-30 | 2024-04-29 | 10 | AWSC | AWSC | DF /F /78/DFFA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400302334 | 1Y PRIME MOVER DFFA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 31 | 0 | Empty | 2024-06-10 | 2024-06-17 | 2024-06-10 | 2024-06-14 | 2024-03-30 | 2024-04-29 | 20 | AWSC | AWSC | DF /F /78/DFFA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400302334 | 1Y PRIME MOVER DFFA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 8 | 0 | Empty | 2024-06-10 | 2024-06-17 | 2024-06-14 | 2024-06-16 | 2024-03-30 | 2024-04-29 | 40 | AWSC | AWSC | DF /F /78/DFFA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400302334 | 1Y PRIME MOVER DFFA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-06-10 | 2024-06-17 | 2024-06-16 | 2024-06-16 | 2024-03-30 | 2024-04-29 | 50 | AWSC | AWSC | DF /F /78/DFFA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400302334 | 1Y PRIME MOVER DFFA-MD-6102 | ISOLATION BY PRODUCTION | AWSC | AWSC | 4 | 0 | Empty | 2024-06-10 | 2024-06-17 | 2024-06-16 | 2024-06-17 | 2024-03-30 | 2024-04-29 | 60 | AWSC | AWSC | DF /F /78/DFFA-MD-6102 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286628 | 1Y WATER MIST SKID MAINT-DFGA-A-0462 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-20 | 2024-05-21 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /G /01/DFGA-A-0462 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286628 | 1Y WATER MIST SKID MAINT-DFGA-A-0462 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-21 | 2024-05-23 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /G /01/DFGA-A-0462 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286628 | 1Y WATER MIST SKID MAINT-DFGA-A-0462 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-23 | 2024-05-25 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /G /01/DFGA-A-0462 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286628 | 1Y WATER MIST SKID MAINT-DFGA-A-0462 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-25 | 2024-05-26 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /G /01/DFGA-A-0462 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286628 | 1Y WATER MIST SKID MAINT-DFGA-A-0462 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-26 | 2024-05-26 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /G /01/DFGA-A-0462 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286628 | 1Y WATER MIST SKID MAINT-DFGA-A-0462 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-26 | 2024-05-27 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /G /01/DFGA-A-0462 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343947 | 6M SW FILTER - DFCM-FT-5213/23 | SW FILTER - DFCM-FT-5213/23 |  |  | 2 | 0 | Empty | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-27 | 10 |  |  | DF /C /51/DFCM-FT-5213 | SW FILTER - DFCM-FT-5213/23 | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100024044 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | AWSC | AWSC | 18 | 0 | OIM FW INL | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-05 | 2018-12-09 | 2019-03-09 | 15 | AWSC | AWSC | DF /F /01/DFFA-HCV-035242 | L3 firewatch on | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100024044 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | AWSC | AWSC | 4 | 0 | OIM FW INL | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-06 | 2018-12-09 | 2019-03-09 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-035242 | L3 firewatch on | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100024044 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | AWSC | AWSC | 10 | 0 | OIM FW INL | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2025-01-07 | 2018-12-09 | 2019-03-09 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-035242 | L3 firewatch on | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100024044 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | AWSC | AWSC | 4 | 0 | OIM FW INL | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-08 | 2018-12-09 | 2019-03-09 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-035242 | L3 firewatch on | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100024044 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | AWSC | AWSC | 1 | 0 | OIM FW INL | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-08 | 2018-12-09 | 2019-03-09 | 45 | AWSC | AWSC | DF /F /01/DFFA-HCV-035242 | L3 firewatch on | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100024044 | CMAT:Change DFFA-HCV-035242 Deluge Defek | L3 firewatch on | AWSC | AWSC | 2 | 0 | OIM FW INL | 2025-01-01 | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2018-12-09 | 2019-03-09 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-035242 | L3 firewatch on | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-06 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 160 | 212 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-06 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 48 | 20 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-17 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | PRODTECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 12 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-17 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 160 | 72 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-17 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 50 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-17 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 60 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 0 | 31 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-17 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 70 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 40 | 48 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-06-18 | 2024-07-04 | 2024-06-06 | 2024-06-21 | 80 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 72 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-09-10 | 2024-09-18 | 2024-06-06 | 2024-06-21 | 90 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 8 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-09-18 | 2024-09-20 | 2024-06-06 | 2024-06-21 | 95 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 40 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-09-20 | 2024-09-30 | 2024-06-06 | 2024-06-21 | 96 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 80 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-09-30 | 2024-10-20 | 2024-06-06 | 2024-06-21 | 97 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 216 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-10-20 | 2024-12-13 | 2024-06-06 | 2024-06-21 | 98 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 144 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-12-13 | 2024-12-28 | 2024-06-06 | 2024-06-21 | 100 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 72 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2024-12-28 | 2025-01-05 | 2024-06-06 | 2024-06-21 | 110 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | PRODTECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 2 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2025-01-05 | 2025-01-05 | 2024-06-06 | 2024-06-21 | 120 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
1 | NOSD | WDF | MTN-MECH | PRODTECH | 2100113991 | DFG Emg.fire pump P-0351 pump defect. | Rigging assistance and Gallow | PCNFSCHSECE | PCNFSCHSECE | 6 | 0 | W25-W26 | 2024-09-10 | 2025-01-07 | 2025-01-05 | 2025-01-07 | 2024-06-06 | 2024-06-21 | 130 | PCNFSCHSECE | PCNFSCHSECE | DF /G /01/DFGA-A-0351 | Rigging assistance and Gallow | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100078868 | Koblings afskræmning defekt på pm-5038 | Isolate DFCM-PM-5038 |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-05-30 | 2025-11-15 | 10 |  |  | DF /C /27/DFCM-PM-5038 | Isolate DFCM-PM-5038 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078868 | Koblings afskræmning defekt på pm-5038 | Isolate DFCM-PM-5038 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-05-30 | 2025-11-15 | 20 |  |  | DF /C /27/DFCM-PM-5038 | Isolate DFCM-PM-5038 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100078868 | Koblings afskræmning defekt på pm-5038 | Isolate DFCM-PM-5038 |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-05-30 | 2025-11-15 | 40 |  |  | DF /C /27/DFCM-PM-5038 | Isolate DFCM-PM-5038 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078868 | Koblings afskræmning defekt på pm-5038 | Isolate DFCM-PM-5038 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-05-30 | 2025-11-15 | 50 |  |  | DF /C /27/DFCM-PM-5038 | Isolate DFCM-PM-5038 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104209 | DFGA-LB-06108 Buoy damaged replace | DFGA-LB-06108 Buoy damaged replace |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-10 | 2024-06-24 | 10 |  |  | DF /G /02/DFGA-LB-06108 | DFGA-LB-06108 Buoy damaged replace | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344041 | 6M LIFE-SAVING AND SAFETY EQ MAINT - DFF | LIFE-SAVING AND SAFETY EQ INSP - DFF | SECE | SECE | 7 | 0 | Empty | 2024-09-08 | 2024-09-09 | 2024-09-08 | 2024-09-09 | 2024-09-08 | 2024-09-24 | 10 | SECE | SECE | DF /F /02/LIFE-SAVING-EQUIPMENT | LIFE-SAVING AND SAFETY EQ INSP - DFF | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200015746 | Galley watertap is defective, replace. | Galley watertap is defective, replace. |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-01 | 2024-03-15 | 10 |  |  | DF /C /82/CATERING-EQUIPMENT | Galley watertap is defective, replace. | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200015746 | Galley watertap is defective, replace. | Galley watertap is defective, replace. |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-01 | 2024-03-15 | 20 |  |  | DF /C /82/CATERING-EQUIPMENT | Galley watertap is defective, replace. | Unknown
A | DFF-1620 | WPM | MTN-TURB | PRODTECH | 2400334412 | 8KH BDV/SDV MAINT, COUNTER-A-1620 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-06-10 | 2024-06-12 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-07-10 | 10 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-MECH | 2400334412 | 8KH BDV/SDV MAINT, COUNTER-A-1620 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-06-10 | 2024-06-12 | 2024-06-10 | 2024-06-11 | 2024-06-10 | 2024-07-10 | 20 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1620 | WPM | MTN-TURB | PRODTECH | 2400334412 | 8KH BDV/SDV MAINT, COUNTER-A-1620 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-06-10 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-10 | 2024-07-10 | 30 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1620 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100042101 | Remote seal for LIT-410444 blocked | Inhibit before isolation / Isolate |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-12-09 | 2021-01-18 | 97 |  |  | DF /G /30/DFGA-LIT-410444 | Inhibit before isolation / Isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042101 | Remote seal for LIT-410444 blocked | Inhibit before isolation / Isolate |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-12-09 | 2021-01-18 | 98 |  |  | DF /G /30/DFGA-LIT-410444 | Inhibit before isolation / Isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042101 | Remote seal for LIT-410444 blocked | Inhibit before isolation / Isolate |  |  | 3.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-12-09 | 2021-01-18 | 100 |  |  | DF /G /30/DFGA-LIT-410444 | Inhibit before isolation / Isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042101 | Remote seal for LIT-410444 blocked | Inhibit before isolation / Isolate |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-12-09 | 2021-01-18 | 199 |  |  | DF /G /30/DFGA-LIT-410444 | Inhibit before isolation / Isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042101 | Remote seal for LIT-410444 blocked | Inhibit before isolation / Isolate |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-12-09 | 2021-01-18 | 400 |  |  | DF /G /30/DFGA-LIT-410444 | Inhibit before isolation / Isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100042101 | Remote seal for LIT-410444 blocked | Inhibit before isolation / Isolate |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-12-09 | 2021-01-18 | 402 |  |  | DF /G /30/DFGA-LIT-410444 | Inhibit before isolation / Isolate | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 6 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-11 | 2023-12-12 | 2020-10-15 | 2020-11-24 | 20 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 12 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-12 | 2023-12-14 | 2020-10-15 | 2020-11-24 | 30 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 6 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-12 | 2023-12-14 | 2020-10-15 | 2020-11-24 | 40 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 40 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-14 | 2023-12-19 | 2020-10-15 | 2020-11-24 | 50 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 6 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-19 | 2023-12-20 | 2020-10-15 | 2020-11-24 | 60 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 12 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-19 | 2023-12-20 | 2020-10-15 | 2020-11-24 | 70 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038940 | DFG Sand Cyclone V-5061 replace liners | Isolate Sand Cyclone V-5061 |  |  | 6 | 0 | Duplicate of PPM | 2023-12-11 | 2023-12-22 | 2023-12-20 | 2023-12-22 | 2020-10-15 | 2020-11-24 | 80 |  |  | DF /G /27/DFGA-V-5061 | Isolate Sand Cyclone V-5061 | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003164 | CMAT:DFF Replace manomerers in ESDV-4100 | Safing manometers |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2018-04-27 | 2019-04-22 | 10 |  |  | DF /F /30/DFFA-ESDV-410033 | Safing manometers | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003164 | CMAT:DFF Replace manomerers in ESDV-4100 | Safing manometers |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2018-04-27 | 2019-04-22 | 20 |  |  | DF /F /30/DFFA-ESDV-410033 | Safing manometers | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003164 | CMAT:DFF Replace manomerers in ESDV-4100 | Safing manometers |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2018-04-27 | 2019-04-22 | 30 |  |  | DF /F /30/DFFA-ESDV-410033 | Safing manometers | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003164 | CMAT:DFF Replace manomerers in ESDV-4100 | Safing manometers |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2018-04-27 | 2019-04-22 | 40 |  |  | DF /F /30/DFFA-ESDV-410033 | Safing manometers | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100093860 | Air dryer DFF fault | Erect and dismantle scaffold |  |  | 1.5 | 2 | Empty | 2024-08-06 | 2024-08-06 | 2024-08-01 | 2024-08-06 | 2023-08-09 | 2023-12-22 | 10 |  |  | DF /F /07/DFFA-A-5401 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093860 | Air dryer DFF fault | Erect and dismantle scaffold |  |  | 4 | 24 | Empty | 2024-08-06 | 2024-08-06 | 2024-08-01 | 2024-08-06 | 2023-08-09 | 2023-12-22 | 20 |  |  | DF /F /07/DFFA-A-5401 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100093860 | Air dryer DFF fault | Erect and dismantle scaffold |  |  | 0 | 2 | Empty | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2023-08-09 | 2023-12-22 | 30 |  |  | DF /F /07/DFFA-A-5401 | Erect and dismantle scaffold | Unknown
3 | D-GASTYE | WDF | MTN-MECH | PRODTECH | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 6.5 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-01 | 2025-01-02 | 2019-05-31 | 2019-06-20 | 9 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-SCAF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-02 | 2025-01-03 | 2019-05-31 | 2019-06-20 | 10 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-PIPF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-02 | 2025-01-03 | 2019-05-31 | 2019-06-20 | 20 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-INST | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-02 | 2025-01-03 | 2019-05-31 | 2019-06-20 | 30 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-SCAF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-03 | 2025-01-05 | 2019-05-31 | 2019-06-20 | 40 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | PRODTECH | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-05 | 2025-01-06 | 2019-05-31 | 2019-06-20 | 50 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-PIPF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-06 | 2025-01-07 | 2019-05-31 | 2019-06-20 | 60 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-INST | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-06 | 2025-01-07 | 2019-05-31 | 2019-06-20 | 70 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-PIPF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-07 | 2025-01-07 | 2019-05-31 | 2019-06-20 | 80 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-INST | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-07 | 2025-01-08 | 2019-05-31 | 2019-06-20 | 90 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-PIPF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-07 | 2025-01-08 | 2019-05-31 | 2019-06-20 | 100 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-INST | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-07 | 2025-01-08 | 2019-05-31 | 2019-06-20 | 110 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-INST | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-08 | 2025-01-12 | 2019-05-31 | 2019-06-20 | 120 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | PRODTECH | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 6.5 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-12 | 2025-01-14 | 2019-05-31 | 2019-06-20 | 130 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | PRODTECH | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-14 | 2025-01-15 | 2019-05-31 | 2019-06-20 | 140 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
3 | D-GASTYE | WDF | MTN-MECH | MTN-SCAF | 2100022907 | PMAT:Valves internleaking Tyra EP-3805 3 | Permit Preparation - Inst | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-17 | 2025-01-15 | 2025-01-17 | 2019-05-31 | 2019-06-20 | 150 | AWSC | AWSC | DF /B /34/DFBA-EP-3805 | Permit Preparation - Inst | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009219 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /B /55/DFB-6-WI-035-9038-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009219 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 2 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /B /55/DFB-6-WI-035-9038-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009219 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /B /55/DFB-6-WI-035-9038-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009219 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 35 |  |  | DF /B /55/DFB-6-WI-035-9038-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009219 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-09 | 2024-01-10 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /B /55/DFB-6-WI-035-9038-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009219 | Insulation assist FORCE 16151 | Bilfinger inspection |  |  | 2 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-10 | 2024-01-10 | 2022-02-08 | 2022-07-08 | 50 |  |  | DF /B /55/DFB-6-WI-035-9038-FC-U | Bilfinger inspection | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235718 | 4Y 380V E-SWB MAINT DFCC-N-1813-04 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235718 | 4Y 380V E-SWB MAINT DFCC-N-1813-04 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 20 | 0 | W09-W10 | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235718 | 4Y 380V E-SWB MAINT DFCC-N-1813-04 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235718 | 4Y 380V E-SWB MAINT DFCC-N-1813-04 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018136 | Replace Transformer relay 1841-M112 | Exchange of protection relay |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M112-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018136 | Replace Transformer relay 1841-M112 | Exchange of protection relay |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M112-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018136 | Replace Transformer relay 1841-M112 | Exchange of protection relay |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M112-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018136 | Replace Transformer relay 1841-M112 | Exchange of protection relay |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M112-02 | Exchange of protection relay | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 20 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-06 | 2023-10-19 | 2024-03-02 | 10 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-13 | 2023-10-19 | 2024-03-02 | 20 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-14 | 2023-10-19 | 2024-03-02 | 30 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 6 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-14 | 2024-07-15 | 2023-10-19 | 2024-03-02 | 40 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 8 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 50 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 2 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 60 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 70 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 10 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-10-19 | 2024-03-02 | 80 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097601 | LB3 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 0 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-05 | 2023-10-19 | 2024-03-02 | 90 | AWSC | AWSC | DF /C /02/DFCI-X-0703 | Denso tape to cover greased thread | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269621 | 6M SW LIFT PUMP MAINT DFCM-P-5303 | SW LIFT PUMP MAINT DFCM-P-5303 |  |  | 2 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-08-08 | 2023-08-27 | 10 |  |  | DF /C /50/DFCM-P-5303 | SW LIFT PUMP MAINT DFCM-P-5303 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-INST | 2400308544 | 1Y 3KV N-SWB MAINT DFCI-N-1801-10 | 3KV N-SWB INSP DFCI-N-1801-10 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-02-07 | 2024-03-14 | 10 |  |  | DF /C /61/DFCI-N-1801-10-01 | 3KV N-SWB INSP DFCI-N-1801-10 | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235562 | 4Y 3KV N-SWB MAINT DFCI-N-1801-24 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-29 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801-24-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235562 | 4Y 3KV N-SWB MAINT DFCI-N-1801-24 | ISOLATION ELECTRICAL | AWSC | AWSC | 18 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2022-12-31 | 2023-03-29 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801-24-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235562 | 4Y 3KV N-SWB MAINT DFCI-N-1801-24 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801-24-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235562 | 4Y 3KV N-SWB MAINT DFCI-N-1801-24 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801-24-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235562 | 4Y 3KV N-SWB MAINT DFCI-N-1801-24 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 50 | AWSC | AWSC | DF /C /61/DFCI-N-1801-24-01 | ISOLATION ELECTRICAL | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100111336 | DFFA-HCV-380028 interna leaking | Production Isolation |  |  | 2 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-06-05 | 2024-10-18 | 10 |  |  | DF /F /54/DFFA-HCV-380028 | Production Isolation | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100111336 | DFFA-HCV-380028 interna leaking | Production Isolation |  |  | 4 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-06-05 | 2024-10-18 | 20 |  |  | DF /F /54/DFFA-HCV-380028 | Production Isolation | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100111336 | DFFA-HCV-380028 interna leaking | Production Isolation |  |  | 2 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-06-05 | 2024-10-18 | 30 |  |  | DF /F /54/DFFA-HCV-380028 | Production Isolation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022391 | Replacement of accumulator ACC-590419 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2019-09-12 | 2020-09-06 | 10 |  |  | DF /G /07/DFGA-ACC-590419 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022391 | Replacement of accumulator ACC-590419 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2019-09-12 | 2020-09-06 | 20 |  |  | DF /G /07/DFGA-ACC-590419 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022391 | Replacement of accumulator ACC-590419 | L3 Prepare rigging equipment |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2019-09-12 | 2020-09-06 | 30 |  |  | DF /G /07/DFGA-ACC-590419 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022391 | Replacement of accumulator ACC-590419 | L3 Prepare rigging equipment |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2019-09-12 | 2020-09-06 | 40 |  |  | DF /G /07/DFGA-ACC-590419 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022391 | Replacement of accumulator ACC-590419 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2019-09-12 | 2020-09-06 | 50 |  |  | DF /G /07/DFGA-ACC-590419 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022391 | Replacement of accumulator ACC-590419 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2019-09-12 | 2020-09-06 | 60 |  |  | DF /G /07/DFGA-ACC-590419 | L3 Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075986 | DFB/78: Light check and repair all over | Isolate/de-isolate of crane DFBA-X-6102 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-11-19 | 2023-04-03 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolate/de-isolate of crane DFBA-X-6102 | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100075986 | DFB/78: Light check and repair all over | Isolate/de-isolate of crane DFBA-X-6102 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2022-11-19 | 2023-04-03 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolate/de-isolate of crane DFBA-X-6102 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075986 | DFB/78: Light check and repair all over | Isolate/de-isolate of crane DFBA-X-6102 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2022-11-19 | 2023-04-03 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolate/de-isolate of crane DFBA-X-6102 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075986 | DFB/78: Light check and repair all over | Isolate/de-isolate of crane DFBA-X-6102 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2022-11-19 | 2023-04-03 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolate/de-isolate of crane DFBA-X-6102 | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-SCAF | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 48 | 23 | Empty | 2025-01-09 | 2025-01-13 | 2023-04-22 | 2023-04-30 | 2021-07-31 | 2021-10-29 | 10 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 10 | 10 | Empty | 2025-01-09 | 2025-01-13 | 2023-05-15 | 2023-06-26 | 2021-07-31 | 2021-10-29 | 20 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2025-01-09 | 2025-01-09 | 2021-07-31 | 2021-10-29 | 30 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2025-01-09 | 2025-01-10 | 2021-07-31 | 2021-10-29 | 40 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 14 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2023-05-17 | 2023-06-26 | 2021-07-31 | 2021-10-29 | 50 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2025-01-10 | 2025-01-11 | 2021-07-31 | 2021-10-29 | 60 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2025-01-11 | 2025-01-12 | 2021-07-31 | 2021-10-29 | 70 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2025-01-12 | 2025-01-13 | 2021-07-31 | 2021-10-29 | 80 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2021-07-31 | 2021-10-29 | 90 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-09 | 2025-01-13 | 2023-05-20 | 2023-06-26 | 2021-07-31 | 2021-10-29 | 100 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-SCAF | 2100052321 | DFCM-E-3660 inlet HCV-361402 seized in o | Prod prepare permit/isolation | PCNFAWSC | PCNFAWSC | 24 | 20 | Empty | 2025-01-09 | 2025-01-13 | 2023-05-21 | 2023-06-26 | 2021-07-31 | 2021-10-29 | 110 | PCNFAWSC | PCNFAWSC | DF /C /23/DFCM-HCV-361402 | Prod prepare permit/isolation | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235622 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235622 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235622 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235622 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-10 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-MECH | MTN-PAIN | 2400344070 | 1Y SLIDING DOORS DFA | SLIDING DOORS DF |  |  | 24 | 0 | Empty | 2024-08-08 | 2024-08-10 | 2024-08-08 | 2024-08-10 | 2024-08-08 | 2024-09-24 | 10 |  |  | DF /A /86 | SLIDING DOORS DF | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400352428 | 3M CRUDE OIL EXP. SKD MAINT-DFCM-A-3650 | CRUDE OIL EXPORT SKD MAINT-DFCM-A-3650 |  |  | 1 | 0 | Empty | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-21 | 10 |  |  | DF /C /23/DFCM-A-3650 | CRUDE OIL EXPORT SKD MAINT-DFCM-A-3650 | Unknown
4 | NE | WDF | MTN-INST | WELLSUPV | 2100055842 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air lines SCFM 8S corrosion |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-04 | 2024-07-26 | 2024-07-26 | 2021-12-12 | 2022-05-11 | 10 |  |  | DF /B /07/DFB-2-AI-054-0801-A1-U | Instrument air lines SCFM 8S corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-INST | 2100055842 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air lines SCFM 8S corrosion |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-04 | 2024-07-26 | 2024-07-26 | 2021-12-12 | 2022-05-11 | 20 |  |  | DF /B /07/DFB-2-AI-054-0801-A1-U | Instrument air lines SCFM 8S corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055842 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air lines SCFM 8S corrosion |  |  | 36 | 0 | Empty | 2024-07-26 | 2024-08-04 | 2024-07-26 | 2024-07-30 | 2021-12-12 | 2022-05-11 | 30 |  |  | DF /B /07/DFB-2-AI-054-0801-A1-U | Instrument air lines SCFM 8S corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-ROPE | 2100055842 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air lines SCFM 8S corrosion |  |  | 36 | 0 | Empty | 2024-07-26 | 2024-08-04 | 2024-07-30 | 2024-08-02 | 2021-12-12 | 2022-05-11 | 40 |  |  | DF /B /07/DFB-2-AI-054-0801-A1-U | Instrument air lines SCFM 8S corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055842 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air lines SCFM 8S corrosion |  |  | 18 | 0 | Empty | 2024-07-26 | 2024-08-04 | 2024-08-02 | 2024-08-04 | 2021-12-12 | 2022-05-11 | 50 |  |  | DF /B /07/DFB-2-AI-054-0801-A1-U | Instrument air lines SCFM 8S corrosion | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298223 | 4Y PRODUCED WAT PUMP MAINT-DFGA-P-3442/3 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-11-06 | 2024-01-18 | 10 | SECE | SECE | DF /G /27/DFGA-P-3442 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400298223 | 4Y PRODUCED WAT PUMP MAINT-DFGA-P-3442/3 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2023-11-06 | 2024-01-18 | 20 | SECE | SECE | DF /G /27/DFGA-P-3442 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298223 | 4Y PRODUCED WAT PUMP MAINT-DFGA-P-3442/3 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2023-11-06 | 2024-01-18 | 30 | SECE | SECE | DF /G /27/DFGA-P-3442 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298223 | 4Y PRODUCED WAT PUMP MAINT-DFGA-P-3442/3 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-11-06 | 2024-01-18 | 40 | SECE | SECE | DF /G /27/DFGA-P-3442 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298223 | 4Y PRODUCED WAT PUMP MAINT-DFGA-P-3442/3 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2023-11-06 | 2024-01-18 | 50 | SECE | SECE | DF /G /27/DFGA-P-3442 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 0 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-16 | 2023-01-16 | 2019-02-06 | 2019-05-07 | 10 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-16 | 2023-01-18 | 2019-02-06 | 2019-05-07 | 20 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-16 | 2023-01-18 | 2019-02-06 | 2019-05-07 | 30 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-18 | 2023-01-19 | 2019-02-06 | 2019-05-07 | 40 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-18 | 2023-01-19 | 2019-02-06 | 2019-05-07 | 50 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 4 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-19 | 2023-01-20 | 2019-02-06 | 2019-05-07 | 60 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-20 | 2023-01-21 | 2019-02-06 | 2019-05-07 | 70 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-20 | 2023-01-21 | 2019-02-06 | 2019-05-07 | 80 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 4 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-21 | 2023-01-22 | 2019-02-06 | 2019-05-07 | 90 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 4 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-22 | 2023-01-23 | 2019-02-06 | 2019-05-07 | 100 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-23 | 2023-01-25 | 2019-02-06 | 2019-05-07 | 110 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100027155 | DFC-XCV-50343 vil ikke lukke | DFC-XCV-50343 vil ikke lukke |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-01-16 | 2023-01-25 | 2023-01-23 | 2023-01-25 | 2019-02-06 | 2019-05-07 | 120 |  |  | DF /C /27/DFCM-XCV-50343 | DFC-XCV-50343 vil ikke lukke | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2015-12-14 | 2016-01-23 | 1 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2015-12-14 | 2016-01-23 | 2 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-03 | 2015-12-14 | 2016-01-23 | 10 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 9 | 1 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2015-12-14 | 2016-01-23 | 20 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-03 | 2015-12-14 | 2016-01-23 | 30 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-07 | 2015-12-14 | 2016-01-23 | 40 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-03 | 2015-12-14 | 2016-01-23 | 50 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-05 | 2015-12-14 | 2016-01-23 | 60 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-03 | 2015-12-14 | 2016-01-23 | 70 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-02 | 2015-12-14 | 2016-01-23 | 80 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | WELLSUPV | 2100023810 | DFF-23 OIL HCV opstrøms Manif. XCVs | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2015-12-14 | 2016-01-23 | 90 | PCNFAWSC | PCNFAWSC | DF /F /10 | Prepare Permits Scaff | Unknown
3 | DFG-IPHP | WDF | MTN-TELE | MTN-TELE | 2100106040 | DFG-GD-133240 to be replaced | DFG-GD-133240 to be replaced | SECE | SECE | 4 | 4 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-03-07 | 2024-07-20 | 10 | SECE | SECE | DF /G /03/DFGA-GD-133240 | DFG-GD-133240 to be replaced | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039645 | DFF 3602 Crudeoil cooler XCV-360087 stuc | Order new gear box | PCNF | PCNF | 0 | 7 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-28 | 2020-12-07 | 10 | PCNF | PCNF | DF /F /21/DFFA-HCV-360087 | Order new gear box | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039645 | DFF 3602 Crudeoil cooler XCV-360087 stuc | Order new gear box | PCNF | PCNF | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-28 | 2020-12-07 | 20 | PCNF | PCNF | DF /F /21/DFFA-HCV-360087 | Order new gear box | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232978 | 4Y 3KV N-SWB-MAINT-DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232978 | 4Y 3KV N-SWB-MAINT-DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | AWSC | AWSC | 21 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-18 | 2022-12-01 | 2023-02-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232978 | 4Y 3KV N-SWB-MAINT-DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | AWSC | AWSC | 5 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-18 | 2022-12-01 | 2023-02-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232978 | 4Y 3KV N-SWB-MAINT-DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-12-01 | 2023-02-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400232978 | 4Y 3KV N-SWB-MAINT-DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | AWSC | AWSC | 6 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-21 | 2022-12-01 | 2023-02-27 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801 | 3KV N-SWB-INSP-DFFA-N-1801 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400244000 | 6M WELL CONT PANEL MAINT - DFFA-FP-3102 | WELL CONT PANEL MAINT - DFFA-FP-3102 | SCH | SCH | 4 | 0 | W21-W22 | 2024-05-28 | 2024-05-29 | 2024-05-28 | 2024-05-29 | 2023-04-18 | 2023-05-04 | 10 | SCH | SCH | DF /F /07/DFFA-FP-3102 | WELL CONT PANEL MAINT - DFFA-FP-3102 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286621 | 1Y HI-FOG SKID MAINT-DFCI-A-0400 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 3 | 3 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-15 | 2024-07-16 | 2023-10-16 | 2023-11-15 | 10 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286621 | 1Y HI-FOG SKID MAINT-DFCI-A-0400 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 10 | 10 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-16 | 2024-07-18 | 2023-10-16 | 2023-11-15 | 20 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286621 | 1Y HI-FOG SKID MAINT-DFCI-A-0400 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 6 | 11 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-18 | 2024-07-20 | 2023-10-16 | 2023-11-15 | 30 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286621 | 1Y HI-FOG SKID MAINT-DFCI-A-0400 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 7 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-20 | 2024-07-21 | 2023-10-16 | 2023-11-15 | 40 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286621 | 1Y HI-FOG SKID MAINT-DFCI-A-0400 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 2 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-21 | 2024-07-21 | 2023-10-16 | 2023-11-15 | 50 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286621 | 1Y HI-FOG SKID MAINT-DFCI-A-0400 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 3 | 3 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-21 | 2024-07-22 | 2023-10-16 | 2023-11-15 | 60 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100047709 | TE-431125A shows wrong temperature | Inhibit before isolation | AWSCSCH | AWSCSCH | 0.5 | 0 | W25-W26 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2021-03-27 | 2021-04-16 | 97 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-TE-431125A | Inhibit before isolation | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100047709 | TE-431125A shows wrong temperature | Inhibit before isolation | AWSCSCH | AWSCSCH | 1 | 0 | W25-W26 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2021-03-27 | 2021-04-16 | 98 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-TE-431125A | Inhibit before isolation | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100047709 | TE-431125A shows wrong temperature | Inhibit before isolation | AWSCSCH | AWSCSCH | 2 | 0 | W25-W26 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2021-03-27 | 2021-04-16 | 101 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-TE-431125A | Inhibit before isolation | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100047709 | TE-431125A shows wrong temperature | Inhibit before isolation | AWSCSCH | AWSCSCH | 1 | 0 | W25-W26 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2021-03-27 | 2021-04-16 | 199 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-TE-431125A | Inhibit before isolation | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-INST | 2100047709 | TE-431125A shows wrong temperature | Inhibit before isolation | AWSCSCH | AWSCSCH | 1 | 0 | W25-W26 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2021-03-27 | 2021-04-16 | 400 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-TE-431125A | Inhibit before isolation | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | PRODTECH | 2100047709 | TE-431125A shows wrong temperature | Inhibit before isolation | AWSCSCH | AWSCSCH | 0.5 | 0 | W25-W26 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2021-03-27 | 2021-04-16 | 402 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-TE-431125A | Inhibit before isolation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 10 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 20 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 30 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 2.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 40 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 2.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 50 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 60 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 70 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084665 | Load cell for DFF T-3914 water clarifier | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-19 | 2023-08-01 | 80 |  |  | DF /F /75/DFFA-WE-390552A | Empty tank and isolate | Unknown
3 | DFE-O04 | WDF | MTN-INST | MTN-INST | 2100053134 | intern leak in Block PT-30040 | Isolate and deisolate transmitter | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2021-08-22 | 2021-11-20 | 10 | AWSC | AWSC | DF /E /10/DFEZ-PT-30040 | Isolate and deisolate transmitter | Unknown
3 | DFE-O04 | WDF | MTN-INST | PRODTECH | 2100053134 | intern leak in Block PT-30040 | Isolate and deisolate transmitter | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2021-08-22 | 2021-11-20 | 20 | AWSC | AWSC | DF /E /10/DFEZ-PT-30040 | Isolate and deisolate transmitter | Unknown
3 | DFE-O04 | WDF | MTN-INST | MTN-INST | 2100053134 | intern leak in Block PT-30040 | Isolate and deisolate transmitter | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2021-08-22 | 2021-11-20 | 30 | AWSC | AWSC | DF /E /10/DFEZ-PT-30040 | Isolate and deisolate transmitter | Unknown
4 | NOSD | WGN | WELLSUPV | PRODTECH | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 10 | 14 | W27 IOP | 2023-02-13 | 2023-02-23 | 2021-07-05 | 2021-07-11 | 2021-02-10 | 2021-07-10 | 11 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | MTN-ROUS | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 16 | 14 | W27 IOP | 2023-02-13 | 2023-02-23 | 2021-07-05 | 2021-07-19 | 2021-02-10 | 2021-07-10 | 20 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | MTN-SCAF | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 16 | 14 | W27 IOP | 2023-02-13 | 2023-02-23 | 2021-07-06 | 2021-07-19 | 2021-02-10 | 2021-07-10 | 21 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | WELLSUPV | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 48 | 0 | W27 IOP | 2023-02-13 | 2023-02-23 | 2023-02-13 | 2023-02-15 | 2021-02-10 | 2021-07-10 | 31 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | VEN-SUBS | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 48 | 0 | W27 IOP | 2023-02-13 | 2023-02-23 | 2023-02-13 | 2023-02-15 | 2021-02-10 | 2021-07-10 | 41 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | VEN-SUBS | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 192 | 0 | W27 IOP | 2023-02-13 | 2023-02-23 | 2023-02-15 | 2023-02-20 | 2021-02-10 | 2021-07-10 | 51 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | WELLSUPV | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 96 | 0 | W27 IOP | 2023-02-13 | 2023-02-23 | 2023-02-15 | 2023-02-20 | 2021-02-10 | 2021-07-10 | 61 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WGN | WELLSUPV | WELLSUPV | 2200005839 | DAN F Flush Regnar pipeline | Rig-up equipment for WS/OTS | PCNF | PCNF | 48 | 0 | W27 IOP | 2023-02-13 | 2023-02-23 | 2023-02-20 | 2023-02-23 | 2021-02-10 | 2021-07-10 | 71 | PCNF | PCNF | DF /A /12/RISERS-PIPELINES | Rig-up equipment for WS/OTS | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079684 | Stuck HCV (shaker Tool) on Both Waterout | Try shakertool to loosen HCV-500058 |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-06-05 | 2025-11-21 | 10 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | Try shakertool to loosen HCV-500058 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079684 | Stuck HCV (shaker Tool) on Both Waterout | Try shakertool to loosen HCV-500058 |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-06-05 | 2025-11-21 | 20 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | Try shakertool to loosen HCV-500058 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079684 | Stuck HCV (shaker Tool) on Both Waterout | Try shakertool to loosen HCV-500058 |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-06-05 | 2025-11-21 | 30 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | Try shakertool to loosen HCV-500058 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022683 | CMAT:Exchange of calibration pot FG-3960 | L3 Isolation equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2019-05-08 | 2019-08-06 | 10 |  |  | DF /E /75/DFEZ-FG-39600 | L3 Isolation equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022683 | CMAT:Exchange of calibration pot FG-3960 | L3 Isolation equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2019-05-08 | 2019-08-06 | 20 |  |  | DF /E /75/DFEZ-FG-39600 | L3 Isolation equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022683 | CMAT:Exchange of calibration pot FG-3960 | L3 Isolation equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2019-05-08 | 2019-08-06 | 30 |  |  | DF /E /75/DFEZ-FG-39600 | L3 Isolation equipment | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076711 | DFE/78:Troubeshoot telescopic function | Build/demol of scaffold - see attached | PCNFSCH | PCNFSCH | 4 | 2 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-12-05 | 2023-04-19 | 10 | PCNFSCH | PCNFSCH | DF /E /78/DFEZ-X-6150 | Build/demol of scaffold - see attached | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076711 | DFE/78:Troubeshoot telescopic function | Build/demol of scaffold - see attached | PCNFSCH | PCNFSCH | 20 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-12-05 | 2023-04-19 | 20 | PCNFSCH | PCNFSCH | DF /E /78/DFEZ-X-6150 | Build/demol of scaffold - see attached | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076711 | DFE/78:Troubeshoot telescopic function | Build/demol of scaffold - see attached | PCNFSCH | PCNFSCH | 3 | 38 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-12-05 | 2023-04-19 | 30 | PCNFSCH | PCNFSCH | DF /E /78/DFEZ-X-6150 | Build/demol of scaffold - see attached | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076711 | DFE/78:Troubeshoot telescopic function | Build/demol of scaffold - see attached | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-12-05 | 2023-04-19 | 40 | PCNFSCH | PCNFSCH | DF /E /78/DFEZ-X-6150 | Build/demol of scaffold - see attached | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100076711 | DFE/78:Troubeshoot telescopic function | Build/demol of scaffold - see attached | PCNFSCH | PCNFSCH | 5 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-12-05 | 2023-04-19 | 50 | PCNFSCH | PCNFSCH | DF /E /78/DFEZ-X-6150 | Build/demol of scaffold - see attached | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-20 | 2022-06-03 | 2022-09-01 | 10 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-19 | 2022-06-03 | 2022-09-01 | 20 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-18 | 2024-09-19 | 2022-06-03 | 2022-09-01 | 30 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 14 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-20 | 2024-09-23 | 2022-06-03 | 2022-09-01 | 40 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-23 | 2024-09-25 | 2022-06-03 | 2022-09-01 | 50 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-25 | 2024-09-27 | 2022-06-03 | 2022-09-01 | 60 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2022-06-03 | 2022-09-01 | 70 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100067911 | HCV-340005-U Internal leaking | Prepare matr/tools |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-09-30 | 2024-09-28 | 2024-09-30 | 2022-06-03 | 2022-09-01 | 80 |  |  | DF /F /10/DFFA-HCV-340005-U | Prepare matr/tools | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235579 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-07-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235579 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-07 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-07-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235579 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-07 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-07-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235579 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-07-02 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 60 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-07 | 2021-03-05 | 2021-03-10 | 10 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 11 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-02 | 2021-03-05 | 2021-03-10 | 20 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 12 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-02 | 2021-03-05 | 2021-03-10 | 30 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 8 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-01 | 2021-03-05 | 2021-03-10 | 40 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 48 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-06 | 2021-03-05 | 2021-03-10 | 50 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 7 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-01 | 2021-03-05 | 2021-03-10 | 60 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 5 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-01 | 2021-03-05 | 2021-03-10 | 70 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 5 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-01 | 2021-03-05 | 2021-03-10 | 80 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 24 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-03 | 2021-03-05 | 2021-03-10 | 90 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 28 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-03 | 2021-03-05 | 2021-03-10 | 100 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 5 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-01 | 2021-03-05 | 2021-03-10 | 110 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 24 | 5 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-02 | 2021-03-05 | 2021-03-10 | 120 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002699 | DAF OCG NPT, 003-01 / TMP312 | Meals & breaks | PCNF | PCNF | 0 | 0 | Empty | 2022-04-01 | 2022-04-07 | 2022-04-01 | 2022-04-01 | 2021-03-05 | 2021-03-10 | 130 | PCNF | PCNF | DF /E | Meals & breaks | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100076855 | DFF Test flow meter Demul out of range | Calibrate Mas flowmeter, Corioli Flowmet |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-12-09 | 2023-04-23 | 10 |  |  | DF /F /75/DFFA-FIT-390518 | Calibrate Mas flowmeter, Corioli Flowmet | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076855 | DFF Test flow meter Demul out of range | Calibrate Mas flowmeter, Corioli Flowmet |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-12-09 | 2023-04-23 | 20 |  |  | DF /F /75/DFFA-FIT-390518 | Calibrate Mas flowmeter, Corioli Flowmet | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100076855 | DFF Test flow meter Demul out of range | Calibrate Mas flowmeter, Corioli Flowmet |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-12-09 | 2023-04-23 | 30 |  |  | DF /F /75/DFFA-FIT-390518 | Calibrate Mas flowmeter, Corioli Flowmet | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009356 | sandblasting assists FORCE 15634 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /B /31/DFB-10-PH-038-0855-C2-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009356 | sandblasting assists FORCE 15634 | Bilfinger inspection |  |  | 33 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /B /31/DFB-10-PH-038-0855-C2-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009356 | sandblasting assists FORCE 15634 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-10 | 2022-02-08 | 2022-07-08 | 22 |  |  | DF /B /31/DFB-10-PH-038-0855-C2-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009356 | sandblasting assists FORCE 15634 | Bilfinger inspection |  |  | 30 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-10 | 2024-01-11 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /B /31/DFB-10-PH-038-0855-C2-U | Bilfinger inspection | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300007898 | DK40 - CONSUMABLE PROD - DECK | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2027-01-31 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308559 | 1Y BDV LUBE/FUNC TEST - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | W21-W22 | 2024-05-20 | 2024-06-02 | 2024-05-20 | 2024-05-22 | 2024-02-14 | 2024-03-15 | 10 | SECE | SECE | DF /C /27/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308559 | 1Y BDV LUBE/FUNC TEST - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 34 | 0 | W21-W22 | 2024-05-20 | 2024-06-02 | 2024-05-22 | 2024-05-31 | 2024-02-14 | 2024-03-15 | 20 | SECE | SECE | DF /C /27/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308559 | 1Y BDV LUBE/FUNC TEST - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | W21-W22 | 2024-05-20 | 2024-06-02 | 2024-05-31 | 2024-06-02 | 2024-02-14 | 2024-03-15 | 30 | SECE | SECE | DF /C /27/BDV | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235847 | 4Y 400V E-SWB MAINT DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235847 | 4Y 400V E-SWB MAINT DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235847 | 4Y 400V E-SWB MAINT DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235847 | 4Y 400V E-SWB MAINT DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A10 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100067307 | DFGA/78: Disconnect cam switch for onsho | Isolate/de-isolate trolley DFGA-X-6135B |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-09-16 | 2024-07-15 | 2024-07-16 | 2022-05-10 | 2022-06-19 | 10 |  |  | DF /G /78/DFGA-X-6135B | Isolate/de-isolate trolley DFGA-X-6135B | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100067307 | DFGA/78: Disconnect cam switch for onsho | Isolate/de-isolate trolley DFGA-X-6135B |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-09-16 | 2024-07-16 | 2024-07-17 | 2022-05-10 | 2022-06-19 | 20 |  |  | DF /G /78/DFGA-X-6135B | Isolate/de-isolate trolley DFGA-X-6135B | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100067307 | DFGA/78: Disconnect cam switch for onsho | Isolate/de-isolate trolley DFGA-X-6135B |  |  | 8 | 0 | W29-W30 | 2024-07-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-05-10 | 2022-06-19 | 40 |  |  | DF /G /78/DFGA-X-6135B | Isolate/de-isolate trolley DFGA-X-6135B | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100067307 | DFGA/78: Disconnect cam switch for onsho | Isolate/de-isolate trolley DFGA-X-6135B |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-05-10 | 2022-06-19 | 50 |  |  | DF /G /78/DFGA-X-6135B | Isolate/de-isolate trolley DFGA-X-6135B | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100067307 | DFGA/78: Disconnect cam switch for onsho | Isolate/de-isolate trolley DFGA-X-6135B |  |  | 0 | 0 | W29-W30 | 2024-07-15 | 2024-09-16 | 2024-07-15 | 2024-07-15 | 2022-05-10 | 2022-06-19 | 60 |  |  | DF /G /78/DFGA-X-6135B | Isolate/de-isolate trolley DFGA-X-6135B | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235588 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1830-05B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235588 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1830-05B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235588 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1830-05B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235588 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1830-05B1 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 0 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-03-15 | 2024-04-15 | 2021-12-31 | 2022-03-31 | 10 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 6 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-03-15 | 2024-04-15 | 2021-12-31 | 2022-03-31 | 20 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 3 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-03-15 | 2024-04-15 | 2021-12-31 | 2022-03-31 | 30 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 6 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-03-15 | 2024-04-15 | 2021-12-31 | 2022-03-31 | 40 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 6 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-03-16 | 2024-04-15 | 2021-12-31 | 2022-03-31 | 50 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 8 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-04-15 | 2024-04-16 | 2021-12-31 | 2022-03-31 | 60 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 6 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-04-16 | 2024-04-17 | 2021-12-31 | 2022-03-31 | 70 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 2 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-04-17 | 2024-04-17 | 2021-12-31 | 2022-03-31 | 80 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 4 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-04-17 | 2024-04-17 | 2021-12-31 | 2022-03-31 | 90 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100059741 | FLM DFB-DFA Bridge - Replace gratings Up | Remove grating firehydrant | PCNF | PCNF | 4 | 0 | Empty | 2024-04-15 | 2024-04-18 | 2024-04-17 | 2024-04-18 | 2021-12-31 | 2022-03-31 | 100 | PCNF | PCNF | DF /B /86/BRIDGE-DFB-DFA | Remove grating firehydrant | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059734 | 3" valve external leaking | Replace 3" valve |  |  | 36 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-18 | 2021-12-23 | 2022-02-01 | 10 |  |  | DF /C /51 | Replace 3" valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059734 | 3" valve external leaking | Replace 3" valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2021-12-23 | 2022-02-01 | 20 |  |  | DF /C /51 | Replace 3" valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059734 | 3" valve external leaking | Replace 3" valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2021-12-23 | 2022-02-01 | 30 |  |  | DF /C /51 | Replace 3" valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059734 | 3" valve external leaking | Replace 3" valve |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-19 | 2021-12-23 | 2022-02-01 | 40 |  |  | DF /C /51 | Replace 3" valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059734 | 3" valve external leaking | Replace 3" valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2021-12-23 | 2022-02-01 | 50 |  |  | DF /C /51 | Replace 3" valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059734 | 3" valve external leaking | Replace 3" valve |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-22 | 2021-12-23 | 2022-02-01 | 60 |  |  | DF /C /51 | Replace 3" valve | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200004579 | Fireguard assistance for Force | Fireguard for Force X-ray | PCNF | PCNF | 0 | 6 | Empty | 2022-12-31 | 2023-01-10 | 2022-12-31 | 2022-12-31 | 2020-09-17 | 2020-12-16 | 10 | PCNF | PCNF | DF /F | Fireguard for Force X-ray | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200004579 | Fireguard assistance for Force | Fireguard for Force X-ray | PCNF | PCNF | 162 | 39.5 | Empty | 2022-12-31 | 2023-01-10 | 2022-12-31 | 2023-01-10 | 2020-09-17 | 2020-12-16 | 20 | PCNF | PCNF | DF /F | Fireguard for Force X-ray | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100048847 | DFF-03 Choke ZT failure | Isolate + Inhibit Position Measurement D | AWSC | AWSC | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-05-13 | 2021-08-11 | 10 | AWSC | AWSC | DF /F /55/DFFA-ZT-300703 | Isolate + Inhibit Position Measurement D | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100048847 | DFF-03 Choke ZT failure | Isolate + Inhibit Position Measurement D | AWSC | AWSC | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-05-13 | 2021-08-11 | 20 | AWSC | AWSC | DF /F /55/DFFA-ZT-300703 | Isolate + Inhibit Position Measurement D | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100048847 | DFF-03 Choke ZT failure | Isolate + Inhibit Position Measurement D | AWSC | AWSC | 2.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-05-13 | 2021-08-11 | 80 | AWSC | AWSC | DF /F /55/DFFA-ZT-300703 | Isolate + Inhibit Position Measurement D | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100048847 | DFF-03 Choke ZT failure | Isolate + Inhibit Position Measurement D | AWSC | AWSC | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2021-05-13 | 2021-08-11 | 90 | AWSC | AWSC | DF /F /55/DFFA-ZT-300703 | Isolate + Inhibit Position Measurement D | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343653 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-09-01 | 2024-09-03 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-12 | 1 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400343653 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 1 | 0 | Empty | 2024-09-01 | 2024-09-03 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-12 | 9 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343653 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 8 | 0 | Empty | 2024-09-01 | 2024-09-03 | 2024-09-01 | 2024-09-03 | 2024-09-01 | 2024-09-12 | 10 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400343653 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 1 | 0 | Empty | 2024-09-01 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-09-01 | 2024-09-12 | 14 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200016543 | Wifi phone to Dan F Medic | Wifi phone to Dan F Medic |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-11-21 | 2024-01-05 | 10 |  |  | DF /C /08 | Wifi phone to Dan F Medic | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 24 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-09-22 | 2024-09-24 | 2022-03-28 | 2022-11-23 | 10 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 2 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-09-25 | 2024-09-25 | 2022-03-28 | 2022-11-23 | 20 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 2 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-09-25 | 2024-09-25 | 2022-03-28 | 2022-11-23 | 30 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 24 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-09-26 | 2024-10-01 | 2022-03-28 | 2022-11-23 | 40 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 5 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-02 | 2024-10-03 | 2022-03-28 | 2022-11-23 | 50 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 0 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-03 | 2024-10-03 | 2022-03-28 | 2022-11-23 | 60 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 12 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-03 | 2024-10-06 | 2022-03-28 | 2022-11-23 | 70 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 2 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-06 | 2024-10-06 | 2022-03-28 | 2022-11-23 | 80 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 5 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-06 | 2024-10-07 | 2022-03-28 | 2022-11-23 | 90 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 4 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-08 | 2024-10-08 | 2022-03-28 | 2022-11-23 | 100 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200008890 | Recertify DFBA-PSV-57315 - 2022 | Re-certify PSV | SCHSECE | SCHSECE | 12 | 0 | W49-50 | 2024-09-22 | 2024-10-09 | 2024-10-08 | 2024-10-09 | 2022-03-28 | 2022-11-23 | 110 | SCHSECE | SCHSECE | DF /B /70/DFBA-PSV-57315 | Re-certify PSV | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 48 | 16 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 10 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 8 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 20 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 30 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 40 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 20 | 15 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 41 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 50 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 60 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 70 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 80 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 90 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 6 | 6 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 100 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 110 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 6 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 120 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 130 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 140 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 1 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 150 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 160 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 170 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 180 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 190 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 200 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 10 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 210 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 220 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 230 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 0 | 22 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-09 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 240 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2022-11-18 | 2023-01-02 | 250 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-10 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 260 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-INST | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 8 | 5 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-31 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 270 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-TURB | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 8 | 5 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-31 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 280 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2022-11-18 | 2023-01-02 | 290 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-01-30 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 300 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 48 | 5 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-03 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 310 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 8 | 5 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 320 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 330 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 4 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 340 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 20 | 42 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 350 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 360 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 4 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 370 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 4 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 380 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 10 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 390 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 4 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 400 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 6 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 410 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 5 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 420 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 5 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 430 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 440 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 4 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 450 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 1 | 9 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 460 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 4 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 470 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 480 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 13 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 490 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 5 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 500 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 2 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 510 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 10 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 520 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 12 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 530 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 4 | 2 | Empty | 2024-07-29 | 2024-08-03 | 2023-07-04 | 2023-07-12 | 2022-11-18 | 2023-01-02 | 540 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2022-11-18 | 2023-01-02 | 550 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2022-11-18 | 2023-01-02 | 560 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
2 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100078164 | Exchange of defect Bearing in LP motor | Vibration Survey | SCH | SCH | 48 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-08-03 | 2022-11-18 | 2023-01-02 | 570 | SCH | SCH | DF /F /31/DFFA-CM-4202 | Vibration Survey | Unknown
4 | DFE-W01 | WDF | MTN-INST | MTN-INST | 2100058313 | DFE-01 hyd. PI'er til SSSV defekt | Replace Pressure gauge | SCH | SCH | 0.5 | 4 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2022-01-24 | 2022-06-23 | 10 | SCH | SCH | DF /E /07/DFEZ-A-3102 | Replace Pressure gauge | Unknown
4 | DFE-W01 | WDF | MTN-INST | MTN-INST | 2100058313 | DFE-01 hyd. PI'er til SSSV defekt | Replace Pressure gauge | SCH | SCH | 2 | 4 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2022-01-24 | 2022-06-23 | 20 | SCH | SCH | DF /E /07/DFEZ-A-3102 | Replace Pressure gauge | Unknown
4 | DFE-W01 | WDF | MTN-INST | MTN-INST | 2100058313 | DFE-01 hyd. PI'er til SSSV defekt | Replace Pressure gauge | SCH | SCH | 0.5 | 4 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2022-01-24 | 2022-06-23 | 30 | SCH | SCH | DF /E /07/DFEZ-A-3102 | Replace Pressure gauge | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095473 | FCV-390056 No regulation axle is stuck | Replace DFFA-FCV-390056 |  |  | 2 | 0 | Empty | 2024-06-14 | 2024-06-15 | 2024-06-14 | 2024-06-14 | 2023-09-14 | 2024-01-27 | 10 |  |  | DF /F /75/DFFA-FCV-390056 | Replace DFFA-FCV-390056 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095473 | FCV-390056 No regulation axle is stuck | Replace DFFA-FCV-390056 |  |  | 4 | 0 | Empty | 2024-06-14 | 2024-06-15 | 2024-06-14 | 2024-06-15 | 2023-09-14 | 2024-01-27 | 20 |  |  | DF /F /75/DFFA-FCV-390056 | Replace DFFA-FCV-390056 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095473 | FCV-390056 No regulation axle is stuck | Replace DFFA-FCV-390056 |  |  | 2 | 0 | Empty | 2024-06-14 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2023-09-14 | 2024-01-27 | 30 |  |  | DF /F /75/DFFA-FCV-390056 | Replace DFFA-FCV-390056 | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004150 | Change 100Mbit ESD MB300 network card | Secure that redundant network is running |  |  | 20 | 0 | Empty | 2024-02-01 | 2024-02-06 | 2024-02-01 | 2024-02-06 | 2022-11-06 | 2023-03-21 | 10 |  |  | DF /F /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004150 | Change 100Mbit ESD MB300 network card | Secure that redundant network is running |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2022-11-06 | 2023-03-21 | 20 |  |  | DF /F /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004150 | Change 100Mbit ESD MB300 network card | Secure that redundant network is running |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2022-11-06 | 2023-03-21 | 30 |  |  | DF /F /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004150 | Change 100Mbit ESD MB300 network card | Secure that redundant network is running |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2022-11-06 | 2023-03-21 | 40 |  |  | DF /F /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004150 | Change 100Mbit ESD MB300 network card | Secure that redundant network is running |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2022-11-06 | 2023-03-21 | 50 |  |  | DF /F /03 | Secure that redundant network is running | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-08 | 2024-01-13 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-14 | 2024-01-15 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 1 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-15 | 2024-01-15 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-15 | 2024-01-16 | 2022-02-07 | 2022-07-07 | 42 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 2 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-16 | 2024-01-17 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-17 | 2024-01-18 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009227 | Insulation assits FORCE 15245 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-21 | 2024-01-18 | 2024-01-21 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /C /28/DFC-4-DP-050-0101-B5-T | Bilfinger inspection | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346564 | 1Y DELUGE SKID, SMOKE TEST-DFEZ-X-0301 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /E /01/DFEZ-X-0301 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346564 | 1Y DELUGE SKID, SMOKE TEST-DFEZ-X-0301 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /E /01/DFEZ-X-0301 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346564 | 1Y DELUGE SKID, SMOKE TEST-DFEZ-X-0301 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /E /01/DFEZ-X-0301 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346564 | 1Y DELUGE SKID, SMOKE TEST-DFEZ-X-0301 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /E /01/DFEZ-X-0301 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346564 | 1Y DELUGE SKID, SMOKE TEST-DFEZ-X-0301 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /E /01/DFEZ-X-0301 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308985 | 6M WELLH CONT PANEL MAINT - DFFA-FP-3103 | WELLH CONT PANEL MAINT - DFFA-FP-3103 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-03-06 | 2024-03-22 | 10 |  |  | DF /F /07/DFFA-FP-3103 | WELLH CONT PANEL MAINT - DFFA-FP-3103 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322290 | DFF-01-WF-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 247 | 0 | Empty | 2024-10-30 | 2024-11-29 | 2024-10-30 | 2024-11-28 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009246 | Insulation assist bilfinger 21284(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-17 | 2023-03-27 | 2023-03-27 | 2022-02-13 | 2022-07-13 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7142-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009246 | Insulation assist bilfinger 21284(COMP) | Bilfinger inspection |  |  | 108 | 0 | Empty | 2023-03-27 | 2023-04-17 | 2023-03-27 | 2023-04-04 | 2022-02-13 | 2022-07-13 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7142-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009246 | Insulation assist bilfinger 21284(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-17 | 2023-04-05 | 2023-04-07 | 2022-02-13 | 2022-07-13 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7142-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009246 | Insulation assist bilfinger 21284(COMP) | Bilfinger inspection |  |  | 9 | 0 | Empty | 2023-03-27 | 2023-04-17 | 2023-04-07 | 2023-04-07 | 2022-02-13 | 2022-07-13 | 33 |  |  | DF /F /55/DFF-6-PHS-030-7142-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009246 | Insulation assist bilfinger 21284(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-17 | 2023-04-08 | 2023-04-13 | 2022-02-13 | 2022-07-13 | 40 |  |  | DF /F /55/DFF-6-PHS-030-7142-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009246 | Insulation assist bilfinger 21284(COMP) | Bilfinger inspection |  |  | 54 | 0 | Empty | 2023-03-27 | 2023-04-17 | 2023-04-13 | 2023-04-17 | 2022-02-13 | 2022-07-13 | 50 |  |  | DF /F /55/DFF-6-PHS-030-7142-GF-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060981 | Leak test of cooler | Rigger assistance/prepare/lifting |  |  | 20 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-31 | 2022-01-05 | 2022-01-25 | 10 |  |  | DF /F /21/DFFA-E-3602 | Rigger assistance/prepare/lifting | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060981 | Leak test of cooler | Rigger assistance/prepare/lifting |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-07-31 | 2024-08-01 | 2022-01-05 | 2022-01-25 | 20 |  |  | DF /F /21/DFFA-E-3602 | Rigger assistance/prepare/lifting | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060981 | Leak test of cooler | Rigger assistance/prepare/lifting |  |  | 24 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-04 | 2022-01-05 | 2022-01-25 | 30 |  |  | DF /F /21/DFFA-E-3602 | Rigger assistance/prepare/lifting | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060981 | Leak test of cooler | Rigger assistance/prepare/lifting |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2022-01-05 | 2022-01-25 | 40 |  |  | DF /F /21/DFFA-E-3602 | Rigger assistance/prepare/lifting | Unknown
A | D-GASTYE | WPM | MTN-MECH | PRODTECH | 2400325543 | 1Y ESDV LEAK TEST DFBA-ESDV-38097 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-09-20 | 5 | AWSCSECE | AWSCSECE | DF /B /34/DFBA-ESDV-38097 | ISOLATION BY PRODUCTION | Unknown
A | D-GASTYE | WPM | MTN-MECH | PRODTECH | 2400325543 | 1Y ESDV LEAK TEST DFBA-ESDV-38097 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-09-20 | 10 | AWSCSECE | AWSCSECE | DF /B /34/DFBA-ESDV-38097 | ISOLATION BY PRODUCTION | Unknown
A | D-GASTYE | WPM | MTN-MECH | PRODTECH | 2400325543 | 1Y ESDV LEAK TEST DFBA-ESDV-38097 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-08-21 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-21 | 2024-09-20 | 20 | AWSCSECE | AWSCSECE | DF /B /34/DFBA-ESDV-38097 | ISOLATION BY PRODUCTION | Unknown
1 | Empty | WRO | MTN-TELE | VEN-ELEC | 2300008967 | ENG305B - New reset SW | ENG305B - New reset SW |  |  | 24 | 0 | W27-W28 | 2024-07-03 | 2024-07-08 | 2024-07-03 | 2024-07-05 | 2024-05-27 | 2024-06-11 | 10 |  |  | DF /C | ENG305B - New reset SW | Unknown
1 | Empty | WRO | MTN-TELE | MTN-TELE | 2300008967 | ENG305B - New reset SW | ENG305B - New reset SW |  |  | 12 | 6 | W27-W28 | 2024-07-03 | 2024-07-08 | 2024-07-05 | 2024-07-08 | 2024-05-27 | 2024-06-11 | 20 |  |  | DF /C | ENG305B - New reset SW | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036455 | DFF-24 C/I still Chem inj flow DFFA-FCV- | Replace DFFA-FCV-390058 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-09-05 | 2020-12-04 | 10 |  |  | DF /F /75/DFFA-FCV-390058 | Replace DFFA-FCV-390058 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036455 | DFF-24 C/I still Chem inj flow DFFA-FCV- | Replace DFFA-FCV-390058 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2020-09-05 | 2020-12-04 | 20 |  |  | DF /F /75/DFFA-FCV-390058 | Replace DFFA-FCV-390058 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036455 | DFF-24 C/I still Chem inj flow DFFA-FCV- | Replace DFFA-FCV-390058 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2020-09-05 | 2020-12-04 | 30 |  |  | DF /F /75/DFFA-FCV-390058 | Replace DFFA-FCV-390058 | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 18 | Empty | 2024-09-22 | 2024-09-22 | 2022-04-05 | 2022-05-19 | 2021-12-15 | 2022-01-20 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2021-12-15 | 2022-01-20 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-RIGG | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 6 | Empty | 2024-09-22 | 2024-09-22 | 2022-04-05 | 2022-05-19 | 2021-12-15 | 2022-01-20 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-RIGG | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 10 | Empty | 2024-09-22 | 2024-09-22 | 2022-04-05 | 2022-05-19 | 2021-12-15 | 2022-01-20 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-ROPE | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2022-04-05 | 2022-05-19 | 2021-12-15 | 2022-01-20 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-ROPE | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2022-04-05 | 2022-05-19 | 2021-12-15 | 2022-01-20 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400176785 | 1Y RENS AF HEATER/EXCHANGER | operation_description_not_present | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 15 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2021-12-15 | 2022-01-20 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /53/DFFB-E-3565 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106765 | DFGA-PM-3958 Cover fan very rusty | De-Isolate Pump Circuit |  |  | 2 | 0 | Empty | 2024-06-18 | 2024-06-21 | 2024-06-18 | 2024-06-18 | 2024-03-19 | 2024-08-01 | 20 |  |  | DF /G /75/DFGA-PM-3958 | De-Isolate Pump Circuit | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106765 | DFGA-PM-3958 Cover fan very rusty | De-Isolate Pump Circuit |  |  | 6 | 0 | Empty | 2024-06-18 | 2024-06-21 | 2024-06-18 | 2024-06-20 | 2024-03-19 | 2024-08-01 | 30 |  |  | DF /G /75/DFGA-PM-3958 | De-Isolate Pump Circuit | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106765 | DFGA-PM-3958 Cover fan very rusty | De-Isolate Pump Circuit |  |  | 2 | 0 | Empty | 2024-06-18 | 2024-06-21 | 2024-06-20 | 2024-06-20 | 2024-03-19 | 2024-08-01 | 40 |  |  | DF /G /75/DFGA-PM-3958 | De-Isolate Pump Circuit | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106765 | DFGA-PM-3958 Cover fan very rusty | De-Isolate Pump Circuit |  |  | 1 | 0 | Empty | 2024-06-18 | 2024-06-21 | 2024-06-20 | 2024-06-21 | 2024-03-19 | 2024-08-01 | 50 |  |  | DF /G /75/DFGA-PM-3958 | De-Isolate Pump Circuit | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100058310 | Filterhousing and HCV bolts both Bypass | Prepare Matr/Tools |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2021-11-23 | 2022-02-21 | 10 |  |  | DF /E /07 | Prepare Matr/Tools | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100058310 | Filterhousing and HCV bolts both Bypass | Prepare Matr/Tools |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-02 | 2021-11-23 | 2022-02-21 | 20 |  |  | DF /E /07 | Prepare Matr/Tools | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100058310 | Filterhousing and HCV bolts both Bypass | Prepare Matr/Tools |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2021-11-23 | 2022-02-21 | 30 |  |  | DF /E /07 | Prepare Matr/Tools | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100058310 | Filterhousing and HCV bolts both Bypass | Prepare Matr/Tools |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2021-11-23 | 2022-02-21 | 40 |  |  | DF /E /07 | Prepare Matr/Tools | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 10 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 20 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 30 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 40 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 50 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 60 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 70 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300002884 | Replaced by 2300005110 | Rental Equipment from Jutlandia |  |  | 0 | 0 | Empty | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2022-02-03 | 2021-10-23 | 2022-08-19 | 80 |  |  | DF /C /84 | Rental Equipment from Jutlandia | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235731 | 4Y 380V E-SWB MAINT DFCI-N-1812-L03 | ISOLATION BY PRODUCTION | PCNFAWSCSECE | PCNFAWSCSECE | 1 | 4 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | PCNFAWSCSECE | PCNFAWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235731 | 4Y 380V E-SWB MAINT DFCI-N-1812-L03 | ISOLATION BY PRODUCTION | PCNFAWSCSECE | PCNFAWSCSECE | 1 | 23 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 20 | PCNFAWSCSECE | PCNFAWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235731 | 4Y 380V E-SWB MAINT DFCI-N-1812-L03 | ISOLATION BY PRODUCTION | PCNFAWSCSECE | PCNFAWSCSECE | 14 | 4 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 30 | PCNFAWSCSECE | PCNFAWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235731 | 4Y 380V E-SWB MAINT DFCI-N-1812-L03 | ISOLATION BY PRODUCTION | PCNFAWSCSECE | PCNFAWSCSECE | 0 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 35 | PCNFAWSCSECE | PCNFAWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235731 | 4Y 380V E-SWB MAINT DFCI-N-1812-L03 | ISOLATION BY PRODUCTION | PCNFAWSCSECE | PCNFAWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 40 | PCNFAWSCSECE | PCNFAWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY PRODUCTION | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 150 | 8.5 | Empty | 2021-07-26 | 2021-09-06 | 2021-07-26 | 2021-07-29 | 2021-02-04 | 2021-05-05 | 10 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 26 | 3.5 | Empty | 2021-07-26 | 2021-09-06 | 2021-07-29 | 2021-07-30 | 2021-02-04 | 2021-05-05 | 20 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 30 | 0 | Empty | 2021-07-26 | 2021-09-06 | 2021-07-30 | 2021-08-02 | 2021-02-04 | 2021-05-05 | 30 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 20 | 0 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-02 | 2021-08-04 | 2021-02-04 | 2021-05-05 | 40 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 120 | 0 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-04 | 2021-08-17 | 2021-02-04 | 2021-05-05 | 50 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 18 | 0.5 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-17 | 2021-08-18 | 2021-02-04 | 2021-05-05 | 60 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 12 | 12 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-18 | 2021-08-18 | 2021-02-04 | 2021-05-05 | 70 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 12 | 75 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-18 | 2021-08-18 | 2021-02-04 | 2021-05-05 | 80 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 60 | 1 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-18 | 2021-08-23 | 2021-02-04 | 2021-05-05 | 90 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 71 | 1 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-23 | 2021-08-30 | 2021-02-04 | 2021-05-05 | 100 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 12 | 0 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-30 | 2021-08-31 | 2021-02-04 | 2021-05-05 | 110 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 60 | 6 | Empty | 2021-07-26 | 2021-09-06 | 2021-08-31 | 2021-09-06 | 2021-02-04 | 2021-05-05 | 120 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002418 | DAF OCG NPT order -ART Piping 24" X-Over | Clean-up & housekeeping | PCNF | PCNF | 0 | 0 | Empty | 2021-07-26 | 2021-09-06 | 2021-09-06 | 2021-09-06 | 2021-02-04 | 2021-05-05 | 130 | PCNF | PCNF | DF | Clean-up & housekeeping | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100035090 | Maintenance Follow-up DFGA-FI-570020 | Remove old Flowmeter |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 10 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035090 | Maintenance Follow-up DFGA-FI-570020 | Remove old Flowmeter |  |  | 1.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 20 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035090 | Maintenance Follow-up DFGA-FI-570020 | Remove old Flowmeter |  |  | 1.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 30 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100035090 | Maintenance Follow-up DFGA-FI-570020 | Remove old Flowmeter |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 40 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035090 | Maintenance Follow-up DFGA-FI-570020 | Remove old Flowmeter |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 50 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100035090 | Maintenance Follow-up DFGA-FI-570020 | Remove old Flowmeter |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2020-10-06 | 2021-03-05 | 60 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
D | NOSD | WPM | PRODTECH | PRODTECH | 2400342618 | PIGGING, P3002 10" DFB-GOC OIL 2W | P3002_DFB-GOC | AWSC | AWSC | 4 | 6 | Empty | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-29 | 2024-09-04 | 10 | AWSC | AWSC | DF /B /23/DFBY-PL-673002 | P3002_DFB-GOC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077594 | Replacement of N2 cylinders | Isolation of reserve bank |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-12-18 | 2023-05-02 | 10 |  |  | DF /G /01/WATER-MIST-SKIDS | Isolation of reserve bank | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077594 | Replacement of N2 cylinders | Isolation of reserve bank |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-12-18 | 2023-05-02 | 20 |  |  | DF /G /01/WATER-MIST-SKIDS | Isolation of reserve bank | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100077594 | Replacement of N2 cylinders | Isolation of reserve bank |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2022-12-18 | 2023-05-02 | 25 |  |  | DF /G /01/WATER-MIST-SKIDS | Isolation of reserve bank | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077594 | Replacement of N2 cylinders | Isolation of reserve bank |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2022-12-18 | 2023-05-02 | 30 |  |  | DF /G /01/WATER-MIST-SKIDS | Isolation of reserve bank | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077594 | Replacement of N2 cylinders | Isolation of reserve bank |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2022-12-18 | 2023-05-02 | 40 |  |  | DF /G /01/WATER-MIST-SKIDS | Isolation of reserve bank | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077594 | Replacement of N2 cylinders | Isolation of reserve bank |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-12-18 | 2023-05-02 | 50 |  |  | DF /G /01/WATER-MIST-SKIDS | Isolation of reserve bank | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100105404 | Findings from 1Y CO2 check DFBA-A-0411 | Replace CO2 hoses |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-02-24 | 2024-07-08 | 10 |  |  | DF /B /01/CO2-SNUFFING-SYSTEM | Replace CO2 hoses | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105404 | Findings from 1Y CO2 check DFBA-A-0411 | Replace CO2 hoses |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-02-24 | 2024-07-08 | 20 |  |  | DF /B /01/CO2-SNUFFING-SYSTEM | Replace CO2 hoses | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100105404 | Findings from 1Y CO2 check DFBA-A-0411 | Replace CO2 hoses |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-02-24 | 2024-07-08 | 30 |  |  | DF /B /01/CO2-SNUFFING-SYSTEM | Replace CO2 hoses | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400246084 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-21 | 2023-05-01 | 10 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400246084 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-21 | 2023-05-01 | 20 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400246084 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-21 | 2023-05-01 | 30 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024915 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger preparation | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2018-11-28 | 2019-04-27 | 5 | AWSC | AWSC | DF /F /12 | L3 Rigger preparation | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100024915 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger preparation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2018-11-28 | 2019-04-27 | 10 | AWSC | AWSC | DF /F /12 | L3 Rigger preparation | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024915 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger preparation | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2018-11-28 | 2019-04-27 | 15 | AWSC | AWSC | DF /F /12 | L3 Rigger preparation | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100024915 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger preparation | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2018-11-28 | 2019-04-27 | 20 | AWSC | AWSC | DF /F /12 | L3 Rigger preparation | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100024915 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger preparation | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2018-11-28 | 2019-04-27 | 21 | AWSC | AWSC | DF /F /12 | L3 Rigger preparation | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100024915 | DF.F.038 W. Inj. Dan Bravo 2" bypass val | L3 Rigger preparation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2018-11-28 | 2019-04-27 | 30 | AWSC | AWSC | DF /F /12 | L3 Rigger preparation | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000784 | DK46 BACKLOAD OC EQ MATERIAL 2019 | DK46 BACKLOAD OC EQ MATERIAL 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-01-01 | 2019-12-31 | 10 |  |  | DF /F | DK46 BACKLOAD OC EQ MATERIAL 2019 | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400328729 | 1Y SIMULTAN AEROTEST SERVICE - DFC | SIMULTAN AEROTEST SERVICE - DFC |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-04-17 | 2024-06-03 | 10 |  |  | DF /C /84/TEST-EQUIPMENT | SIMULTAN AEROTEST SERVICE - DFC | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2018-04-30 | 2018-06-09 | 10 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-17 | 2018-04-30 | 2018-06-09 | 20 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-18 | 2018-04-30 | 2018-06-09 | 30 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-19 | 2018-04-30 | 2018-06-09 | 40 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-21 | 2018-04-30 | 2018-06-09 | 50 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-22 | 2018-04-30 | 2018-06-09 | 55 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-22 | 2018-04-30 | 2018-06-09 | 60 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | QAQCMECH | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2018-04-30 | 2018-06-09 | 70 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2018-04-30 | 2018-06-09 | 80 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100023667 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-up hoist for LCV-50741 |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2018-04-30 | 2018-06-09 | 90 |  |  | DF /C /28/DFCM-LCV-50741 | L3 Rig-up hoist for LCV-50741 | Unknown
2 | NOSD | WGN | MTN-MECH | PRODTECH | 2200018538 | DFFA-V-5012 liner replacement in connect | DFFA-V-5012 liner replacement, PVI |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-05-14 | 2024-06-28 | 10 |  |  | DF /F /27/DFFA-V-5012 | DFFA-V-5012 liner replacement, PVI | Unknown
2 | NOSD | WGN | MTN-MECH | PRODTECH | 2200018538 | DFFA-V-5012 liner replacement in connect | DFFA-V-5012 liner replacement, PVI |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-05-14 | 2024-06-28 | 20 |  |  | DF /F /27/DFFA-V-5012 | DFFA-V-5012 liner replacement, PVI | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 4 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-05-10 | 2024-05-13 | 2024-10-12 | 2024-12-31 | 22 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 2 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-05-10 | 2024-05-13 | 2024-10-12 | 2024-12-31 | 23 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 25 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284233 | PSV Calibration - DFBA-PSV-39063 | Remove PSV and Install blinds | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W19-W20 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /75/DFBA-PSV-39063 | Remove PSV and Install blinds | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235591 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2023-03-31 | 2023-06-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235591 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A | ISOLATION ELECTRICAL | AWSC | AWSC | 30 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-29 | 2023-03-31 | 2023-06-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235591 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A | ISOLATION ELECTRICAL | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-29 | 2024-10-02 | 2023-03-31 | 2023-06-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235591 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2023-03-31 | 2023-06-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802A | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024907 | Exchange DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | PCNF | PCNF | 10 | 2 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2018-08-30 | 2019-01-27 | 10 | PCNF | PCNF | DF /F /75/DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024907 | Exchange DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | PCNF | PCNF | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2018-08-30 | 2019-01-27 | 20 | PCNF | PCNF | DF /F /75/DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024907 | Exchange DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-17 | 2018-08-30 | 2019-01-27 | 30 | PCNF | PCNF | DF /F /75/DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100024907 | Exchange DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-17 | 2018-08-30 | 2019-01-27 | 40 | PCNF | PCNF | DF /F /75/DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024907 | Exchange DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | PCNF | PCNF | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-17 | 2018-08-30 | 2019-01-27 | 50 | PCNF | PCNF | DF /F /75/DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024907 | Exchange DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | PCNF | PCNF | 8 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-18 | 2018-08-30 | 2019-01-27 | 60 | PCNF | PCNF | DF /F /75/DFFA-XCV-760007 | L3 prepare scaffold & lifting eq | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100042166 | Deluge downstream valve HCV-035326 | reorder butterfly and bolts | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2021-02-24 | 2021-07-24 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-035326 | reorder butterfly and bolts | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042166 | Deluge downstream valve HCV-035326 | reorder butterfly and bolts | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-04 | 2021-02-24 | 2021-07-24 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-035326 | reorder butterfly and bolts | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100042166 | Deluge downstream valve HCV-035326 | reorder butterfly and bolts | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-04 | 2021-02-24 | 2021-07-24 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-035326 | reorder butterfly and bolts | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100042166 | Deluge downstream valve HCV-035326 | reorder butterfly and bolts | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2021-02-24 | 2021-07-24 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-035326 | reorder butterfly and bolts | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042166 | Deluge downstream valve HCV-035326 | reorder butterfly and bolts | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2021-02-24 | 2021-07-24 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-035326 | reorder butterfly and bolts | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042166 | Deluge downstream valve HCV-035326 | reorder butterfly and bolts | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2021-02-24 | 2021-07-24 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-035326 | reorder butterfly and bolts | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346558 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0327 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0327 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346558 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0327 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0327 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346558 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0327 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0327 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346558 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0327 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0327 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346558 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0327 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0327 | ISOLATION BY PRODUCTION | Unknown
3 | DFB-OIL | WDF | MTN-INST | PRODTECH | 2100086355 | Replace Push button | Inhibit Push button |  |  | 0.5 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | 2023-04-14 | 2023-08-27 | 10 |  |  | DF /B /10/DFBA-SSSV-30316 | Inhibit Push button | Unknown
3 | DFB-OIL | WDF | MTN-INST | MTN-INST | 2100086355 | Replace Push button | Inhibit Push button |  |  | 0.5 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | 2023-04-14 | 2023-08-27 | 20 |  |  | DF /B /10/DFBA-SSSV-30316 | Inhibit Push button | Unknown
3 | DFB-OIL | WDF | MTN-INST | MTN-INST | 2100086355 | Replace Push button | Inhibit Push button |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | 2023-04-14 | 2023-08-27 | 30 |  |  | DF /B /10/DFBA-SSSV-30316 | Inhibit Push button | Unknown
3 | DFB-OIL | WDF | MTN-INST | MTN-INST | 2100086355 | Replace Push button | Inhibit Push button |  |  | 0.5 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2023-04-14 | 2023-08-27 | 40 |  |  | DF /B /10/DFBA-SSSV-30316 | Inhibit Push button | Unknown
3 | DFB-OIL | WDF | MTN-INST | PRODTECH | 2100086355 | Replace Push button | Inhibit Push button |  |  | 0.5 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2023-04-14 | 2023-08-27 | 50 |  |  | DF /B /10/DFBA-SSSV-30316 | Inhibit Push button | Unknown
3 | DFB-OIL | WDF | MTN-INST | PRODTECH | 2100086355 | Replace Push button | Inhibit Push button |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2023-04-14 | 2023-08-27 | 60 |  |  | DF /B /10/DFBA-SSSV-30316 | Inhibit Push button | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023395 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 10 |  |  | DF /C /07/DFCM-HCV-54380-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023395 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 20 |  |  | DF /C /07/DFCM-HCV-54380-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023395 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 30 |  |  | DF /C /07/DFCM-HCV-54380-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023395 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 40 |  |  | DF /C /07/DFCM-HCV-54380-U | Isolation of valve | Unknown
2 | DFB-W11 | WDF | MTN-INST | MTN-INST | 2100105583 | Change DFB-11 WI orifices | Change ABB constant in ICCS |  |  | 0.5 | 0 | Empty | 2024-06-30 | 2024-07-02 | 2024-06-30 | 2024-06-30 | 2024-01-18 | 2024-03-03 | 10 |  |  | DF /B /55/DFBA-FE-35035 | Change ABB constant in ICCS | Unknown
2 | DFB-W11 | WDF | MTN-INST | MTN-INST | 2100105583 | Change DFB-11 WI orifices | Change ABB constant in ICCS |  |  | 5 | 0 | Empty | 2024-06-30 | 2024-07-02 | 2024-06-30 | 2024-07-01 | 2024-01-18 | 2024-03-03 | 20 |  |  | DF /B /55/DFBA-FE-35035 | Change ABB constant in ICCS | Unknown
2 | DFB-W11 | WDF | MTN-INST | MTN-TELE | 2100105583 | Change DFB-11 WI orifices | Change ABB constant in ICCS |  |  | 1 | 0 | Empty | 2024-06-30 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2024-01-18 | 2024-03-03 | 30 |  |  | DF /B /55/DFBA-FE-35035 | Change ABB constant in ICCS | Unknown
2 | DFB-W11 | WDF | MTN-INST | PRODTECH | 2100105583 | Change DFB-11 WI orifices | Change ABB constant in ICCS |  |  | 1 | 0 | Empty | 2024-06-30 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2024-01-18 | 2024-03-03 | 40 |  |  | DF /B /55/DFBA-FE-35035 | Change ABB constant in ICCS | Unknown
2 | DFB-W11 | WDF | MTN-INST | MTN-INST | 2100105583 | Change DFB-11 WI orifices | Change ABB constant in ICCS |  |  | 1 | 0 | Empty | 2024-06-30 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-01-18 | 2024-03-03 | 50 |  |  | DF /B /55/DFBA-FE-35035 | Change ABB constant in ICCS | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 6 | 8 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 10 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 2 | 18 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 20 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 8 | 8 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 30 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 40 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-INST | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 3 | 6 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 41 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 12 | 20 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 50 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 12 | 4 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 60 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-INST | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 70 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 80 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 3 | 1 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 90 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 6 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 100 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ROPE | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 110 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-INST | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 1 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 120 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-INST | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 1 | 0 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-08 | 2022-03-07 | 130 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ROUS | 2100052900 | XCV-380606 på WI Halfdan pig Launcher ZS | Remove ZSC-ZSO | PCNFSCH | PCNFSCH | 8 | 8 | W29-W30 | 2024-07-16 | 2024-07-16 | 2024-07-01 | 2024-07-11 | 2021-10-08 | 2022-03-07 | 140 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-XCV-380606 | Remove ZSC-ZSO | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077608 | Watermist Filling valve defective | Isolation |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 10 |  |  | DF /G /01/DFGA-A-0462 | Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077608 | Watermist Filling valve defective | Isolation |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 20 |  |  | DF /G /01/DFGA-A-0462 | Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077608 | Watermist Filling valve defective | Isolation |  |  | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2022-12-18 | 2023-05-02 | 30 |  |  | DF /G /01/DFGA-A-0462 | Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077608 | Watermist Filling valve defective | Isolation |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2022-12-18 | 2023-05-02 | 40 |  |  | DF /G /01/DFGA-A-0462 | Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077608 | Watermist Filling valve defective | Isolation |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 50 |  |  | DF /G /01/DFGA-A-0462 | Isolation | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 10 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
2 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 20 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 30 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 35 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 24 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 40 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
2 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 50 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012214 | Replace water bottles, A section, A-0462 | Report Serial No. on bottles to User Res | PCNFSECE | PCNFSECE | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-10-19 | 2022-12-03 | 60 | PCNFSECE | PCNFSECE | DF /G /01/DFGA-A-0462 | Report Serial No. on bottles to User Res | Unknown
4 | NOSD | WDF | MTN-ROUS | VEN-MECH | 2100077778 | DFE LB1 replace foundation bolts | Isolate lifeboat in maintenance wires | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-07 | 2025-10-23 | 10 | SECE | SECE | DF /E /02/DFEZ-X-0701 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-ROUS | VEN-MECH | 2100077778 | DFE LB1 replace foundation bolts | Isolate lifeboat in maintenance wires | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-07 | 2025-10-23 | 20 | SECE | SECE | DF /E /02/DFEZ-X-0701 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-ROUS | VEN-MECH | 2100077778 | DFE LB1 replace foundation bolts | Isolate lifeboat in maintenance wires | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-07 | 2025-10-23 | 30 | SECE | SECE | DF /E /02/DFEZ-X-0701 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-ROUS | VEN-MECH | 2100077778 | DFE LB1 replace foundation bolts | Isolate lifeboat in maintenance wires | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-07 | 2025-10-23 | 35 | SECE | SECE | DF /E /02/DFEZ-X-0701 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-ROUS | MTN-PAIN | 2100077778 | DFE LB1 replace foundation bolts | Isolate lifeboat in maintenance wires | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-05-07 | 2025-10-23 | 40 | SECE | SECE | DF /E /02/DFEZ-X-0701 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100022817 | CMAT:Exchange leaking spools on potwater | L3 Prepare scaffold & spools |  |  | 67 | 0 | Empty | 2023-02-13 | 2023-02-27 | 2023-02-13 | 2023-02-18 | 2019-06-27 | 2019-11-24 | 10 |  |  | DF /C /85 | L3 Prepare scaffold & spools | Unknown
4 | NOSD | WDF | MTN-PAIN | PRODTECH | 2100022817 | CMAT:Exchange leaking spools on potwater | L3 Prepare scaffold & spools |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-27 | 2023-02-18 | 2023-02-19 | 2019-06-27 | 2019-11-24 | 20 |  |  | DF /C /85 | L3 Prepare scaffold & spools | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PIPF | 2100022817 | CMAT:Exchange leaking spools on potwater | L3 Prepare scaffold & spools |  |  | 16.100000000000001421085471515 | 0 | Empty | 2023-02-13 | 2023-02-27 | 2023-02-19 | 2023-02-20 | 2019-06-27 | 2019-11-24 | 30 |  |  | DF /C /85 | L3 Prepare scaffold & spools | Unknown
4 | NOSD | WDF | MTN-PAIN | PRODTECH | 2100022817 | CMAT:Exchange leaking spools on potwater | L3 Prepare scaffold & spools |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-27 | 2023-02-20 | 2023-02-21 | 2019-06-27 | 2019-11-24 | 40 |  |  | DF /C /85 | L3 Prepare scaffold & spools | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100022817 | CMAT:Exchange leaking spools on potwater | L3 Prepare scaffold & spools |  |  | 67 | 0 | Empty | 2023-02-13 | 2023-02-27 | 2023-02-21 | 2023-02-27 | 2019-06-27 | 2019-11-24 | 50 |  |  | DF /C /85 | L3 Prepare scaffold & spools | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344332 | 1Y HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-21 | 2024-08-23 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-09-26 | 10 |  |  | DF /F /75/DFFA-FP-3990 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344332 | 1Y HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 | DE-ISOLATION BY PRODUCTION |  |  | 5 | 0 | Empty | 2024-08-21 | 2024-08-23 | 2024-08-21 | 2024-08-22 | 2024-08-21 | 2024-09-26 | 20 |  |  | DF /F /75/DFFA-FP-3990 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400344332 | 1Y HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 | DE-ISOLATION BY PRODUCTION |  |  | 3 | 0 | Empty | 2024-08-21 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2024-08-21 | 2024-09-26 | 30 |  |  | DF /F /75/DFFA-FP-3990 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344332 | 1Y HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-21 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2024-08-21 | 2024-09-26 | 40 |  |  | DF /F /75/DFFA-FP-3990 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235315 | 6M SAND JETTING PUMP MAINT-DFCI-P-5044 | SAND JETTING PUMP INSP-DFCI-P-5044 |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-25 | 2023-03-16 | 10 |  |  | DF /C /27/DFCI-P-5044 | SAND JETTING PUMP INSP-DFCI-P-5044 | Unknown
4 | KRA-OIL | WGN | MTN-MECH | PRODTECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-03 | 2024-06-03 | 2023-06-03 | 2025-11-19 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | PRODTECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-03 | 2024-06-04 | 2023-06-03 | 2025-11-19 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | MTN-RIGG | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 24 | 12 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-04 | 2024-06-07 | 2023-06-03 | 2025-11-19 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | MTN-MECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 5 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-07 | 2024-06-08 | 2023-06-03 | 2025-11-19 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | MTN-MECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-08 | 2024-06-08 | 2023-06-03 | 2025-11-19 | 50 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | MTN-RIGG | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 12 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-08 | 2024-06-10 | 2023-06-03 | 2025-11-19 | 60 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | PRODTECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-10 | 2024-06-10 | 2023-06-03 | 2025-11-19 | 70 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | MTN-MECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 5 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-10 | 2024-06-11 | 2023-06-03 | 2025-11-19 | 80 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | PRODTECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 4 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-11 | 2024-06-12 | 2023-06-03 | 2025-11-19 | 90 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
4 | KRA-OIL | WGN | MTN-MECH | MTN-MECH | 2200012622 | Replace DFBA-PSV-38182 - PSV 2023 | new PSV | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | Empty | 2024-06-03 | 2024-06-12 | 2024-06-12 | 2024-06-12 | 2023-06-03 | 2025-11-19 | 100 | PCNFSCHSECE | PCNFSCHSECE | DF /B /11/DFBA-PSV-38182 | new PSV | Unknown
A | DFF-1630 | WPM | MTN-TURB | PRODTECH | 2400322772 | 8KH MAIN GEN. SERVICE, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 0 | W17-W18 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-22 | 2024-05-22 | 10 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-TURB | VEN-INST | 2400322772 | 8KH MAIN GEN. SERVICE, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 18 | 18 | W17-W18 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-22 | 2024-05-22 | 20 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-TURB | MTN-ELEC | 2400322772 | 8KH MAIN GEN. SERVICE, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 18 | 18 | W17-W18 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-22 | 2024-05-22 | 30 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-TURB | MTN-TURB | 2400322772 | 8KH MAIN GEN. SERVICE, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 32 | 32 | W17-W18 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-22 | 2024-05-22 | 40 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-TURB | PRODTECH | 2400322772 | 8KH MAIN GEN. SERVICE, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 5 | W17-W18 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-22 | 2024-05-22 | 50 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000964 | SCADA SW for ENG469Q Catalyst pumps | SCADA SW for ENG469Q Catalyst pumps | AWSC | AWSC | 12 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 10 | AWSC | AWSC | DF /B /04/DFBA-FP-2036 | SCADA SW for ENG469Q Catalyst pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000964 | SCADA SW for ENG469Q Catalyst pumps | SCADA SW for ENG469Q Catalyst pumps | AWSC | AWSC | 6 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 20 | AWSC | AWSC | DF /B /04/DFBA-FP-2036 | SCADA SW for ENG469Q Catalyst pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000964 | SCADA SW for ENG469Q Catalyst pumps | SCADA SW for ENG469Q Catalyst pumps | AWSC | AWSC | 0 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 30 | AWSC | AWSC | DF /B /04/DFBA-FP-2036 | SCADA SW for ENG469Q Catalyst pumps | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269331 | 3M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-10 | 2023-08-20 | 10 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /F | additional materials | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF /F | additional materials | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 30 |  |  | DF /F | additional materials | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 40 |  |  | DF /F | additional materials | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 50 |  |  | DF /F | additional materials | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 60 |  |  | DF /F | additional materials | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000749 | GE SYST 69 TIL 31.12.2019 | additional materials |  |  | 0 | 0 | Empty | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2020-05-26 | 2019-12-31 | 2019-12-31 | 70 |  |  | DF /F | additional materials | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400351956 | 1Y DOWNHOLE GAUGE SYSTEM - DFB | DOWNHOLE GAUGE SYSTEM MAINT - DFB |  |  | 4 | 0 | W37-W38 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-10-15 | 10 |  |  | DF /B /10/CONTROL-PANELS | DOWNHOLE GAUGE SYSTEM MAINT - DFB | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087260 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /G /05/DFGA-LP-1852-45 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087260 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /G /05/DFGA-LP-1852-45 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087260 | Battery fault on emergency light | Isolate and prove dead. |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /G /05/DFGA-LP-1852-45 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087260 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 50 |  |  | DF /G /05/DFGA-LP-1852-45 | Isolate and prove dead. | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300007102 | DK40 - CONSUMABLE CAMPAIGN CoW24 - PROD. | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. |  |  | 0 | 0 | Empty | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2026-10-31 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 2 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 3 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 4 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 5 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-SCAF | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 24 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 8 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | PRODTECH | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 5 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 10 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 5 | 12 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 20 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-MECH | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 3 | 12 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 30 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-RIGG | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 3 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 40 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-RIGG | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 3 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 50 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-PAIN | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 12 | 12 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 51 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-PAIN | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-08-28 | 2023-01-10 | 52 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-PAIN | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-08-28 | 2023-01-10 | 53 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-PAIN | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-08-28 | 2023-01-10 | 54 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-LAGG | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-08-28 | 2023-01-10 | 55 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 5 | 12 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 60 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-MECH | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 3 | 12 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 70 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 1 | 12 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 80 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | PRODTECH | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 4 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-27 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 90 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-SCAF | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 10 | 10 | Empty | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-08-28 | 2023-01-10 | 100 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ROPE | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-12-05 | 2022-08-28 | 2023-01-10 | 110 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100071521 | *Change out HE-3573 Minox. Linewalk w/Si | 2100071521-0002~COATING* | SCH | SCH | 0 | 0 | Empty | 2022-12-05 | 2022-12-05 | 2022-10-24 | 2022-10-31 | 2022-08-28 | 2023-01-10 | 120 | SCH | SCH | DF /F /53/DFFB-HE-3573 | 2100071521-0002~COATING* | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100031489 | ANOP 1½" GFS pilot Gas is heavily corrod | additional materials |  |  | 0 | 0 | Empty | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2020-04-27 | 2020-05-17 | 10 |  |  | DF /B /70/DFB-1.5-GF-057-0813-AD-U | additional materials | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100031489 | ANOP 1½" GFS pilot Gas is heavily corrod | additional materials |  |  | 0 | 0 | Empty | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2020-04-27 | 2020-05-17 | 20 |  |  | DF /B /70/DFB-1.5-GF-057-0813-AD-U | additional materials | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300007175 | DK40 - CONSUMABLE PROD - OFFICE | DK40 - CONSUMABLE PROD - OFFICE |  |  | 0 | 0 | Empty | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2026-11-08 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OFFICE | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100045352 | DFE04 Replace tubing PT-30196 (INST-TUBF | Isolate pressure transmitter |  |  | 1 | 0 | Align with DFA-04 loss WO | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-02-27 | 2021-05-28 | 10 |  |  | DF /E /10/DFEZ-PT-30196 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100045352 | DFE04 Replace tubing PT-30196 (INST-TUBF | Isolate pressure transmitter |  |  | 0.5 | 0 | Align with DFA-04 loss WO | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-02-27 | 2021-05-28 | 20 |  |  | DF /E /10/DFEZ-PT-30196 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100045352 | DFE04 Replace tubing PT-30196 (INST-TUBF | Isolate pressure transmitter |  |  | 5 | 0 | Align with DFA-04 loss WO | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2021-02-27 | 2021-05-28 | 30 |  |  | DF /E /10/DFEZ-PT-30196 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100045352 | DFE04 Replace tubing PT-30196 (INST-TUBF | Isolate pressure transmitter |  |  | 1 | 0 | Align with DFA-04 loss WO | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-02-27 | 2021-05-28 | 40 |  |  | DF /E /10/DFEZ-PT-30196 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100045352 | DFE04 Replace tubing PT-30196 (INST-TUBF | Isolate pressure transmitter |  |  | 1 | 0 | Align with DFA-04 loss WO | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-02-27 | 2021-05-28 | 50 |  |  | DF /E /10/DFEZ-PT-30196 | Isolate pressure transmitter | Unknown
2 | SIWL | WDF | MTN-MECH | PRODTECH | 2100103973 | DFB-12 Hydraulic 400 bar return line hot | Production isolation |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2024-07-30 | 2023-12-20 | 2024-02-03 | 10 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100103973 | DFB-12 Hydraulic 400 bar return line hot | Production isolation |  |  | 6 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2024-08-01 | 2023-12-20 | 2024-02-03 | 20 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100103973 | DFB-12 Hydraulic 400 bar return line hot | Production isolation |  |  | 6 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-08-31 | 2024-09-01 | 2023-12-20 | 2024-02-03 | 30 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
2 | SIWL | WDF | MTN-MECH | PRODTECH | 2100103973 | DFB-12 Hydraulic 400 bar return line hot | Production isolation |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2023-12-20 | 2024-02-03 | 40 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235742 | 4Y 400V UPS-DP F.TEST DFFB-DP-1906A/B | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /06/DFFB-DP-1906A | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235742 | 4Y 400V UPS-DP F.TEST DFFB-DP-1906A/B | ISOLATION ELECTRICAL | SECE | SECE | 18 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /06/DFFB-DP-1906A | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235742 | 4Y 400V UPS-DP F.TEST DFFB-DP-1906A/B | ISOLATION ELECTRICAL | SECE | SECE | 3 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /06/DFFB-DP-1906A | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235742 | 4Y 400V UPS-DP F.TEST DFFB-DP-1906A/B | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /06/DFFB-DP-1906A | ISOLATION ELECTRICAL | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100081819 | DFC XM-5223 trips after start on FT-5223 | Erect and dismantle scaffold | PCNFSCH | PCNFSCH | 2 | 14 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-01-24 | 2023-03-10 | 10 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5223 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100081819 | DFC XM-5223 trips after start on FT-5223 | Erect and dismantle scaffold | PCNFSCH | PCNFSCH | 1 | 2 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-01-24 | 2023-03-10 | 20 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5223 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100081819 | DFC XM-5223 trips after start on FT-5223 | Erect and dismantle scaffold | PCNFSCH | PCNFSCH | 4 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-01-24 | 2023-03-10 | 30 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5223 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100081819 | DFC XM-5223 trips after start on FT-5223 | Erect and dismantle scaffold | PCNFSCH | PCNFSCH | 1 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-01-24 | 2023-03-10 | 40 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5223 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100081819 | DFC XM-5223 trips after start on FT-5223 | Erect and dismantle scaffold | PCNFSCH | PCNFSCH | 1 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-01-24 | 2023-03-10 | 50 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5223 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100081819 | DFC XM-5223 trips after start on FT-5223 | Erect and dismantle scaffold | PCNFSCH | PCNFSCH | 0 | 5 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-04-11 | 2024-04-28 | 2023-01-24 | 2023-03-10 | 60 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5223 | Erect and dismantle scaffold | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322237 | DFB-28-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 68 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
2 | DFB-W03 | WDF | MTN-INST | PRODTECH | 2100075979 | DFB-03 Choke ZSO,ZSC & ZT justering | Calibrate Position Measurement Device | PCNFSCH | PCNFSCH | 2 | 0 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-10-10 | 2022-11-24 | 10 | PCNFSCH | PCNFSCH | DF /B /55/DFBA-ZT-30003 | Calibrate Position Measurement Device | Unknown
2 | DFB-W03 | WDF | MTN-INST | MTN-INST | 2100075979 | DFB-03 Choke ZSO,ZSC & ZT justering | Calibrate Position Measurement Device | PCNFSCH | PCNFSCH | 3 | 18 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-10-10 | 2022-11-24 | 20 | PCNFSCH | PCNFSCH | DF /B /55/DFBA-ZT-30003 | Calibrate Position Measurement Device | Unknown
2 | DFB-W03 | WDF | MTN-INST | MTN-INST | 2100075979 | DFB-03 Choke ZSO,ZSC & ZT justering | Calibrate Position Measurement Device | PCNFSCH | PCNFSCH | 1 | 4 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-10-10 | 2022-11-24 | 25 | PCNFSCH | PCNFSCH | DF /B /55/DFBA-ZT-30003 | Calibrate Position Measurement Device | Unknown
2 | DFB-W03 | WDF | MTN-INST | PRODTECH | 2100075979 | DFB-03 Choke ZSO,ZSC & ZT justering | Calibrate Position Measurement Device | PCNFSCH | PCNFSCH | 2 | 0 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-10-10 | 2022-11-24 | 30 | PCNFSCH | PCNFSCH | DF /B /55/DFBA-ZT-30003 | Calibrate Position Measurement Device | Unknown
2 | DFB-W03 | WDF | MTN-INST | MTN-SCAF | 2100075979 | DFB-03 Choke ZSO,ZSC & ZT justering | Calibrate Position Measurement Device | PCNFSCH | PCNFSCH | 10 | 20 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-01-29 | 2024-07-15 | 2022-10-10 | 2022-11-24 | 40 | PCNFSCH | PCNFSCH | DF /B /55/DFBA-ZT-30003 | Calibrate Position Measurement Device | Unknown
2 | DFB-W03 | WDF | MTN-INST | MTN-SCAF | 2100075979 | DFB-03 Choke ZSO,ZSC & ZT justering | Calibrate Position Measurement Device | PCNFSCH | PCNFSCH | 6 | 0 | W31-W32 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-10-10 | 2022-11-24 | 50 | PCNFSCH | PCNFSCH | DF /B /55/DFBA-ZT-30003 | Calibrate Position Measurement Device | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-05 | 2024-10-05 | 2024-03-28 | 2024-08-10 | 10 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-05 | 2024-10-05 | 2024-03-28 | 2024-08-10 | 20 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-05 | 2024-10-05 | 2024-03-28 | 2024-08-10 | 30 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 3 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-05 | 2024-10-06 | 2024-03-28 | 2024-08-10 | 40 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-06 | 2024-10-06 | 2024-03-28 | 2024-08-10 | 50 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-06 | 2024-10-06 | 2024-03-28 | 2024-08-10 | 60 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-06 | 2024-10-06 | 2024-03-28 | 2024-08-10 | 70 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-06 | 2024-10-06 | 2024-03-28 | 2024-08-10 | 80 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-06 | 2024-10-06 | 2024-03-28 | 2024-08-10 | 90 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107145 | DFG NON HAZ XCV F.T.C. | Isolate XCV |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2024-03-28 | 2024-08-10 | 100 |  |  | DF /G /28/DFGA-XCV-500462 | Isolate XCV | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074852 | Heater Tripped | Fault finding/Repair HE-1256B |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2022-11-01 | 2023-03-16 | 10 |  |  | DF /F /09/DFFB-HE-1256B | Fault finding/Repair HE-1256B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074852 | Heater Tripped | Fault finding/Repair HE-1256B |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2022-11-01 | 2023-03-16 | 20 |  |  | DF /F /09/DFFB-HE-1256B | Fault finding/Repair HE-1256B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074852 | Heater Tripped | Fault finding/Repair HE-1256B |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2022-11-01 | 2023-03-16 | 30 |  |  | DF /F /09/DFFB-HE-1256B | Fault finding/Repair HE-1256B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107865 | Defect Flow trans. DFB-FT-35033 well 20 | Test FT-35031 before removing |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-04-04 | 2024-08-17 | 10 |  |  | DF /B /55/DFBA-FT-35033 | Test FT-35031 before removing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107865 | Defect Flow trans. DFB-FT-35033 well 20 | Test FT-35031 before removing |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2024-04-04 | 2024-08-17 | 20 |  |  | DF /B /55/DFBA-FT-35033 | Test FT-35031 before removing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107865 | Defect Flow trans. DFB-FT-35033 well 20 | Test FT-35031 before removing |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-04-04 | 2024-08-17 | 30 |  |  | DF /B /55/DFBA-FT-35033 | Test FT-35031 before removing | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337274 | 1Y HVAC SUPP WELD TENT CHECK DFFA-A-1203 | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2024-07-18 | 2024-08-17 | 10 | SECE | SECE | DF /F /09/DFFA-A-1203 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337274 | 1Y HVAC SUPP WELD TENT CHECK DFFA-A-1203 | PERSONAL ISOLATION | SECE | SECE | 10 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-08-17 | 20 | SECE | SECE | DF /F /09/DFFA-A-1203 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337274 | 1Y HVAC SUPP WELD TENT CHECK DFFA-A-1203 | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-08-17 | 30 | SECE | SECE | DF /F /09/DFFA-A-1203 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337274 | 1Y HVAC SUPP WELD TENT CHECK DFFA-A-1203 | PERSONAL ISOLATION | SECE | SECE | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-08-17 | 40 | SECE | SECE | DF /F /09/DFFA-A-1203 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235928 | 6M FRESH AIR FILTERS DAN F | FRESH AIR STATIONS DAN F |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-02-23 | 2023-03-20 | 10 |  |  | DF /C /07 | FRESH AIR STATIONS DAN F | Unknown
D | NOSD | WPM | MTN-MECH | MTN-INST | 2400235928 | 6M FRESH AIR FILTERS DAN F | FRESH AIR STATIONS DAN F |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-02-23 | 2023-03-20 | 12 |  |  | DF /C /07 | FRESH AIR STATIONS DAN F | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006743 | DF Removal of temp support | PO Semco |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-04-01 | 2021-05-11 | 10 |  |  | DF | PO Semco | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200006743 | DF Removal of temp support | PO Semco |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-04-01 | 2021-05-11 | 20 |  |  | DF | PO Semco | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268045 | 6M SDV LUB/MAINT HPSEP - DFG | SDV LUB/INSP HPSEP - DFG |  |  | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-07-18 | 2023-08-03 | 10 |  |  | DF /G /03/SDV-VALVES | SDV LUB/INSP HPSEP - DFG | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112079 | Defective motor DFCI-BM-12802 for conden | De-isolate |  |  | 1.5 | 0 | Empty | 2024-08-20 | 2024-08-22 | 2024-08-20 | 2024-08-20 | 2024-05-04 | 2024-06-18 | 10 |  |  | DF /C /09/DFCI-BM-12802 | De-isolate | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112079 | Defective motor DFCI-BM-12802 for conden | De-isolate |  |  | 2 | 0 | Empty | 2024-08-20 | 2024-08-22 | 2024-08-20 | 2024-08-20 | 2024-05-04 | 2024-06-18 | 20 |  |  | DF /C /09/DFCI-BM-12802 | De-isolate | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112079 | Defective motor DFCI-BM-12802 for conden | De-isolate |  |  | 2 | 0 | Empty | 2024-08-20 | 2024-08-22 | 2024-08-20 | 2024-08-21 | 2024-05-04 | 2024-06-18 | 30 |  |  | DF /C /09/DFCI-BM-12802 | De-isolate | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112079 | Defective motor DFCI-BM-12802 for conden | De-isolate |  |  | 1.5 | 0 | Empty | 2024-08-20 | 2024-08-22 | 2024-08-21 | 2024-08-21 | 2024-05-04 | 2024-06-18 | 40 |  |  | DF /C /09/DFCI-BM-12802 | De-isolate | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112079 | Defective motor DFCI-BM-12802 for conden | De-isolate |  |  | 1 | 0 | Empty | 2024-08-20 | 2024-08-22 | 2024-08-21 | 2024-08-22 | 2024-05-04 | 2024-06-18 | 50 |  |  | DF /C /09/DFCI-BM-12802 | De-isolate | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-11-12 | 2024-03-26 | 10 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2023-11-12 | 2024-03-26 | 20 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 8 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-25 | 2023-11-12 | 2024-03-26 | 30 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2023-11-12 | 2024-03-26 | 40 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-23 | 2023-11-12 | 2024-03-26 | 50 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2023-11-12 | 2024-03-26 | 60 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-23 | 2023-11-12 | 2024-03-26 | 70 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-23 | 2023-11-12 | 2024-03-26 | 80 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-11-12 | 2024-03-26 | 90 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 10 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-11-12 | 2024-03-26 | 100 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100098922 | ESDV-500108 intern leak Close drain FF | Line for extra Gaskets/bolts | SECE | SECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-11-12 | 2024-03-26 | 110 | SECE | SECE | DF /F /28/DFFA-ESDV-500108 | Line for extra Gaskets/bolts | Unknown
3 | DAN FG | WDF | MTN-ELEC | PRODTECH | 2100023221 | CMAT:Change of defect RCD units | Set isolation | AWSC | AWSC | 4 | 0 | W16 Caverion | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2019-11-22 | 2020-02-20 | 10 | AWSC | AWSC | DF /G /05/DFGA-LP-1852 | Set isolation | Unknown
3 | DAN FG | WDF | MTN-ELEC | MTN-ELEC | 2100023221 | CMAT:Change of defect RCD units | Set isolation | AWSC | AWSC | 50 | 0 | W16 Caverion | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-07 | 2019-11-22 | 2020-02-20 | 20 | AWSC | AWSC | DF /G /05/DFGA-LP-1852 | Set isolation | Unknown
3 | DAN FG | WDF | MTN-ELEC | PRODTECH | 2100023221 | CMAT:Change of defect RCD units | Set isolation | AWSC | AWSC | 3 | 0 | W16 Caverion | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2019-11-22 | 2020-02-20 | 30 | AWSC | AWSC | DF /G /05/DFGA-LP-1852 | Set isolation | Unknown
3 | DAN FG | WDF | MTN-ELEC | MTN-ELEC | 2100023221 | CMAT:Change of defect RCD units | Set isolation | AWSC | AWSC | 0 | 0 | W16 Caverion | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2019-11-22 | 2020-02-20 | 40 | AWSC | AWSC | DF /G /05/DFGA-LP-1852 | Set isolation | Unknown
3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300001081 | 4 stk. Non-IS AI flyttes til IS AI | 4 stk. Non-IS AI flyttes til IS AI |  |  | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2010-01-01 | 2030-12-31 | 10 |  |  | DF /F /04/DFFA-FP-2093 | 4 stk. Non-IS AI flyttes til IS AI | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085206 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-03-28 | 2023-08-10 | 10 |  |  | DF /C /05/DFCI-DP-1828 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085206 | Battery fault on emergency light | Change batteries |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-03-28 | 2023-08-10 | 20 |  |  | DF /C /05/DFCI-DP-1828 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085206 | Battery fault on emergency light | Change batteries |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-03-28 | 2023-08-10 | 30 |  |  | DF /C /05/DFCI-DP-1828 | Change batteries | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100042894 | DFF-HCV-530174-D Sealing face corrosion | Assist for changeout HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2021-01-08 | 2021-04-08 | 10 |  |  | DF /F /31/DFFA-HCV-530174-D | Assist for changeout HCV | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100042894 | DFF-HCV-530174-D Sealing face corrosion | Assist for changeout HCV |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2021-01-08 | 2021-04-08 | 15 |  |  | DF /F /31/DFFA-HCV-530174-D | Assist for changeout HCV | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100042894 | DFF-HCV-530174-D Sealing face corrosion | Assist for changeout HCV |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-18 | 2021-01-08 | 2021-04-08 | 20 |  |  | DF /F /31/DFFA-HCV-530174-D | Assist for changeout HCV | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100042894 | DFF-HCV-530174-D Sealing face corrosion | Assist for changeout HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2021-01-08 | 2021-04-08 | 30 |  |  | DF /F /31/DFFA-HCV-530174-D | Assist for changeout HCV | Unknown
3 | Empty | WDF | MTN-PAIN | MTN-ROPE | 2100098021 | FFSR Temp Repair to DFB16" 9021 | PO EMS |  |  | 0 | 0 | Empty | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2024-11-15 | 10 |  |  | DF /B /12/DFB-16-PHS-033-9021-BD-U | PO EMS | Unknown
3 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100098021 | FFSR Temp Repair to DFB16" 9021 | PO EMS |  |  | 0 | 0 | Empty | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2023-10-03 | 2024-11-15 | 20 |  |  | DF /B /12/DFB-16-PHS-033-9021-BD-U | PO EMS | Unknown
B | NOSD | WPM | MTN-INST | MTN-TELE | 2400329522 | 1Y LINE-OF-SIGHT-RADIO-SYSTEM TEST- DFC | LINE-OF-SIGHT-RADIO-SYSTEM TEST- DFC |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-12 | 2024-06-11 | 10 |  |  | DF /C /08/LOS-RADIO-WITH-ANTENNA | LINE-OF-SIGHT-RADIO-SYSTEM TEST- DFC | Unknown
3 | NOSD | WGN | MTN-SCAF | WELLSUPV | 2200006766 | scaffold assits FORCE 21737 | Build scaffolding DFF lev 1 | PCNF | PCNF | 24 | 0 | Empty | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2021-04-07 | 2021-05-17 | 10 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Build scaffolding DFF lev 1 | Unknown
3 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200006766 | scaffold assits FORCE 21737 | Build scaffolding DFF lev 1 | PCNF | PCNF | 10 | 20 | Empty | 2024-03-15 | 2024-03-16 | 2021-03-20 | 2021-03-25 | 2021-04-07 | 2021-05-17 | 20 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Build scaffolding DFF lev 1 | Unknown
3 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200006766 | scaffold assits FORCE 21737 | Build scaffolding DFF lev 1 | PCNF | PCNF | 6 | 4 | Empty | 2024-03-15 | 2024-03-16 | 2021-03-25 | 2021-06-24 | 2021-04-07 | 2021-05-17 | 30 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Build scaffolding DFF lev 1 | Unknown
3 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200006766 | scaffold assits FORCE 21737 | Build scaffolding DFF lev 1 | PCNF | PCNF | 12 | 7 | Empty | 2024-03-15 | 2024-03-16 | 2021-03-23 | 2021-03-25 | 2021-04-07 | 2021-05-17 | 40 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Build scaffolding DFF lev 1 | Unknown
3 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200006766 | scaffold assits FORCE 21737 | Build scaffolding DFF lev 1 | PCNF | PCNF | 8 | 8 | Empty | 2024-03-15 | 2024-03-16 | 2021-03-25 | 2021-09-05 | 2021-04-07 | 2021-05-17 | 50 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Build scaffolding DFF lev 1 | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-24 | 2016-06-08 | 2016-07-18 | 10 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 1.3000000000000000444089209845 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 12 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 2.7000000000000001776356839392 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 15 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 20 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 6.700000000000000177635683938 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-23 | 2016-06-08 | 2016-07-18 | 30 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 13.400000000000000355271367876 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-23 | 2016-06-08 | 2016-07-18 | 40 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2024-08-23 | 2016-06-08 | 2016-07-18 | 50 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-23 | 2016-06-08 | 2016-07-18 | 60 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 0.6999999999999999555910790147 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 70 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027948 | Check valve replacement | Replacement of the check valve | AWSC | AWSC | 1.3000000000000000444089209845 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 80 | AWSC | AWSC | DF /A /12 | Replacement of the check valve | Unknown
B | NE | WPM | MTN-MECH | PRODTECH | 2400291804 | 1Y CHOKE VALVES/INSTR MAINT - DFF | DE-ISOLATION BY PRODUCTION |  |  | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-08-26 | 2024-09-02 | 2023-11-15 | 2023-12-15 | 10 |  |  | DF /F /10/INSTRUMENTS | DE-ISOLATION BY PRODUCTION | Unknown
B | NE | WPM | MTN-MECH | MTN-MECH | 2400291804 | 1Y CHOKE VALVES/INSTR MAINT - DFF | DE-ISOLATION BY PRODUCTION |  |  | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-09-02 | 2024-09-09 | 2023-11-15 | 2023-12-15 | 20 |  |  | DF /F /10/INSTRUMENTS | DE-ISOLATION BY PRODUCTION | Unknown
B | NE | WPM | MTN-MECH | MTN-INST | 2400291804 | 1Y CHOKE VALVES/INSTR MAINT - DFF | DE-ISOLATION BY PRODUCTION |  |  | 14 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-09-09 | 2024-09-12 | 2023-11-15 | 2023-12-15 | 30 |  |  | DF /F /10/INSTRUMENTS | DE-ISOLATION BY PRODUCTION | Unknown
B | NE | WPM | MTN-MECH | PRODTECH | 2400291804 | 1Y CHOKE VALVES/INSTR MAINT - DFF | DE-ISOLATION BY PRODUCTION |  |  | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-09-12 | 2024-09-19 | 2023-11-15 | 2023-12-15 | 40 |  |  | DF /F /10/INSTRUMENTS | DE-ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344335 | 3Y POT WATER TANK/ PUMP MAINT DFCM-A-102 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-07-28 | 2024-09-28 | 10 | SECE | SECE | DF /C /85/DFCM-A-1028 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344335 | 3Y POT WATER TANK/ PUMP MAINT DFCM-A-102 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 3 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-13 | 2024-07-28 | 2024-09-28 | 20 | SECE | SECE | DF /C /85/DFCM-A-1028 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344335 | 3Y POT WATER TANK/ PUMP MAINT DFCM-A-102 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 4 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-15 | 2024-07-28 | 2024-09-28 | 30 | SECE | SECE | DF /C /85/DFCM-A-1028 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344335 | 3Y POT WATER TANK/ PUMP MAINT DFCM-A-102 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 5 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-07-28 | 2024-09-28 | 40 | SECE | SECE | DF /C /85/DFCM-A-1028 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344335 | 3Y POT WATER TANK/ PUMP MAINT DFCM-A-102 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-07-28 | 2024-09-28 | 50 | SECE | SECE | DF /C /85/DFCM-A-1028 | ISOLATION BY PRODUCTION | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-SCAF | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 10 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | PRODTECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 20 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-RIGG | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 30 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 40 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 50 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | PRODTECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 60 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-SCAF | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 70 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | PRODTECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 80 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-RIGG | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 90 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 100 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 110 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
4 | DFC-5037 | WDF | MTN-MECH | PRODTECH | 2100053943 | HCV for LT kan ikke betjenes | Isolate lower HCV |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-10 | 2022-04-09 | 120 |  |  | DF /C /27/SYSTEM-27-MANUAL-VALVES | Isolate lower HCV | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | WELLSUPV | 2100049476 | ANOP Rejected Spools PSV-530164 | Order materials. |  |  | 0 | 0 | Empty | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2021-05-09 | 2021-06-18 | 10 |  |  | DF /F /31/DFFA-E-4301 | Order materials. | Unknown
3 | DFF-IPHP | WDF | MTN-MECH | VEN-MECH | 2100049476 | ANOP Rejected Spools PSV-530164 | Order materials. |  |  | 0 | 0 | Empty | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2021-05-09 | 2021-06-18 | 20 |  |  | DF /F /31/DFFA-E-4301 | Order materials. | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018137 | Replace Feeder protection 1841-M114 | Exchange of protection relay |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M114-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018137 | Replace Feeder protection 1841-M114 | Exchange of protection relay |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M114-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018137 | Replace Feeder protection 1841-M114 | Exchange of protection relay |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M114-02 | Exchange of protection relay | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018137 | Replace Feeder protection 1841-M114 | Exchange of protection relay |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M114-02 | Exchange of protection relay | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241884 | 6M BREATH. AIR COMP. CLEAN - A-5405/5406 | BREATH. AIR COMP. CLEAN - A-5405/5406 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-05 | 2023-04-24 | 10 |  |  | DF /G /02/DFGA-A-5405 | BREATH. AIR COMP. CLEAN - A-5405/5406 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058468 | Replace DFF workshop fan in toilet | Replace ventilator |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-04 | 2022-03-04 | 10 |  |  | DF /F /09 | Replace ventilator | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058468 | Replace DFF workshop fan in toilet | Replace ventilator |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-04 | 2022-03-04 | 20 |  |  | DF /F /09 | Replace ventilator | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058468 | Replace DFF workshop fan in toilet | Replace ventilator |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-12-04 | 2022-03-04 | 30 |  |  | DF /F /09 | Replace ventilator | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258810 | 1Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 38 | 0 | W33 - DK40-M-7171 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258810 | 1Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | W33 - DK40-M-7171 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258810 | 1Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | W33 - DK40-M-7171 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROPE | 2400258810 | 1Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 8 | 8 | W33 - DK40-M-7171 | 2024-06-17 | 2024-06-17 | 2023-11-22 | 2023-11-29 | 2023-05-02 | 2023-06-01 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100098773 | Actuator malfunction | Production isolation |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-09-26 | 2023-11-10 | 10 |  |  | DF /F /20/DFFA-XCV-340566 | Production isolation | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098773 | Actuator malfunction | Production isolation |  |  | 8 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-09-26 | 2023-11-10 | 20 |  |  | DF /F /20/DFFA-XCV-340566 | Production isolation | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100098773 | Actuator malfunction | Production isolation |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-09-26 | 2023-11-10 | 30 |  |  | DF /F /20/DFFA-XCV-340566 | Production isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095202 | flex hose on supply to hose reel leaking | Deisolate, Check func and for leaks | SECE | SECE | 2 | 0 | W15-W16 | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-09-12 | 2024-01-25 | 10 | SECE | SECE | DF /F /01/DFFB-HRF-0396 | Deisolate, Check func and for leaks | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095202 | flex hose on supply to hose reel leaking | Deisolate, Check func and for leaks | SECE | SECE | 3 | 0 | W15-W16 | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2023-09-12 | 2024-01-25 | 20 | SECE | SECE | DF /F /01/DFFB-HRF-0396 | Deisolate, Check func and for leaks | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095202 | flex hose on supply to hose reel leaking | Deisolate, Check func and for leaks | SECE | SECE | 2 | 0 | W15-W16 | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2023-09-12 | 2024-01-25 | 30 | SECE | SECE | DF /F /01/DFFB-HRF-0396 | Deisolate, Check func and for leaks | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284284 | PSV Exchange - DFFB-PSV-358017 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /54/DFFB-PSV-358017 | Prod Assist (breaking containment) | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284284 | PSV Exchange - DFFB-PSV-358017 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /54/DFFB-PSV-358017 | Prod Assist (breaking containment) | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284284 | PSV Exchange - DFFB-PSV-358017 | Prod Assist (breaking containment) | AWSC | AWSC | 5 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-06 | 2024-10-07 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /54/DFFB-PSV-358017 | Prod Assist (breaking containment) | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284284 | PSV Exchange - DFFB-PSV-358017 | Prod Assist (breaking containment) | AWSC | AWSC | 4 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-07 | 2024-10-07 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /54/DFFB-PSV-358017 | Prod Assist (breaking containment) | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284284 | PSV Exchange - DFFB-PSV-358017 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-07 | 2024-10-08 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /54/DFFB-PSV-358017 | Prod Assist (breaking containment) | Unknown
A | DFF-3580 | WPM | MTN-MECH | VEN-INSP | 2400284284 | PSV Exchange - DFFB-PSV-358017 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /54/DFFB-PSV-358017 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400337281 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-5 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 27 | 0 | Empty | 2024-06-13 | 2024-06-14 | 2024-06-13 | 2024-06-14 | 2024-06-13 | 2024-08-14 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-5 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100047985 | DFGA-PD-3960 intern læk | Isolate PD-3960 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-07-31 | 2021-04-13 | 2021-05-23 | 20 |  |  | DF /G /75/DFGA-PD-3960 | Isolate PD-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047985 | DFGA-PD-3960 intern læk | Isolate PD-3960 |  |  | 20 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-31 | 2024-08-05 | 2021-04-13 | 2021-05-23 | 30 |  |  | DF /G /75/DFGA-PD-3960 | Isolate PD-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100047985 | DFGA-PD-3960 intern læk | Isolate PD-3960 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-05 | 2024-08-06 | 2021-04-13 | 2021-05-23 | 40 |  |  | DF /G /75/DFGA-PD-3960 | Isolate PD-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097391 | Radiator cap defective. | Replace radiator cap. FLM |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-19 | 2024-03-02 | 10 |  |  | DF /G /05/DFGA-E-1740 | Replace radiator cap. FLM | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097391 | Radiator cap defective. | Replace radiator cap. FLM |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-19 | 2024-03-02 | 20 |  |  | DF /G /05/DFGA-E-1740 | Replace radiator cap. FLM | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-24 | 2016-06-08 | 2016-07-18 | 10 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 2.7000000000000001776356839392 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 20 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 2.7000000000000001776356839392 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 25 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 30 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-23 | 2016-06-08 | 2016-07-18 | 40 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-23 | 2016-06-08 | 2016-07-18 | 45 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2024-08-24 | 2016-06-08 | 2016-07-18 | 48 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2024-08-24 | 2016-06-08 | 2016-07-18 | 50 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2016-06-08 | 2016-07-18 | 60 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-24 | 2016-06-08 | 2016-07-18 | 70 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 2.7000000000000001776356839392 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 80 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027732 | Replacement of HCV-380032 w. EP-3803 | Safing of the HCV | AWSC | AWSC | 2.7000000000000001776356839392 | 0 | Moved to 2022 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 90 | AWSC | AWSC | DF /A /12/DFAA-HCV-380032 | Safing of the HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025078 | Replacement of B&B valve and indicator P | L3 Isolate PDI 360011 according to PID. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2019-01-02 | 2019-04-02 | 10 |  |  | DF /F /21/DFFA-HCV-360082 | L3 Isolate PDI 360011 according to PID. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025078 | Replacement of B&B valve and indicator P | L3 Isolate PDI 360011 according to PID. |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2019-01-02 | 2019-04-02 | 20 |  |  | DF /F /21/DFFA-HCV-360082 | L3 Isolate PDI 360011 according to PID. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025078 | Replacement of B&B valve and indicator P | L3 Isolate PDI 360011 according to PID. |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2019-01-02 | 2019-04-02 | 30 |  |  | DF /F /21/DFFA-HCV-360082 | L3 Isolate PDI 360011 according to PID. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025078 | Replacement of B&B valve and indicator P | L3 Isolate PDI 360011 according to PID. |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2019-01-02 | 2019-04-02 | 40 |  |  | DF /F /21/DFFA-HCV-360082 | L3 Isolate PDI 360011 according to PID. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025078 | Replacement of B&B valve and indicator P | L3 Isolate PDI 360011 according to PID. |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2019-01-02 | 2019-04-02 | 50 |  |  | DF /F /21/DFFA-HCV-360082 | L3 Isolate PDI 360011 according to PID. | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300006996 | DO NOT USE - Replaced by 2300007898 | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2026-10-17 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344336 | 6M SW FILTERS & BLOWERS MAINT - DFB | SW FILTERS & BLOWERS MAINT - DFB |  |  | 1 | 0 | Empty | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-26 | 10 |  |  | DF /B /51/DFBA-FT-3505 | SW FILTERS & BLOWERS MAINT - DFB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344336 | 6M SW FILTERS & BLOWERS MAINT - DFB | SW FILTERS & BLOWERS MAINT - DFB |  |  | 1 | 0 | Empty | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-26 | 20 |  |  | DF /B /51/DFBA-FT-3505 | SW FILTERS & BLOWERS MAINT - DFB | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022390 | Replacement of accumulator ACC-590414 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2019-09-12 | 2020-09-06 | 10 |  |  | DF /G /07/DFGA-ACC-590414 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022390 | Replacement of accumulator ACC-590414 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2019-09-12 | 2020-09-06 | 20 |  |  | DF /G /07/DFGA-ACC-590414 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022390 | Replacement of accumulator ACC-590414 | L3 Prepare rigging equipment |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2019-09-12 | 2020-09-06 | 30 |  |  | DF /G /07/DFGA-ACC-590414 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022390 | Replacement of accumulator ACC-590414 | L3 Prepare rigging equipment |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2019-09-12 | 2020-09-06 | 40 |  |  | DF /G /07/DFGA-ACC-590414 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022390 | Replacement of accumulator ACC-590414 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2019-09-12 | 2020-09-06 | 50 |  |  | DF /G /07/DFGA-ACC-590414 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022390 | Replacement of accumulator ACC-590414 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2019-09-12 | 2020-09-06 | 60 |  |  | DF /G /07/DFGA-ACC-590414 | L3 Prepare rigging equipment | Unknown
A | DFG-3590 | WPM | MTN-MECH | PRODTECH | 2400215987 | 2Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 2 | 0 | W17-W18 | 2024-05-27 | 2024-05-30 | 2024-05-27 | 2024-05-27 | 2022-10-14 | 2022-11-29 | 10 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-ELEC | 2400215987 | 2Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 5 | 0 | W17-W18 | 2024-05-27 | 2024-05-30 | 2024-05-27 | 2024-05-28 | 2022-10-14 | 2022-11-29 | 20 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-MECH | 2400215987 | 2Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 4 | 0 | W17-W18 | 2024-05-27 | 2024-05-30 | 2024-05-28 | 2024-05-29 | 2022-10-14 | 2022-11-29 | 30 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-INST | 2400215987 | 2Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 2.5 | 0 | W17-W18 | 2024-05-27 | 2024-05-30 | 2024-05-29 | 2024-05-30 | 2022-10-14 | 2022-11-29 | 40 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | PRODTECH | 2400215987 | 2Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 2 | 0 | W17-W18 | 2024-05-27 | 2024-05-30 | 2024-05-30 | 2024-05-30 | 2022-10-14 | 2022-11-29 | 50 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259305 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-05-09 | 2023-06-14 | 10 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259305 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-05-09 | 2023-06-14 | 20 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400259305 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2023-05-09 | 2023-06-14 | 30 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259305 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-05-09 | 2023-06-14 | 40 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259305 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-05-09 | 2023-06-14 | 50 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400330009 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-24 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 36 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-04-24 | 2024-06-25 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-24 | ATEX EQUIPMENT INSPECTION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322646 | 1Y HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 | HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-03-29 | 2024-05-15 | 10 |  |  | DF /C /09/DFCC-BM-1255 | HVAC SUPP ACC CONT CHECK-DFCC-BM-1255 | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-05-20 | 2024-05-20 | 2020-09-09 | 2020-12-08 | 10 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-05-20 | 2024-05-20 | 2020-09-09 | 2020-12-08 | 20 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 100 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-05-20 | 2024-05-29 | 2020-09-09 | 2020-12-08 | 30 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 100 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-05-29 | 2024-06-06 | 2020-09-09 | 2020-12-08 | 40 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 100 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-06 | 2024-06-11 | 2020-09-09 | 2020-12-08 | 50 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 100 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-11 | 2024-06-16 | 2020-09-09 | 2020-12-08 | 55 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 50 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-16 | 2024-06-21 | 2020-09-09 | 2020-12-08 | 60 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-21 | 2024-06-21 | 2020-09-09 | 2020-12-08 | 70 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 8 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-21 | 2024-06-22 | 2020-09-09 | 2020-12-08 | 80 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 8 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-22 | 2024-06-24 | 2020-09-09 | 2020-12-08 | 90 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100036667 | DFCI/78: Replace corroded wire sheaves b | Replace wiresheaves in A-frame |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-07-22 | 2024-06-24 | 2024-06-24 | 2020-09-09 | 2020-12-08 | 100 |  |  | DF /C /78/DFCI-X-6101 | Replace wiresheaves in A-frame | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-30 | 2019-02-06 | 2019-05-07 | 10 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-07-30 | 2019-02-06 | 2019-05-07 | 20 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-07-31 | 2019-02-06 | 2019-05-07 | 30 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-31 | 2024-08-01 | 2019-02-06 | 2019-05-07 | 40 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-02 | 2019-02-06 | 2019-05-07 | 50 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-02 | 2019-02-06 | 2019-05-07 | 60 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-03 | 2019-02-06 | 2019-05-07 | 70 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-03 | 2019-02-06 | 2019-05-07 | 80 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-04 | 2019-02-06 | 2019-05-07 | 90 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-04 | 2019-02-06 | 2019-05-07 | 100 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 9 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-07 | 2019-02-06 | 2019-05-07 | 110 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2019-02-06 | 2019-05-07 | 120 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2019-02-06 | 2019-05-07 | 130 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025323 | CMAT:Changeout PM-3959 + A&B pumps | L3 Prepare hoisting device |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2019-02-06 | 2019-05-07 | 140 |  |  | DF /F /75/DFFA-A-3957 | L3 Prepare hoisting device | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100111617 | DFG-GD-134504 defekt | Inhibit & replace DFG-GD-134504 | SCHSECE | SCHSECE | 8 | 8 | W19-W20 | 2024-05-09 | 2024-05-11 | 2024-05-09 | 2024-05-11 | 2024-06-11 | 2024-10-24 | 10 | SCHSECE | SCHSECE | DF /G /03/DFGA-GD-134504 | Inhibit & replace DFG-GD-134504 | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100111617 | DFG-GD-134504 defekt | Inhibit & replace DFG-GD-134504 | SCHSECE | SCHSECE | 5 | 5 | W19-W20 | 2024-05-09 | 2024-05-11 | 2024-05-09 | 2024-05-11 | 2024-06-11 | 2024-10-24 | 20 | SCHSECE | SCHSECE | DF /G /03/DFGA-GD-134504 | Inhibit & replace DFG-GD-134504 | Unknown
A | DFG-1640 | WPM | MTN-MECH | PRODTECH | 2400321373 | 8KH SDV/BDV MAINT, COUNTER-A-1640 | DE-ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-04-08 | 2024-05-08 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /G /60/DFGA-A-1640 | DE-ISOLATION BY PRODUCTION | Unknown
A | DFG-1640 | WPM | MTN-MECH | MTN-MECH | 2400321373 | 8KH SDV/BDV MAINT, COUNTER-A-1640 | DE-ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 6 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-18 | 2024-04-08 | 2024-05-08 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /G /60/DFGA-A-1640 | DE-ISOLATION BY PRODUCTION | Unknown
A | DFG-1640 | WPM | MTN-MECH | PRODTECH | 2400321373 | 8KH SDV/BDV MAINT, COUNTER-A-1640 | DE-ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-04-08 | 2024-05-08 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /G /60/DFGA-A-1640 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259292 | 3M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-06-08 | 2023-06-18 | 10 |  |  | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337269 | 6M METH INJ PUMP SKID MAINT-DFFA-A-4600 | METH INJ PUMP SKID MAINT-DFFA-A-4600 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-26 | 2024-08-14 | 10 |  |  | DF /F /75/DFFA-A-4600 | METH INJ PUMP SKID MAINT-DFFA-A-4600 | Unknown
3 | DFX-OIL | WDF | MTN-INST | PRODTECH | 2100094013 | DFA-22 flowline ESD pressure trans fault | operation_description_not_present | SECE | SECE | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-15 | 2023-12-28 | 10 | SECE | SECE | DF /A /10/DFAA-PT-30574 | operation_description_not_present | Unknown
3 | DFX-OIL | WDF | MTN-INST | MTN-INST | 2100094013 | DFA-22 flowline ESD pressure trans fault | operation_description_not_present | SECE | SECE | 1.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-15 | 2023-12-28 | 20 | SECE | SECE | DF /A /10/DFAA-PT-30574 | operation_description_not_present | Unknown
3 | DFX-OIL | WDF | MTN-INST | MTN-INST | 2100094013 | DFA-22 flowline ESD pressure trans fault | operation_description_not_present | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-15 | 2023-12-28 | 30 | SECE | SECE | DF /A /10/DFAA-PT-30574 | operation_description_not_present | Unknown
3 | DFX-OIL | WDF | MTN-INST | MTN-INST | 2100094013 | DFA-22 flowline ESD pressure trans fault | operation_description_not_present | SECE | SECE | 1.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-08-15 | 2023-12-28 | 40 | SECE | SECE | DF /A /10/DFAA-PT-30574 | operation_description_not_present | Unknown
3 | DFX-OIL | WDF | MTN-INST | PRODTECH | 2100094013 | DFA-22 flowline ESD pressure trans fault | operation_description_not_present | SECE | SECE | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-08-15 | 2023-12-28 | 50 | SECE | SECE | DF /A /10/DFAA-PT-30574 | operation_description_not_present | Unknown
3 | DFX-OIL | WDF | MTN-INST | MTN-INST | 2100094013 | DFA-22 flowline ESD pressure trans fault | operation_description_not_present | SECE | SECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-15 | 2023-12-28 | 60 | SECE | SECE | DF /A /10/DFAA-PT-30574 | operation_description_not_present | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100047990 | Bleed Valve upstream DFCI-PSV-34002 defe | Outcome from findings | PCNF | PCNF | 3 | 4 | W23-24 Sece Mech | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-04-23 | 2021-07-22 | 10 | PCNF | PCNF | DF /C /11/DFCI-PSV-34002 | Outcome from findings | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100047990 | Bleed Valve upstream DFCI-PSV-34002 defe | Outcome from findings | PCNF | PCNF | 1 | 4 | W23-24 Sece Mech | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-04-23 | 2021-07-22 | 20 | PCNF | PCNF | DF /C /11/DFCI-PSV-34002 | Outcome from findings | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339100 | DFC_1Y_60500 INT STRUCT INSP - GVI | DFC_1Y_60500 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_60500 (ACCOMMODATION L4) | DFC_1Y_60500 INT STRUCT INSP - GVI | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094784 | DFFW/78 No light inside piedestal. | Faultfinding and replace light bulbs |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-07-12 | 2023-08-26 | 10 |  |  | DF /F /78/DFFA-A-6102 | Faultfinding and replace light bulbs | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094784 | DFFW/78 No light inside piedestal. | Faultfinding and replace light bulbs |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-07-12 | 2023-08-26 | 20 |  |  | DF /F /78/DFFA-A-6102 | Faultfinding and replace light bulbs | Unknown
3 | Empty | WRO | VEN-INST | VEN-INST | 2300006948 | Firmware upgrade Dan ESD RTU's | Telecom support | SCH | SCH | 0 | 0 | W47-48 | 2023-11-20 | 2023-12-04 | 2023-11-20 | 2023-11-20 | 2023-12-09 | 2024-04-22 | 10 | SCH | SCH | DF /F /03/DFFA-FP-0223 | Telecom support | Unknown
3 | Empty | WRO | VEN-INST | VEN-INST | 2300006948 | Firmware upgrade Dan ESD RTU's | Telecom support | SCH | SCH | 80 | 64 | W47-48 | 2023-11-20 | 2023-12-04 | 2023-11-20 | 2023-11-28 | 2023-12-09 | 2024-04-22 | 20 | SCH | SCH | DF /F /03/DFFA-FP-0223 | Telecom support | Unknown
3 | Empty | WRO | VEN-INST | MTN-TELE | 2300006948 | Firmware upgrade Dan ESD RTU's | Telecom support | SCH | SCH | 25 | 67 | W47-48 | 2023-11-20 | 2023-12-04 | 2023-11-28 | 2023-12-04 | 2023-12-09 | 2024-04-22 | 30 | SCH | SCH | DF /F /03/DFFA-FP-0223 | Telecom support | Unknown
A | DFG-3590 | WPM | MTN-TURB | MTN-TURB | 2400315919 | 2,5KH TURBINE WASH DFGA-A-3590 COUNTER | TURBINE WASH DFGA-A-3590 COUNTER | AWSCSCHSECE | AWSCSCHSECE | 12 | 0 | W25-W26 | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-23 | 2024-04-07 | 2024-04-23 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /G /54/DFGA-A-3590 | TURBINE WASH DFGA-A-3590 COUNTER | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059890 | Heat trace circut 53 failed DP-1855 | Set personal isolation |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-03-24 | 2022-11-19 | 10 |  |  | DF /G /61/DFGA-DP-1855-53 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059890 | Heat trace circut 53 failed DP-1855 | Set personal isolation |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-03-24 | 2022-11-19 | 20 |  |  | DF /G /61/DFGA-DP-1855-53 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059890 | Heat trace circut 53 failed DP-1855 | Set personal isolation |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-03-24 | 2022-11-19 | 30 |  |  | DF /G /61/DFGA-DP-1855-53 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100045743 | DFG clarify interface test options | Clarify design of drip rings |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-06 | 2021-06-04 | 10 |  |  | DF /G /27/DFGA-LIT-340610 | Clarify design of drip rings | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100045743 | DFG clarify interface test options | Clarify design of drip rings |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-06 | 2021-06-04 | 20 |  |  | DF /G /27/DFGA-LIT-340610 | Clarify design of drip rings | Unknown
A | NOSD | WPM | MTN-CRAN | PRODTECH | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 2 | 3 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-03 | 2024-07-03 | 2024-05-08 | 2024-06-07 | 10 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 60 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-03 | 2024-07-10 | 2024-05-08 | 2024-06-07 | 20 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 18 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-11 | 2024-07-15 | 2024-05-08 | 2024-06-07 | 25 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 8 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-15 | 2024-07-17 | 2024-05-08 | 2024-06-07 | 30 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-TELE | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 3 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-17 | 2024-07-18 | 2024-05-08 | 2024-06-07 | 50 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | PRODTECH | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-18 | 2024-07-18 | 2024-05-08 | 2024-06-07 | 60 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 16 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-18 | 2024-07-20 | 2024-05-08 | 2024-06-07 | 70 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 16 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-20 | 2024-07-22 | 2024-05-08 | 2024-06-07 | 80 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 3 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-22 | 2024-07-23 | 2024-05-08 | 2024-06-07 | 85 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 24 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-23 | 2024-07-29 | 2024-05-08 | 2024-06-07 | 90 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 12 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-07-29 | 2024-08-01 | 2024-05-08 | 2024-06-07 | 100 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 16 | 5 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-08-01 | 2024-08-05 | 2024-05-08 | 2024-06-07 | 110 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400308977 | 1Y PED CRANE CHECK VENDOR-DFCI-X-6101 | Assist crane vendor | AWSC | AWSC | 0 | 0 | W27-W28 | 2024-07-03 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2024-05-08 | 2024-06-07 | 120 | AWSC | AWSC | DF /C /78/DFCI-X-6101 | Assist crane vendor | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 0 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-01 | 2025-02-01 | 2020-11-21 | 2021-02-19 | 10 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 480 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-01 | 2025-02-18 | 2020-11-21 | 2021-02-19 | 20 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ACCO | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 36 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-18 | 2025-02-21 | 2020-11-21 | 2021-02-19 | 30 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-SCAF | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 0 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2020-11-21 | 2021-02-19 | 40 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 0 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2020-11-21 | 2021-02-19 | 50 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 0 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2020-11-21 | 2021-02-19 | 60 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 0 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2020-11-21 | 2021-02-19 | 70 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200005653 | DFC Water Damage Cabins Level 4 & 2 | Vendor EL scop |  |  | 0 | 0 | W39 IOP 6-29/9 | 2025-02-01 | 2025-02-21 | 2025-02-21 | 2025-02-21 | 2020-11-21 | 2021-02-19 | 80 |  |  | DF /C /82 | Vendor EL scop | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095434 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2023-09-07 | 2024-01-20 | 10 |  |  | DF /G /05/DFGA-LP-1852 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095434 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2023-09-07 | 2024-01-20 | 20 |  |  | DF /G /05/DFGA-LP-1852 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095434 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 10 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-15 | 2023-09-07 | 2024-01-20 | 30 |  |  | DF /G /05/DFGA-LP-1852 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095434 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2023-09-07 | 2024-01-20 | 40 |  |  | DF /G /05/DFGA-LP-1852 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095434 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2023-09-07 | 2024-01-20 | 50 |  |  | DF /G /05/DFGA-LP-1852 | Isolate Equipment. | Unknown
3 | DFF-O02 | WDF | MTN-MECH | PRODTECH | 2100029431 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3102 | Safing of hydraulic drawer | AWSCSCH | AWSCSCH | 2 | 0 | W19-W20 | 2024-05-09 | 2024-05-12 | 2024-05-09 | 2024-05-09 | 2020-03-22 | 2020-05-01 | 10 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3102 | Safing of hydraulic drawer | Unknown
3 | DFF-O02 | WDF | MTN-MECH | MTN-MECH | 2100029431 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3102 | Safing of hydraulic drawer | AWSCSCH | AWSCSCH | 6 | 0 | W19-W20 | 2024-05-09 | 2024-05-12 | 2024-05-09 | 2024-05-10 | 2020-03-22 | 2020-05-01 | 20 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3102 | Safing of hydraulic drawer | Unknown
3 | DFF-O02 | WDF | MTN-MECH | MTN-MECH | 2100029431 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3102 | Safing of hydraulic drawer | AWSCSCH | AWSCSCH | 6 | 0 | W19-W20 | 2024-05-09 | 2024-05-12 | 2024-05-10 | 2024-05-11 | 2020-03-22 | 2020-05-01 | 25 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3102 | Safing of hydraulic drawer | Unknown
3 | DFF-O02 | WDF | MTN-MECH | PRODTECH | 2100029431 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3102 | Safing of hydraulic drawer | AWSCSCH | AWSCSCH | 2 | 0 | W19-W20 | 2024-05-09 | 2024-05-12 | 2024-05-11 | 2024-05-12 | 2020-03-22 | 2020-05-01 | 30 | AWSCSCH | AWSCSCH | DF /F /07/DFFA-FP-3102 | Safing of hydraulic drawer | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343679 | 6M BDV LUB/MAINT - DFC | BDV LUB/INSP - DFC |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2024-08-30 | 2024-09-15 | 10 |  |  | DF /C /27/BDV | BDV LUB/INSP - DFC | Unknown
3 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 2 | 2 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-03 | 2023-04-29 | 2023-09-11 | 10 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-TURB | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 1.5 | 2 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-03 | 2023-04-29 | 2023-09-11 | 20 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-RIGG | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 2.5 | 2.5 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-03 | 2024-07-04 | 2023-04-29 | 2023-09-11 | 30 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-RIGG | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 2.5 | 2.5 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-04 | 2024-07-05 | 2023-04-29 | 2023-09-11 | 40 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-TURB | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 1.5 | 2 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-05 | 2024-07-05 | 2023-04-29 | 2023-09-11 | 50 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 2 | 2 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-05 | 2024-07-05 | 2023-04-29 | 2023-09-11 | 60 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
3 | DFF-3580 | WDF | MTN-MECH | MTN-TURB | 2100087401 | Mechanical pump leaks oil to turbine oil | Isolation & safing of DFFB-A-3580 |  |  | 1 | 1 | W27-W28 | 2024-07-03 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2023-04-29 | 2023-09-11 | 70 |  |  | DF /F /54/DFFB-GEA-3580 | Isolation & safing of DFFB-A-3580 | Unknown
D | NOSD | WPM | MTN-INST | MTN-ELEC | 2400284144 | 1Y WORKSHOP TOOLS CHECK - DFC | WORKSHOP TOOLS CHECK - DFC | SCH | SCH | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-09-14 | 2023-10-31 | 10 | SCH | SCH | DF /C /84/WORKSHOP-EQUIPMENT | WORKSHOP TOOLS CHECK - DFC | Unknown
4 | DFB-3550 | WDF | MTN-INST | PRODTECH | 2100070245 | DFBA-SOV-35898 is about to rust away | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 10 | SECE | SECE | DF /B /54/DFBA-ESDV-35898 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3550 | WDF | MTN-INST | MTN-INST | 2100070245 | DFBA-SOV-35898 is about to rust away | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 20 | SECE | SECE | DF /B /54/DFBA-ESDV-35898 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3550 | WDF | MTN-INST | MTN-INST | 2100070245 | DFBA-SOV-35898 is about to rust away | Isolate solenoid valve (SDV) | SECE | SECE | 2 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-12-18 | 2025-06-05 | 30 | SECE | SECE | DF /B /54/DFBA-ESDV-35898 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3550 | WDF | MTN-INST | MTN-INST | 2100070245 | DFBA-SOV-35898 is about to rust away | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 40 | SECE | SECE | DF /B /54/DFBA-ESDV-35898 | Isolate solenoid valve (SDV) | Unknown
4 | DFB-3550 | WDF | MTN-INST | PRODTECH | 2100070245 | DFBA-SOV-35898 is about to rust away | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 50 | SECE | SECE | DF /B /54/DFBA-ESDV-35898 | Isolate solenoid valve (SDV) | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006473 | Contingency valves for Dan PVI Campaign | Additional materials |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-22 | 2021-04-03 | 10 |  |  | DF /F /20/SYSTEM-20-MANUAL-VALVES | Additional materials | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006473 | Contingency valves for Dan PVI Campaign | Additional materials |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-22 | 2021-04-03 | 20 |  |  | DF /F /20/SYSTEM-20-MANUAL-VALVES | Additional materials | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006473 | Contingency valves for Dan PVI Campaign | Additional materials |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-22 | 2021-04-03 | 30 |  |  | DF /F /20/SYSTEM-20-MANUAL-VALVES | Additional materials | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006473 | Contingency valves for Dan PVI Campaign | Additional materials |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-22 | 2021-04-03 | 40 |  |  | DF /F /20/SYSTEM-20-MANUAL-VALVES | Additional materials | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200006473 | Contingency valves for Dan PVI Campaign | Additional materials |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-22 | 2021-04-03 | 50 |  |  | DF /F /20/SYSTEM-20-MANUAL-VALVES | Additional materials | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100053195 | DFF-14 Scada THP transmitter faulty | DFF-14 Scada THP transmitter faulty |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-08-14 | 2021-09-23 | 10 |  |  | DF /F /55/DFFA-PIT-300514 | DFF-14 Scada THP transmitter faulty | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100053195 | DFF-14 Scada THP transmitter faulty | DFF-14 Scada THP transmitter faulty |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2021-08-14 | 2021-09-23 | 20 |  |  | DF /F /55/DFFA-PIT-300514 | DFF-14 Scada THP transmitter faulty | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-02-12 | 2020-05-12 | 5 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-02-12 | 2020-05-12 | 10 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 15 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 20 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 30 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-02-12 | 2020-05-12 | 40 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 50 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025199 | DFGA-LG-410001 changeout of LG and HCV's | Isolate DFGA-LG-410001 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 60 |  |  | DF /G /30/DFGA-LG-410001 | Isolate DFGA-LG-410001 LG and HCV | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322264 | DFC-36-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048077 | DFBA-A-0460 Res bank out of service | De-Isolate/Test DFBA-A-0460 | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2021-04-07 | 2021-05-17 | 10 | SECE | SECE | DF /B /01/DFBA-A-0460 | De-Isolate/Test DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048077 | DFBA-A-0460 Res bank out of service | De-Isolate/Test DFBA-A-0460 | SECE | SECE | 20 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-27 | 2024-08-29 | 2021-04-07 | 2021-05-17 | 20 | SECE | SECE | DF /B /01/DFBA-A-0460 | De-Isolate/Test DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048077 | DFBA-A-0460 Res bank out of service | De-Isolate/Test DFBA-A-0460 | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2021-04-07 | 2021-05-17 | 30 | SECE | SECE | DF /B /01/DFBA-A-0460 | De-Isolate/Test DFBA-A-0460 | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018308 | mess room cooler blinking led lights | Isolate cooler |  |  | 0 | 0 | Empty | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-04-17 | 2024-06-01 | 10 |  |  | DF /C | Isolate cooler | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018308 | mess room cooler blinking led lights | Isolate cooler |  |  | 0.5 | 0 | Empty | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-04-17 | 2024-06-01 | 20 |  |  | DF /C | Isolate cooler | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018308 | mess room cooler blinking led lights | Isolate cooler |  |  | 1.5 | 1 | Empty | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-04-17 | 2024-06-01 | 30 |  |  | DF /C | Isolate cooler | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018308 | mess room cooler blinking led lights | Isolate cooler |  |  | 0.5 | 0 | Empty | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-04-17 | 2024-06-01 | 40 |  |  | DF /C | Isolate cooler | Unknown
A | DFF-OIL | WPM | MTN-MECH | PRODTECH | 2400221187 | 1Y SDV LUBE/FUNC TEST OIL - DFF-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-12-20 | 2023-01-19 | 10 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-OIL | WPM | MTN-MECH | MTN-MECH | 2400221187 | 1Y SDV LUBE/FUNC TEST OIL - DFF-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2022-12-20 | 2023-01-19 | 20 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-OIL | WPM | MTN-MECH | PRODTECH | 2400221187 | 1Y SDV LUBE/FUNC TEST OIL - DFF-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2022-12-20 | 2023-01-19 | 30 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098336 | DFA/78 Replace coolant with new type | Isolate-de-isolate |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-10-29 | 2024-03-12 | 10 |  |  | DF /A /78/DFAA-MD-6102 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098336 | DFA/78 Replace coolant with new type | Isolate-de-isolate |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-10-29 | 2024-03-12 | 20 |  |  | DF /A /78/DFAA-MD-6102 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100098336 | DFA/78 Replace coolant with new type | Isolate-de-isolate |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-10-29 | 2024-03-12 | 30 |  |  | DF /A /78/DFAA-MD-6102 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098336 | DFA/78 Replace coolant with new type | Isolate-de-isolate |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-10-29 | 2024-03-12 | 40 |  |  | DF /A /78/DFAA-MD-6102 | Isolate-de-isolate | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339276 | DFF_1Y_33400 INT STRUCT INSP - GVI | DFF_1Y_33400 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_33400 (MEZZ ACCESS) | DFF_1Y_33400 INT STRUCT INSP - GVI | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235851 | 4Y 400V E-SWB MAINT DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235851 | 4Y 400V E-SWB MAINT DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235851 | 4Y 400V E-SWB MAINT DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235851 | 4Y 400V E-SWB MAINT DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A14 | 400V E-SWB MAINT DFGA-N-1843-A14 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339042 | DFA_1Y_30600 INT STRUCT INSP - GVI | DFA_1Y_30600 INT STRUCT INSP - GVI | SECE | SECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | SECE | SECE | DF /A /86/EL_30600 (ROOF DECK) | DFA_1Y_30600 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 4 | 0 | Empty | 2024-07-19 | 2024-07-21 | 2023-02-21 | 2023-10-27 | 2022-12-30 | 2023-05-14 | 10 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 8 | 8 | Empty | 2024-07-19 | 2024-07-21 | 2023-02-22 | 2023-10-27 | 2022-12-30 | 2023-05-14 | 20 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 6 | 8 | Empty | 2024-07-19 | 2024-07-21 | 2023-02-22 | 2023-10-27 | 2022-12-30 | 2023-05-14 | 30 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 20 | 0 | Empty | 2024-07-19 | 2024-07-21 | 2024-07-19 | 2024-07-19 | 2022-12-30 | 2023-05-14 | 40 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 12 | 0 | Empty | 2024-07-19 | 2024-07-21 | 2024-07-19 | 2024-07-21 | 2022-12-30 | 2023-05-14 | 45 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 20 | 8 | Empty | 2024-07-19 | 2024-07-21 | 2024-07-19 | 2024-07-19 | 2022-12-30 | 2023-05-14 | 50 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 50 | 8 | Empty | 2024-07-19 | 2024-07-21 | 2024-07-19 | 2024-07-19 | 2022-12-30 | 2023-05-14 | 60 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 0 | 0 | Empty | 2024-07-19 | 2024-07-21 | 2023-02-21 | 2023-10-27 | 2022-12-30 | 2023-05-14 | 70 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 0 | 0 | Empty | 2024-07-19 | 2024-07-21 | 2023-02-21 | 2023-10-27 | 2022-12-30 | 2023-05-14 | 80 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100078019 | DFC: Replacement of all hyd. hoses | Assist with work scope | PCNF | PCNF | 0 | 0 | Empty | 2024-07-19 | 2024-07-21 | 2023-02-21 | 2023-10-27 | 2022-12-30 | 2023-05-14 | 90 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Assist with work scope | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080794 | Spring in checkvalve broken C-5450 | Spring in checkvalve broken C-5450 | AWSCSCH | AWSCSCH | 4 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-02-22 | 2023-07-07 | 10 | AWSCSCH | AWSCSCH | DF /G /07/DFGA-P-5450 | Spring in checkvalve broken C-5450 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 0 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 3 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 6 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 2 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 50 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 4 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 60 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059757 | FLMR DFC - Repl of gratings EL +54200 | DFC - Replacement of gratings EL +54200 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 70 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +54200 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322310 | DFG-54-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /54/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2019-01-22 | 2019-04-22 | 10 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2019-01-22 | 2019-04-22 | 20 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2019-01-22 | 2019-04-22 | 30 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2019-01-22 | 2019-04-22 | 40 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2019-01-22 | 2019-04-22 | 50 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2019-01-22 | 2019-04-22 | 60 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2019-01-22 | 2019-04-22 | 70 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023934 | Rør tilstoppet, defekt ventil | L2 Exchange valve connection K3 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2019-01-22 | 2019-04-22 | 80 |  |  | DF /G /28/DFGA-T-5045 | L2 Exchange valve connection K3 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 0 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-26 | 2022-01-26 | 2021-05-09 | 2021-06-18 | 2 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 0 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-26 | 2022-01-26 | 2021-05-09 | 2021-06-18 | 3 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 0 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-26 | 2022-01-26 | 2021-05-09 | 2021-06-18 | 10 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 8 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-26 | 2022-01-26 | 2021-05-09 | 2021-06-18 | 20 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 24 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-26 | 2022-01-27 | 2021-05-09 | 2021-06-18 | 30 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 6 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-27 | 2022-01-27 | 2021-05-09 | 2021-06-18 | 40 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 12 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-27 | 2022-01-27 | 2021-05-09 | 2021-06-18 | 50 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 24 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-27 | 2022-01-28 | 2021-05-09 | 2021-06-18 | 60 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100049114 | ANOP DFC leak from 8" firewater ringmain | ASSEMBLE-HT+TEST + REINSULATE |  |  | 3 | 0 | Empty | 2022-01-26 | 2022-01-28 | 2022-01-28 | 2022-01-28 | 2021-05-09 | 2021-06-18 | 140 |  |  | DF /C /01/DFC-8-WF-003-0009-AN-U | ASSEMBLE-HT+TEST + REINSULATE | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024975 | Heater element DFFA-XE-1201 to be taken | L3 Isolate DFFA-XE-1201 |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2019-11-12 | 2021-11-01 | 10 |  |  | DF /F /09/DFFA-XE-1201 | L3 Isolate DFFA-XE-1201 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024975 | Heater element DFFA-XE-1201 to be taken | L3 Isolate DFFA-XE-1201 |  |  | 26 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-04 | 2019-11-12 | 2021-11-01 | 20 |  |  | DF /F /09/DFFA-XE-1201 | L3 Isolate DFFA-XE-1201 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024975 | Heater element DFFA-XE-1201 to be taken | L3 Isolate DFFA-XE-1201 |  |  | 10 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-04 | 2024-07-07 | 2019-11-12 | 2021-11-01 | 30 |  |  | DF /F /09/DFFA-XE-1201 | L3 Isolate DFFA-XE-1201 | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 24 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-02 | 2017-03-11 | 2017-06-09 | 9 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 12 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-04 | 2017-03-11 | 2017-06-09 | 10 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 4 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-02 | 2024-02-03 | 2017-03-11 | 2017-06-09 | 11 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 60 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-03 | 2024-02-08 | 2017-03-11 | 2017-06-09 | 12 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 30 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-08 | 2024-02-10 | 2017-03-11 | 2017-06-09 | 20 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 15 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-08 | 2024-02-10 | 2017-03-11 | 2017-06-09 | 21 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 36 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-10 | 2024-02-13 | 2017-03-11 | 2017-06-09 | 30 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 36 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-13 | 2024-02-16 | 2017-03-11 | 2017-06-09 | 40 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 24 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-16 | 2024-02-17 | 2017-03-11 | 2017-06-09 | 50 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 20 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-16 | 2024-02-18 | 2017-03-11 | 2017-06-09 | 51 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 30 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-17 | 2024-02-19 | 2017-03-11 | 2017-06-09 | 60 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 24 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-19 | 2024-02-21 | 2017-03-11 | 2017-06-09 | 61 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 24 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-21 | 2024-02-22 | 2017-03-11 | 2017-06-09 | 70 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 24 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-22 | 2024-02-23 | 2017-03-11 | 2017-06-09 | 90 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 36 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-21 | 2024-02-25 | 2017-03-11 | 2017-06-09 | 100 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 130 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 140 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 150 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 160 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 170 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 180 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 190 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 200 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024139 | DFC/78: DFC Replace Whip Hoist winch | Operation of crane |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-25 | 2024-02-01 | 2024-02-01 | 2017-03-11 | 2017-06-09 | 210 |  |  | DF /C /78/DFCI-X-6101 | Operation of crane | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000961 | SCADA SW for ENG469M Polyelectric pumps | SCADA SW for ENG469M Polyelectric pumps | AWSC | AWSC | 12 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 10 | AWSC | AWSC | DF /B /04/DFBA-FP-2036 | SCADA SW for ENG469M Polyelectric pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000961 | SCADA SW for ENG469M Polyelectric pumps | SCADA SW for ENG469M Polyelectric pumps | AWSC | AWSC | 6 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 20 | AWSC | AWSC | DF /B /04/DFBA-FP-2036 | SCADA SW for ENG469M Polyelectric pumps | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000961 | SCADA SW for ENG469M Polyelectric pumps | SCADA SW for ENG469M Polyelectric pumps | AWSC | AWSC | 0 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-05 | 2019-07-05 | 30 | AWSC | AWSC | DF /B /04/DFBA-FP-2036 | SCADA SW for ENG469M Polyelectric pumps | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-RIGG | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 12 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-19 | 2019-09-13 | 2019-10-03 | 5 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | PRODTECH | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 6 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-19 | 2024-09-21 | 2019-09-13 | 2019-10-03 | 10 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-MECH | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 14 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-21 | 2024-09-23 | 2019-09-13 | 2019-10-03 | 20 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-RIGG | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 6 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2019-09-13 | 2019-10-03 | 30 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | PRODTECH | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 6 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2019-09-13 | 2019-10-03 | 40 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-RIGG | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 8 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2019-09-13 | 2019-10-03 | 50 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-MECH | 2100025152 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 0 | 0 | Hold Step | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-18 | 2019-09-13 | 2019-10-03 | 60 | AWSC | AWSC | DF /G /76/DFGA-E-5343 | L3 Rigg up for replace valve(s) | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235726 | 4Y 380V E-SWB MAINT DFCI-N-1812-R07 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235726 | 4Y 380V E-SWB MAINT DFCI-N-1812-R07 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 22 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-12 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235726 | 4Y 380V E-SWB MAINT DFCI-N-1812-R07 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235726 | 4Y 380V E-SWB MAINT DFCI-N-1812-R07 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235726 | 4Y 380V E-SWB MAINT DFCI-N-1812-R07 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235819 | 4Y 380V E-SWB MAINT DFFA-N-1812 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /05/DFFA-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235819 | 4Y 380V E-SWB MAINT DFFA-N-1812 | ISOLATION BY PRODUCTION | SECE | SECE | 14 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /05/DFFA-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235819 | 4Y 380V E-SWB MAINT DFFA-N-1812 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /05/DFFA-N-1812 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235819 | 4Y 380V E-SWB MAINT DFFA-N-1812 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /05/DFFA-N-1812 | ISOLATION BY PRODUCTION | Unknown
3 | NE | WRO | PRODTECH | PRODTECH | 2300000740 | GE SYS. 03,04,05,06,07 HSE SITE ADVISOR | NEW COMPONENTS |  |  | 0 | 0 | Empty | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2019-01-27 | 2019-12-31 | 10 |  |  | DF /C | NEW COMPONENTS | Unknown
3 | NE | WRO | PRODTECH | PRODTECH | 2300000740 | GE SYS. 03,04,05,06,07 HSE SITE ADVISOR | NEW COMPONENTS |  |  | 0 | 0 | Empty | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2019-01-27 | 2019-12-31 | 20 |  |  | DF /C | NEW COMPONENTS | Unknown
3 | NE | WRO | PRODTECH | PRODTECH | 2300000740 | GE SYS. 03,04,05,06,07 HSE SITE ADVISOR | NEW COMPONENTS |  |  | 0 | 0 | Empty | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2019-01-27 | 2019-12-31 | 30 |  |  | DF /C | NEW COMPONENTS | Unknown
3 | NE | WRO | PRODTECH | PRODTECH | 2300000740 | GE SYS. 03,04,05,06,07 HSE SITE ADVISOR | NEW COMPONENTS |  |  | 0 | 0 | Empty | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2019-01-27 | 2019-12-31 | 40 |  |  | DF /C | NEW COMPONENTS | Unknown
3 | NE | WRO | PRODTECH | PRODTECH | 2300000740 | GE SYS. 03,04,05,06,07 HSE SITE ADVISOR | NEW COMPONENTS |  |  | 0 | 0 | Empty | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2019-01-27 | 2019-12-31 | 50 |  |  | DF /C | NEW COMPONENTS | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200016995 | Rollertable for dishwasher | Rollertable for dishwasher |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-12-31 | 2024-02-14 | 10 |  |  | DF /C /82/DFCC-X-13015 | Rollertable for dishwasher | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 12 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-24 | 2023-06-17 | 2023-10-30 | 10 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | PRODTECH | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 4 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-24 | 2024-08-25 | 2023-06-17 | 2023-10-30 | 20 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-INST | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-25 | 2024-08-26 | 2023-06-17 | 2023-10-30 | 30 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-MECH | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 8 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2023-06-17 | 2023-10-30 | 40 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 8 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2023-06-17 | 2023-10-30 | 50 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-INST | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-28 | 2023-06-17 | 2023-10-30 | 60 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | PRODTECH | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-28 | 2023-06-17 | 2023-10-30 | 70 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-MECH | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 6 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-29 | 2023-06-17 | 2023-10-30 | 80 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100089996 | DFBA-CVA-30419 External leak | Isolate system |  |  | 4 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2023-06-17 | 2023-10-30 | 90 |  |  | DF /B /10/DFBA-CVA-30419 | Isolate system | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100101417 | kabel LN-1803-3511-L2K er kortsluttet | kabel LN-1803-3511-L2K er kortsluttet | PCNF | PCNF | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-12-19 | 2024-05-02 | 10 | PCNF | PCNF | DF /F /61/DFFA-DP-1803-2-F14 | kabel LN-1803-3511-L2K er kortsluttet | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100101417 | kabel LN-1803-3511-L2K er kortsluttet | kabel LN-1803-3511-L2K er kortsluttet | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-12-19 | 2024-05-02 | 20 | PCNF | PCNF | DF /F /61/DFFA-DP-1803-2-F14 | kabel LN-1803-3511-L2K er kortsluttet | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100101417 | kabel LN-1803-3511-L2K er kortsluttet | kabel LN-1803-3511-L2K er kortsluttet | PCNF | PCNF | 10 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-12-19 | 2024-05-02 | 30 | PCNF | PCNF | DF /F /61/DFFA-DP-1803-2-F14 | kabel LN-1803-3511-L2K er kortsluttet | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100101417 | kabel LN-1803-3511-L2K er kortsluttet | kabel LN-1803-3511-L2K er kortsluttet | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-12-19 | 2024-05-02 | 40 | PCNF | PCNF | DF /F /61/DFFA-DP-1803-2-F14 | kabel LN-1803-3511-L2K er kortsluttet | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100101417 | kabel LN-1803-3511-L2K er kortsluttet | kabel LN-1803-3511-L2K er kortsluttet | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-12-19 | 2024-05-02 | 50 | PCNF | PCNF | DF /F /61/DFFA-DP-1803-2-F14 | kabel LN-1803-3511-L2K er kortsluttet | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046906 | Checkventil ved DFFA-HCV-500124 Intern l | Replace Check valve DFFA-HCV-500124 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-05-30 | 2021-10-27 | 10 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | Replace Check valve DFFA-HCV-500124 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046906 | Checkventil ved DFFA-HCV-500124 Intern l | Replace Check valve DFFA-HCV-500124 |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-05-30 | 2021-10-27 | 20 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | Replace Check valve DFFA-HCV-500124 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046906 | Checkventil ved DFFA-HCV-500124 Intern l | Replace Check valve DFFA-HCV-500124 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-05-30 | 2021-10-27 | 30 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | Replace Check valve DFFA-HCV-500124 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322242 | DFB-20-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /20/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100062996 | Replace/Flush Lube oil in CD Pump | Isolate DFBA-P-5022 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2022-04-26 | 2022-09-23 | 20 |  |  | DF /B /28/DFBA-P-5022 | Isolate DFBA-P-5022 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100062996 | Replace/Flush Lube oil in CD Pump | Isolate DFBA-P-5022 |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-21 | 2022-04-26 | 2022-09-23 | 30 |  |  | DF /B /28/DFBA-P-5022 | Isolate DFBA-P-5022 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100062996 | Replace/Flush Lube oil in CD Pump | Isolate DFBA-P-5022 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2022-04-26 | 2022-09-23 | 40 |  |  | DF /B /28/DFBA-P-5022 | Isolate DFBA-P-5022 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400316146 | 8KH LP COMP - DFFA-C-4202, COUNTER | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | AWSCSECE | AWSCSECE | 5 | 0 | W35-W36 | 2025-01-01 | 2025-01-11 | 2025-01-01 | 2025-01-02 | 2024-03-30 | 2024-04-29 | 10 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4202 | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316146 | 8KH LP COMP - DFFA-C-4202, COUNTER | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | AWSCSECE | AWSCSECE | 10 | 0 | W35-W36 | 2025-01-01 | 2025-01-11 | 2025-01-02 | 2025-01-04 | 2024-03-30 | 2024-04-29 | 20 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4202 | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400316146 | 8KH LP COMP - DFFA-C-4202, COUNTER | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | AWSCSECE | AWSCSECE | 18 | 0 | W35-W36 | 2025-01-01 | 2025-01-11 | 2025-01-04 | 2025-01-09 | 2024-03-30 | 2024-04-29 | 30 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4202 | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400316146 | 8KH LP COMP - DFFA-C-4202, COUNTER | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | AWSCSECE | AWSCSECE | 5 | 0 | W35-W36 | 2025-01-01 | 2025-01-11 | 2025-01-09 | 2025-01-10 | 2024-03-30 | 2024-04-29 | 40 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4202 | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400316146 | 8KH LP COMP - DFFA-C-4202, COUNTER | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | AWSCSECE | AWSCSECE | 5 | 0 | W35-W36 | 2025-01-01 | 2025-01-11 | 2025-01-10 | 2025-01-11 | 2024-03-30 | 2024-04-29 | 50 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4202 | LP COMP. UNIT OVERHAUL - DFFA-C-4202 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235765 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-02C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235765 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-02C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235765 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-02C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235765 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-02C1 | ISOLATION ELECTRICAL | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 10 | 10 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 10 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 16 | 16 | Empty | 2024-07-03 | 2024-07-13 | 2024-06-23 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 12 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 16 | 16 | Empty | 2024-07-03 | 2024-07-13 | 2024-06-23 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 15 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-04 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 20 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 8 | 25 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-05 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 30 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 16 | 34 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 40 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-05 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 50 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-05 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 60 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 16 | 16 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-05 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 70 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 16 | 16 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 80 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 10 | 10 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 90 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 10 | 10 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-13 | 2019-10-06 | 2019-11-15 | 100 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-PIPF | 2100024935 | Dan FA, Change of HCV on DFFA-EP-3804 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 0 | 16 | Empty | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-03 | 2019-10-06 | 2019-11-15 | 110 | PCNFAWSC | PCNFAWSC | DF /F /54/DFFA-EP-3804 | Setup/de-rig rigg. equipment | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322270 | DFC-27-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 95 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101423 | Replace Safety switch DFGA-EM-SW-5440 | De-Isolate Circuit |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-18 | 2024-05-01 | 20 |  |  | DF /G /07/DFGA-EM-5440 | De-Isolate Circuit | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101423 | Replace Safety switch DFGA-EM-SW-5440 | De-Isolate Circuit |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-18 | 2024-05-01 | 30 |  |  | DF /G /07/DFGA-EM-5440 | De-Isolate Circuit | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101423 | Replace Safety switch DFGA-EM-SW-5440 | De-Isolate Circuit |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-18 | 2024-05-01 | 40 |  |  | DF /G /07/DFGA-EM-5440 | De-Isolate Circuit | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101423 | Replace Safety switch DFGA-EM-SW-5440 | De-Isolate Circuit |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-18 | 2024-05-01 | 50 |  |  | DF /G /07/DFGA-EM-5440 | De-Isolate Circuit | Unknown
4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013512 | handeling of safety locker Dan FF | handeling of safety locker Dan FF |  |  | 10 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-08-03 | 2026-01-19 | 10 |  |  | DF /F /84 | handeling of safety locker Dan FF | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400206503 | 6M BDV LUB/MAINT IPHP - DFG | BDV LUB/INSP IPHP - DFG | SCH | SCH | 1 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-08-22 | 2022-09-07 | 10 | SCH | SCH | DF /G /31/DFGA-BDV-430013 | BDV LUB/INSP IPHP - DFG | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-01 | 2024-08-01 | 2018-11-27 | 2019-04-26 | 5 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-01 | 2024-08-01 | 2018-11-27 | 2019-04-26 | 10 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 16 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-02 | 2024-08-05 | 2018-11-27 | 2019-04-26 | 15 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-06 | 2024-08-07 | 2018-11-27 | 2019-04-26 | 17 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-08 | 2024-08-08 | 2018-11-27 | 2019-04-26 | 30 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-08 | 2024-08-08 | 2018-11-27 | 2019-04-26 | 40 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-09 | 2024-08-09 | 2018-11-27 | 2019-04-26 | 50 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-09 | 2024-08-10 | 2018-11-27 | 2019-04-26 | 60 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 6 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-10 | 2024-08-11 | 2018-11-27 | 2019-04-26 | 70 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 4 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-11 | 2024-08-11 | 2018-11-27 | 2019-04-26 | 80 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 4 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-11 | 2024-08-12 | 2018-11-27 | 2019-04-26 | 90 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 4 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-12 | 2024-08-12 | 2018-11-27 | 2019-04-26 | 100 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-12 | 2024-08-12 | 2018-11-27 | 2019-04-26 | 110 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-13 | 2024-08-14 | 2018-11-27 | 2019-04-26 | 120 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2018-11-27 | 2019-04-26 | 125 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2018-11-27 | 2019-04-26 | 130 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100025025 | Actautor valve drivetrain repair DFFA-ES | L3 Inhibit DFFA-ESDV-340048 | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2018-11-27 | 2019-04-26 | 135 | AWSC | AWSC | DF /F /20/DFFA-ESDV-340048 | L3 Inhibit DFFA-ESDV-340048 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094939 | Periodic error on door contact | Isolate Door switch |  |  | 1.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-08-11 | 2023-12-24 | 10 |  |  | DF /F /31/DFFA-A-4310 | Isolate Door switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094939 | Periodic error on door contact | Isolate Door switch |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-08-11 | 2023-12-24 | 20 |  |  | DF /F /31/DFFA-A-4310 | Isolate Door switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094939 | Periodic error on door contact | Isolate Door switch |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-08-11 | 2023-12-24 | 30 |  |  | DF /F /31/DFFA-A-4310 | Isolate Door switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094939 | Periodic error on door contact | Isolate Door switch |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-08-11 | 2023-12-24 | 40 |  |  | DF /F /31/DFFA-A-4310 | Isolate Door switch | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342408 | 2Y 220V UPS.SYST BATT & CHAR F.TEST-DFC | 220V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 20 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-17 | 2024-07-21 | 2024-07-17 | 2024-09-01 | 10 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 220V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342408 | 2Y 220V UPS.SYST BATT & CHAR F.TEST-DFC | 220V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-17 | 2024-09-01 | 20 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 220V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342408 | 2Y 220V UPS.SYST BATT & CHAR F.TEST-DFC | 220V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-17 | 2024-09-01 | 30 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 220V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400342408 | 2Y 220V UPS.SYST BATT & CHAR F.TEST-DFC | 220V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-17 | 2024-09-01 | 40 | AWSCSECE | AWSCSECE | DF /C /06/UPS-SYSTEMS | 220V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
3 | DFB-O10 | WDF | MTN-INST | PRODTECH | 2100046327 | Invertere ZSO og ZSC på DFB10 MCV | Replace Monitoring | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 10 | AWSC | AWSC | DF /B /10/DFBA-MCV-30046 | Replace Monitoring | Unknown
3 | DFB-O10 | WDF | MTN-INST | MTN-INST | 2100046327 | Invertere ZSO og ZSC på DFB10 MCV | Replace Monitoring | AWSC | AWSC | 4 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 12 | AWSC | AWSC | DF /B /10/DFBA-MCV-30046 | Replace Monitoring | Unknown
3 | DFB-O10 | WDF | MTN-INST | MTN-TELE | 2100046327 | Invertere ZSO og ZSC på DFB10 MCV | Replace Monitoring | AWSC | AWSC | 3 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 20 | AWSC | AWSC | DF /B /10/DFBA-MCV-30046 | Replace Monitoring | Unknown
3 | DFB-O10 | WDF | MTN-INST | PRODTECH | 2100046327 | Invertere ZSO og ZSC på DFB10 MCV | Replace Monitoring | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2021-05-20 | 2021-10-17 | 30 | AWSC | AWSC | DF /B /10/DFBA-MCV-30046 | Replace Monitoring | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300006582 | DK40 - REPLACED BY 2300008270 | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2024-03-09 | 2026-08-26 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400292167 | 6M SW FILTERS & BLOWERS MAINT - DFE | SW FILTERS & BLOWERS MAINT - DFE |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-23 | 10 |  |  | DF /E /51/DFEY-FT-3511 | SW FILTERS & BLOWERS MAINT - DFE | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400292167 | 6M SW FILTERS & BLOWERS MAINT - DFE | SW FILTERS & BLOWERS MAINT - DFE |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2023-12-23 | 20 |  |  | DF /E /51/DFEY-FT-3511 | SW FILTERS & BLOWERS MAINT - DFE | Unknown
A | DFG-3590 | WPM | MTN-MECH | PRODTECH | 2400290946 | 1Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W17-W18 | 2024-10-05 | 2024-10-08 | 2024-10-05 | 2024-10-05 | 2023-10-30 | 2023-11-29 | 10 | SCHSECE | SCHSECE | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-INST | 2400290946 | 1Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2.5 | 0 | W17-W18 | 2024-10-05 | 2024-10-08 | 2024-10-05 | 2024-10-06 | 2023-10-30 | 2023-11-29 | 20 | SCHSECE | SCHSECE | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-MECH | 2400290946 | 1Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W17-W18 | 2024-10-05 | 2024-10-08 | 2024-10-06 | 2024-10-07 | 2023-10-30 | 2023-11-29 | 30 | SCHSECE | SCHSECE | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | MTN-ELEC | 2400290946 | 1Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W17-W18 | 2024-10-05 | 2024-10-08 | 2024-10-07 | 2024-10-08 | 2023-10-30 | 2023-11-29 | 40 | SCHSECE | SCHSECE | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
A | DFG-3590 | WPM | MTN-MECH | PRODTECH | 2400290946 | 1Y BOOSTER PUMP MAINT DFGA-P-3547/48 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W17-W18 | 2024-10-05 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2023-10-30 | 2023-11-29 | 50 | SCHSECE | SCHSECE | DF /G /54/DFGA-P-3547 | ISOLATION BY PRODUCTION | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 16 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-03 | 2020-10-04 | 2020-10-24 | 10 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 8 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2020-10-04 | 2020-10-24 | 20 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2020-10-04 | 2020-10-24 | 30 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 2 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2020-10-04 | 2020-10-24 | 40 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 2 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2020-10-04 | 2020-10-24 | 50 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 8 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2020-10-04 | 2020-10-24 | 60 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2020-10-04 | 2020-10-24 | 70 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-07 | 2020-10-04 | 2020-10-24 | 80 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2020-10-04 | 2020-10-24 | 90 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-INST | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 2 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2020-10-04 | 2020-10-24 | 100 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 3 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2020-10-04 | 2020-10-24 | 110 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 6 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2020-10-04 | 2020-10-24 | 120 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038894 | XCV-354164 air leakage on actuator | De-isolate XCV-354164 | AWSC | AWSC | 10 | 0 | W49-50 | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2020-10-04 | 2020-10-24 | 130 | AWSC | AWSC | DF /F /51/DFFA-XCV-354164 | De-isolate XCV-354164 | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 0 | 0 | Empty | 2023-02-28 | 2023-05-05 | 2023-02-28 | 2023-02-28 | 2022-01-27 | 2022-04-27 | 2 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 0 | 0 | Empty | 2023-02-28 | 2023-05-05 | 2023-02-28 | 2023-02-28 | 2022-01-27 | 2022-04-27 | 3 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 0 | 0 | Empty | 2023-02-28 | 2023-05-05 | 2023-02-28 | 2023-02-28 | 2022-01-27 | 2022-04-27 | 4 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 0 | 0 | Empty | 2023-02-28 | 2023-05-05 | 2023-02-28 | 2023-02-28 | 2022-01-27 | 2022-04-27 | 10 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 100 | 15 | Empty | 2023-02-28 | 2023-05-05 | 2023-02-28 | 2023-03-08 | 2022-01-27 | 2022-04-27 | 20 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 300 | 40 | Empty | 2023-02-28 | 2023-05-05 | 2023-03-08 | 2023-04-02 | 2022-01-27 | 2022-04-27 | 30 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 300 | 40 | Empty | 2023-02-28 | 2023-05-05 | 2023-04-02 | 2023-04-27 | 2022-01-27 | 2022-04-27 | 40 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061170 | ANOCR DWEA647058-DFF-ESC-ROUTE~NOT-22000 | DFF Escape route walkways require FM | AWSC | AWSC | 100 | 8 | Empty | 2023-02-28 | 2023-05-05 | 2023-04-27 | 2023-05-05 | 2022-01-27 | 2022-04-27 | 50 | AWSC | AWSC | DF /F /86/FABRIC-MAINTENANCE | DFF Escape route walkways require FM | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097603 | HVAC PDSL-12356A switch deffective | Isolate Diff. Pressure Switch |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-14 | 2024-02-26 | 10 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate Diff. Pressure Switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097603 | HVAC PDSL-12356A switch deffective | Isolate Diff. Pressure Switch |  |  | 2.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-14 | 2024-02-26 | 20 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate Diff. Pressure Switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100097603 | HVAC PDSL-12356A switch deffective | Isolate Diff. Pressure Switch |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-14 | 2024-02-26 | 30 |  |  | DF /C /09/DFCI-PDSL-12356A | Isolate Diff. Pressure Switch | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-18 | 2021-02-07 | 2021-03-19 | 10 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | PRODTECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-19 | 2021-02-07 | 2021-03-19 | 20 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-19 | 2024-09-19 | 2021-02-07 | 2021-03-19 | 30 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-RIGG | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-19 | 2024-09-20 | 2021-02-07 | 2021-03-19 | 40 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-21 | 2021-02-07 | 2021-03-19 | 50 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-RIGG | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-21 | 2021-02-07 | 2021-03-19 | 60 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-22 | 2021-02-07 | 2021-03-19 | 70 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-22 | 2024-09-24 | 2021-02-07 | 2021-03-19 | 80 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2021-02-07 | 2021-03-19 | 90 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-25 | 2021-02-07 | 2021-03-19 | 100 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | PRODTECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2021-02-07 | 2021-03-19 | 110 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044852 | DFG PCV-570432 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-27 | 2021-02-07 | 2021-03-19 | 120 |  |  | DF /G /70/DFGA-PCV-570432 | Isolate PCV | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 2 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-06 | 2024-11-06 | 2023-11-06 | 2024-03-20 | 10 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-SCAF | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 10 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-06 | 2024-11-08 | 2023-11-06 | 2024-03-20 | 20 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 5 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-09 | 2024-11-10 | 2023-11-06 | 2024-03-20 | 30 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 9 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-09 | 2024-11-11 | 2023-11-06 | 2024-03-20 | 40 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 5 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-11 | 2024-11-12 | 2023-11-06 | 2024-03-20 | 50 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 9 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-10 | 2024-11-12 | 2023-11-06 | 2024-03-20 | 60 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 2 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2023-11-06 | 2024-03-20 | 70 |  |  | DF /B /55 | Build Scaffold | Unknown
3 | DFX-WI | WDF | MTN-MECH | MTN-SCAF | 2100098779 | HCV internal leak. | Build Scaffold |  |  | 4 | 0 | Empty | 2024-11-06 | 2024-11-12 | 2024-11-12 | 2024-11-12 | 2023-11-06 | 2024-03-20 | 80 |  |  | DF /B /55 | Build Scaffold | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286619 | 1Y FIREWATER MIST SKID MAINT-DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | SECE | SECE | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-20 | 2024-05-21 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /B /01/DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286619 | 1Y FIREWATER MIST SKID MAINT-DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | SECE | SECE | 10 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-21 | 2024-05-23 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /B /01/DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286619 | 1Y FIREWATER MIST SKID MAINT-DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | SECE | SECE | 6 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-23 | 2024-05-25 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /B /01/DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286619 | 1Y FIREWATER MIST SKID MAINT-DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | SECE | SECE | 4 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-25 | 2024-05-26 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /B /01/DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286619 | 1Y FIREWATER MIST SKID MAINT-DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | SECE | SECE | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-26 | 2024-05-26 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /B /01/DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286619 | 1Y FIREWATER MIST SKID MAINT-DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | SECE | SECE | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-27 | 2024-05-26 | 2024-05-27 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /B /01/DFBA-A-0460 | FIREWATER MIST SKID MAINT-DFBA-A-0460 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055690 | Defekt gear på HCV-430011D. | Backload gearbox to User Resp as 3 part |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2021-12-12 | 2022-05-11 | 10 |  |  | DF /F /32/DFFA-HCV-430011A-D | Backload gearbox to User Resp as 3 part | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055690 | Defekt gear på HCV-430011D. | Backload gearbox to User Resp as 3 part |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2021-12-12 | 2022-05-11 | 20 |  |  | DF /F /32/DFFA-HCV-430011A-D | Backload gearbox to User Resp as 3 part | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055690 | Defekt gear på HCV-430011D. | Backload gearbox to User Resp as 3 part |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2021-12-12 | 2022-05-11 | 30 |  |  | DF /F /32/DFFA-HCV-430011A-D | Backload gearbox to User Resp as 3 part | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055690 | Defekt gear på HCV-430011D. | Backload gearbox to User Resp as 3 part |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2021-12-12 | 2022-05-11 | 40 |  |  | DF /F /32/DFFA-HCV-430011A-D | Backload gearbox to User Resp as 3 part | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055690 | Defekt gear på HCV-430011D. | Backload gearbox to User Resp as 3 part |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2021-12-12 | 2022-05-11 | 50 |  |  | DF /F /32/DFFA-HCV-430011A-D | Backload gearbox to User Resp as 3 part | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055690 | Defekt gear på HCV-430011D. | Backload gearbox to User Resp as 3 part |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2021-12-12 | 2022-05-11 | 60 |  |  | DF /F /32/DFFA-HCV-430011A-D | Backload gearbox to User Resp as 3 part | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235599 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-9 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-9-1-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235599 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-9 | ISOLATION ELECTRICAL |  |  | 31 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-23 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-9-1-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235599 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-9 | ISOLATION ELECTRICAL |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-23 | 2024-09-25 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-9-1-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235599 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-9 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-9-1-1 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100050986 | FLM DFC - Handrail Stair Repl. EL +67.45 | Remove step |  |  | 6 | 0 | Empty | 2021-06-06 | 2021-06-11 | 2021-06-06 | 2021-06-07 | 2021-06-06 | 2021-09-04 | 10 |  |  | DF /C /86/50700 - HANDRAILS | Remove step | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100050986 | FLM DFC - Handrail Stair Repl. EL +67.45 | Remove step |  |  | 2 | 0 | Empty | 2021-06-06 | 2021-06-11 | 2021-06-07 | 2021-06-07 | 2021-06-06 | 2021-09-04 | 20 |  |  | DF /C /86/50700 - HANDRAILS | Remove step | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100050986 | FLM DFC - Handrail Stair Repl. EL +67.45 | Remove step |  |  | 10 | 0 | Empty | 2021-06-06 | 2021-06-11 | 2021-06-07 | 2021-06-09 | 2021-06-06 | 2021-09-04 | 30 |  |  | DF /C /86/50700 - HANDRAILS | Remove step | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100050986 | FLM DFC - Handrail Stair Repl. EL +67.45 | Remove step |  |  | 8 | 0 | Empty | 2021-06-06 | 2021-06-11 | 2021-06-09 | 2021-06-10 | 2021-06-06 | 2021-09-04 | 40 |  |  | DF /C /86/50700 - HANDRAILS | Remove step | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100050986 | FLM DFC - Handrail Stair Repl. EL +67.45 | Remove step |  |  | 2 | 0 | Empty | 2021-06-06 | 2021-06-11 | 2021-06-10 | 2021-06-10 | 2021-06-06 | 2021-09-04 | 50 |  |  | DF /C /86/50700 - HANDRAILS | Remove step | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100050986 | FLM DFC - Handrail Stair Repl. EL +67.45 | Remove step |  |  | 6 | 0 | Empty | 2021-06-06 | 2021-06-11 | 2021-06-10 | 2021-06-11 | 2021-06-06 | 2021-09-04 | 60 |  |  | DF /C /86/50700 - HANDRAILS | Remove step | Unknown
B | NOSD | WPM | MTN-INST | PRODTECH | 2400337264 | 1Y GAS CHROM-FISCAL-VENDOR-DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | AWSC | AWSC | 0.5 | 0 | Empty | 2024-07-18 | 2024-07-24 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-08-17 | 10 | AWSC | AWSC | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
B | NOSD | WPM | MTN-INST | MTN-INST | 2400337264 | 1Y GAS CHROM-FISCAL-VENDOR-DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | AWSC | AWSC | 8 | 0 | Empty | 2024-07-18 | 2024-07-24 | 2024-07-18 | 2024-07-20 | 2024-07-18 | 2024-08-17 | 20 | AWSC | AWSC | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
B | NOSD | WPM | MTN-INST | PRODLABO | 2400337264 | 1Y GAS CHROM-FISCAL-VENDOR-DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | AWSC | AWSC | 1.5 | 0 | Empty | 2024-07-18 | 2024-07-24 | 2024-07-20 | 2024-07-20 | 2024-07-18 | 2024-08-17 | 30 | AWSC | AWSC | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
B | NOSD | WPM | MTN-INST | PRODTECH | 2400337264 | 1Y GAS CHROM-FISCAL-VENDOR-DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | AWSC | AWSC | 0.5 | 0 | Empty | 2024-07-18 | 2024-07-24 | 2024-07-20 | 2024-07-20 | 2024-07-18 | 2024-08-17 | 40 | AWSC | AWSC | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
B | NOSD | WPM | MTN-INST | VEN-INST | 2400337264 | 1Y GAS CHROM-FISCAL-VENDOR-DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | AWSC | AWSC | 36 | 0 | Empty | 2024-07-18 | 2024-07-24 | 2024-07-20 | 2024-07-24 | 2024-07-18 | 2024-08-17 | 50 | AWSC | AWSC | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
A | KRA-OIL | WPM | MTN-MECH | PRODTECH | 2400307931 | 1Y ESDV LEAK TEST - DFAA-ESDV-38169. | DE-ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-01-11 | 2024-02-10 | 10 | AWSCSECE | AWSCSECE | DF /A /12/DFAA-ESDV-38169 | DE-ISOLATION BY PRODUCTION | Unknown
A | KRA-OIL | WPM | MTN-MECH | PRODTECH | 2400307931 | 1Y ESDV LEAK TEST - DFAA-ESDV-38169. | DE-ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2024-01-11 | 2024-02-10 | 20 | AWSCSECE | AWSCSECE | DF /A /12/DFAA-ESDV-38169 | DE-ISOLATION BY PRODUCTION | Unknown
A | KRA-OIL | WPM | MTN-MECH | PRODTECH | 2400307931 | 1Y ESDV LEAK TEST - DFAA-ESDV-38169. | DE-ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-01-11 | 2024-02-10 | 30 | AWSCSECE | AWSCSECE | DF /A /12/DFAA-ESDV-38169 | DE-ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 3 | Empty | 2020-11-30 | 2024-01-10 | 2020-08-19 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 4 | Empty | 2020-11-30 | 2024-01-10 | 2020-08-26 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 16.100000000000001421085471515 | 25.5 | Empty | 2020-11-30 | 2024-01-10 | 2020-08-19 | 2020-12-13 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 6 | 12 | Empty | 2020-11-30 | 2024-01-10 | 2020-08-25 | 2020-09-04 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 9 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 6 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2022-04-26 | 2022-04-26 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 13.400000000000000355271367876 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 90 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 100 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 18 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 110 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-10 | 2019-09-12 | 2019-12-11 | 120 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002913 | DFF-Insulation assists FORCE 13522 | BUILD SCAFFOLDING | PCNF | PCNF | 6 | 0 | Empty | 2020-11-30 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 130 | PCNF | PCNF | DF /F /55/DFF-6-WI-035-7103-GF-U | BUILD SCAFFOLDING | Unknown
3 | DFF-W31 | WDF | MTN-INST | PRODTECH | 2100059738 | DFF-31 Replace Position Measurement Devi | Isolate Position Measurement Device |  |  | 0.5 | 0 | Awaiting loss approval | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-02 | 2022-04-02 | 10 |  |  | DF /F /55/DFFA-ZT-300731 | Isolate Position Measurement Device | Unknown
3 | DFF-W31 | WDF | MTN-INST | MTN-INST | 2100059738 | DFF-31 Replace Position Measurement Devi | Isolate Position Measurement Device |  |  | 2 | 0 | Awaiting loss approval | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-02 | 2022-04-02 | 20 |  |  | DF /F /55/DFFA-ZT-300731 | Isolate Position Measurement Device | Unknown
3 | DFF-W31 | WDF | MTN-INST | PRODTECH | 2100059738 | DFF-31 Replace Position Measurement Devi | Isolate Position Measurement Device |  |  | 0.5 | 0 | Awaiting loss approval | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-01-02 | 2022-04-02 | 30 |  |  | DF /F /55/DFFA-ZT-300731 | Isolate Position Measurement Device | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-SCAF | 2100098781 | E-5345 Disch.seawater 16"HCV intern leak | Build Scaffold |  |  | 6 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-23 | 2023-11-04 | 2024-03-18 | 10 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100098781 | E-5345 Disch.seawater 16"HCV intern leak | Build Scaffold |  |  | 2 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-23 | 2023-11-04 | 2024-03-18 | 20 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100098781 | E-5345 Disch.seawater 16"HCV intern leak | Build Scaffold |  |  | 4 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2023-11-04 | 2024-03-18 | 30 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100098781 | E-5345 Disch.seawater 16"HCV intern leak | Build Scaffold |  |  | 4 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2023-11-04 | 2024-03-18 | 40 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100098781 | E-5345 Disch.seawater 16"HCV intern leak | Build Scaffold |  |  | 2 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2023-11-04 | 2024-03-18 | 50 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-SCAF | 2100098781 | E-5345 Disch.seawater 16"HCV intern leak | Build Scaffold |  |  | 4 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-11-04 | 2024-03-18 | 60 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
C | NOSD | WPM | PRODLABO | VEN-INSP | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 30 | 75 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2021-04-18 | 2021-04-29 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2021-04-18 | 2021-04-29 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
C | NOSD | WPM | PRODLABO | MTN-TURB | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 10 | 10 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2021-04-18 | 2021-04-29 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
C | NOSD | WPM | PRODLABO | MTN-SCAF | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 15 | 10 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2021-04-18 | 2021-04-29 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
C | NOSD | WPM | PRODLABO | VEN-INSP | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 15 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-16 | 2021-04-18 | 2021-04-29 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
C | NOSD | WPM | PRODLABO | VEN-INSP | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 15 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-16 | 2021-04-18 | 2021-04-29 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
C | NOSD | WPM | PRODLABO | MTN-TURB | 2400117341 | 3M NOx in Exhaust, VENDOR, DFF | Nox measure DFFA-A-4301 'CAL2' | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-14 | 2021-04-18 | 2021-04-29 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /31/DFFA-CT-4301 | Nox measure DFFA-A-4301 'CAL2' | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100089242 | Replacement of radiator hose C-5409 | Replace hose | PCNFSCH | PCNFSCH | 1 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-06-01 | 2023-10-14 | 10 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5409 | Replace hose | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100089242 | Replacement of radiator hose C-5409 | Replace hose | PCNFSCH | PCNFSCH | 2 | 8 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-06-01 | 2023-10-14 | 30 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5409 | Replace hose | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100089242 | Replacement of radiator hose C-5409 | Replace hose | PCNFSCH | PCNFSCH | 1 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-06-01 | 2023-10-14 | 40 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5409 | Replace hose | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088062 | Defekt nødlys DFF Roof | Defekt nødlys DFF Roof |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-08 | 2023-09-20 | 10 |  |  | DF /F /05/DFFA-N-1813 | Defekt nødlys DFF Roof | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100088062 | Defekt nødlys DFF Roof | Defekt nødlys DFF Roof |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-08 | 2023-09-20 | 20 |  |  | DF /F /05/DFFA-N-1813 | Defekt nødlys DFF Roof | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088062 | Defekt nødlys DFF Roof | Defekt nødlys DFF Roof |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-08 | 2023-09-20 | 30 |  |  | DF /F /05/DFFA-N-1813 | Defekt nødlys DFF Roof | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100088062 | Defekt nødlys DFF Roof | Defekt nødlys DFF Roof |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-08 | 2023-09-20 | 40 |  |  | DF /F /05/DFFA-N-1813 | Defekt nødlys DFF Roof | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025172 | CMAT:Replace DFGA-SOV-500629 | L3 Isolation of DFGA-SOV-500629 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2018-12-19 | 2019-05-18 | 5 |  |  | DF /G /27/DFGA-XCV-500629 | L3 Isolation of DFGA-SOV-500629 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025172 | CMAT:Replace DFGA-SOV-500629 | L3 Isolation of DFGA-SOV-500629 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2018-12-19 | 2019-05-18 | 10 |  |  | DF /G /27/DFGA-XCV-500629 | L3 Isolation of DFGA-SOV-500629 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025172 | CMAT:Replace DFGA-SOV-500629 | L3 Isolation of DFGA-SOV-500629 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2018-12-19 | 2019-05-18 | 30 |  |  | DF /G /27/DFGA-XCV-500629 | L3 Isolation of DFGA-SOV-500629 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 17.399999999999998578914528472 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-13 | 2023-02-15 | 2018-02-04 | 2018-03-16 | 10 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-15 | 2023-02-15 | 2018-02-04 | 2018-03-16 | 15 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 6 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-15 | 2023-02-17 | 2018-02-04 | 2018-03-16 | 20 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 17.399999999999998578914528472 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-17 | 2023-02-17 | 2018-02-04 | 2018-03-16 | 30 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 17.399999999999998578914528472 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-17 | 2023-02-20 | 2018-02-04 | 2018-03-16 | 35 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-20 | 2023-02-21 | 2018-02-04 | 2018-03-16 | 40 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100026138 | CMAT:Ventiler på vent afgang, intern utæ | Install scaff |  |  | 10.699999999999999289457264235 | 0 | Empty | 2023-02-13 | 2023-02-22 | 2023-02-21 | 2023-02-22 | 2018-02-04 | 2018-03-16 | 50 |  |  | DF /F /34/DFFA-EP-3805 | Install scaff | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400281432 | 3Y DFFA-A-1620 FUEL - METERING | DFFA-A-1620 FUEL - METERING |  |  | 3 | 3 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-07-27 | 2023-10-09 | 10 |  |  | DF /F /60/DFFA-A-1620 | DFFA-A-1620 FUEL - METERING | Unknown
D | NOSD | WPM | PRODTECH | PRODTECH | 2400329634 | PIGGING, P3010 12" DFF-DAD WI 2W | P3010_DFF-DAD | AWSC | AWSC | 4 | 0 | Empty | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-14 | 2024-06-20 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673010 | P3010_DFF-DAD | Unknown
3 | NOSD | WDF | MTN-ROUS | MTN-ROUS | 2100098340 | Materials for PPM on fire eq. | Materials for PPM on fire eq. |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-31 | 2024-03-14 | 10 |  |  | DF /F /01 | Materials for PPM on fire eq. | Unknown
D | NOSD | WPM | PRODLABO | PRODLABO | 2400281411 | 3M SAMPLING OF OiW CORRELATIONS | SAMPLE OF OiW CORRELATION DFF,DFG,DFC |  |  | 1 | 0 | Empty | 2023-10-01 | 2023-10-01 | 2023-10-01 | 2023-10-01 | 2023-09-30 | 2023-10-15 | 10 |  |  | DF /G /27/DFGA-AT-500600 | SAMPLE OF OiW CORRELATION DFF,DFG,DFC | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300001934 | Rettelse af tekst til Chem INJ (SCADA) | Rettelse af tekst til Chem INJ (SCADA) |  |  | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2021-03-15 | 2022-01-09 | 10 |  |  | DF /C /04 | Rettelse af tekst til Chem INJ (SCADA) | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077616 | Findning A-05 from 1Y inspection helifue | Isolate heli fuel system | PCNFSCH | PCNFSCH | 2 | 0 | W25-W26 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-04-30 | 2025-10-16 | 20 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077616 | Findning A-05 from 1Y inspection helifue | Isolate heli fuel system | PCNFSCH | PCNFSCH | 4 | 0 | W25-W26 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-04-30 | 2025-10-16 | 30 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077616 | Findning A-05 from 1Y inspection helifue | Isolate heli fuel system | PCNFSCH | PCNFSCH | 4 | 0 | W25-W26 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-04-30 | 2025-10-16 | 40 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077616 | Findning A-05 from 1Y inspection helifue | Isolate heli fuel system | PCNFSCH | PCNFSCH | 2 | 0 | W25-W26 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-04-30 | 2025-10-16 | 50 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100105405 | Fusible Link on firedamper DFC-FD-12371 | YDERLIGERE MATERIALER | SCHSECE | SCHSECE | 6 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-16 | 2024-02-23 | 2024-07-07 | 2 | SCHSECE | SCHSECE | DF /C /09/DFCI-FD-12371 | YDERLIGERE MATERIALER | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105405 | Fusible Link on firedamper DFC-FD-12371 | YDERLIGERE MATERIALER | SCHSECE | SCHSECE | 2 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-02-23 | 2024-07-07 | 5 | SCHSECE | SCHSECE | DF /C /09/DFCI-FD-12371 | YDERLIGERE MATERIALER | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105405 | Fusible Link on firedamper DFC-FD-12371 | YDERLIGERE MATERIALER | SCHSECE | SCHSECE | 4 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2024-02-23 | 2024-07-07 | 10 | SCHSECE | SCHSECE | DF /C /09/DFCI-FD-12371 | YDERLIGERE MATERIALER | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105405 | Fusible Link on firedamper DFC-FD-12371 | YDERLIGERE MATERIALER | SCHSECE | SCHSECE | 1 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-17 | 2024-02-23 | 2024-07-07 | 20 | SCHSECE | SCHSECE | DF /C /09/DFCI-FD-12371 | YDERLIGERE MATERIALER | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105405 | Fusible Link on firedamper DFC-FD-12371 | YDERLIGERE MATERIALER | SCHSECE | SCHSECE | 2 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2024-02-23 | 2024-07-07 | 30 | SCHSECE | SCHSECE | DF /C /09/DFCI-FD-12371 | YDERLIGERE MATERIALER | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100105405 | Fusible Link on firedamper DFC-FD-12371 | YDERLIGERE MATERIALER | SCHSECE | SCHSECE | 0 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-02-23 | 2024-07-07 | 40 | SCHSECE | SCHSECE | DF /C /09/DFCI-FD-12371 | YDERLIGERE MATERIALER | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235779 | 4Y 400V N-SWB MAINT-DFFB-N-1828-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235779 | 4Y 400V N-SWB MAINT-DFFB-N-1828-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 21 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235779 | 4Y 400V N-SWB MAINT-DFFB-N-1828-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-29 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828-10 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235779 | 4Y 400V N-SWB MAINT-DFFB-N-1828-10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828-10 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339141 | DFD_1Y_BRIDGE B-D INT STRUCT INSP - GVI | DFD_1Y_BRIDGE B-D INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /D /86/BRIDGE-DFB-DFD (FLARE TOWER) | DFD_1Y_BRIDGE B-D INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042774 | Chemcal Injection - Inst. tube rubbing | Install protecting spiral bonding on tub |  |  | 14 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2021-01-01 | 2021-04-01 | 10 |  |  | DF /F /75/DFFA-A-3930 | Install protecting spiral bonding on tub | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100042774 | Chemcal Injection - Inst. tube rubbing | Install protecting spiral bonding on tub |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2021-01-01 | 2021-04-01 | 20 |  |  | DF /F /75/DFFA-A-3930 | Install protecting spiral bonding on tub | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 10 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 20 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 30 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 40 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 50 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 60 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 70 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 80 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 90 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 100 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101810 | LG-340037 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-12-28 | 2024-05-11 | 110 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Install rigging equipment | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322271 | DFC-11-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 14 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /11/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 24 | 5 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-17 | 2024-07-20 | 2024-10-30 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 5 | 4 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-20 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-21 | 2024-07-22 | 2024-10-30 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-22 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 12 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-23 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-24 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 80 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 5 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-25 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 90 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-26 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 100 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-26 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 110 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-27 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 120 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284310 | PSV Calibration - DFGA-PSV-530059A | Scaffolding | AWSC | AWSC | 10 | 4 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-27 | 2024-07-28 | 2024-10-30 | 2024-12-31 | 130 | AWSC | AWSC | DF /G /51/DFGA-PSV-530059A | Scaffolding | Unknown
2 | Empty | WDF | PRODTECH | PRODTECH | 2100112338 | Glycol filter FT-4101 højt DP | Change filter cartridge |  |  | 24 | 4 | Empty | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-06-24 | 10 |  |  | DF /F /30/DFFA-FT-4101 | Change filter cartridge | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018472 | Spare 800 series GE relays | Add materials |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-06-21 | 2024-11-03 | 10 |  |  | DF /G /61/CONTROL-PANELS | Add materials | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018472 | Spare 800 series GE relays | Add materials |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-06-21 | 2024-11-03 | 20 |  |  | DF /G /61/CONTROL-PANELS | Add materials | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200018472 | Spare 800 series GE relays | Add materials |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-06-21 | 2024-11-03 | 30 |  |  | DF /G /61/CONTROL-PANELS | Add materials | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018472 | Spare 800 series GE relays | Add materials |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-06-21 | 2024-11-03 | 40 |  |  | DF /G /61/CONTROL-PANELS | Add materials | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018472 | Spare 800 series GE relays | Add materials |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-06-21 | 2024-11-03 | 50 |  |  | DF /G /61/CONTROL-PANELS | Add materials | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-03-27 | 2023-03-29 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-03-30 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-ELEC | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-04-01 | 2023-04-04 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-04-04 | 2023-04-04 | 2022-02-07 | 2022-07-07 | 42 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-ELEC | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-04-04 | 2023-04-08 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 36 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-04-08 | 2023-04-12 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200009231 | Insulation assists Bilfinger 22081(COMP) | Bilfinger inspection |  |  | 18 | 0 | Empty | 2023-03-27 | 2023-04-14 | 2023-04-12 | 2023-04-14 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /F /27/DFF-2-DPS-050-8073-AB-T | Bilfinger inspection | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100027150 | Replacement of DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2016-12-23 | 2017-01-12 | 10 | AWSC | AWSC | DF /C /27/DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100027150 | Replacement of DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 20 | AWSC | AWSC | DF /C /27/DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100027150 | Replacement of DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 30 | AWSC | AWSC | DF /C /27/DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | Unknown
3 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100027150 | Replacement of DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 40 | AWSC | AWSC | DF /C /27/DFCM-PDCV-50346 | Safing af DFCM-PDCV-50346 | Unknown
B | NOSD | WPM | MTN-INST | MTN-INST | 2400292178 | 3Y HP SEP DFFA-V-3401 - METERING | HP SEP DFFA-V-3401 - METERING | AWSC | AWSC | 6 | 0 | Empty | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2023-10-23 | 2023-12-24 | 10 | AWSC | AWSC | DF /F /20/METERING | HP SEP DFFA-V-3401 - METERING | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337275 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL ISOLATION |  |  | 1 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2024-08-17 | 10 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337275 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL ISOLATION |  |  | 9 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-18 | 2024-07-20 | 2024-07-18 | 2024-08-17 | 20 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337275 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL ISOLATION |  |  | 3 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-20 | 2024-07-21 | 2024-07-18 | 2024-08-17 | 30 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337275 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL ISOLATION |  |  | 1 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-18 | 2024-08-17 | 40 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337275 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL ISOLATION |  |  | 2 | 0 | Empty | 2024-07-18 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-18 | 2024-08-17 | 50 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL ISOLATION | Unknown
A | DFF-IPHP | WPM | MTN-INST | PRODTECH | 2400244402 | 1Y NITROGEN GEN SKID MAINT-DFCM-A-0807 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2023-04-09 | 2023-05-09 | 10 | SECE | SECE | DF /C /74/DFCM-A-0807 | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-INST | MTN-MECH | 2400244402 | 1Y NITROGEN GEN SKID MAINT-DFCM-A-0807 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-24 | 2023-04-09 | 2023-05-09 | 20 | SECE | SECE | DF /C /74/DFCM-A-0807 | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-INST | MTN-INST | 2400244402 | 1Y NITROGEN GEN SKID MAINT-DFCM-A-0807 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2023-04-09 | 2023-05-09 | 30 | SECE | SECE | DF /C /74/DFCM-A-0807 | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-INST | PRODTECH | 2400244402 | 1Y NITROGEN GEN SKID MAINT-DFCM-A-0807 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2023-04-09 | 2023-05-09 | 40 | SECE | SECE | DF /C /74/DFCM-A-0807 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235848 | 4Y 400V E-SWB MAINT DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235848 | 4Y 400V E-SWB MAINT DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235848 | 4Y 400V E-SWB MAINT DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235848 | 4Y 400V E-SWB MAINT DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A11 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328719 | 1Y FIRE DOORS TEST - DFA | FIRE DOORS TEST - DFA | SECE | SECE | 5 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-06-05 | 10 | SECE | SECE | DF /A /02/FIRE-DOORS | FIRE DOORS TEST - DFA | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-03-28 | 2022-05-24 | 2022-10-21 | 10 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 6 | 6 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-03-28 | 2022-05-24 | 2022-10-21 | 20 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 24 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-03-31 | 2022-05-24 | 2022-10-21 | 30 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 24 | 24 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-31 | 2024-04-01 | 2022-05-24 | 2022-10-21 | 40 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 16 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-01 | 2024-04-02 | 2022-05-24 | 2022-10-21 | 50 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 16 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-02 | 2024-04-04 | 2022-05-24 | 2022-10-21 | 51 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 8 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2022-05-24 | 2022-10-21 | 60 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064275 | SYNSR-667006 DFC - Repair stair EL +6365 | DFC - Repair stair EL +63650 ST044 |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2022-05-24 | 2022-10-21 | 70 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +63650 ST044 | Unknown
4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100099731 | ANOPR: Replacement spool. DFFA-FCV-35030 | Losen bolts and install new spool - torq |  |  | 0 | 0 | Empty | 2024-04-03 | 2024-04-07 | 2024-04-03 | 2024-04-03 | 2024-04-03 | 2026-09-20 | 10 |  |  | DF /F /54/DFF-10-WI-035-7021-AM-F | Losen bolts and install new spool - torq | Unknown
4 | NE | WDF | MTN-MECH | PRODTECH | 2100099731 | ANOPR: Replacement spool. DFFA-FCV-35030 | Losen bolts and install new spool - torq |  |  | 2 | 0 | Empty | 2024-04-03 | 2024-04-07 | 2024-04-03 | 2024-04-04 | 2024-04-03 | 2026-09-20 | 20 |  |  | DF /F /54/DFF-10-WI-035-7021-AM-F | Losen bolts and install new spool - torq | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100099731 | ANOPR: Replacement spool. DFFA-FCV-35030 | Losen bolts and install new spool - torq |  |  | 12 | 0 | Empty | 2024-04-03 | 2024-04-07 | 2024-04-04 | 2024-04-05 | 2024-04-03 | 2026-09-20 | 30 |  |  | DF /F /54/DFF-10-WI-035-7021-AM-F | Losen bolts and install new spool - torq | Unknown
4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100099731 | ANOPR: Replacement spool. DFFA-FCV-35030 | Losen bolts and install new spool - torq |  |  | 12 | 0 | Empty | 2024-04-03 | 2024-04-07 | 2024-04-05 | 2024-04-07 | 2024-04-03 | 2026-09-20 | 40 |  |  | DF /F /54/DFF-10-WI-035-7021-AM-F | Losen bolts and install new spool - torq | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100099731 | ANOPR: Replacement spool. DFFA-FCV-35030 | Losen bolts and install new spool - torq |  |  | 2 | 0 | Empty | 2024-04-03 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-03 | 2026-09-20 | 50 |  |  | DF /F /54/DFF-10-WI-035-7021-AM-F | Losen bolts and install new spool - torq | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100099731 | ANOPR: Replacement spool. DFFA-FCV-35030 | Losen bolts and install new spool - torq |  |  | 0 | 0 | Empty | 2024-04-03 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-03 | 2026-09-20 | 60 |  |  | DF /F /54/DFF-10-WI-035-7021-AM-F | Losen bolts and install new spool - torq | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400337682 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-7 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 19 | 0 | Empty | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-08-21 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-7 | ATEX EQUIPMENT INSPECTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291803 | 6M POT WATER SAMPLE PUMP MAINT-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-25 | 2023-12-14 | 10 |  |  | DF /C /85/DFCM-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400291803 | 6M POT WATER SAMPLE PUMP MAINT-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-25 | 2023-12-14 | 20 |  |  | DF /C /85/DFCM-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100024888 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L3 Isolate equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2019-04-11 | 2019-05-21 | 10 | AWSC | AWSC | DF /C /27/DFCM-P-5015 | L3 Isolate equipment | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024888 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L3 Isolate equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2019-04-11 | 2019-05-21 | 20 | AWSC | AWSC | DF /C /27/DFCM-P-5015 | L3 Isolate equipment | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024888 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L3 Isolate equipment | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-03 | 2019-04-11 | 2019-05-21 | 25 | AWSC | AWSC | DF /C /27/DFCM-P-5015 | L3 Isolate equipment | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | PRODTECH | 2100024888 | SMAT:ExCHNG HCV+CHK vlv downstream DFCM | L3 Isolate equipment | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2019-04-11 | 2019-05-21 | 30 | AWSC | AWSC | DF /C /27/DFCM-P-5015 | L3 Isolate equipment | Unknown
D | NOSD | WPM | MTN-INST | MTN-TELE | 2400344340 | 1Y DFC FLOW COMP CHECK - METERING | DFC FLOW COMP CHECK - METERING | AWSC | AWSC | 2 | 0 | Empty | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-09-26 | 10 | AWSC | AWSC | DF /C /34/DFCI-FY-37014 | DFC FLOW COMP CHECK - METERING | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235587 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-04 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1830-04B1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235587 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-04 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1830-04B1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235587 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-04 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1830-04B1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235587 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-04 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1830-04B1 | DE-ISOLATION ELECTRICAL | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-INST | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 36 | 36 | Empty | 2024-02-24 | 2024-03-10 | 2024-02-22 | 2024-02-24 | 2024-02-22 | 2024-03-08 | 10 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-SCAF | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 0 | 32 | Empty | 2024-02-24 | 2024-03-10 | 2024-02-24 | 2024-02-24 | 2024-02-22 | 2024-03-08 | 20 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-RIGG | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 16 | 16 | Empty | 2024-02-24 | 2024-03-10 | 2024-02-24 | 2024-02-26 | 2024-02-22 | 2024-03-08 | 25 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-MECH | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 24 | 66 | Empty | 2024-02-24 | 2024-03-10 | 2024-02-26 | 2024-02-29 | 2024-02-22 | 2024-03-08 | 30 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-RIGG | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 32 | 46 | Empty | 2024-02-24 | 2024-03-10 | 2024-02-29 | 2024-03-04 | 2024-02-22 | 2024-03-08 | 40 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-RIGG | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 16 | 0 | Empty | 2024-02-24 | 2024-03-10 | 2024-03-04 | 2024-03-06 | 2024-02-22 | 2024-03-08 | 50 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
1 | DFF-3520 | WDF | MTN-INST | MTN-SCAF | 2100107792 | FCV-350207 (3520) - Change Valve | Change Valve |  |  | 32 | 0 | Empty | 2024-02-24 | 2024-03-10 | 2024-03-06 | 2024-03-10 | 2024-02-22 | 2024-03-08 | 60 |  |  | DF /F /54/DFFA-FY-350207 | Change Valve | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235769 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-08B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235769 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-08B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235769 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-08B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235769 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-08B1 | ISOLATION ELECTRICAL | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-RIGG | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2021-02-01 | 2021-03-13 | 10 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | PRODTECH | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-17 | 2021-02-01 | 2021-03-13 | 20 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-MECH | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-18 | 2021-02-01 | 2021-03-13 | 30 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-MECH | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2021-02-01 | 2021-03-13 | 40 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-RIGG | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2021-02-01 | 2021-03-13 | 50 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-MECH | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2021-02-01 | 2021-03-13 | 60 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | PRODTECH | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2021-02-01 | 2021-03-13 | 70 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-MECH | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2021-02-01 | 2021-03-13 | 80 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
3 | DFF-5701 | WDF | MTN-MECH | MTN-RIGG | 2100044486 | Actuator heverly cooroded | L3 Isolate control air for FCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2021-02-01 | 2021-03-13 | 90 |  |  | DF /F /70/DFFA-FCV-570233 | L3 Isolate control air for FCV | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339103 | DFC_1Y_67955 INT STRUCT INSP - GVI | DFC_1Y_67955 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_67955 (FOAM MONITOR PF) | DFC_1Y_67955 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346562 | 3M SPRINKLER-SYSTEM MAINT-DFC | SPRINKLER-SYSTEM MAINT-DFC | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-10-02 | 10 | SECE | SECE | DF /C /01/SPRINKLER-SYSTEM | SPRINKLER-SYSTEM MAINT-DFC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2023-04-05 | 2023-08-18 | 10 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2023-04-05 | 2023-08-18 | 20 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2023-04-05 | 2023-08-18 | 30 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2023-04-05 | 2023-08-18 | 40 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 15 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-19 | 2023-04-05 | 2023-08-18 | 50 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-04-05 | 2023-08-18 | 60 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-04-05 | 2023-08-18 | 70 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-04-05 | 2023-08-18 | 80 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2023-04-05 | 2023-08-18 | 90 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085824 | Exchange of DFGA-P-3959 | New pump and materials for installation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2023-04-05 | 2023-08-18 | 100 |  |  | DF /G /75/DFGA-P-3959 | New pump and materials for installation | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 5 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-16 | 2024-11-17 | 2024-11-15 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-17 | 2024-11-17 | 2024-11-15 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-17 | 2024-11-18 | 2024-11-15 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
A | NE | WPM | MTN-MECH | VEN-INSP | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-18 | 2024-11-18 | 2024-11-15 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
A | NE | WPM | MTN-MECH | MTN-SCAF | 2400284300 | PSV Exchange - DFGA-VAB-500867 | Scaffolding | AWSC | AWSC | 10 | 0 | Empty | 2024-11-15 | 2024-11-19 | 2024-11-18 | 2024-11-19 | 2024-11-15 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /27/DFGA-VAB-500867 | Scaffolding | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029879 | FE07 lækker internt i Master ventil | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2020-03-23 | 2020-05-02 | 10 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029879 | FE07 lækker internt i Master ventil | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2020-03-23 | 2020-05-02 | 20 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029879 | FE07 lækker internt i Master ventil | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2020-03-23 | 2020-05-02 | 25 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029879 | FE07 lækker internt i Master ventil | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2020-03-23 | 2020-05-02 | 30 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2020-05-23 | 2020-08-21 | 10 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2020-05-23 | 2020-08-21 | 20 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2020-05-23 | 2020-08-21 | 30 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-01 | 2020-05-23 | 2020-08-21 | 40 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2020-05-23 | 2020-08-21 | 50 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2020-05-23 | 2020-08-21 | 60 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100031604 | Leaking vaccum breaker for DFFA-P-5302 | Scaffold erection Step-up work PF |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2020-05-23 | 2020-08-21 | 70 |  |  | DF /F /50/DFFA-VBA-5302 | Scaffold erection Step-up work PF | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092672 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-12 | 2024-08-13 | 2023-07-27 | 2023-12-09 | 10 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100092672 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-13 | 2024-08-16 | 2023-07-27 | 2023-12-09 | 20 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092672 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-13 | 2024-08-14 | 2023-07-27 | 2023-12-09 | 30 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092672 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2023-07-27 | 2023-12-09 | 40 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100092672 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-14 | 2024-08-17 | 2023-07-27 | 2023-12-09 | 50 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
D | DAB-WI | WPM | PRODTECH | PRODTECH | 2400343719 | PIGGING, P3010 12" DFF-DAD WI 2W | P3010_DFF-DAD | AWSC | AWSC | 4 | 0 | Empty | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-09-06 | 2024-09-12 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673010 | P3010_DFF-DAD | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400329530 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-22 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 38 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-04-14 | 2024-06-15 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-22 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322251 | DFC-75-CI-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | Empty | WDF | MTN-ROPE | MTN-MECH | 2100057179 | ANOPR: Utility & Instrument Air Batch-01 | SCFM 9V corrosion to DFB-1"-AU-54855-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-01-07 | 2022-06-06 | 10 |  |  | DF /B /07/DFB-1-AU-054-0855-A1-U | SCFM 9V corrosion to DFB-1"-AU-54855-A1 | Unknown
4 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100057179 | ANOPR: Utility & Instrument Air Batch-01 | SCFM 9V corrosion to DFB-1"-AU-54855-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-01-07 | 2022-06-06 | 20 |  |  | DF /B /07/DFB-1-AU-054-0855-A1-U | SCFM 9V corrosion to DFB-1"-AU-54855-A1 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325739 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /F /75/DFFA-A-39704 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339281 | DFF_1Y_46060 INT STRUCT INSP - GVI | DFF_1Y_46060 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_46060 (WL MODULE DECK) | DFF_1Y_46060 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400293705 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 0 | Empty | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-20 | 2023-12-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100047335 | Mount glass and stop button DFA LC-3914 | Replace broken/missing parts |  |  | 2 | 0 | W35-W36 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2021-04-08 | 2021-07-07 | 10 |  |  | DF /A /75/DFAA-PM-3914 | Replace broken/missing parts | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100047335 | Mount glass and stop button DFA LC-3914 | Replace broken/missing parts |  |  | 1 | 0 | W35-W36 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2021-04-08 | 2021-07-07 | 20 |  |  | DF /A /75/DFAA-PM-3914 | Replace broken/missing parts | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100047335 | Mount glass and stop button DFA LC-3914 | Replace broken/missing parts |  |  | 2 | 0 | W35-W36 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2021-04-08 | 2021-07-07 | 30 |  |  | DF /A /75/DFAA-PM-3914 | Replace broken/missing parts | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100047335 | Mount glass and stop button DFA LC-3914 | Replace broken/missing parts |  |  | 0 | 0 | W35-W36 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2021-04-08 | 2021-07-07 | 40 |  |  | DF /A /75/DFAA-PM-3914 | Replace broken/missing parts | Unknown
3 | DFF-LP-2 | WDF | MTN-MECH | MTN-MECH | 2100053196 | DFF LP-komp. OIl TCV 420525 defekt | Isolet the LPcomp units |  |  | 0 | 0 | W35-W36 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-08-12 | 2021-09-21 | 10 |  |  | DF /F /31/DFFA-TCV-420525 | Isolet the LPcomp units | Unknown
3 | DFF-LP-2 | WDF | MTN-MECH | PRODTECH | 2100053196 | DFF LP-komp. OIl TCV 420525 defekt | Isolet the LPcomp units |  |  | 2 | 0 | W35-W36 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-08-12 | 2021-09-21 | 20 |  |  | DF /F /31/DFFA-TCV-420525 | Isolet the LPcomp units | Unknown
3 | DFF-LP-2 | WDF | MTN-MECH | MTN-MECH | 2100053196 | DFF LP-komp. OIl TCV 420525 defekt | Isolet the LPcomp units |  |  | 6 | 0 | W35-W36 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-08-12 | 2021-09-21 | 30 |  |  | DF /F /31/DFFA-TCV-420525 | Isolet the LPcomp units | Unknown
3 | DFF-LP-2 | WDF | MTN-MECH | PRODTECH | 2100053196 | DFF LP-komp. OIl TCV 420525 defekt | Isolet the LPcomp units |  |  | 2 | 0 | W35-W36 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-08-12 | 2021-09-21 | 40 |  |  | DF /F /31/DFFA-TCV-420525 | Isolet the LPcomp units | Unknown
3 | NE | WRO | MTN-ELEC | VEN-ELEC | 2300000779 | DAF PM lys, JB og H/T materialer 2019 | DAF PM lys og H/T materialer 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-01-11 | 2020-12-31 | 10 |  |  | DF /C /6 | DAF PM lys og H/T materialer 2019 | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100105557 | 4Y400/230V UPS-DP-F,TES-DFGA-DP-1940A/B | Site Visit - TBT. Coordinate with CCR | AWSC | AWSC | 0 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-01-17 | 2024-03-02 | 10 | AWSC | AWSC | DF /G /06/DFGA-DP-1940A | Site Visit - TBT. Coordinate with CCR | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100105557 | 4Y400/230V UPS-DP-F,TES-DFGA-DP-1940A/B | Site Visit - TBT. Coordinate with CCR | AWSC | AWSC | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-01-17 | 2024-03-02 | 20 | AWSC | AWSC | DF /G /06/DFGA-DP-1940A | Site Visit - TBT. Coordinate with CCR | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100105557 | 4Y400/230V UPS-DP-F,TES-DFGA-DP-1940A/B | Site Visit - TBT. Coordinate with CCR | AWSC | AWSC | 3 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-01-17 | 2024-03-02 | 30 | AWSC | AWSC | DF /G /06/DFGA-DP-1940A | Site Visit - TBT. Coordinate with CCR | Unknown
2 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100105557 | 4Y400/230V UPS-DP-F,TES-DFGA-DP-1940A/B | Site Visit - TBT. Coordinate with CCR | AWSC | AWSC | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-01-17 | 2024-03-02 | 40 | AWSC | AWSC | DF /G /06/DFGA-DP-1940A | Site Visit - TBT. Coordinate with CCR | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-08 | 2024-01-10 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-11 | 2024-01-11 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-11 | 2024-01-14 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-14 | 2024-01-15 | 2022-02-07 | 2022-07-07 | 45 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-15 | 2024-01-19 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-19 | 2024-01-20 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009220 | Insulation assist FORCE 19002 | Bilfinger inspection |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-22 | 2024-01-20 | 2024-01-22 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /C /01/DFC-3-WF-003-0047-A3-F | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100099830 | FA-05 THP PIT-30029 DBB int leak | Replace DBB valve & calibrate PIT |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-26 | 2024-04-09 | 10 |  |  | DF /A /10/DFAA-PIT-30029 | Replace DBB valve & calibrate PIT | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099830 | FA-05 THP PIT-30029 DBB int leak | Replace DBB valve & calibrate PIT |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-26 | 2024-04-09 | 20 |  |  | DF /A /10/DFAA-PIT-30029 | Replace DBB valve & calibrate PIT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092673 | Rep of Lighting Fixtures | DE-ISOLATE AND TEST |  |  | 5 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-12 | 2024-08-13 | 2023-07-27 | 2023-12-09 | 10 |  |  | DF /F /05/DFFA-N-1812 | DE-ISOLATE AND TEST | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100092673 | Rep of Lighting Fixtures | DE-ISOLATE AND TEST |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-13 | 2024-08-16 | 2023-07-27 | 2023-12-09 | 20 |  |  | DF /F /05/DFFA-N-1812 | DE-ISOLATE AND TEST | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092673 | Rep of Lighting Fixtures | DE-ISOLATE AND TEST |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-13 | 2024-08-14 | 2023-07-27 | 2023-12-09 | 30 |  |  | DF /F /05/DFFA-N-1812 | DE-ISOLATE AND TEST | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092673 | Rep of Lighting Fixtures | DE-ISOLATE AND TEST |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-14 | 2024-08-17 | 2023-07-27 | 2023-12-09 | 40 |  |  | DF /F /05/DFFA-N-1812 | DE-ISOLATE AND TEST | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100092673 | Rep of Lighting Fixtures | DE-ISOLATE AND TEST |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-14 | 2024-08-14 | 2023-07-27 | 2023-12-09 | 50 |  |  | DF /F /05/DFFA-N-1812 | DE-ISOLATE AND TEST | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400336966 | PIGGING, P3014 16" DFF-HDA WI 2W | P3014_DFF-HDA | AWSC | AWSC | 4 | 6 | Empty | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-04 | 2024-08-10 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673014 | P3014_DFF-HDA | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235632 | 4Y 380V N-SWB MAINT-DFFA-N-1803-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235632 | 4Y 380V N-SWB MAINT-DFFA-N-1803-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235632 | 4Y 380V N-SWB MAINT-DFFA-N-1803-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235632 | 4Y 380V N-SWB MAINT-DFFA-N-1803-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803-01 | ISOLATION ELECTRICAL | Unknown
A | DFX-LIFT | WPM | MTN-MECH | PRODTECH | 2400346567 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | ISOLATION BY PRODUCTION | SECE | SECE | 15 | 0 | Empty | 2024-09-04 | 2024-09-22 | 2024-09-04 | 2024-09-07 | 2024-09-04 | 2024-10-04 | 10 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFX-LIFT | WPM | MTN-MECH | MTN-MECH | 2400346567 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | ISOLATION BY PRODUCTION | SECE | SECE | 45 | 0 | Empty | 2024-09-04 | 2024-09-22 | 2024-09-07 | 2024-09-18 | 2024-09-04 | 2024-10-04 | 20 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFX-LIFT | WPM | MTN-MECH | MTN-INST | 2400346567 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-04 | 2024-09-22 | 2024-09-19 | 2024-09-19 | 2024-09-04 | 2024-10-04 | 30 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFX-LIFT | WPM | MTN-MECH | PRODTECH | 2400346567 | 1Y SDV LUBE/FUNC TEST - DFA/B/C/E | ISOLATION BY PRODUCTION | SECE | SECE | 15 | 0 | Empty | 2024-09-04 | 2024-09-22 | 2024-09-19 | 2024-09-22 | 2024-09-04 | 2024-10-04 | 40 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400344057 | 1Y PORTABLE RADIO TEST-DFC | PORTABLE RADIO TEST-DFC | SECE | SECE | 7 | 7 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-08-23 | 2024-09-22 | 10 | SECE | SECE | DF /C /08/EXTERNAL-COMMUNICATION | PORTABLE RADIO TEST-DFC | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | PRODTECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-26 | 2024-08-26 | 2024-02-26 | 2024-07-10 | 10 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-26 | 2024-08-27 | 2024-02-26 | 2024-07-10 | 20 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-RIGG | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-27 | 2024-08-28 | 2024-02-26 | 2024-07-10 | 30 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-28 | 2024-08-29 | 2024-02-26 | 2024-07-10 | 40 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-RIGG | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-29 | 2024-08-30 | 2024-02-26 | 2024-07-10 | 50 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-30 | 2024-08-31 | 2024-02-26 | 2024-07-10 | 60 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-INST | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-31 | 2024-09-01 | 2024-02-26 | 2024-07-10 | 61 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-02-26 | 2024-07-10 | 70 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | PRODTECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2024-02-26 | 2024-07-10 | 80 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100105186 | Repleace complete DFCI-PCV-34003 | Isolate PCV-34003 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-02-26 | 2024-07-10 | 90 |  |  | DF /C /11/DFCI-PCV-34003 | Isolate PCV-34003 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400315641 | 3M CRUDE OIL EXP. SKD MAINT-DFCM-A-3650 | CRUDE OIL EXPORT SKD MAINT-DFCM-A-3650 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-10 | 2024-04-21 | 10 |  |  | DF /C /23/DFCM-A-3650 | CRUDE OIL EXPORT SKD MAINT-DFCM-A-3650 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400281092 | 1Y SEWER TREAT. UNIT MAINT DFCM-A-5101 | SEWER TREAT. UNIT MAINT DFCM-A-5101 | SCH | SCH | 24 | 6 | 24-W03-04 | 2024-01-16 | 2024-01-27 | 2024-01-16 | 2024-01-21 | 2023-08-27 | 2023-10-02 | 10 | SCH | SCH | DF /C /82/DFCM-A-5101 | SEWER TREAT. UNIT MAINT DFCM-A-5101 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400281092 | 1Y SEWER TREAT. UNIT MAINT DFCM-A-5101 | SEWER TREAT. UNIT MAINT DFCM-A-5101 | SCH | SCH | 24 | 0 | 24-W03-04 | 2024-01-16 | 2024-01-27 | 2024-01-22 | 2024-01-27 | 2023-08-27 | 2023-10-02 | 20 | SCH | SCH | DF /C /82/DFCM-A-5101 | SEWER TREAT. UNIT MAINT DFCM-A-5101 | Unknown
3 | DFB-W20 | WDF | MTN-INST | PRODTECH | 2100065074 | DFB-20 ZT'er ustabil, choke holdes i man | Isolate and Inhibit Position Measurement | AWSC | AWSC | 2 | 0 | W37 IOP? | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-04-09 | 2022-07-08 | 10 | AWSC | AWSC | DF /B /55/DFBA-ZT-30423 | Isolate and Inhibit Position Measurement | Unknown
3 | DFB-W20 | WDF | MTN-INST | MTN-INST | 2100065074 | DFB-20 ZT'er ustabil, choke holdes i man | Isolate and Inhibit Position Measurement | AWSC | AWSC | 2 | 0 | W37 IOP? | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2022-04-09 | 2022-07-08 | 20 | AWSC | AWSC | DF /B /55/DFBA-ZT-30423 | Isolate and Inhibit Position Measurement | Unknown
3 | DFB-W20 | WDF | MTN-INST | MTN-INST | 2100065074 | DFB-20 ZT'er ustabil, choke holdes i man | Isolate and Inhibit Position Measurement | AWSC | AWSC | 2 | 0 | W37 IOP? | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-04-09 | 2022-07-08 | 30 | AWSC | AWSC | DF /B /55/DFBA-ZT-30423 | Isolate and Inhibit Position Measurement | Unknown
3 | DFB-W20 | WDF | MTN-INST | PRODTECH | 2100065074 | DFB-20 ZT'er ustabil, choke holdes i man | Isolate and Inhibit Position Measurement | AWSC | AWSC | 2 | 0 | W37 IOP? | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2022-04-09 | 2022-07-08 | 40 | AWSC | AWSC | DF /B /55/DFBA-ZT-30423 | Isolate and Inhibit Position Measurement | Unknown
C | NOSD | WPM | MTN-TURB | MTN-TURB | 2400350883 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-10-03 | 2024-10-05 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-08 | 1 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-TURB | MTN-TURB | 2400350883 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-10-03 | 2024-10-05 | 2024-10-03 | 2024-10-05 | 2024-10-03 | 2024-10-08 | 10 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2023-04-17 | 2023-06-01 | 10 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2023-04-17 | 2023-06-01 | 20 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2023-04-17 | 2023-06-01 | 25 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2023-04-17 | 2023-06-01 | 30 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-17 | 2023-04-17 | 2023-06-01 | 40 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2023-04-17 | 2023-06-01 | 50 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-17 | 2023-06-01 | 60 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-17 | 2023-06-01 | 70 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2023-04-17 | 2023-06-01 | 75 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-17 | 2023-06-01 | 80 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2023-04-17 | 2023-06-01 | 90 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089240 | DFG Anti Fouling alarm on TI Anode | Removal of JB + cables |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2023-04-17 | 2023-06-01 | 100 |  |  | DF /G /52/DFGA-A-5501 | Removal of JB + cables | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087265 | Battery fault on emergency lights | Battery fault on emergency lights |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-27 | 2023-09-09 | 10 |  |  | DF /F /61/DFFB-DP-1832A-01-Q05 | Battery fault on emergency lights | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087265 | Battery fault on emergency lights | Battery fault on emergency lights |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-27 | 2023-09-09 | 20 |  |  | DF /F /61/DFFB-DP-1832A-01-Q05 | Battery fault on emergency lights | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087265 | Battery fault on emergency lights | Battery fault on emergency lights |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-27 | 2023-09-09 | 30 |  |  | DF /F /61/DFFB-DP-1832A-01-Q05 | Battery fault on emergency lights | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087265 | Battery fault on emergency lights | Battery fault on emergency lights |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-04-27 | 2023-09-09 | 40 |  |  | DF /F /61/DFFB-DP-1832A-01-Q05 | Battery fault on emergency lights | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049115 | DFF Hydro cyclon reject XCV stock | Isolation of valve | PCNF | PCNF | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-05-03 | 2021-06-12 | 10 | PCNF | PCNF | DF /F /27/DFFA-XCV-500721 | Isolation of valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049115 | DFF Hydro cyclon reject XCV stock | Isolation of valve | PCNF | PCNF | 6 | 30 | W25-W26 | 2024-06-17 | 2024-06-17 | 2023-02-13 | 2023-06-09 | 2021-05-03 | 2021-06-12 | 30 | PCNF | PCNF | DF /F /27/DFFA-XCV-500721 | Isolation of valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049115 | DFF Hydro cyclon reject XCV stock | Isolation of valve | PCNF | PCNF | 4 | 12 | W25-W26 | 2024-06-17 | 2024-06-17 | 2023-02-13 | 2023-06-09 | 2021-05-03 | 2021-06-12 | 35 | PCNF | PCNF | DF /F /27/DFFA-XCV-500721 | Isolation of valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049115 | DFF Hydro cyclon reject XCV stock | Isolation of valve | PCNF | PCNF | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-05-03 | 2021-06-12 | 40 | PCNF | PCNF | DF /F /27/DFFA-XCV-500721 | Isolation of valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049115 | DFF Hydro cyclon reject XCV stock | Isolation of valve | PCNF | PCNF | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-05-03 | 2021-06-12 | 50 | PCNF | PCNF | DF /F /27/DFFA-XCV-500721 | Isolation of valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049115 | DFF Hydro cyclon reject XCV stock | Isolation of valve | PCNF | PCNF | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-05-03 | 2021-06-12 | 999 | PCNF | PCNF | DF /F /27/DFFA-XCV-500721 | Isolation of valve | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339045 | DFB_1Y_24720 INT STRUCT INSP - GVI | DFB_1Y_24720 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_24720 (MEZZANINE DECK) | DFB_1Y_24720 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400344342 | 4Y HEAT DETECTORS CHECK - DFF/G | HEAT DETECTORS CHECK | SECE | SECE | 58 | 72 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-29 | 2024-07-18 | 2024-09-29 | 10 | SECE | SECE | DF /F /03/FGS-DETECTORS | HEAT DETECTORS CHECK | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400282089 | 1Y BREATH. AIR COMP. MAINT - A-5405/5406 | BREATH. AIR COMP. MAINT - A-5405/5406 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-18 | 2023-10-24 | 10 |  |  | DF /G /02/DFGA-A-5405 | BREATH. AIR COMP. MAINT - A-5405/5406 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400282089 | 1Y BREATH. AIR COMP. MAINT - A-5405/5406 | BREATH. AIR COMP. MAINT - A-5405/5406 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-18 | 2023-10-24 | 20 |  |  | DF /G /02/DFGA-A-5405 | BREATH. AIR COMP. MAINT - A-5405/5406 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259301 | 6M DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG |  |  | 2 | 0 | Empty | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-06-02 | 2023-06-21 | 10 |  |  | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025154 | DFGA-V-5072 DFG Drain sep. defekt 2" ven | L3 Isolate DFG Drain sep. defekt 2" vent |  |  | 3 | 0 | W33-W34 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2018-11-11 | 2019-04-10 | 10 |  |  | DF /G /28/DFGA-V-5072 | L3 Isolate DFG Drain sep. defekt 2" vent | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025154 | DFGA-V-5072 DFG Drain sep. defekt 2" ven | L3 Isolate DFG Drain sep. defekt 2" vent |  |  | 6 | 0 | W33-W34 | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2018-11-11 | 2019-04-10 | 20 |  |  | DF /G /28/DFGA-V-5072 | L3 Isolate DFG Drain sep. defekt 2" vent | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025154 | DFGA-V-5072 DFG Drain sep. defekt 2" ven | L3 Isolate DFG Drain sep. defekt 2" vent |  |  | 3 | 0 | W33-W34 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2018-11-11 | 2019-04-10 | 30 |  |  | DF /G /28/DFGA-V-5072 | L3 Isolate DFG Drain sep. defekt 2" vent | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024003 | Replace of valve PCV-57739. | L3 Pre. Install rigging gear |  |  | 2 | 0 | Prod Req. | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2018-05-13 | 2018-08-11 | 10 |  |  | DF /C /70/DFCM-PCV-57739 | L3 Pre. Install rigging gear | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024003 | Replace of valve PCV-57739. | L3 Pre. Install rigging gear |  |  | 2 | 0 | Prod Req. | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2018-05-13 | 2018-08-11 | 20 |  |  | DF /C /70/DFCM-PCV-57739 | L3 Pre. Install rigging gear | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024003 | Replace of valve PCV-57739. | L3 Pre. Install rigging gear |  |  | 12 | 0 | Prod Req. | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2018-05-13 | 2018-08-11 | 30 |  |  | DF /C /70/DFCM-PCV-57739 | L3 Pre. Install rigging gear | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024003 | Replace of valve PCV-57739. | L3 Pre. Install rigging gear |  |  | 2 | 0 | Prod Req. | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2018-05-13 | 2018-08-11 | 40 |  |  | DF /C /70/DFCM-PCV-57739 | L3 Pre. Install rigging gear | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024003 | Replace of valve PCV-57739. | L3 Pre. Install rigging gear |  |  | 2 | 0 | Prod Req. | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2018-05-13 | 2018-08-11 | 50 |  |  | DF /C /70/DFCM-PCV-57739 | L3 Pre. Install rigging gear | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2018-01-18 | 2018-02-27 | 10 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2018-01-18 | 2018-02-27 | 20 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 6.700000000000000177635683938 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-23 | 2018-01-18 | 2018-02-27 | 30 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 5.4000000000000003552713678785 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-24 | 2018-01-18 | 2018-02-27 | 35 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-24 | 2024-09-24 | 2018-01-18 | 2018-02-27 | 40 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 5.4000000000000003552713678785 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-24 | 2024-09-25 | 2018-01-18 | 2018-02-27 | 50 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 6.700000000000000177635683938 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-25 | 2024-09-25 | 2018-01-18 | 2018-02-27 | 60 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-25 | 2024-09-25 | 2018-01-18 | 2018-02-27 | 70 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | QAQCELEC | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-25 | 2024-09-26 | 2018-01-18 | 2018-02-27 | 80 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-26 | 2018-01-18 | 2018-02-27 | 85 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 5.4000000000000003552713678785 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2018-01-18 | 2018-02-27 | 90 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024659 | DFF 12" Halfdan HP Gas Pig Receiver | L3-Safing of system |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2018-01-18 | 2018-02-27 | 100 |  |  | DF /F /34/DFFA-BDV-380313 | L3-Safing of system | Unknown
2 | DFB-W23 | WDF | MTN-INST | MTN-INST | 2100076351 | DFB-23 Choke ZSO, ZSC & ZT adjustment | Calibrate Position Switch ZSO |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-10-17 | 2022-12-01 | 10 |  |  | DF /B /55/DFBA-ZT-30426 | Calibrate Position Switch ZSO | Unknown
2 | DFB-W23 | WDF | MTN-INST | MTN-INST | 2100076351 | DFB-23 Choke ZSO, ZSC & ZT adjustment | Calibrate Position Switch ZSO |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-10-17 | 2022-12-01 | 20 |  |  | DF /B /55/DFBA-ZT-30426 | Calibrate Position Switch ZSO | Unknown
2 | DFB-W23 | WDF | MTN-INST | MTN-INST | 2100076351 | DFB-23 Choke ZSO, ZSC & ZT adjustment | Calibrate Position Switch ZSO |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-10-17 | 2022-12-01 | 30 |  |  | DF /B /55/DFBA-ZT-30426 | Calibrate Position Switch ZSO | Unknown
2 | DFB-W23 | WDF | MTN-INST | MTN-INST | 2100076351 | DFB-23 Choke ZSO, ZSC & ZT adjustment | Calibrate Position Switch ZSO |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-10-17 | 2022-12-01 | 40 |  |  | DF /B /55/DFBA-ZT-30426 | Calibrate Position Switch ZSO | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022761 | DFC/78: SMAT Fit galvanized endstops run | L3 Erect Scaffold for endstops |  |  | 32 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-13 | 2023-02-16 | 2019-03-30 | 2019-06-28 | 10 |  |  | DF /C /78/DFCI-X-61120 | L3 Erect Scaffold for endstops | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022761 | DFC/78: SMAT Fit galvanized endstops run | L3 Erect Scaffold for endstops |  |  | 12 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-17 | 2023-02-19 | 2019-03-30 | 2019-06-28 | 20 |  |  | DF /C /78/DFCI-X-61120 | L3 Erect Scaffold for endstops | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022761 | DFC/78: SMAT Fit galvanized endstops run | L3 Erect Scaffold for endstops |  |  | 16 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-20 | 2023-02-21 | 2019-03-30 | 2019-06-28 | 30 |  |  | DF /C /78/DFCI-X-61120 | L3 Erect Scaffold for endstops | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 16 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-04 | 2024-07-06 | 2017-08-23 | 2017-11-21 | 5 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 12 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-01 | 2024-07-04 | 2017-08-23 | 2017-11-21 | 10 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-06 | 2024-07-06 | 2017-08-23 | 2017-11-21 | 20 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 12 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-06 | 2024-07-09 | 2017-08-23 | 2017-11-21 | 30 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-09 | 2024-07-09 | 2017-08-23 | 2017-11-21 | 40 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-09 | 2024-07-10 | 2017-08-23 | 2017-11-21 | 50 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 13.400000000000000355271367876 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-08 | 2024-07-10 | 2017-08-23 | 2017-11-21 | 60 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027370 | Replace cable DFBA-1810-71-L2A | Mount insulation |  |  | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-10 | 2024-07-09 | 2024-07-10 | 2017-08-23 | 2017-11-21 | 70 |  |  | DF /B /61/DFBA-N-1810-C_71 | Mount insulation | Unknown
3 | Empty | WRO | MTN-TELE | MTN-TELE | 2300006263 | Inst. & Test of Drag Reducer cabling | Inst. & Test of Drag Reducer cabling |  |  | 0 | 0 | Empty | 2023-09-14 | 2023-09-20 | 2023-09-14 | 2023-09-14 | 2023-09-14 | 2024-01-27 | 10 |  |  | DF /C | Inst. & Test of Drag Reducer cabling | Unknown
3 | Empty | WRO | MTN-TELE | MTN-TELE | 2300006263 | Inst. & Test of Drag Reducer cabling | Inst. & Test of Drag Reducer cabling |  |  | 60 | 25 | Empty | 2023-09-14 | 2023-09-20 | 2023-09-14 | 2023-09-20 | 2023-09-14 | 2024-01-27 | 20 |  |  | DF /C | Inst. & Test of Drag Reducer cabling | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286633 | 3M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-06 | 2023-11-16 | 10 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235589 | 4Y 680V E/N-DP-MAINT-DFC-L/S POWER EX | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1801 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235589 | 4Y 680V E/N-DP-MAINT-DFC-L/S POWER EX | ISOLATION ELECTRICAL | AWSC | AWSC | 47 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-09-22 | 2024-10-03 | 2023-03-16 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1801 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235589 | 4Y 680V E/N-DP-MAINT-DFC-L/S POWER EX | ISOLATION ELECTRICAL | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-10-04 | 2024-10-07 | 2023-03-16 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1801 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235589 | 4Y 680V E/N-DP-MAINT-DFC-L/S POWER EX | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2023-03-16 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1801 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329998 | 3M INSTR AIR SYSTEM MAINT - DFCM-A-5401 | INSTR AIR SYSTEM MAINT - DFCM-A-5401 |  |  | 3 | 0 | Empty | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2024-06-29 | 10 |  |  | DF /C /07/INSTRUMENT-AIR-SYSTEM | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106764 | Glycol circulation pump leaking | Setup/demaount gear and rigging |  |  | 0 | 56 | W29-W30 | 2024-07-25 | 2024-07-25 | 2024-07-16 | 2024-07-25 | 2024-03-05 | 2024-07-18 | 10 |  |  | DF /F /30/DFFA-P-4102 | Setup/demaount gear and rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100106764 | Glycol circulation pump leaking | Setup/demaount gear and rigging |  |  | 20 | 41 | W29-W30 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-03-05 | 2024-07-18 | 20 |  |  | DF /F /30/DFFA-P-4102 | Setup/demaount gear and rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100106764 | Glycol circulation pump leaking | Setup/demaount gear and rigging |  |  | 0 | 8 | W29-W30 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-03-05 | 2024-07-18 | 30 |  |  | DF /F /30/DFFA-P-4102 | Setup/demaount gear and rigging | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235287 | 4Y 3KV N-SWB MAINT DFCI-N-1801-10 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2022-12-16 | 2023-03-14 | 10 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-10-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235287 | 4Y 3KV N-SWB MAINT DFCI-N-1801-10 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 33 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-18 | 2022-12-16 | 2023-03-14 | 20 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-10-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235287 | 4Y 3KV N-SWB MAINT DFCI-N-1801-10 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 11 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-21 | 2022-12-16 | 2023-03-14 | 30 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-10-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-INST | 2400235287 | 4Y 3KV N-SWB MAINT DFCI-N-1801-10 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2022-12-16 | 2023-03-14 | 40 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-10-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235287 | 4Y 3KV N-SWB MAINT DFCI-N-1801-10 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2022-12-16 | 2023-03-14 | 50 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-10-01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-29 | 2024-07-31 | 2021-02-18 | 2021-05-19 | 9 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-31 | 2024-08-01 | 2021-02-18 | 2021-05-19 | 10 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-01 | 2024-08-01 | 2021-02-18 | 2021-05-19 | 20 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-01 | 2024-08-02 | 2021-02-18 | 2021-05-19 | 30 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-02 | 2024-08-03 | 2021-02-18 | 2021-05-19 | 40 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-03 | 2024-08-03 | 2021-02-18 | 2021-05-19 | 50 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-03 | 2024-08-04 | 2021-02-18 | 2021-05-19 | 60 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-08 | 2024-08-09 | 2021-02-18 | 2021-05-19 | 65 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-04 | 2024-08-05 | 2021-02-18 | 2021-05-19 | 70 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-05 | 2024-08-06 | 2021-02-18 | 2021-05-19 | 80 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-06 | 2024-08-06 | 2021-02-18 | 2021-05-19 | 90 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-06 | 2024-08-07 | 2021-02-18 | 2021-05-19 | 100 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044918 | DFG LCV-410491 Dårlig integritet | Isolate LCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-07 | 2024-08-08 | 2021-02-18 | 2021-05-19 | 110 |  |  | DF /G /30/DFGA-LCV-410491 | Isolate LCV | Unknown
3 | NOSD | WGN | MTN-CRAN | PRODTECH | 2200017651 | DFG/78: Crane Master 3 to Master 4 | Mobilization of Liebherr tech |  |  | 2 | 0 | Empty | 2024-08-26 | 2024-09-07 | 2024-08-26 | 2024-08-26 | 2024-04-06 | 2024-08-19 | 10 |  |  | DF /G /78/DFGA-A-6140 | Mobilization of Liebherr tech | Unknown
3 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200017651 | DFG/78: Crane Master 3 to Master 4 | Mobilization of Liebherr tech |  |  | 160 | 0 | Empty | 2024-08-26 | 2024-09-07 | 2024-08-26 | 2024-09-04 | 2024-04-06 | 2024-08-19 | 20 |  |  | DF /G /78/DFGA-A-6140 | Mobilization of Liebherr tech | Unknown
3 | NOSD | WGN | MTN-CRAN | MTN-RIGG | 2200017651 | DFG/78: Crane Master 3 to Master 4 | Mobilization of Liebherr tech |  |  | 10 | 0 | Empty | 2024-08-26 | 2024-09-07 | 2024-08-26 | 2024-08-27 | 2024-04-06 | 2024-08-19 | 30 |  |  | DF /G /78/DFGA-A-6140 | Mobilization of Liebherr tech | Unknown
3 | NOSD | WGN | MTN-CRAN | VEN-CRAN | 2200017651 | DFG/78: Crane Master 3 to Master 4 | Mobilization of Liebherr tech |  |  | 30 | 0 | Empty | 2024-08-26 | 2024-09-07 | 2024-09-04 | 2024-09-05 | 2024-04-06 | 2024-08-19 | 40 |  |  | DF /G /78/DFGA-A-6140 | Mobilization of Liebherr tech | Unknown
3 | NOSD | WGN | MTN-CRAN | MTN-ROUS | 2200017651 | DFG/78: Crane Master 3 to Master 4 | Mobilization of Liebherr tech |  |  | 15 | 0 | Empty | 2024-08-26 | 2024-09-07 | 2024-09-04 | 2024-09-07 | 2024-04-06 | 2024-08-19 | 50 |  |  | DF /G /78/DFGA-A-6140 | Mobilization of Liebherr tech | Unknown
3 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200017651 | DFG/78: Crane Master 3 to Master 4 | Mobilization of Liebherr tech |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-09-07 | 2024-08-26 | 2024-08-26 | 2024-04-06 | 2024-08-19 | 60 |  |  | DF /G /78/DFGA-A-6140 | Mobilization of Liebherr tech | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-13 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284315 | PSV Exchange - DFGA-PSV-410591 | new psv | AWSC | AWSC | 0 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /75/DFGA-PSV-410591 | new psv | Unknown
4 | DFF-5010 | WDF | MTN-MECH | PRODTECH | 2100029698 | HCV 3" Seawater supply sidder fast | Demount valve | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-06-04 | 2020-11-01 | 10 | AWSC | AWSC | DF /F /27/DFFA-V-5010 | Demount valve | Unknown
4 | DFF-5010 | WDF | MTN-MECH | MTN-MECH | 2100029698 | HCV 3" Seawater supply sidder fast | Demount valve | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2020-06-04 | 2020-11-01 | 20 | AWSC | AWSC | DF /F /27/DFFA-V-5010 | Demount valve | Unknown
4 | DFF-5010 | WDF | MTN-MECH | MTN-RIGG | 2100029698 | HCV 3" Seawater supply sidder fast | Demount valve | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2020-06-04 | 2020-11-01 | 30 | AWSC | AWSC | DF /F /27/DFFA-V-5010 | Demount valve | Unknown
4 | DFF-5010 | WDF | MTN-MECH | MTN-MECH | 2100029698 | HCV 3" Seawater supply sidder fast | Demount valve | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2020-06-04 | 2020-11-01 | 40 | AWSC | AWSC | DF /F /27/DFFA-V-5010 | Demount valve | Unknown
4 | DFF-5010 | WDF | MTN-MECH | PRODTECH | 2100029698 | HCV 3" Seawater supply sidder fast | Demount valve | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2020-06-04 | 2020-11-01 | 50 | AWSC | AWSC | DF /F /27/DFFA-V-5010 | Demount valve | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 10 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 240 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-09-23 | 2024-10-12 | 2023-04-06 | 2025-09-22 | 20 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 90 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-10-13 | 2024-10-20 | 2023-04-06 | 2025-09-22 | 21 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 60 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-10-13 | 2024-10-16 | 2023-04-06 | 2025-09-22 | 30 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 60 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-10-16 | 2024-10-19 | 2023-04-06 | 2025-09-22 | 40 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 48 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-10-19 | 2024-10-21 | 2023-04-06 | 2025-09-22 | 50 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-10-21 | 2024-10-23 | 2023-04-06 | 2025-09-22 | 60 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-10-21 | 2024-10-24 | 2023-04-06 | 2025-09-22 | 70 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100076005 | DFFW/78: Wire rope pulleys replacement | Re-order A frame sheave kit |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-10-24 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 80 |  |  | DF /F /78/DFFA-A-6102 | Re-order A frame sheave kit | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344324 | 6M FW HOSE REELS ACCOM MAINT-DFC | FW HOSE REELS ACCOM MAINT-DFC | SECE | SECE | 4 | 0 | Empty | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-28 | 10 | SECE | SECE | DF /C /01/FW-HOSEREELS | FW HOSE REELS ACCOM MAINT-DFC | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 2 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-13 | 2024-05-13 | 2023-10-13 | 2024-02-25 | 10 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 1 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-13 | 2024-05-13 | 2023-10-13 | 2024-02-25 | 20 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 4 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-13 | 2024-05-14 | 2023-10-13 | 2024-02-25 | 30 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 4 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-13 | 2024-05-13 | 2023-10-13 | 2024-02-25 | 40 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 4 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-14 | 2024-05-14 | 2023-10-13 | 2024-02-25 | 50 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 4 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2023-10-13 | 2024-02-25 | 60 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 1 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2023-10-13 | 2024-02-25 | 70 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 1 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2023-10-13 | 2024-02-25 | 80 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 1 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2023-10-13 | 2024-02-25 | 90 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097389 | DFF15 ext hyd leak manifold XCV actuator | Isolate Hydr. & Controls |  |  | 2 | 0 | Empty | 2024-05-13 | 2024-05-15 | 2024-05-14 | 2024-05-15 | 2023-10-13 | 2024-02-25 | 100 |  |  | DF /F /10/DFFA-XCV-301315 | Isolate Hydr. & Controls | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342399 | 3M LIFE-SAVING AND SAFETY EQ MAINT - DFB | LIFE-SAVING AND SAFETY EQ INSP | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-09-10 | 10 | SECE | SECE | DF /B /02/LIFE-SAVING-EQUIPMENT | LIFE-SAVING AND SAFETY EQ INSP | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235707 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR06-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235707 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR06 | ISOLATION ELECTRICAL | AWSC | AWSC | 19 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR06-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235707 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR06 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR06-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235707 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR06-BA001 | ISOLATION ELECTRICAL | Unknown
2 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300004774 | Power outlets and network in office cont | Install power outlets |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2023-02-12 | 2023-03-29 | 10 |  |  | DF /C /82 | Install power outlets | Unknown
2 | NE | WRO | MTN-ELEC | MTN-TELE | 2300004774 | Power outlets and network in office cont | Install power outlets |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2023-02-12 | 2023-03-29 | 20 |  |  | DF /C /82 | Install power outlets | Unknown
2 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300004774 | Power outlets and network in office cont | Install power outlets |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2023-02-12 | 2023-03-29 | 30 |  |  | DF /C /82 | Install power outlets | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027369 | Rope-Udskift rådne lampe supports | Rope access |  |  | 24 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-13 | 2023-02-15 | 2017-06-14 | 2017-07-24 | 10 |  |  | DF /C /6 | Rope access | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027369 | Rope-Udskift rådne lampe supports | Rope access |  |  | 24 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-16 | 2023-02-18 | 2017-06-14 | 2017-07-24 | 20 |  |  | DF /C /6 | Rope access | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 1 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 2 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 3 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 12 | Empty | 2025-01-01 | 2025-01-01 | 2023-04-07 | 2023-09-09 | 2015-11-14 | 2016-12-24 | 10 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 4 | 12 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 20 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 30 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 40 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 50 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 60 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 70 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 80 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 90 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 100 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 110 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 120 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 130 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-ROPE | 2100023809 | @-DFF-34 OIL XCV-301334 internlæk DFF | Prepare permit Weld | PCNFAWSC | PCNFAWSC | 8 | 8 | Empty | 2025-01-01 | 2025-01-01 | 2023-05-07 | 2023-09-09 | 2015-11-14 | 2016-12-24 | 140 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301334 | Prepare permit Weld | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193022 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59170 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59170 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /07/DFAA-FP-59170 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59170 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086856 | DFF34 Chemical FCV- 390198 broken | Isolation DFFA-FCV-390198 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-03-07 | 2023-04-21 | 10 |  |  | DF /F /75/DFFA-FCV-390198 | Isolation DFFA-FCV-390198 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086856 | DFF34 Chemical FCV- 390198 broken | Isolation DFFA-FCV-390198 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-03-07 | 2023-04-21 | 20 |  |  | DF /F /75/DFFA-FCV-390198 | Isolation DFFA-FCV-390198 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086856 | DFF34 Chemical FCV- 390198 broken | Isolation DFFA-FCV-390198 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-03-07 | 2023-04-21 | 30 |  |  | DF /F /75/DFFA-FCV-390198 | Isolation DFFA-FCV-390198 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235624 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-12 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-12 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235624 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-12 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-12 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235624 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-12 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-12 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235624 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-12 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-12 | ISOLATION ELECTRICAL | Unknown
A | DFF-1610 | WPM | MTN-MECH | PRODTECH | 2400264197 | 8KH SDV/BDV MAINT, COUNTER-DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2023-06-30 | 2023-07-01 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-07-30 | 10 | AWSC | AWSC | DF /F /60/DFFA-A-1610 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-MECH | MTN-MECH | 2400264197 | 8KH SDV/BDV MAINT, COUNTER-DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSC | AWSC | 4 | 0 | Empty | 2023-06-30 | 2023-07-01 | 2023-06-30 | 2023-07-01 | 2023-06-30 | 2023-07-30 | 20 | AWSC | AWSC | DF /F /60/DFFA-A-1610 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-MECH | PRODTECH | 2400264197 | 8KH SDV/BDV MAINT, COUNTER-DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2023-06-30 | 2023-07-01 | 2023-07-01 | 2023-07-01 | 2023-06-30 | 2023-07-30 | 30 | AWSC | AWSC | DF /F /60/DFFA-A-1610 | ISOLATION BY PRODUCTION | Unknown
3 | Empty | WDF | MTN-INST | MTN-INST | 2100111817 | DFF-5010 replace tubing 1/2 for 3/4 (INS | DFF-5010 replace tubing 1/2 for 3/4" |  |  | 12 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-08-01 | 2024-06-01 | 2024-10-14 | 10 |  |  | DF /F /27/DFFA-V-5010 | DFF-5010 replace tubing 1/2 for 3/4" | Unknown
3 | Empty | WDF | MTN-INST | MTN-INST | 2100111817 | DFF-5010 replace tubing 1/2 for 3/4 (INS | DFF-5010 replace tubing 1/2 for 3/4" |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-01 | 2024-06-01 | 2024-10-14 | 20 |  |  | DF /F /27/DFFA-V-5010 | DFF-5010 replace tubing 1/2 for 3/4" | Unknown
3 | Empty | WDF | MTN-INST | MTN-INST | 2100111817 | DFF-5010 replace tubing 1/2 for 3/4 (INS | DFF-5010 replace tubing 1/2 for 3/4" |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-03 | 2024-06-01 | 2024-10-14 | 30 |  |  | DF /F /27/DFFA-V-5010 | DFF-5010 replace tubing 1/2 for 3/4" | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322291 | DFF-28-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 15 | 3.25 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235696 | 4Y 380V E-SWB MAINT-DFAA-N-1801 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-24 | 2023-01-30 | 2023-04-13 | 10 | AWSCSECE | AWSCSECE | DF /A /05/DFAA-N-1801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235696 | 4Y 380V E-SWB MAINT-DFAA-N-1801 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 10 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 | 2023-01-30 | 2023-04-13 | 20 | AWSCSECE | AWSCSECE | DF /A /05/DFAA-N-1801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235696 | 4Y 380V E-SWB MAINT-DFAA-N-1801 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-01-30 | 2023-04-13 | 30 | AWSCSECE | AWSCSECE | DF /A /05/DFAA-N-1801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235696 | 4Y 380V E-SWB MAINT-DFAA-N-1801 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-01-30 | 2023-04-13 | 40 | AWSCSECE | AWSCSECE | DF /A /05/DFAA-N-1801 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 10 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 20 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 1.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 30 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 40 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 50 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 60 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100073126 | Change Inst.pipe for DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-09-29 | 2023-02-11 | 70 |  |  | DF /G /32/DFGA-BDV-430003 | Isolate and Inhibit Blow Down Valve | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100105894 | HCV between FF and FG is parsing. | Isolate HCV |  |  | 2 | 0 | Empty | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-05-05 | 2024-03-05 | 2024-07-18 | 10 |  |  | DF /G /74/DFGA-V-0851 | Isolate HCV | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105894 | HCV between FF and FG is parsing. | Isolate HCV |  |  | 2 | 0 | Empty | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-05-05 | 2024-03-05 | 2024-07-18 | 20 |  |  | DF /G /74/DFGA-V-0851 | Isolate HCV | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105894 | HCV between FF and FG is parsing. | Isolate HCV |  |  | 2 | 0 | Empty | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-05-05 | 2024-03-05 | 2024-07-18 | 30 |  |  | DF /G /74/DFGA-V-0851 | Isolate HCV | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100105894 | HCV between FF and FG is parsing. | Isolate HCV |  |  | 2 | 0 | Empty | 2024-05-05 | 2024-05-06 | 2024-05-05 | 2024-05-06 | 2024-03-05 | 2024-07-18 | 40 |  |  | DF /G /74/DFGA-V-0851 | Isolate HCV | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105894 | HCV between FF and FG is parsing. | Isolate HCV |  |  | 1 | 0 | Empty | 2024-05-05 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-03-05 | 2024-07-18 | 50 |  |  | DF /G /74/DFGA-V-0851 | Isolate HCV | Unknown
3 | DFGHPSEP | WDF | MTN-PIPF | MTN-MECH | 2100025339 | SMAT:LCV-340022 actuator rustenheleventi | Instrument assistance | AWSC | AWSC | 6 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-07 | 2024-06-10 | 2015-03-06 | 2015-06-04 | 10 | AWSC | AWSC | DF /G /20/DFGA-LCV-340022 | Instrument assistance | Unknown
3 | DFGHPSEP | WDF | MTN-PIPF | PRODTECH | 2100025339 | SMAT:LCV-340022 actuator rustenheleventi | Instrument assistance | AWSC | AWSC | 3 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-10 | 2024-06-11 | 2015-03-06 | 2015-06-04 | 20 | AWSC | AWSC | DF /G /20/DFGA-LCV-340022 | Instrument assistance | Unknown
3 | DFGHPSEP | WDF | MTN-PIPF | MTN-RIGG | 2100025339 | SMAT:LCV-340022 actuator rustenheleventi | Instrument assistance | AWSC | AWSC | 6 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-11 | 2024-06-12 | 2015-03-06 | 2015-06-04 | 30 | AWSC | AWSC | DF /G /20/DFGA-LCV-340022 | Instrument assistance | Unknown
3 | DFGHPSEP | WDF | MTN-PIPF | MTN-INST | 2100025339 | SMAT:LCV-340022 actuator rustenheleventi | Instrument assistance | AWSC | AWSC | 6 | 6 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-11 | 2024-06-12 | 2015-03-06 | 2015-06-04 | 40 | AWSC | AWSC | DF /G /20/DFGA-LCV-340022 | Instrument assistance | Unknown
3 | DFGHPSEP | WDF | MTN-PIPF | MTN-MECH | 2100025339 | SMAT:LCV-340022 actuator rustenheleventi | Instrument assistance | AWSC | AWSC | 15 | 24 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-11 | 2024-06-13 | 2015-03-06 | 2015-06-04 | 50 | AWSC | AWSC | DF /G /20/DFGA-LCV-340022 | Instrument assistance | Unknown
3 | DFGHPSEP | WDF | MTN-PIPF | PRODTECH | 2100025339 | SMAT:LCV-340022 actuator rustenheleventi | Instrument assistance | AWSC | AWSC | 3 | 0 | Empty | 2024-06-07 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2015-03-06 | 2015-06-04 | 60 | AWSC | AWSC | DF /G /20/DFGA-LCV-340022 | Instrument assistance | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025212 | Udskiftning af N2 flaske DFGA-A-5940 | Remove accumulator and blind open ends |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2019-12-06 | 2020-03-05 | 10 |  |  | DF /G /07/DFGA-A-5940 | Remove accumulator and blind open ends | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025212 | Udskiftning af N2 flaske DFGA-A-5940 | Remove accumulator and blind open ends |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2019-12-06 | 2020-03-05 | 20 |  |  | DF /G /07/DFGA-A-5940 | Remove accumulator and blind open ends | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025212 | Udskiftning af N2 flaske DFGA-A-5940 | Remove accumulator and blind open ends |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2019-12-06 | 2020-03-05 | 30 |  |  | DF /G /07/DFGA-A-5940 | Remove accumulator and blind open ends | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025212 | Udskiftning af N2 flaske DFGA-A-5940 | Remove accumulator and blind open ends |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2019-12-06 | 2020-03-05 | 40 |  |  | DF /G /07/DFGA-A-5940 | Remove accumulator and blind open ends | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025212 | Udskiftning af N2 flaske DFGA-A-5940 | Remove accumulator and blind open ends |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2019-12-06 | 2020-03-05 | 50 |  |  | DF /G /07/DFGA-A-5940 | Remove accumulator and blind open ends | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025212 | Udskiftning af N2 flaske DFGA-A-5940 | Remove accumulator and blind open ends |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2019-12-06 | 2020-03-05 | 60 |  |  | DF /G /07/DFGA-A-5940 | Remove accumulator and blind open ends | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084824 | PVI DAN F Level glass LG-50743 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-05 | 2026-01-21 | 10 |  |  | DF /C /28/DFCM-LG-50743 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084824 | PVI DAN F Level glass LG-50743 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-05 | 2026-01-21 | 20 |  |  | DF /C /28/DFCM-LG-50743 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084824 | PVI DAN F Level glass LG-50743 | Isolate Heat Tracing and Light |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-05 | 2026-01-21 | 30 |  |  | DF /C /28/DFCM-LG-50743 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084824 | PVI DAN F Level glass LG-50743 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-05 | 2026-01-21 | 40 |  |  | DF /C /28/DFCM-LG-50743 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084824 | PVI DAN F Level glass LG-50743 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-05 | 2026-01-21 | 50 |  |  | DF /C /28/DFCM-LG-50743 | Isolate Heat Tracing and Light | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339030 | DFA_1Y_JACKET ABOVE WATER INSPECTION | DFA_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /86/JACKET - L.A.T. TO EL 22000 | DFA_1Y_JACKET ABOVE WATER INSPECTION | Unknown
3 | NOSD | WGN | VEN-MECH | MTN-MECH | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 10 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
3 | NOSD | WGN | VEN-MECH | MTN-MECH | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 20 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
3 | NOSD | WGN | VEN-MECH | MTN-TURB | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 30 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 60 | 59 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 40 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 180 | 155 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 50 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 50 | 45 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 60 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007083 | Stud mounting, baseline vib meas. FF | Vendor Equipment | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 70 | PCNFAWSC | PCNFAWSC | DF /F /9 | Vendor Equipment | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 2 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-05 | 2024-08-05 | 2024-08-15 | 2024-09-14 | 10 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 72 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-05 | 2024-08-09 | 2024-08-15 | 2024-09-14 | 20 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 12 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-09 | 2024-08-12 | 2024-08-15 | 2024-09-14 | 30 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 4 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-12 | 2024-08-13 | 2024-08-15 | 2024-09-14 | 35 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 2 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-13 | 2024-08-13 | 2024-08-15 | 2024-09-14 | 50 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 24 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-13 | 2024-08-19 | 2024-08-15 | 2024-09-14 | 60 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 12 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-19 | 2024-08-22 | 2024-08-15 | 2024-09-14 | 70 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400321271 | 1Y PED CRANE CHECK VENDOR-DFAA-X-6102 | Oil change luff and splitter gear | AWSC | AWSC | 16 | 0 | Empty | 2024-08-05 | 2024-08-26 | 2024-08-22 | 2024-08-26 | 2024-08-15 | 2024-09-14 | 80 | AWSC | AWSC | DF /A /78/DFAA-X-6102 | Oil change luff and splitter gear | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-INST | 2400282065 | 8000H COMPRESSOR SKID, COUNTER | ELECTRICAL CHECK | AWSCSCH | AWSCSCH | 24 | 0 | W37-38 | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-27 | 2023-12-18 | 2024-01-17 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | ELECTRICAL CHECK | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400282065 | 8000H COMPRESSOR SKID, COUNTER | ELECTRICAL CHECK | AWSCSCH | AWSCSCH | 16 | 0 | W37-38 | 2024-09-22 | 2024-10-01 | 2024-09-28 | 2024-09-29 | 2023-12-18 | 2024-01-17 | 20 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | ELECTRICAL CHECK | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-ELEC | 2400282065 | 8000H COMPRESSOR SKID, COUNTER | ELECTRICAL CHECK | AWSCSCH | AWSCSCH | 5 | 0 | W37-38 | 2024-09-22 | 2024-10-01 | 2024-09-30 | 2024-10-01 | 2023-12-18 | 2024-01-17 | 30 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | ELECTRICAL CHECK | Unknown
A | DFF-IPHP | WPM | MTN-TURB | VEN-MECH | 2400282065 | 8000H COMPRESSOR SKID, COUNTER | ELECTRICAL CHECK | AWSCSCH | AWSCSCH | 12 | 0 | W37-38 | 2024-09-22 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2023-12-18 | 2024-01-17 | 40 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | ELECTRICAL CHECK | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100042107 | DFA-A-3102 WI well 4 utæt hydraulik | Replacement with spare drawer |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2021-03-23 | 2021-11-18 | 10 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100042107 | DFA-A-3102 WI well 4 utæt hydraulik | Replacement with spare drawer |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2021-03-23 | 2021-11-18 | 20 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100042107 | DFA-A-3102 WI well 4 utæt hydraulik | Replacement with spare drawer |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2021-03-23 | 2021-11-18 | 30 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100042107 | DFA-A-3102 WI well 4 utæt hydraulik | Replacement with spare drawer |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2021-03-23 | 2021-11-18 | 40 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
D | NOSD | WPM | MTN-INST | MTN-ELEC | 2400219575 | 1Y SOURCE MAINT VENDOR - DFC | SOURCE MAINT AND WIPE TEST - DFC | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-11-12 | 2022-12-29 | 10 | AWSC | AWSC | DF /C /80 | SOURCE MAINT AND WIPE TEST - DFC | Unknown
D | NOSD | WPM | MTN-INST | MTN-ELEC | 2400219575 | 1Y SOURCE MAINT VENDOR - DFC | SOURCE MAINT AND WIPE TEST - DFC | AWSC | AWSC | 6 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-11-12 | 2022-12-29 | 20 | AWSC | AWSC | DF /C /80 | SOURCE MAINT AND WIPE TEST - DFC | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-MECH | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-22 | 2021-06-29 | 2021-11-26 | 10 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | PRODTECH | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-22 | 2021-06-29 | 2021-11-26 | 20 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-MECH | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 12 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-24 | 2021-06-29 | 2021-11-26 | 30 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-RIGG | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 20 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-25 | 2021-06-29 | 2021-11-26 | 40 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-RIGG | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 10 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-25 | 2024-08-26 | 2021-06-29 | 2021-11-26 | 50 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-MECH | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 20 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-28 | 2021-06-29 | 2021-11-26 | 60 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-LAGG | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 20 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-30 | 2021-06-29 | 2021-11-26 | 70 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-MECH | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2021-06-29 | 2021-11-26 | 80 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | PRODTECH | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2021-06-29 | 2021-11-26 | 90 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
3 | DFC-1701 | WDF | MTN-MECH | MTN-SCAF | 2100050199 | Replace exhaust muffler | Replace exhaust muffler |  |  | 10 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-23 | 2021-06-29 | 2021-11-26 | 100 |  |  | DF /C /05/DFCI-G-1701 | Replace exhaust muffler | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322234 | DFB-54-CO-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /54/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 24 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-06 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-09 | 2024-12-10 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-10 | 2024-12-10 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-10 | 2024-12-11 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 12 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-11 | 2024-12-13 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-13 | 2024-12-13 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-13 | 2024-12-14 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-15 | 2024-12-15 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-15 | 2024-12-15 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284278 | PSV Calibration - DFFA-PSV-440027 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-16 | 2024-12-16 | 2024-12-16 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /F /31/DFFA-PSV-440027 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100113679 | DFC/78 Replace temp sensor f. exhaust | Replace sensor incl cable |  |  | 1 | 0 | Empty | 2024-09-13 | 2024-09-14 | 2024-09-13 | 2024-09-13 | 2024-07-13 | 2024-11-25 | 10 |  |  | DF /C /78/DFCI-MD-6101 | Replace sensor incl cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100113679 | DFC/78 Replace temp sensor f. exhaust | Replace sensor incl cable |  |  | 3 | 0 | Empty | 2024-09-13 | 2024-09-14 | 2024-09-13 | 2024-09-14 | 2024-07-13 | 2024-11-25 | 20 |  |  | DF /C /78/DFCI-MD-6101 | Replace sensor incl cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100113679 | DFC/78 Replace temp sensor f. exhaust | Replace sensor incl cable |  |  | 1 | 0 | Empty | 2024-09-13 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-07-13 | 2024-11-25 | 30 |  |  | DF /C /78/DFCI-MD-6101 | Replace sensor incl cable | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400302010 | 1Y SYS 27 INSTRUMENTS/VALVES MAINT-DFC | SYS 27 INSTRUMENTS/VALVES MAINT-DFC | SCHSECE | SCHSECE | 36 | 7 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-15 | 2024-07-24 | 2024-01-01 | 2024-01-31 | 10 | SCHSECE | SCHSECE | DF /C /27/INSTRUMENTS | SYS 27 INSTRUMENTS/VALVES MAINT-DFC | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302010 | 1Y SYS 27 INSTRUMENTS/VALVES MAINT-DFC | SYS 27 INSTRUMENTS/VALVES MAINT-DFC | SCHSECE | SCHSECE | 3 | 7 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-24 | 2024-07-25 | 2024-01-01 | 2024-01-31 | 20 | SCHSECE | SCHSECE | DF /C /27/INSTRUMENTS | SYS 27 INSTRUMENTS/VALVES MAINT-DFC | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001383 | DK40 - erstattes af 2300002154 - SAFETY | DK40 - CONSUMABLE PROD - SAFETY EQ |  |  | 0 | 0 | Empty | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - SAFETY EQ | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001383 | DK40 - erstattes af 2300002154 - SAFETY | DK40 - CONSUMABLE PROD - SAFETY EQ |  |  | 0 | 0 | Empty | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - SAFETY EQ | Unknown
3 | DFF-3580 | WDF | MTN-INST | MTN-MECH | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 0 | 8 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-05-14 | 2021-06-03 | 10 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
3 | DFF-3580 | WDF | MTN-INST | PRODTECH | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-05-14 | 2021-06-03 | 20 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
3 | DFF-3580 | WDF | MTN-INST | VEN-MECH | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 30 | 2 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2021-05-14 | 2021-06-03 | 30 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
3 | DFF-3580 | WDF | MTN-INST | VEN-MECH | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 30 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2021-05-14 | 2021-06-03 | 40 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
3 | DFF-3580 | WDF | MTN-INST | VEN-ELEC | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 30 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2021-05-14 | 2021-06-03 | 50 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
3 | DFF-3580 | WDF | MTN-INST | PRODTECH | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-05-14 | 2021-06-03 | 60 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
3 | DFF-3580 | WDF | MTN-INST | VEN-ELEC | 2100049985 | DFFB-B-3568 update scade | Change of DFFB-VSD-3568 parameters | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-05-14 | 2021-06-03 | 70 | PCNFAWSC | PCNFAWSC | DF /F /53/DFFB-B-3568 | Change of DFFB-VSD-3568 parameters | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400308563 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-3 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 26 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2024-01-10 | 2024-03-12 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-3 | ATEX EQUIPMENT INSPECTION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215518 | 3Y DUCT CLEAN VENDOR - DFC | DUCT CLEAN VENDOR - DFC | AWSCSCH | AWSCSCH | 180 | 0 | W13-W14 | 2024-09-09 | 2024-09-30 | 2024-09-09 | 2024-09-27 | 2022-08-16 | 2022-11-23 | 10 | AWSCSCH | AWSCSCH | DF /C /09 | DUCT CLEAN VENDOR - DFC | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215518 | 3Y DUCT CLEAN VENDOR - DFC | DUCT CLEAN VENDOR - DFC | AWSCSCH | AWSCSCH | 0 | 0 | W13-W14 | 2024-09-09 | 2024-09-30 | 2024-09-27 | 2024-09-27 | 2022-08-16 | 2022-11-23 | 20 | AWSCSCH | AWSCSCH | DF /C /09 | DUCT CLEAN VENDOR - DFC | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400215518 | 3Y DUCT CLEAN VENDOR - DFC | DUCT CLEAN VENDOR - DFC | AWSCSCH | AWSCSCH | 10 | 0 | W13-W14 | 2024-09-09 | 2024-09-30 | 2024-09-27 | 2024-09-30 | 2022-08-16 | 2022-11-23 | 30 | AWSCSCH | AWSCSCH | DF /C /09 | DUCT CLEAN VENDOR - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100065956 | outlet hose from P-3118 is leaking. | Isolate P-3118 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-04-27 | 2022-07-26 | 10 |  |  | DF /F /07/DFFA-P-3118 | Isolate P-3118 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100065956 | outlet hose from P-3118 is leaking. | Isolate P-3118 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-04-27 | 2022-07-26 | 20 |  |  | DF /F /07/DFFA-P-3118 | Isolate P-3118 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100065956 | outlet hose from P-3118 is leaking. | Isolate P-3118 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-04-27 | 2022-07-26 | 30 |  |  | DF /F /07/DFFA-P-3118 | Isolate P-3118 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100065956 | outlet hose from P-3118 is leaking. | Isolate P-3118 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-04-27 | 2022-07-26 | 40 |  |  | DF /F /07/DFFA-P-3118 | Isolate P-3118 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100065956 | outlet hose from P-3118 is leaking. | Isolate P-3118 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-04-27 | 2022-07-26 | 50 |  |  | DF /F /07/DFFA-P-3118 | Isolate P-3118 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100065956 | outlet hose from P-3118 is leaking. | Isolate P-3118 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2022-04-27 | 2022-07-26 | 60 |  |  | DF /F /07/DFFA-P-3118 | Isolate P-3118 | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 2 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-28 | 2024-08-28 | 2021-03-07 | 2021-08-04 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 8 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-28 | 2024-08-28 | 2021-03-07 | 2021-08-04 | 20 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 3 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-28 | 2024-08-28 | 2021-03-07 | 2021-08-04 | 30 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 12 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-28 | 2024-08-29 | 2021-03-07 | 2021-08-04 | 40 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 6 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-29 | 2024-08-29 | 2021-03-07 | 2021-08-04 | 50 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 6 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-29 | 2024-08-30 | 2021-03-07 | 2021-08-04 | 60 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 3 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-30 | 2024-08-31 | 2021-03-07 | 2021-08-04 | 70 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 4 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-31 | 2024-08-31 | 2021-03-07 | 2021-08-04 | 80 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100042724 | DFFA-HCV-440026-U defective/seized Gearb | Rigger Assist lifting points/supporting | AWSCSCH | AWSCSCH | 4 | 0 | W37-38 | 2024-08-28 | 2024-09-01 | 2024-08-31 | 2024-09-01 | 2021-03-07 | 2021-08-04 | 90 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-HCV-440026-U | Rigger Assist lifting points/supporting | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 6 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-02 | 2024-09-03 | 2023-01-12 | 2023-02-26 | 1 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | MTN-MECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 6 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-03 | 2024-09-05 | 2023-01-12 | 2023-02-26 | 2 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 6 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-05 | 2024-09-06 | 2023-01-12 | 2023-02-26 | 3 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | MTN-RIGG | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 10 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-06 | 2024-09-07 | 2023-01-12 | 2023-02-26 | 4 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | MTN-MECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 12 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-06 | 2024-09-07 | 2023-01-12 | 2023-02-26 | 5 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 12 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-07 | 2024-09-09 | 2023-01-12 | 2023-02-26 | 10 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | MTN-MECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 12 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-09 | 2024-09-10 | 2023-01-12 | 2023-02-26 | 20 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 4 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-10 | 2024-09-11 | 2023-01-12 | 2023-02-26 | 30 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 12 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-11 | 2024-09-14 | 2023-01-12 | 2023-02-26 | 40 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 0 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-02 | 2024-09-02 | 2023-01-12 | 2023-02-26 | 50 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
2 | DFF-3580 | WDF | PRODTECH | PRODTECH | 2100080892 | Flush Deoxidiser on minox acc program | Production Isolation/flushing | AWSC | AWSC | 0 | 0 | Empty | 2024-09-02 | 2024-09-14 | 2024-09-02 | 2024-09-02 | 2023-01-12 | 2023-02-26 | 60 | AWSC | AWSC | DF /F /53/DFFB-VX-3566 | Production Isolation/flushing | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316049 | 3M LIFE-SAVING AND SAFETY EQ MAINT - DFA | LIFE-SAVING AND SAFETY EQ INSP - DFA | SECE | SECE | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-04-24 | 2024-05-04 | 10 | SECE | SECE | DF /A /02/LIFE-SAVING-EQUIPMENT | LIFE-SAVING AND SAFETY EQ INSP - DFA | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 2 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2017-02-13 | 2017-07-13 | 10 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 1 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-02-13 | 2017-07-13 | 20 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-02-13 | 2017-07-13 | 30 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 1 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-02-13 | 2017-07-13 | 40 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 6 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2017-02-13 | 2017-07-13 | 50 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 2 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2017-02-13 | 2017-07-13 | 60 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 4 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2017-02-13 | 2017-07-13 | 70 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 3 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2017-02-13 | 2017-07-13 | 80 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 2 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2017-02-13 | 2017-07-13 | 90 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 1 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2017-02-13 | 2017-07-13 | 100 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2017-02-13 | 2017-07-13 | 110 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 1 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-02-13 | 2017-07-13 | 120 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025103 | @+DFFA-FCV-360067 stem ekstern læk | Preparation for rigging | AWSC | AWSC | 1 | 0 | DFF-OIL outage | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-02-13 | 2017-07-13 | 130 | AWSC | AWSC | DF /F /21/DFFA-FCV-360067 | Preparation for rigging | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100092671 | RESET PB DFFA-PB-021211 NEED TO REPLACE | Replace pushbutton and test |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-07-26 | 2023-12-08 | 10 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100092671 | RESET PB DFFA-PB-021211 NEED TO REPLACE | Replace pushbutton and test |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-07-26 | 2023-12-08 | 20 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100092671 | RESET PB DFFA-PB-021211 NEED TO REPLACE | Replace pushbutton and test |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-07-26 | 2023-12-08 | 30 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048121 | Defect Bleed Vlv handle HCV330013-U | Prod prepare permit/isolations |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2021-06-24 | 2021-11-21 | 10 |  |  | DF /F /10/DFFA-HCV-330013-U | Prod prepare permit/isolations | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048121 | Defect Bleed Vlv handle HCV330013-U | Prod prepare permit/isolations |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2021-06-24 | 2021-11-21 | 20 |  |  | DF /F /10/DFFA-HCV-330013-U | Prod prepare permit/isolations | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048121 | Defect Bleed Vlv handle HCV330013-U | Prod prepare permit/isolations |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2021-06-24 | 2021-11-21 | 30 |  |  | DF /F /10/DFFA-HCV-330013-U | Prod prepare permit/isolations | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048121 | Defect Bleed Vlv handle HCV330013-U | Prod prepare permit/isolations |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2021-06-24 | 2021-11-21 | 40 |  |  | DF /F /10/DFFA-HCV-330013-U | Prod prepare permit/isolations | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048121 | Defect Bleed Vlv handle HCV330013-U | Prod prepare permit/isolations |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2021-06-24 | 2021-11-21 | 50 |  |  | DF /F /10/DFFA-HCV-330013-U | Prod prepare permit/isolations | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048121 | Defect Bleed Vlv handle HCV330013-U | Prod prepare permit/isolations |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2021-06-24 | 2021-11-21 | 60 |  |  | DF /F /10/DFFA-HCV-330013-U | Prod prepare permit/isolations | Unknown
3 | DFB-O02 | WDF | MTN-INST | PRODTECH | 2100067310 | DFB-02 choke ZSC can not be activated | Isolate and Inhibit Choke Valve | AWSCSCH | AWSCSCH | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2022-04-25 | 2022-07-24 | 10 | AWSCSCH | AWSCSCH | DF /B /10/DFBA-CVA-30002 | Isolate and Inhibit Choke Valve | Unknown
3 | DFB-O02 | WDF | MTN-INST | MTN-INST | 2100067310 | DFB-02 choke ZSC can not be activated | Isolate and Inhibit Choke Valve | AWSCSCH | AWSCSCH | 1 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-04-25 | 2022-07-24 | 20 | AWSCSCH | AWSCSCH | DF /B /10/DFBA-CVA-30002 | Isolate and Inhibit Choke Valve | Unknown
3 | DFB-O02 | WDF | MTN-INST | MTN-INST | 2100067310 | DFB-02 choke ZSC can not be activated | Isolate and Inhibit Choke Valve | AWSCSCH | AWSCSCH | 1 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2022-04-25 | 2022-07-24 | 30 | AWSCSCH | AWSCSCH | DF /B /10/DFBA-CVA-30002 | Isolate and Inhibit Choke Valve | Unknown
3 | DFB-O02 | WDF | MTN-INST | PRODTECH | 2100067310 | DFB-02 choke ZSC can not be activated | Isolate and Inhibit Choke Valve | AWSCSCH | AWSCSCH | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2022-04-25 | 2022-07-24 | 40 | AWSCSCH | AWSCSCH | DF /B /10/DFBA-CVA-30002 | Isolate and Inhibit Choke Valve | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 0 | 0 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-06-12 | 10 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 15 | 24 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-13 | 2022-01-14 | 2022-01-13 | 2022-06-12 | 20 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 75 | 60 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-14 | 2022-01-20 | 2022-01-13 | 2022-06-12 | 30 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 50 | 100 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-20 | 2022-01-22 | 2022-01-13 | 2022-06-12 | 40 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 50 | 95 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-22 | 2022-01-23 | 2022-01-13 | 2022-06-12 | 50 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 50 | 30 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-23 | 2022-01-28 | 2022-01-13 | 2022-06-12 | 60 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057418 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 24.720 | PCNF | PCNF | 12 | 0 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-28 | 2022-01-28 | 2022-01-13 | 2022-06-12 | 70 | PCNF | PCNF | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 24.720 | Unknown
2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100111332 | Intrnally leaking HCVs and drainvalves | Rigger assistance/valves off/on |  |  | 12 | 0 | Empty | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2024-04-25 | 2024-06-09 | 10 |  |  | DF /F /54/DFFA-HCV-380027 | Rigger assistance/valves off/on | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100111332 | Intrnally leaking HCVs and drainvalves | Rigger assistance/valves off/on |  |  | 3 | 0 | Empty | 2024-08-26 | 2024-08-30 | 2024-08-27 | 2024-08-28 | 2024-04-25 | 2024-06-09 | 20 |  |  | DF /F /54/DFFA-HCV-380027 | Rigger assistance/valves off/on | Unknown
2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100111332 | Intrnally leaking HCVs and drainvalves | Rigger assistance/valves off/on |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-30 | 2024-08-28 | 2024-08-28 | 2024-04-25 | 2024-06-09 | 30 |  |  | DF /F /54/DFFA-HCV-380027 | Rigger assistance/valves off/on | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100111332 | Intrnally leaking HCVs and drainvalves | Rigger assistance/valves off/on |  |  | 8 | 0 | Empty | 2024-08-26 | 2024-08-30 | 2024-08-28 | 2024-08-29 | 2024-04-25 | 2024-06-09 | 40 |  |  | DF /F /54/DFFA-HCV-380027 | Rigger assistance/valves off/on | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100111332 | Intrnally leaking HCVs and drainvalves | Rigger assistance/valves off/on |  |  | 6 | 0 | Empty | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2024-04-25 | 2024-06-09 | 50 |  |  | DF /F /54/DFFA-HCV-380027 | Rigger assistance/valves off/on | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100111332 | Intrnally leaking HCVs and drainvalves | Rigger assistance/valves off/on |  |  | 3 | 0 | Empty | 2024-08-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2024-04-25 | 2024-06-09 | 60 |  |  | DF /F /54/DFFA-HCV-380027 | Rigger assistance/valves off/on | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-PIPF | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 0 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-15 | 2023-10-15 | 2022-08-20 | 2022-10-04 | 10 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-PIPF | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 4 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-15 | 2023-10-16 | 2022-08-20 | 2022-10-04 | 20 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-RIGG | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 4 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-16 | 2023-10-16 | 2022-08-20 | 2022-10-04 | 30 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-RIGG | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 4 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-16 | 2023-10-17 | 2022-08-20 | 2022-10-04 | 40 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | PRODTECH | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 2 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-17 | 2023-10-17 | 2022-08-20 | 2022-10-04 | 50 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-PIPF | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 12 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-17 | 2023-10-18 | 2022-08-20 | 2022-10-04 | 60 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-RIGG | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 6 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-18 | 2023-10-18 | 2022-08-20 | 2022-10-04 | 70 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-RIGG | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 6 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-18 | 2023-10-19 | 2022-08-20 | 2022-10-04 | 80 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-PIPF | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 14 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-19 | 2023-10-20 | 2022-08-20 | 2022-10-04 | 90 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | PRODTECH | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 2 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-20 | 2023-10-20 | 2022-08-20 | 2022-10-04 | 100 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-RIGG | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 4 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-20 | 2023-10-21 | 2022-08-20 | 2022-10-04 | 110 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
2 | DAN FG | WDF | MTN-PIPF | MTN-PIPF | 2100074494 | FFSPR WF Replacement spool required | Remove lifting gear |  |  | 4 | 0 | Empty | 2023-10-15 | 2023-10-21 | 2023-10-21 | 2023-10-21 | 2022-08-20 | 2022-10-04 | 120 |  |  | DF /G /01/DFG-4-WF-003-0355-AM-U | Remove lifting gear | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235843 | 4Y 400V E-SWB MAINT DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235843 | 4Y 400V E-SWB MAINT DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235843 | 4Y 400V E-SWB MAINT DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235843 | 4Y 400V E-SWB MAINT DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A05 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-22 | 2021-06-29 | 2021-11-26 | 10 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-22 | 2024-08-23 | 2021-06-29 | 2021-11-26 | 20 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 26 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-23 | 2024-08-26 | 2021-06-29 | 2021-11-26 | 30 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2021-06-29 | 2021-11-26 | 40 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-27 | 2021-06-29 | 2021-11-26 | 50 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-27 | 2021-06-29 | 2021-11-26 | 60 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-27 | 2024-08-28 | 2021-06-29 | 2021-11-26 | 100 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100048335 | DFCM-PSV-52212 - Corroded Flange sealing | L3 Pre. Linewalk |  |  | 14 | 0 | Empty | 2024-08-22 | 2024-08-30 | 2024-08-28 | 2024-08-30 | 2021-06-29 | 2021-11-26 | 110 |  |  | DF /C /51/DFCM-PSV-52212 | L3 Pre. Linewalk | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400309007 | 6M FRESH AIR FILTERS DAN F | FRESH AIR STATIONS DAN F |  |  | 5 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2024-02-24 | 2024-03-20 | 10 |  |  | DF /C /07 | FRESH AIR STATIONS DAN F | Unknown
D | NOSD | WPM | MTN-MECH | MTN-INST | 2400309007 | 6M FRESH AIR FILTERS DAN F | FRESH AIR STATIONS DAN F |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-02-24 | 2024-03-20 | 12 |  |  | DF /C /07 | FRESH AIR STATIONS DAN F | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104397 | FD 12720 does not close | Erect scaffold | PCNFSCHSECE | PCNFSCHSECE | 4 | 0 | Empty | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-05-06 | 2023-12-31 | 2024-02-14 | 9 | PCNFSCHSECE | PCNFSCHSECE | DF /B /09/DFBA-FD-12720 | Erect scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104397 | FD 12720 does not close | Erect scaffold | PCNFSCHSECE | PCNFSCHSECE | 1 | 1 | Empty | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-05-06 | 2023-12-31 | 2024-02-14 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /B /09/DFBA-FD-12720 | Erect scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104397 | FD 12720 does not close | Erect scaffold | PCNFSCHSECE | PCNFSCHSECE | 4 | 6 | Empty | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-05-06 | 2023-12-31 | 2024-02-14 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /B /09/DFBA-FD-12720 | Erect scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104397 | FD 12720 does not close | Erect scaffold | PCNFSCHSECE | PCNFSCHSECE | 1 | 1 | Empty | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-05-06 | 2023-12-31 | 2024-02-14 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /B /09/DFBA-FD-12720 | Erect scaffold | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104397 | FD 12720 does not close | Erect scaffold | PCNFSCHSECE | PCNFSCHSECE | 4 | 0 | Empty | 2024-05-06 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2023-12-31 | 2024-02-14 | 31 | PCNFSCHSECE | PCNFSCHSECE | DF /B /09/DFBA-FD-12720 | Erect scaffold | Unknown
A | DAN-GAS | WPM | MTN-MECH | MTN-MECH | 2400235298 | 6M ESDV FUNC TEST DFBA-ESDV-38097 | ESDV INST ASSIST DFBA-ESDV-38097 | SECE | SECE | 1 | 0 | Empty | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2023-02-27 | 2023-03-15 | 10 | SECE | SECE | DF /B /34/DFBA-ESDV-38097 | ESDV INST ASSIST DFBA-ESDV-38097 | Unknown
A | DAN-GAS | WPM | MTN-MECH | MTN-INST | 2400235298 | 6M ESDV FUNC TEST DFBA-ESDV-38097 | ESDV INST ASSIST DFBA-ESDV-38097 | SECE | SECE | 1 | 0 | Empty | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2023-02-27 | 2023-03-15 | 20 | SECE | SECE | DF /B /34/DFBA-ESDV-38097 | ESDV INST ASSIST DFBA-ESDV-38097 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300004397 | DK40 - CONSUMABLE MTN - TELECOM | DK40 - CONSUMABLE MTN - TELECOM |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2023-06-28 | 2025-12-14 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - TELECOM | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100074848 | DFA/78: Drain main fuel tank | Drain 10% of fuel tank located at slewbe |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-10-31 | 2023-03-15 | 10 |  |  | DF /A /78/DFAA-X-6102 | Drain 10% of fuel tank located at slewbe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074848 | DFA/78: Drain main fuel tank | Drain 10% of fuel tank located at slewbe |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-01 | 2022-10-31 | 2023-03-15 | 20 |  |  | DF /A /78/DFAA-X-6102 | Drain 10% of fuel tank located at slewbe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074848 | DFA/78: Drain main fuel tank | Drain 10% of fuel tank located at slewbe |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2022-10-31 | 2023-03-15 | 30 |  |  | DF /A /78/DFAA-X-6102 | Drain 10% of fuel tank located at slewbe | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-03-27 | 2023-03-29 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-03-30 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-03-31 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-04-01 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-04-01 | 2023-04-03 | 2022-02-07 | 2022-07-07 | 52 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 28 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-04-03 | 2023-04-06 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009232 | Insulation assists Bilfinger 22197(COMP) | Install + test heattracing |  |  | 18 | 0 | Empty | 2023-03-27 | 2023-04-08 | 2023-04-06 | 2023-04-08 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Install + test heattracing | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100040992 | DFCM-V-5037 PVI Contingency valves | DFCM-V-5037 PVI Contingency valves |  |  | 0 | 0 | Empty | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2021-01-04 | 10 |  |  | DF /C /27/DFCM-V-5037 | DFCM-V-5037 PVI Contingency valves | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100040992 | DFCM-V-5037 PVI Contingency valves | DFCM-V-5037 PVI Contingency valves |  |  | 0 | 0 | Empty | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2020-11-25 | 2021-01-04 | 20 |  |  | DF /C /27/DFCM-V-5037 | DFCM-V-5037 PVI Contingency valves | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400292163 | 3M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-08 | 2023-12-18 | 10 |  |  | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003189 | CMAT:DFGA-ESDV-570505 Udskift def manome | Safing af ESDV - hydraulik systemet |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-03 | 2023-04-04 | 2018-03-08 | 2019-03-03 | 10 |  |  | DF /G /71/DFGA-ESDV-570505 | Safing af ESDV - hydraulik systemet | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003189 | CMAT:DFGA-ESDV-570505 Udskift def manome | Safing af ESDV - hydraulik systemet |  |  | 2 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-05 | 2018-03-08 | 2019-03-03 | 20 |  |  | DF /G /71/DFGA-ESDV-570505 | Safing af ESDV - hydraulik systemet | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003189 | CMAT:DFGA-ESDV-570505 Udskift def manome | Safing af ESDV - hydraulik systemet |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-06 | 2018-03-08 | 2019-03-03 | 30 |  |  | DF /G /71/DFGA-ESDV-570505 | Safing af ESDV - hydraulik systemet | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 10 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 20 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 30 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 40 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 50 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 60 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096904 | P-3116 does not build up pressure. | Connect electrically |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-28 | 2023-10-12 | 70 |  |  | DF /F /07/DFFA-P-3116 | Connect electrically | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011643 | DFG FFLB2 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-02-14 | 2025-08-02 | 10 |  |  | DF /G /02/DFGA-X-0702 | Replace hydraulic hoses | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200011643 | DFG FFLB2 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-02-14 | 2025-08-02 | 20 |  |  | DF /G /02/DFGA-X-0702 | Replace hydraulic hoses | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200011643 | DFG FFLB2 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 18 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-02-14 | 2025-08-02 | 30 |  |  | DF /G /02/DFGA-X-0702 | Replace hydraulic hoses | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200011643 | DFG FFLB2 Replace hydraulic hoses | Replace hydraulic hoses |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-02-14 | 2025-08-02 | 40 |  |  | DF /G /02/DFGA-X-0702 | Replace hydraulic hoses | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080286 | replace cabinet | replace cabinet |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-02-12 | 2023-06-27 | 10 |  |  | DF /G /01/DFGA-HE-03102 | replace cabinet | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025030 | CMAT:Exchange of internal pump PRV-39055 | L3 Isolate equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2018-11-15 | 2018-12-25 | 10 |  |  | DF /F /75/DFFA-PRV-390550 | L3 Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025030 | CMAT:Exchange of internal pump PRV-39055 | L3 Isolate equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2018-11-15 | 2018-12-25 | 20 |  |  | DF /F /75/DFFA-PRV-390550 | L3 Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025030 | CMAT:Exchange of internal pump PRV-39055 | L3 Isolate equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2018-11-15 | 2018-12-25 | 30 |  |  | DF /F /75/DFFA-PRV-390550 | L3 Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025030 | CMAT:Exchange of internal pump PRV-39055 | L3 Isolate equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2018-11-15 | 2018-12-25 | 40 |  |  | DF /F /75/DFFA-PRV-390550 | L3 Isolate equipment | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400269346 | 6M SW FILT FEED PUMP MAINT P-3511/12/13 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2023-07-27 | 2023-08-15 | 5 |  |  | DF /C /54/DFCM-P-3511 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269346 | 6M SW FILT FEED PUMP MAINT P-3511/12/13 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2023-07-27 | 2023-08-15 | 10 |  |  | DF /C /54/DFCM-P-3511 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400269346 | 6M SW FILT FEED PUMP MAINT P-3511/12/13 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2023-07-27 | 2023-08-15 | 20 |  |  | DF /C /54/DFCM-P-3511 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316047 | 6M SDV LUB/MAINT OIL - DFB | SDV LUB/INSP OIL - DFB |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-17 | 2024-05-03 | 10 |  |  | DF /B /03/SDV-VALVES | SDV LUB/INSP OIL - DFB | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097006 | DFA/78 Flushing of slew bearing _ Grease | Assist | SCH | SCH | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-12 | 2024-02-24 | 10 | SCH | SCH | DF /A /78/DFAA-X-6102 | Assist | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100097006 | DFA/78 Flushing of slew bearing _ Grease | Assist | SCH | SCH | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-12 | 2024-02-24 | 20 | SCH | SCH | DF /A /78/DFAA-X-6102 | Assist | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235574 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235574 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-02-14 | 2023-05-13 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235574 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-02-14 | 2023-05-13 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235574 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-02-14 | 2023-05-13 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-02-01 | ISOLATION ELECTRICAL | Unknown
C | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400298191 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-07-15 | 2024-07-12 | 2024-07-12 | 2024-01-03 | 2024-01-08 | 1 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400298191 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-07-12 | 2024-07-15 | 2024-07-12 | 2024-07-15 | 2024-01-03 | 2024-01-08 | 10 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 268 | 0 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-01-16 | 2023-02-13 | 2017-09-18 | 2017-10-28 | 10 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WDF | MTN-ROPE | QAQCPAIN | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 2 | 0 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-02-13 | 2023-02-13 | 2017-09-18 | 2017-10-28 | 62 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 615.8999999999999772626324555 | 39 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-02-13 | 2023-02-13 | 2017-09-18 | 2017-10-28 | 70 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 308.10000000000002273736754425 | 20 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-02-13 | 2023-02-13 | 2017-09-18 | 2017-10-28 | 72 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 67 | 0 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-02-13 | 2023-02-20 | 2017-09-18 | 2017-10-28 | 82 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 134 | 0 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-02-20 | 2023-03-06 | 2017-09-18 | 2017-10-28 | 92 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024835 | ANOC SMAT: ISO DFA 3"-DPS-50701(bridge) | L3 Mounting of insulation + cleaning | PCNF | PCNF | 201 | 0 | W03-04 | 2023-01-16 | 2023-03-23 | 2023-03-06 | 2023-03-23 | 2017-09-18 | 2017-10-28 | 100 | PCNF | PCNF | DF /A /28/DFA-3-DPS-050-0701-AD-F | L3 Mounting of insulation + cleaning | Unknown
3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200011357 | Protection Settings DFFB-N-1829-01K1 | Protection Settings DFFB-N-1829-01K1 |  |  | 1 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-08-26 | 2023-01-08 | 10 |  |  | DF /F /05/DFFB-N-1829-01K1 | Protection Settings DFFB-N-1829-01K1 | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200011357 | Protection Settings DFFB-N-1829-01K1 | Protection Settings DFFB-N-1829-01K1 |  |  | 2 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-08-26 | 2023-01-08 | 20 |  |  | DF /F /05/DFFB-N-1829-01K1 | Protection Settings DFFB-N-1829-01K1 | Unknown
3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200011357 | Protection Settings DFFB-N-1829-01K1 | Protection Settings DFFB-N-1829-01K1 |  |  | 1 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-08-26 | 2023-01-08 | 30 |  |  | DF /F /05/DFFB-N-1829-01K1 | Protection Settings DFFB-N-1829-01K1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057122 | utæt pulsationsdæmper | Isolate DFFA-PD-3923 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2021-11-11 | 2022-02-09 | 20 |  |  | DF /F /75/DFFA-P-3923 | Isolate DFFA-PD-3923 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057122 | utæt pulsationsdæmper | Isolate DFFA-PD-3923 |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-08-02 | 2021-11-11 | 2022-02-09 | 30 |  |  | DF /F /75/DFFA-P-3923 | Isolate DFFA-PD-3923 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057122 | utæt pulsationsdæmper | Isolate DFFA-PD-3923 |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2021-11-11 | 2022-02-09 | 40 |  |  | DF /F /75/DFFA-P-3923 | Isolate DFFA-PD-3923 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100115441 | DFB/78 The pressure in the accumulator d | Isolate de-isolate crane |  |  | 1 | 0 | W35-W36 | 2024-08-28 | 2024-09-01 | 2024-08-28 | 2024-08-29 | 2024-06-28 | 2024-08-12 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolate de-isolate crane | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100115441 | DFB/78 The pressure in the accumulator d | Isolate de-isolate crane |  |  | 5 | 0 | W35-W36 | 2024-08-28 | 2024-09-01 | 2024-08-29 | 2024-08-30 | 2024-06-28 | 2024-08-12 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolate de-isolate crane | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100115441 | DFB/78 The pressure in the accumulator d | Isolate de-isolate crane |  |  | 5 | 0 | W35-W36 | 2024-08-28 | 2024-09-01 | 2024-08-30 | 2024-08-31 | 2024-06-28 | 2024-08-12 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolate de-isolate crane | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100115441 | DFB/78 The pressure in the accumulator d | Isolate de-isolate crane |  |  | 2 | 0 | W35-W36 | 2024-08-28 | 2024-09-01 | 2024-08-31 | 2024-09-01 | 2024-06-28 | 2024-08-12 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolate de-isolate crane | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235714 | 4Y 380V E-DP INSPECT EMER. LIGHT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-26 | 2023-03-01 | 2023-05-13 | 10 | SECE | SECE | DF /C /05/EMERGENCY-POWER-BOARDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235714 | 4Y 380V E-DP INSPECT EMER. LIGHT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 18 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-29 | 2023-03-01 | 2023-05-13 | 20 | SECE | SECE | DF /C /05/EMERGENCY-POWER-BOARDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235714 | 4Y 380V E-DP INSPECT EMER. LIGHT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2023-03-01 | 2023-05-13 | 30 | SECE | SECE | DF /C /05/EMERGENCY-POWER-BOARDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235714 | 4Y 380V E-DP INSPECT EMER. LIGHT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-30 | 2024-08-30 | 2023-03-01 | 2023-05-13 | 40 | SECE | SECE | DF /C /05/EMERGENCY-POWER-BOARDS | ISOLATION BY PRODUCTION | Unknown
2 | DFG-FUEL | WDF | MTN-ELEC | VEN-ELEC | 2100087618 | DFG-1640 incommer GAA mecanical defect | DFG-1640 incommer GAA mecanical defect | SCH | SCH | 12 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-03-20 | 2023-05-04 | 10 | SCH | SCH | DF /G /61/DFGA-N-1841-M102-01 | DFG-1640 incommer GAA mecanical defect | Unknown
2 | DFG-FUEL | WDF | MTN-ELEC | MTN-ELEC | 2100087618 | DFG-1640 incommer GAA mecanical defect | DFG-1640 incommer GAA mecanical defect | SCH | SCH | 0 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-03-20 | 2023-05-04 | 20 | SCH | SCH | DF /G /61/DFGA-N-1841-M102-01 | DFG-1640 incommer GAA mecanical defect | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100094508 | Faulty temp. transmitter DFGA-TIT-530436 | Check transmitter and barrier |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-07-12 | 2023-08-26 | 10 |  |  | DF /G /76/DFGA-TIT-530436 | Check transmitter and barrier | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100089843 | DFC comp-5408 leak from cooler | Replace hose | SCH | SCH | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-06-10 | 2023-10-23 | 10 | SCH | SCH | DF /C /07/DFCM-A-5408 | Replace hose | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100089843 | DFC comp-5408 leak from cooler | Replace hose | SCH | SCH | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-06-10 | 2023-10-23 | 20 | SCH | SCH | DF /C /07/DFCM-A-5408 | Replace hose | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100089843 | DFC comp-5408 leak from cooler | Replace hose | SCH | SCH | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-06-10 | 2023-10-23 | 30 | SCH | SCH | DF /C /07/DFCM-A-5408 | Replace hose | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258777 | 1Y CHEMICAL INJ. PUMP SKID, A-39230 | 1Y CHEMICAL INJ. PUMP SKID, A-39230 |  |  | 6 | 24 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-23 | 2023-04-26 | 2023-06-01 | 10 |  |  | DF /A /75/DFAA-A-39230 | 1Y CHEMICAL INJ. PUMP SKID, A-39230 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400258777 | 1Y CHEMICAL INJ. PUMP SKID, A-39230 | 1Y CHEMICAL INJ. PUMP SKID, A-39230 |  |  | 6 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-25 | 2023-04-26 | 2023-06-01 | 20 |  |  | DF /A /75/DFAA-A-39230 | 1Y CHEMICAL INJ. PUMP SKID, A-39230 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286630 | 1Y WATER MIST SKID MAINT-DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | SECE | SECE | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-07-29 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /G /01/DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286630 | 1Y WATER MIST SKID MAINT-DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | SECE | SECE | 10 | 4 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-08-01 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /G /01/DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286630 | 1Y WATER MIST SKID MAINT-DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | SECE | SECE | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-01 | 2024-08-02 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /G /01/DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286630 | 1Y WATER MIST SKID MAINT-DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | SECE | SECE | 4 | 4 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-03 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /G /01/DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286630 | 1Y WATER MIST SKID MAINT-DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | SECE | SECE | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-03 | 2024-08-04 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /G /01/DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286630 | 1Y WATER MIST SKID MAINT-DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | SECE | SECE | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-04 | 2024-08-04 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /G /01/DFGA-A-0465 | WATER MIST SKID MAINT-DFGA-A-0465 | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400342412 | 2Y ESD-PUSH BUTTONS TEST - DFA/B/E | ESD-PUSH BUTTONS TEST - DFA/B/E | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-07-17 | 2024-09-01 | 10 | AWSCSECE | AWSCSECE | DF /A /03/ESD-PUSHBUTTONS | ESD-PUSH BUTTONS TEST - DFA/B/E | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-29 | 2018-02-25 | 2018-07-25 | 10 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-29 | 2018-02-25 | 2018-07-25 | 20 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-30 | 2018-02-25 | 2018-07-25 | 30 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-08-01 | 2018-02-25 | 2018-07-25 | 35 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-03 | 2018-02-25 | 2018-07-25 | 40 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-05 | 2018-02-25 | 2018-07-25 | 45 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-05 | 2024-08-06 | 2018-02-25 | 2018-07-25 | 50 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 8 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-06 | 2024-08-07 | 2018-02-25 | 2018-07-25 | 60 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 4 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2018-02-25 | 2018-07-25 | 70 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2018-02-25 | 2018-07-25 | 80 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003166 | SMAT:AN FF-DFFA-XCV-301305, actuator | L3-Check of material | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2018-02-25 | 2018-07-25 | 90 | PCNF | PCNF | DF /F /10/DFFA-XCV-301305 | L3-Check of material | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000929 | SCADA SW for DFDCOM | SCADA SW for DFDCOM | AWSC | AWSC | 24 | 0 | W50 ABB | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-07 | 2019-06-20 | 2019-11-17 | 10 | AWSC | AWSC | DF /C /04/DFCI-FP-2051 | SCADA SW for DFDCOM | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000929 | SCADA SW for DFDCOM | SCADA SW for DFDCOM | AWSC | AWSC | 10 | 0 | W50 ABB | 2024-10-05 | 2024-10-10 | 2024-10-07 | 2024-10-10 | 2019-06-20 | 2019-11-17 | 20 | AWSC | AWSC | DF /C /04/DFCI-FP-2051 | SCADA SW for DFDCOM | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000929 | SCADA SW for DFDCOM | SCADA SW for DFDCOM | AWSC | AWSC | 0 | 0 | W50 ABB | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2019-06-20 | 2019-11-17 | 30 | AWSC | AWSC | DF /C /04/DFCI-FP-2051 | SCADA SW for DFDCOM | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200018651 | Mixer in galley is worn out need service | Mixer in galley is worn out need service |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-07-11 | 2024-11-23 | 10 |  |  | DF /C /82/DFCC-X-13013 | Mixer in galley is worn out need service | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200018651 | Mixer in galley is worn out need service | Mixer in galley is worn out need service |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-07-11 | 2024-11-23 | 20 |  |  | DF /C /82/DFCC-X-13013 | Mixer in galley is worn out need service | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200018651 | Mixer in galley is worn out need service | Mixer in galley is worn out need service |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-07-11 | 2024-11-23 | 30 |  |  | DF /C /82/DFCC-X-13013 | Mixer in galley is worn out need service | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200018651 | Mixer in galley is worn out need service | Mixer in galley is worn out need service |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-11 | 2024-11-23 | 40 |  |  | DF /C /82/DFCC-X-13013 | Mixer in galley is worn out need service | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200018651 | Mixer in galley is worn out need service | Mixer in galley is worn out need service |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-11 | 2024-11-23 | 50 |  |  | DF /C /82/DFCC-X-13013 | Mixer in galley is worn out need service | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235580 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-08-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235580 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-08-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235580 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-08-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235580 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-08-01 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235744 | 4Y 400/230V UPS-DP-F.TST-DFFA-DP-1820-26 | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /06/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235744 | 4Y 400/230V UPS-DP-F.TST-DFFA-DP-1820-26 | ISOLATION ELECTRICAL | SECE | SECE | 12 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /06/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235744 | 4Y 400/230V UPS-DP-F.TST-DFFA-DP-1820-26 | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /06/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235744 | 4Y 400/230V UPS-DP-F.TST-DFFA-DP-1820-26 | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /06/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400325368 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-18 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 23 | 0 | Empty | 2024-05-26 | 2024-05-27 | 2024-05-26 | 2024-05-27 | 2024-03-24 | 2024-05-25 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-18 | ATEX EQUIPMENT INSPECTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235778 | 4Y 400V N-SWB MAINT-DFFB-N-1828-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828-09 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235778 | 4Y 400V N-SWB MAINT-DFFB-N-1828-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 35 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-30 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828-09 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235778 | 4Y 400V N-SWB MAINT-DFFB-N-1828-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-01 | 2024-10-03 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828-09 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235778 | 4Y 400V N-SWB MAINT-DFFB-N-1828-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828-09 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343946 | 6M SW FILTER - DFCM-FT-5211/21/31/41 | SW FILTER - DFCM-FT-5211/21/31/41 |  |  | 2 | 0 | Empty | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-27 | 10 |  |  | DF /C /51/DFCM-FT-5211 | SW FILTER - DFCM-FT-5211/21/31/41 | Unknown
3 | DFB-W01 | WDF | MTN-INST | MTN-INST | 2100086061 | DFB-01 ZT choke faulty | Replace Position Measurement Device |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-07 | 2023-08-20 | 10 |  |  | DF /B /55/DFBA-ZT-30001 | Replace Position Measurement Device | Unknown
3 | DFB-W01 | WDF | MTN-INST | MTN-INST | 2100086061 | DFB-01 ZT choke faulty | Replace Position Measurement Device |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-07 | 2023-08-20 | 20 |  |  | DF /B /55/DFBA-ZT-30001 | Replace Position Measurement Device | Unknown
3 | DFB-W01 | WDF | MTN-INST | MTN-INST | 2100086061 | DFB-01 ZT choke faulty | Replace Position Measurement Device |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-07 | 2023-08-20 | 30 |  |  | DF /B /55/DFBA-ZT-30001 | Replace Position Measurement Device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104206 | DFFA-STR-0603 Replace belts and blankets | DFFA-STR-0603 Replace belts and blankets |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-10 | 2024-06-24 | 10 |  |  | DF /F /02/DFFA-STR-0603 | DFFA-STR-0603 Replace belts and blankets | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025104 | PMAT:DFFA-V-3402 PVI Contingency valves. | Recive materials. |  |  | 1 | 0 | Empty | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2019-04-02 | 2021-03-22 | 10 |  |  | DF /F /20/DFFA-V-3402 | Recive materials. | Unknown
4 | Empty | WRO | PRODLABO | PRODLABO | 2300004782 | DK40 - Replaced by 2300006565 | OIW Correlation |  |  | 0 | 0 | Empty | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2026-01-28 | 10 |  |  | DF /C /75 | OIW Correlation | Unknown
4 | Empty | WRO | PRODLABO | PRODLABO | 2300004782 | DK40 - Replaced by 2300006565 | OIW Correlation |  |  | 0 | 0 | Empty | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2026-01-28 | 20 |  |  | DF /C /75 | OIW Correlation | Unknown
4 | Empty | WRO | PRODLABO | PRODLABO | 2300004782 | DK40 - Replaced by 2300006565 | OIW Correlation |  |  | 0 | 0 | Empty | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2026-01-28 | 30 |  |  | DF /C /75 | OIW Correlation | Unknown
4 | Empty | WRO | PRODLABO | PRODLABO | 2300004782 | DK40 - Replaced by 2300006565 | OIW Correlation |  |  | 0 | 0 | Empty | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2023-08-12 | 2026-01-28 | 40 |  |  | DF /C /75 | OIW Correlation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100111333 | DFC Gen HI-FOG PSL alarm. | Leak search | SECE | SECE | 4 | 0 | Empty | 2024-06-07 | 2024-06-09 | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-10-20 | 10 | SECE | SECE | DF /C /01/DFCI-PSL-04120 | Leak search | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100111333 | DFC Gen HI-FOG PSL alarm. | Leak search | SECE | SECE | 1 | 0 | Empty | 2024-06-07 | 2024-06-09 | 2024-06-08 | 2024-06-09 | 2024-06-07 | 2024-10-20 | 20 | SECE | SECE | DF /C /01/DFCI-PSL-04120 | Leak search | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 2 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 3 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 4 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 5 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 2 | 19 | Empty | 2024-04-05 | 2024-04-26 | 2020-10-09 | 2021-06-02 | 2020-09-08 | 2020-12-07 | 10 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 96 | 0.5 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-09 | 2020-09-08 | 2020-12-07 | 20 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 12 | 12 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-06 | 2021-03-08 | 2020-09-08 | 2020-12-07 | 30 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 2.5 | Empty | 2024-04-05 | 2024-04-26 | 2021-05-31 | 2021-06-12 | 2020-09-08 | 2020-12-07 | 40 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-05-31 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 50 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 5 | 23.5 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-17 | 2021-04-25 | 2020-09-08 | 2020-12-07 | 60 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 5 | 12 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-21 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 70 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 5 | 5 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-13 | 2021-05-02 | 2020-09-08 | 2020-12-07 | 90 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 60 | 61 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-14 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 100 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 8 | 8 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-13 | 2021-05-02 | 2020-09-08 | 2020-12-07 | 107 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 8 | 8.5 | Empty | 2024-04-05 | 2024-04-26 | 2021-05-03 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 108 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 2 | 2 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-15 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 110 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 4 | 29 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-17 | 2021-04-25 | 2020-09-08 | 2020-12-07 | 120 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 40 | 38.5 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-18 | 2021-04-25 | 2020-09-08 | 2020-12-07 | 121 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 8 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-20 | 2021-04-25 | 2020-09-08 | 2020-12-07 | 123 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 4 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-05-31 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 125 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 6 | 11 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-24 | 2021-06-01 | 2020-09-08 | 2020-12-07 | 130 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 6 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-22 | 2021-04-25 | 2020-09-08 | 2020-12-07 | 170 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 18 | 17.5 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-20 | 2021-06-12 | 2020-09-08 | 2020-12-07 | 180 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 2 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 190 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 8 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-03-26 | 2021-04-25 | 2020-09-08 | 2020-12-07 | 200 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 32 | 32 | Empty | 2024-04-05 | 2024-04-26 | 2021-06-01 | 2021-06-15 | 2020-09-08 | 2020-12-07 | 250 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 30 | 8 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-08 | 2020-09-08 | 2020-12-07 | 260 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-06-15 | 2021-06-15 | 2020-09-08 | 2020-12-07 | 270 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 280 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 290 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 16 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-06 | 2020-09-08 | 2020-12-07 | 300 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 5 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-06 | 2020-09-08 | 2020-12-07 | 310 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 5 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 320 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 96 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-06 | 2024-04-10 | 2020-09-08 | 2020-12-07 | 330 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 120 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-07 | 2024-04-12 | 2020-09-08 | 2020-12-07 | 340 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 32 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-09 | 2020-09-08 | 2020-12-07 | 341 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 32 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-07 | 2024-04-09 | 2020-09-08 | 2020-12-07 | 350 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 2 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-09 | 2024-04-10 | 2020-09-08 | 2020-12-07 | 360 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 48 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-09 | 2024-04-12 | 2020-09-08 | 2020-12-07 | 370 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 24 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-09 | 2024-04-10 | 2020-09-08 | 2020-12-07 | 380 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 48 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-12 | 2024-04-15 | 2020-09-08 | 2020-12-07 | 390 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 40 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-12 | 2024-04-13 | 2020-09-08 | 2020-12-07 | 400 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-13 | 2024-04-13 | 2020-09-08 | 2020-12-07 | 410 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-13 | 2024-04-13 | 2020-09-08 | 2020-12-07 | 420 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | INP-SITE | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-13 | 2024-04-13 | 2020-09-08 | 2020-12-07 | 430 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 24 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2021-06-12 | 2021-06-12 | 2020-09-08 | 2020-12-07 | 440 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 4 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-14 | 2024-04-14 | 2020-09-08 | 2020-12-07 | 450 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 50 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-15 | 2024-04-20 | 2020-09-08 | 2020-12-07 | 460 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 96 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-20 | 2024-04-26 | 2020-09-08 | 2020-12-07 | 470 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 480 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100037152 | ANOP DFF Replace 12" Spool WI Line, PT-3 | Vendor PR for SO Weld on Flange | PCNF | PCNF | 0 | 0 | Empty | 2024-04-05 | 2024-04-26 | 2024-04-05 | 2024-04-05 | 2020-09-08 | 2020-12-07 | 490 | PCNF | PCNF | DF /F /54/DFF-12-WI-035-9049-AB-U | Vendor PR for SO Weld on Flange | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058084 | DFFA-P-3909 Oil change on pump | Isolate DFFA-P-3909 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-04-27 | 2023-02-21 | 10 |  |  | DF /F /75/DFFA-P-3909 | Isolate DFFA-P-3909 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058084 | DFFA-P-3909 Oil change on pump | Isolate DFFA-P-3909 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-04-27 | 2023-02-21 | 20 |  |  | DF /F /75/DFFA-P-3909 | Isolate DFFA-P-3909 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058084 | DFFA-P-3909 Oil change on pump | Isolate DFFA-P-3909 |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-04-27 | 2023-02-21 | 30 |  |  | DF /F /75/DFFA-P-3909 | Isolate DFFA-P-3909 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058084 | DFFA-P-3909 Oil change on pump | Isolate DFFA-P-3909 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-04-27 | 2023-02-21 | 40 |  |  | DF /F /75/DFFA-P-3909 | Isolate DFFA-P-3909 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058084 | DFFA-P-3909 Oil change on pump | Isolate DFFA-P-3909 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-04-27 | 2023-02-21 | 50 |  |  | DF /F /75/DFFA-P-3909 | Isolate DFFA-P-3909 | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400325774 | 5Y LIFE BOAT LOAD TEST - DFGA-X-0702 | LIFEBOAT LOAD TEST - DFGA-X-0702 | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-03-13 | 2024-06-01 | 10 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0702 | LIFEBOAT LOAD TEST - DFGA-X-0702 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400325774 | 5Y LIFE BOAT LOAD TEST - DFGA-X-0702 | LIFEBOAT LOAD TEST - DFGA-X-0702 | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-03-13 | 2024-06-01 | 20 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0702 | LIFEBOAT LOAD TEST - DFGA-X-0702 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084827 | PVI DAN F Level glass LG-500104 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 10 |  |  | DF /F /28/DFFA-LG-500104 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084827 | PVI DAN F Level glass LG-500104 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 20 |  |  | DF /F /28/DFFA-LG-500104 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084827 | PVI DAN F Level glass LG-500104 | Isolate Heat Tracing |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-08-02 | 2026-01-18 | 30 |  |  | DF /F /28/DFFA-LG-500104 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084827 | PVI DAN F Level glass LG-500104 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 40 |  |  | DF /F /28/DFFA-LG-500104 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084827 | PVI DAN F Level glass LG-500104 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 50 |  |  | DF /F /28/DFFA-LG-500104 | Isolate Heat Tracing | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322661 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-17 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 33 | 0 | Empty | 2024-06-27 | 2024-06-28 | 2024-06-27 | 2024-06-28 | 2024-03-21 | 2024-05-22 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-17 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322266 | DFC-27-OD-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322256 | DFC-28-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 48 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009235 | Insulation assist bilfinger 22075 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /F /27/DFF-3-DO-050-8071-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009235 | Insulation assist bilfinger 22075 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /F /27/DFF-3-DO-050-8071-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009235 | Insulation assist bilfinger 22075 | Bilfinger inspection |  |  | 3 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 22 |  |  | DF /F /27/DFF-3-DO-050-8071-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009235 | Insulation assist bilfinger 22075 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-10 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /F /27/DFF-3-DO-050-8071-AD-T | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097001 | DFCC-C-1303 Thermal error. | DFCC-C-1303 Thermal error. |  |  | 0 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-12 | 2024-02-24 | 10 |  |  | DF /C /82/DFCC-C-1303 | DFCC-C-1303 Thermal error. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100097001 | DFCC-C-1303 Thermal error. | DFCC-C-1303 Thermal error. |  |  | 1 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-12 | 2024-02-24 | 20 |  |  | DF /C /82/DFCC-C-1303 | DFCC-C-1303 Thermal error. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097001 | DFCC-C-1303 Thermal error. | DFCC-C-1303 Thermal error. |  |  | 2 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-12 | 2024-02-24 | 30 |  |  | DF /C /82/DFCC-C-1303 | DFCC-C-1303 Thermal error. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100097001 | DFCC-C-1303 Thermal error. | DFCC-C-1303 Thermal error. |  |  | 1 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-12 | 2024-02-24 | 40 |  |  | DF /C /82/DFCC-C-1303 | DFCC-C-1303 Thermal error. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097001 | DFCC-C-1303 Thermal error. | DFCC-C-1303 Thermal error. |  |  | 1 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-12 | 2024-02-24 | 50 |  |  | DF /C /82/DFCC-C-1303 | DFCC-C-1303 Thermal error. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100097001 | DFCC-C-1303 Thermal error. | DFCC-C-1303 Thermal error. |  |  | 0 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-12 | 2024-02-24 | 60 |  |  | DF /C /82/DFCC-C-1303 | DFCC-C-1303 Thermal error. | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328724 | 6M DEAERATOR MAINT - DFAA-V-3501 - DFA | DEAERATOR MAINT - DFAA-V-3501 - DFA |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-18 | 2024-06-06 | 10 |  |  | DF /A /53/DFAA-V-3501 | DEAERATOR MAINT - DFAA-V-3501 - DFA | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259282 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-06-18 | 10 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259282 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2023-05-13 | 2023-06-18 | 20 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259282 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2023-05-13 | 2023-06-18 | 30 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400259282 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2023-05-13 | 2023-06-18 | 40 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259282 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2023-05-13 | 2023-06-18 | 50 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235285 | 4Y 3KV N-SWB MAINT DFCI-N-1801-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2022-12-16 | 2023-03-14 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801-08-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235285 | 4Y 3KV N-SWB MAINT DFCI-N-1801-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 27 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-18 | 2022-12-16 | 2023-03-14 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801-08-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235285 | 4Y 3KV N-SWB MAINT DFCI-N-1801-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-20 | 2022-12-16 | 2023-03-14 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801-08-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235285 | 4Y 3KV N-SWB MAINT DFCI-N-1801-08 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2022-12-16 | 2023-03-14 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801-08-01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100072536 | Drawer repair for Turbine 1640 Starter | Isolate and retract drawer |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-09-22 | 2023-02-04 | 10 |  |  | DF /G /05/DFGA-N-1843-A01-HA001 | Isolate and retract drawer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072536 | Drawer repair for Turbine 1640 Starter | Isolate and retract drawer |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-09-22 | 2023-02-04 | 20 |  |  | DF /G /05/DFGA-N-1843-A01-HA001 | Isolate and retract drawer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072536 | Drawer repair for Turbine 1640 Starter | Isolate and retract drawer |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-09-22 | 2023-02-04 | 30 |  |  | DF /G /05/DFGA-N-1843-A01-HA001 | Isolate and retract drawer | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100072536 | Drawer repair for Turbine 1640 Starter | Isolate and retract drawer |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-09-22 | 2023-02-04 | 40 |  |  | DF /G /05/DFGA-N-1843-A01-HA001 | Isolate and retract drawer | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400281426 | 1Y WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCHSECE | SCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-09-11 | 2023-10-11 | 10 | SCHSECE | SCHSECE | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400281426 | 1Y WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCHSECE | SCHSECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2023-09-11 | 2023-10-11 | 20 | SCHSECE | SCHSECE | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400281426 | 1Y WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCHSECE | SCHSECE | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-16 | 2023-09-11 | 2023-10-11 | 30 | SCHSECE | SCHSECE | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400281426 | 1Y WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCHSECE | SCHSECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2023-09-11 | 2023-10-11 | 40 | SCHSECE | SCHSECE | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400281426 | 1Y WELL HYD. PANEL MAINT - DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | SCHSECE | SCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2023-09-11 | 2023-10-11 | 50 | SCHSECE | SCHSECE | DF /E /07/DFEZ-A-3102 | WELL HYD. PANEL MAINT - DFEZ-A-3102 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096112 | EMG. SHOWER DFCC-EMS-0673 water problem | De-isolate accordingly |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-09-05 | 2024-01-18 | 10 |  |  | DF /C /02/DFCC-EMS-0673 | De-isolate accordingly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096112 | EMG. SHOWER DFCC-EMS-0673 water problem | De-isolate accordingly |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-09-05 | 2024-01-18 | 20 |  |  | DF /C /02/DFCC-EMS-0673 | De-isolate accordingly | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096112 | EMG. SHOWER DFCC-EMS-0673 water problem | De-isolate accordingly |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-09-05 | 2024-01-18 | 30 |  |  | DF /C /02/DFCC-EMS-0673 | De-isolate accordingly | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100104203 | DFC malfunc. bleed valve on HCV-36026 | Remove old Bleed HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-02-09 | 2024-06-23 | 10 |  |  | DF /C /26/DFCI-HCV-36026 | Remove old Bleed HCV | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100104203 | DFC malfunc. bleed valve on HCV-36026 | Remove old Bleed HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-02-09 | 2024-06-23 | 20 |  |  | DF /C /26/DFCI-HCV-36026 | Remove old Bleed HCV | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100104203 | DFC malfunc. bleed valve on HCV-36026 | Remove old Bleed HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2024-02-09 | 2024-06-23 | 30 |  |  | DF /C /26/DFCI-HCV-36026 | Remove old Bleed HCV | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100104203 | DFC malfunc. bleed valve on HCV-36026 | Remove old Bleed HCV |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2024-02-09 | 2024-06-23 | 40 |  |  | DF /C /26/DFCI-HCV-36026 | Remove old Bleed HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030500 | Recharge DFFA-PD-460212 (Nitrogen on pul | Isolate DFFA-PD-460212 + P4602 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-04-05 | 2020-07-04 | 10 |  |  | DF /F /75/DFFA-PD-460212 | Isolate DFFA-PD-460212 + P4602 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100030500 | Recharge DFFA-PD-460212 (Nitrogen on pul | Isolate DFFA-PD-460212 + P4602 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-04-05 | 2020-07-04 | 20 |  |  | DF /F /75/DFFA-PD-460212 | Isolate DFFA-PD-460212 + P4602 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030500 | Recharge DFFA-PD-460212 (Nitrogen on pul | Isolate DFFA-PD-460212 + P4602 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-04-05 | 2020-07-04 | 30 |  |  | DF /F /75/DFFA-PD-460212 | Isolate DFFA-PD-460212 + P4602 | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300006748 | DO NOT USE - Replaced by 2300007686 | add materials |  |  | 0 | 0 | Empty | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2026-09-11 | 10 |  |  | DF /C /84 | add materials | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300006748 | DO NOT USE - Replaced by 2300007686 | add materials |  |  | 0 | 0 | Empty | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2026-09-11 | 20 |  |  | DF /C /84 | add materials | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300006748 | DO NOT USE - Replaced by 2300007686 | add materials |  |  | 0 | 0 | Empty | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2026-09-11 | 30 |  |  | DF /C /84 | add materials | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100044568 | Replace tubing w. hose DFGA-A-0462. | Isolate DFGA-A-0462 | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2021-05-07 | 2021-05-31 | 2021-02-02 | 2021-03-14 | 10 | PCNFAWSC | PCNFAWSC | DF /G /01/DFGA-A-0462 | Isolate DFGA-A-0462 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044568 | Replace tubing w. hose DFGA-A-0462. | Isolate DFGA-A-0462 | PCNFAWSC | PCNFAWSC | 2 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2021-05-07 | 2021-05-08 | 2021-02-02 | 2021-03-14 | 20 | PCNFAWSC | PCNFAWSC | DF /G /01/DFGA-A-0462 | Isolate DFGA-A-0462 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100044568 | Replace tubing w. hose DFGA-A-0462. | Isolate DFGA-A-0462 | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2021-05-07 | 2021-05-31 | 2021-02-02 | 2021-03-14 | 30 | PCNFAWSC | PCNFAWSC | DF /G /01/DFGA-A-0462 | Isolate DFGA-A-0462 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100044568 | Replace tubing w. hose DFGA-A-0462. | Isolate DFGA-A-0462 | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-02-02 | 2021-03-14 | 40 | PCNFAWSC | PCNFAWSC | DF /G /01/DFGA-A-0462 | Isolate DFGA-A-0462 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044568 | Replace tubing w. hose DFGA-A-0462. | Isolate DFGA-A-0462 | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-02-02 | 2021-03-14 | 50 | PCNFAWSC | PCNFAWSC | DF /G /01/DFGA-A-0462 | Isolate DFGA-A-0462 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100044568 | Replace tubing w. hose DFGA-A-0462. | Isolate DFGA-A-0462 | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-02-02 | 2021-03-14 | 60 | PCNFAWSC | PCNFAWSC | DF /G /01/DFGA-A-0462 | Isolate DFGA-A-0462 | Unknown
3 | DFA-O18 | WDF | MTN-INST | MTN-INST | 2100098848 | DFA-18 Choke ZT needs adjustment | Choke's ZT needs adjustment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-11-10 | 2024-03-24 | 10 | AWSC | AWSC | DF /A /10/DFAA-ZT-30306 | Choke's ZT needs adjustment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-07 | 2024-06-07 | 2020-04-07 | 2021-04-02 | 10 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 12 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-07 | 2024-06-09 | 2020-04-07 | 2021-04-02 | 20 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-09 | 2024-06-09 | 2020-04-07 | 2021-04-02 | 30 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-09 | 2024-06-09 | 2020-04-07 | 2021-04-02 | 40 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-09 | 2024-06-10 | 2020-04-07 | 2021-04-02 | 50 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-10 | 2024-06-11 | 2020-04-07 | 2021-04-02 | 60 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-11 | 2024-06-11 | 2020-04-07 | 2021-04-02 | 70 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-11 | 2024-06-11 | 2020-04-07 | 2021-04-02 | 80 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-11 | 2024-06-12 | 2020-04-07 | 2021-04-02 | 90 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-12 | 2024-06-12 | 2020-04-07 | 2021-04-02 | 100 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-12 | 2024-06-12 | 2020-04-07 | 2021-04-02 | 110 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-12 | 2024-06-13 | 2020-04-07 | 2021-04-02 | 120 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-13 | 2024-06-14 | 2020-04-07 | 2021-04-02 | 130 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-14 | 2024-06-14 | 2020-04-07 | 2021-04-02 | 140 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-14 | 2024-06-14 | 2020-04-07 | 2021-04-02 | 150 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-14 | 2024-06-15 | 2020-04-07 | 2021-04-02 | 160 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 12 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-15 | 2024-06-16 | 2020-04-07 | 2021-04-02 | 170 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100027599 | Exchange valves XCV-30080 & 30080A | Prepare rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-06-07 | 2024-06-17 | 2024-06-16 | 2024-06-17 | 2020-04-07 | 2021-04-02 | 180 | AWSC | AWSC | DF /B /10/DFBA-XCV-30080 | Prepare rigging equipment | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298675 | 1Y INERT GAS GEN UNIT MAINT-DFFA-A-0801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-12-23 | 2024-01-22 | 10 | SECE | SECE | DF /F /74/DFFA-A-0801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298675 | 1Y INERT GAS GEN UNIT MAINT-DFFA-A-0801 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-12-23 | 2024-01-22 | 20 | SECE | SECE | DF /F /74/DFFA-A-0801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400298675 | 1Y INERT GAS GEN UNIT MAINT-DFFA-A-0801 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-12-23 | 2024-01-22 | 30 | SECE | SECE | DF /F /74/DFFA-A-0801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400298675 | 1Y INERT GAS GEN UNIT MAINT-DFFA-A-0801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-12-23 | 2024-01-22 | 40 | SECE | SECE | DF /F /74/DFFA-A-0801 | ISOLATION BY PRODUCTION | Unknown
B | DHDHPGAS | WPM | MTN-MECH | PRODTECH | 2400176987 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | REGISTRATION OF WORKING HOURS | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-12-19 | 2022-02-19 | 2 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | REGISTRATION OF WORKING HOURS | Unknown
B | DHDHPGAS | WPM | MTN-MECH | MTN-ELEC | 2400176987 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | REGISTRATION OF WORKING HOURS | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-12-19 | 2022-02-19 | 10 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | REGISTRATION OF WORKING HOURS | Unknown
B | DHDHPGAS | WPM | MTN-MECH | MTN-MECH | 2400176987 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | REGISTRATION OF WORKING HOURS | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-12-19 | 2022-02-19 | 20 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | REGISTRATION OF WORKING HOURS | Unknown
B | DHDHPGAS | WPM | MTN-MECH | MTN-MECH | 2400176987 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | REGISTRATION OF WORKING HOURS | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-12-19 | 2022-02-19 | 30 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | REGISTRATION OF WORKING HOURS | Unknown
B | DHDHPGAS | WPM | MTN-MECH | PRODTECH | 2400176987 | 3Y FUNC, VISUAL, EX INSP ESDV (DHDHPGAS) | REGISTRATION OF WORKING HOURS | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-12-19 | 2022-02-19 | 40 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | REGISTRATION OF WORKING HOURS | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2023-12-27 | 2024-02-10 | 10 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-07-30 | 2023-12-27 | 2024-02-10 | 20 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-08-01 | 2023-12-27 | 2024-02-10 | 30 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-08-01 | 2023-12-27 | 2024-02-10 | 40 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-03 | 2023-12-27 | 2024-02-10 | 50 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-05 | 2023-12-27 | 2024-02-10 | 60 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-05 | 2023-12-27 | 2024-02-10 | 70 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-12-27 | 2024-02-10 | 80 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2023-12-27 | 2024-02-10 | 90 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104298 | DFF-PCV-530006 needs cleaning | Isolate DFF-PCV-530006 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2023-12-27 | 2024-02-10 | 100 |  |  | DF /F /50/DFFA-PCV-530006 | Isolate DFF-PCV-530006 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104821 | DFC WIC HVAC B-1221A can't start | Repair instrument tubing | PCNF | PCNF | 12 | 14 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-01-06 | 2024-01-07 | 2024-01-06 | 2024-02-20 | 10 | PCNF | PCNF | DF /C /09/DFCI-B-1221A | Repair instrument tubing | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104821 | DFC WIC HVAC B-1221A can't start | Repair instrument tubing | PCNF | PCNF | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-06 | 2024-02-20 | 20 | PCNF | PCNF | DF /C /09/DFCI-B-1221A | Repair instrument tubing | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104821 | DFC WIC HVAC B-1221A can't start | Repair instrument tubing | PCNF | PCNF | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-06 | 2024-02-20 | 30 | PCNF | PCNF | DF /C /09/DFCI-B-1221A | Repair instrument tubing | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263365 | 3M SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-06-29 | 2023-07-10 | 10 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263365 | 3M SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2023-06-29 | 2023-07-10 | 12 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
D | Empty | WPM | PRODTECH | MTN-MECH | 2400344389 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 0 | 0 | Empty | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-09-23 | 2024-09-29 | 1 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400344389 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 4 | 0 | Empty | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-09-23 | 2024-09-29 | 2 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065844 | ANOCR DFB - Paint Structure EL +30600 | Erect Scaffold & habitats |  |  | 0 | 0 | Empty | 2022-06-22 | 2022-08-15 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-11-19 | 10 |  |  | DF /B /86/30600 - PRIM AND SEC STRUCT | Erect Scaffold & habitats | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065844 | ANOCR DFB - Paint Structure EL +30600 | Erect Scaffold & habitats |  |  | 76 | 0 | Empty | 2022-06-22 | 2022-08-15 | 2022-06-22 | 2022-07-02 | 2022-06-22 | 2022-11-19 | 20 |  |  | DF /B /86/30600 - PRIM AND SEC STRUCT | Erect Scaffold & habitats | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065844 | ANOCR DFB - Paint Structure EL +30600 | Erect Scaffold & habitats |  |  | 6 | 0 | Empty | 2022-06-22 | 2022-08-15 | 2022-07-02 | 2022-07-02 | 2022-06-22 | 2022-11-19 | 30 |  |  | DF /B /86/30600 - PRIM AND SEC STRUCT | Erect Scaffold & habitats | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065844 | ANOCR DFB - Paint Structure EL +30600 | Erect Scaffold & habitats |  |  | 513 | 0 | Empty | 2022-06-22 | 2022-08-15 | 2022-07-02 | 2022-08-14 | 2022-06-22 | 2022-11-19 | 40 |  |  | DF /B /86/30600 - PRIM AND SEC STRUCT | Erect Scaffold & habitats | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100065844 | ANOCR DFB - Paint Structure EL +30600 | Erect Scaffold & habitats |  |  | 12 | 0 | Empty | 2022-06-22 | 2022-08-15 | 2022-08-14 | 2022-08-15 | 2022-06-22 | 2022-11-19 | 50 |  |  | DF /B /86/30600 - PRIM AND SEC STRUCT | Erect Scaffold & habitats | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100044249 | DFC LEVEL 1. DFC-XCV-50445 SIDDER FAST | Vendor to Troubleshoot on XCV-50445 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCI-XCV-50445 | Vendor to Troubleshoot on XCV-50445 | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100044249 | DFC LEVEL 1. DFC-XCV-50445 SIDDER FAST | Vendor to Troubleshoot on XCV-50445 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCI-XCV-50445 | Vendor to Troubleshoot on XCV-50445 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000754 | DECK * IKKE MAX/MIN* 01.01.19-31.12.19 | DECK 21.03.20 |  |  | 0 | 0 | Empty | 2020-03-21 | 2020-03-21 | 2020-03-21 | 2020-03-21 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF | DECK 21.03.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000754 | DECK * IKKE MAX/MIN* 01.01.19-31.12.19 | DECK 21.03.20 |  |  | 0 | 0 | Empty | 2020-03-21 | 2020-03-21 | 2020-03-21 | 2020-03-21 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF | DECK 21.03.20 | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400337674 | 1Y WEIGHT IN HLO REPLACE - DFCC-WT-69008 | WEIGHT IN HLO REPLACE - DFCC-WT-69008 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-07-07 | 2024-08-23 | 10 |  |  | DF /C /84/DFCC-WT-69008 | WEIGHT IN HLO REPLACE - DFCC-WT-69008 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-21 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-21 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 5 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 5 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-28 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-28 | 2024-06-29 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-06-30 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284239 | PSV Calibration - DFCI-PSV-34004 | Documentation & CNF WO | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /20/DFCI-PSV-34004 | Documentation & CNF WO | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2020-12-07 | 2021-05-06 | 10 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2020-12-07 | 2021-05-06 | 20 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-16 | 2020-12-07 | 2021-05-06 | 30 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-16 | 2024-09-19 | 2020-12-07 | 2021-05-06 | 40 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-20 | 2020-12-07 | 2021-05-06 | 50 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-20 | 2024-09-20 | 2020-12-07 | 2021-05-06 | 60 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-20 | 2024-09-21 | 2020-12-07 | 2021-05-06 | 70 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2024-09-23 | 2020-12-07 | 2021-05-06 | 75 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2020-12-07 | 2021-05-06 | 80 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2020-12-07 | 2021-05-06 | 90 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038736 | DFG/78: Replace floating block main hook | Order new floating block |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2020-12-07 | 2021-05-06 | 100 |  |  | DF /G /78/DFGA-A-6140 | Order new floating block | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235797 | 4Y 380V N-SWB MAINT-DFBA-N-1810 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235797 | 4Y 380V N-SWB MAINT-DFBA-N-1810 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235797 | 4Y 380V N-SWB MAINT-DFBA-N-1810 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235797 | 4Y 380V N-SWB MAINT-DFBA-N-1810 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810 | ISOLATION ELECTRICAL | Unknown
A | DFA-OIL | WPM | MTN-MECH | PRODTECH | 2400214777 | 1Y SDV LUBE/FUNC TEST OIL - DFA | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2022-10-06 | 2022-11-05 | 10 | SECE | SECE | DF /A /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFA-OIL | WPM | MTN-MECH | MTN-MECH | 2400214777 | 1Y SDV LUBE/FUNC TEST OIL - DFA | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2022-10-06 | 2022-11-05 | 20 | SECE | SECE | DF /A /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFA-OIL | WPM | MTN-MECH | PRODTECH | 2400214777 | 1Y SDV LUBE/FUNC TEST OIL - DFA | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-10-06 | 2022-11-05 | 30 | SECE | SECE | DF /A /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100036494 | DFF 400V Breaker DFFA-N-1813 - SCADA | Additional materials | SCH | SCH | 3 | 0 | 24-W07-08 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2020-08-27 | 2020-10-06 | 10 | SCH | SCH | DF /F /05/DFFA-N-1813-2 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100036494 | DFF 400V Breaker DFFA-N-1813 - SCADA | Additional materials | SCH | SCH | 0 | 0 | 24-W07-08 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2020-08-27 | 2020-10-06 | 20 | SCH | SCH | DF /F /05/DFFA-N-1813-2 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100036494 | DFF 400V Breaker DFFA-N-1813 - SCADA | Additional materials | SCH | SCH | 0 | 0 | 24-W07-08 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2020-08-27 | 2020-10-06 | 30 | SCH | SCH | DF /F /05/DFFA-N-1813-2 | Additional materials | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036454 | DFF-21 CI/ still Scale inj flow DFFA-FCV | Replace DFFA-FCV-390189 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-09-05 | 2020-12-04 | 10 |  |  | DF /F /75/DFFA-FCV-390189 | Replace DFFA-FCV-390189 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036454 | DFF-21 CI/ still Scale inj flow DFFA-FCV | Replace DFFA-FCV-390189 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2020-09-05 | 2020-12-04 | 20 |  |  | DF /F /75/DFFA-FCV-390189 | Replace DFFA-FCV-390189 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036454 | DFF-21 CI/ still Scale inj flow DFFA-FCV | Replace DFFA-FCV-390189 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2020-09-05 | 2020-12-04 | 30 |  |  | DF /F /75/DFFA-FCV-390189 | Replace DFFA-FCV-390189 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235801 | 4Y 380V N-SWB MAINT-DFBA-N-1810-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_25 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235801 | 4Y 380V N-SWB MAINT-DFBA-N-1810-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_25 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235801 | 4Y 380V N-SWB MAINT-DFBA-N-1810-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_25 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235801 | 4Y 380V N-SWB MAINT-DFBA-N-1810-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_25 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193023 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59180 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59180 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /07/DFAA-FP-59180 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59180 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2022-12-05 | 2023-04-19 | 10 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2022-12-05 | 2023-04-19 | 20 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2022-12-05 | 2023-04-19 | 29 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2022-12-05 | 2023-04-19 | 30 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2022-12-05 | 2023-04-19 | 40 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2022-12-05 | 2023-04-19 | 49 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2022-12-05 | 2023-04-19 | 50 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2022-12-05 | 2023-04-19 | 60 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2022-12-05 | 2023-04-19 | 70 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081823 | DFG XCV-500862 can't open. | Mount new actuator on Valve |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2022-12-05 | 2023-04-19 | 80 |  |  | DF /G /27/DFGA-XCV-500862 | Mount new actuator on Valve | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235802 | 4Y 380V N-SWB MAINT-DFBA-N-1810-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_84 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235802 | 4Y 380V N-SWB MAINT-DFBA-N-1810-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_84 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235802 | 4Y 380V N-SWB MAINT-DFBA-N-1810-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_84 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235802 | 4Y 380V N-SWB MAINT-DFBA-N-1810-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_84 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059774 | Cable to light fixture missing support | Tiewrap loose cable |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-03-03 | 2022-07-31 | 10 |  |  | DF /F /62 | Tiewrap loose cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059774 | Cable to light fixture missing support | Tiewrap loose cable |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-03-03 | 2022-07-31 | 20 |  |  | DF /F /62 | Tiewrap loose cable | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 10 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 1 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 20 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2023-08-12 | 2023-12-25 | 30 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 40 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 50 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 60 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 1 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 70 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 1 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 80 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 1 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-08-12 | 2023-12-25 | 90 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100093864 | DFB-ESDV-33086 Extern Hydraulik leak | Remove damaged Actuator | SECE | SECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2023-08-12 | 2023-12-25 | 100 | SECE | SECE | DF /A /10/DFAA-ESDV-33086 | Remove damaged Actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-15 | 2024-07-15 | 2021-04-06 | 2021-07-05 | 10 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-15 | 2024-07-16 | 2021-04-06 | 2021-07-05 | 20 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-16 | 2024-07-19 | 2021-04-06 | 2021-07-05 | 30 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-19 | 2024-07-19 | 2021-04-06 | 2021-07-05 | 40 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-19 | 2024-07-19 | 2021-04-06 | 2021-07-05 | 50 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-19 | 2024-07-21 | 2021-04-06 | 2021-07-05 | 60 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047332 | DFA/78 Repair threads electrical swivel | Isolate crane DFAA-X-6102 |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2021-04-06 | 2021-07-05 | 70 |  |  | DF /A /78/DFAA-X-6102 | Isolate crane DFAA-X-6102 | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2019-05-20 | 2019-06-09 | 10 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | PRODTECH | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-02 | 2019-05-20 | 2019-06-09 | 20 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2019-05-20 | 2019-06-09 | 30 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2019-05-20 | 2019-06-09 | 40 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-04 | 2019-05-20 | 2019-06-09 | 50 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2019-05-20 | 2019-06-09 | 60 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2019-05-20 | 2019-06-09 | 70 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
3 | DFCLPSEP | WDF | MTN-MECH | PRODTECH | 2100022676 | CMAT:Exchange stem gasket DFCM-LCV-36110 | L3 Prepare Rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2019-05-20 | 2019-06-09 | 80 | AWSC | AWSC | DF /C /23/DFCM-LCV-36110 | L3 Prepare Rigging equipment | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073893 | Lækage på fusible loop på DFA deluge | Assist rope access team | PCNF | PCNF | 20 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-10-08 | 2023-02-20 | 10 | PCNF | PCNF | DF /A /01/DFAA-PT-11203 | Assist rope access team | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073893 | Lækage på fusible loop på DFA deluge | Assist rope access team | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-10-08 | 2023-02-20 | 20 | PCNF | PCNF | DF /A /01/DFAA-PT-11203 | Assist rope access team | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073893 | Lækage på fusible loop på DFA deluge | Assist rope access team | PCNF | PCNF | 16 | 42 | W27-W28 | 2024-07-29 | 2024-07-29 | 2023-02-13 | 2023-04-05 | 2022-10-08 | 2023-02-20 | 30 | PCNF | PCNF | DF /A /01/DFAA-PT-11203 | Assist rope access team | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073893 | Lækage på fusible loop på DFA deluge | Assist rope access team | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-10-08 | 2023-02-20 | 40 | PCNF | PCNF | DF /A /01/DFAA-PT-11203 | Assist rope access team | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073893 | Lækage på fusible loop på DFA deluge | Assist rope access team | PCNF | PCNF | 10 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-10-08 | 2023-02-20 | 50 | PCNF | PCNF | DF /A /01/DFAA-PT-11203 | Assist rope access team | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100073893 | Lækage på fusible loop på DFA deluge | Assist rope access team | PCNF | PCNF | 12 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-10-08 | 2023-02-20 | 60 | PCNF | PCNF | DF /A /01/DFAA-PT-11203 | Assist rope access team | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073516 | DFF-LT-390010 Defective | Build and remove scafffolding | PCNF | PCNF | 12 | 20 | W27-W28 | 2024-07-29 | 2024-07-31 | 2022-08-26 | 2023-11-25 | 2022-08-26 | 2022-09-10 | 10 | PCNF | PCNF | DF /F /75/DFFA-LIT-390010 | Build and remove scafffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073516 | DFF-LT-390010 Defective | Build and remove scafffolding | PCNF | PCNF | 0 | 24 | W27-W28 | 2024-07-29 | 2024-07-31 | 2022-08-27 | 2023-11-25 | 2022-08-26 | 2022-09-10 | 20 | PCNF | PCNF | DF /F /75/DFFA-LIT-390010 | Build and remove scafffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073516 | DFF-LT-390010 Defective | Build and remove scafffolding | PCNF | PCNF | 6 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-08-26 | 2022-09-10 | 30 | PCNF | PCNF | DF /F /75/DFFA-LIT-390010 | Build and remove scafffolding | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100073516 | DFF-LT-390010 Defective | Build and remove scafffolding | PCNF | PCNF | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2023-10-20 | 2023-11-25 | 2022-08-26 | 2022-09-10 | 40 | PCNF | PCNF | DF /F /75/DFFA-LIT-390010 | Build and remove scafffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100073516 | DFF-LT-390010 Defective | Build and remove scafffolding | PCNF | PCNF | 10 | 20 | W27-W28 | 2024-07-29 | 2024-07-31 | 2022-09-25 | 2023-11-25 | 2022-08-26 | 2022-09-10 | 50 | PCNF | PCNF | DF /F /75/DFFA-LIT-390010 | Build and remove scafffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100073516 | DFF-LT-390010 Defective | Build and remove scafffolding | PCNF | PCNF | 10 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2022-08-26 | 2022-09-10 | 60 | PCNF | PCNF | DF /F /75/DFFA-LIT-390010 | Build and remove scafffolding | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235768 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-07 | 380V N-SWB MAINT-DFEZ-N-1803-07 | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-07B1 | 380V N-SWB MAINT-DFEZ-N-1803-07 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235768 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-07 | 380V N-SWB MAINT-DFEZ-N-1803-07 | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-07B1 | 380V N-SWB MAINT-DFEZ-N-1803-07 | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 18 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-01 | 2025-01-03 | 2016-08-11 | 2017-04-08 | 10 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 12 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-03 | 2025-01-04 | 2016-08-11 | 2017-04-08 | 20 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 18 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-04 | 2025-01-06 | 2016-08-11 | 2017-04-08 | 30 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 10 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-07 | 2025-01-09 | 2016-08-11 | 2017-04-08 | 40 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 12 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-09 | 2025-01-10 | 2016-08-11 | 2017-04-08 | 50 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 1 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-11 | 2025-01-11 | 2016-08-11 | 2017-04-08 | 60 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100027032 | Replace Gaskets on DFGA-XCV-033553 | Isolate 3 Valves as on P&ID | AWSC | AWSC | 0 | 0 | OIM FW EXL - Freeze E | 2025-01-01 | 2025-01-11 | 2025-01-01 | 2025-01-01 | 2016-08-11 | 2017-04-08 | 70 | AWSC | AWSC | DF /G /01/DFGA-FO-033553 | Isolate 3 Valves as on P&ID | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098343 | DFFW/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2023-10-29 | 2024-03-12 | 10 |  |  | DF /F /78/DFFA-MD-6102 | Start up and top up if neccessery | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098343 | DFFW/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2023-10-29 | 2024-03-12 | 20 |  |  | DF /F /78/DFFA-MD-6102 | Start up and top up if neccessery | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100098343 | DFFW/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2023-10-29 | 2024-03-12 | 30 |  |  | DF /F /78/DFFA-MD-6102 | Start up and top up if neccessery | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098343 | DFFW/78 Replace coolant with new type | Start up and top up if neccessery |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2023-10-29 | 2024-03-12 | 40 |  |  | DF /F /78/DFFA-MD-6102 | Start up and top up if neccessery | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012624 | PSV Exchange DFBA-PSV-33001 - PSV 2023 | operation_description_not_present |  |  | 2 | 2 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /B /10/DFBA-PSV-33001 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012624 | PSV Exchange DFBA-PSV-33001 - PSV 2023 | operation_description_not_present |  |  | 2 | 2 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /B /10/DFBA-PSV-33001 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012624 | PSV Exchange DFBA-PSV-33001 - PSV 2023 | operation_description_not_present |  |  | 5 | 14 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /B /10/DFBA-PSV-33001 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012624 | PSV Exchange DFBA-PSV-33001 - PSV 2023 | operation_description_not_present |  |  | 4 | 4 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /B /10/DFBA-PSV-33001 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012624 | PSV Exchange DFBA-PSV-33001 - PSV 2023 | operation_description_not_present |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /B /10/DFBA-PSV-33001 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012624 | PSV Exchange DFBA-PSV-33001 - PSV 2023 | operation_description_not_present |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-06-03 | 2025-11-19 | 60 |  |  | DF /B /10/DFBA-PSV-33001 | operation_description_not_present | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400306656 | 6M CRUD OL BOSTR PUMP -DFCM-P-3620/10 | CRUD OL BOSTR PMP MAINT-DFCM-P-3620/10 | SCH | SCH | 4 | 0 | W23-W24 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-06 | 2024-02-08 | 2024-02-24 | 10 | SCH | SCH | DF /C /23/DFCM-P-3620 | CRUD OL BOSTR PMP MAINT-DFCM-P-3620/10 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400306656 | 6M CRUD OL BOSTR PUMP -DFCM-P-3620/10 | CRUD OL BOSTR PMP MAINT-DFCM-P-3620/10 | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-06 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-02-08 | 2024-02-24 | 20 | SCH | SCH | DF /C /23/DFCM-P-3620 | CRUD OL BOSTR PMP MAINT-DFCM-P-3620/10 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077770 | DFC LB1 replace foundation bolts | Replace winch foundation bolts one by on |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-09 | 2025-10-25 | 10 |  |  | DF /C /02/DFCI-X-0701 | Replace winch foundation bolts one by on | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077770 | DFC LB1 replace foundation bolts | Replace winch foundation bolts one by on |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 20 |  |  | DF /C /02/DFCI-X-0701 | Replace winch foundation bolts one by on | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077770 | DFC LB1 replace foundation bolts | Replace winch foundation bolts one by on |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 30 |  |  | DF /C /02/DFCI-X-0701 | Replace winch foundation bolts one by on | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077770 | DFC LB1 replace foundation bolts | Replace winch foundation bolts one by on |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-09 | 2025-10-25 | 35 |  |  | DF /C /02/DFCI-X-0701 | Replace winch foundation bolts one by on | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100077770 | DFC LB1 replace foundation bolts | Replace winch foundation bolts one by on |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 40 |  |  | DF /C /02/DFCI-X-0701 | Replace winch foundation bolts one by on | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329994 | 3M FIREWATER PUMP PKG MAINT-DFEY-A-0303 | FIREWATER PUMP PKG MAINT-DFEY-A-0303 | SCHSECE | SCHSECE | 8 | 0 | W23-W24 | 2024-07-26 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-06-20 | 2024-06-30 | 10 | SCHSECE | SCHSECE | DF /E /01/DFEY-A-0303 | FIREWATER PUMP PKG MAINT-DFEY-A-0303 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060281 | Replace light fixture DFCC-801-24-L1N | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-03-11 | 2022-08-08 | 10 |  |  | DF /C /05/DFCC-N-1813-04-05-Q24 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100060281 | Replace light fixture DFCC-801-24-L1N | Isolate accordingly |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-03-11 | 2022-08-08 | 20 |  |  | DF /C /05/DFCC-N-1813-04-05-Q24 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100060281 | Replace light fixture DFCC-801-24-L1N | Isolate accordingly |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-03-11 | 2022-08-08 | 30 |  |  | DF /C /05/DFCC-N-1813-04-05-Q24 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060281 | Replace light fixture DFCC-801-24-L1N | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-03-11 | 2022-08-08 | 40 |  |  | DF /C /05/DFCC-N-1813-04-05-Q24 | Isolate accordingly | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344334 | 1Y SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-27 | 2024-08-29 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-09-26 | 10 | SECE | SECE | DF /G /75/DFGA-A-3988 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344334 | 1Y SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SECE | SECE | 4 | 0 | W35-W36 | 2024-08-27 | 2024-08-29 | 2024-08-27 | 2024-08-28 | 2024-08-27 | 2024-09-26 | 20 | SECE | SECE | DF /G /75/DFGA-A-3988 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344334 | 1Y SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SECE | SECE | 4 | 0 | W35-W36 | 2024-08-27 | 2024-08-29 | 2024-08-28 | 2024-08-29 | 2024-08-27 | 2024-09-26 | 30 | SECE | SECE | DF /G /75/DFGA-A-3988 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344334 | 1Y SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-27 | 2024-09-26 | 40 | SECE | SECE | DF /G /75/DFGA-A-3988 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344334 | 1Y SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-27 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-08-27 | 2024-09-26 | 50 | SECE | SECE | DF /G /75/DFGA-A-3988 | SCALE INH INJ PMP MAINT-DFGA-P-3988/9 | Unknown
D | Empty | WPM | PRODTECH | MTN-MECH | 2400337750 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 0 | 0 | Empty | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-08-12 | 2024-08-18 | 1 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400337750 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 4 | 8 | Empty | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-08-12 | 2024-08-18 | 2 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076136 | DFG: Replace emg. diesel cutoff valve | Replace Emg. dielsel cutoff valve | SCH | SCH | 2 | 2 | W33-34 | 2023-08-18 | 2023-08-20 | 2023-08-18 | 2023-08-18 | 2022-11-24 | 2023-04-08 | 10 | SCH | SCH | DF /G /78/DFGA-A-6140 | Replace Emg. dielsel cutoff valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076136 | DFG: Replace emg. diesel cutoff valve | Replace Emg. dielsel cutoff valve | SCH | SCH | 6 | 4 | W33-34 | 2023-08-18 | 2023-08-20 | 2023-08-18 | 2023-08-19 | 2022-11-24 | 2023-04-08 | 20 | SCH | SCH | DF /G /78/DFGA-A-6140 | Replace Emg. dielsel cutoff valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076136 | DFG: Replace emg. diesel cutoff valve | Replace Emg. dielsel cutoff valve | SCH | SCH | 1 | 24 | W33-34 | 2023-08-18 | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2022-11-24 | 2023-04-08 | 30 | SCH | SCH | DF /G /78/DFGA-A-6140 | Replace Emg. dielsel cutoff valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076136 | DFG: Replace emg. diesel cutoff valve | Replace Emg. dielsel cutoff valve | SCH | SCH | 0 | 1 | W33-34 | 2023-08-18 | 2023-08-20 | 2023-08-18 | 2023-08-18 | 2022-11-24 | 2023-04-08 | 40 | SCH | SCH | DF /G /78/DFGA-A-6140 | Replace Emg. dielsel cutoff valve | Unknown
A | DFG-3590 | WPM | MTN-TURB | MTN-INST | 2400298422 | 8KH WI PUMP SERV-DFGA-A-3590 COUNTER | PO Solar Turbines | AWSCSCH | AWSCSCH | 30 | 99 | Empty | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-12-16 | 2024-01-15 | 10 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-A-3590 | PO Solar Turbines | Unknown
A | DFG-3590 | WPM | MTN-TURB | VEN-MECH | 2400298422 | 8KH WI PUMP SERV-DFGA-A-3590 COUNTER | PO Solar Turbines | AWSCSCH | AWSCSCH | 90 | 29 | Empty | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-12-16 | 2024-01-15 | 20 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-A-3590 | PO Solar Turbines | Unknown
A | DFG-3590 | WPM | MTN-TURB | MTN-ELEC | 2400298422 | 8KH WI PUMP SERV-DFGA-A-3590 COUNTER | PO Solar Turbines | AWSCSCH | AWSCSCH | 16 | 16 | Empty | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-12-16 | 2024-01-15 | 30 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-A-3590 | PO Solar Turbines | Unknown
A | DFG-3590 | WPM | MTN-TURB | MTN-TURB | 2400298422 | 8KH WI PUMP SERV-DFGA-A-3590 COUNTER | PO Solar Turbines | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-12-16 | 2024-01-15 | 40 | AWSCSCH | AWSCSCH | DF /G /54/DFGA-A-3590 | PO Solar Turbines | Unknown
3 | DFF-W03 | WDF | MTN-MECH | PRODTECH | 2100029433 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3103 | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2020-03-22 | 2020-05-01 | 10 | AWSC | AWSC | DF /F /07/DFFA-FP-3103 | Drawer to be sent onshore for repair | Unknown
3 | DFF-W03 | WDF | MTN-MECH | MTN-MECH | 2100029433 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3103 | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2020-03-22 | 2020-05-01 | 20 | AWSC | AWSC | DF /F /07/DFFA-FP-3103 | Drawer to be sent onshore for repair | Unknown
3 | DFF-W03 | WDF | MTN-MECH | MTN-MECH | 2100029433 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3103 | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2020-03-22 | 2020-05-01 | 25 | AWSC | AWSC | DF /F /07/DFFA-FP-3103 | Drawer to be sent onshore for repair | Unknown
3 | DFF-W03 | WDF | MTN-MECH | PRODTECH | 2100029433 | DFF SSSV OVERIDE SOV STUCK OPEN, FP-3103 | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2020-03-22 | 2020-05-01 | 30 | AWSC | AWSC | DF /F /07/DFFA-FP-3103 | Drawer to be sent onshore for repair | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235803 | 4Y 380V N-SWB MAINT-DFBA-N-1810-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_35 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235803 | 4Y 380V N-SWB MAINT-DFBA-N-1810-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-02-14 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_35 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235803 | 4Y 380V N-SWB MAINT-DFBA-N-1810-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-02-14 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_35 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235803 | 4Y 380V N-SWB MAINT-DFBA-N-1810-06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-02-14 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_35 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235565 | 4Y 380V E/N-DP-DFCC-DP-DFC-DISTR.-PANEL | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /61/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235565 | 4Y 380V E/N-DP-DFCC-DP-DFC-DISTR.-PANEL | ISOLATION ELECTRICAL | AWSC | AWSC | 27 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-28 | 2023-02-14 | 2023-05-13 | 20 | AWSC | AWSC | DF /C /61/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235565 | 4Y 380V E/N-DP-DFCC-DP-DFC-DISTR.-PANEL | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-02-14 | 2023-05-13 | 30 | AWSC | AWSC | DF /C /61/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235565 | 4Y 380V E/N-DP-DFCC-DP-DFC-DISTR.-PANEL | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-02-14 | 2023-05-13 | 40 | AWSC | AWSC | DF /C /61/DISTRIBUTION-PANELS | ISOLATION ELECTRICAL | Unknown
B | DFG-3590 | WPM | MTN-MECH | MTN-MECH | 2400330121 | 4KH SDV/BDV LUB/MAINT WI DFGA-A-3590 | SDV/BDV LUB/INSP WI DFGA-A-3590 | AWSC | AWSC | 2.5 | 0 | Empty | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-06-23 | 10 | AWSC | AWSC | DF /G /54/DFGA-A-3590 | SDV/BDV LUB/INSP WI DFGA-A-3590 | Unknown
4 | DFF-TSEP | WDF | MTN-MECH | PRODTECH | 2100024993 | Exchange XCV-500041 | Isolate equipment | AWSC | AWSC | 4 | 0 | W49-50 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2020-01-30 | 2020-06-28 | 10 | AWSC | AWSC | DF /F /27/DFFA-XCV-500041 | Isolate equipment | Unknown
4 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100024993 | Exchange XCV-500041 | Isolate equipment | AWSC | AWSC | 4 | 0 | W49-50 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2020-01-30 | 2020-06-28 | 20 | AWSC | AWSC | DF /F /27/DFFA-XCV-500041 | Isolate equipment | Unknown
4 | DFF-TSEP | WDF | MTN-MECH | MTN-INST | 2100024993 | Exchange XCV-500041 | Isolate equipment | AWSC | AWSC | 4 | 0 | W49-50 | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2020-01-30 | 2020-06-28 | 30 | AWSC | AWSC | DF /F /27/DFFA-XCV-500041 | Isolate equipment | Unknown
4 | DFF-TSEP | WDF | MTN-MECH | PRODTECH | 2100024993 | Exchange XCV-500041 | Isolate equipment | AWSC | AWSC | 4 | 0 | W49-50 | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2020-01-30 | 2020-06-28 | 40 | AWSC | AWSC | DF /F /27/DFFA-XCV-500041 | Isolate equipment | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258809 | 1Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 38 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258809 | 1Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258809 | 1Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258809 | 1Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258809 | 1Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-05-02 | 2023-06-01 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROPE | 2400258809 | 1Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 6 | 6 | W25-W26 | 2024-06-17 | 2024-06-17 | 2023-11-22 | 2023-11-29 | 2023-05-02 | 2023-06-01 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100024011 | Change of valve for DFG-FIT-340441 | L3 Isolation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-10-20 | 2019-01-18 | 10 | AWSC | AWSC | DF /G /20 | L3 Isolation | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-INST | 2100024011 | Change of valve for DFG-FIT-340441 | L3 Isolation | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2018-10-20 | 2019-01-18 | 20 | AWSC | AWSC | DF /G /20 | L3 Isolation | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100024011 | Change of valve for DFG-FIT-340441 | L3 Isolation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-10-20 | 2019-01-18 | 30 | AWSC | AWSC | DF /G /20 | L3 Isolation | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235844 | 4Y 400V E-SWB MAINT DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235844 | 4Y 400V E-SWB MAINT DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235844 | 4Y 400V E-SWB MAINT DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235844 | 4Y 400V E-SWB MAINT DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A06 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059755 | FLMR DFC - Repl of gratings EL +60500 | DFC - Replacement of gratings EL +60500 |  |  | 0 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +60500 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059755 | FLMR DFC - Repl of gratings EL +60500 | DFC - Replacement of gratings EL +60500 |  |  | 3 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +60500 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059755 | FLMR DFC - Repl of gratings EL +60500 | DFC - Replacement of gratings EL +60500 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +60500 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059755 | FLMR DFC - Repl of gratings EL +60500 | DFC - Replacement of gratings EL +60500 |  |  | 6 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +60500 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059755 | FLMR DFC - Repl of gratings EL +60500 | DFC - Replacement of gratings EL +60500 |  |  | 3 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 50 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +60500 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059755 | FLMR DFC - Repl of gratings EL +60500 | DFC - Replacement of gratings EL +60500 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 60 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +60500 | Unknown
3 | NE | WRO | MTN-INST | MTN-INST | 2300002923 | DFG-PDIT-440430 (change of range) | De-Isolate PDIT | PCNF | PCNF | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-06-12 | 2021-09-10 | 10 | PCNF | PCNF | DF /G /31/DFGA-PDIT-440430 | De-Isolate PDIT | Unknown
3 | NE | WRO | MTN-INST | MTN-INST | 2300002923 | DFG-PDIT-440430 (change of range) | De-Isolate PDIT | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-06-12 | 2021-09-10 | 20 | PCNF | PCNF | DF /G /31/DFGA-PDIT-440430 | De-Isolate PDIT | Unknown
3 | NE | WRO | MTN-INST | MTN-INST | 2300002923 | DFG-PDIT-440430 (change of range) | De-Isolate PDIT | PCNF | PCNF | 6 | 36 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-06-12 | 2021-09-10 | 30 | PCNF | PCNF | DF /G /31/DFGA-PDIT-440430 | De-Isolate PDIT | Unknown
3 | NE | WRO | MTN-INST | MTN-INST | 2300002923 | DFG-PDIT-440430 (change of range) | De-Isolate PDIT | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-06-12 | 2021-09-10 | 40 | PCNF | PCNF | DF /G /31/DFGA-PDIT-440430 | De-Isolate PDIT | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235309 | 4Y 3KV E-SWB MAINT-DFCI-N-1811 | PO Caverion | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-14 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | PO Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235309 | 4Y 3KV E-SWB MAINT-DFCI-N-1811 | PO Caverion | AWSCSECE | AWSCSECE | 16 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | PO Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235309 | 4Y 3KV E-SWB MAINT-DFCI-N-1811 | PO Caverion | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | PO Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235309 | 4Y 3KV E-SWB MAINT-DFCI-N-1811 | PO Caverion | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | PO Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235309 | 4Y 3KV E-SWB MAINT-DFCI-N-1811 | PO Caverion | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 50 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | PO Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235309 | 4Y 3KV E-SWB MAINT-DFCI-N-1811 | PO Caverion | AWSCSECE | AWSCSECE | 0.1000000000000000055511151231 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-31 | 2023-03-14 | 60 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1811 | PO Caverion | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087750 | Nød armatur 1812-10903-L3A | Nød armatur 1812-10903-L3A |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 10 |  |  | DF /F /05/DFFA-N-1812-03 | Nød armatur 1812-10903-L3A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087750 | Nød armatur 1812-10903-L3A | Nød armatur 1812-10903-L3A |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 20 |  |  | DF /F /05/DFFA-N-1812-03 | Nød armatur 1812-10903-L3A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087750 | Nød armatur 1812-10903-L3A | Nød armatur 1812-10903-L3A |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 30 |  |  | DF /F /05/DFFA-N-1812-03 | Nød armatur 1812-10903-L3A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087750 | Nød armatur 1812-10903-L3A | Nød armatur 1812-10903-L3A |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 40 |  |  | DF /F /05/DFFA-N-1812-03 | Nød armatur 1812-10903-L3A | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 10 | 6 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 10 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 4 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 20 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 12 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 30 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 4 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 40 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 4 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 50 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 4 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 60 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 12 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 70 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 5 | 0 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 | 2021-02-03 | 2021-03-15 | 80 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100044606 | LV157, DFGA-HCV-030126 intern lækage. | Isolate equipment | PCNF | PCNF | 5 | 5 | W51-52 OIM FW INL MPM | 2023-01-23 | 2023-01-23 | 2021-10-15 | 2022-01-17 | 2021-02-03 | 2021-03-15 | 90 | PCNF | PCNF | DF /G /01/DFGA-HCV-030126 | Isolate equipment | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235671 | 4Y 380V N-SWB MAINT-DFCI-N-1821-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1821-2A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235671 | 4Y 380V N-SWB MAINT-DFCI-N-1821-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1821-2A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235671 | 4Y 380V N-SWB MAINT-DFCI-N-1821-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1821-2A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235671 | 4Y 380V N-SWB MAINT-DFCI-N-1821-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1821-2A01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 2 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 3 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 4 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 5 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 8 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 10.099999999999999644728632116 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2024-01-02 | 2019-06-10 | 2019-06-30 | 10 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 10.099999999999999644728632116 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2024-01-02 | 2019-06-10 | 2019-06-30 | 20 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 10.099999999999999644728632116 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2024-01-02 | 2019-06-10 | 2019-06-30 | 30 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 10.099999999999999644728632116 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2024-01-02 | 2019-06-10 | 2019-06-30 | 40 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-01 | 2024-01-02 | 2019-06-10 | 2019-06-30 | 50 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-02 | 2024-01-04 | 2019-06-10 | 2019-06-30 | 52 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 4 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-04 | 2024-01-05 | 2019-06-10 | 2019-06-30 | 54 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 2.7000000000000001776356839392 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-05 | 2024-01-06 | 2019-06-10 | 2019-06-30 | 56 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-06 | 2024-01-07 | 2019-06-10 | 2019-06-30 | 60 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-07 | 2024-01-09 | 2019-06-10 | 2019-06-30 | 70 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-09 | 2024-01-12 | 2019-06-10 | 2019-06-30 | 80 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-12 | 2024-01-13 | 2019-06-10 | 2019-06-30 | 90 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-13 | 2024-01-15 | 2019-06-10 | 2019-06-30 | 92 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0.6999999999999999555910790147 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-15 | 2024-01-15 | 2019-06-10 | 2019-06-30 | 100 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-15 | 2024-01-16 | 2019-06-10 | 2019-06-30 | 110 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 111 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 112 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 113 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 4 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 114 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 115 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2023-12-31 | 2023-12-31 | 2019-06-10 | 2019-06-30 | 116 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-16 | 2024-01-19 | 2019-06-10 | 2019-06-30 | 120 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 4 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-19 | 2024-01-20 | 2019-06-10 | 2019-06-30 | 122 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-20 | 2024-01-22 | 2019-06-10 | 2019-06-30 | 130 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 16.100000000000001421085471515 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-22 | 2024-01-26 | 2019-06-10 | 2019-06-30 | 140 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-26 | 2024-01-28 | 2019-06-10 | 2019-06-30 | 150 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 4 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-28 | 2024-01-29 | 2019-06-10 | 2019-06-30 | 160 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 4 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-29 | 2024-01-30 | 2019-06-10 | 2019-06-30 | 170 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024400 | ANOP Replace spool and valve for service | L3 Prepare of Permit (Weld) | AWSC | AWSC | 4 | 0 | Empty | 2023-12-31 | 2024-01-31 | 2024-01-30 | 2024-01-31 | 2019-06-10 | 2019-06-30 | 180 | AWSC | AWSC | DF /B /77 | L3 Prepare of Permit (Weld) | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059753 | FLMR DFC - Repl of gratings EL +47000 | DFC - Replacement of gratings EL +47000 |  |  | 0 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /C /86/47000 - GRATINGS | DFC - Replacement of gratings EL +47000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059753 | FLMR DFC - Repl of gratings EL +47000 | DFC - Replacement of gratings EL +47000 |  |  | 2 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /C /86/47000 - GRATINGS | DFC - Replacement of gratings EL +47000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059753 | FLMR DFC - Repl of gratings EL +47000 | DFC - Replacement of gratings EL +47000 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /C /86/47000 - GRATINGS | DFC - Replacement of gratings EL +47000 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059753 | FLMR DFC - Repl of gratings EL +47000 | DFC - Replacement of gratings EL +47000 |  |  | 8 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /C /86/47000 - GRATINGS | DFC - Replacement of gratings EL +47000 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400307844 | 1Y SEAWATER FILTER PKG MAINT-DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-02-02 | 2024-03-09 | 20 |  |  | DF /G /51/DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307844 | 1Y SEAWATER FILTER PKG MAINT-DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-02 | 2024-03-09 | 30 |  |  | DF /G /51/DFGA-A-5357 | SEAWATER FILTER PKG MAINT-DFGA-A-5357 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 20 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 24 | 10 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-17 | 2024-07-20 | 2024-10-30 | 2024-12-31 | 30 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 5 | 6 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-20 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 40 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 2 | 2 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-21 | 2024-07-22 | 2024-10-30 | 2024-12-31 | 50 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-22 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 60 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 12 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-23 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 70 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-24 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 80 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 5 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-25 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 90 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-26 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 100 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-26 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 110 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-27 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 120 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284231 | PSV Calibration - DFBA-PSV-35355 | Scaffolding | AWSC | AWSC | 10 | 4 | W29-W30 | 2024-07-16 | 2024-07-28 | 2024-07-27 | 2024-07-28 | 2024-10-30 | 2024-12-31 | 130 | AWSC | AWSC | DF /B /53/DFBA-PSV-35355 | Scaffolding | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322305 | DFG-36-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 17 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235826 | 4Y 380V E-SWB MAINT DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235826 | 4Y 380V E-SWB MAINT DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 |  |  | 14 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235826 | 4Y 380V E-SWB MAINT DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235826 | 4Y 380V E-SWB MAINT DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFA-N-1812-07 | 380V E-SWB MAINT DFFA-N-1812-07 | Unknown
3 | Empty | WRO | PRODTECH | PRODTECH | 2300002498 | DK40 PAINT MATERIAL ORDER 2021 | 2300002498 20.09 BAG WASTE CHEM |  |  | 0 | 0 | Empty | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-02-04 | 2021-03-16 | 10 |  |  | DF /F | 2300002498 20.09 BAG WASTE CHEM | Unknown
3 | Empty | WRO | PRODTECH | PRODTECH | 2300002498 | DK40 PAINT MATERIAL ORDER 2021 | 2300002498 20.09 BAG WASTE CHEM |  |  | 0 | 0 | Empty | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-02-04 | 2021-03-16 | 20 |  |  | DF /F | 2300002498 20.09 BAG WASTE CHEM | Unknown
3 | Empty | WRO | PRODTECH | PRODTECH | 2300002498 | DK40 PAINT MATERIAL ORDER 2021 | 2300002498 20.09 BAG WASTE CHEM |  |  | 0 | 0 | Empty | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-02-04 | 2021-03-16 | 30 |  |  | DF /F | 2300002498 20.09 BAG WASTE CHEM | Unknown
3 | Empty | WRO | PRODTECH | PRODTECH | 2300002498 | DK40 PAINT MATERIAL ORDER 2021 | 2300002498 20.09 BAG WASTE CHEM |  |  | 0 | 0 | Empty | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-02-04 | 2021-03-16 | 40 |  |  | DF /F | 2300002498 20.09 BAG WASTE CHEM | Unknown
3 | Empty | WRO | PRODTECH | PRODTECH | 2300002498 | DK40 PAINT MATERIAL ORDER 2021 | 2300002498 20.09 BAG WASTE CHEM |  |  | 0 | 0 | Empty | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-02-04 | 2021-03-16 | 50 |  |  | DF /F | 2300002498 20.09 BAG WASTE CHEM | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400342710 | DFF-10-PHS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 343 | 0 | Empty | 2024-11-15 | 2025-01-14 | 2024-11-15 | 2025-01-13 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /10/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259291 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Oil for replacement | SECE | SECE | 2 | 0 | Empty | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-05-15 | 2023-06-14 | 10 | SECE | SECE | DF /C /27/DFCM-P-5015 | Oil for replacement | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259291 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Oil for replacement | SECE | SECE | 4 | 4 | Empty | 2024-08-14 | 2024-08-14 | 2024-07-29 | 2024-08-12 | 2023-05-15 | 2023-06-14 | 20 | SECE | SECE | DF /C /27/DFCM-P-5015 | Oil for replacement | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259291 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Oil for replacement | SECE | SECE | 4 | 0 | Empty | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-05-15 | 2023-06-14 | 30 | SECE | SECE | DF /C /27/DFCM-P-5015 | Oil for replacement | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400259291 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Oil for replacement | SECE | SECE | 1 | 0 | Empty | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-05-15 | 2023-06-14 | 40 | SECE | SECE | DF /C /27/DFCM-P-5015 | Oil for replacement | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259291 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Oil for replacement | SECE | SECE | 2 | 0 | Empty | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-05-15 | 2023-06-14 | 50 | SECE | SECE | DF /C /27/DFCM-P-5015 | Oil for replacement | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259291 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Oil for replacement | SECE | SECE | 0 | 0 | Empty | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-05-15 | 2023-06-14 | 60 | SECE | SECE | DF /C /27/DFCM-P-5015 | Oil for replacement | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036451 | it is pi next to the pressure transmitte | Replace needel valve |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-16 | 2020-11-14 | 10 |  |  | DF /F /37/DFFA-PIT-290437 | Replace needel valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036451 | it is pi next to the pressure transmitte | Replace needel valve |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-16 | 2020-11-14 | 20 |  |  | DF /F /37/DFFA-PIT-290437 | Replace needel valve | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235728 | 4Y 380V E-SWB MAINT DFCI-N-1812-0 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 3 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235728 | 4Y 380V E-SWB MAINT DFCI-N-1812-0 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 16 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-12 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235728 | 4Y 380V E-SWB MAINT DFCI-N-1812-0 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 3 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-12 | 2024-05-13 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235728 | 4Y 380V E-SWB MAINT DFCI-N-1812-0 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235728 | 4Y 380V E-SWB MAINT DFCI-N-1812-0 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 3 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-13 | 2024-05-14 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 2 | 2 | Empty | 2024-07-29 | 2024-07-29 | 2023-07-17 | 2023-07-30 | 2022-01-08 | 2022-01-28 | 10 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 2 | 2 | Empty | 2024-07-29 | 2024-07-29 | 2023-07-17 | 2023-07-30 | 2022-01-08 | 2022-01-28 | 20 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 24 | 12 | Empty | 2024-07-29 | 2024-07-29 | 2023-07-18 | 2023-07-30 | 2022-01-08 | 2022-01-28 | 30 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 5 | 18 | Empty | 2024-07-29 | 2024-07-29 | 2023-07-21 | 2023-07-30 | 2022-01-08 | 2022-01-28 | 40 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 50 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 12 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 60 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 70 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 5 | 12 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 80 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 4 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 90 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 4 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 100 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061165 | DFFA-PSV-410533 lækker til flare | Prod Assist (breaking containment) | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-08 | 2022-01-28 | 110 | PCNFSCH | PCNFSCH | DF /F /30/DFFA-PSV-410533 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 10 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 20 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 8 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-13 | 2022-12-18 | 2023-05-02 | 25 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 12 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2022-12-18 | 2023-05-02 | 30 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 3 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2022-12-18 | 2023-05-02 | 40 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 50 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078007 | Replace 4pcs. N2 cylinders DFGA-A-0462 | Additional materials - lost in warehouse |  |  | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2022-12-18 | 2023-05-02 | 60 |  |  | DF /G /01/DFGA-A-0462 | Additional materials - lost in warehouse | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053487 | Replace floodlights DFE | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-30 | 2022-03-29 | 10 |  |  | DF /E /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053487 | Replace floodlights DFE | Set personal isolation |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-30 | 2022-03-29 | 20 |  |  | DF /E /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053487 | Replace floodlights DFE | Set personal isolation |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 30 |  |  | DF /E /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053487 | Replace floodlights DFE | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 40 |  |  | DF /E /62 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100110792 | DFCC-PDIT-12018 defekt | Replace & calibrate DFCC-PDIT-12018 |  |  | 6 | 0 | Empty | 2024-05-23 | 2024-05-25 | 2024-05-23 | 2024-05-25 | 2024-05-23 | 2024-10-05 | 10 |  |  | DF /C /09/DFCC-PDIT-12018 | Replace & calibrate DFCC-PDIT-12018 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235828 | 4Y 380V E-SWB MAINT DFFA-N-1812-09 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFA-N-1812-09 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235828 | 4Y 380V E-SWB MAINT DFFA-N-1812-09 | ISOLATION BY PRODUCTION |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFA-N-1812-09 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235828 | 4Y 380V E-SWB MAINT DFFA-N-1812-09 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFA-N-1812-09 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235828 | 4Y 380V E-SWB MAINT DFFA-N-1812-09 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFA-N-1812-09 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 0 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-08-26 | 10 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 0 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-13 | 2023-04-13 | 2023-04-13 | 2023-08-26 | 20 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 2 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-13 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 30 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 2 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 40 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 2 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 50 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 4 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 60 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 4 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 70 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 0 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 80 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100087411 | SYNPR Replace 2"-DOS-500162-AB-T | Replace 2"-DOS-500162-AB-T |  |  | 2 | 0 | Empty | 2023-04-13 | 2023-04-14 | 2023-04-14 | 2023-04-14 | 2023-04-13 | 2023-08-26 | 90 |  |  | DF /G /28/DFG-2-DOS-050-0162-AB-T | Replace 2"-DOS-500162-AB-T | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-SCAF | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 24 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-18 | 2022-03-28 | 2022-11-23 | 10 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | PRODTECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 20 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | PRODTECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 30 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-RIGG | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 6 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-16 | 2022-03-28 | 2022-11-23 | 40 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-16 | 2022-03-28 | 2022-11-23 | 50 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 60 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-RIGG | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 6 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-09-13 | 2024-09-15 | 2022-03-28 | 2022-11-23 | 70 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | PRODTECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-09-13 | 2024-09-14 | 2022-03-28 | 2022-11-23 | 80 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-09-14 | 2024-09-15 | 2022-03-28 | 2022-11-23 | 90 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | PRODTECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 4 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-09-13 | 2024-09-14 | 2022-03-28 | 2022-11-23 | 100 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-SCAF | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 12 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-09-12 | 2024-09-14 | 2022-03-28 | 2022-11-23 | 110 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-09-14 | 2024-09-14 | 2022-03-28 | 2022-11-23 | 120 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 130 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 140 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
4 | DFX-WI | WGN | MTN-MECH | MTN-MECH | 2200008881 | PSV Exchange - DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-09-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 150 |  |  | DF /B /55/DFBA-PSV-35788 | DAN F Campaign 2024 batch 3 bolts ETC. | Unknown
3 | DFF-O20 | WDF | MTN-INST | PRODTECH | 2100023525 | SMAT:Changeout of SOV. | Isolation of hydraulic part of Choke | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2017-12-18 | 2018-03-18 | 10 | AWSC | AWSC | DF /F /10/DFFA-WCV-300420 | Isolation of hydraulic part of Choke | Unknown
3 | DFF-O20 | WDF | MTN-INST | MTN-MECH | 2100023525 | SMAT:Changeout of SOV. | Isolation of hydraulic part of Choke | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2017-12-18 | 2018-03-18 | 20 | AWSC | AWSC | DF /F /10/DFFA-WCV-300420 | Isolation of hydraulic part of Choke | Unknown
3 | DFF-O20 | WDF | MTN-INST | PRODTECH | 2100023525 | SMAT:Changeout of SOV. | Isolation of hydraulic part of Choke | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2017-12-18 | 2018-03-18 | 30 | AWSC | AWSC | DF /F /10/DFFA-WCV-300420 | Isolation of hydraulic part of Choke | Unknown
3 | DFF-O20 | WDF | MTN-INST | MTN-MECH | 2100023525 | SMAT:Changeout of SOV. | Isolation of hydraulic part of Choke | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2017-12-18 | 2018-03-18 | 40 | AWSC | AWSC | DF /F /10/DFFA-WCV-300420 | Isolation of hydraulic part of Choke | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400346577 | 1Y CHEM DISTR PANEL MAINT-DFFA-A-39709 | CHEM DISTR PANEL MAINT-DFFA-A-39709 |  |  | 16 | 0 | Empty | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-10-01 | 10 |  |  | DF /F /75/DFFA-A-39709 | CHEM DISTR PANEL MAINT-DFFA-A-39709 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053307 | Level transmitter change PVENT | Isolate Contact Level transmitter (float |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2021-08-28 | 2021-11-26 | 10 |  |  | DF /G /30/DFGA-LIT-410554 | Isolate Contact Level transmitter (float | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053307 | Level transmitter change PVENT | Isolate Contact Level transmitter (float |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2021-08-28 | 2021-11-26 | 20 |  |  | DF /G /30/DFGA-LIT-410554 | Isolate Contact Level transmitter (float | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053307 | Level transmitter change PVENT | Isolate Contact Level transmitter (float |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2021-08-28 | 2021-11-26 | 30 |  |  | DF /G /30/DFGA-LIT-410554 | Isolate Contact Level transmitter (float | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100042073 | Dan Temporary Chem. Injec. in poor state | Receive refurbished pump skid |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-09-08 | 2024-07-29 | 2024-07-30 | 2020-12-14 | 2021-01-23 | 10 |  |  | DF /B /75 | Receive refurbished pump skid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100042073 | Dan Temporary Chem. Injec. in poor state | Receive refurbished pump skid |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-09-08 | 2024-09-08 | 2024-09-08 | 2020-12-14 | 2021-01-23 | 20 |  |  | DF /B /75 | Receive refurbished pump skid | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400206509 | 1Y DFFA-FT-340558 PROD WATER - METERING | DFFA-FT-340558 PROD WATER - METERING | PCNFSCH | PCNFSCH | 7 | 10 | W25-W26 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2022-07-06 | 2022-08-22 | 10 | PCNFSCH | PCNFSCH | DF /F /27/DFFA-FT-340558 | DFFA-FT-340558 PROD WATER - METERING | Unknown
D | NOSD | WPM | MTN-INST | MTN-RIGG | 2400206509 | 1Y DFFA-FT-340558 PROD WATER - METERING | DFFA-FT-340558 PROD WATER - METERING | PCNFSCH | PCNFSCH | 6 | 14 | W25-W26 | 2024-06-30 | 2024-06-30 | 2022-11-22 | 2022-12-24 | 2022-07-06 | 2022-08-22 | 20 | PCNFSCH | PCNFSCH | DF /F /27/DFFA-FT-340558 | DFFA-FT-340558 PROD WATER - METERING | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400206509 | 1Y DFFA-FT-340558 PROD WATER - METERING | DFFA-FT-340558 PROD WATER - METERING | PCNFSCH | PCNFSCH | 0 | 0 | W25-W26 | 2024-06-30 | 2024-06-30 | 2022-12-05 | 2022-12-08 | 2022-07-06 | 2022-08-22 | 30 | PCNFSCH | PCNFSCH | DF /F /27/DFFA-FT-340558 | DFFA-FT-340558 PROD WATER - METERING | Unknown
D | NOSD | WPM | MTN-INST | MTN-SCAF | 2400206509 | 1Y DFFA-FT-340558 PROD WATER - METERING | DFFA-FT-340558 PROD WATER - METERING | PCNFSCH | PCNFSCH | 8 | 3 | W25-W26 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2022-07-06 | 2022-08-22 | 40 | PCNFSCH | PCNFSCH | DF /F /27/DFFA-FT-340558 | DFFA-FT-340558 PROD WATER - METERING | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 12 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2016-12-23 | 2017-01-12 | 10 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | PRODTECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 2 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2016-12-23 | 2017-01-12 | 20 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-INST | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 2 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2016-12-23 | 2017-01-12 | 30 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-RIGG | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 2 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 40 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 0 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 50 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-RIGG | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 2 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 60 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 0 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2016-12-23 | 2017-01-12 | 70 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-INST | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 1 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2016-12-23 | 2017-01-12 | 80 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-INST | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 1 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2016-12-23 | 2017-01-12 | 90 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 0 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2016-12-23 | 2017-01-12 | 100 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | PRODTECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 1 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2016-12-23 | 2017-01-12 | 110 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 0 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2016-12-23 | 2017-01-12 | 120 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | DFF-TSEP | WDF | MTN-MECH | MTN-MECH | 2100025040 | Replacement of DFFA-PDCV-500606 | Repalcement of PDCV-500606 | AWSC | AWSC | 0 | 0 | Possible Iso issue | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2016-12-23 | 2017-01-12 | 130 | AWSC | AWSC | DF /F /27/DFFA-PDCV-500606 | Repalcement of PDCV-500606 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023939 | CMAT:Change strainer DFFA-FT-5905 | L3 deisolate system |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2019-01-05 | 2019-04-05 | 10 |  |  | DF /F /07/DFFA-FT-5905 | L3 deisolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023939 | CMAT:Change strainer DFFA-FT-5905 | L3 deisolate system |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2019-01-05 | 2019-04-05 | 20 |  |  | DF /F /07/DFFA-FT-5905 | L3 deisolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023939 | CMAT:Change strainer DFFA-FT-5905 | L3 deisolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2019-01-05 | 2019-04-05 | 30 |  |  | DF /F /07/DFFA-FT-5905 | L3 deisolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023939 | CMAT:Change strainer DFFA-FT-5905 | L3 deisolate system |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2019-01-05 | 2019-04-05 | 40 |  |  | DF /F /07/DFFA-FT-5905 | L3 deisolate system | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 24 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-05 | 2024-12-07 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-06 | 2024-12-07 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 12 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-09 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-07 | 2024-12-07 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-09 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
A | DFF-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284277 | PSV Calibration - DFFA-PSV-440026 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-09 | 2024-12-08 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /F /31/DFFA-PSV-440026 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100086861 | DFC HVAC Service Void motor RPM faulty | Troubleshooting/Replacement on speed ele |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-21 | 2023-09-03 | 10 |  |  | DF /C /09/DFCC-SE-12015B | Troubleshooting/Replacement on speed ele | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086861 | DFC HVAC Service Void motor RPM faulty | Troubleshooting/Replacement on speed ele |  |  | 2.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-21 | 2023-09-03 | 20 |  |  | DF /C /09/DFCC-SE-12015B | Troubleshooting/Replacement on speed ele | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100086861 | DFC HVAC Service Void motor RPM faulty | Troubleshooting/Replacement on speed ele |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-04-21 | 2023-09-03 | 30 |  |  | DF /C /09/DFCC-SE-12015B | Troubleshooting/Replacement on speed ele | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100106449 | Leakages on Promac | Replace/repair flowmeter |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2024-03-14 | 2024-07-27 | 10 |  |  | DF /C /85/DFCM-A-1027 | Replace/repair flowmeter | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106449 | Leakages on Promac | Replace/repair flowmeter |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-27 | 2024-03-14 | 2024-07-27 | 20 |  |  | DF /C /85/DFCM-A-1027 | Replace/repair flowmeter | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106449 | Leakages on Promac | Replace/repair flowmeter |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-27 | 2024-08-28 | 2024-03-14 | 2024-07-27 | 30 |  |  | DF /C /85/DFCM-A-1027 | Replace/repair flowmeter | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106449 | Leakages on Promac | Replace/repair flowmeter |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-28 | 2024-08-29 | 2024-03-14 | 2024-07-27 | 40 |  |  | DF /C /85/DFCM-A-1027 | Replace/repair flowmeter | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | PRODTECH | 2400330120 | 40KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 0 | W35-W36 | 2024-06-10 | 2024-06-20 | 2024-06-10 | 2024-06-11 | 2024-04-10 | 2024-06-29 | 10 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | MTN-INST | 2400330120 | 40KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 18 | 0 | W35-W36 | 2024-06-10 | 2024-06-20 | 2024-06-11 | 2024-06-15 | 2024-04-10 | 2024-06-29 | 20 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | MTN-MECH | 2400330120 | 40KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 10 | 0 | W35-W36 | 2024-06-10 | 2024-06-20 | 2024-06-15 | 2024-06-18 | 2024-04-10 | 2024-06-29 | 30 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | MTN-ELEC | 2400330120 | 40KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 0 | W35-W36 | 2024-06-10 | 2024-06-20 | 2024-06-18 | 2024-06-19 | 2024-04-10 | 2024-06-29 | 40 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | PRODTECH | 2400330120 | 40KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 0 | W35-W36 | 2024-06-10 | 2024-06-20 | 2024-06-19 | 2024-06-20 | 2024-04-10 | 2024-06-29 | 50 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 2 | 8 | W3-4 | 2024-09-22 | 2024-09-27 | 2021-01-18 | 2024-01-01 | 2019-03-07 | 2019-03-27 | 10 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROUS | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 2 | 8 | W3-4 | 2024-09-22 | 2024-09-27 | 2021-01-18 | 2024-01-01 | 2019-03-07 | 2019-03-27 | 20 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 4 | 0 | W3-4 | 2024-09-22 | 2024-09-27 | 2022-01-12 | 2024-01-01 | 2019-03-07 | 2019-03-27 | 30 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 0 | 23 | W3-4 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2019-03-07 | 2019-03-27 | 40 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 2 | 6 | W3-4 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2019-03-07 | 2019-03-27 | 50 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 4 | 0 | W3-4 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2019-03-07 | 2019-03-27 | 60 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100024107 | Calibrate DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | PCNFSCH | PCNFSCH | 24 | 0 | W3-4 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-27 | 2019-03-07 | 2019-03-27 | 70 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-WE-390611B | L3 Calibrate DFGA-WE-390611B | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100086073 | DFG/78 Lightning on crane | Replace light bulbs - See not and attach |  |  | 2 | 0 | W25-W26 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2026-02-07 | 10 |  |  | DF /G /78/DFGA-A-6140 | Replace light bulbs - See not and attach | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086073 | DFG/78 Lightning on crane | Replace light bulbs - See not and attach |  |  | 4 | 0 | W25-W26 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-08-22 | 2026-02-07 | 20 |  |  | DF /G /78/DFGA-A-6140 | Replace light bulbs - See not and attach | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100086073 | DFG/78 Lightning on crane | Replace light bulbs - See not and attach |  |  | 12 | 0 | W25-W26 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-08-22 | 2026-02-07 | 30 |  |  | DF /G /78/DFGA-A-6140 | Replace light bulbs - See not and attach | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | PRODTECH | 2400259289 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-05-21 | 2023-06-20 | 10 | SECE | SECE | DF /G /70/DFGA-XE-5742 | ISOLATION BY PRODUCTION | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | MTN-ELEC | 2400259289 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-05-21 | 2023-06-20 | 20 | SECE | SECE | DF /G /70/DFGA-XE-5742 | ISOLATION BY PRODUCTION | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | MTN-INST | 2400259289 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-05-21 | 2023-06-20 | 30 | SECE | SECE | DF /G /70/DFGA-XE-5742 | ISOLATION BY PRODUCTION | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | PRODTECH | 2400259289 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-05-21 | 2023-06-20 | 40 | SECE | SECE | DF /G /70/DFGA-XE-5742 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-20 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-22 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 8 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-23 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-23 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 51 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-22 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-22 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-23 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-23 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284270 | PSV Calibration - DFFA-PSV-410027 | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-25 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /30/DFFA-PSV-410027 | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235719 | 4Y 380V E-SWB MAINT DFCC-N-1813-05 | 380V E-SWB MAINT DFCC-N-1813-05 | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-05 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235719 | 4Y 380V E-SWB MAINT DFCC-N-1813-05 | 380V E-SWB MAINT DFCC-N-1813-05 | AWSCSECE | AWSCSECE | 6 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-05 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235719 | 4Y 380V E-SWB MAINT DFCC-N-1813-05 | 380V E-SWB MAINT DFCC-N-1813-05 | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-05 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235719 | 4Y 380V E-SWB MAINT DFCC-N-1813-05 | 380V E-SWB MAINT DFCC-N-1813-05 | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-05 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100022777 | ANOP Reestablish missing supports DFA we | L3 Reestablish missing supports DFA well |  |  | 18 | 0 | No materials ordered | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2024-03-17 | 2019-06-13 | 2019-11-10 | 10 |  |  | DF /A /10 | L3 Reestablish missing supports DFA well | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100022777 | ANOP Reestablish missing supports DFA we | L3 Reestablish missing supports DFA well |  |  | 8 | 0 | No materials ordered | 2024-03-15 | 2024-03-19 | 2024-03-17 | 2024-03-19 | 2019-06-13 | 2019-11-10 | 20 |  |  | DF /A /10 | L3 Reestablish missing supports DFA well | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024985 | PVI LG-340037 Lower leg blocked to leve | Lower leg blocked to level glass | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2020-01-12 | 2020-04-11 | 10 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100024985 | PVI LG-340037 Lower leg blocked to leve | Lower leg blocked to level glass | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2020-01-12 | 2020-04-11 | 20 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024985 | PVI LG-340037 Lower leg blocked to leve | Lower leg blocked to level glass | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-03 | 2020-01-12 | 2020-04-11 | 30 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024985 | PVI LG-340037 Lower leg blocked to leve | Lower leg blocked to level glass | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-03 | 2024-08-05 | 2020-01-12 | 2020-04-11 | 40 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100024985 | PVI LG-340037 Lower leg blocked to leve | Lower leg blocked to level glass | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2020-01-12 | 2020-04-11 | 50 | AWSC | AWSC | DF /F /20/DFFA-LG-340037 | Lower leg blocked to level glass | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284250 | PSV Exchange - DFCI-PSV-57149 | Documentation & CNF WO | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57149 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284250 | PSV Exchange - DFCI-PSV-57149 | Documentation & CNF WO | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57149 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284250 | PSV Exchange - DFCI-PSV-57149 | Documentation & CNF WO | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-31 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57149 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284250 | PSV Exchange - DFCI-PSV-57149 | Documentation & CNF WO | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57149 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284250 | PSV Exchange - DFCI-PSV-57149 | Documentation & CNF WO | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57149 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284250 | PSV Exchange - DFCI-PSV-57149 | Documentation & CNF WO | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57149 | Documentation & CNF WO | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235577 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-05 | 380V N-SWB-INSP-DFCC-N-1803-05 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-05-01 | 380V N-SWB-INSP-DFCC-N-1803-05 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235577 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-05 | 380V N-SWB-INSP-DFCC-N-1803-05 | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-05-01 | 380V N-SWB-INSP-DFCC-N-1803-05 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235577 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-05 | 380V N-SWB-INSP-DFCC-N-1803-05 | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-05-01 | 380V N-SWB-INSP-DFCC-N-1803-05 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235577 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-05 | 380V N-SWB-INSP-DFCC-N-1803-05 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-05-01 | 380V N-SWB-INSP-DFCC-N-1803-05 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329498 | 6M SDV LUB/MAINT LPSEP - DFC | SDV LUB/INSP LPSEP - DFC |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-26 | 2024-06-11 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP LPSEP - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 36 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-08-01 | 2020-12-16 | 2021-03-16 | 10 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2020-12-16 | 2021-03-16 | 20 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-02 | 2020-12-16 | 2021-03-16 | 30 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-03 | 2020-12-16 | 2021-03-16 | 40 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-03 | 2020-12-16 | 2021-03-16 | 50 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-03 | 2020-12-16 | 2021-03-16 | 60 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-03 | 2020-12-16 | 2021-03-16 | 70 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100041654 | DFC-HCV-030140 Intern læk | Scaffold removal |  |  | 24 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-05 | 2020-12-16 | 2021-03-16 | 80 |  |  | DF /C /01/DFCM-HCV-030140 | Scaffold removal | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100080523 | DFA-14 WCV Well Head PB | Isolate push button |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-18 | 2023-07-03 | 10 |  |  | DF /A /10/DFAA-WCV-30338 | Isolate push button | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100080523 | DFA-14 WCV Well Head PB | Isolate push button |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-18 | 2023-07-03 | 20 |  |  | DF /A /10/DFAA-WCV-30338 | Isolate push button | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100080523 | DFA-14 WCV Well Head PB | Isolate push button |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-18 | 2023-07-03 | 30 |  |  | DF /A /10/DFAA-WCV-30338 | Isolate push button | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100080523 | DFA-14 WCV Well Head PB | Isolate push button |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-18 | 2023-07-03 | 40 |  |  | DF /A /10/DFAA-WCV-30338 | Isolate push button | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100080523 | DFA-14 WCV Well Head PB | Isolate push button |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-18 | 2023-07-03 | 50 |  |  | DF /A /10/DFAA-WCV-30338 | Isolate push button | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100077173 | FLMR DFF - Replace Handrail ST012 EL. 27 | DFF - Replace Handrail ST012 EL. 27.000 |  |  | 0 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-12-31 | 10 |  |  | DF /F /86/27500 - HANDRAILS | DFF - Replace Handrail ST012 EL. 27.000 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-ROPE | 2100077173 | FLMR DFF - Replace Handrail ST012 EL. 27 | DFF - Replace Handrail ST012 EL. 27.000 |  |  | 3 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-12-31 | 20 |  |  | DF /F /86/27500 - HANDRAILS | DFF - Replace Handrail ST012 EL. 27.000 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-ROPE | 2100077173 | FLMR DFF - Replace Handrail ST012 EL. 27 | DFF - Replace Handrail ST012 EL. 27.000 |  |  | 10 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-04-30 | 2023-05-03 | 2023-04-30 | 2023-12-31 | 30 |  |  | DF /F /86/27500 - HANDRAILS | DFF - Replace Handrail ST012 EL. 27.000 | Unknown
3 | DFC-FUEL | WDF | MTN-INST | PRODTECH | 2100087408 | Replace SDBB valve and piping PT-57136 | Isolate Pressure transmitter |  |  | 0.1000000000000000055511151231 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 10 |  |  | DF /C /70/DFCI-PT-57136 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100087408 | Replace SDBB valve and piping PT-57136 | Isolate Pressure transmitter |  |  | 0.5 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 20 |  |  | DF /C /70/DFCI-PT-57136 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-MECH | 2100087408 | Replace SDBB valve and piping PT-57136 | Isolate Pressure transmitter |  |  | 0.1000000000000000055511151231 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 30 |  |  | DF /C /70/DFCI-PT-57136 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-PIPF | 2100087408 | Replace SDBB valve and piping PT-57136 | Isolate Pressure transmitter |  |  | 2.5 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 40 |  |  | DF /C /70/DFCI-PT-57136 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100087408 | Replace SDBB valve and piping PT-57136 | Isolate Pressure transmitter |  |  | 1 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 50 |  |  | DF /C /70/DFCI-PT-57136 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | PRODTECH | 2100087408 | Replace SDBB valve and piping PT-57136 | Isolate Pressure transmitter |  |  | 0.1000000000000000055511151231 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 60 |  |  | DF /C /70/DFCI-PT-57136 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025438 | Replace actuator DFBA-XCV-30401 | L3 Isolation of DFBA-XCV-30401 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2018-05-19 | 2018-08-17 | 10 |  |  | DF /B /10/DFBA-XCV-30401 | L3 Isolation of DFBA-XCV-30401 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025438 | Replace actuator DFBA-XCV-30401 | L3 Isolation of DFBA-XCV-30401 |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2018-05-19 | 2018-08-17 | 20 |  |  | DF /B /10/DFBA-XCV-30401 | L3 Isolation of DFBA-XCV-30401 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025438 | Replace actuator DFBA-XCV-30401 | L3 Isolation of DFBA-XCV-30401 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2018-05-19 | 2018-08-17 | 30 |  |  | DF /B /10/DFBA-XCV-30401 | L3 Isolation of DFBA-XCV-30401 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322240 | DFB-28-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 44 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024275 | ANOSR Weld cracks DFC Crane Pedestal Lad | L3 Permit & Preparation |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2024-03-15 | 2024-04-01 | 2024-03-15 | 2024-03-15 | 2019-07-24 | 2019-10-22 | 10 |  |  | DF /C /86/CRANE-PEDESTAL | L3 Permit & Preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024275 | ANOSR Weld cracks DFC Crane Pedestal Lad | L3 Permit & Preparation |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2024-03-15 | 2024-04-01 | 2024-03-15 | 2024-03-16 | 2019-07-24 | 2019-10-22 | 11 |  |  | DF /C /86/CRANE-PEDESTAL | L3 Permit & Preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024275 | ANOSR Weld cracks DFC Crane Pedestal Lad | L3 Permit & Preparation |  |  | 90 | 0 | Empty | 2024-03-15 | 2024-04-01 | 2024-03-16 | 2024-03-27 | 2019-07-24 | 2019-10-22 | 12 |  |  | DF /C /86/CRANE-PEDESTAL | L3 Permit & Preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024275 | ANOSR Weld cracks DFC Crane Pedestal Lad | L3 Permit & Preparation |  |  | 8 | 0 | Empty | 2024-03-15 | 2024-04-01 | 2024-03-27 | 2024-03-28 | 2019-07-24 | 2019-10-22 | 20 |  |  | DF /C /86/CRANE-PEDESTAL | L3 Permit & Preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024275 | ANOSR Weld cracks DFC Crane Pedestal Lad | L3 Permit & Preparation |  |  | 30 | 0 | Empty | 2024-03-15 | 2024-04-01 | 2024-03-28 | 2024-04-01 | 2019-07-24 | 2019-10-22 | 30 |  |  | DF /C /86/CRANE-PEDESTAL | L3 Permit & Preparation | Unknown
3 | NOSD | WDF | MTN-MECH | INP-SITE | 2100024275 | ANOSR Weld cracks DFC Crane Pedestal Lad | L3 Permit & Preparation |  |  | 2 | 0 | Empty | 2024-03-15 | 2024-04-01 | 2024-03-15 | 2024-03-15 | 2019-07-24 | 2019-10-22 | 40 |  |  | DF /C /86/CRANE-PEDESTAL | L3 Permit & Preparation | Unknown
2 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100106535 | DFC/78 Hydraulic start pressure drop | Isolate/deisolate crane | SCH | SCH | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-16 | 2024-02-01 | 2024-03-17 | 10 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate/deisolate crane | Unknown
2 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100106535 | DFC/78 Hydraulic start pressure drop | Isolate/deisolate crane | SCH | SCH | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-16 | 2024-07-19 | 2024-02-01 | 2024-03-17 | 20 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate/deisolate crane | Unknown
2 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100106535 | DFC/78 Hydraulic start pressure drop | Isolate/deisolate crane | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-16 | 2024-07-16 | 2024-02-01 | 2024-03-17 | 30 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate/deisolate crane | Unknown
2 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100022398 | ANOP Change wire support on dead end DFB | Change wire support on dead end DFB |  |  | 4 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-08-29 | 2019-09-03 | 10 |  |  | DF /B /12 | Change wire support on dead end DFB | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100093124 | Change DFF-PBS-4203 | Isolate pushbutton control |  |  | 1 | 0 | W35-W36 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-07-30 | 2023-12-12 | 10 |  |  | DF /F /31/DFFA-PM-4203 | Isolate pushbutton control | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093124 | Change DFF-PBS-4203 | Isolate pushbutton control |  |  | 1 | 0 | W35-W36 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-07-30 | 2023-12-12 | 20 |  |  | DF /F /31/DFFA-PM-4203 | Isolate pushbutton control | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093124 | Change DFF-PBS-4203 | Isolate pushbutton control |  |  | 6 | 0 | W35-W36 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-07-30 | 2023-12-12 | 30 |  |  | DF /F /31/DFFA-PM-4203 | Isolate pushbutton control | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093124 | Change DFF-PBS-4203 | Isolate pushbutton control |  |  | 1 | 0 | W35-W36 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-30 | 2023-12-12 | 40 |  |  | DF /F /31/DFFA-PM-4203 | Isolate pushbutton control | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100093124 | Change DFF-PBS-4203 | Isolate pushbutton control |  |  | 1 | 0 | W35-W36 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-30 | 2023-12-12 | 50 |  |  | DF /F /31/DFFA-PM-4203 | Isolate pushbutton control | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315819 | 1Y EMERGENCY LIGHT ROOF TEST- DFF | PERSONAL ISOLATION | SCHSECE | SCHSECE | 1 | 4 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-17 | 2024-03-26 | 2024-04-25 | 10 | SCHSECE | SCHSECE | DF /F /62/EMERGENCY-LIGHTING-ROOF | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315819 | 1Y EMERGENCY LIGHT ROOF TEST- DFF | PERSONAL ISOLATION | SCHSECE | SCHSECE | 12 | 62 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-20 | 2024-03-26 | 2024-04-25 | 20 | SCHSECE | SCHSECE | DF /F /62/EMERGENCY-LIGHTING-ROOF | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400315819 | 1Y EMERGENCY LIGHT ROOF TEST- DFF | PERSONAL ISOLATION | SCHSECE | SCHSECE | 1 | 4 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-03-26 | 2024-04-25 | 30 | SCHSECE | SCHSECE | DF /F /62/EMERGENCY-LIGHTING-ROOF | PERSONAL ISOLATION | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 10 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 20 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-05-18 | 2024-07-02 | 30 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-05-18 | 2024-07-02 | 40 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-05-18 | 2024-07-02 | 50 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-05-18 | 2024-07-02 | 60 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-05-18 | 2024-07-02 | 70 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-05-18 | 2024-07-02 | 80 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-05-18 | 2024-07-02 | 90 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112901 | DFFA-PSV-393405 leaking from tell tail h | PSV393405 leaking from tell tail hole |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-05-18 | 2024-07-02 | 100 |  |  | DF /F /75/DFFA-PSV-393405 | PSV393405 leaking from tell tail hole | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291614 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-12-02 | 2023-12-12 | 1 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291614 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-12-02 | 2023-12-12 | 9 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291614 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-25 | 2023-12-02 | 2023-12-12 | 10 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400291614 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-25 | 2024-09-28 | 2023-12-02 | 2023-12-12 | 12 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291614 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-12-02 | 2023-12-12 | 14 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322296 | DFF-50-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 10 | 3.5 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /50/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WGN | MTN-ELEC | MTN-MECH | 2200003185 | SMAT:DFG Replace SOV on ESDV-390002 | Test and documentation |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2018-05-05 | 2020-04-24 | 10 |  |  | DF /G /75/DFGA-ESDV-390002 | Test and documentation | Unknown
4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200003185 | SMAT:DFG Replace SOV on ESDV-390002 | Test and documentation |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2018-05-05 | 2020-04-24 | 20 |  |  | DF /G /75/DFGA-ESDV-390002 | Test and documentation | Unknown
4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200003185 | SMAT:DFG Replace SOV on ESDV-390002 | Test and documentation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2018-05-05 | 2020-04-24 | 30 |  |  | DF /G /75/DFGA-ESDV-390002 | Test and documentation | Unknown
4 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200003185 | SMAT:DFG Replace SOV on ESDV-390002 | Test and documentation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2018-05-05 | 2020-04-24 | 40 |  |  | DF /G /75/DFGA-ESDV-390002 | Test and documentation | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104197 | DFEZ-HR-0311 1 1/2'' HOSE PIN HOLE | Deisolate and check for leaks | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-12-23 | 2024-02-06 | 10 | SECE | SECE | DF /E /01/DFEZ-HR-0311 | Deisolate and check for leaks | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104197 | DFEZ-HR-0311 1 1/2'' HOSE PIN HOLE | Deisolate and check for leaks | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-12-23 | 2024-02-06 | 20 | SECE | SECE | DF /E /01/DFEZ-HR-0311 | Deisolate and check for leaks | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104197 | DFEZ-HR-0311 1 1/2'' HOSE PIN HOLE | Deisolate and check for leaks | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-12-23 | 2024-02-06 | 30 | SECE | SECE | DF /E /01/DFEZ-HR-0311 | Deisolate and check for leaks | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269351 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL DE-ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-07-18 | 2023-08-17 | 10 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269351 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL DE-ISOLATION |  |  | 9 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2023-07-18 | 2023-08-17 | 20 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269351 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL DE-ISOLATION |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2023-07-18 | 2023-08-17 | 30 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269351 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL DE-ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2023-07-18 | 2023-08-17 | 40 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269351 | 1Y HVAC SUPP/EXH SANDBL CONT DFFA-A-1266 | PERSONAL DE-ISOLATION |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-07-18 | 2023-08-17 | 50 |  |  | DF /F /09/DFFA-A-1266 | PERSONAL DE-ISOLATION | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 10 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 20 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 0.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 30 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 2.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 40 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 2.5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 50 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-19 | 2023-08-01 | 60 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-19 | 2023-08-01 | 70 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084666 | Load cell for DFF T-3940 Hypochlor | Empty tank and isolate |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-19 | 2023-08-01 | 80 |  |  | DF /F /75/DFFA-WE-390671A | Empty tank and isolate | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400269322 | 6M PED CRANE CHECK VENDOR-DFFA-A-6102 | Oilsampling Main and Whip Winch | AWSC | AWSC | 38 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-18 | 2024-09-23 | 2023-10-13 | 2023-10-29 | 20 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Oilsampling Main and Whip Winch | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400269322 | 6M PED CRANE CHECK VENDOR-DFFA-A-6102 | Oilsampling Main and Whip Winch | AWSC | AWSC | 6 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-10-13 | 2023-10-29 | 30 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Oilsampling Main and Whip Winch | Unknown
B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400269322 | 6M PED CRANE CHECK VENDOR-DFFA-A-6102 | Oilsampling Main and Whip Winch | AWSC | AWSC | 6 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-10-13 | 2023-10-29 | 40 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Oilsampling Main and Whip Winch | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100082295 | Instrumentluft lækage til XCV-040672 | Troubleshoot on air leak on PCV for DFGA |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-16 | 2023-07-29 | 10 |  |  | DF /G /01/DFGA-XCV-040672 | Troubleshoot on air leak on PCV for DFGA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 2 | 17 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 16 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-12 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-12 | 2024-05-12 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 2 | 1 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235720 | 4Y 380V E-SWB MAINT DFCI-N-1812 | additional materials | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-13 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 60 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100023538 | Rustne bæringer for HVAC ved gen. rum | Rustne bæringer for HVAC ved gen. rum |  |  | 0 | 0 | Empty | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2018-04-01 | 2019-03-27 | 10 |  |  | DF /C /09 | Rustne bæringer for HVAC ved gen. rum | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100023538 | Rustne bæringer for HVAC ved gen. rum | Rustne bæringer for HVAC ved gen. rum |  |  | 12 | 0 | Empty | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2023-11-02 | 2018-04-01 | 2019-03-27 | 170 |  |  | DF /C /09 | Rustne bæringer for HVAC ved gen. rum | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235300 | 6M CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | SCH | SCH | 5 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-03-01 | 2023-03-17 | 10 | SCH | SCH | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235300 | 6M CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | SCH | SCH | 2 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-03-01 | 2023-03-17 | 20 | SCH | SCH | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100079752 | DFG: Wire to exhaust temperature sensor | Isolate/de-isolate crane |  |  | 2 | 2 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2023-01-26 | 2023-06-10 | 10 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100079752 | DFG: Wire to exhaust temperature sensor | Isolate/de-isolate crane |  |  | 4 | 20 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2023-01-26 | 2023-06-10 | 20 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100079752 | DFG: Wire to exhaust temperature sensor | Isolate/de-isolate crane |  |  | 15 | 10 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-03 | 2023-01-26 | 2023-06-10 | 30 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100079752 | DFG: Wire to exhaust temperature sensor | Isolate/de-isolate crane |  |  | 1 | 1 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2023-01-26 | 2023-06-10 | 40 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate crane | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-16 | 2024-07-17 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 24 | 8 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-17 | 2024-07-19 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 5 | 4.5 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-18 | 2024-07-19 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 5 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-19 | 2024-07-20 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 4 | 3 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-19 | 2024-07-20 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 12 | 15 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-17 | 2024-09-19 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 5 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 2 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 10 | 0 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2024-10-19 | 2024-12-31 | 130 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284279 | PSV Calibration - DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 0 | 2 | W29-W30 | 2024-07-16 | 2024-09-19 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 140 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354109 | DFFA-PSV-354109 Offshore from WS Måde | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-MECH | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 14 | 22 | Empty | 2024-08-07 | 2024-08-22 | 2023-09-11 | 2023-09-15 | 2023-09-15 | 2024-01-28 | 5 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 1 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-07 | 2024-08-07 | 2023-09-15 | 2024-01-28 | 10 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 26 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-07 | 2024-08-07 | 2023-09-15 | 2024-01-28 | 20 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 26 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-07 | 2024-08-08 | 2023-09-15 | 2024-01-28 | 30 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 26 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-08 | 2024-08-10 | 2023-09-15 | 2024-01-28 | 40 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 60 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-08 | 2024-08-12 | 2023-09-15 | 2024-01-28 | 50 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 50 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-12 | 2024-08-15 | 2023-09-15 | 2024-01-28 | 60 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 40 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-15 | 2024-08-19 | 2023-09-15 | 2024-01-28 | 70 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 16 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-19 | 2024-08-20 | 2023-09-15 | 2024-01-28 | 80 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 30 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-19 | 2024-08-22 | 2023-09-15 | 2024-01-28 | 90 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 0 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-07 | 2024-08-07 | 2023-09-15 | 2024-01-28 | 100 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100096123 | DFFW/78 Replace luffing winch | Order luff wire from WO 2400241874 | PCNF | PCNF | 0 | 0 | Empty | 2024-08-07 | 2024-08-22 | 2024-08-07 | 2024-08-07 | 2023-09-15 | 2024-01-28 | 110 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Order luff wire from WO 2400241874 | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300003106 | DK40 - Replaced by 2300003650 | Round trip equipment |  |  | 1 | 0 | Empty | 2024-02-01 | 2024-02-03 | 2024-02-01 | 2024-02-01 | 2022-01-19 | 2022-11-15 | 10 |  |  | DF /C /84 | Round trip equipment | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300003106 | DK40 - Replaced by 2300003650 | Round trip equipment |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-03 | 2024-02-01 | 2024-02-01 | 2022-01-19 | 2022-11-15 | 20 |  |  | DF /C /84 | Round trip equipment | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300003106 | DK40 - Replaced by 2300003650 | Round trip equipment |  |  | 6 | 0 | Empty | 2024-02-01 | 2024-02-03 | 2024-02-01 | 2024-02-03 | 2022-01-19 | 2022-11-15 | 30 |  |  | DF /C /84 | Round trip equipment | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300003106 | DK40 - Replaced by 2300003650 | Round trip equipment |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2022-01-19 | 2022-11-15 | 40 |  |  | DF /C /84 | Round trip equipment | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300003106 | DK40 - Replaced by 2300003650 | Round trip equipment |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2022-01-19 | 2022-11-15 | 50 |  |  | DF /C /84 | Round trip equipment | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300003106 | DK40 - Replaced by 2300003650 | Round trip equipment |  |  | 0 | 0 | Empty | 2024-02-01 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2022-01-19 | 2022-11-15 | 60 |  |  | DF /C /84 | Round trip equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057871 | DFCM-FT-5211 Corrosion lid sealing face | DFCM-FT-5211 Corrosion lid sealing face |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-11-12 | 2021-12-22 | 10 |  |  | DF /C /51/DFCM-FT-5211 | DFCM-FT-5211 Corrosion lid sealing face | Unknown
4 | NOSD | WRO | MTN-INST | MTN-INST | 2300003275 | DO NOT USE - Replaced by 2300007087 | DK40 - CONSUMABLE MTN - INST |  |  | 0 | 0 | Empty | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2024-01-30 | 2022-03-30 | 2023-01-24 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - INST | Unknown
4 | Empty | WRO | MTN-TELE | MTN-TELE | 2300006310 | DK40 - REplaced by 2300007433 | DK40 - CONSUMABLE MTN - TELECOM |  |  | 0 | 0 | Empty | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2026-07-22 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - TELECOM | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100072242 | ANOCR External corrosion DFB-2-GI-08-900 | Wash down, surface prep and coatings |  |  | 0 | 0 | Empty | 2023-01-25 | 2023-02-01 | 2023-01-25 | 2023-01-25 | 2023-01-25 | 2025-07-13 | 10 |  |  | DF /B /74/DFB-2-GI-008-9004-AA-U | Wash down, surface prep and coatings | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100072242 | ANOCR External corrosion DFB-2-GI-08-900 | Wash down, surface prep and coatings |  |  | 12 | 0 | Empty | 2023-01-25 | 2023-02-01 | 2023-01-25 | 2023-01-25 | 2023-01-25 | 2025-07-13 | 20 |  |  | DF /B /74/DFB-2-GI-008-9004-AA-U | Wash down, surface prep and coatings | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100072242 | ANOCR External corrosion DFB-2-GI-08-900 | Wash down, surface prep and coatings |  |  | 6 | 0 | Empty | 2023-01-25 | 2023-02-01 | 2023-01-25 | 2023-01-26 | 2023-01-25 | 2025-07-13 | 30 |  |  | DF /B /74/DFB-2-GI-008-9004-AA-U | Wash down, surface prep and coatings | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100072242 | ANOCR External corrosion DFB-2-GI-08-900 | Wash down, surface prep and coatings |  |  | 114 | 0 | Empty | 2023-01-25 | 2023-02-01 | 2023-01-26 | 2023-02-01 | 2023-01-25 | 2025-07-13 | 40 |  |  | DF /B /74/DFB-2-GI-008-9004-AA-U | Wash down, surface prep and coatings | Unknown
4 | Empty | WDF | MTN-PAIN | MTN-PAIN | 2100072242 | ANOCR External corrosion DFB-2-GI-08-900 | Wash down, surface prep and coatings |  |  | 12 | 0 | Empty | 2023-01-25 | 2023-02-01 | 2023-02-01 | 2023-02-01 | 2023-01-25 | 2025-07-13 | 50 |  |  | DF /B /74/DFB-2-GI-008-9004-AA-U | Wash down, surface prep and coatings | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 1 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 25 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 27 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-12 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284227 | PSV Calibration - DFAA-PSV-392313 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /A /75/DFAA-PSV-392313 | Remove PSV and Install blinds | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235641 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L03 | 400V N-SWB INSP-DFCI-N-1802-L03 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L03A | 400V N-SWB INSP-DFCI-N-1802-L03 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235641 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L03 | 400V N-SWB INSP-DFCI-N-1802-L03 | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L03A | 400V N-SWB INSP-DFCI-N-1802-L03 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235641 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L03 | 400V N-SWB INSP-DFCI-N-1802-L03 | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L03A | 400V N-SWB INSP-DFCI-N-1802-L03 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235641 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L03 | 400V N-SWB INSP-DFCI-N-1802-L03 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L03A | 400V N-SWB INSP-DFCI-N-1802-L03 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322254 | DFC-27-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 20 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036457 | DFF-02 C/I still Chem inj flow DFFA-FCV- | Replace DFFA-FCV-390053 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-09-05 | 2020-12-04 | 10 |  |  | DF /F /75/DFFA-FCV-390053 | Replace DFFA-FCV-390053 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036457 | DFF-02 C/I still Chem inj flow DFFA-FCV- | Replace DFFA-FCV-390053 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2020-09-05 | 2020-12-04 | 20 |  |  | DF /F /75/DFFA-FCV-390053 | Replace DFFA-FCV-390053 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036457 | DFF-02 C/I still Chem inj flow DFFA-FCV- | Replace DFFA-FCV-390053 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2020-09-05 | 2020-12-04 | 30 |  |  | DF /F /75/DFFA-FCV-390053 | Replace DFFA-FCV-390053 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346565 | 1Y MV DELUGE SKD, SMOKE TEST-DFFA-A-0302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-21 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /F /01/DFFA-A-0302 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346565 | 1Y MV DELUGE SKD, SMOKE TEST-DFFA-A-0302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 14 | 0 | W33-W34 | 2024-08-14 | 2024-08-21 | 2024-08-15 | 2024-08-18 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /F /01/DFFA-A-0302 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346565 | 1Y MV DELUGE SKD, SMOKE TEST-DFFA-A-0302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 0 | W33-W34 | 2024-08-14 | 2024-08-21 | 2024-08-18 | 2024-08-19 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /F /01/DFFA-A-0302 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346565 | 1Y MV DELUGE SKD, SMOKE TEST-DFFA-A-0302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 0 | W33-W34 | 2024-08-14 | 2024-08-21 | 2024-08-19 | 2024-08-20 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /F /01/DFFA-A-0302 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400346565 | 1Y MV DELUGE SKD, SMOKE TEST-DFFA-A-0302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-21 | 2024-08-20 | 2024-08-21 | 2024-08-31 | 2024-09-30 | 50 | AWSCSECE | AWSCSECE | DF /F /01/DFFA-A-0302 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346565 | 1Y MV DELUGE SKD, SMOKE TEST-DFFA-A-0302 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-31 | 2024-09-30 | 60 | AWSCSECE | AWSCSECE | DF /F /01/DFFA-A-0302 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-17 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 24 | 6 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-17 | 2024-07-20 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 5 | 5 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 2 | 2 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 12 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 5 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-25 | 2024-07-26 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-26 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284260 | PSV Calibration - DFFA-PSV-330010 | Rigging assist (remove) & Scaff | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /F /10/DFFA-PSV-330010 | Rigging assist (remove) & Scaff | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298231 | 3M SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-12-30 | 2024-01-10 | 10 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400298231 | 3M SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2023-12-30 | 2024-01-10 | 12 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344339 | 2Y 110V UPS.SYST BATT & CHAR F.TEST-DFC | 110V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 16 | 0 | Empty | 2024-08-13 | 2024-08-16 | 2024-08-13 | 2024-08-16 | 2024-08-13 | 2024-09-28 | 10 | AWSCSECE | AWSCSECE | DF /C /06/DFCI-A-1905 | 110V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344339 | 2Y 110V UPS.SYST BATT & CHAR F.TEST-DFC | 110V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-08-13 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-13 | 2024-09-28 | 20 | AWSCSECE | AWSCSECE | DF /C /06/DFCI-A-1905 | 110V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344339 | 2Y 110V UPS.SYST BATT & CHAR F.TEST-DFC | 110V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-08-13 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-13 | 2024-09-28 | 30 | AWSCSECE | AWSCSECE | DF /C /06/DFCI-A-1905 | 110V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344339 | 2Y 110V UPS.SYST BATT & CHAR F.TEST-DFC | 110V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-08-13 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-08-13 | 2024-09-28 | 40 | AWSCSECE | AWSCSECE | DF /C /06/DFCI-A-1905 | 110V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105408 | DFE04 Flowline Temp faulty indication | Check transmitter / apply thermal paste |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-02-18 | 2024-07-02 | 10 |  |  | DF /E /10/DFEZ-TE-30016 | Check transmitter / apply thermal paste | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-ROPE | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 0 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-18 | 2024-09-18 | 2023-01-07 | 2025-06-25 | 10 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-ROPE | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 0 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-18 | 2024-09-18 | 2023-01-07 | 2025-06-25 | 20 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-18 | 2024-09-19 | 2023-01-07 | 2025-06-25 | 30 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 5 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-19 | 2024-09-20 | 2023-01-07 | 2025-06-25 | 40 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 5 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-20 | 2024-09-21 | 2023-01-07 | 2025-06-25 | 50 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-21 | 2024-09-22 | 2023-01-07 | 2025-06-25 | 60 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-07 | 2025-06-25 | 70 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100071369 | DFC HCV-33015 internally leaking. | Isolate HCV |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-01-07 | 2025-06-25 | 80 |  |  | DF /C /10/DFCI-HCV-33015-U | Isolate HCV | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100065950 | No indication on openlimit switch | Overide BDV valve / Inhibit ZSO |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-04-05 | 2022-05-15 | 10 |  |  | DF /G /31/DFGA-BDV-570041 | Overide BDV valve / Inhibit ZSO | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100065950 | No indication on openlimit switch | Overide BDV valve / Inhibit ZSO |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-04-05 | 2022-05-15 | 20 |  |  | DF /G /31/DFGA-BDV-570041 | Overide BDV valve / Inhibit ZSO | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100065950 | No indication on openlimit switch | Overide BDV valve / Inhibit ZSO |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-04-05 | 2022-05-15 | 30 |  |  | DF /G /31/DFGA-BDV-570041 | Overide BDV valve / Inhibit ZSO | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100065950 | No indication on openlimit switch | Overide BDV valve / Inhibit ZSO |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-04-05 | 2022-05-15 | 40 |  |  | DF /G /31/DFGA-BDV-570041 | Overide BDV valve / Inhibit ZSO | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100065950 | No indication on openlimit switch | Overide BDV valve / Inhibit ZSO |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-04-05 | 2022-05-15 | 50 |  |  | DF /G /31/DFGA-BDV-570041 | Overide BDV valve / Inhibit ZSO | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 10 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 20 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 30 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 40 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-05-11 | 50 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 60 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 70 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 80 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-28 | 2024-05-11 | 90 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-12-28 | 2024-05-11 | 100 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100101809 | LG-340033 need to be cleaned. | Install rigging equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-12-28 | 2024-05-11 | 110 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Install rigging equipment | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106932 | DFF HP-sep sandtrap XCV indication fault | XCV limit switches investigation |  |  | 2 | 10 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-22 | 2024-08-04 | 10 |  |  | DF /F /20/DFFA-XCV-340512 | XCV limit switches investigation | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344051 | 6M ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 |  |  | 1 | 0 | Empty | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2024-09-19 | 10 |  |  | DF /G /75/DFGA-A-3956 | ANTI-FOAM PUMPS MAINT-DFGA-P-3956/7 | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2026-01-01 | 2026-01-02 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2020-08-25 | 2020-08-25 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 42 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2026-01-02 | 2026-01-04 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 4 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2020-08-25 | 2020-08-25 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 9 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 4 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 22 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2026-01-01 | 2026-01-02 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002919 | DFB-Insulation assists FORCE 9554. | L3 Prepare Permit Scaff | PCNF | PCNF | 0 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-04 | 2026-01-03 | 2026-01-03 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /B /27/DFB-6-PHS-038-0864-AB-U | L3 Prepare Permit Scaff | Unknown
C | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400291643 | 1Y SW BOOSTER PUMP MAINT DFAA-P-3506/07 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2023-10-29 | 2023-12-04 | 10 |  |  | DF /A /54/DFAA-P-3506 | ISOLATION BY PRODUCTION | Unknown
C | DFE-3551 | WPM | MTN-MECH | MTN-ELEC | 2400291643 | 1Y SW BOOSTER PUMP MAINT DFAA-P-3506/07 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | Empty | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2023-10-29 | 2023-12-04 | 20 |  |  | DF /A /54/DFAA-P-3506 | ISOLATION BY PRODUCTION | Unknown
C | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400291643 | 1Y SW BOOSTER PUMP MAINT DFAA-P-3506/07 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | Empty | 2024-07-30 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-10-29 | 2023-12-04 | 30 |  |  | DF /A /54/DFAA-P-3506 | ISOLATION BY PRODUCTION | Unknown
C | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400291643 | 1Y SW BOOSTER PUMP MAINT DFAA-P-3506/07 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-10-29 | 2023-12-04 | 40 |  |  | DF /A /54/DFAA-P-3506 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 10 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 20 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 30 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 40 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 50 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 60 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 70 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 80 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 90 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 100 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-24 | 2023-04-08 | 110 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-TELE | 2100075976 | XCV test seperator cant operate | Isolate pneumatic and controls | PCNF | PCNF | 0 | 3 | W35-W36 | 2024-08-26 | 2024-08-26 | 2023-03-04 | 2023-09-01 | 2022-11-24 | 2023-04-08 | 120 | PCNF | PCNF | DF /F /27/DFFA-XCV-500623 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057176 | Rusten sov SHUTDOWN VALVE CLOSED DRAIN | Replace and adjust Control panel (SDV) |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-11-12 | 2022-02-10 | 10 |  |  | DF /C /70/DFCM-ESDV-57170 | Replace and adjust Control panel (SDV) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057176 | Rusten sov SHUTDOWN VALVE CLOSED DRAIN | Replace and adjust Control panel (SDV) |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-11-12 | 2022-02-10 | 20 |  |  | DF /C /70/DFCM-ESDV-57170 | Replace and adjust Control panel (SDV) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057176 | Rusten sov SHUTDOWN VALVE CLOSED DRAIN | Replace and adjust Control panel (SDV) |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-11-12 | 2022-02-10 | 30 |  |  | DF /C /70/DFCM-ESDV-57170 | Replace and adjust Control panel (SDV) | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-ROPE | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 0 | 117 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-17 | 2024-01-17 | 2023-09-15 | 2023-11-28 | 10 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | VEN-INSP | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 0 | 0 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-17 | 2024-01-17 | 2023-09-15 | 2023-11-28 | 20 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-ROPE | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 0 | 0 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-17 | 2024-01-17 | 2023-09-15 | 2023-11-28 | 30 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-SCAF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 25 | 34 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-17 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 40 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-SCAF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 15 | 15 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-17 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 50 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-SCAF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 60 | 69 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-21 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 60 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-RIGG | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 15 | 56 | Empty | 2024-01-17 | 2024-02-24 | 2024-01-30 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 70 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-PIPF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 6 | 6 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-19 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 80 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-PIPF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 6 | 6 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-19 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 90 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-PIPF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 15 | 15 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-19 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 100 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-PIPF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 6 | 14 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-19 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 110 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-PIPF | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 20 | 20 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-19 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 120 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-PAIN | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 20 | 31 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-19 | 2024-02-23 | 2023-09-15 | 2023-11-28 | 130 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | DFF-3580 | WDF | MTN-ROPE | MTN-LAGG | 2100095654 | FFSPR: LOPC From 2" weldolet - WI system | Rigging of 10" and 18" | PCNF | PCNF | 0 | 16 | Empty | 2024-01-17 | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2023-09-15 | 2023-11-28 | 140 | PCNF | PCNF | DF /F /54/DFF-18-WI-035-9144-BB-U | Rigging of 10" and 18" | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029878 | FE03 er internal leak på MCV i hydraulik | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | No Vendor booking | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2020-03-23 | 2020-05-02 | 10 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029878 | FE03 er internal leak på MCV i hydraulik | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | No Vendor booking | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2020-03-23 | 2020-05-02 | 20 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029878 | FE03 er internal leak på MCV i hydraulik | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | No Vendor booking | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2020-03-23 | 2020-05-02 | 25 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029878 | FE03 er internal leak på MCV i hydraulik | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | No Vendor booking | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2020-03-23 | 2020-05-02 | 30 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Drawer to be sent onshore for repair | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044255 | DFC LEVEL 1. DFC-XCV-50399 ZSC/ZSO FEJL | Vendor to Troubleshoot on XCV-50399 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-03 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50399 | Vendor to Troubleshoot on XCV-50399 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044255 | DFC LEVEL 1. DFC-XCV-50399 ZSC/ZSO FEJL | Vendor to Troubleshoot on XCV-50399 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50399 | Vendor to Troubleshoot on XCV-50399 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-29 | 2024-03-12 | 10 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-29 | 2024-03-12 | 20 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 30 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 40 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 50 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 60 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 70 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 75 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098439 | DFC XCV-34305 Valve is Stuck | Remove actuator, check if function is ok |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-29 | 2024-03-12 | 80 |  |  | DF /C /27/DFCM-XCV-34305 | Remove actuator, check if function is ok | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003188 | CMAT:DFGA ESDV-500713 Udskift def manom | Safing af ESDV - hydraulik systemet |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-03 | 2023-04-04 | 2018-03-08 | 2019-03-03 | 10 |  |  | DF /G /28/DFGA-ESDV-500713 | Safing af ESDV - hydraulik systemet | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003188 | CMAT:DFGA ESDV-500713 Udskift def manom | Safing af ESDV - hydraulik systemet |  |  | 2 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-05 | 2018-03-08 | 2019-03-03 | 20 |  |  | DF /G /28/DFGA-ESDV-500713 | Safing af ESDV - hydraulik systemet | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003188 | CMAT:DFGA ESDV-500713 Udskift def manom | Safing af ESDV - hydraulik systemet |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-06 | 2018-03-08 | 2019-03-03 | 30 |  |  | DF /G /28/DFGA-ESDV-500713 | Safing af ESDV - hydraulik systemet | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322286 | DFF-28-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308998 | 1Y HVAC SUPPLY CHECK DFCC-A-1201 | RETURN TO OPERATION | SECE | SECE | 1 | 0 | Empty | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2024-08-25 | 2024-02-18 | 2024-03-19 | 10 | SECE | SECE | DF /C /09/DFCC-A-1201 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308998 | 1Y HVAC SUPPLY CHECK DFCC-A-1201 | RETURN TO OPERATION | SECE | SECE | 12 | 0 | Empty | 2024-08-25 | 2024-08-28 | 2024-08-25 | 2024-08-28 | 2024-02-18 | 2024-03-19 | 20 | SECE | SECE | DF /C /09/DFCC-A-1201 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308998 | 1Y HVAC SUPPLY CHECK DFCC-A-1201 | RETURN TO OPERATION | SECE | SECE | 1 | 0 | Empty | 2024-08-25 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-02-18 | 2024-03-19 | 30 | SECE | SECE | DF /C /09/DFCC-A-1201 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308998 | 1Y HVAC SUPPLY CHECK DFCC-A-1201 | RETURN TO OPERATION | SECE | SECE | 2 | 0 | Empty | 2024-08-25 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-02-18 | 2024-03-19 | 40 | SECE | SECE | DF /C /09/DFCC-A-1201 | RETURN TO OPERATION | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098772 | DFCXM5221 cannot be reset | Isolate Circuit |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-09-26 | 2023-11-10 | 20 |  |  | DF /C /51/DFCM-XM-5221 | Isolate Circuit | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098772 | DFCXM5221 cannot be reset | Isolate Circuit |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-09-26 | 2023-11-10 | 30 |  |  | DF /C /51/DFCM-XM-5221 | Isolate Circuit | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098772 | DFCXM5221 cannot be reset | Isolate Circuit |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-09-26 | 2023-11-10 | 40 |  |  | DF /C /51/DFCM-XM-5221 | Isolate Circuit | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100098772 | DFCXM5221 cannot be reset | Isolate Circuit |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-09-26 | 2023-11-10 | 50 |  |  | DF /C /51/DFCM-XM-5221 | Isolate Circuit | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291654 | 6M BRIDGE TROLLEY 10T - DFFZ-X-6150 | assist | AWSC | AWSC | 10 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-17 | 2023-11-17 | 2023-12-12 | 10 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | assist | Unknown
D | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400291654 | 6M BRIDGE TROLLEY 10T - DFFZ-X-6150 | assist | AWSC | AWSC | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2023-11-17 | 2023-12-12 | 20 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | assist | Unknown
D | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400291654 | 6M BRIDGE TROLLEY 10T - DFFZ-X-6150 | assist | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-11-17 | 2023-12-12 | 30 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | assist | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-21 | 2024-06-24 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-24 | 2024-06-25 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 10 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-26 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-27 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-28 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-28 | 2024-06-29 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284285 | PSV Calibration - DFFA-PSV-570011 | Rigging assist (remove) | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /F /70/DFFA-PSV-570011 | Rigging assist (remove) | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235658 | 4Y 400V N-SWB MAINT DFCI-N-1802-R09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R09A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235658 | 4Y 400V N-SWB MAINT DFCI-N-1802-R09 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R09A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235658 | 4Y 400V N-SWB MAINT DFCI-N-1802-R09 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R09A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235658 | 4Y 400V N-SWB MAINT DFCI-N-1802-R09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R09A | ISOLATION ELECTRICAL | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-ROPE | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 3 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-05 | 2024-10-05 | 2022-01-02 | 2022-06-01 | 5 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 10 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-05 | 2024-10-07 | 2022-01-02 | 2022-06-01 | 10 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 3 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-07 | 2024-10-08 | 2022-01-02 | 2022-06-01 | 20 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 5 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-08 | 2024-10-09 | 2022-01-02 | 2022-06-01 | 30 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 5 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-09 | 2024-10-10 | 2022-01-02 | 2022-06-01 | 40 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 5 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-09 | 2024-10-10 | 2022-01-02 | 2022-06-01 | 50 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 5 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-10 | 2024-10-11 | 2022-01-02 | 2022-06-01 | 60 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 3 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-12 | 2024-10-12 | 2022-01-02 | 2022-06-01 | 70 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 8 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-12 | 2024-10-14 | 2022-01-02 | 2022-06-01 | 80 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100056694 | Internal leak DFFA-HCV-340070 | Remove old HCV-340070 |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-14 | 2024-10-05 | 2024-10-05 | 2022-01-02 | 2022-06-01 | 90 |  |  | DF /F /32/DFFA-HCV-340070 | Remove old HCV-340070 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044952 | Hydraulic In-filter Unit corroded | Prod deisolate w function/leak test |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2021-04-20 | 2021-09-17 | 10 |  |  | DF /A /07/DFAA-A-5902 | Prod deisolate w function/leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044952 | Hydraulic In-filter Unit corroded | Prod deisolate w function/leak test |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-31 | 2021-04-20 | 2021-09-17 | 20 |  |  | DF /A /07/DFAA-A-5902 | Prod deisolate w function/leak test | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044952 | Hydraulic In-filter Unit corroded | Prod deisolate w function/leak test |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-02 | 2021-04-20 | 2021-09-17 | 30 |  |  | DF /A /07/DFAA-A-5902 | Prod deisolate w function/leak test | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044952 | Hydraulic In-filter Unit corroded | Prod deisolate w function/leak test |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2021-04-20 | 2021-09-17 | 40 |  |  | DF /A /07/DFAA-A-5902 | Prod deisolate w function/leak test | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044952 | Hydraulic In-filter Unit corroded | Prod deisolate w function/leak test |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2021-04-20 | 2021-09-17 | 50 |  |  | DF /A /07/DFAA-A-5902 | Prod deisolate w function/leak test | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 3 | Empty | 2024-01-08 | 2024-01-13 | 2020-08-19 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2020-10-30 | 2020-11-10 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 32.20000000000000284217094303 | 70.5 | Empty | 2024-01-08 | 2024-01-13 | 2020-08-20 | 2020-12-13 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 8 | 5 | Empty | 2024-01-08 | 2024-01-13 | 2020-10-21 | 2020-11-10 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 8 | 20 | Empty | 2024-01-08 | 2024-01-13 | 2020-11-26 | 2020-12-27 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 26.800000000000000710542735752 | 22 | Empty | 2024-01-08 | 2024-01-13 | 2020-12-03 | 2020-12-13 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 90 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 100 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-ELEC | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2019-09-12 | 2019-12-11 | 110 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 120 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-ELEC | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-13 | 2019-09-12 | 2019-12-11 | 130 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2019-09-12 | 2019-12-11 | 140 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002914 | DFF-Insulation assists FORCE 13521 | BUILD SCAFFOLDING | PCNF | PCNF | 6 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 150 | PCNF | PCNF | DF /F /55/DFF-2-WI-035-7203-GF-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039225 | Firewater HCV-030165 internal leaking | Production isolation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-10-30 | 2021-01-28 | 10 |  |  | DF /F /01/DFFA-HCV-030165 | Production isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100039225 | Firewater HCV-030165 internal leaking | Production isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2020-10-30 | 2021-01-28 | 20 |  |  | DF /F /01/DFFA-HCV-030165 | Production isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039225 | Firewater HCV-030165 internal leaking | Production isolation |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2020-10-30 | 2021-01-28 | 30 |  |  | DF /F /01/DFFA-HCV-030165 | Production isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100039225 | Firewater HCV-030165 internal leaking | Production isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2020-10-30 | 2021-01-28 | 40 |  |  | DF /F /01/DFFA-HCV-030165 | Production isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-ROPE | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 6 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-03 | 2018-11-05 | 2018-11-25 | 9 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 3 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2018-11-05 | 2018-11-25 | 10 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 1 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-02 | 2018-11-05 | 2018-11-25 | 20 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 10 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-05 | 2018-11-05 | 2018-11-25 | 30 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 1 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2018-11-05 | 2018-11-25 | 40 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 3 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2018-11-05 | 2018-11-25 | 50 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100023656 | Replace valve handles DFEZ-P-5012 | Isolation | AWSCSCH | AWSCSCH | 0 | 0 | IOP | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2018-11-05 | 2018-11-25 | 60 | AWSCSCH | AWSCSCH | DF /E /28/DFEZ-P-5012 | Isolation | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400321277 | 3M HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | HPU FOR ESDV CTRL MAINT - DFBA-A-5903 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-02 | 2024-05-12 | 10 |  |  | DF /B /07/DFBA-A-5903 | HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2022-07-08 | 2022-08-22 | 10 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-16 | 2022-07-08 | 2022-08-22 | 20 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-17 | 2022-07-08 | 2022-08-22 | 30 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-18 | 2022-07-08 | 2022-08-22 | 40 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2022-07-08 | 2022-08-22 | 50 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2022-07-08 | 2022-08-22 | 60 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-20 | 2022-07-08 | 2022-08-22 | 70 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-20 | 2022-07-08 | 2022-08-22 | 80 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-21 | 2022-07-08 | 2022-08-22 | 90 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2022-07-08 | 2022-08-22 | 100 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071365 | DFE-BDV-33060 test manifold malfunction | Demount old BDV | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2022-07-08 | 2022-08-22 | 110 | SECE | SECE | DF /E /10/DFEZ-BDV-33060 | Demount old BDV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053334 | Corroded sealing face on drip ring | Production Isolation/Permit |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-08-29 | 2021-11-27 | 10 |  |  | DF /G /30/DFGA-PSV-570011B | Production Isolation/Permit | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053334 | Corroded sealing face on drip ring | Production Isolation/Permit |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-08-29 | 2021-11-27 | 20 |  |  | DF /G /30/DFGA-PSV-570011B | Production Isolation/Permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053334 | Corroded sealing face on drip ring | Production Isolation/Permit |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-08-29 | 2021-11-27 | 30 |  |  | DF /G /30/DFGA-PSV-570011B | Production Isolation/Permit | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053334 | Corroded sealing face on drip ring | Production Isolation/Permit |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2021-08-29 | 2021-11-27 | 40 |  |  | DF /G /30/DFGA-PSV-570011B | Production Isolation/Permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053334 | Corroded sealing face on drip ring | Production Isolation/Permit |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2021-08-29 | 2021-11-27 | 50 |  |  | DF /G /30/DFGA-PSV-570011B | Production Isolation/Permit | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 10 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 20 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-16 | 2022-01-17 | 2022-01-16 | 2022-06-15 | 20 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 35 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-17 | 2022-01-18 | 2022-01-16 | 2022-06-15 | 30 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 35 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-18 | 2022-01-19 | 2022-01-16 | 2022-06-15 | 40 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 35 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-19 | 2022-01-20 | 2022-01-16 | 2022-06-15 | 50 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 35 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-20 | 2022-01-22 | 2022-01-16 | 2022-06-15 | 60 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057554 | SYNSR-667006 DFB - Replacement Handrail | DFB - Replacement Handrail EL. 37.300 |  |  | 10 | 0 | Empty | 2022-01-16 | 2022-01-22 | 2022-01-22 | 2022-01-22 | 2022-01-16 | 2022-06-15 | 70 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 37.300 | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003142 | CMAT:DFB FB19 Replacment of PI-303319 ( | L3 Safing of PI-303319 |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2018-04-07 | 2018-07-06 | 10 |  |  | DF /B /10 | L3 Safing of PI-303319 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003142 | CMAT:DFB FB19 Replacment of PI-303319 ( | L3 Safing of PI-303319 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2018-04-07 | 2018-07-06 | 20 |  |  | DF /B /10 | L3 Safing of PI-303319 | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003142 | CMAT:DFB FB19 Replacment of PI-303319 ( | L3 Safing of PI-303319 |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2018-04-07 | 2018-07-06 | 30 |  |  | DF /B /10 | L3 Safing of PI-303319 | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100088901 | DFF-GD-124701 defekt | Install scaffolding | SCHSECE | SCHSECE | 0.5 | 0.5 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-05-20 | 2023-10-02 | 10 | SCHSECE | SCHSECE | DF /F /03/DFFA-GD-124701 | Install scaffolding | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100088901 | DFF-GD-124701 defekt | Install scaffolding | SCHSECE | SCHSECE | 2 | 2 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-05-20 | 2023-10-02 | 20 | SCHSECE | SCHSECE | DF /F /03/DFFA-GD-124701 | Install scaffolding | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100088901 | DFF-GD-124701 defekt | Install scaffolding | SCHSECE | SCHSECE | 0.5 | 0.5 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-05-20 | 2023-10-02 | 30 | SCHSECE | SCHSECE | DF /F /03/DFFA-GD-124701 | Install scaffolding | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100088901 | DFF-GD-124701 defekt | Install scaffolding | SCHSECE | SCHSECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-05-20 | 2023-10-02 | 40 | SCHSECE | SCHSECE | DF /F /03/DFFA-GD-124701 | Install scaffolding | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-SCAF | 2100088901 | DFF-GD-124701 defekt | Install scaffolding | SCHSECE | SCHSECE | 12 | 12 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2023-05-20 | 2023-10-02 | 50 | SCHSECE | SCHSECE | DF /F /03/DFFA-GD-124701 | Install scaffolding | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322285 | DFF-27-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300005495 | REPLACED BY 2300006310 | DK40 - CONSUMABLE MTN - TELECOM |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2023-10-24 | 2026-04-11 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - TELECOM | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080795 | DFG N2 FCV very unstable | Troubleshoot FCV-080574 in general Leaks |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-02-20 | 2023-07-05 | 10 |  |  | DF /G /74/DFGA-FCV-080574 | Troubleshoot FCV-080574 in general Leaks | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080795 | DFG N2 FCV very unstable | Troubleshoot FCV-080574 in general Leaks |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-02-20 | 2023-07-05 | 20 |  |  | DF /G /74/DFGA-FCV-080574 | Troubleshoot FCV-080574 in general Leaks | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080795 | DFG N2 FCV very unstable | Troubleshoot FCV-080574 in general Leaks |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-02-20 | 2023-07-05 | 30 |  |  | DF /G /74/DFGA-FCV-080574 | Troubleshoot FCV-080574 in general Leaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 29 | 7.5 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-04 | 2022-04-04 | 2021-07-01 | 2021-07-06 | 10 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 5 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-04 | 2022-04-04 | 2021-07-01 | 2021-07-06 | 20 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 6 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-04 | 2022-04-05 | 2021-07-01 | 2021-07-06 | 30 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 4 | 2.5 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-05 | 2022-04-05 | 2021-07-01 | 2021-07-06 | 40 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 23 | 11 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-05 | 2022-04-05 | 2021-07-01 | 2021-07-06 | 50 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 3 | 13 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-05 | 2022-04-05 | 2021-07-01 | 2021-07-06 | 60 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 2 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-05 | 2022-04-05 | 2021-07-01 | 2021-07-06 | 70 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 2 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-05 | 2022-04-05 | 2021-07-01 | 2021-07-06 | 80 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 11 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-05 | 2022-04-06 | 2021-07-01 | 2021-07-06 | 90 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 13 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-06 | 2022-04-08 | 2021-07-01 | 2021-07-06 | 100 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 2 | 0 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2021-07-01 | 2021-07-06 | 110 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300003081 | DAF OCG NPT order-TRPBCOM Telecom Reinst | Clean-up & housekeeping | PCNF | PCNF | 11 | 2 | Empty | 2022-04-04 | 2022-04-08 | 2022-04-08 | 2022-04-08 | 2021-07-01 | 2021-07-06 | 120 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
4 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003809 | Change to Total ANAC Lub. Oil sampling | Change to Total ANAC Lub. Oil sampling |  |  | 120 | 0 | Empty | 2020-07-01 | 2020-07-21 | 2020-07-01 | 2020-07-21 | 2020-07-01 | 2020-11-28 | 10 |  |  | DF /F /9 | Change to Total ANAC Lub. Oil sampling | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400221593 | 6M HPU FOR MFF1 SCRAMS MAINT - FP-3001 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2023-01-10 | 2023-01-26 | 10 |  |  | DF /F /07/DFFA-FP-3001 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400221593 | 6M HPU FOR MFF1 SCRAMS MAINT - FP-3001 | DE-ISOLATION BY PRODUCTION |  |  | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2023-01-10 | 2023-01-26 | 20 |  |  | DF /F /07/DFFA-FP-3001 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400221593 | 6M HPU FOR MFF1 SCRAMS MAINT - FP-3001 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2023-01-10 | 2023-01-26 | 30 |  |  | DF /F /07/DFFA-FP-3001 | DE-ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322306 | DFG-01-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087257 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /G /05/DFGA-LP-1852-19 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087257 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /G /05/DFGA-LP-1852-19 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087257 | Battery fault on emergency light | Isolate and prove dead. |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /G /05/DFGA-LP-1852-19 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087257 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /G /05/DFGA-LP-1852-19 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 32 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-08-02 | 2014-12-10 | 2015-01-19 | 10 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-03 | 2014-12-10 | 2015-01-19 | 20 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-04 | 2014-12-10 | 2015-01-19 | 30 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-05 | 2014-12-10 | 2015-01-19 | 40 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-05 | 2024-08-06 | 2014-12-10 | 2015-01-19 | 50 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-06 | 2024-08-07 | 2014-12-10 | 2015-01-19 | 60 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2014-12-10 | 2015-01-19 | 70 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2014-12-10 | 2015-01-19 | 80 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024149 | Replace DFGZ-HCV-030109 (20" F.W. LV-153 | Rig up for replacing DFGZ-HCV-030109 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-29 | 2014-12-10 | 2015-01-19 | 90 |  |  | DF /G /01/DFGZ-HCV-030109 | Rig up for replacing DFGZ-HCV-030109 | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400268265 | 4Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-23 | 2024-07-29 | 2024-07-29 | 2023-05-17 | 2023-08-13 | 10 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268265 | 4Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 56 | 0 | W29-W30 | 2024-07-29 | 2024-08-23 | 2024-07-29 | 2024-08-12 | 2023-05-17 | 2023-08-13 | 20 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400268265 | 4Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 40 | 0 | W29-W30 | 2024-07-29 | 2024-08-23 | 2024-08-12 | 2024-08-22 | 2023-05-17 | 2023-08-13 | 30 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400268265 | 4Y CHEMICAL INJECTION PUMPS MAINT-DAN FB | CHEMICAL INJECTION PUMPS MAINT-DAN FB |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2023-05-17 | 2023-08-13 | 40 |  |  | DF /B /75/DFBA-A-3913 | CHEMICAL INJECTION PUMPS MAINT-DAN FB | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 2 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-06 | 2023-11-06 | 2021-05-11 | 2021-10-08 | 10 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 1 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-06 | 2023-11-06 | 2021-05-11 | 2021-10-08 | 15 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 3 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-06 | 2023-11-07 | 2021-05-11 | 2021-10-08 | 20 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 1 | 3 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-07 | 2023-11-07 | 2021-05-11 | 2021-10-08 | 30 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 4 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-06 | 2023-11-07 | 2021-05-11 | 2021-10-08 | 35 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 2 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-07 | 2023-11-08 | 2021-05-11 | 2021-10-08 | 40 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 3 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-08 | 2023-11-09 | 2021-05-11 | 2021-10-08 | 50 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045844 | DFFA-HRF-0326 Håndtag på HCV | Deisolate upstream the HCV for | PCNF | PCNF | 1 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2021-05-11 | 2021-10-08 | 60 | PCNF | PCNF | DF /F /01/DFFA-HRF-0326 | Deisolate upstream the HCV for | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322314 | DFG-01-WF-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 172 | 0 | Empty | 2024-10-30 | 2024-11-29 | 2024-10-30 | 2024-11-28 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067914 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Small Step-up scaffold erection |  |  | 24 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2022-05-22 | 2022-08-20 | 10 |  |  | DF /F /54/DFFA-EP-3804 | Small Step-up scaffold erection | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067914 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Small Step-up scaffold erection |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2022-05-22 | 2022-08-20 | 20 |  |  | DF /F /54/DFFA-EP-3804 | Small Step-up scaffold erection | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067914 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Small Step-up scaffold erection |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2022-05-22 | 2022-08-20 | 30 |  |  | DF /F /54/DFFA-EP-3804 | Small Step-up scaffold erection | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067914 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Small Step-up scaffold erection |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-05 | 2022-05-22 | 2022-08-20 | 40 |  |  | DF /F /54/DFFA-EP-3804 | Small Step-up scaffold erection | Unknown
3 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067914 | 2" BY-PASS hcv FOR dAB b wi LAUNCER | Small Step-up scaffold erection |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2022-05-22 | 2022-08-20 | 50 |  |  | DF /F /54/DFFA-EP-3804 | Small Step-up scaffold erection | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400329529 | 1Y DFB FLAREGAS MEAS - METERING | DFB FLAREGAS MEAS - METERING | AWSC | AWSC | 12 | 0 | Empty | 2024-05-13 | 2024-05-18 | 2024-05-13 | 2024-05-15 | 2024-05-13 | 2024-06-18 | 10 | AWSC | AWSC | DF /B /36/METERING | DFB FLAREGAS MEAS - METERING | Unknown
C | NOSD | WPM | MTN-INST | VEN-INST | 2400329529 | 1Y DFB FLAREGAS MEAS - METERING | DFB FLAREGAS MEAS - METERING | AWSC | AWSC | 20 | 0 | Empty | 2024-05-13 | 2024-05-18 | 2024-05-16 | 2024-05-18 | 2024-05-13 | 2024-06-18 | 20 | AWSC | AWSC | DF /B /36/METERING | DFB FLAREGAS MEAS - METERING | Unknown
4 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100079922 | Brüel and Kjær module No 5 is faulty | Replace Brüel & Kjær module No. 5 |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2023-06-13 | 2025-11-29 | 10 |  |  | DF /G /54/DFGA-A-3590 | Replace Brüel & Kjær module No. 5 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-05 | 2024-10-05 | 2024-01-07 | 2024-03-20 | 10 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-05 | 2024-10-06 | 2024-01-07 | 2024-03-20 | 20 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-06 | 2024-10-07 | 2024-01-07 | 2024-03-20 | 30 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-INST | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-07 | 2024-10-08 | 2024-01-07 | 2024-03-20 | 40 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-01-07 | 2024-03-20 | 50 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-01-07 | 2024-03-20 | 60 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-01-07 | 2024-03-20 | 70 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400309001 | 4Y HVAC COOL UNIT VEND DFGA-C-1202/1203 | PO Norspie | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-10-05 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-01-07 | 2024-03-20 | 80 | AWSCSECE | AWSCSECE | DF /G /09/DFGA-A-1202 | PO Norspie | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235792 | 4Y HT FROM MAINT DFFA-N-1802 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2024-06-03 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235792 | 4Y HT FROM MAINT DFFA-N-1802 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2024-06-05 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235792 | 4Y HT FROM MAINT DFFA-N-1802 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235792 | 4Y HT FROM MAINT DFFA-N-1802 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107863 | DFAA-HR-0341 REPLACE VALVE LEACKING | Isolate hosereel and heat tracing |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2024-04-07 | 2024-08-20 | 10 |  |  | DF /A /01/DFAA-HR-0341 | Isolate hosereel and heat tracing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107863 | DFAA-HR-0341 REPLACE VALVE LEACKING | Isolate hosereel and heat tracing |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2024-04-07 | 2024-08-20 | 20 |  |  | DF /A /01/DFAA-HR-0341 | Isolate hosereel and heat tracing | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107863 | DFAA-HR-0341 REPLACE VALVE LEACKING | Isolate hosereel and heat tracing |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-04-07 | 2024-08-20 | 30 |  |  | DF /A /01/DFAA-HR-0341 | Isolate hosereel and heat tracing | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-06-10 | 2020-11-07 | 10 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-06-10 | 2020-11-07 | 20 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-06-10 | 2020-11-07 | 30 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-06-10 | 2020-11-07 | 40 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2020-06-10 | 2020-11-07 | 50 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-06-10 | 2020-11-07 | 60 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100030504 | Corroded solenoid valve. XCV-30525 | Overide , tag DFAA-XCV-30525 |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-06-10 | 2020-11-07 | 70 |  |  | DF /A /10/DFAA-XCV-30525 | Overide , tag DFAA-XCV-30525 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400343682 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-12 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 32 | 0 | Empty | 2024-07-12 | 2024-07-13 | 2024-07-12 | 2024-07-13 | 2024-07-12 | 2024-09-12 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-12 | ATEX EQUIPMENT INSPECTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235634 | 4Y 380V N-SWB MAINT-DFFA-N-1803-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-12 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-DP-1803-3 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235634 | 4Y 380V N-SWB MAINT-DFFA-N-1803-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 60 | 0 | Empty | 2024-09-22 | 2024-10-12 | 2024-09-22 | 2024-10-07 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-DP-1803-3 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235634 | 4Y 380V N-SWB MAINT-DFFA-N-1803-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 20 | 0 | Empty | 2024-09-22 | 2024-10-12 | 2024-10-07 | 2024-10-12 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-DP-1803-3 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235634 | 4Y 380V N-SWB MAINT-DFFA-N-1803-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-DP-1803-3 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235583 | 4Y 380V N-SWB-MAINT-DFBA-N-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1830 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235583 | 4Y 380V N-SWB-MAINT-DFBA-N-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1830 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235583 | 4Y 380V N-SWB-MAINT-DFBA-N-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1830 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235583 | 4Y 380V N-SWB-MAINT-DFBA-N-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1830 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400344038 | 1Y LIFE RAFT INSPECTION - DFA/DFB/DFC | LIFE RAFT INSPECTION - DFA/DFB/DFC | SECE | SECE | 3 | 0 | W33-W34 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-09-23 | 10 | SECE | SECE | DF /A /02/LIFE-RAFT | LIFE RAFT INSPECTION - DFA/DFB/DFC | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307835 | 2Y FW BTR PUMP HELIDEK MAINT-P-0305/06 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 2 | 2 | W23-W24 | 2024-06-05 | 2024-06-10 | 2024-06-05 | 2024-06-05 | 2024-01-23 | 2024-03-09 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /01/DFCC-P-0305 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307835 | 2Y FW BTR PUMP HELIDEK MAINT-P-0305/06 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 6 | 6 | W23-W24 | 2024-06-05 | 2024-06-10 | 2024-06-05 | 2024-06-06 | 2024-01-23 | 2024-03-09 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /01/DFCC-P-0305 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400307835 | 2Y FW BTR PUMP HELIDEK MAINT-P-0305/06 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 6 | 6 | W23-W24 | 2024-06-05 | 2024-06-10 | 2024-06-07 | 2024-06-08 | 2024-01-23 | 2024-03-09 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /01/DFCC-P-0305 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400307835 | 2Y FW BTR PUMP HELIDEK MAINT-P-0305/06 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 6 | 6 | W23-W24 | 2024-06-05 | 2024-06-10 | 2024-06-08 | 2024-06-09 | 2024-01-23 | 2024-03-09 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /01/DFCC-P-0305 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400307835 | 2Y FW BTR PUMP HELIDEK MAINT-P-0305/06 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 1 | 1 | W23-W24 | 2024-06-05 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-01-23 | 2024-03-09 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /C /01/DFCC-P-0305 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400307835 | 2Y FW BTR PUMP HELIDEK MAINT-P-0305/06 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 2 | 1 | W23-W24 | 2024-06-05 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-01-23 | 2024-03-09 | 60 | AWSCSCHSECE | AWSCSCHSECE | DF /C /01/DFCC-P-0305 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259023 | 6M DEAERATOR MAINT - DFAA-V-3501 - DFA | DEAERATOR MAINT - DFAA-V-3501 - DFA |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-18 | 2023-06-06 | 10 |  |  | DF /A /53/DFAA-V-3501 | DEAERATOR MAINT - DFAA-V-3501 - DFA | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100068260 | DFG 20" receiver inlet XCV faulty indic. | Erect scaffold |  |  | 8 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-09 | 2022-09-07 | 10 |  |  | DF /G /34/DFGA-HOV-380132A | Erect scaffold | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100068260 | DFG 20" receiver inlet XCV faulty indic. | Erect scaffold |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-06-09 | 2022-09-07 | 20 |  |  | DF /G /34/DFGA-HOV-380132A | Erect scaffold | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100068260 | DFG 20" receiver inlet XCV faulty indic. | Erect scaffold |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-09 | 2022-09-07 | 30 |  |  | DF /G /34/DFGA-HOV-380132A | Erect scaffold | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100068260 | DFG 20" receiver inlet XCV faulty indic. | Erect scaffold |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-09 | 2022-09-07 | 40 |  |  | DF /G /34/DFGA-HOV-380132A | Erect scaffold | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100068260 | DFG 20" receiver inlet XCV faulty indic. | Erect scaffold |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-09 | 2022-09-07 | 50 |  |  | DF /G /34/DFGA-HOV-380132A | Erect scaffold | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400302677 | 6M HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-01-27 | 2024-02-12 | 10 |  |  | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302677 | 6M HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-01-27 | 2024-02-12 | 20 |  |  | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400302677 | 6M HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-01-27 | 2024-02-12 | 30 |  |  | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400330006 | 1Y NORM EQUIPMENT MAINT - DFF | NORM EQUIPMENT MAINT - DFF |  |  | 5 | 0 | Empty | 2024-05-12 | 2024-05-13 | 2024-05-12 | 2024-05-13 | 2024-05-12 | 2024-06-28 | 10 |  |  | DF /F /84 | NORM EQUIPMENT MAINT - DFF | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 3 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-16 | 2021-12-04 | 2022-03-04 | 10 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-SCAF | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 10 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-16 | 2024-09-18 | 2021-12-04 | 2022-03-04 | 20 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 2 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-19 | 2021-12-04 | 2022-03-04 | 30 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 3 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-19 | 2024-09-19 | 2021-12-04 | 2022-03-04 | 40 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 3 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-19 | 2024-09-20 | 2021-12-04 | 2022-03-04 | 50 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 2 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-20 | 2024-09-21 | 2021-12-04 | 2022-03-04 | 60 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 5 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-21 | 2024-09-22 | 2021-12-04 | 2022-03-04 | 70 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 1 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2021-12-04 | 2022-03-04 | 80 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 4 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2021-12-04 | 2022-03-04 | 90 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 2 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-23 | 2024-09-24 | 2021-12-04 | 2022-03-04 | 100 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 2 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-24 | 2021-12-04 | 2022-03-04 | 110 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 2 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2021-12-04 | 2022-03-04 | 120 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-SCAF | 2100058422 | DFA-16 Liftgas FCV-45034 trim is to big. | Erect scaffold |  |  | 4 | 0 | Req loss agreement | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2021-12-04 | 2022-03-04 | 130 |  |  | DF /A /37/DFAA-FCV-45034 | Erect scaffold | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003039 | Isolation assists FORCE 1245 | L3 Create permit. | PCNF | PCNF | 8.699999999999999289457264236 | 17.5 | Empty | 2022-06-08 | 2026-01-01 | 2020-10-19 | 2020-11-09 | 2018-12-27 | 2019-03-27 | 10 | PCNF | PCNF | DF /G /32/DFG-10-GPS-044-0011-FB-U | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003039 | Isolation assists FORCE 1245 | L3 Create permit. | PCNF | PCNF | 10.099999999999999644728632116 | 6 | Empty | 2022-06-08 | 2026-01-01 | 2020-10-23 | 2020-11-09 | 2018-12-27 | 2019-03-27 | 30 | PCNF | PCNF | DF /G /32/DFG-10-GPS-044-0011-FB-U | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003039 | Isolation assists FORCE 1245 | L3 Create permit. | PCNF | PCNF | 1 | 0 | Empty | 2022-06-08 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-27 | 2019-03-27 | 40 | PCNF | PCNF | DF /G /32/DFG-10-GPS-044-0011-FB-U | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003039 | Isolation assists FORCE 1245 | L3 Create permit. | PCNF | PCNF | 6.700000000000000177635683938 | 5.5 | Empty | 2022-06-08 | 2026-01-01 | 2022-06-08 | 2022-06-08 | 2018-12-27 | 2019-03-27 | 50 | PCNF | PCNF | DF /G /32/DFG-10-GPS-044-0011-FB-U | L3 Create permit. | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284302 | PSV Exchange - DFGA-PSV-500772 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /28/DFGA-PSV-500772 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284302 | PSV Exchange - DFGA-PSV-500772 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /28/DFGA-PSV-500772 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284302 | PSV Exchange - DFGA-PSV-500772 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-13 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /28/DFGA-PSV-500772 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284302 | PSV Exchange - DFGA-PSV-500772 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /28/DFGA-PSV-500772 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284302 | PSV Exchange - DFGA-PSV-500772 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /28/DFGA-PSV-500772 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284302 | PSV Exchange - DFGA-PSV-500772 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /28/DFGA-PSV-500772 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100065318 | Socket outlet 1808 14L2C | Preppere unistrut | PCNFSCH | PCNFSCH | 1 | 0 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-04-12 | 2022-07-11 | 10 | PCNFSCH | PCNFSCH | DF /C /61/DFCI-DP-1808-14 | Preppere unistrut | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100065318 | Socket outlet 1808 14L2C | Preppere unistrut | PCNFSCH | PCNFSCH | 1 | 0 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-04-12 | 2022-07-11 | 20 | PCNFSCH | PCNFSCH | DF /C /61/DFCI-DP-1808-14 | Preppere unistrut | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100065318 | Socket outlet 1808 14L2C | Preppere unistrut | PCNFSCH | PCNFSCH | 2 | 0 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-04-12 | 2022-07-11 | 30 | PCNFSCH | PCNFSCH | DF /C /61/DFCI-DP-1808-14 | Preppere unistrut | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100065318 | Socket outlet 1808 14L2C | Preppere unistrut | PCNFSCH | PCNFSCH | 1 | 0 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-04-12 | 2022-07-11 | 40 | PCNFSCH | PCNFSCH | DF /C /61/DFCI-DP-1808-14 | Preppere unistrut | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400325778 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-19 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 31 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-03-29 | 2024-05-30 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-19 | ATEX EQUIPMENT INSPECTION | Unknown
B | DFG-IPHP | WPM | MTN-TURB | MTN-TURB | 2400344186 | 4000H TURBINE SKID, COUNTER | NIC 23.40 Rev.00 Inspect Exh. Diff. | AWSC | AWSC | 14 | 0 | Empty | 2024-12-01 | 2024-12-04 | 2024-12-01 | 2024-12-04 | 2024-09-06 | 2024-09-22 | 10 | AWSC | AWSC | DF /G /31/DFGA-A-4302 | NIC 23.40 Rev.00 Inspect Exh. Diff. | Unknown
B | DFG-IPHP | WPM | MTN-TURB | MTN-TURB | 2400344186 | 4000H TURBINE SKID, COUNTER | NIC 23.40 Rev.00 Inspect Exh. Diff. | AWSC | AWSC | 2 | 0 | Empty | 2024-12-01 | 2024-12-04 | 2024-12-04 | 2024-12-04 | 2024-09-06 | 2024-09-22 | 20 | AWSC | AWSC | DF /G /31/DFGA-A-4302 | NIC 23.40 Rev.00 Inspect Exh. Diff. | Unknown
4 | DFB-OIL | WGN | MTN-MECH | WELLSUPV | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 3 | 3 | Empty | 2024-09-15 | 2024-09-15 | 2021-03-13 | 2023-05-31 | 2021-01-09 | 2021-09-06 | 10 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | PRODTECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 2 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 20 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-RIGG | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 30 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 30 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | PRODTECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 2 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 40 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | PRODTECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 50 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-RIGG | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 16 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 60 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-PIPF | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 5 | 10 | Empty | 2024-09-15 | 2024-09-15 | 2022-04-03 | 2023-05-31 | 2021-01-09 | 2021-09-06 | 70 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-PIPF | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 75 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-MECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 80 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | PRODTECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 90 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-PIPF | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 100 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | PRODTECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 110 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-RIGG | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 14 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 120 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-PIPF | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 130 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-PIPF | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 140 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-PIPF | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 150 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-MECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 160 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
4 | DFB-OIL | WGN | MTN-MECH | MTN-MECH | 2200004923 | Replace DFCI-PSV-33015 - PSV 2023 | new psv | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-01-09 | 2021-09-06 | 170 | PCNF | PCNF | DF /C /10/DFCI-PSV-33015 | new psv | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341922 | DFG_1Y_32200 INT STRUCT INSP - GVI | DFG_1Y_32200 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/EL_32200 & 33000 (MEZZ DECK) | DFG_1Y_32200 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400342394 | 1Y FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-18 | 2024-08-12 | 2024-08-12 | 2024-08-03 | 2024-09-02 | 10 | AWSCSECE | AWSCSECE | DF /C /01/FIREWATER-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342394 | 1Y FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-08-12 | 2024-08-18 | 2024-08-12 | 2024-08-15 | 2024-08-03 | 2024-09-02 | 20 | AWSCSECE | AWSCSECE | DF /C /01/FIREWATER-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400342394 | 1Y FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-08-12 | 2024-08-18 | 2024-08-15 | 2024-08-16 | 2024-08-03 | 2024-09-02 | 30 | AWSCSECE | AWSCSECE | DF /C /01/FIREWATER-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400342394 | 1Y FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-18 | 2024-08-16 | 2024-08-17 | 2024-08-03 | 2024-09-02 | 40 | AWSCSECE | AWSCSECE | DF /C /01/FIREWATER-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400342394 | 1Y FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-08-12 | 2024-08-18 | 2024-08-17 | 2024-08-18 | 2024-08-03 | 2024-09-02 | 50 | AWSCSECE | AWSCSECE | DF /C /01/FIREWATER-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400342394 | 1Y FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-18 | 2024-08-18 | 2024-08-18 | 2024-08-03 | 2024-09-02 | 60 | AWSCSECE | AWSCSECE | DF /C /01/FIREWATER-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 24 | 8 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 5 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 12 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 5 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-18 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 4 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 0 | 0 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 130 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284235 | PSV Exchange - DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | AWSC | AWSC | 0 | 22 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 140 | AWSC | AWSC | DF /C /01/DFCM-PSV-03480 | DFCM-PSV-03480 Offshore from WS Måde | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044248 | Håndtag knækket af 1" bypass ventil DFFA | Inform SYS Responible on status |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-04-07 | 2021-09-04 | 10 |  |  | DF /F /27/DFFA-PSV-500758 | Inform SYS Responible on status | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044248 | Håndtag knækket af 1" bypass ventil DFFA | Inform SYS Responible on status |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-04-07 | 2021-09-04 | 20 |  |  | DF /F /27/DFFA-PSV-500758 | Inform SYS Responible on status | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044248 | Håndtag knækket af 1" bypass ventil DFFA | Inform SYS Responible on status |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-04-07 | 2021-09-04 | 30 |  |  | DF /F /27/DFFA-PSV-500758 | Inform SYS Responible on status | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075996 | DFFW: Replace buffer + bolts under cabin | Build/demol of scaffold for access |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2022-11-22 | 2023-04-06 | 10 |  |  | DF /F /78/DFFA-A-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100075996 | DFFW: Replace buffer + bolts under cabin | Build/demol of scaffold for access |  |  | 40 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-08-02 | 2022-11-22 | 2023-04-06 | 20 |  |  | DF /F /78/DFFA-A-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075996 | DFFW: Replace buffer + bolts under cabin | Build/demol of scaffold for access |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-05 | 2022-11-22 | 2023-04-06 | 30 |  |  | DF /F /78/DFFA-A-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100075996 | DFFW: Replace buffer + bolts under cabin | Build/demol of scaffold for access |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-05 | 2022-11-22 | 2023-04-06 | 35 |  |  | DF /F /78/DFFA-A-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100075996 | DFFW: Replace buffer + bolts under cabin | Build/demol of scaffold for access |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-05 | 2022-11-22 | 2023-04-06 | 40 |  |  | DF /F /78/DFFA-A-6102 | Build/demol of scaffold for access | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235592 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-31 | 2023-06-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235592 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-31 | 2023-06-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235592 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-31 | 2023-06-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235592 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-31 | 2023-06-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802A-1 | 380V N-SWB-INSP-DFFA-N-1802A-1 | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300007686 | DK40 - CONSUMABLE MTN - ELEC | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2027-01-02 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 8 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-12-18 | 2024-01-17 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-ELEC | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-23 | 2023-12-18 | 2024-01-17 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-INST | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 10 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-26 | 2023-12-18 | 2024-01-17 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
A | DFF-IPHP | WPM | MTN-TURB | VEN-MECH | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 12 | 4 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-12-18 | 2024-01-17 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-12-18 | 2024-01-17 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-12-18 | 2024-01-17 | 60 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400282067 | 8000H TURBINE SKID, COUNTER | Increase of PO 4500102165 | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-12-18 | 2024-01-17 | 70 | AWSCSCHSECE | AWSCSCHSECE | DF /F /31/DFFA-A-4301 | Increase of PO 4500102165 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075993 | DFFE/78: Replace Windspeed sensor bracke | Replace tube for Windspeed sensor in A-f |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-11-21 | 2023-04-05 | 10 |  |  | DF /F /78/DFFA-A-6101 | Replace tube for Windspeed sensor in A-f | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075993 | DFFE/78: Replace Windspeed sensor bracke | Replace tube for Windspeed sensor in A-f |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-11-21 | 2023-04-05 | 20 |  |  | DF /F /78/DFFA-A-6101 | Replace tube for Windspeed sensor in A-f | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075993 | DFFE/78: Replace Windspeed sensor bracke | Replace tube for Windspeed sensor in A-f |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2022-11-21 | 2023-04-05 | 30 |  |  | DF /F /78/DFFA-A-6101 | Replace tube for Windspeed sensor in A-f | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308999 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL DE-ISOLATION |  |  | 1 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2024-09-03 | 2024-02-18 | 2024-03-19 | 10 |  |  | DF /C /09/DFCI-A-1221 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308999 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL DE-ISOLATION |  |  | 12 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2024-09-06 | 2024-02-18 | 2024-03-19 | 20 |  |  | DF /C /09/DFCI-A-1221 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308999 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL DE-ISOLATION |  |  | 1 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-02-18 | 2024-03-19 | 30 |  |  | DF /C /09/DFCI-A-1221 | PERSONAL DE-ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308999 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL DE-ISOLATION |  |  | 2 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-02-18 | 2024-03-19 | 40 |  |  | DF /C /09/DFCI-A-1221 | PERSONAL DE-ISOLATION | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075978 | Water in hyd oil in WHP A-3102. | Isolation of DFAA-A-3102 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-10-10 | 2022-11-24 | 10 |  |  | DF /A /07/DFAA-A-3102 | Isolation of DFAA-A-3102 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075978 | Water in hyd oil in WHP A-3102. | Isolation of DFAA-A-3102 |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-10-10 | 2022-11-24 | 20 |  |  | DF /A /07/DFAA-A-3102 | Isolation of DFAA-A-3102 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075978 | Water in hyd oil in WHP A-3102. | Isolation of DFAA-A-3102 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-10-10 | 2022-11-24 | 30 |  |  | DF /A /07/DFAA-A-3102 | Isolation of DFAA-A-3102 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308560 | 1Y BDV LUBE/FUNC TEST - DFA/B/E | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | W21-W22 | 2024-05-20 | 2024-05-30 | 2024-05-20 | 2024-05-22 | 2024-02-10 | 2024-03-11 | 10 | SECE | SECE | DF /A /70/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308560 | 1Y BDV LUBE/FUNC TEST - DFA/B/E | ISOLATION BY PRODUCTION | SECE | SECE | 26 | 0 | W21-W22 | 2024-05-20 | 2024-05-30 | 2024-05-22 | 2024-05-28 | 2024-02-10 | 2024-03-11 | 20 | SECE | SECE | DF /A /70/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400308560 | 1Y BDV LUBE/FUNC TEST - DFA/B/E | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | W21-W22 | 2024-05-20 | 2024-05-30 | 2024-05-28 | 2024-05-30 | 2024-02-10 | 2024-03-11 | 30 | SECE | SECE | DF /A /70/BDV | ISOLATION BY PRODUCTION | Unknown
1 | NOSD | WDF | MTN-INST | MTN-INST | 2100113970 | Replacement of DFF-LT-410012 | FLM:DFF-LT-410012 Afviger fra LT-410011 | SECE | SECE | 0 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-06-06 | 2024-06-08 | 2024-07-17 | 2024-11-29 | 10 | SECE | SECE | DF /F /30/DFFA-LIT-410011 | FLM:DFF-LT-410012 Afviger fra LT-410011 | Unknown
1 | NOSD | WDF | MTN-INST | MTN-INST | 2100113970 | Replacement of DFF-LT-410012 | FLM:DFF-LT-410012 Afviger fra LT-410011 | SECE | SECE | 10 | 10 | Empty | 2024-07-17 | 2024-07-21 | 2024-06-06 | 2024-06-08 | 2024-07-17 | 2024-11-29 | 20 | SECE | SECE | DF /F /30/DFFA-LIT-410011 | FLM:DFF-LT-410012 Afviger fra LT-410011 | Unknown
1 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100113970 | Replacement of DFF-LT-410012 | FLM:DFF-LT-410012 Afviger fra LT-410011 | SECE | SECE | 20 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-06-06 | 2024-06-08 | 2024-07-17 | 2024-11-29 | 30 | SECE | SECE | DF /F /30/DFFA-LIT-410011 | FLM:DFF-LT-410012 Afviger fra LT-410011 | Unknown
1 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100113970 | Replacement of DFF-LT-410012 | FLM:DFF-LT-410012 Afviger fra LT-410011 | SECE | SECE | 20 | 18 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-17 | 2024-07-18 | 2024-07-17 | 2024-11-29 | 40 | SECE | SECE | DF /F /30/DFFA-LIT-410011 | FLM:DFF-LT-410012 Afviger fra LT-410011 | Unknown
1 | NOSD | WDF | MTN-INST | MTN-INST | 2100113970 | Replacement of DFF-LT-410012 | FLM:DFF-LT-410012 Afviger fra LT-410011 | SECE | SECE | 16 | 30 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-18 | 2024-07-20 | 2024-07-17 | 2024-11-29 | 50 | SECE | SECE | DF /F /30/DFFA-LIT-410011 | FLM:DFF-LT-410012 Afviger fra LT-410011 | Unknown
1 | NOSD | WDF | MTN-INST | MTN-INST | 2100113970 | Replacement of DFF-LT-410012 | FLM:DFF-LT-410012 Afviger fra LT-410011 | SECE | SECE | 2 | 0 | Empty | 2024-07-17 | 2024-07-21 | 2024-07-20 | 2024-07-21 | 2024-07-17 | 2024-11-29 | 60 | SECE | SECE | DF /F /30/DFFA-LIT-410011 | FLM:DFF-LT-410012 Afviger fra LT-410011 | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009238 | Insulation assist bilfinger 22392 | Bilfinger |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /32/DFF-16-GPS-044-7004-EB-U | Bilfinger | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009238 | Insulation assist bilfinger 22392 | Bilfinger |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /32/DFF-16-GPS-044-7004-EB-U | Bilfinger | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009238 | Insulation assist bilfinger 22392 | Bilfinger |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-09 | 2022-02-07 | 2022-07-07 | 22 |  |  | DF /F /32/DFF-16-GPS-044-7004-EB-U | Bilfinger | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009238 | Insulation assist bilfinger 22392 | Bilfinger |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-12 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /32/DFF-16-GPS-044-7004-EB-U | Bilfinger | Unknown
4 | NOSD | WGN | MTN-LAGG | VEN-INSP | 2200009238 | Insulation assist bilfinger 22392 | Bilfinger |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /32/DFF-16-GPS-044-7004-EB-U | Bilfinger | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339104 | DFC_1Y_HELIDECK INT STRUCT INSP - GVI | DFC_1Y_HELIDECK INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/HELIDECK-STRUCTURE | DFC_1Y_HELIDECK INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095138 | HOSE REEL LEAKING | Replace hosereel, fit new swivel and hos | SECE | SECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2023-09-08 | 2024-01-21 | 10 | SECE | SECE | DF /F /01/DFFA-HRF-0309 | Replace hosereel, fit new swivel and hos | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095138 | HOSE REEL LEAKING | Replace hosereel, fit new swivel and hos | SECE | SECE | 8 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2023-09-08 | 2024-01-21 | 20 | SECE | SECE | DF /F /01/DFFA-HRF-0309 | Replace hosereel, fit new swivel and hos | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100095138 | HOSE REEL LEAKING | Replace hosereel, fit new swivel and hos | SECE | SECE | 8 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-02 | 2023-09-08 | 2024-01-21 | 30 | SECE | SECE | DF /F /01/DFFA-HRF-0309 | Replace hosereel, fit new swivel and hos | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095138 | HOSE REEL LEAKING | Replace hosereel, fit new swivel and hos | SECE | SECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2023-09-08 | 2024-01-21 | 40 | SECE | SECE | DF /F /01/DFFA-HRF-0309 | Replace hosereel, fit new swivel and hos | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344068 | 6M BDV LUB/MAINT- DFG | BDV LUB/INSP- DFG |  |  | 8 | 0 | Empty | 2024-09-07 | 2024-09-08 | 2024-09-07 | 2024-09-08 | 2024-09-07 | 2024-09-23 | 10 |  |  | DF /G /34/BDV | BDV LUB/INSP- DFG | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 0 | 0 | W33-34 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-03-27 | 2022-05-06 | 10 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 1 | 0 | W33-34 | 2024-09-22 | 2024-09-23 | 2023-08-15 | 2023-10-21 | 2022-03-27 | 2022-05-06 | 20 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 3 | 0 | W33-34 | 2024-09-22 | 2024-09-23 | 2023-08-15 | 2023-10-21 | 2022-03-27 | 2022-05-06 | 30 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 3 | 22 | W33-34 | 2024-09-22 | 2024-09-23 | 2023-08-16 | 2023-10-21 | 2022-03-27 | 2022-05-06 | 40 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 0 | 0 | W33-34 | 2024-09-22 | 2024-09-23 | 2023-08-16 | 2023-10-21 | 2022-03-27 | 2022-05-06 | 50 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 6 | 6 | W33-34 | 2024-09-22 | 2024-09-23 | 2023-08-15 | 2023-10-21 | 2022-03-27 | 2022-05-06 | 60 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 12 | 0 | W33-34 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2022-03-27 | 2022-05-06 | 70 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100064891 | DFG-ESDV-340042 stock open | Troubleshoot DFG-ESDV-340042 stock open | PCNFSECE | PCNFSECE | 0 | 0 | W33-34 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-03-27 | 2022-05-06 | 80 | PCNFSECE | PCNFSECE | DF /G /23/DFGA-ESDV-340042 | Troubleshoot DFG-ESDV-340042 stock open | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-PAIN | 2100036137 | ANOCR Ex corrosion DFB-2-GI-08-9011-AA | Set up equipment |  |  | 0 | 0 | Empty | 2020-08-20 | 2020-09-01 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-11-18 | 10 |  |  | DF /B /74/DFB-2-GI-008-9011-AA-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100036137 | ANOCR Ex corrosion DFB-2-GI-08-9011-AA | Set up equipment |  |  | 12 | 0 | Empty | 2020-08-20 | 2020-09-01 | 2020-08-20 | 2020-08-21 | 2020-08-20 | 2020-11-18 | 20 |  |  | DF /B /74/DFB-2-GI-008-9011-AA-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100036137 | ANOCR Ex corrosion DFB-2-GI-08-9011-AA | Set up equipment |  |  | 6 | 0 | Empty | 2020-08-20 | 2020-09-01 | 2020-08-21 | 2020-08-21 | 2020-08-20 | 2020-11-18 | 30 |  |  | DF /B /74/DFB-2-GI-008-9011-AA-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100036137 | ANOCR Ex corrosion DFB-2-GI-08-9011-AA | Set up equipment |  |  | 114 | 0 | Empty | 2020-08-20 | 2020-09-01 | 2020-08-21 | 2020-08-31 | 2020-08-20 | 2020-11-18 | 40 |  |  | DF /B /74/DFB-2-GI-008-9011-AA-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100036137 | ANOCR Ex corrosion DFB-2-GI-08-9011-AA | Set up equipment |  |  | 12 | 0 | Empty | 2020-08-20 | 2020-09-01 | 2020-08-31 | 2020-09-01 | 2020-08-20 | 2020-11-18 | 50 |  |  | DF /B /74/DFB-2-GI-008-9011-AA-U | Set up equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 4 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-12 | 2019-04-15 | 2019-09-12 | 10 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 2 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-12 | 2019-04-15 | 2019-09-12 | 20 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 2 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-12 | 2019-04-15 | 2019-09-12 | 30 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 1 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-13 | 2019-04-15 | 2019-09-12 | 40 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 4 | 10 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-13 | 2019-04-15 | 2019-09-12 | 50 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 4 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-13 | 2023-05-13 | 2019-04-15 | 2019-09-12 | 60 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 1 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-13 | 2023-05-14 | 2019-04-15 | 2019-09-12 | 70 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 4 | 10 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-13 | 2023-05-14 | 2019-04-15 | 2019-09-12 | 80 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 2 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-14 | 2023-05-14 | 2019-04-15 | 2019-09-12 | 90 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 4 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-14 | 2023-05-15 | 2019-04-15 | 2019-09-12 | 100 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 0 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-12 | 2019-04-15 | 2019-09-12 | 110 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100023946 | Replace DFBA-PSV-33004 - PSV 2023 | L3 Pre. Permit and linewalk. |  |  | 0 | 0 | Empty | 2023-05-12 | 2023-05-15 | 2023-05-12 | 2023-05-12 | 2019-04-15 | 2019-09-12 | 120 |  |  | DF /B /10/DFBA-PSV-33004 | L3 Pre. Permit and linewalk. | Unknown
3 | NE | WDF | MTN-ELEC | PRODTECH | 2100095468 | Start signal from SCADA missing Periodic | Isolate Breaker | PCNF | PCNF | 2 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-09-12 | 2024-01-25 | 20 | PCNF | PCNF | DF /E /61/DFEZ-N-1801 | Isolate Breaker | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100095468 | Start signal from SCADA missing Periodic | Isolate Breaker | PCNF | PCNF | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-09-12 | 2024-01-25 | 30 | PCNF | PCNF | DF /E /61/DFEZ-N-1801 | Isolate Breaker | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100095468 | Start signal from SCADA missing Periodic | Isolate Breaker | PCNF | PCNF | 2 | 3 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-09-12 | 2024-01-25 | 40 | PCNF | PCNF | DF /E /61/DFEZ-N-1801 | Isolate Breaker | Unknown
3 | NE | WDF | MTN-ELEC | MTN-ELEC | 2100095468 | Start signal from SCADA missing Periodic | Isolate Breaker | PCNF | PCNF | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-09-12 | 2024-01-25 | 50 | PCNF | PCNF | DF /E /61/DFEZ-N-1801 | Isolate Breaker | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087751 | Nød armatur 1812-10905-L2B | Nød armatur 1812-10905-L2B |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 10 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatur 1812-10905-L2B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087751 | Nød armatur 1812-10905-L2B | Nød armatur 1812-10905-L2B |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 20 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatur 1812-10905-L2B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087751 | Nød armatur 1812-10905-L2B | Nød armatur 1812-10905-L2B |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 30 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatur 1812-10905-L2B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087751 | Nød armatur 1812-10905-L2B | Nød armatur 1812-10905-L2B |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 40 |  |  | DF /F /05/DFFA-N-1812-05 | Nød armatur 1812-10905-L2B | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100080202 | DFB-20 choke failure to open on demand. | Replace SOV |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-10 | 2023-06-25 | 10 |  |  | DF /B /55/DFBA-CVA-30423 | Replace SOV | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100080202 | DFB-20 choke failure to open on demand. | Replace SOV |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-02-10 | 2023-06-25 | 20 |  |  | DF /B /55/DFBA-CVA-30423 | Replace SOV | Unknown
B | DFG-IPHP | WPM | MTN-TURB | MTN-TURB | 2400344185 | 4000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION & GREASING | AWSC | AWSC | 18 | 0 | Empty | 2024-12-01 | 2024-12-06 | 2024-12-01 | 2024-12-05 | 2024-09-06 | 2024-09-22 | 10 | AWSC | AWSC | DF /G /31/DFGA-A-4302 | VISUAL INSPECTION & GREASING | Unknown
B | DFG-IPHP | WPM | MTN-TURB | MTN-INST | 2400344185 | 4000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION & GREASING | AWSC | AWSC | 6 | 0 | Empty | 2024-12-01 | 2024-12-06 | 2024-12-05 | 2024-12-06 | 2024-09-06 | 2024-09-22 | 20 | AWSC | AWSC | DF /G /31/DFGA-A-4302 | VISUAL INSPECTION & GREASING | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009254 | Insulation assist FORCE 20063(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-03 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /G /28/DFG-6-DPS-050-0208-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009254 | Insulation assist FORCE 20063(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-03 | 2023-03-27 | 2023-03-29 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /G /28/DFG-6-DPS-050-0208-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009254 | Insulation assist FORCE 20063(COMP) | Bilfinger inspection |  |  | 8 | 0 | Empty | 2023-03-27 | 2023-04-03 | 2023-03-30 | 2023-03-30 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /G /28/DFG-6-DPS-050-0208-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009254 | Insulation assist FORCE 20063(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-04-03 | 2023-03-30 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 35 |  |  | DF /G /28/DFG-6-DPS-050-0208-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009254 | Insulation assist FORCE 20063(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-03 | 2023-03-31 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /G /28/DFG-6-DPS-050-0208-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009254 | Insulation assist FORCE 20063(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-03 | 2023-04-01 | 2023-04-03 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /G /28/DFG-6-DPS-050-0208-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 12 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-07-29 | 2024-07-30 | 2018-10-28 | 2019-03-27 | 10 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-07-30 | 2024-07-31 | 2018-10-28 | 2019-03-27 | 20 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-INST | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-07-31 | 2024-08-01 | 2018-10-28 | 2019-03-27 | 30 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ELEC | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-01 | 2024-08-01 | 2018-10-28 | 2019-03-27 | 35 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 10 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-01 | 2024-08-02 | 2018-10-28 | 2019-03-27 | 40 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 10 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-02 | 2024-08-03 | 2018-10-28 | 2019-03-27 | 50 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 10 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-05 | 2024-08-06 | 2018-10-28 | 2019-03-27 | 60 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-INST | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-08 | 2024-08-09 | 2018-10-28 | 2019-03-27 | 70 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ELEC | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-09 | 2024-08-10 | 2018-10-28 | 2019-03-27 | 75 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-10 | 2024-08-10 | 2018-10-28 | 2019-03-27 | 80 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003148 | Dan FB-Corroded Valtek Actu LCV-50419 | Re-connect electrical on actuator |  |  | 8 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-10 | 2024-08-11 | 2018-10-28 | 2019-03-27 | 90 |  |  | DF /B /27/DFBA-LCV-50419 | Re-connect electrical on actuator | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400343677 | 1Y BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 |  |  | 1 | 0 | Empty | 2024-08-09 | 2024-08-10 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-09-14 | 10 |  |  | DF /F /75/DFFA-A-3931 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343677 | 1Y BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 |  |  | 2 | 0 | Empty | 2024-08-09 | 2024-08-10 | 2024-08-09 | 2024-08-09 | 2024-08-09 | 2024-09-14 | 20 |  |  | DF /F /75/DFFA-A-3931 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400343677 | 1Y BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 |  |  | 2 | 0 | Empty | 2024-08-09 | 2024-08-10 | 2024-08-09 | 2024-08-10 | 2024-08-09 | 2024-09-14 | 30 |  |  | DF /F /75/DFFA-A-3931 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400343677 | 1Y BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 |  |  | 2 | 0 | Empty | 2024-08-09 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-09 | 2024-09-14 | 40 |  |  | DF /F /75/DFFA-A-3931 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400343677 | 1Y BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 |  |  | 1 | 0 | Empty | 2024-08-09 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-09 | 2024-09-14 | 50 |  |  | DF /F /75/DFFA-A-3931 | BIOCIDE INJ PUMP MAINT-DFCI-P-3901 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235652 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R15 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R15B1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235652 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R15 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R15B1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235652 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R15 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R15B1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235652 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R15 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R15B1 | DE-ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100111337 | Floodlight is not working | Floodlight is not working |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-06-08 | 2024-10-21 | 10 |  |  | DF /F /61/DFFA-N-1802B-07 | Floodlight is not working | Unknown
3 | NOSD | WDF | MTN-TURB | PRODTECH | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 2 | 0 | Empty | 2024-04-24 | 2024-04-30 | 2021-11-09 | 2021-12-18 | 2021-04-07 | 2021-05-17 | 10 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 8 | 6 | Empty | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-04-24 | 2021-04-07 | 2021-05-17 | 20 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
3 | NOSD | WDF | MTN-TURB | PRODTECH | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 2 | 0 | Empty | 2024-04-24 | 2024-04-30 | 2021-11-09 | 2021-12-18 | 2021-04-07 | 2021-05-17 | 30 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
3 | NOSD | WDF | MTN-TURB | VEN-MECH | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 12 | 0 | Empty | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-04-24 | 2021-04-07 | 2021-05-17 | 40 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-INST | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 12.5 | 0 | Empty | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-04-27 | 2021-04-07 | 2021-05-17 | 50 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 25 | 0 | Empty | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-04-30 | 2021-04-07 | 2021-05-17 | 60 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TELE | 2100047919 | Compass vibration system issues | Observation - Vibration | PCNF | PCNF | 20 | 0 | Empty | 2024-04-24 | 2024-04-30 | 2024-04-24 | 2024-04-29 | 2021-04-07 | 2021-05-17 | 70 | PCNF | PCNF | DF /F /54/DFFA-P-3520 | Observation - Vibration | Unknown
4 | NE | WRO | MTN-SAT | MTN-SAT | 2300000550 | DUCSAT Replaced by 2300003118 Do NOT Use | DUCSAT CONSUM DAN SAT |  |  | 0 | 0 | Empty | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2010-01-01 | 2030-12-31 | 10 |  |  | DF /F | DUCSAT CONSUM DAN SAT | Unknown
4 | NE | WRO | MTN-SAT | MTN-SAT | 2300000550 | DUCSAT Replaced by 2300003118 Do NOT Use | DUCSAT CONSUM DAN SAT |  |  | 0 | 0 | Empty | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2010-01-01 | 2030-12-31 | 20 |  |  | DF /F | DUCSAT CONSUM DAN SAT | Unknown
4 | NE | WRO | MTN-SAT | MTN-SAT | 2300000550 | DUCSAT Replaced by 2300003118 Do NOT Use | DUCSAT CONSUM DAN SAT |  |  | 0 | 0 | Empty | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2010-01-01 | 2030-12-31 | 30 |  |  | DF /F | DUCSAT CONSUM DAN SAT | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400315822 | 3M CRUDE OIL EXP. SKD MAINT-DFCM-A-3660 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3660 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-15 | 2024-04-26 | 10 |  |  | DF /C /23/DFCM-A-3660 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3660 | Unknown
D | NOSD | WPM | MTN-MECH | MTN-PAIN | 2400263071 | 1Y SLIDING DOORS DFG | SLIDING DOORS DFG |  |  | 16 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-05-17 | 2023-07-03 | 10 |  |  | DF /G /86 | SLIDING DOORS DFG | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235829 | 4Y 380V E-SWB MAINT DFFA-N-1812-10 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1812-10 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235829 | 4Y 380V E-SWB MAINT DFFA-N-1812-10 | ISOLATION BY PRODUCTION | SCH | SCH | 10 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1812-10 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235829 | 4Y 380V E-SWB MAINT DFFA-N-1812-10 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1812-10 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235829 | 4Y 380V E-SWB MAINT DFFA-N-1812-10 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1812-10 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096744 | udskiftning af ventiler og ventilhåndtag | replace valve |  |  | 1 | 0 | Empty | 2024-06-20 | 2024-06-22 | 2024-06-20 | 2024-06-20 | 2024-02-20 | 2026-08-08 | 10 |  |  | DF /C /01/DFCC-A-0304B | replace valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096744 | udskiftning af ventiler og ventilhåndtag | replace valve |  |  | 4 | 0 | Empty | 2024-06-20 | 2024-06-22 | 2024-06-20 | 2024-06-21 | 2024-02-20 | 2026-08-08 | 20 |  |  | DF /C /01/DFCC-A-0304B | replace valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096744 | udskiftning af ventiler og ventilhåndtag | replace valve |  |  | 1 | 0 | Empty | 2024-06-20 | 2024-06-22 | 2024-06-21 | 2024-06-22 | 2024-02-20 | 2026-08-08 | 30 |  |  | DF /C /01/DFCC-A-0304B | replace valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 24 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-02 | 2024-05-08 | 2020-07-01 | 2020-07-06 | 5 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 40 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-08 | 2024-05-18 | 2020-07-01 | 2020-07-06 | 10 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 5 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-18 | 2024-05-19 | 2020-07-01 | 2020-07-06 | 20 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 10 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-19 | 2024-05-22 | 2020-07-01 | 2020-07-06 | 30 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 10 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-22 | 2024-05-24 | 2020-07-01 | 2020-07-06 | 40 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 5 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-24 | 2024-05-25 | 2020-07-01 | 2020-07-06 | 50 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 15 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-25 | 2024-05-29 | 2020-07-01 | 2020-07-06 | 60 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 0 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-29 | 2024-05-29 | 2020-07-01 | 2020-07-06 | 70 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100034503 | Hydraulic skid needs overhaul. | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 0 | 0 | Vendor | 2024-05-02 | 2024-08-27 | 2024-05-29 | 2024-05-29 | 2020-07-01 | 2020-07-06 | 80 | AWSC | AWSC | DF /F /07/DFFA-A-5901 | Vendor troubleshoot Hydraulic cabinets | Unknown
4 | DFC-FUEL | WDF | MTN-INST | PRODTECH | 2100070244 | DFCM-SOV-57652 is about to rust away. | Deisolate and repeal inhibits ShutDown V | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 10 | SECE | SECE | DF /C /70/DFCM-ESDV-57652 | Deisolate and repeal inhibits ShutDown V | Unknown
4 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100070244 | DFCM-SOV-57652 is about to rust away. | Deisolate and repeal inhibits ShutDown V | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 20 | SECE | SECE | DF /C /70/DFCM-ESDV-57652 | Deisolate and repeal inhibits ShutDown V | Unknown
4 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100070244 | DFCM-SOV-57652 is about to rust away. | Deisolate and repeal inhibits ShutDown V | SECE | SECE | 2 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-18 | 2025-06-05 | 30 | SECE | SECE | DF /C /70/DFCM-ESDV-57652 | Deisolate and repeal inhibits ShutDown V | Unknown
4 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100070244 | DFCM-SOV-57652 is about to rust away. | Deisolate and repeal inhibits ShutDown V | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-12-18 | 2025-06-05 | 40 | SECE | SECE | DF /C /70/DFCM-ESDV-57652 | Deisolate and repeal inhibits ShutDown V | Unknown
4 | DFC-FUEL | WDF | MTN-INST | PRODTECH | 2100070244 | DFCM-SOV-57652 is about to rust away. | Deisolate and repeal inhibits ShutDown V | SECE | SECE | 1 | 0 | Empty | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-12-18 | 2025-06-05 | 50 | SECE | SECE | DF /C /70/DFCM-ESDV-57652 | Deisolate and repeal inhibits ShutDown V | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339095 | DFC_1Y_43600 INT STRUCT INSP - GVI | DFC_1Y_43600 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_43600 (L4 MEZZANINE DECK) | DFC_1Y_43600 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328726 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | RETURN TO OPERATION | SECE | SECE | 1 | 0 | Empty | 2024-05-06 | 2024-05-08 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-06-05 | 10 | SECE | SECE | DF /F /09/DFFB-A-1251 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328726 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | RETURN TO OPERATION | SECE | SECE | 7 | 0 | Empty | 2024-05-06 | 2024-05-08 | 2024-05-06 | 2024-05-07 | 2024-05-06 | 2024-06-05 | 20 | SECE | SECE | DF /F /09/DFFB-A-1251 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328726 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | RETURN TO OPERATION | SECE | SECE | 1 | 0 | Empty | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-06 | 2024-06-05 | 30 | SECE | SECE | DF /F /09/DFFB-A-1251 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328726 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | RETURN TO OPERATION | SECE | SECE | 2 | 0 | Empty | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-06 | 2024-06-05 | 40 | SECE | SECE | DF /F /09/DFFB-A-1251 | RETURN TO OPERATION | Unknown
3 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200010043 | ANOCR assist Bilfinger 22106 | assist Bilfinger 22106 |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-13 | 2023-02-13 | 2022-02-15 | 2022-03-27 | 10 |  |  | DF /F /27/DFFA-T-5053 | assist Bilfinger 22106 | Unknown
3 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200010043 | ANOCR assist Bilfinger 22106 | assist Bilfinger 22106 |  |  | 48 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-13 | 2023-02-15 | 2022-02-15 | 2022-03-27 | 20 |  |  | DF /F /27/DFFA-T-5053 | assist Bilfinger 22106 | Unknown
3 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200010043 | ANOCR assist Bilfinger 22106 | assist Bilfinger 22106 |  |  | 120 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-15 | 2023-02-25 | 2022-02-15 | 2022-03-27 | 30 |  |  | DF /F /27/DFFA-T-5053 | assist Bilfinger 22106 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259587 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-05-24 | 2023-06-23 | 10 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400259587 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-05-24 | 2023-06-23 | 20 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259587 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 4 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2023-05-24 | 2023-06-23 | 30 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259587 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3801 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2023-05-24 | 2023-06-23 | 40 | SECE | SECE | DF /F /34/DFFA-EP-3801 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-MECH | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 272 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-06-15 | 2024-08-21 | 2024-10-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-SCAF | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 312 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-08-22 | 2024-11-07 | 2024-10-01 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-ELEC | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 17 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-08 | 2024-11-12 | 2024-10-01 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-RIGG | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-12 | 2024-11-12 | 2024-10-01 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-PIPF | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-12 | 2024-11-12 | 2024-10-01 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-ROPE | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-12 | 2024-11-12 | 2024-10-01 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-INST | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-12 | 2024-11-12 | 2024-10-01 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-PAIN | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 82 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-12 | 2024-11-20 | 2024-10-01 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | PRODTECH | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 15 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-20 | 2024-11-24 | 2024-10-01 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | VEN-INSP | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-24 | 2024-11-25 | 2024-10-01 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | DFF-LP-1 | WPM | VEN-INSP | MTN-LAGG | 2400291991 | PVI Major - DFFA-E-4201 | Rigging and lifting work | AWSCSECE | AWSCSECE | 32 | 0 | Empty | 2024-06-15 | 2024-11-29 | 2024-11-25 | 2024-11-29 | 2024-10-01 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-E-4201 | Rigging and lifting work | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284299 | PSV Exchange - DFGA-PSV-340051 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /27/DFGA-PSV-340051 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284299 | PSV Exchange - DFGA-PSV-340051 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /27/DFGA-PSV-340051 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284299 | PSV Exchange - DFGA-PSV-340051 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /27/DFGA-PSV-340051 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284299 | PSV Exchange - DFGA-PSV-340051 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /27/DFGA-PSV-340051 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284299 | PSV Exchange - DFGA-PSV-340051 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /27/DFGA-PSV-340051 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284299 | PSV Exchange - DFGA-PSV-340051 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /27/DFGA-PSV-340051 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2021-10-18 | 2021-11-27 | 10 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2021-10-18 | 2021-11-27 | 20 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2021-10-18 | 2021-11-27 | 30 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2021-10-18 | 2021-11-27 | 40 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2021-10-18 | 2021-11-27 | 50 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 16 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2021-10-18 | 2021-11-27 | 60 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2021-10-18 | 2021-11-27 | 70 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2021-10-18 | 2021-11-27 | 80 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100056487 | HT cable is damaged must be replaced | Remove insulation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2021-10-18 | 2021-11-27 | 90 |  |  | DF /F /61/DFFA-DP-1802A-7-F16 | Remove insulation | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235304 | 6M CHEMICAL INJECTION PUMPS MAINT-DAN FE | CHEMICAL INJECTION PUMPS MAINT-DAN FE | SCH | SCH | 16 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2023-02-26 | 2023-03-17 | 10 | SCH | SCH | DF /E /75/DFEY-A-3901 | CHEMICAL INJECTION PUMPS MAINT-DAN FE | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018134 | Replace Motor protection 1841-M110 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M110-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018134 | Replace Motor protection 1841-M110 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M110-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018134 | Replace Motor protection 1841-M110 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M110-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018134 | Replace Motor protection 1841-M110 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M110-02 | New mat num | Unknown
3 | DFE-O06 | WDF | MTN-MECH | MTN-RIGG | 2100079221 | Olielækage fra aktuator | Rigging preparation |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2023-01-22 | 2023-06-06 | 10 |  |  | DF /E /10/DFEZ-CVA-30006 | Rigging preparation | Unknown
3 | DFE-O06 | WDF | MTN-MECH | PRODTECH | 2100079221 | Olielækage fra aktuator | Rigging preparation |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-23 | 2023-01-22 | 2023-06-06 | 20 |  |  | DF /E /10/DFEZ-CVA-30006 | Rigging preparation | Unknown
3 | DFE-O06 | WDF | MTN-MECH | MTN-MECH | 2100079221 | Olielækage fra aktuator | Rigging preparation |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-25 | 2023-01-22 | 2023-06-06 | 30 |  |  | DF /E /10/DFEZ-CVA-30006 | Rigging preparation | Unknown
3 | DFE-O06 | WDF | MTN-MECH | MTN-RIGG | 2100079221 | Olielækage fra aktuator | Rigging preparation |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-25 | 2023-01-22 | 2023-06-06 | 40 |  |  | DF /E /10/DFEZ-CVA-30006 | Rigging preparation | Unknown
3 | DFE-O06 | WDF | MTN-MECH | PRODTECH | 2100079221 | Olielækage fra aktuator | Rigging preparation |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-01-22 | 2023-06-06 | 50 |  |  | DF /E /10/DFEZ-CVA-30006 | Rigging preparation | Unknown
3 | DFE-O06 | WDF | MTN-MECH | MTN-RIGG | 2100079221 | Olielækage fra aktuator | Rigging preparation |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-01-22 | 2023-06-06 | 60 |  |  | DF /E /10/DFEZ-CVA-30006 | Rigging preparation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-03-08 | 2024-07-21 | 20 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 10 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2024-03-08 | 2024-07-21 | 25 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-03-08 | 2024-07-21 | 30 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2024-03-08 | 2024-07-21 | 40 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2024-03-08 | 2024-07-21 | 50 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-03-08 | 2024-07-21 | 60 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100106038 | Dehumidyfier A trips breaker/RCD | Build scaffold for lifting |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-03-08 | 2024-07-21 | 70 |  |  | DF /C /03 | Build scaffold for lifting | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 160 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-09 | 2023-01-09 | 2021-12-23 | 2022-01-28 | 2 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-09 | 2023-01-09 | 2021-12-23 | 2022-01-28 | 3 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-09 | 2023-01-09 | 2021-12-23 | 2022-01-28 | 4 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-09 | 2023-01-09 | 2021-12-23 | 2022-01-28 | 5 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-09 | 2023-01-09 | 2021-12-23 | 2022-01-28 | 10 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 232 | 89 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-09 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 20 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 58 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 30 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 232 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 40 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 232 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 50 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 24 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 60 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 12 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 70 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 32 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 80 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 90 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 100 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 110 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 120 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 130 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
2 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100061197 | ANOC Paint of DFA-16" brigde DFA-DFB. | Additional materials 1,6T leverblocks | PCNF | PCNF | 0 | 0 | Empty | 2023-01-09 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2021-12-23 | 2022-01-28 | 140 | PCNF | PCNF | DF /A /12/DFA-16-PHS-033-9009-BD-U | Additional materials 1,6T leverblocks | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-30 | 2019-02-06 | 2019-05-07 | 10 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-07-30 | 2019-02-06 | 2019-05-07 | 20 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-07-31 | 2019-02-06 | 2019-05-07 | 25 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-31 | 2024-08-01 | 2019-02-06 | 2019-05-07 | 30 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-02 | 2019-02-06 | 2019-05-07 | 40 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-02 | 2019-02-06 | 2019-05-07 | 50 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-03 | 2019-02-06 | 2019-05-07 | 60 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-03 | 2019-02-06 | 2019-05-07 | 70 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-04 | 2019-02-06 | 2019-05-07 | 80 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-04 | 2019-02-06 | 2019-05-07 | 90 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 9 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-07 | 2019-02-06 | 2019-05-07 | 95 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2019-02-06 | 2019-05-07 | 100 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-07 | 2019-02-06 | 2019-05-07 | 110 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025322 | CMAT:Changeout PM-3958 + A&B pumps | L3 Dismantle hoisting device |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2019-02-06 | 2019-05-07 | 120 |  |  | DF /F /75/DFFA-A-3957 | L3 Dismantle hoisting device | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 10 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 20 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 30 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 40 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-10-14 | 2021-01-12 | 50 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2020-10-14 | 2021-01-12 | 60 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2020-10-14 | 2021-01-12 | 70 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-10-14 | 2021-01-12 | 80 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-10-14 | 2021-01-12 | 90 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2020-10-14 | 2021-01-12 | 100 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038442 | DFG - Replace XCV 500472 Due to FFC | Remove Insulation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2020-10-14 | 2021-01-12 | 110 |  |  | DF /G /28/DFGA-XCV-500472 | Remove Insulation | Unknown
4 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200003724 | Epoxy changing facility | Service PO rental equipment |  |  | 0 | 0 | Empty | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2020-07-16 | 2021-03-13 | 10 |  |  | DF /C /86/FABRIC-MAINTENANCE | Service PO rental equipment | Unknown
4 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200003724 | Epoxy changing facility | Service PO rental equipment |  |  | 0 | 0 | Empty | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2020-07-16 | 2021-03-13 | 20 |  |  | DF /C /86/FABRIC-MAINTENANCE | Service PO rental equipment | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235711 | 4Y 380V E-SWB MAINT-DFBA-N-1831-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-24 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235711 | 4Y 380V E-SWB MAINT-DFBA-N-1831-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 8 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235711 | 4Y 380V E-SWB MAINT-DFBA-N-1831-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 30 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235711 | 4Y 380V E-SWB MAINT-DFBA-N-1831-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 40 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
4 | Empty | WDF | MTN-MECH | VEN-MECH | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 0 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-09-30 | 2023-09-30 | 2022-02-06 | 2022-07-06 | 10 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | MTN-PIPF | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 8 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-09-30 | 2023-10-01 | 2022-02-06 | 2022-07-06 | 20 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | PRODTECH | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 8 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-01 | 2023-10-02 | 2022-02-06 | 2022-07-06 | 30 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | MTN-PIPF | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 16 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-02 | 2023-10-03 | 2022-02-06 | 2022-07-06 | 40 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | INP-SITE | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 2 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-03 | 2023-10-03 | 2022-02-06 | 2022-07-06 | 50 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | MTN-PIPF | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 12 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-03 | 2023-10-03 | 2022-02-06 | 2022-07-06 | 60 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | MTN-PIPF | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 4 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-03 | 2023-10-04 | 2022-02-06 | 2022-07-06 | 70 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | PRODTECH | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 8 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-04 | 2023-10-05 | 2022-02-06 | 2022-07-06 | 80 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | Empty | WDF | MTN-MECH | MTN-PIPF | 2100059343 | FFSPR :DAN-2021-193 FCC on 3" spool | Prepare work area |  |  | 4 | 0 | Empty | 2023-09-30 | 2023-10-05 | 2023-10-05 | 2023-10-05 | 2022-02-06 | 2022-07-06 | 90 |  |  | DF /G /28/DFG-3-DOS-050-0168-AB-T | Prepare work area | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100042061 | DFA-A-3102 WI well 12 skuffe utæt | Replacement with spare drawer |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2021-03-23 | 2021-11-18 | 10 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100042061 | DFA-A-3102 WI well 12 skuffe utæt | Replacement with spare drawer |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2021-03-23 | 2021-11-18 | 20 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100042061 | DFA-A-3102 WI well 12 skuffe utæt | Replacement with spare drawer |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2021-03-23 | 2021-11-18 | 30 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100042061 | DFA-A-3102 WI well 12 skuffe utæt | Replacement with spare drawer |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2021-03-23 | 2021-11-18 | 40 |  |  | DF /A /07/DFAA-A-3102 | Replacement with spare drawer | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400352434 | 3Y FIRE DAMPER CHECK - DFE | RETURN TO OPERATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-10-23 | 10 | SECE | SECE | DF /E /09/FIRE-DAMPERS | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400352434 | 3Y FIRE DAMPER CHECK - DFE | RETURN TO OPERATION | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-10-23 | 20 | SECE | SECE | DF /E /09/FIRE-DAMPERS | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400352434 | 3Y FIRE DAMPER CHECK - DFE | RETURN TO OPERATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-22 | 2024-10-23 | 30 | SECE | SECE | DF /E /09/FIRE-DAMPERS | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400352434 | 3Y FIRE DAMPER CHECK - DFE | RETURN TO OPERATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-22 | 2024-10-23 | 40 | SECE | SECE | DF /E /09/FIRE-DAMPERS | RETURN TO OPERATION | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400337656 | 1Y ABB SCADA CHECK - DFA/B/C/E/F/G | ABB SCADA CHECK - DFA/B/C/E/F/G |  |  | 18 | 0 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-19 | 2024-07-18 | 2024-08-23 | 10 |  |  | DF /C /04/CONTROL-PANELS | ABB SCADA CHECK - DFA/B/C/E/F/G | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-RIGG | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-27 | 2024-02-12 | 2024-06-26 | 10 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | PRODTECH | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-27 | 2024-08-27 | 2024-02-12 | 2024-06-26 | 20 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-MECH | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-27 | 2024-08-28 | 2024-02-12 | 2024-06-26 | 30 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-RIGG | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 16 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-08-30 | 2024-02-12 | 2024-06-26 | 40 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-MECH | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-30 | 2024-08-31 | 2024-02-12 | 2024-06-26 | 50 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-RIGG | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 16 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-31 | 2024-09-02 | 2024-02-12 | 2024-06-26 | 60 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-MECH | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-02 | 2024-02-12 | 2024-06-26 | 70 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | PRODTECH | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2024-02-12 | 2024-06-26 | 80 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
3 | DFG-1740 | WDF | MTN-MECH | MTN-RIGG | 2100104506 | DFGA-MUF-1741 Cracks and hole in muffler | Prepare for rigging |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-12 | 2024-06-26 | 90 |  |  | DF /G /05/DFGA-MUF-1741 | Prepare for rigging | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400306662 | 4Y SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-12-07 | 2024-02-18 | 10 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400306662 | 4Y SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-12-07 | 2024-02-18 | 20 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400306662 | 4Y SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2023-12-07 | 2024-02-18 | 30 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400306662 | 4Y SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-12-07 | 2024-02-18 | 40 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400306662 | 4Y SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-12-07 | 2024-02-18 | 50 | SECE | SECE | DF /G /75/DFGA-A-3940 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-TURB | MTN-TURB | 2400343730 | Borescope Inspection and Wash | TURBINE WASH, COUNTER-DFFA-A-1630 | AWSC | AWSC | 8 | 0 | W33-W34 | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-16 | 2024-09-01 | 2024-09-11 | 10 | AWSC | AWSC | DF /F /60/DFFA-A-1630 | TURBINE WASH, COUNTER-DFFA-A-1630 | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100075275 | DFB LC HCV Broken handle | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2023-03-26 | 2025-09-11 | 10 |  |  | DF /B /37/DFBA-HCV-40122 | Rigging assist. Rig in/out | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100075275 | DFB LC HCV Broken handle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2023-03-26 | 2025-09-11 | 20 |  |  | DF /B /37/DFBA-HCV-40122 | Rigging assist. Rig in/out | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100075275 | DFB LC HCV Broken handle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2023-03-26 | 2025-09-11 | 30 |  |  | DF /B /37/DFBA-HCV-40122 | Rigging assist. Rig in/out | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100075275 | DFB LC HCV Broken handle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2023-03-26 | 2025-09-11 | 40 |  |  | DF /B /37/DFBA-HCV-40122 | Rigging assist. Rig in/out | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100075275 | DFB LC HCV Broken handle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2023-03-26 | 2025-09-11 | 50 |  |  | DF /B /37/DFBA-HCV-40122 | Rigging assist. Rig in/out | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100075275 | DFB LC HCV Broken handle | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2023-03-26 | 2025-09-11 | 60 |  |  | DF /B /37/DFBA-HCV-40122 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2018-04-29 | 2018-06-08 | 5 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2018-04-29 | 2018-06-08 | 10 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-07-31 | 2018-04-29 | 2018-06-08 | 20 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-31 | 2024-08-01 | 2018-04-29 | 2018-06-08 | 30 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-03 | 2018-04-29 | 2018-06-08 | 40 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-03 | 2018-04-29 | 2018-06-08 | 50 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-04 | 2018-04-29 | 2018-06-08 | 60 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2018-04-29 | 2018-06-08 | 70 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023697 | CMAT:DAN FC replacement of sealkit at va | L3-Inspection of materials |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2018-04-29 | 2018-06-08 | 80 |  |  | DF /C /51/DFCM-XCV-52213 | L3-Inspection of materials | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 2 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 2 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 4 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 1 | 2 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 25 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 27 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 5 | 0 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-08-31 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 4 | 0 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-08-31 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284228 | PSV Calibration - DFAA-PSV-392323 | Backload PSV for recalibration | AWSC | AWSC | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /A /75/DFAA-PSV-392323 | Backload PSV for recalibration | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-12-08 | 2023-04-22 | 10 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-12-08 | 2023-04-22 | 20 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2022-12-08 | 2023-04-22 | 30 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-27 | 2022-12-08 | 2023-04-22 | 40 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2022-12-08 | 2023-04-22 | 50 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2022-12-08 | 2023-04-22 | 60 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076710 | Batterier defekte | Isolate accordingly - LAUS work |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2022-12-08 | 2023-04-22 | 70 |  |  | DF /E /54/DFEY-AE-3551 | Isolate accordingly - LAUS work | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344064 | 3Y FIRE DAMPER CHECK LEVEL 1 - DFG | FIRE DAMPER CHECK LEVEL 1 - DFG | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 10 | SECE | SECE | DF /G /09/FIRE-DAMPERS | FIRE DAMPER CHECK LEVEL 1 - DFG | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344064 | 3Y FIRE DAMPER CHECK LEVEL 1 - DFG | FIRE DAMPER CHECK LEVEL 1 - DFG | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 20 | SECE | SECE | DF /G /09/FIRE-DAMPERS | FIRE DAMPER CHECK LEVEL 1 - DFG | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344064 | 3Y FIRE DAMPER CHECK LEVEL 1 - DFG | FIRE DAMPER CHECK LEVEL 1 - DFG | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 30 | SECE | SECE | DF /G /09/FIRE-DAMPERS | FIRE DAMPER CHECK LEVEL 1 - DFG | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344064 | 3Y FIRE DAMPER CHECK LEVEL 1 - DFG | FIRE DAMPER CHECK LEVEL 1 - DFG | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 40 | SECE | SECE | DF /G /09/FIRE-DAMPERS | FIRE DAMPER CHECK LEVEL 1 - DFG | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400344064 | 3Y FIRE DAMPER CHECK LEVEL 1 - DFG | FIRE DAMPER CHECK LEVEL 1 - DFG | SECE | SECE | 4 | 8 | W33-W34 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-07-23 | 2024-09-23 | 50 | SECE | SECE | DF /G /09/FIRE-DAMPERS | FIRE DAMPER CHECK LEVEL 1 - DFG | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322289 | DFF-28-GLS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DFE-OIL | WGN | MTN-INST | PRODTECH | 2200003056 | Slanger, rør og fittings efterspændes | Fittings, rør og slanger efterspændes i | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-07-21 | 2017-08-10 | 10 | AWSC | AWSC | DF /E /34/DFEZ-ESDV-45092 | Fittings, rør og slanger efterspændes i | Unknown
3 | DFE-OIL | WGN | MTN-INST | MTN-MECH | 2200003056 | Slanger, rør og fittings efterspændes | Fittings, rør og slanger efterspændes i | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2017-07-21 | 2017-08-10 | 20 | AWSC | AWSC | DF /E /34/DFEZ-ESDV-45092 | Fittings, rør og slanger efterspændes i | Unknown
3 | DFE-OIL | WGN | MTN-INST | PRODTECH | 2200003056 | Slanger, rør og fittings efterspændes | Fittings, rør og slanger efterspændes i | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2017-07-21 | 2017-08-10 | 30 | AWSC | AWSC | DF /E /34/DFEZ-ESDV-45092 | Fittings, rør og slanger efterspændes i | Unknown
D | NOSD | WPM | PRODTECH | PRODTECH | 2400337751 | PIGGING, P3002 10" DFB-GOC OIL 2W | P3002_DFB-GOC | AWSC | AWSC | 4 | 5 | Empty | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-15 | 2024-08-21 | 10 | AWSC | AWSC | DF /B /23/DFBY-PL-673002 | P3002_DFB-GOC | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057919 | Replace / repair floodlight 1903-37-L3E | De-isolate accordingly | SCH | SCH | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-11-22 | 2022-02-20 | 10 | SCH | SCH | DF /C /62/UPS-LIGHTING | De-isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057919 | Replace / repair floodlight 1903-37-L3E | De-isolate accordingly | SCH | SCH | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-11-22 | 2022-02-20 | 20 | SCH | SCH | DF /C /62/UPS-LIGHTING | De-isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100057919 | Replace / repair floodlight 1903-37-L3E | De-isolate accordingly | SCH | SCH | 6 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-11-22 | 2022-02-20 | 30 | SCH | SCH | DF /C /62/UPS-LIGHTING | De-isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057919 | Replace / repair floodlight 1903-37-L3E | De-isolate accordingly | SCH | SCH | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-11-22 | 2022-02-20 | 40 | SCH | SCH | DF /C /62/UPS-LIGHTING | De-isolate accordingly | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076856 | DFFW/78: Boom pivot assembly | Perform proof load test |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-15 | 2024-07-16 | 2022-12-09 | 2023-04-23 | 10 |  |  | DF /F /78/DFFA-A-6102 | Perform proof load test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100076856 | DFFW/78: Boom pivot assembly | Perform proof load test |  |  | 40 | 0 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-16 | 2024-07-19 | 2022-12-09 | 2023-04-23 | 20 |  |  | DF /F /78/DFFA-A-6102 | Perform proof load test | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076856 | DFFW/78: Boom pivot assembly | Perform proof load test |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-19 | 2024-07-20 | 2022-12-09 | 2023-04-23 | 30 |  |  | DF /F /78/DFFA-A-6102 | Perform proof load test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100076856 | DFFW/78: Boom pivot assembly | Perform proof load test |  |  | 16 | 0 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-20 | 2024-07-22 | 2022-12-09 | 2023-04-23 | 40 |  |  | DF /F /78/DFFA-A-6102 | Perform proof load test | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100076856 | DFFW/78: Boom pivot assembly | Perform proof load test |  |  | 18 | 0 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-22 | 2024-07-24 | 2022-12-09 | 2023-04-23 | 50 |  |  | DF /F /78/DFFA-A-6102 | Perform proof load test | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100076856 | DFFW/78: Boom pivot assembly | Perform proof load test |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-25 | 2024-07-22 | 2024-07-25 | 2022-12-09 | 2023-04-23 | 60 |  |  | DF /F /78/DFFA-A-6102 | Perform proof load test | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-PAIN | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-03-28 | 2024-03-28 | 2022-04-21 | 2022-09-18 | 10 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | VEN-MECH | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-03-28 | 2024-03-28 | 2022-04-21 | 2022-09-18 | 20 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | VEN-MECH | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-03-28 | 2024-03-28 | 2022-04-21 | 2022-09-18 | 30 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-SCAF | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 96 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-03-28 | 2024-04-08 | 2022-04-21 | 2022-09-18 | 40 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-ELEC | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 24 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-04-09 | 2024-04-14 | 2022-04-21 | 2022-09-18 | 50 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | VEN-ELEC | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 48 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-04-15 | 2024-04-17 | 2022-04-21 | 2022-09-18 | 55 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-MECH | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 24 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-04-17 | 2024-04-20 | 2022-04-21 | 2022-09-18 | 60 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-SCAF | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 32 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-04-20 | 2024-04-24 | 2022-04-21 | 2022-09-18 | 70 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-PAIN | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 288 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-04-24 | 2024-05-04 | 2022-04-21 | 2022-09-18 | 80 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-MECH | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 32 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-05-04 | 2024-05-08 | 2022-04-21 | 2022-09-18 | 90 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-MECH | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 24 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-05-08 | 2024-05-11 | 2022-04-21 | 2022-09-18 | 100 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-SCAF | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 72 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-05-11 | 2024-05-20 | 2022-04-21 | 2022-09-18 | 110 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-PAIN | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 72 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-05-20 | 2024-05-28 | 2022-04-21 | 2022-09-18 | 120 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-SCAF | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 32 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-05-28 | 2024-06-01 | 2022-04-21 | 2022-09-18 | 130 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | MTN-ELEC | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 8 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-06-01 | 2024-06-03 | 2022-04-21 | 2022-09-18 | 140 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | VEN-ELEC | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-04-21 | 2022-09-18 | 160 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
4 | DFF-TSEP | WGN | MTN-MECH | VEN-MECH | 2200009679 | ANOV Rep PVI DFFA-V-3403 test separator | MATRIALER |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-04-21 | 2022-09-18 | 170 |  |  | DF /F /11/DFFA-V-3403 | MATRIALER | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-22 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-05-24 | 2024-05-24 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-05-24 | 2024-05-24 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-05-24 | 2024-05-24 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-20 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-20 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284230 | PSV Calibration - DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-05-21 | 2024-08-22 | 2024-08-19 | 2024-08-19 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /51/DFBA-PSV-35372 | DFBA-PSV-35372 Offshore from WS Måde | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2020-12-16 | 2022-08-06 | 2020-11-10 | 2020-11-10 | 2019-10-12 | 2020-01-10 | 10 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 17.399999999999998578914528472 | 5 | Empty | 2020-12-16 | 2022-08-06 | 2020-08-20 | 2020-09-01 | 2019-10-12 | 2020-01-10 | 20 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 5 | 0 | Empty | 2020-12-16 | 2022-08-06 | 2021-01-07 | 2021-01-07 | 2019-10-12 | 2020-01-10 | 30 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 0.6999999999999999555910790147 | 10 | Empty | 2020-12-16 | 2022-08-06 | 2020-12-17 | 2021-02-01 | 2019-10-12 | 2020-01-10 | 40 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 13.400000000000000355271367876 | 0 | Empty | 2020-12-16 | 2022-08-06 | 2022-08-05 | 2022-08-06 | 2019-10-12 | 2020-01-10 | 50 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 0.6999999999999999555910790147 | 0 | Empty | 2020-12-16 | 2022-08-06 | 2022-08-06 | 2022-08-06 | 2019-10-12 | 2020-01-10 | 60 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002944 | Insulation assists FORCE 15926 | L3 permit prep | PCNF | PCNF | 0 | 0 | Empty | 2020-12-16 | 2022-08-06 | 2021-01-07 | 2021-01-07 | 2019-10-12 | 2020-01-10 | 70 | PCNF | PCNF | DF /G /32/DFG-26-GPS-043-0009-DD-A | L3 permit prep | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 3 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-09 | 2024-11-10 | 2023-04-09 | 2025-09-25 | 10 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 8 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-10 | 2024-11-12 | 2023-04-09 | 2025-09-25 | 20 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 2 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-12 | 2024-11-12 | 2023-04-09 | 2025-09-25 | 30 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 2 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-12 | 2024-11-13 | 2023-04-09 | 2025-09-25 | 40 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 2 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-13 | 2024-11-13 | 2023-04-09 | 2025-09-25 | 50 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 2 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-13 | 2024-11-14 | 2023-04-09 | 2025-09-25 | 60 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 4 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-14 | 2024-11-15 | 2023-04-09 | 2025-09-25 | 70 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100077103 | DFF - Machine Flange on HCV-530136. | Isolate HCV 530136 |  |  | 0 | 0 | Empty | 2024-11-09 | 2024-11-15 | 2024-11-15 | 2024-11-15 | 2023-04-09 | 2025-09-25 | 80 |  |  | DF /F /76/DFFA-HCV-530136 | Isolate HCV 530136 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100070409 | DFC: Replace eye bolts on exhaust | Isolation/deisolation of crane |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-12-20 | 2025-06-07 | 10 |  |  | DF /C /78/DFCI-X-6101 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100070409 | DFC: Replace eye bolts on exhaust | Isolation/deisolation of crane |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2022-12-20 | 2025-06-07 | 20 |  |  | DF /C /78/DFCI-X-6101 | Isolation/deisolation of crane | Unknown
D | Empty | WPM | PRODTECH | MTN-MECH | 2400342617 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 0 | 0 | Empty | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-08-26 | 2024-09-01 | 1 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400342617 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 4 | 8 | Empty | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-08-26 | 2024-09-01 | 2 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029891 | DFCM-P-3661 AUX LUBE OIL PUMP Electrical | Isolate AUX LUBE OIL PUMP DFCM-PM-3661 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-06-09 | 2020-11-06 | 10 |  |  | DF /C /23/DFCM-P-3661 | Isolate AUX LUBE OIL PUMP DFCM-PM-3661 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029891 | DFCM-P-3661 AUX LUBE OIL PUMP Electrical | Isolate AUX LUBE OIL PUMP DFCM-PM-3661 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2020-06-09 | 2020-11-06 | 20 |  |  | DF /C /23/DFCM-P-3661 | Isolate AUX LUBE OIL PUMP DFCM-PM-3661 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029891 | DFCM-P-3661 AUX LUBE OIL PUMP Electrical | Isolate AUX LUBE OIL PUMP DFCM-PM-3661 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2020-06-09 | 2020-11-06 | 30 |  |  | DF /C /23/DFCM-P-3661 | Isolate AUX LUBE OIL PUMP DFCM-PM-3661 | Unknown
1 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013157 | Scaffold for 3D survey - AOGV tool | Erect scaff DFF Level 1 | PCNF | PCNF | 0 | 0 | Empty | 2023-01-31 | 2023-02-05 | 2023-01-31 | 2023-01-31 | 2023-01-31 | 2023-02-15 | 10 | PCNF | PCNF | DF /C /28/DFCM-V-5002 | Erect scaff DFF Level 1 | Unknown
1 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013157 | Scaffold for 3D survey - AOGV tool | Erect scaff DFF Level 1 | PCNF | PCNF | 16 | 26 | Empty | 2023-01-31 | 2023-02-05 | 2023-01-31 | 2023-02-02 | 2023-01-31 | 2023-02-15 | 20 | PCNF | PCNF | DF /C /28/DFCM-V-5002 | Erect scaff DFF Level 1 | Unknown
1 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013157 | Scaffold for 3D survey - AOGV tool | Erect scaff DFF Level 1 | PCNF | PCNF | 6 | 16 | Empty | 2023-01-31 | 2023-02-05 | 2023-02-02 | 2023-02-02 | 2023-01-31 | 2023-02-15 | 30 | PCNF | PCNF | DF /C /28/DFCM-V-5002 | Erect scaff DFF Level 1 | Unknown
1 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013157 | Scaffold for 3D survey - AOGV tool | Erect scaff DFF Level 1 | PCNF | PCNF | 18 | 26 | Empty | 2023-01-31 | 2023-02-05 | 2023-02-02 | 2023-02-04 | 2023-01-31 | 2023-02-15 | 40 | PCNF | PCNF | DF /C /28/DFCM-V-5002 | Erect scaff DFF Level 1 | Unknown
1 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013157 | Scaffold for 3D survey - AOGV tool | Erect scaff DFF Level 1 | PCNF | PCNF | 12 | 6 | Empty | 2023-01-31 | 2023-02-05 | 2023-02-04 | 2023-02-05 | 2023-01-31 | 2023-02-15 | 50 | PCNF | PCNF | DF /C /28/DFCM-V-5002 | Erect scaff DFF Level 1 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100104212 | HCV Gear broken | Rigger assistance |  |  | 6 | 0 | Empty | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2026-11-26 | 10 |  |  | DF /B /54 | Rigger assistance | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100104212 | HCV Gear broken | Rigger assistance |  |  | 3 | 0 | Empty | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2026-11-26 | 20 |  |  | DF /B /54 | Rigger assistance | Unknown
4 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100104212 | HCV Gear broken | Rigger assistance |  |  | 8 | 0 | Empty | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2026-11-26 | 30 |  |  | DF /B /54 | Rigger assistance | Unknown
4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100104212 | HCV Gear broken | Rigger assistance |  |  | 10 | 0 | Empty | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2026-11-26 | 40 |  |  | DF /B /54 | Rigger assistance | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100104212 | HCV Gear broken | Rigger assistance |  |  | 3 | 0 | Empty | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2026-11-26 | 50 |  |  | DF /B /54 | Rigger assistance | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100104212 | HCV Gear broken | Rigger assistance |  |  | 0 | 0 | Empty | 2024-06-09 | 2024-06-10 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2026-11-26 | 60 |  |  | DF /B /54 | Rigger assistance | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-22 | 2024-09-22 | 2022-05-02 | 2023-02-26 | 10 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-22 | 2024-09-23 | 2022-05-02 | 2023-02-26 | 20 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-23 | 2024-09-23 | 2022-05-02 | 2023-02-26 | 30 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-23 | 2024-09-25 | 2022-05-02 | 2023-02-26 | 40 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-23 | 2024-09-24 | 2022-05-02 | 2023-02-26 | 50 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-23 | 2024-09-24 | 2022-05-02 | 2023-02-26 | 60 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-25 | 2024-09-25 | 2022-05-02 | 2023-02-26 | 70 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-12-24 | 2024-12-24 | 2022-05-02 | 2023-02-26 | 80 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-12-24 | 2024-12-26 | 2022-05-02 | 2023-02-26 | 90 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-12-24 | 2024-12-26 | 2022-05-02 | 2023-02-26 | 100 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-12-24 | 2024-12-26 | 2022-05-02 | 2023-02-26 | 110 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-12-26 | 2024-12-27 | 2022-05-02 | 2023-02-26 | 120 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2022-05-02 | 2023-02-26 | 130 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-22 | 2024-09-22 | 2022-05-02 | 2023-02-26 | 140 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058383 | DFFA-P-3910 METHANOL PUMP Onshore for ov | Rigger assistance Survey/prep hoist etc |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-12-27 | 2024-09-22 | 2024-09-22 | 2022-05-02 | 2023-02-26 | 150 |  |  | DF /F /75/DFFA-P-3910 | Rigger assistance Survey/prep hoist etc | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-03 | 2022-03-28 | 2022-11-23 | 10 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-03 | 2024-07-03 | 2022-03-28 | 2022-11-23 | 20 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-RIGG | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 24 | 24 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-04 | 2024-07-06 | 2022-03-28 | 2022-11-23 | 30 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 5 | 6 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-07 | 2024-07-08 | 2022-03-28 | 2022-11-23 | 40 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 0 | 3 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-08 | 2024-07-08 | 2022-03-28 | 2022-11-23 | 50 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-RIGG | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 12 | 12 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-08 | 2024-07-09 | 2022-03-28 | 2022-11-23 | 60 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-09 | 2024-07-10 | 2022-03-28 | 2022-11-23 | 70 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 5 | 4 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-10 | 2024-07-11 | 2022-03-28 | 2022-11-23 | 80 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | PRODTECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-11 | 2024-07-12 | 2022-03-28 | 2022-11-23 | 90 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-ELEC | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-12 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 100 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-LAGG | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 110 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 0 | 0 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 120 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
4 | HD-DANWI | WGN | MTN-MECH | MTN-MECH | 2200008919 | Exchange DFFA-PSV-351033 - PSV 2023 | DFFA-PSV-351033 Offshore from WS Måde | SCH | SCH | 0 | 2 | W27-W28 | 2024-07-03 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2022-03-28 | 2022-11-23 | 130 | SCH | SCH | DF /F /54/DFFA-PSV-351033 | DFFA-PSV-351033 Offshore from WS Måde | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003034 | Isolation assist to FORCE 14237 | L3 Create permit. | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-20 | 2020-09-01 | 2018-12-28 | 2019-03-28 | 10 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0302-AD-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003034 | Isolation assist to FORCE 14237 | L3 Create permit. | PCNF | PCNF | 10.099999999999999644728632116 | 15 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-14 | 2020-08-22 | 2018-12-28 | 2019-03-28 | 20 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0302-AD-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003034 | Isolation assist to FORCE 14237 | L3 Create permit. | PCNF | PCNF | 5 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-28 | 2019-03-28 | 40 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0302-AD-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003034 | Isolation assist to FORCE 14237 | L3 Create permit. | PCNF | PCNF | 6.700000000000000177635683938 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-28 | 2019-03-28 | 50 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0302-AD-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003034 | Isolation assist to FORCE 14237 | L3 Create permit. | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2018-12-28 | 2019-03-28 | 60 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0302-AD-F | L3 Create permit. | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400230366 | 6M GAS CHROMTOGRPH-FISCAL-DFCI-FP-371 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | SCH | SCH | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-29 | 2023-02-17 | 10 | SCH | SCH | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
C | NOSD | WPM | MTN-INST | PRODLABO | 2400230366 | 6M GAS CHROMTOGRPH-FISCAL-DFCI-FP-371 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | SCH | SCH | 1.5 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-29 | 2023-02-17 | 20 | SCH | SCH | DF /C /34/DFCI-FP-3716 | GAS CHROMTOGRPH-FISCAL-DFCI-FP-3716 | Unknown
4 | DFE-3551 | WGN | MTN-MECH | PRODTECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | PRODTECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | MTN-RIGG | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-25 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | MTN-MECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-26 | 2024-09-27 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | MTN-MECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-27 | 2024-09-27 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | MTN-RIGG | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-27 | 2024-09-28 | 2023-06-03 | 2025-11-19 | 60 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | PRODTECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-28 | 2024-09-29 | 2023-06-03 | 2025-11-19 | 70 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | MTN-MECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2023-06-03 | 2025-11-19 | 80 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | PRODTECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2023-06-03 | 2025-11-19 | 90 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
4 | DFE-3551 | WGN | MTN-MECH | MTN-MECH | 2200012617 | DFAA-PSV-35691 - PSV 2023 | new psv |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2023-06-03 | 2025-11-19 | 100 |  |  | DF /A /55/DFAA-PSV-35691 | new psv | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232986 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-04 | PO Cetec | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-12-01 | 2023-02-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-04 | PO Cetec | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232986 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-04 | PO Cetec | AWSC | AWSC | 7 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-04 | PO Cetec | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232986 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-04 | PO Cetec | AWSC | AWSC | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-04 | PO Cetec | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232986 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-04 | PO Cetec | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-04 | PO Cetec | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400232986 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-04 | PO Cetec | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-12-01 | 2023-02-27 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-04 | PO Cetec | Unknown
3 | DFF-O34 | WDF | MTN-MECH | PRODTECH | 2100028057 | Tighten stuffing box FCV-290134 | L3 Tighten stuffing box | AWSC | AWSC | 4 | 0 | W37-38 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2019-07-22 | 2019-08-31 | 10 | AWSC | AWSC | DF /F /37/DFFA-FCV-290134 | L3 Tighten stuffing box | Unknown
3 | DFF-O34 | WDF | MTN-MECH | MTN-MECH | 2100028057 | Tighten stuffing box FCV-290134 | L3 Tighten stuffing box | AWSC | AWSC | 3 | 0 | W37-38 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2019-07-22 | 2019-08-31 | 20 | AWSC | AWSC | DF /F /37/DFFA-FCV-290134 | L3 Tighten stuffing box | Unknown
3 | DFF-O34 | WDF | MTN-MECH | PRODTECH | 2100028057 | Tighten stuffing box FCV-290134 | L3 Tighten stuffing box | AWSC | AWSC | 4 | 0 | W37-38 | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2019-07-22 | 2019-08-31 | 30 | AWSC | AWSC | DF /F /37/DFFA-FCV-290134 | L3 Tighten stuffing box | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061171 | Gaskets chlorite quill must be changed | Gaskets chlorite quill must be changed |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-01-10 | 2022-04-10 | 10 |  |  | DF /G /75/DFGA-HCV-553006 | Gaskets chlorite quill must be changed | Unknown
3 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100061171 | Gaskets chlorite quill must be changed | Gaskets chlorite quill must be changed |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-01-10 | 2022-04-10 | 20 |  |  | DF /G /75/DFGA-HCV-553006 | Gaskets chlorite quill must be changed | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061171 | Gaskets chlorite quill must be changed | Gaskets chlorite quill must be changed |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-01-10 | 2022-04-10 | 30 |  |  | DF /G /75/DFGA-HCV-553006 | Gaskets chlorite quill must be changed | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100061171 | Gaskets chlorite quill must be changed | Gaskets chlorite quill must be changed |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-01-10 | 2022-04-10 | 40 |  |  | DF /G /75/DFGA-HCV-553006 | Gaskets chlorite quill must be changed | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235581 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829A | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1829A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235581 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829A | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1829A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235581 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829A | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1829A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235581 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829A | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1829A | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-15 | 2020-11-10 | 2021-04-09 | 10 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-15 | 2020-11-10 | 2021-04-09 | 20 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-17 | 2020-11-10 | 2021-04-09 | 25 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-15 | 2020-11-10 | 2021-04-09 | 30 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 36 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-16 | 2024-07-18 | 2020-11-10 | 2021-04-09 | 40 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 8 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-19 | 2024-07-19 | 2020-11-10 | 2021-04-09 | 50 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 8 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-20 | 2024-07-20 | 2020-11-10 | 2021-04-09 | 51 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-20 | 2024-07-22 | 2020-11-10 | 2021-04-09 | 60 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-22 | 2024-07-23 | 2020-11-10 | 2021-04-09 | 70 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-24 | 2024-07-26 | 2020-11-10 | 2021-04-09 | 80 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-26 | 2024-07-26 | 2020-11-10 | 2021-04-09 | 90 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-26 | 2024-07-27 | 2020-11-10 | 2021-04-09 | 100 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 18 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-27 | 2024-07-29 | 2020-11-10 | 2021-04-09 | 110 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 20 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-27 | 2024-07-29 | 2020-11-10 | 2021-04-09 | 111 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036819 | DFFW/78: Replace whip winch | Function check: Measure winch speed up/d |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-11-10 | 2021-04-09 | 120 |  |  | DF /F /78/DFFA-A-6102 | Function check: Measure winch speed up/d | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100037391 | Intern lækage i hyd-blok til XCV-50421 S | Demount solenoid valve |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2020-09-11 | 2020-10-21 | 10 |  |  | DF /C /27/DFCI-XCV-50421 | Demount solenoid valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100037391 | Intern lækage i hyd-blok til XCV-50421 S | Demount solenoid valve |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-09-11 | 2020-10-21 | 20 |  |  | DF /C /27/DFCI-XCV-50421 | Demount solenoid valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100037391 | Intern lækage i hyd-blok til XCV-50421 S | Demount solenoid valve |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-09-11 | 2020-10-21 | 30 |  |  | DF /C /27/DFCI-XCV-50421 | Demount solenoid valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100037391 | Intern lækage i hyd-blok til XCV-50421 S | Demount solenoid valve |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2020-09-11 | 2020-10-21 | 40 |  |  | DF /C /27/DFCI-XCV-50421 | Demount solenoid valve | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322233 | DFB-75-CI-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 7 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337663 | 6M H2S SCAV PUMP SKID MAINT-DFFA-A-7601 | H2S SCAV PUMP SKID MAINT-DFFA-A-7601 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-02 | 2024-08-21 | 10 |  |  | DF /F /75/DFFA-A-7601 | H2S SCAV PUMP SKID MAINT-DFFA-A-7601 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000661 | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-01-01 | 2020-12-31 | 10 |  |  | DF /C | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000661 | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-01-01 | 2020-12-31 | 20 |  |  | DF /C | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000661 | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-01-01 | 2020-12-31 | 30 |  |  | DF /C | DK46 MATCON, OQ,TEGN MATERIAL ORDER 2020 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-MECH | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-10 | 2022-02-07 | 2022-07-07 | 25 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-10 | 2024-01-11 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-11 | 2024-01-14 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-14 | 2024-01-15 | 2022-02-07 | 2022-07-07 | 45 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-19 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-19 | 2024-01-21 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-MECH | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-21 | 2024-01-22 | 2022-02-07 | 2022-07-07 | 65 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009373 | Insulation assist FORCE 19492 | Remove grating |  |  | 3 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-22 | 2024-01-23 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /F /28/DFF-4-DO-050-8015-AB-T | Remove grating | Unknown
2 | SIWL | WDF | MTN-MECH | PRODTECH | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-09-22 | 2024-09-22 | 2022-11-23 | 2023-01-07 | 10 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-09-22 | 2024-09-24 | 2022-11-23 | 2023-01-07 | 20 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 15 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-09-24 | 2024-09-26 | 2022-11-23 | 2023-01-07 | 30 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-09-24 | 2024-09-25 | 2022-11-23 | 2023-01-07 | 40 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-09-26 | 2024-09-27 | 2022-11-23 | 2023-01-07 | 50 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-11-26 | 2024-11-26 | 2022-11-23 | 2023-01-07 | 60 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 15 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-11-26 | 2024-11-28 | 2022-11-23 | 2023-01-07 | 70 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-11-26 | 2024-11-27 | 2022-11-23 | 2023-01-07 | 80 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | PRODTECH | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-11-28 | 2024-11-29 | 2022-11-23 | 2023-01-07 | 90 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100078392 | DFA-11 choke CVA-30011 | Rig-down for removal DFAA-CVA-30005 |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-11-30 | 2024-11-29 | 2024-11-30 | 2022-11-23 | 2023-01-07 | 100 |  |  | DF /A /55/DFAA-CVA-30011 | Rig-down for removal DFAA-CVA-30005 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085362 | Battery fault on emergency light | Change batteries |  |  | 1 | 1 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-03-30 | 2023-08-12 | 10 |  |  | DF /C /05/DFCI-DP-1824 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085362 | Battery fault on emergency light | Change batteries |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-03-30 | 2023-08-12 | 20 |  |  | DF /C /05/DFCI-DP-1824 | Change batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085362 | Battery fault on emergency light | Change batteries |  |  | 1 | 1 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-03-30 | 2023-08-12 | 30 |  |  | DF /C /05/DFCI-DP-1824 | Change batteries | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400221597 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-11-01 | 2023-01-28 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-05 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221597 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 19 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-11-01 | 2023-01-28 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-05 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400221597 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2022-11-01 | 2023-01-28 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-05 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400221597 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-11-01 | 2023-01-28 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-05 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400221597 | 4Y 3KV N-SWB MAINT-DFFA-N-1801A-05 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | W41-42 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-11-01 | 2023-01-28 | 60 | AWSC | AWSC | DF /F /61/DFFA-N-1801A-05 | ISOLATION ELECTRICAL | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042839 | Deluge DFF leaking pilot valve xv-035205 | replace/repair pilot valve | SCHSECE | SCHSECE | 2 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2021-03-03 | 2021-07-31 | 10 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035205 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042839 | Deluge DFF leaking pilot valve xv-035205 | replace/repair pilot valve | SCHSECE | SCHSECE | 8 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-24 | 2021-03-03 | 2021-07-31 | 20 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035205 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042839 | Deluge DFF leaking pilot valve xv-035205 | replace/repair pilot valve | SCHSECE | SCHSECE | 2 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2021-03-03 | 2021-07-31 | 30 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035205 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042839 | Deluge DFF leaking pilot valve xv-035205 | replace/repair pilot valve | SCHSECE | SCHSECE | 0 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2021-03-03 | 2021-07-31 | 40 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035205 | replace/repair pilot valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 20 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-06 | 2023-10-19 | 2024-03-02 | 10 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-13 | 2023-10-19 | 2024-03-02 | 20 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-14 | 2023-10-19 | 2024-03-02 | 30 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 6 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-14 | 2024-07-15 | 2023-10-19 | 2024-03-02 | 40 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 8 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 50 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 2 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 60 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 70 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 10 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-10-19 | 2024-03-02 | 80 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097582 | LB1 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 0 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-05 | 2023-10-19 | 2024-03-02 | 90 | AWSC | AWSC | DF /C /02/DFCI-X-0701 | Denso tape to cover greased thread | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400298224 | 6M POT WATER MAKER SKID MAINT-A-1027/37 | POT WATER MAKER SKID MAINT-A-1027/37 | SCH | SCH | 9 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-12-22 | 2024-01-10 | 10 | SCH | SCH | DF /C /85/DFCM-A-1027 | POT WATER MAKER SKID MAINT-A-1027/37 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025171 | Change strainer DFGA-S-5003 | L3 test and clean |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-03-22 | 2019-06-20 | 10 |  |  | DF /G /28/DFGA-S-5003 | L3 test and clean | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025171 | Change strainer DFGA-S-5003 | L3 test and clean |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-03-22 | 2019-06-20 | 20 |  |  | DF /G /28/DFGA-S-5003 | L3 test and clean | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025171 | Change strainer DFGA-S-5003 | L3 test and clean |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2019-03-22 | 2019-06-20 | 30 |  |  | DF /G /28/DFGA-S-5003 | L3 test and clean | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025171 | Change strainer DFGA-S-5003 | L3 test and clean |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2019-03-22 | 2019-06-20 | 40 |  |  | DF /G /28/DFGA-S-5003 | L3 test and clean | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322309 | DFG-53-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /53/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2023-06-21 | 2025-12-07 | 10 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2023-06-21 | 2025-12-07 | 20 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-24 | 2023-06-21 | 2025-12-07 | 30 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-24 | 2024-09-24 | 2023-06-21 | 2025-12-07 | 35 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-24 | 2024-09-26 | 2023-06-21 | 2025-12-07 | 40 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-26 | 2024-09-29 | 2023-06-21 | 2025-12-07 | 60 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-29 | 2024-09-29 | 2023-06-21 | 2025-12-07 | 70 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-29 | 2024-10-01 | 2023-06-21 | 2025-12-07 | 80 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-01 | 2024-10-01 | 2023-06-21 | 2025-12-07 | 90 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-02 | 2024-10-02 | 2023-06-21 | 2025-12-07 | 100 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-02 | 2024-10-03 | 2023-06-21 | 2025-12-07 | 110 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-06-21 | 2025-12-07 | 120 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-06-21 | 2025-12-07 | 130 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080290 | DP-1854 heat trace to circut Q17 defect. | DP-1854 heat trace to circut Q17 defect | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-06-21 | 2025-12-07 | 140 | AWSC | AWSC | DF /G /61/DFGA-DP-1854-17 | DP-1854 heat trace to circut Q17 defect | Unknown
1 | NOSD | WGN | MTN-PAIN | WELLSUPV | 2200016363 | IRP ID 114258 supports | PO EMS | SECE | SECE | 0 | 0 | Empty | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-24 | 10 | SECE | SECE | DF /C /10/DFC-6-PT-033-0003-C2-U | PO EMS | Unknown
1 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200016363 | IRP ID 114258 supports | PO EMS | SECE | SECE | 0 | 0 | Empty | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2023-11-24 | 20 | SECE | SECE | DF /C /10/DFC-6-PT-033-0003-C2-U | PO EMS | Unknown
2 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100102204 | DFG-FT-350911 spurious failure | Troubleshooting | PCNF | PCNF | 4 | 12 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-19 | 2023-12-03 | 2023-11-19 | 2023-12-04 | 10 | PCNF | PCNF | DF /G /54/DFGA-FIT-350911 | Troubleshooting | Unknown
2 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100102204 | DFG-FT-350911 spurious failure | Troubleshooting | PCNF | PCNF | 12 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-19 | 2023-12-04 | 20 | PCNF | PCNF | DF /G /54/DFGA-FIT-350911 | Troubleshooting | Unknown
2 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100102204 | DFG-FT-350911 spurious failure | Troubleshooting | PCNF | PCNF | 12 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-19 | 2023-12-04 | 30 | PCNF | PCNF | DF /G /54/DFGA-FIT-350911 | Troubleshooting | Unknown
A | DFGHPSEP | WPM | MTN-MECH | PRODTECH | 2400222494 | 1Y SDV LUBE/FUNC TEST HPSEP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-01-04 | 2023-02-03 | 10 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFGHPSEP | WPM | MTN-MECH | MTN-MECH | 2400222494 | 1Y SDV LUBE/FUNC TEST HPSEP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-25 | 2023-01-04 | 2023-02-03 | 20 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFGHPSEP | WPM | MTN-MECH | MTN-INST | 2400222494 | 1Y SDV LUBE/FUNC TEST HPSEP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2023-01-04 | 2023-02-03 | 30 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFGHPSEP | WPM | MTN-MECH | PRODTECH | 2400222494 | 1Y SDV LUBE/FUNC TEST HPSEP - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-01-04 | 2023-02-03 | 40 | SECE | SECE | DF /G /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400302340 | 1Y LP HYDRCY PUMP SKID MAINT-DFFA-A-5003 | ISOLATON BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2024-01-06 | 2024-02-05 | 10 | SECE | SECE | DF /F /27/DFFA-A-5003 | ISOLATON BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302340 | 1Y LP HYDRCY PUMP SKID MAINT-DFFA-A-5003 | ISOLATON BY PRODUCTION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-13 | 2024-01-06 | 2024-02-05 | 20 | SECE | SECE | DF /F /27/DFFA-A-5003 | ISOLATON BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400302340 | 1Y LP HYDRCY PUMP SKID MAINT-DFFA-A-5003 | ISOLATON BY PRODUCTION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-13 | 2024-08-14 | 2024-01-06 | 2024-02-05 | 30 | SECE | SECE | DF /F /27/DFFA-A-5003 | ISOLATON BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400302340 | 1Y LP HYDRCY PUMP SKID MAINT-DFFA-A-5003 | ISOLATON BY PRODUCTION | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-16 | 2024-01-06 | 2024-02-05 | 40 | SECE | SECE | DF /F /27/DFFA-A-5003 | ISOLATON BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400302340 | 1Y LP HYDRCY PUMP SKID MAINT-DFFA-A-5003 | ISOLATON BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-16 | 2024-08-16 | 2024-01-06 | 2024-02-05 | 50 | SECE | SECE | DF /F /27/DFFA-A-5003 | ISOLATON BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086696 | Replace floodlight DFCI-LN-1903-26-L1B | Isolate and prove dead |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-04-17 | 2023-08-30 | 10 |  |  | DF /C /62 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100086696 | Replace floodlight DFCI-LN-1903-26-L1B | Isolate and prove dead |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-04-17 | 2023-08-30 | 20 |  |  | DF /C /62 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086696 | Replace floodlight DFCI-LN-1903-26-L1B | Isolate and prove dead |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-04-17 | 2023-08-30 | 30 |  |  | DF /C /62 | Isolate and prove dead | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341919 | DFG_1Y_22000 INT STRUCT INSP - GVI | DFG_1Y_22000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/EL_22000 (LEVEL1) | DFG_1Y_22000 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029897 | Troubleshoot on small power | Test after fix | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2020-06-09 | 2020-11-06 | 10 | PCNF | PCNF | DF /F /61/DFFA-N-1802B-7-5 | Test after fix | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029897 | Troubleshoot on small power | Test after fix | PCNF | PCNF | 4 | 16 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2020-06-09 | 2020-11-06 | 20 | PCNF | PCNF | DF /F /61/DFFA-N-1802B-7-5 | Test after fix | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100029897 | Troubleshoot on small power | Test after fix | PCNF | PCNF | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2020-06-09 | 2020-11-06 | 30 | PCNF | PCNF | DF /F /61/DFFA-N-1802B-7-5 | Test after fix | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 8 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-23 | 2023-01-25 | 2019-06-02 | 2019-06-22 | 10 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-ROPE | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 8 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-23 | 2023-01-25 | 2019-06-02 | 2019-06-22 | 20 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PIPF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 8 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-24 | 2023-01-25 | 2019-06-02 | 2019-06-22 | 30 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 30.19999999999999928945726423 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-25 | 2023-01-28 | 2019-06-02 | 2019-06-22 | 40 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-ROPE | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 8 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-28 | 2023-01-29 | 2019-06-02 | 2019-06-22 | 50 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PIPF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 4 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-29 | 2023-01-29 | 2019-06-02 | 2019-06-22 | 60 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PIPF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 4 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-29 | 2023-01-29 | 2019-06-02 | 2019-06-22 | 70 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PIPF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 4 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-29 | 2023-01-29 | 2019-06-02 | 2019-06-22 | 80 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PIPF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-29 | 2023-01-29 | 2019-06-02 | 2019-06-22 | 90 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | QAQCELEC | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 2 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-29 | 2023-01-30 | 2019-06-02 | 2019-06-22 | 100 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-ROPE | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 6 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-30 | 2023-01-30 | 2019-06-02 | 2019-06-22 | 110 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 24.100000000000001421085471515 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-30 | 2023-02-01 | 2019-06-02 | 2019-06-22 | 120 |  |  | DF | L3 Permit - Scaffold | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-ROPE | 2100022928 | Well 13 Inspection of springsupport | L3 Permit - Scaffold |  |  | 16.100000000000001421085471515 | 0 | Empty | 2023-01-23 | 2023-02-01 | 2023-01-23 | 2023-01-24 | 2019-06-02 | 2019-06-22 | 170 |  |  | DF | L3 Permit - Scaffold | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322660 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-16 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-03-16 | 2024-05-17 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-16 | ATEX EQUIPMENT INSPECTION | Unknown
4 | D-GASTYE | WDF | MTN-MECH | PRODTECH | 2100032278 | DFB NOGAT Riser lækage v HCV v PIer | Remove old Valve |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2020-08-10 | 2021-01-07 | 10 |  |  | DF /B /34/DFB-12-GP-038-0811-XX-U | Remove old Valve | Unknown
4 | D-GASTYE | WDF | MTN-MECH | MTN-MECH | 2100032278 | DFB NOGAT Riser lækage v HCV v PIer | Remove old Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2020-08-10 | 2021-01-07 | 20 |  |  | DF /B /34/DFB-12-GP-038-0811-XX-U | Remove old Valve | Unknown
4 | D-GASTYE | WDF | MTN-MECH | MTN-MECH | 2100032278 | DFB NOGAT Riser lækage v HCV v PIer | Remove old Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2020-08-10 | 2021-01-07 | 30 |  |  | DF /B /34/DFB-12-GP-038-0811-XX-U | Remove old Valve | Unknown
4 | D-GASTYE | WDF | MTN-MECH | MTN-MECH | 2100032278 | DFB NOGAT Riser lækage v HCV v PIer | Remove old Valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2020-08-10 | 2021-01-07 | 40 |  |  | DF /B /34/DFB-12-GP-038-0811-XX-U | Remove old Valve | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329444 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-06-02 | 2024-06-08 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-12 | 1 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329444 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-06-02 | 2024-06-08 | 2024-06-02 | 2024-06-02 | 2024-06-02 | 2024-06-12 | 9 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329444 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-06-02 | 2024-06-08 | 2024-06-02 | 2024-06-05 | 2024-06-02 | 2024-06-12 | 10 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400329444 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-06-02 | 2024-06-08 | 2024-06-05 | 2024-06-08 | 2024-06-02 | 2024-06-12 | 12 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329444 | 3M SANDCYKLON | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 2 | 0 | Empty | 2024-06-02 | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-06-02 | 2024-06-12 | 14 |  |  | DF /G /27/DFGA-V-3441 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
3 | NOSD | WGN | PRODTECH | PRODTECH | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 0 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-06-27 | 2024-06-27 | 2024-06-27 | 2024-11-09 | 10 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | MTN-ROPE | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 12 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-11-09 | 20 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | MTN-ROPE | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 24 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-06-29 | 2024-07-02 | 2024-06-27 | 2024-11-09 | 30 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | MTN-ROPE | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 6 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-02 | 2024-07-02 | 2024-06-27 | 2024-11-09 | 40 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | VEN-MECH | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 12 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-02 | 2024-07-04 | 2024-06-27 | 2024-11-09 | 50 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | PRODTECH | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 12 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-04 | 2024-07-07 | 2024-06-27 | 2024-11-09 | 60 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | VEN-MECH | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 12 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-07 | 2024-07-08 | 2024-06-27 | 2024-11-09 | 70 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | PRODTECH | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 12 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-08 | 2024-07-11 | 2024-06-27 | 2024-11-09 | 80 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | MTN-ROPE | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 3 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-11 | 2024-07-11 | 2024-06-27 | 2024-11-09 | 90 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | MTN-ROPE | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 12 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-11 | 2024-07-13 | 2024-06-27 | 2024-11-09 | 100 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | NOSD | WGN | PRODTECH | MTN-ROPE | 2200018527 | Freeze Plug Flare outlet DFG Drain Sep. | Freeze Plug Flare outlet DFG Drain Sep. | SECE | SECE | 0 | 0 | Empty | 2024-06-27 | 2024-07-13 | 2024-07-13 | 2024-07-13 | 2024-06-27 | 2024-11-09 | 110 | SECE | SECE | DF /G /28/DFGA-V-5072 | Freeze Plug Flare outlet DFG Drain Sep. | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 12 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 5 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 3 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-19 | 2024-09-20 | 2020-02-12 | 2020-05-12 | 10 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 8 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-20 | 2024-09-22 | 2020-02-12 | 2020-05-12 | 15 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 8 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-20 | 2024-09-22 | 2020-02-12 | 2020-05-12 | 20 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 3 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2020-02-12 | 2020-05-12 | 30 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 8 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2020-02-12 | 2020-05-12 | 40 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100025195 | DFGA-LG-410445 changeout of LG and HCV's | Isolate DFGA-LG-410445 LG and HCV | AWSC | AWSC | 0 | 0 | Campaign - ENG548 | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2024-09-18 | 2020-02-12 | 2020-05-12 | 50 | AWSC | AWSC | DF /G /30/DFGA-LG-410445 | Isolate DFGA-LG-410445 LG and HCV | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341923 | DFG_1Y_37000 INT STRUCT INSP - GVI | DFG_1Y_37000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/EL_37000 (LEVEL3) | DFG_1Y_37000 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040472 | Replace Socket outlet | Isolate accordingly |  |  | 1 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-01-24 | 2021-06-23 | 10 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040472 | Replace Socket outlet | Isolate accordingly |  |  | 3 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2021-01-24 | 2021-06-23 | 20 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040472 | Replace Socket outlet | Isolate accordingly |  |  | 1 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-01-24 | 2021-06-23 | 30 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040472 | Replace Socket outlet | Isolate accordingly |  |  | 0 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-01-24 | 2021-06-23 | 40 |  |  | DF /G /61 | Isolate accordingly | Unknown
3 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100025290 | Skift af ventiler ved FIT-500820 | Servicere FIT-500820 + skift af ventiler | AWSC | AWSC | 30 | 0 | W/200659082 | 2025-01-01 | 2025-01-11 | 2025-01-01 | 2025-01-05 | 2016-12-21 | 2017-01-30 | 10 | AWSC | AWSC | DF /G /27/DFGA-FE-500820 | Servicere FIT-500820 + skift af ventiler | Unknown
3 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100025290 | Skift af ventiler ved FIT-500820 | Servicere FIT-500820 + skift af ventiler | AWSC | AWSC | 30 | 0 | W/200659082 | 2025-01-01 | 2025-01-11 | 2025-01-05 | 2025-01-09 | 2016-12-21 | 2017-01-30 | 20 | AWSC | AWSC | DF /G /27/DFGA-FE-500820 | Servicere FIT-500820 + skift af ventiler | Unknown
3 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100025290 | Skift af ventiler ved FIT-500820 | Servicere FIT-500820 + skift af ventiler | AWSC | AWSC | 8 | 0 | W/200659082 | 2025-01-01 | 2025-01-11 | 2025-01-09 | 2025-01-11 | 2016-12-21 | 2017-01-30 | 30 | AWSC | AWSC | DF /G /27/DFGA-FE-500820 | Servicere FIT-500820 + skift af ventiler | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 2 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 3 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 4 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 5 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PAIN | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 10 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PAIN | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 20 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PAIN | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 30 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-ROPE | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-06 | 2020-11-08 | 2021-09-04 | 40 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-ROPE | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 28 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-06 | 2024-06-08 | 2020-11-08 | 2021-09-04 | 45 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-SCAF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 36 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-08 | 2024-06-11 | 2020-11-08 | 2021-09-04 | 50 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-LAGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 2 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-11 | 2024-06-11 | 2020-11-08 | 2021-09-04 | 60 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-ELEC | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 2 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-11 | 2024-06-12 | 2020-11-08 | 2021-09-04 | 70 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-RIGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 16 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-12 | 2024-06-14 | 2020-11-08 | 2021-09-04 | 80 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | PRODTECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 8 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-14 | 2024-06-15 | 2020-11-08 | 2021-09-04 | 90 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PIPF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 1 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-15 | 2024-06-15 | 2020-11-08 | 2021-09-04 | 100 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PIPF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 4 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-15 | 2024-06-15 | 2020-11-08 | 2021-09-04 | 110 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PIPF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 24 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-15 | 2024-06-16 | 2020-11-08 | 2021-09-04 | 120 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-RIGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 15 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-16 | 2024-06-17 | 2020-11-08 | 2021-09-04 | 125 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-RIGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 15 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-17 | 2024-06-18 | 2020-11-08 | 2021-09-04 | 126 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-RIGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 15 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-18 | 2024-06-19 | 2020-11-08 | 2021-09-04 | 127 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-RIGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 15 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-19 | 2024-06-21 | 2020-11-08 | 2021-09-04 | 128 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PIPF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 30 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-21 | 2024-06-22 | 2020-11-08 | 2021-09-04 | 130 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PIPF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 6 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-22 | 2024-06-22 | 2020-11-08 | 2021-09-04 | 140 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PAIN | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 8 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-22 | 2024-06-23 | 2020-11-08 | 2021-09-04 | 145 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-INST | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 6 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-23 | 2024-06-24 | 2020-11-08 | 2021-09-04 | 150 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-ELEC | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 4 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-24 | 2024-06-25 | 2020-11-08 | 2021-09-04 | 170 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-LAGG | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 12 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-25 | 2024-06-27 | 2020-11-08 | 2021-09-04 | 180 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-SCAF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 15 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-27 | 2024-06-28 | 2020-11-08 | 2021-09-04 | 185 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-SCAF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 24 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-28 | 2024-06-30 | 2020-11-08 | 2021-09-04 | 190 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-PIPF | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 9 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-30 | 2024-06-30 | 2020-11-08 | 2021-09-04 | 200 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | MTN-ROPE | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-30 | 2024-06-30 | 2020-11-08 | 2021-09-04 | 210 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-30 | 2024-06-30 | 2020-11-08 | 2021-09-04 | 220 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 0 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-30 | 2024-06-30 | 2020-11-08 | 2021-09-04 | 230 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
4 | DFA-W13 | WGN | MTN-PIPF | VEN-MECH | 2200003982 | ANOPR WI Flow line replacement DFA-13 | DRAFT-0002-2.REPL-6in-COATING | SCH | SCH | 65 | 0 | Empty | 2024-06-06 | 2024-07-03 | 2024-06-30 | 2024-07-03 | 2020-11-08 | 2021-09-04 | 240 | SCH | SCH | DF /A /55/DFA-6-WI-035-9058-FEW-U | DRAFT-0002-2.REPL-6in-COATING | Unknown
2 | SIWL | WDF | MTN-MECH | PRODTECH | 2100103975 | DFB-9 Hydraulic 400 bar return line hot | Production isolation |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2024-07-30 | 2023-12-20 | 2024-02-03 | 10 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100103975 | DFB-9 Hydraulic 400 bar return line hot | Production isolation |  |  | 6 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-07-30 | 2024-08-01 | 2023-12-20 | 2024-02-03 | 20 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
2 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100103975 | DFB-9 Hydraulic 400 bar return line hot | Production isolation |  |  | 6 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-08-31 | 2024-09-01 | 2023-12-20 | 2024-02-03 | 30 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
2 | SIWL | WDF | MTN-MECH | PRODTECH | 2100103975 | DFB-9 Hydraulic 400 bar return line hot | Production isolation |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2023-12-20 | 2024-02-03 | 40 |  |  | DF /B /07/DFBA-A-3101 | Production isolation | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339273 | DFF_1Y_31150 INT STRUCT INSP - GVI | DFF_1Y_31150 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_31150 & 31450 (WELL) | DFF_1Y_31150 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-20 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 21 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 41 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 60 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-29 | 2024-10-30 | 2024-12-31 | 61 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 70 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 80 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-25 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 90 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284271 | PSV Calibration - DFFA-PSV-410534 | Documentation & CNF WO | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-06-29 | 2024-06-26 | 2024-06-26 | 2024-10-30 | 2024-12-31 | 100 | AWSCSCHSECE | AWSCSCHSECE | DF /F /30/DFFA-PSV-410534 | Documentation & CNF WO | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-30 | 2021-02-21 | 2021-05-22 | 10 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-07-30 | 2021-02-21 | 2021-05-22 | 20 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-30 | 2024-07-31 | 2021-02-21 | 2021-05-22 | 30 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-31 | 2024-08-01 | 2021-02-21 | 2021-05-22 | 40 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-01 | 2021-02-21 | 2021-05-22 | 50 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-02 | 2021-02-21 | 2021-05-22 | 60 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-04 | 2021-02-21 | 2021-05-22 | 70 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-05 | 2021-02-21 | 2021-05-22 | 80 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-05 | 2024-08-05 | 2021-02-21 | 2021-05-22 | 90 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-05 | 2024-08-06 | 2021-02-21 | 2021-05-22 | 100 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-06 | 2024-08-06 | 2021-02-21 | 2021-05-22 | 110 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045067 | DFG LCV-340018 Dårlig integritet | Rigging assist. Rig in/out |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-06 | 2024-08-08 | 2021-02-21 | 2021-05-22 | 120 |  |  | DF /G /27/DFGA-LCV-340018 | Rigging assist. Rig in/out | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075994 | DFFE/78: Replace drain pipe from roof | Replace drain pipe |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-11-21 | 2023-04-05 | 10 |  |  | DF /F /78/DFFA-A-6101 | Replace drain pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075994 | DFFE/78: Replace drain pipe from roof | Replace drain pipe |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-11-21 | 2023-04-05 | 20 |  |  | DF /F /78/DFFA-A-6101 | Replace drain pipe | Unknown
3 | DFCLPSEP | WGN | MTN-MECH | PRODTECH | 2200003041 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in lifting out actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2018-05-13 | 2018-08-11 | 10 | AWSC | AWSC | DF /C /20/DFCI-PCV-34027 | L3 Assist in lifting out actuator | Unknown
3 | DFCLPSEP | WGN | MTN-MECH | MTN-RIGG | 2200003041 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in lifting out actuator | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-03 | 2018-05-13 | 2018-08-11 | 15 | AWSC | AWSC | DF /C /20/DFCI-PCV-34027 | L3 Assist in lifting out actuator | Unknown
3 | DFCLPSEP | WGN | MTN-MECH | MTN-MECH | 2200003041 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in lifting out actuator | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-05 | 2018-05-13 | 2018-08-11 | 25 | AWSC | AWSC | DF /C /20/DFCI-PCV-34027 | L3 Assist in lifting out actuator | Unknown
3 | DFCLPSEP | WGN | MTN-MECH | MTN-RIGG | 2200003041 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in lifting out actuator | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-01-07 | 2018-05-13 | 2018-08-11 | 26 | AWSC | AWSC | DF /C /20/DFCI-PCV-34027 | L3 Assist in lifting out actuator | Unknown
3 | DFCLPSEP | WGN | MTN-MECH | PRODTECH | 2200003041 | CMAT:Replace actuator DFCI-PCV-34027, L2 | L3 Assist in lifting out actuator | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-07 | 2025-01-07 | 2018-05-13 | 2018-08-11 | 30 | AWSC | AWSC | DF /C /20/DFCI-PCV-34027 | L3 Assist in lifting out actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2020-03-25 | 2020-05-04 | 5 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2020-03-25 | 2020-05-04 | 10 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2020-03-25 | 2020-05-04 | 30 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2020-03-25 | 2020-05-04 | 40 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2020-03-25 | 2020-05-04 | 50 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2020-03-25 | 2020-05-04 | 60 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029690 | Replace Actuator DFFA-XCV-301104 (Ekst. | Isolate hydraulik supply DFFA-XCV-301104 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-03-25 | 2020-05-04 | 70 |  |  | DF /F /10/DFFA-XCV-301104 | Isolate hydraulik supply DFFA-XCV-301104 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089994 | Elev. table in galley actuator defect | Replace Actuatorer |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-06-16 | 2023-10-29 | 10 |  |  | DF /C /03/FZ-71-ACC-MESS-CHNG-RM-LVL-1 | Replace Actuatorer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089994 | Elev. table in galley actuator defect | Replace Actuatorer |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-06-16 | 2023-10-29 | 20 |  |  | DF /C /03/FZ-71-ACC-MESS-CHNG-RM-LVL-1 | Replace Actuatorer | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 5 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 4 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284258 | PSV Exchange - DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | AWSC | AWSC | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /E /75/DFEZ-PSV-39602D | DFEZ-PSV-39602D Offshore from WS Måde | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053479 | Replace floodlight DFC1803-4-L2B | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 10 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053479 | Replace floodlight DFC1803-4-L2B | Set personal isolation |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-31 | 2022-03-30 | 20 |  |  | DF /C /62 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053479 | Replace floodlight DFC1803-4-L2B | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-31 | 2022-03-30 | 30 |  |  | DF /C /62 | Set personal isolation | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235836 | 4Y 400V E-SWB MAINT DFFB-N-1829-02 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFB-N-1829-02 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235836 | 4Y 400V E-SWB MAINT DFFB-N-1829-02 | ISOLATION BY PRODUCTION |  |  | 14 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFB-N-1829-02 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235836 | 4Y 400V E-SWB MAINT DFFB-N-1829-02 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFB-N-1829-02 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235836 | 4Y 400V E-SWB MAINT DFFB-N-1829-02 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFB-N-1829-02 | ISOLATION BY PRODUCTION | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | PRODTECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 3 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2021-04-09 | 2021-12-05 | 10 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 2 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2021-04-09 | 2021-12-05 | 20 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 3 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2021-04-09 | 2021-12-05 | 30 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 3 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2021-04-09 | 2021-12-05 | 40 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 3 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2021-04-09 | 2021-12-05 | 50 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 2 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2021-04-09 | 2021-12-05 | 60 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 2 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2021-04-09 | 2021-12-05 | 70 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | PRODTECH | 2100042997 | DFCI-ESDV-34031 Rusten magnetventil | Isolate Hydraulic |  |  | 3 | 0 | BL-TEAM | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2021-04-09 | 2021-12-05 | 80 |  |  | DF /C /20/DFCI-ESDV-34031 | Isolate Hydraulic | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339278 | DFF_1Y_35870 INT STRUCT INSP - GVI | DFF_1Y_35870 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_35870 (MAIN DECK LAYDOWN) | DFF_1Y_35870 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003191 | CMAT:DFGA-ESDV-570027 Udskift def manome | Udskift af manometer på DFGA-ESDV-570027 |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-03 | 2023-04-04 | 2018-03-08 | 2019-03-03 | 10 |  |  | DF /G /70/DFGA-ESDV-570027 | Udskift af manometer på DFGA-ESDV-570027 | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003191 | CMAT:DFGA-ESDV-570027 Udskift def manome | Udskift af manometer på DFGA-ESDV-570027 |  |  | 2 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-05 | 2018-03-08 | 2019-03-03 | 20 |  |  | DF /G /70/DFGA-ESDV-570027 | Udskift af manometer på DFGA-ESDV-570027 | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003191 | CMAT:DFGA-ESDV-570027 Udskift def manome | Udskift af manometer på DFGA-ESDV-570027 |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-06 | 2018-03-08 | 2019-03-03 | 30 |  |  | DF /G /70/DFGA-ESDV-570027 | Udskift af manometer på DFGA-ESDV-570027 | Unknown
3 | NE | WDF | MTN-MECH | MTN-PAIN | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 10 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | VEN-MECH | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 0 | 5 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 20 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 70 | 70 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 30 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | MTN-PIPF | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 100 | 100 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 40 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | MTN-ROPE | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 50 | 96 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 50 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 60 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | MTN-PIPF | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 36 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 70 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
3 | NE | WDF | MTN-MECH | MTN-SCAF | 2100068053 | FFSPR: Utility & Instrument Air Batch-02 | FFSP: 2" air utility line replacement | PCNF | PCNF | 50 | 67 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2022-03-04 | 2022-08-09 | 80 | PCNF | PCNF | DF /B /07/DFB-2-AU-054-0851-A1-F | FFSP: 2" air utility line replacement | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322249 | DFB-27-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 10 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344329 | 6M INST AIR DRYER SKID MAINT-DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 |  |  | 2 | 0 | Empty | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-29 | 10 |  |  | DF /F /07/DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400344329 | 6M INST AIR DRYER SKID MAINT-DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 |  |  | 1 | 0 | Empty | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-10 | 2024-09-29 | 20 |  |  | DF /F /07/DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067645 | HT DFFA Cable damged | Isolate and prove dead |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-05-28 | 2022-08-26 | 10 |  |  | DF /F /61/DFFA-DP-1802A-7-F14 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067645 | HT DFFA Cable damged | Isolate and prove dead |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2022-05-28 | 2022-08-26 | 20 |  |  | DF /F /61/DFFA-DP-1802A-7-F14 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100067645 | HT DFFA Cable damged | Isolate and prove dead |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2022-05-28 | 2022-08-26 | 30 |  |  | DF /F /61/DFFA-DP-1802A-7-F14 | Isolate and prove dead | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235613 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235613 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 20 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235613 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-28 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235613 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B | DE-ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400215381 | 1Y NITROGEN GEN PACKGE MAINT-DFGA-A-0850 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W23-W24 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-06 | 2022-10-16 | 2022-11-15 | 10 | SCHSECE | SCHSECE | DF /G /74/DFGA-A-0850 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400215381 | 1Y NITROGEN GEN PACKGE MAINT-DFGA-A-0850 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W23-W24 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-07 | 2022-10-16 | 2022-11-15 | 20 | SCHSECE | SCHSECE | DF /G /74/DFGA-A-0850 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400215381 | 1Y NITROGEN GEN PACKGE MAINT-DFGA-A-0850 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W23-W24 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-06 | 2022-10-16 | 2022-11-15 | 30 | SCHSECE | SCHSECE | DF /G /74/DFGA-A-0850 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400215381 | 1Y NITROGEN GEN PACKGE MAINT-DFGA-A-0850 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W23-W24 | 2024-06-06 | 2024-06-07 | 2024-06-06 | 2024-06-06 | 2022-10-16 | 2022-11-15 | 40 | SCHSECE | SCHSECE | DF /G /74/DFGA-A-0850 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235568 | 4Y 400V N-SWB-MAINT-DFCC-N-1836 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1836 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235568 | 4Y 400V N-SWB-MAINT-DFCC-N-1836 | ISOLATION ELECTRICAL | AWSC | AWSC | 49 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-22 | 2024-10-04 | 2023-02-14 | 2023-05-13 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1836 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235568 | 4Y 400V N-SWB-MAINT-DFCC-N-1836 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-04 | 2024-10-08 | 2023-02-14 | 2023-05-13 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1836 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235568 | 4Y 400V N-SWB-MAINT-DFCC-N-1836 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2023-02-14 | 2023-05-13 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1836 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400306670 | 6M PROD WTR HP/LP SKD MAINT-DFFA-A-5001 | PROD WTR HP/LP SKD INSP-DFFA-A-5001 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2024-02-04 | 2024-02-23 | 10 |  |  | DF /F /27/DFFA-A-5001 | PROD WTR HP/LP SKD INSP-DFFA-A-5001 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042844 | Deluge DFF leaking pilot valve xv-035353 | replace/repair pilot valve | SCHSECE | SCHSECE | 2 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2021-03-03 | 2021-07-31 | 10 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035353 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042844 | Deluge DFF leaking pilot valve xv-035353 | replace/repair pilot valve | SCHSECE | SCHSECE | 8 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-24 | 2021-03-03 | 2021-07-31 | 20 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035353 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042844 | Deluge DFF leaking pilot valve xv-035353 | replace/repair pilot valve | SCHSECE | SCHSECE | 2 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2021-03-03 | 2021-07-31 | 30 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035353 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042844 | Deluge DFF leaking pilot valve xv-035353 | replace/repair pilot valve | SCHSECE | SCHSECE | 0 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2021-03-03 | 2021-07-31 | 40 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035353 | replace/repair pilot valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044093 | DFF Minox Methanol P-4601 poor performen | Return of pump | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-02-12 | 2024-03-31 | 2021-01-24 | 2021-03-05 | 20 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-4601 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044093 | DFF Minox Methanol P-4601 poor performen | Return of pump | PCNFSCH | PCNFSCH | 12 | 10 | Empty | 2024-09-16 | 2024-09-16 | 2024-02-12 | 2024-03-31 | 2021-01-24 | 2021-03-05 | 30 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-4601 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044093 | DFF Minox Methanol P-4601 poor performen | Return of pump | PCNFSCH | PCNFSCH | 12 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-01-24 | 2021-03-05 | 40 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-4601 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044093 | DFF Minox Methanol P-4601 poor performen | Return of pump | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-01-24 | 2021-03-05 | 50 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-4601 | Return of pump | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044093 | DFF Minox Methanol P-4601 poor performen | Return of pump | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-01-24 | 2021-03-05 | 60 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-4601 | Return of pump | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099201 | RCD broken Q43 | RCD broken Q43 |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-03 | 2023-11-17 | 10 |  |  | DF /G /05/DFGA-LP-1852-43 | RCD broken Q43 | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100099201 | RCD broken Q43 | RCD broken Q43 |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-03 | 2023-11-17 | 20 |  |  | DF /G /05/DFGA-LP-1852-43 | RCD broken Q43 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099201 | RCD broken Q43 | RCD broken Q43 |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-03 | 2023-11-17 | 30 |  |  | DF /G /05/DFGA-LP-1852-43 | RCD broken Q43 | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099201 | RCD broken Q43 | RCD broken Q43 |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-03 | 2023-11-17 | 40 |  |  | DF /G /05/DFGA-LP-1852-43 | RCD broken Q43 | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100099201 | RCD broken Q43 | RCD broken Q43 |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-03 | 2023-11-17 | 50 |  |  | DF /G /05/DFGA-LP-1852-43 | RCD broken Q43 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322279 | DFF-23-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /23/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093111 | HCV for hosereel X-0358 corroded | Replace Valve | SECE | SECE | 2 | 0 | Empty | 2024-07-24 | 2024-07-26 | 2024-07-24 | 2024-07-24 | 2023-08-02 | 2023-12-15 | 10 | SECE | SECE | DF /C /01/DFCC-X-0358 | Replace Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093111 | HCV for hosereel X-0358 corroded | Replace Valve | SECE | SECE | 4 | 0 | Empty | 2024-07-24 | 2024-07-26 | 2024-07-24 | 2024-07-25 | 2023-08-02 | 2023-12-15 | 20 | SECE | SECE | DF /C /01/DFCC-X-0358 | Replace Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093111 | HCV for hosereel X-0358 corroded | Replace Valve | SECE | SECE | 2 | 0 | Empty | 2024-07-24 | 2024-07-26 | 2024-07-25 | 2024-07-26 | 2023-08-02 | 2023-12-15 | 30 | SECE | SECE | DF /C /01/DFCC-X-0358 | Replace Valve | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 2 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-20 | 2024-07-20 | 2023-09-20 | 2026-03-08 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 3 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2023-09-20 | 2026-03-08 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2023-09-20 | 2026-03-08 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 3 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2023-09-20 | 2026-03-08 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-22 | 2024-07-22 | 2023-09-20 | 2026-03-08 | 50 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2023-09-20 | 2026-03-08 | 60 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 3 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2023-09-20 | 2026-03-08 | 70 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-24 | 2024-07-24 | 2023-09-20 | 2026-03-08 | 80 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2023-09-20 | 2026-03-08 | 90 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 8 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-25 | 2024-07-27 | 2023-09-20 | 2026-03-08 | 100 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100088070 | DFB/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 8 | 0 | Empty | 2024-07-20 | 2024-07-27 | 2024-07-25 | 2024-07-27 | 2023-09-20 | 2026-03-08 | 110 |  |  | DF /B /78/DFBA-X-6102 | Isolate and de-isolate | Unknown
3 | NOSD | WGN | INP-SITE | PRODTECH | 2200014150 | Inspection to investigate cabin support | Inspect cabin support |  |  | 1 | 0 | Empty | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-07-10 | 2023-06-02 | 2023-10-15 | 10 |  |  | DF /G /78/DFGA-A-6140 | Inspect cabin support | Unknown
3 | NOSD | WGN | INP-SITE | VEN-INSP | 2200014150 | Inspection to investigate cabin support | Inspect cabin support |  |  | 15 | 0 | Empty | 2023-07-10 | 2023-07-13 | 2023-07-10 | 2023-07-11 | 2023-06-02 | 2023-10-15 | 20 |  |  | DF /G /78/DFGA-A-6140 | Inspect cabin support | Unknown
3 | NOSD | WGN | INP-SITE | MTN-ROPE | 2200014150 | Inspection to investigate cabin support | Inspect cabin support |  |  | 24 | 0 | Empty | 2023-07-10 | 2023-07-13 | 2023-07-11 | 2023-07-13 | 2023-06-02 | 2023-10-15 | 30 |  |  | DF /G /78/DFGA-A-6140 | Inspect cabin support | Unknown
3 | NOSD | WGN | INP-SITE | MTN-ROUS | 2200014150 | Inspection to investigate cabin support | Inspect cabin support |  |  | 3 | 0 | Empty | 2023-07-10 | 2023-07-13 | 2023-07-13 | 2023-07-13 | 2023-06-02 | 2023-10-15 | 40 |  |  | DF /G /78/DFGA-A-6140 | Inspect cabin support | Unknown
3 | NOSD | WGN | INP-SITE | VEN-INSP | 2200014150 | Inspection to investigate cabin support | Inspect cabin support |  |  | 3 | 0 | Empty | 2023-07-10 | 2023-07-13 | 2023-07-13 | 2023-07-13 | 2023-06-02 | 2023-10-15 | 50 |  |  | DF /G /78/DFGA-A-6140 | Inspect cabin support | Unknown
3 | NOSD | WGN | INP-SITE | MTN-ROUS | 2200014150 | Inspection to investigate cabin support | Inspect cabin support |  |  | 3 | 0 | Empty | 2023-07-10 | 2023-07-13 | 2023-07-13 | 2023-07-13 | 2023-06-02 | 2023-10-15 | 60 |  |  | DF /G /78/DFGA-A-6140 | Inspect cabin support | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308557 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 1 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2024-09-03 | 2024-02-15 | 2024-03-16 | 10 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308557 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 12 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2024-09-06 | 2024-02-15 | 2024-03-16 | 20 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308557 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 1 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-02-15 | 2024-03-16 | 30 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400308557 | 1Y HVAC SUPPLY UTIL R. CHECK DFEZ-A-1201 | PERSONAL ISOLATION |  |  | 2 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-02-15 | 2024-03-16 | 40 |  |  | DF /E /09/DFEZ-A-1201 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400352436 | 1Y FIRE DAMPER CHECK - DFCI | FIRE DAMPER CHECK - DFCI | SECE | SECE | 25 | 0 | W39-W40 | 2024-09-23 | 2024-09-29 | 2024-09-23 | 2024-09-29 | 2024-09-23 | 2024-10-23 | 10 | SECE | SECE | DF /C /09/FIRE-DAMPERS | FIRE DAMPER CHECK - DFCI | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075984 | DFB Turbine Control HVAC blower | DFB Turbine Control HVAC blower |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2022-11-24 | 2023-04-08 | 10 |  |  | DF /B /09/DFBA-B-1243A | DFB Turbine Control HVAC blower | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003003 | Tightening of the fittings on DFCM-AC | L3 Safing of DFCM-ACC-59512 |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2018-02-28 | 2018-04-09 | 10 |  |  | DF /C /07/DFCM-ACC-59512 | L3 Safing of DFCM-ACC-59512 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003003 | Tightening of the fittings on DFCM-AC | L3 Safing of DFCM-ACC-59512 |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-02-28 | 2018-04-09 | 20 |  |  | DF /C /07/DFCM-ACC-59512 | L3 Safing of DFCM-ACC-59512 | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003003 | Tightening of the fittings on DFCM-AC | L3 Safing of DFCM-ACC-59512 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2018-02-28 | 2018-04-09 | 30 |  |  | DF /C /07/DFCM-ACC-59512 | L3 Safing of DFCM-ACC-59512 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062918 | ANOSR DFA - Repair tertiary structure EL | Wash down, surface prep and coatings |  |  | 0 | 0 | Empty | 2022-05-02 | 2022-06-16 | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-09-29 | 10 |  |  | DF /A /86/24720 - TERT STRUCT | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062918 | ANOSR DFA - Repair tertiary structure EL | Wash down, surface prep and coatings |  |  | 6 | 0 | Empty | 2022-05-02 | 2022-06-16 | 2022-05-02 | 2022-05-03 | 2022-05-02 | 2022-09-29 | 20 |  |  | DF /A /86/24720 - TERT STRUCT | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062918 | ANOSR DFA - Repair tertiary structure EL | Wash down, surface prep and coatings |  |  | 50 | 0 | Empty | 2022-05-02 | 2022-06-16 | 2022-05-03 | 2022-05-09 | 2022-05-02 | 2022-09-29 | 30 |  |  | DF /A /86/24720 - TERT STRUCT | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062918 | ANOSR DFA - Repair tertiary structure EL | Wash down, surface prep and coatings |  |  | 184 | 0 | Empty | 2022-05-02 | 2022-06-16 | 2022-05-09 | 2022-06-01 | 2022-05-02 | 2022-09-29 | 40 |  |  | DF /A /86/24720 - TERT STRUCT | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062918 | ANOSR DFA - Repair tertiary structure EL | Wash down, surface prep and coatings |  |  | 117 | 0 | Empty | 2022-05-02 | 2022-06-16 | 2022-06-01 | 2022-06-16 | 2022-05-02 | 2022-09-29 | 50 |  |  | DF /A /86/24720 - TERT STRUCT | Wash down, surface prep and coatings | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062918 | ANOSR DFA - Repair tertiary structure EL | Wash down, surface prep and coatings |  |  | 6 | 0 | Empty | 2022-05-02 | 2022-06-16 | 2022-06-16 | 2022-06-16 | 2022-05-02 | 2022-09-29 | 60 |  |  | DF /A /86/24720 - TERT STRUCT | Wash down, surface prep and coatings | Unknown
3 | SIWL | WDF | MTN-INST | PRODTECH | 2100073047 | Leaking instrument valve PT-35219 | Isolate Pressure transmitter |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-30 | 2023-02-12 | 10 |  |  | DF /B /55/DFBA-PT-35219 | Isolate Pressure transmitter | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100073047 | Leaking instrument valve PT-35219 | Isolate Pressure transmitter |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-30 | 2023-02-12 | 20 |  |  | DF /B /55/DFBA-PT-35219 | Isolate Pressure transmitter | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100073047 | Leaking instrument valve PT-35219 | Isolate Pressure transmitter |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-30 | 2023-02-12 | 30 |  |  | DF /B /55/DFBA-PT-35219 | Isolate Pressure transmitter | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100073047 | Leaking instrument valve PT-35219 | Isolate Pressure transmitter |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-30 | 2023-02-12 | 40 |  |  | DF /B /55/DFBA-PT-35219 | Isolate Pressure transmitter | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100073047 | Leaking instrument valve PT-35219 | Isolate Pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-30 | 2023-02-12 | 45 |  |  | DF /B /55/DFBA-PT-35219 | Isolate Pressure transmitter | Unknown
3 | SIWL | WDF | MTN-INST | PRODTECH | 2100073047 | Leaking instrument valve PT-35219 | Isolate Pressure transmitter |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-09-30 | 2023-02-12 | 50 |  |  | DF /B /55/DFBA-PT-35219 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094370 | DFAA/78 Problems with overpressure in th | Door seal on generic number | PCNF | PCNF | 5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-08-21 | 2024-01-03 | 10 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Door seal on generic number | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100094370 | DFAA/78 Problems with overpressure in th | Door seal on generic number | PCNF | PCNF | 5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-03-10 | 2024-04-24 | 2023-08-21 | 2024-01-03 | 20 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Door seal on generic number | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100094370 | DFAA/78 Problems with overpressure in th | Door seal on generic number | PCNF | PCNF | 5 | 10 | Empty | 2024-07-29 | 2024-07-30 | 2024-03-11 | 2024-04-24 | 2023-08-21 | 2024-01-03 | 30 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Door seal on generic number | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094370 | DFAA/78 Problems with overpressure in th | Door seal on generic number | PCNF | PCNF | 5 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-08-21 | 2024-01-03 | 40 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Door seal on generic number | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094370 | DFAA/78 Problems with overpressure in th | Door seal on generic number | PCNF | PCNF | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-08-21 | 2024-01-03 | 50 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Door seal on generic number | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094370 | DFAA/78 Problems with overpressure in th | Door seal on generic number | PCNF | PCNF | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-08-21 | 2024-01-03 | 60 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Door seal on generic number | Unknown
D | NOSD | WPM | PRODTECH | PRODTECH | 2400336969 | PIGGING, P3002 10" DFB-GOC OIL 2W | P3002_DFB-GOC | AWSC | AWSC | 4 | 12 | Empty | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-08-01 | 2024-08-07 | 10 | AWSC | AWSC | DF /B /23/DFBY-PL-673002 | P3002_DFB-GOC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235664 | 4Y 400V N-SWB MAINT DFCI-N-1802-R04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R4 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235664 | 4Y 400V N-SWB MAINT DFCI-N-1802-R04 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R4 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235664 | 4Y 400V N-SWB MAINT DFCI-N-1802-R04 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R4 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235664 | 4Y 400V N-SWB MAINT DFCI-N-1802-R04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R4 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235618 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-6 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2024-09-18 | 2023-04-30 | 2023-07-27 | 10 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-6 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235618 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-6 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 11 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2024-09-21 | 2023-04-30 | 2023-07-27 | 20 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-6 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235618 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-6 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 6 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-21 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 30 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-6 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235618 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-6 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 40 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-6 | ISOLATION ELECTRICAL | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087256 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /G /05/DFGA-LP-1852-10 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087256 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /G /05/DFGA-LP-1852-10 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087256 | Battery fault on emergency light | Isolate and prove dead. |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /G /05/DFGA-LP-1852-10 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087256 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /G /05/DFGA-LP-1852-10 | Isolate and prove dead. | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009249 | Insulation assist FORCE 19941(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /55/DFF-6-WI-030-7102-GFW-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009249 | Insulation assist FORCE 19941(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-28 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /55/DFF-6-WI-030-7102-GFW-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009249 | Insulation assist FORCE 19941(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-28 | 2023-03-28 | 2022-02-07 | 2022-07-07 | 25 |  |  | DF /F /55/DFF-6-WI-030-7102-GFW-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009249 | Insulation assist FORCE 19941(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-28 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /55/DFF-6-WI-030-7102-GFW-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071666 | Replace Light Fixture LE-1813-3904-L1A | Set personal isolation |  |  | 1 | 0 | Hold Step | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-07-28 | 2022-12-10 | 10 |  |  | DF /F /62/EMERGENCY-LIGHTING-LEVEL-1 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071666 | Replace Light Fixture LE-1813-3904-L1A | Set personal isolation |  |  | 4 | 0 | Hold Step | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-07-28 | 2022-12-10 | 20 |  |  | DF /F /62/EMERGENCY-LIGHTING-LEVEL-1 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071666 | Replace Light Fixture LE-1813-3904-L1A | Set personal isolation |  |  | 1 | 0 | Hold Step | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-07-28 | 2022-12-10 | 30 |  |  | DF /F /62/EMERGENCY-LIGHTING-LEVEL-1 | Set personal isolation | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100023024 | Replace broken Mech. Interlock | Set Isolation, pull drawer |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2020-01-15 | 2021-01-09 | 10 |  |  | DF /F /61/DFFA-N-1801B-02-01 | Set Isolation, pull drawer | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100023024 | Replace broken Mech. Interlock | Set Isolation, pull drawer |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2020-01-15 | 2021-01-09 | 20 |  |  | DF /F /61/DFFA-N-1801B-02-01 | Set Isolation, pull drawer | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100023024 | Replace broken Mech. Interlock | Set Isolation, pull drawer |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2020-01-15 | 2021-01-09 | 30 |  |  | DF /F /61/DFFA-N-1801B-02-01 | Set Isolation, pull drawer | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009221 | Insulation assist FORCE 18999(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /C /01/DFC-4-WF-003-0147-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009221 | Insulation assist FORCE 18999(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-27 | 2023-03-28 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /C /01/DFC-4-WF-003-0147-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009221 | Insulation assist FORCE 18999(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-28 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /C /01/DFC-4-WF-003-0147-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009221 | Insulation assist FORCE 18999(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-31 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 35 |  |  | DF /C /01/DFC-4-WF-003-0147-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009221 | Insulation assist FORCE 18999(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-31 | 2023-04-04 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /C /01/DFC-4-WF-003-0147-A3-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009221 | Insulation assist FORCE 18999(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-04-04 | 2023-04-06 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /C /01/DFC-4-WF-003-0147-A3-F | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100102104 | DFAA/78 Smells a lot of exhaust gas in t | Exhaust manifold - Right side - See LT | PCNF | PCNF | 4 | 10 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-12-31 | 2024-05-14 | 10 | PCNF | PCNF | DF /A /78/DFAA-MD-6102 | Exhaust manifold - Right side - See LT | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100102104 | DFAA/78 Smells a lot of exhaust gas in t | Exhaust manifold - Right side - See LT | PCNF | PCNF | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-12-31 | 2024-05-14 | 20 | PCNF | PCNF | DF /A /78/DFAA-MD-6102 | Exhaust manifold - Right side - See LT | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100102104 | DFAA/78 Smells a lot of exhaust gas in t | Exhaust manifold - Right side - See LT | PCNF | PCNF | 6 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-12-31 | 2024-05-14 | 30 | PCNF | PCNF | DF /A /78/DFAA-MD-6102 | Exhaust manifold - Right side - See LT | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235833 | 4Y 380V E-SWB MAINT DFFA-N-1813-03 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235833 | 4Y 380V E-SWB MAINT DFFA-N-1813-03 | ISOLATION BY PRODUCTION |  |  | 22 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235833 | 4Y 380V E-SWB MAINT DFFA-N-1813-03 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235833 | 4Y 380V E-SWB MAINT DFFA-N-1813-03 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100036495 | ANOCR Paint escape routes battery room | Wash down, surface prep and coatings | PCNF | PCNF | 0 | 0 | Empty | 2020-12-07 | 2020-12-17 | 2020-12-07 | 2020-12-07 | 2020-09-05 | 2020-12-04 | 10 | PCNF | PCNF | DF /A /02/ESCAPE-ROUTES | Wash down, surface prep and coatings | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100036495 | ANOCR Paint escape routes battery room | Wash down, surface prep and coatings | PCNF | PCNF | 54 | 0 | Empty | 2020-12-07 | 2020-12-17 | 2020-12-07 | 2020-12-13 | 2020-09-05 | 2020-12-04 | 20 | PCNF | PCNF | DF /A /02/ESCAPE-ROUTES | Wash down, surface prep and coatings | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ELEC | 2100036495 | ANOCR Paint escape routes battery room | Wash down, surface prep and coatings | PCNF | PCNF | 15 | 18 | Empty | 2020-12-07 | 2020-12-17 | 2020-12-13 | 2020-12-17 | 2020-09-05 | 2020-12-04 | 30 | PCNF | PCNF | DF /A /02/ESCAPE-ROUTES | Wash down, surface prep and coatings | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 26.100000000000001421085471512 | 26 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2020-09-27 | 2020-09-30 | 2017-11-05 | 2017-12-15 | 10 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 5.4000000000000003552713678785 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-01 | 2024-04-01 | 2017-11-05 | 2017-12-15 | 20 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 5.4000000000000003552713678785 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-01 | 2024-04-02 | 2017-11-05 | 2017-12-15 | 30 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 3 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-02 | 2024-04-02 | 2017-11-05 | 2017-12-15 | 40 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 26.100000000000001421085471512 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-02 | 2024-04-04 | 2017-11-05 | 2017-12-15 | 50 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 3 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-04 | 2024-04-05 | 2017-11-05 | 2017-12-15 | 60 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 17.399999999999998578914528472 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-05 | 2024-04-06 | 2017-11-05 | 2017-12-15 | 70 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 30.19999999999999928945726423 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-06 | 2024-04-10 | 2017-11-05 | 2017-12-15 | 80 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 8.699999999999999289457264236 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-10 | 2024-04-11 | 2017-11-05 | 2017-12-15 | 90 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 0 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2017-11-05 | 2017-12-15 | 100 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100027610 | Udskift 10 meter rør DFF PM-3919/20 | Stillads skammel | PCNF | PCNF | 0 | 0 | G.S 02-10 See header text | 2024-04-01 | 2024-04-11 | 2024-04-11 | 2024-04-11 | 2017-11-05 | 2017-12-15 | 110 | PCNF | PCNF | DF /F /75 | Stillads skammel | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 0 | 0 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2022-05-20 | 2022-05-20 | 2021-09-02 | 2021-09-22 | 10 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 36 | 360 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2021-12-01 | 2022-05-17 | 2021-09-02 | 2021-09-22 | 20 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 3 | 3 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2021-12-01 | 2022-05-17 | 2021-09-02 | 2021-09-22 | 30 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 0 | 0 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2022-05-19 | 2022-05-19 | 2021-09-02 | 2021-09-22 | 40 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 252 | 126 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2022-04-12 | 2022-05-17 | 2021-09-02 | 2021-09-22 | 50 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 108 | 185 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2022-08-25 | 2022-08-25 | 2021-09-02 | 2021-09-22 | 60 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100054688 | FFSC DFB-16"-PHS-339011-BD Ext. coor. in | Extend scaffolding | PCNFSCH | PCNFSCH | 120 | 97 | W17-18 - New operation | 2022-05-19 | 2022-08-25 | 2022-05-09 | 2022-05-17 | 2021-09-02 | 2021-09-22 | 70 | PCNFSCH | PCNFSCH | DF /B /12/DFB-16-PHS-033-9011-BD-U | Extend scaffolding | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 10 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 20 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | PRODTECH | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 30 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 40 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 50 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | INP-SITE | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 60 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 70 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 80 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 90 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | PRODTECH | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 100 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100089594 | ANOPR Replacement Spool DFG-3"-DOS-50016 | Prepare work area |  |  | 0 | 0 | Empty | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 110 |  |  | DF /G /28/DFG-3-DOS-050-0164-AB-T | Prepare work area | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018145 | Replace Motor protection 1841-M122 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M122-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018145 | Replace Motor protection 1841-M122 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M122-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018145 | Replace Motor protection 1841-M122 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M122-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018145 | Replace Motor protection 1841-M122 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M122-02 | Isolation of Breaker section | Unknown
A | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-RIGG | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-17 | 2024-07-20 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 5 | 12 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 2 | 2 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-RIGG | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-25 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | DFE-3551 | WPM | MTN-MECH | VEN-INSP | 2400284256 | PSV Calibration - DFEZ-PSV-35877 | Rigging assist (remove) | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 120 | AWSCSECE | AWSCSECE | DF /E /54/DFEZ-PSV-35877 | Rigging assist (remove) | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322247 | DFB-36-GI-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WGN | VEN-INST | MTN-PAIN | 2200009357 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-02-16 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /C /28/DFC-3-DO-050-0317-B-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-SCAF | 2200009357 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 336 | 0 | Empty | 2024-01-08 | 2024-02-16 | 2024-01-08 | 2024-01-28 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /C /28/DFC-3-DO-050-0317-B-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-PAIN | 2200009357 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 20 | 0 | Empty | 2024-01-08 | 2024-02-16 | 2024-01-29 | 2024-01-31 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /C /28/DFC-3-DO-050-0317-B-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | VEN-INST | 2200009357 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-02-16 | 2024-01-31 | 2024-01-31 | 2022-02-08 | 2022-07-08 | 32 |  |  | DF /C /28/DFC-3-DO-050-0317-B-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-PAIN | 2200009357 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 37 | 0 | Empty | 2024-01-08 | 2024-02-16 | 2024-01-31 | 2024-02-04 | 2022-02-08 | 2022-07-08 | 33 |  |  | DF /C /28/DFC-3-DO-050-0317-B-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-SCAF | 2200009357 | Sandblasting assist FORCE 21054 | Bilfinger inspection |  |  | 200 | 0 | Empty | 2024-01-08 | 2024-02-16 | 2024-02-04 | 2024-02-16 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /C /28/DFC-3-DO-050-0317-B-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009371 | removing of support. pack 9458(COMP-2022 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-27 | 2022-02-10 | 2022-07-10 | 10 |  |  | DF /A /10/DFA-12-PHS-033-9048-FD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009371 | removing of support. pack 9458(COMP-2022 | Bilfinger inspection |  |  | 20 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-29 | 2022-02-10 | 2022-07-10 | 20 |  |  | DF /A /10/DFA-12-PHS-033-9048-FD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009371 | removing of support. pack 9458(COMP-2022 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-29 | 2023-03-30 | 2022-02-10 | 2022-07-10 | 22 |  |  | DF /A /10/DFA-12-PHS-033-9048-FD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009371 | removing of support. pack 9458(COMP-2022 | Bilfinger inspection |  |  | 10 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-30 | 2023-03-31 | 2022-02-10 | 2022-07-10 | 30 |  |  | DF /A /10/DFA-12-PHS-033-9048-FD-U | Bilfinger inspection | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259874 | 1Y WIRELINE OVERRIDE PANELS - DFF WH S | WIRELINE OVERRIDE PANELS-DFF WH S |  |  | 6.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2023-05-29 | 2023-06-28 | 10 |  |  | DF /F /07 | WIRELINE OVERRIDE PANELS-DFF WH S | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400259874 | 1Y WIRELINE OVERRIDE PANELS - DFF WH S | WIRELINE OVERRIDE PANELS-DFF WH S |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2023-05-29 | 2023-06-28 | 20 |  |  | DF /F /07 | WIRELINE OVERRIDE PANELS-DFF WH S | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-15 | 2024-07-15 | 2023-09-10 | 2026-02-26 | 10 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-15 | 2024-07-16 | 2023-09-10 | 2026-02-26 | 20 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-15 | 2024-07-16 | 2023-09-10 | 2026-02-26 | 30 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-16 | 2024-07-16 | 2023-09-10 | 2026-02-26 | 40 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-17 | 2024-07-17 | 2023-09-10 | 2026-02-26 | 50 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-17 | 2024-07-18 | 2023-09-10 | 2026-02-26 | 60 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-18 | 2024-07-18 | 2023-09-10 | 2026-02-26 | 70 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-PAIN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-19 | 2024-07-19 | 2023-09-10 | 2026-02-26 | 80 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-19 | 2024-07-20 | 2023-09-10 | 2026-02-26 | 90 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 8 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-20 | 2024-07-22 | 2023-09-10 | 2026-02-26 | 100 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100087412 | DFA/78 Bolts for winch flanges+paint | Isolate and de-isolate |  |  | 8 | 0 | Empty | 2024-07-15 | 2024-07-22 | 2024-07-20 | 2024-07-22 | 2023-09-10 | 2026-02-26 | 110 |  |  | DF /A /78/DFAA-X-6102 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058593 | Defect DFCI-FI-57792 | Replace Flow gauge |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-02-06 | 2022-07-06 | 10 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058593 | Defect DFCI-FI-57792 | Replace Flow gauge |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-02-06 | 2022-07-06 | 20 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058593 | Defect DFCI-FI-57792 | Replace Flow gauge |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-02-06 | 2022-07-06 | 30 |  |  | DF /C /70/DF-PURGEGAS-2 | Replace Flow gauge | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235756 | 4Y 24V UPS-DP F.TEST DFBA-DP-1910 | ISOLATION BY ELECTRICAL | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-24 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /06/DFBA-DP-1910 | ISOLATION BY ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235756 | 4Y 24V UPS-DP F.TEST DFBA-DP-1910 | ISOLATION BY ELECTRICAL | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /06/DFBA-DP-1910 | ISOLATION BY ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235756 | 4Y 24V UPS-DP F.TEST DFBA-DP-1910 | ISOLATION BY ELECTRICAL | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 30 | AWSCSECE | AWSCSECE | DF /B /06/DFBA-DP-1910 | ISOLATION BY ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235756 | 4Y 24V UPS-DP F.TEST DFBA-DP-1910 | ISOLATION BY ELECTRICAL | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 40 | AWSCSECE | AWSCSECE | DF /B /06/DFBA-DP-1910 | ISOLATION BY ELECTRICAL | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400263358 | 1Y PROD. WATER & RECYCLE PUMP MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-07-29 | 2023-06-15 | 2023-07-15 | 10 | SECE | SECE | DF /C /27/DFCM-A-5030 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-INST | 2400263358 | 1Y PROD. WATER & RECYCLE PUMP MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-08-01 | 2023-06-15 | 2023-07-15 | 20 | SECE | SECE | DF /C /27/DFCM-A-5030 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-ELEC | 2400263358 | 1Y PROD. WATER & RECYCLE PUMP MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 9 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-01 | 2024-08-04 | 2023-06-15 | 2023-07-15 | 30 | SECE | SECE | DF /C /27/DFCM-A-5030 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400263358 | 1Y PROD. WATER & RECYCLE PUMP MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-04 | 2024-08-05 | 2023-06-15 | 2023-07-15 | 40 | SECE | SECE | DF /C /27/DFCM-A-5030 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400263358 | 1Y PROD. WATER & RECYCLE PUMP MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-06 | 2024-08-05 | 2024-08-06 | 2023-06-15 | 2023-07-15 | 50 | SECE | SECE | DF /C /27/DFCM-A-5030 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100062994 | DFB-04 Pigtails missing inst tubing (INS | Replace Flow transmitter tubing |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-04-23 | 2022-09-20 | 10 |  |  | DF /B /55/DFBA-FT-35025 | Replace Flow transmitter tubing | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100062994 | DFB-04 Pigtails missing inst tubing (INS | Replace Flow transmitter tubing |  |  | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2022-04-23 | 2022-09-20 | 20 |  |  | DF /B /55/DFBA-FT-35025 | Replace Flow transmitter tubing | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100062994 | DFB-04 Pigtails missing inst tubing (INS | Replace Flow transmitter tubing |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2022-04-23 | 2022-09-20 | 30 |  |  | DF /B /55/DFBA-FT-35025 | Replace Flow transmitter tubing | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026485 | Rep & return of PD-3933 | L3 Removal of pulsation damper |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-11-01 | 2024-07-29 | 2024-07-30 | 2018-04-29 | 2018-06-08 | 10 |  |  | DF /F /75/DFFA-PD-3933 | L3 Removal of pulsation damper | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026485 | Rep & return of PD-3933 | L3 Removal of pulsation damper |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-11-01 | 2024-07-30 | 2024-07-31 | 2018-04-29 | 2018-06-08 | 20 |  |  | DF /F /75/DFFA-PD-3933 | L3 Removal of pulsation damper | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026485 | Rep & return of PD-3933 | L3 Removal of pulsation damper |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-11-01 | 2024-07-31 | 2024-07-31 | 2018-04-29 | 2018-06-08 | 30 |  |  | DF /F /75/DFFA-PD-3933 | L3 Removal of pulsation damper | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100026485 | Rep & return of PD-3933 | L3 Removal of pulsation damper |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-11-01 | 2024-10-29 | 2024-10-31 | 2018-04-29 | 2018-06-08 | 40 |  |  | DF /F /75/DFFA-PD-3933 | L3 Removal of pulsation damper | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100026485 | Rep & return of PD-3933 | L3 Removal of pulsation damper |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-11-01 | 2024-10-31 | 2024-11-01 | 2018-04-29 | 2018-06-08 | 50 |  |  | DF /F /75/DFFA-PD-3933 | L3 Removal of pulsation damper | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 10 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 20 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 24 | 20 | Empty | 2024-07-15 | 2024-07-15 | 2023-12-16 | 2023-12-16 | 2023-06-03 | 2025-11-19 | 30 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 40 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 50 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 12 | 10 | Empty | 2024-07-15 | 2024-07-15 | 2023-12-16 | 2023-12-16 | 2023-06-03 | 2025-11-19 | 60 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 70 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 80 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 4 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 90 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012640 | Replace DFGA-PSV-500624A - PSV 2023 | new PSV | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 100 | PCNF | PCNF | DF /G /27/DFGA-PSV-500624A | new PSV | Unknown
A | DFF-TSEP | WPM | MTN-MECH | PRODTECH | 2400221584 | 1Y SDV LUBE/FUNC TEST TSEP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2022-12-24 | 2023-01-23 | 10 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-TSEP | WPM | MTN-MECH | MTN-MECH | 2400221584 | 1Y SDV LUBE/FUNC TEST TSEP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 9 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2022-12-24 | 2023-01-23 | 20 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-TSEP | WPM | MTN-MECH | PRODTECH | 2400221584 | 1Y SDV LUBE/FUNC TEST TSEP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2022-12-24 | 2023-01-23 | 30 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400306619 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 0 | Empty | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-20 | 2024-02-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100107868 | DFF HP oil oultet FT malfucntion | clearify with onshore what to do | SCH | SCH | 4 | 4 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-03 | 2024-07-08 | 2024-03-06 | 2024-07-19 | 10 | SCH | SCH | DF /F /20/DFFA-FT-340505 | clearify with onshore what to do | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107868 | DFF HP oil oultet FT malfucntion | clearify with onshore what to do | SCH | SCH | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-06 | 2024-07-19 | 20 | SCH | SCH | DF /F /20/DFFA-FT-340505 | clearify with onshore what to do | Unknown
3 | NOSD | WGN | INP-SITE | WELLSUPV | 2200007639 | X-ray of DFF-24-OCS-034-7014-AB-U | X-ray of DFF-24-OCS-034-7014-AB-U |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2021-07-31 | 2021-08-20 | 10 |  |  | DF /F /20/DFF-24-OCS-034-7014-AB-U | X-ray of DFF-24-OCS-034-7014-AB-U | Unknown
3 | NOSD | WGN | INP-SITE | MTN-SCAF | 2200007639 | X-ray of DFF-24-OCS-034-7014-AB-U | X-ray of DFF-24-OCS-034-7014-AB-U |  |  | 50 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-16 | 2021-07-31 | 2021-08-20 | 20 |  |  | DF /F /20/DFF-24-OCS-034-7014-AB-U | X-ray of DFF-24-OCS-034-7014-AB-U | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009222 | Insulation assist FORCE 20023 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /C /27/DFC-10-WOS-050-9031-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009222 | Insulation assist FORCE 20023 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /C /27/DFC-10-WOS-050-9031-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009222 | Insulation assist FORCE 20023 | Bilfinger inspection |  |  | 3 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 25 |  |  | DF /C /27/DFC-10-WOS-050-9031-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200009222 | Insulation assist FORCE 20023 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-11 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /C /27/DFC-10-WOS-050-9031-AB-U | Bilfinger inspection | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400106210 | 6M GALLEY (DFC-13A03) | 6m Galley Check |  |  | 24 | 0 | No VEND booking | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-27 | 2021-03-13 | 2021-04-01 | 10 |  |  | DF /C /82/CATERING-EQUIPMENT | 6m Galley Check | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400106210 | 6M GALLEY (DFC-13A03) | 6m Galley Check |  |  | 1 | 0 | No VEND booking | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2021-03-13 | 2021-04-01 | 20 |  |  | DF /C /82/CATERING-EQUIPMENT | 6m Galley Check | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400106210 | 6M GALLEY (DFC-13A03) | 6m Galley Check |  |  | 8 | 0 | No VEND booking | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2021-03-13 | 2021-04-01 | 30 |  |  | DF /C /82/CATERING-EQUIPMENT | 6m Galley Check | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400106210 | 6M GALLEY (DFC-13A03) | 6m Galley Check |  |  | 4 | 0 | No VEND booking | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2021-03-13 | 2021-04-01 | 40 |  |  | DF /C /82/CATERING-EQUIPMENT | 6m Galley Check | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400106210 | 6M GALLEY (DFC-13A03) | 6m Galley Check |  |  | 1 | 0 | No VEND booking | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-27 | 2021-03-13 | 2021-04-01 | 50 |  |  | DF /C /82/CATERING-EQUIPMENT | 6m Galley Check | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 10 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 20 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 22 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 1 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-07-03 | 2024-07-03 | 2024-10-12 | 2024-12-31 | 25 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 26 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 27 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 5 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2024-10-12 | 2024-12-31 | 30 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 4 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2024-10-12 | 2024-12-31 | 40 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-12-31 | 50 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284291 | PSV Calibration - DFFA-PSV-390530 | Remove PSV and Install blinds | AWSCSCH | AWSCSCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-09-02 | 2024-09-02 | 2024-09-02 | 2024-10-12 | 2024-12-31 | 60 | AWSCSCH | AWSCSCH | DF /F /75/DFFA-PSV-390530 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400342424 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-10 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 29 | 0 | Empty | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-09-03 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-10 | ATEX EQUIPMENT INSPECTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344055 | 3M AVIATION FUEL SKID MAINT-DFCI-A-5601 | AVIATION FUEL SKID MAINT-DFCI-A-5601 |  |  | 4 | 0 | W37-W38 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-22 | 10 |  |  | DF /C /81/DFCL-A-5602 | AVIATION FUEL SKID MAINT-DFCI-A-5601 | Unknown
D | NOSD | WPM | MTN-TURB | MTN-TURB | 2400344004 | 1M DFGA-GT-4302 Silencer Thermography | SAFETY INFORMATION |  |  | 0 | 0 | Empty | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-18 | 1 |  |  | DF /G /31/DFGA-GT-4302 | SAFETY INFORMATION | Unknown
D | NOSD | WPM | MTN-TURB | MTN-TURB | 2400344004 | 1M DFGA-GT-4302 Silencer Thermography | SAFETY INFORMATION |  |  | 2 | 0 | Empty | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-09-18 | 10 |  |  | DF /G /31/DFGA-GT-4302 | SAFETY INFORMATION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400342707 | DFA-12-PH-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 26 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /12/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2023-05-13 | 2023-09-25 | 10 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-07-31 | 2023-05-13 | 2023-09-25 | 20 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-07-31 | 2024-08-02 | 2023-05-13 | 2023-09-25 | 30 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-03 | 2023-05-13 | 2023-09-25 | 40 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-04 | 2023-05-13 | 2023-09-25 | 50 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-05-13 | 2023-09-25 | 60 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088254 | XCV-52210 can not be operated | Rigger assistance |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2023-05-13 | 2023-09-25 | 70 |  |  | DF /C /51/DFCM-XCV-52210 | Rigger assistance | Unknown
2 | DFF-LP-1 | WDF | MTN-MECH | MTN-MECH | 2100071502 | Cleaning of Lube oil suction Y-stainer f | ISOLATION |  |  | 1 | 0 | W35-W36 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-18 | 2022-07-11 | 2022-08-25 | 10 |  |  | DF /F /31/DFFA-P-4201 | ISOLATION | Unknown
2 | DFF-LP-1 | WDF | MTN-MECH | MTN-MECH | 2100071502 | Cleaning of Lube oil suction Y-stainer f | ISOLATION |  |  | 10 | 0 | W35-W36 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-21 | 2022-07-11 | 2022-08-25 | 20 |  |  | DF /F /31/DFFA-P-4201 | ISOLATION | Unknown
2 | DFF-LP-1 | WDF | MTN-MECH | MTN-MECH | 2100071502 | Cleaning of Lube oil suction Y-stainer f | ISOLATION |  |  | 1 | 0 | W35-W36 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2022-07-11 | 2022-08-25 | 30 |  |  | DF /F /31/DFFA-P-4201 | ISOLATION | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100092314 | SDBB external leak DFFA-PI-380110 | Isolate pressure gauge |  |  | 2.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-03 | 2026-05-21 | 10 |  |  | DF /F /34/INSTRUMENTS | Isolate pressure gauge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100092314 | SDBB external leak DFFA-PI-380110 | Isolate pressure gauge |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-03 | 2026-05-21 | 20 |  |  | DF /F /34/INSTRUMENTS | Isolate pressure gauge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100092314 | SDBB external leak DFFA-PI-380110 | Isolate pressure gauge |  |  | 2.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-03 | 2026-05-21 | 30 |  |  | DF /F /34/INSTRUMENTS | Isolate pressure gauge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100092314 | SDBB external leak DFFA-PI-380110 | Isolate pressure gauge |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-03 | 2026-05-21 | 40 |  |  | DF /F /34/INSTRUMENTS | Isolate pressure gauge | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100092314 | SDBB external leak DFFA-PI-380110 | Isolate pressure gauge |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-03 | 2026-05-21 | 50 |  |  | DF /F /34/INSTRUMENTS | Isolate pressure gauge | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003190 | CMAT:DFGA-ESDV-400423 Udskift def manome | Safing af ESDV - hydraulik systemet |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-03 | 2023-04-04 | 2018-03-08 | 2019-03-03 | 10 |  |  | DF /G /36/DFGA-ESDV-400423 | Safing af ESDV - hydraulik systemet | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003190 | CMAT:DFGA-ESDV-400423 Udskift def manome | Safing af ESDV - hydraulik systemet |  |  | 2 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-05 | 2018-03-08 | 2019-03-03 | 20 |  |  | DF /G /36/DFGA-ESDV-400423 | Safing af ESDV - hydraulik systemet | Unknown
4 | NOSD | WGN | PRODTECH | PRODTECH | 2200003190 | CMAT:DFGA-ESDV-400423 Udskift def manome | Safing af ESDV - hydraulik systemet |  |  | 6 | 0 | Empty | 2023-04-03 | 2023-04-06 | 2023-04-05 | 2023-04-06 | 2018-03-08 | 2019-03-03 | 30 |  |  | DF /G /36/DFGA-ESDV-400423 | Safing af ESDV - hydraulik systemet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | VEN-MECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 8 | 0 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2021-08-10 | 2021-08-10 | 2019-09-15 | 2020-02-12 | 10 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | VEN-MECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 6 | 2 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2019-07-01 | 2021-08-10 | 2019-09-15 | 2020-02-12 | 20 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | PRODTECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 3 | 0 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2019-09-15 | 2020-02-12 | 30 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 3 | 0 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2019-09-15 | 2020-02-12 | 40 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 3 | 0 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2019-09-15 | 2020-02-12 | 50 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | PRODTECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 3 | 0 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2019-09-15 | 2020-02-12 | 60 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
4 | DFCLPSEP | WDF | MTN-MECH | MTN-MECH | 2100022851 | Stuck HCV on DFC LP-sep. water outlet | Stuck HCV on DFC LP-sep. water outlet | PCNFAWSC | PCNFAWSC | 2 | 0 | Vendor + BL-TEAM | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2019-09-15 | 2020-02-12 | 70 | PCNFAWSC | PCNFAWSC | DF /C /20/DFCI-V-3403 | Stuck HCV on DFC LP-sep. water outlet | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337419 | 1Y SEWER TREATMENT UNIT DFCM-A-5101 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2024-04-18 | 2024-05-24 | 10 |  |  | DF /C /82/DFCM-A-5160 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400337419 | 1Y SEWER TREATMENT UNIT DFCM-A-5101 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2024-04-18 | 2024-05-24 | 20 |  |  | DF /C /82/DFCM-A-5160 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400337419 | 1Y SEWER TREATMENT UNIT DFCM-A-5101 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-04-18 | 2024-05-24 | 30 |  |  | DF /C /82/DFCM-A-5160 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 10 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 20 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 30 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 40 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 50 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 60 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 70 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 80 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 90 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 100 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 110 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 120 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 6 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 130 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 6 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 140 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 150 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 160 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 170 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 180 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 190 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 200 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 210 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 220 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 230 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 240 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100066176 | Replace lights DFA, DFA & DFB bridges | Isolate DFA lights accordingly | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-04-22 | 2022-07-21 | 250 | PCNF | PCNF | DF /A /62 | Isolate DFA lights accordingly | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 24 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-06 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-09 | 2024-12-10 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-10 | 2024-12-10 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-10 | 2024-12-11 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 12 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-11 | 2024-12-13 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-13 | 2024-12-13 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-13 | 2024-12-14 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-15 | 2024-12-15 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-15 | 2024-12-15 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-16 | 2024-12-16 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-SCAF | 2400284274 | PSV Calibration - DFFA-PSV-430038 | Scaffolding | AWSC | AWSC | 10 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-16 | 2024-12-17 | 2024-10-19 | 2024-12-31 | 130 | AWSC | AWSC | DF /F /31/DFFA-PSV-430038 | Scaffolding | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-15 | 2021-09-30 | 2021-11-09 | 10 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-16 | 2021-09-30 | 2021-11-09 | 20 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-16 | 2024-09-18 | 2021-09-30 | 2021-11-09 | 30 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-20 | 2021-09-30 | 2021-11-09 | 40 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-20 | 2024-09-21 | 2021-09-30 | 2021-11-09 | 50 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-21 | 2024-09-22 | 2021-09-30 | 2021-11-09 | 60 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2021-09-30 | 2021-11-09 | 70 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-23 | 2024-09-24 | 2021-09-30 | 2021-11-09 | 80 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-24 | 2021-09-30 | 2021-11-09 | 90 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2021-09-30 | 2021-11-09 | 100 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2021-09-30 | 2021-11-09 | 110 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055552 | Olie lækake fra XCV-301334 | Isolate hydraulics |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2021-09-30 | 2021-11-09 | 120 |  |  | DF /F /10/DFFA-XCV-301334 | Isolate hydraulics | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339047 | DFB_1Y_27050 INT STRUCT INSP - GVI | DFB_1Y_27050 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_27050 (MEZZANINE DECK) | DFB_1Y_27050 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100086705 | Replace defect floodlight DFGA-LN-18436 | scaffold up. |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-21 | 2023-04-18 | 2023-08-31 | 10 |  |  | DF /G /62 | scaffold up. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086705 | Replace defect floodlight DFGA-LN-18436 | scaffold up. |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-21 | 2023-04-18 | 2023-08-31 | 20 |  |  | DF /G /62 | scaffold up. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086705 | Replace defect floodlight DFGA-LN-18436 | scaffold up. |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-22 | 2023-04-18 | 2023-08-31 | 30 |  |  | DF /G /62 | scaffold up. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086705 | Replace defect floodlight DFGA-LN-18436 | scaffold up. |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-18 | 2023-08-31 | 40 |  |  | DF /G /62 | scaffold up. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100086705 | Replace defect floodlight DFGA-LN-18436 | scaffold up. |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-22 | 2024-09-27 | 2023-04-18 | 2023-08-31 | 50 |  |  | DF /G /62 | scaffold up. | Unknown
3 | DFG-IGF | WDF | MTN-MECH | PRODTECH | 2100025174 | CMAT:Clean Water clarifier quill. | L3 isolate quill and | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2019-05-31 | 2019-06-20 | 10 | AWSC | AWSC | DF /G /75/DFGA-CP-5001 | L3 isolate quill and | Unknown
3 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100025174 | CMAT:Clean Water clarifier quill. | L3 isolate quill and | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-23 | 2019-05-31 | 2019-06-20 | 20 | AWSC | AWSC | DF /G /75/DFGA-CP-5001 | L3 isolate quill and | Unknown
3 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100025174 | CMAT:Clean Water clarifier quill. | L3 isolate quill and | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2019-05-31 | 2019-06-20 | 30 | AWSC | AWSC | DF /G /75/DFGA-CP-5001 | L3 isolate quill and | Unknown
3 | DFG-IGF | WDF | MTN-MECH | PRODTECH | 2100025174 | CMAT:Clean Water clarifier quill. | L3 isolate quill and | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2019-05-31 | 2019-06-20 | 40 | AWSC | AWSC | DF /G /75/DFGA-CP-5001 | L3 isolate quill and | Unknown
3 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100025174 | CMAT:Clean Water clarifier quill. | L3 isolate quill and | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2019-05-31 | 2019-06-20 | 50 | AWSC | AWSC | DF /G /75/DFGA-CP-5001 | L3 isolate quill and | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100097868 | DFB - FB vent frame arrestor | Additional materials | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-26 | 2024-03-09 | 10 | SECE | SECE | DF /B /36/DFBA-FA-4004 | Additional materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097868 | DFB - FB vent frame arrestor | Additional materials | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-26 | 2024-03-09 | 20 | SECE | SECE | DF /B /36/DFBA-FA-4004 | Additional materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 2 | 11 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 10 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 12 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 30 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 15 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 40 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 9 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 50 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 9 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 60 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 9 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 70 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 9 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 80 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 9 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 90 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 24 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 100 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 9 | 29 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-01-13 | 2022-04-13 | 110 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100060315 | Replace nozzels - DFA/B/C/E/F/G | Replace/Clean Nozzle DFAA-X-0322 | PCNF | PCNF | 15 | 22 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2022-01-13 | 2022-04-13 | 120 | PCNF | PCNF | DF /A /01 | Replace/Clean Nozzle DFAA-X-0322 | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235573 | 4Y 380V UPS-DP MAINT-DFBA-DP-1834-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-01-01 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-B04 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235573 | 4Y 380V UPS-DP MAINT-DFBA-DP-1834-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 14 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-01-01 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-B04 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235573 | 4Y 380V UPS-DP MAINT-DFBA-DP-1834-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-26 | 2023-01-01 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-B04 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235573 | 4Y 380V UPS-DP MAINT-DFBA-DP-1834-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-01-01 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-B04 | ISOLATION ELECTRICAL | Unknown
3 | DFG20MPH | WDF | MTN-MECH | MTN-RIGG | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 6 | 5 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2020-02-05 | 2020-05-05 | 10 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2020-02-05 | 2020-05-05 | 20 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 14 | 51 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2020-02-05 | 2020-05-05 | 30 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 4 | 4 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-05 | 2020-02-05 | 2020-05-05 | 40 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2020-02-05 | 2020-05-05 | 50 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | MTN-RIGG | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 4 | 6 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2020-02-05 | 2020-05-05 | 60 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2020-02-05 | 2020-05-05 | 70 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
3 | DFG20MPH | WDF | MTN-MECH | MTN-SCAF | 2100026509 | DFG Lvl 2 Replace BDV 380137 | Rig-up hoist for removal of BDV 380137 | AWSC | AWSC | 18 | 30 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-06 | 2020-02-05 | 2020-05-05 | 80 | AWSC | AWSC | DF /G /34/DFGA-BDV-380137 | Rig-up hoist for removal of BDV 380137 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259013 | 6M SDV LUB/MAINT LPSEP - DFC | SDV LUB/INSP LPSEP - DFC |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-26 | 2023-06-11 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP LPSEP - DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235787 | 4Y 380V N-SWB MAINT-DFCC-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235787 | 4Y 380V N-SWB MAINT-DFCC-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235787 | 4Y 380V N-SWB MAINT-DFCC-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235787 | 4Y 380V N-SWB MAINT-DFCC-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059732 | Replace defect valve on DFCC-HR-0334 | Prod prepare permit/isolations |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-12-23 | 2022-02-01 | 10 |  |  | DF /C /01/DFCC-HR-0334 | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059732 | Replace defect valve on DFCC-HR-0334 | Prod prepare permit/isolations |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-12-23 | 2022-02-01 | 20 |  |  | DF /C /01/DFCC-HR-0334 | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059732 | Replace defect valve on DFCC-HR-0334 | Prod prepare permit/isolations |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-23 | 2022-02-01 | 30 |  |  | DF /C /01/DFCC-HR-0334 | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059732 | Replace defect valve on DFCC-HR-0334 | Prod prepare permit/isolations |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-23 | 2022-02-01 | 40 |  |  | DF /C /01/DFCC-HR-0334 | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059732 | Replace defect valve on DFCC-HR-0334 | Prod prepare permit/isolations |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-23 | 2022-02-01 | 50 |  |  | DF /C /01/DFCC-HR-0334 | Prod prepare permit/isolations | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059732 | Replace defect valve on DFCC-HR-0334 | Prod prepare permit/isolations |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-12-23 | 2022-02-01 | 60 |  |  | DF /C /01/DFCC-HR-0334 | Prod prepare permit/isolations | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235831 | 4Y 380V E-SWB MAINT DFFA-N-1813-01 | Increase of PO 4500119437 | SCH | SCH | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1813-01 | Increase of PO 4500119437 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235831 | 4Y 380V E-SWB MAINT DFFA-N-1813-01 | Increase of PO 4500119437 | SCH | SCH | 6 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1813-01 | Increase of PO 4500119437 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235831 | 4Y 380V E-SWB MAINT DFFA-N-1813-01 | Increase of PO 4500119437 | SCH | SCH | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1813-01 | Increase of PO 4500119437 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235831 | 4Y 380V E-SWB MAINT DFFA-N-1813-01 | Increase of PO 4500119437 | SCH | SCH | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1813-01 | Increase of PO 4500119437 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235831 | 4Y 380V E-SWB MAINT DFFA-N-1813-01 | Increase of PO 4500119437 | SCH | SCH | 0 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2023-04-15 | 2023-06-27 | 50 | SCH | SCH | DF /F /05/DFFA-N-1813-01 | Increase of PO 4500119437 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235831 | 4Y 380V E-SWB MAINT DFFA-N-1813-01 | Increase of PO 4500119437 | SCH | SCH | 0 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2023-04-15 | 2023-06-27 | 60 | SCH | SCH | DF /F /05/DFFA-N-1813-01 | Increase of PO 4500119437 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024987 | PVI LG-340033 Lower leg blocked to level | Lower leg blocked to level glass | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2020-01-12 | 2020-04-11 | 10 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100024987 | PVI LG-340033 Lower leg blocked to level | Lower leg blocked to level glass | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2020-01-12 | 2020-04-11 | 20 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024987 | PVI LG-340033 Lower leg blocked to level | Lower leg blocked to level glass | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-03 | 2020-01-12 | 2020-04-11 | 30 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100024987 | PVI LG-340033 Lower leg blocked to level | Lower leg blocked to level glass | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-03 | 2024-08-05 | 2020-01-12 | 2020-04-11 | 40 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Lower leg blocked to level glass | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100024987 | PVI LG-340033 Lower leg blocked to level | Lower leg blocked to level glass | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2020-01-12 | 2020-04-11 | 50 | AWSC | AWSC | DF /F /20/DFFA-LG-340033 | Lower leg blocked to level glass | Unknown
3 | Empty | WGN | UNKNOWN | WELLSUPV | 2200014245 | B10 Switch | B10 Switch |  |  | 0 | 0 | Empty | 2023-06-11 | 2023-06-11 | 2023-06-11 | 2023-06-11 | 2023-06-11 | 2023-10-24 | 10 |  |  | DF | B10 Switch | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400325354 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235633 | 4Y 380V N-SWB MAINT-DFFA-N-1803-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235633 | 4Y 380V N-SWB MAINT-DFFA-N-1803-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235633 | 4Y 380V N-SWB MAINT-DFFA-N-1803-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235633 | 4Y 380V N-SWB MAINT-DFFA-N-1803-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803-02 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400215377 | 3M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-11-06 | 2022-11-16 | 10 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
3 | DFA-O18 | WDF | MTN-INST | PRODTECH | 2100050463 | DFA-18 flowline press trans low signal. | Install new tubing for PIT | AWSC | AWSC | 2 | 0 | Align WL - Mat on HOLD | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-06-18 | 2021-09-16 | 10 | AWSC | AWSC | DF /A /10/DFAA-PT-30210 | Install new tubing for PIT | Unknown
3 | DFA-O18 | WDF | MTN-INST | MTN-INST | 2100050463 | DFA-18 flowline press trans low signal. | Install new tubing for PIT | AWSC | AWSC | 6 | 0 | Align WL - Mat on HOLD | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-06-18 | 2021-09-16 | 20 | AWSC | AWSC | DF /A /10/DFAA-PT-30210 | Install new tubing for PIT | Unknown
3 | DFA-O18 | WDF | MTN-INST | PRODTECH | 2100050463 | DFA-18 flowline press trans low signal. | Install new tubing for PIT | AWSC | AWSC | 2 | 0 | Align WL - Mat on HOLD | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-06-18 | 2021-09-16 | 30 | AWSC | AWSC | DF /A /10/DFAA-PT-30210 | Install new tubing for PIT | Unknown
C | NOSD | WPM | MTN-INST | VEN-INST | 2400306654 | 4Y H2S ANALYSER MAINT-DFFA-A-37200 | H2S ANALYSER MAINT-DFFA-A-37200 | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2023-11-21 | 2024-02-17 | 10 | AWSC | AWSC | DF /F /34/DFFA-A-37200 | H2S ANALYSER MAINT-DFFA-A-37200 | Unknown
C | NOSD | WPM | MTN-INST | MTN-TELE | 2400306654 | 4Y H2S ANALYSER MAINT-DFFA-A-37200 | H2S ANALYSER MAINT-DFFA-A-37200 | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-25 | 2023-11-21 | 2024-02-17 | 20 | AWSC | AWSC | DF /F /34/DFFA-A-37200 | H2S ANALYSER MAINT-DFFA-A-37200 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056271 | DFCM/78: Gantry motor noise from blower | Investigate end cover on motor blower | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-01-21 | 2022-09-18 | 10 | PCNF | PCNF | DF /C /78/DFCM-X-6105 | Investigate end cover on motor blower | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056271 | DFCM/78: Gantry motor noise from blower | Investigate end cover on motor blower | PCNF | PCNF | 2 | 14 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-01-21 | 2022-09-18 | 20 | PCNF | PCNF | DF /C /78/DFCM-X-6105 | Investigate end cover on motor blower | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056271 | DFCM/78: Gantry motor noise from blower | Investigate end cover on motor blower | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-01-21 | 2022-09-18 | 30 | PCNF | PCNF | DF /C /78/DFCM-X-6105 | Investigate end cover on motor blower | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056271 | DFCM/78: Gantry motor noise from blower | Investigate end cover on motor blower | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-01-21 | 2022-09-18 | 40 | PCNF | PCNF | DF /C /78/DFCM-X-6105 | Investigate end cover on motor blower | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097351 | DFGA-HRW-03101 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 10 | SECE | SECE | DF /G /01/DFGA-HRW-03101 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097351 | DFGA-HRW-03101 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 2 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 20 | SECE | SECE | DF /G /01/DFGA-HRW-03101 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097351 | DFGA-HRW-03101 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 30 | SECE | SECE | DF /G /01/DFGA-HRW-03101 | Replace hose on hosereel | Unknown
3 | DFA-W10 | WDF | MTN-MECH | MTN-RIGG | 2100096131 | DFA-10 choke extern water leak. | Isolate choke |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-09-17 | 2024-01-30 | 10 |  |  | DF /A /55/DFAA-CVA-30010 | Isolate choke | Unknown
3 | DFA-W10 | WDF | MTN-MECH | PRODTECH | 2100096131 | DFA-10 choke extern water leak. | Isolate choke |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-23 | 2023-09-17 | 2024-01-30 | 20 |  |  | DF /A /55/DFAA-CVA-30010 | Isolate choke | Unknown
3 | DFA-W10 | WDF | MTN-MECH | MTN-RIGG | 2100096131 | DFA-10 choke extern water leak. | Isolate choke |  |  | 10 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-25 | 2023-09-17 | 2024-01-30 | 30 |  |  | DF /A /55/DFAA-CVA-30010 | Isolate choke | Unknown
3 | DFA-W10 | WDF | MTN-MECH | MTN-MECH | 2100096131 | DFA-10 choke extern water leak. | Isolate choke |  |  | 10 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-25 | 2023-09-17 | 2024-01-30 | 40 |  |  | DF /A /55/DFAA-CVA-30010 | Isolate choke | Unknown
3 | DFA-W10 | WDF | MTN-MECH | PRODTECH | 2100096131 | DFA-10 choke extern water leak. | Isolate choke |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2023-09-17 | 2024-01-30 | 50 |  |  | DF /A /55/DFAA-CVA-30010 | Isolate choke | Unknown
3 | DFA-W10 | WDF | MTN-MECH | MTN-RIGG | 2100096131 | DFA-10 choke extern water leak. | Isolate choke |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-09-17 | 2024-01-30 | 60 |  |  | DF /A /55/DFAA-CVA-30010 | Isolate choke | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100070404 | 1Y follow up of water damage Project | 1Y follow up of water damage Project | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-08-01 | 2022-12-14 | 10 | PCNF | PCNF | DF /C /09/ACCOMMODATION-LEVEL-1 | 1Y follow up of water damage Project | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100070404 | 1Y follow up of water damage Project | 1Y follow up of water damage Project | PCNF | PCNF | 24 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-08-01 | 2022-12-14 | 20 | PCNF | PCNF | DF /C /09/ACCOMMODATION-LEVEL-1 | 1Y follow up of water damage Project | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100070404 | 1Y follow up of water damage Project | 1Y follow up of water damage Project | PCNF | PCNF | 6 | 14 | Empty | 2024-07-15 | 2024-07-15 | 2022-08-24 | 2023-10-12 | 2022-08-01 | 2022-12-14 | 30 | PCNF | PCNF | DF /C /09/ACCOMMODATION-LEVEL-1 | 1Y follow up of water damage Project | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100070404 | 1Y follow up of water damage Project | 1Y follow up of water damage Project | PCNF | PCNF | 4 | 8 | Empty | 2024-07-15 | 2024-07-15 | 2022-08-25 | 2023-10-12 | 2022-08-01 | 2022-12-14 | 40 | PCNF | PCNF | DF /C /09/ACCOMMODATION-LEVEL-1 | 1Y follow up of water damage Project | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100070404 | 1Y follow up of water damage Project | 1Y follow up of water damage Project | PCNF | PCNF | 8 | 0 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-08-01 | 2022-12-14 | 50 | PCNF | PCNF | DF /C /09/ACCOMMODATION-LEVEL-1 | 1Y follow up of water damage Project | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095415 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-09-05 | 2024-01-18 | 10 |  |  | DF /A /05/DFAA-N-1801-04 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095415 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-09-05 | 2024-01-18 | 20 |  |  | DF /A /05/DFAA-N-1801-04 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095415 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-09-05 | 2024-01-18 | 30 |  |  | DF /A /05/DFAA-N-1801-04 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095415 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-09-05 | 2024-01-18 | 40 |  |  | DF /A /05/DFAA-N-1801-04 | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095415 | udskife batterier/spoler efter lystjek | Isolate Equipment. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-09-05 | 2024-01-18 | 50 |  |  | DF /A /05/DFAA-N-1801-04 | Isolate Equipment. | Unknown
4 | NOSD | WRO | VEN-ELEC | VEN-ELEC | 2300004032 | DK40 Switchgear / Light Team consumables | Rope access equipm Semco |  |  | 0 | 0 | Empty | 2023-01-08 | 2023-01-08 | 2023-01-08 | 2023-01-08 | 2023-01-08 | 2025-06-26 | 10 |  |  | DF /C /61 | Rope access equipm Semco | Unknown
4 | NOSD | WRO | VEN-ELEC | VEN-ELEC | 2300004032 | DK40 Switchgear / Light Team consumables | Rope access equipm Semco |  |  | 0 | 0 | Empty | 2023-01-08 | 2023-01-08 | 2023-01-08 | 2023-01-08 | 2023-01-08 | 2025-06-26 | 20 |  |  | DF /C /61 | Rope access equipm Semco | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055328 | Change Floodlight DFG | Additional materials |  |  | 0.5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-04 | 2022-05-03 | 10 |  |  | DF /G /62 | Additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055328 | Change Floodlight DFG | Additional materials |  |  | 4 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-04 | 2022-05-03 | 20 |  |  | DF /G /62 | Additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055328 | Change Floodlight DFG | Additional materials |  |  | 0.5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-12-04 | 2022-05-03 | 30 |  |  | DF /G /62 | Additional materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055328 | Change Floodlight DFG | Additional materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-12-04 | 2022-05-03 | 40 |  |  | DF /G /62 | Additional materials | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 2 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 3 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 4 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 5 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 7 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 8 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | PRODTECH | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2018-07-21 | 2018-08-30 | 10 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2018-07-21 | 2018-08-30 | 11 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2018-07-21 | 2018-08-30 | 12 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2018-07-21 | 2018-08-30 | 13 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-05 | 2018-07-21 | 2018-08-30 | 14 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-MECH | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2018-07-21 | 2018-08-30 | 19 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-PIPF | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2018-07-21 | 2018-08-30 | 20 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | PRODTECH | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2018-07-21 | 2018-08-30 | 30 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
3 | DFGFLARE | WDF | MTN-ROPE | MTN-ROPE | 2100023776 | ANOPR DFF Korroderet flang på flare syst | Check PTW/Site visit. | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2018-07-21 | 2018-08-30 | 40 | AWSC | AWSC | DF /F /36 | Check PTW/Site visit. | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400328736 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-21 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 30 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-04-08 | 2024-06-09 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-21 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 10 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 10 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 20 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 3 | 2 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 30 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 40 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 50 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 4 | 18 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 60 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 2 | 18 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 80 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 90 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2022-11-16 | 2023-03-31 | 100 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 110 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 4 | 6 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 120 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 2 | 18 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 130 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2022-11-16 | 2023-03-31 | 150 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100075617 | No flow/pressure from P-3960 | Erect/Dismantle Scaffold Gallow | PCNFSCH | PCNFSCH | 6 | 3 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2022-11-16 | 2023-03-31 | 160 | PCNFSCH | PCNFSCH | DF /G /75/DFGA-P-3960 | Erect/Dismantle Scaffold Gallow | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346557 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0326 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0326 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346557 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0326 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0326 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346557 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0326 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0326 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346557 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0326 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0326 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346557 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0326 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0326 | ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245862 | 4Y HVAC COOL UNIT VENDOR DFCI-A-12074 | PERSONAL ISOLATION | AWSC | AWSC | 1 | 1 | W17-W18 | 2024-04-26 | 2024-05-05 | 2024-04-26 | 2024-04-26 | 2023-01-28 | 2023-05-25 | 10 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245862 | 4Y HVAC COOL UNIT VENDOR DFCI-A-12074 | PERSONAL ISOLATION | AWSC | AWSC | 30 | 24 | W17-W18 | 2024-04-26 | 2024-05-05 | 2024-04-26 | 2024-05-03 | 2023-01-28 | 2023-05-25 | 20 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400245862 | 4Y HVAC COOL UNIT VENDOR DFCI-A-12074 | PERSONAL ISOLATION | AWSC | AWSC | 6 | 3 | W17-W18 | 2024-04-26 | 2024-05-05 | 2024-05-03 | 2024-05-05 | 2023-01-28 | 2023-05-25 | 30 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245862 | 4Y HVAC COOL UNIT VENDOR DFCI-A-12074 | PERSONAL ISOLATION | AWSC | AWSC | 1 | 1 | W17-W18 | 2024-04-26 | 2024-05-05 | 2024-05-05 | 2024-05-05 | 2023-01-28 | 2023-05-25 | 40 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245862 | 4Y HVAC COOL UNIT VENDOR DFCI-A-12074 | PERSONAL ISOLATION | AWSC | AWSC | 2 | 2 | W17-W18 | 2024-04-26 | 2024-05-05 | 2024-05-05 | 2024-05-05 | 2023-01-28 | 2023-05-25 | 50 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245862 | 4Y HVAC COOL UNIT VENDOR DFCI-A-12074 | PERSONAL ISOLATION | AWSC | AWSC | 0 | 0 | W17-W18 | 2024-04-26 | 2024-05-05 | 2024-04-26 | 2024-04-26 | 2023-01-28 | 2023-05-25 | 60 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | PERSONAL ISOLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023563 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 3.399999999999999911182158029 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2018-03-10 | 2018-06-08 | 5 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100023563 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 10 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023563 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 1 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 15 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023563 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 20 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023563 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-15 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 25 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100023563 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-15 | 2023-02-16 | 2018-03-10 | 2018-06-08 | 30 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060124 | Replace JB 1855-0056-L2-A1 | Prove dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-01-09 | 2022-04-09 | 10 |  |  | DF /G /61/DFGA-DP-1855-56 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060124 | Replace JB 1855-0056-L2-A1 | Prove dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-01-09 | 2022-04-09 | 20 |  |  | DF /G /61/DFGA-DP-1855-56 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060124 | Replace JB 1855-0056-L2-A1 | Prove dead |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2022-01-09 | 2022-04-09 | 30 |  |  | DF /G /61/DFGA-DP-1855-56 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060124 | Replace JB 1855-0056-L2-A1 | Prove dead |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-27 | 2022-01-09 | 2022-04-09 | 40 |  |  | DF /G /61/DFGA-DP-1855-56 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060124 | Replace JB 1855-0056-L2-A1 | Prove dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2022-01-09 | 2022-04-09 | 50 |  |  | DF /G /61/DFGA-DP-1855-56 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060124 | Replace JB 1855-0056-L2-A1 | Prove dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2022-01-09 | 2022-04-09 | 60 |  |  | DF /G /61/DFGA-DP-1855-56 | Prove dead | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2016-06-22 | 2016-08-22 | 10 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2016-06-22 | 2016-08-22 | 20 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2016-06-22 | 2016-08-22 | 30 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2016-06-22 | 2016-08-22 | 40 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2016-06-22 | 2016-08-22 | 50 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2016-06-22 | 2016-08-22 | 60 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2016-06-22 | 2016-08-22 | 70 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100025102 | PMAT:@+Skift af HCV vent på DFFA-T-5052. | Line for missing Bolts | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2016-06-22 | 2016-08-22 | 80 | AWSC | AWSC | DF /F /28/DFFA-T-5052 | Line for missing Bolts | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339283 | DFF_1Y_46975 INT STRUCT INSP - GVI | DFF_1Y_46975 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_46975 (WL MODULE DECK) | DFF_1Y_46975 INT STRUCT INSP - GVI | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400219097 | 1Y CHOKE VALVES/INSTR MAINT - DFF | ISOLATION BY PRODUCTION |  |  | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-08-26 | 2024-09-02 | 2022-11-15 | 2022-12-15 | 10 |  |  | DF /F /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400219097 | 1Y CHOKE VALVES/INSTR MAINT - DFF | ISOLATION BY PRODUCTION |  |  | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-09-02 | 2024-09-09 | 2022-11-15 | 2022-12-15 | 20 |  |  | DF /F /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400219097 | 1Y CHOKE VALVES/INSTR MAINT - DFF | ISOLATION BY PRODUCTION |  |  | 14 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-09-09 | 2024-09-12 | 2022-11-15 | 2022-12-15 | 30 |  |  | DF /F /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400219097 | 1Y CHOKE VALVES/INSTR MAINT - DFF | ISOLATION BY PRODUCTION |  |  | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-19 | 2024-09-12 | 2024-09-19 | 2022-11-15 | 2022-12-15 | 40 |  |  | DF /F /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400282066 | 8000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION AND FUNCTION TEST | AWSCSCH | AWSCSCH | 12 | 2 | W37-38 | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2023-12-18 | 2024-01-17 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | VISUAL INSPECTION AND FUNCTION TEST | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-INST | 2400282066 | 8000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION AND FUNCTION TEST | AWSCSCH | AWSCSCH | 10 | 0 | W37-38 | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-25 | 2023-12-18 | 2024-01-17 | 20 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | VISUAL INSPECTION AND FUNCTION TEST | Unknown
A | DFF-IPHP | WPM | MTN-TURB | MTN-ELEC | 2400282066 | 8000H IN/OUTSIDE SKID, COUNTER | VISUAL INSPECTION AND FUNCTION TEST | AWSCSCH | AWSCSCH | 4 | 0 | W37-38 | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-12-18 | 2024-01-17 | 30 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | VISUAL INSPECTION AND FUNCTION TEST | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100047667 | DFA-15 PT-30303 ekstern leak | Monitor process | AWSC | AWSC | 0.5 | 0 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-03-26 | 2021-04-15 | 97 | AWSC | AWSC | DF /A /10/DFAA-PT-30303 | Monitor process | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100047667 | DFA-15 PT-30303 ekstern leak | Monitor process | AWSC | AWSC | 1 | 0 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-03-26 | 2021-04-15 | 98 | AWSC | AWSC | DF /A /10/DFAA-PT-30303 | Monitor process | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100047667 | DFA-15 PT-30303 ekstern leak | Monitor process | AWSC | AWSC | 4 | 0 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-03-26 | 2021-04-15 | 101 | AWSC | AWSC | DF /A /10/DFAA-PT-30303 | Monitor process | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100047667 | DFA-15 PT-30303 ekstern leak | Monitor process | AWSC | AWSC | 1 | 0 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-03-26 | 2021-04-15 | 199 | AWSC | AWSC | DF /A /10/DFAA-PT-30303 | Monitor process | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100047667 | DFA-15 PT-30303 ekstern leak | Monitor process | AWSC | AWSC | 1 | 0 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-03-26 | 2021-04-15 | 400 | AWSC | AWSC | DF /A /10/DFAA-PT-30303 | Monitor process | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100047667 | DFA-15 PT-30303 ekstern leak | Monitor process | AWSC | AWSC | 0.5 | 0 | Empty | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2021-03-26 | 2021-04-15 | 402 | AWSC | AWSC | DF /A /10/DFAA-PT-30303 | Monitor process | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 5 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 4 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284224 | PSV Exchange - DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | AWSC | AWSC | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /A /07/DFAA-PSV-30086 | DFAA-PSV-30086 Offshore from WS Måde | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400285953 | 6M PRIME MOVER DFBA-MD-6102 | PRIME MOVER MAINTENANCE DFBA-MD-6102 |  |  | 16 | 0 | W23-W24 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2024-03-01 | 2024-03-17 | 10 |  |  | DF /B /78/DFBA-MD-6102 | PRIME MOVER MAINTENANCE DFBA-MD-6102 | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100060619 | Heater on DFF main HVAC tripped | Order new heating element | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2022-02-03 | 2023-10-27 | 2021-12-30 | 2022-01-19 | 10 | PCNFSCH | PCNFSCH | DF /F /09/DFFA-XE-1203 | Order new heating element | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060619 | Heater on DFF main HVAC tripped | Order new heating element | PCNFSCH | PCNFSCH | 8 | 24 | Empty | 2024-07-30 | 2024-07-30 | 2022-02-03 | 2023-10-27 | 2021-12-30 | 2022-01-19 | 20 | PCNFSCH | PCNFSCH | DF /F /09/DFFA-XE-1203 | Order new heating element | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100060619 | Heater on DFF main HVAC tripped | Order new heating element | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2022-02-03 | 2023-10-27 | 2021-12-30 | 2022-01-19 | 30 | PCNFSCH | PCNFSCH | DF /F /09/DFFA-XE-1203 | Order new heating element | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060619 | Heater on DFF main HVAC tripped | Order new heating element | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2022-02-06 | 2023-10-27 | 2021-12-30 | 2022-01-19 | 40 | PCNFSCH | PCNFSCH | DF /F /09/DFFA-XE-1203 | Order new heating element | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060619 | Heater on DFF main HVAC tripped | Order new heating element | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-12-30 | 2022-01-19 | 50 | PCNFSCH | PCNFSCH | DF /F /09/DFFA-XE-1203 | Order new heating element | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235849 | 4Y 400V E-SWB MAINT DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235849 | 4Y 400V E-SWB MAINT DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235849 | 4Y 400V E-SWB MAINT DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235849 | 4Y 400V E-SWB MAINT DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A12 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100106754 | DFE ESDV-45004 defective SOV/blok | New solenoid valve |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-05 | 2024-03-21 | 10 |  |  | DF /E /37/DFEZ-ESDV-45004 | New solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106754 | DFE ESDV-45004 defective SOV/blok | New solenoid valve |  |  | 0.5 | 6 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-05 | 2024-03-21 | 20 |  |  | DF /E /37/DFEZ-ESDV-45004 | New solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106754 | DFE ESDV-45004 defective SOV/blok | New solenoid valve |  |  | 2.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-05 | 2024-03-21 | 30 |  |  | DF /E /37/DFEZ-ESDV-45004 | New solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106754 | DFE ESDV-45004 defective SOV/blok | New solenoid valve |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-05 | 2024-03-21 | 40 |  |  | DF /E /37/DFEZ-ESDV-45004 | New solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100106754 | DFE ESDV-45004 defective SOV/blok | New solenoid valve |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-05 | 2024-03-21 | 50 |  |  | DF /E /37/DFEZ-ESDV-45004 | New solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106754 | DFE ESDV-45004 defective SOV/blok | New solenoid valve |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-02-05 | 2024-03-21 | 60 |  |  | DF /E /37/DFEZ-ESDV-45004 | New solenoid valve | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 8.699999999999999289457264236 | 0 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 8.699999999999999289457264236 | 7.5 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2021-01-12 | 2021-01-21 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 20 | 35 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2020-08-21 | 2020-12-13 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 8 | 9 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2020-09-09 | 2020-09-16 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 12 | 0 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 8 | 7 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2021-01-11 | 2021-03-27 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 14 | 63.5 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2025-12-31 | 2025-12-31 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002916 | DFF-Insulation assists FORCE 13341. | L3 Prepare Permit Lagger | PCNF | PCNF | 0 | 0 | CON-ELEC req'd | 2021-01-20 | 2026-01-02 | 2021-03-27 | 2021-03-27 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /F /27/DFF-2-DPS-050-8073-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107866 | Defekt handel on FT-35037 well 24 | Isolate pressure transmitters |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-04-04 | 2024-08-17 | 10 |  |  | DF /B /55/DFBA-FT-35037 | Isolate pressure transmitters | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107866 | Defekt handel on FT-35037 well 24 | Isolate pressure transmitters |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-04-04 | 2024-08-17 | 20 |  |  | DF /B /55/DFBA-FT-35037 | Isolate pressure transmitters | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107866 | Defekt handel on FT-35037 well 24 | Isolate pressure transmitters |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-04-04 | 2024-08-17 | 30 |  |  | DF /B /55/DFBA-FT-35037 | Isolate pressure transmitters | Unknown
3 | NOSD | WGN | PRODTECH | PRODTECH | 2200016250 | Test of new Firefighters helmets & comms | FPS-COM 5000 to test |  |  | 9 | 0 | Empty | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2023-12-10 | 2024-04-23 | 10 |  |  | DF /C /02/DFCI-FE-0641 | FPS-COM 5000 to test | Unknown
3 | NOSD | WGN | PRODTECH | PRODTECH | 2200016250 | Test of new Firefighters helmets & comms | FPS-COM 5000 to test |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-16 | 2024-03-16 | 2024-03-16 | 2023-12-10 | 2024-04-23 | 20 |  |  | DF /C /02/DFCI-FE-0641 | FPS-COM 5000 to test | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200004578 | Fireguard assistance Force 8/12 - 21/12 | Fireguard for Force X-ray | PCNF | PCNF | 0 | 13 | Empty | 2022-12-31 | 2023-01-10 | 2022-12-31 | 2022-12-31 | 2020-09-17 | 2020-12-16 | 10 | PCNF | PCNF | DF /C | Fireguard for Force X-ray | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200004578 | Fireguard assistance Force 8/12 - 21/12 | Fireguard for Force X-ray | PCNF | PCNF | 162 | 22 | Empty | 2022-12-31 | 2023-01-10 | 2022-12-31 | 2023-01-10 | 2020-09-17 | 2020-12-16 | 20 | PCNF | PCNF | DF /C | Fireguard for Force X-ray | Unknown
A | DFCHPSEP | WPM | MTN-MECH | PRODTECH | 2400215980 | 1Y SDV LUBE/FUNC TEST HPSEP - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-11-07 | 2022-12-07 | 10 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFCHPSEP | WPM | MTN-MECH | MTN-MECH | 2400215980 | 1Y SDV LUBE/FUNC TEST HPSEP - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2022-11-07 | 2022-12-07 | 20 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFCHPSEP | WPM | MTN-MECH | PRODTECH | 2400215980 | 1Y SDV LUBE/FUNC TEST HPSEP - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2022-11-07 | 2022-12-07 | 30 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235781 | 4Y 400V N-DP MAINT-DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235781 | 4Y 400V N-DP MAINT-DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | AWSC | AWSC | 27 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-28 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235781 | 4Y 400V N-DP MAINT-DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-29 | 2024-10-01 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235781 | 4Y 400V N-DP MAINT-DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-DP-1832-A | 400V N-DP INSP-DFFB-DP-1832-A | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235582 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829B | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1829B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235582 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829B | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1829B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235582 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829B | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1829B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235582 | 4Y 220V HT-DP-MAINT-DFCI-DP-1829B | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1829B | ISOLATION ELECTRICAL | Unknown
4 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100022386 | DFFA-XCV-500042 valve and actuator has t | L3 Isolate DFFA-XCV-500042 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2018-05-13 | 2018-10-10 | 10 | AWSC | AWSC | DF /F /27/DFFA-XCV-500042 | L3 Isolate DFFA-XCV-500042 | Unknown
4 | DAN-OIL | WDF | MTN-MECH | MTN-ELEC | 2100022386 | DFFA-XCV-500042 valve and actuator has t | L3 Isolate DFFA-XCV-500042 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-05-13 | 2018-10-10 | 15 | AWSC | AWSC | DF /F /27/DFFA-XCV-500042 | L3 Isolate DFFA-XCV-500042 | Unknown
4 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100022386 | DFFA-XCV-500042 valve and actuator has t | L3 Isolate DFFA-XCV-500042 | AWSC | AWSC | 5 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-05-13 | 2018-10-10 | 20 | AWSC | AWSC | DF /F /27/DFFA-XCV-500042 | L3 Isolate DFFA-XCV-500042 | Unknown
4 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100022386 | DFFA-XCV-500042 valve and actuator has t | L3 Isolate DFFA-XCV-500042 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2018-05-13 | 2018-10-10 | 30 | AWSC | AWSC | DF /F /27/DFFA-XCV-500042 | L3 Isolate DFFA-XCV-500042 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058423 | DFF-FCV-390187 DFF-17 Chem Flow. | Replace DFFA-FCV-390187 |  |  | 25 | 0 | W31-W32 | 2024-07-29 | 2024-08-11 | 2024-07-29 | 2024-08-04 | 2021-12-03 | 2022-03-03 | 10 |  |  | DF /F /75/DFFA-FCV-390187 | Replace DFFA-FCV-390187 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-TELE | 2100058423 | DFF-FCV-390187 DFF-17 Chem Flow. | Replace DFFA-FCV-390187 |  |  | 25 | 0 | W31-W32 | 2024-07-29 | 2024-08-11 | 2024-08-04 | 2024-08-10 | 2021-12-03 | 2022-03-03 | 20 |  |  | DF /F /75/DFFA-FCV-390187 | Replace DFFA-FCV-390187 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058423 | DFF-FCV-390187 DFF-17 Chem Flow. | Replace DFFA-FCV-390187 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-11 | 2024-08-10 | 2024-08-11 | 2021-12-03 | 2022-03-03 | 30 |  |  | DF /F /75/DFFA-FCV-390187 | Replace DFFA-FCV-390187 | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-02-12 | 2020-05-12 | 5 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-02-12 | 2020-05-12 | 10 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 15 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 20 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 30 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-02-12 | 2020-05-12 | 40 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100025200 | DFGA-LG-410521 changeout of LG and HCV's | Isolate DFGA-LG-410521 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 50 |  |  | DF /G /30/DFGA-LG-410521 | Isolate DFGA-LG-410521 LG and HCV | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322284 | DFF-36-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 29 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024276 | DFC corroded welding on helinet support | tæret beslagsvejsning på fangnet sup. |  |  | 0 | 0 | Moved to 2022 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-11-12 | 2019-04-11 | 10 |  |  | DF /C /02 | tæret beslagsvejsning på fangnet sup. | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024276 | DFC corroded welding on helinet support | tæret beslagsvejsning på fangnet sup. |  |  | 12.099999999999999644728632116 | 0 | Moved to 2022 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-11-12 | 2019-04-11 | 170 |  |  | DF /C /02 | tæret beslagsvejsning på fangnet sup. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 1 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2018-12-28 | 2019-03-28 | 10 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 4.700000000000000177635683938 | 2 | Empty | 2020-08-28 | 2024-01-17 | 2020-08-29 | 2020-12-13 | 2018-12-28 | 2019-03-28 | 30 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 33.5 | 29 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2018-12-28 | 2019-03-28 | 35 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 5 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-09 | 2018-12-28 | 2019-03-28 | 40 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 33.5 | 5 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-12 | 2018-12-28 | 2019-03-28 | 45 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 26.800000000000000710542735752 | 11 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-12 | 2024-01-14 | 2018-12-28 | 2019-03-28 | 50 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 108 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-17 | 2018-12-28 | 2019-03-28 | 60 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-11 | 2018-12-28 | 2019-03-28 | 70 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-10 | 2018-12-28 | 2019-03-28 | 80 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 48 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-14 | 2018-12-28 | 2019-03-28 | 90 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003149 | CMAT:Scaff / Iso assists FORCE 13528 | BUILD SCAFFOLDING | PCNF | PCNF | 72 | 0 | Empty | 2020-08-28 | 2024-01-17 | 2024-01-09 | 2024-01-14 | 2018-12-28 | 2019-03-28 | 100 | PCNF | PCNF | DF /C /28/DFC-4-DP-050-0101-AD-T | BUILD SCAFFOLDING | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344031 | 1Y HELID FOAM SYS MAINT-DFCC-A-0304A/B | HELID FOAM SYS MAINT-DFCC-A-0304A/B | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-08-18 | 2024-08-21 | 2024-08-18 | 2024-08-20 | 2024-08-18 | 2024-09-17 | 10 | AWSCSECE | AWSCSECE | DF /C /01/HELIDECK-FIRE-FIGHTING | HELID FOAM SYS MAINT-DFCC-A-0304A/B | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344031 | 1Y HELID FOAM SYS MAINT-DFCC-A-0304A/B | HELID FOAM SYS MAINT-DFCC-A-0304A/B | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-08-18 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-08-18 | 2024-09-17 | 30 | AWSCSECE | AWSCSECE | DF /C /01/HELIDECK-FIRE-FIGHTING | HELID FOAM SYS MAINT-DFCC-A-0304A/B | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235710 | 4Y 380V E-SWB MAINT-DFBA-N-1831-01 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-24 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235710 | 4Y 380V E-SWB MAINT-DFBA-N-1831-01 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 8 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-24 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235710 | 4Y 380V E-SWB MAINT-DFBA-N-1831-01 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 30 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235710 | 4Y 380V E-SWB MAINT-DFBA-N-1831-01 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-10 | 2024-07-24 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 40 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200017127 | ANOP: 2024 Dan F PVI Repairs | PO IKM Ocean team |  |  | 0 | 0 | Empty | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2026-12-23 | 10 |  |  | DF /A /86/FABRIC-MAINTENANCE | PO IKM Ocean team | Unknown
4 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200017127 | ANOP: 2024 Dan F PVI Repairs | PO IKM Ocean team |  |  | 0 | 0 | Empty | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2026-12-23 | 20 |  |  | DF /A /86/FABRIC-MAINTENANCE | PO IKM Ocean team | Unknown
4 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200017127 | ANOP: 2024 Dan F PVI Repairs | PO IKM Ocean team |  |  | 0 | 0 | Empty | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2026-12-23 | 30 |  |  | DF /A /86/FABRIC-MAINTENANCE | PO IKM Ocean team | Unknown
4 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200017127 | ANOP: 2024 Dan F PVI Repairs | PO IKM Ocean team |  |  | 0 | 0 | Empty | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2024-07-06 | 2026-12-23 | 40 |  |  | DF /A /86/FABRIC-MAINTENANCE | PO IKM Ocean team | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 8 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-05 | 2024-10-06 | 2023-10-15 | 2024-02-27 | 10 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-07 | 2024-10-07 | 2023-10-15 | 2024-02-27 | 20 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 18 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-07 | 2024-10-09 | 2023-10-15 | 2024-02-27 | 30 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 8 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-09 | 2024-10-11 | 2023-10-15 | 2024-02-27 | 40 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 18 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-11 | 2024-10-13 | 2023-10-15 | 2024-02-27 | 50 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 8 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-14 | 2024-10-15 | 2023-10-15 | 2024-02-27 | 60 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 5 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-16 | 2024-10-17 | 2023-10-15 | 2024-02-27 | 70 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 4 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-17 | 2024-10-18 | 2023-10-15 | 2024-02-27 | 80 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100097875 | P-3502 doesent delever vaccuum | Isolate DFFA-P-3502 |  |  | 8 | 0 | Empty | 2024-10-05 | 2024-10-20 | 2024-10-18 | 2024-10-20 | 2023-10-15 | 2024-02-27 | 90 |  |  | DF /F /53/DFFA-P-3502 | Isolate DFFA-P-3502 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030524 | XCV-500881 broken oil mist lubricator | Isolate XCV-500881 oil mist lubricator |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2020-06-23 | 2020-11-20 | 10 |  |  | DF /G /27/DFGA-XCV-500881 | Isolate XCV-500881 oil mist lubricator | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100030524 | XCV-500881 broken oil mist lubricator | Isolate XCV-500881 oil mist lubricator |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-06-23 | 2020-11-20 | 20 |  |  | DF /G /27/DFGA-XCV-500881 | Isolate XCV-500881 oil mist lubricator | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030524 | XCV-500881 broken oil mist lubricator | Isolate XCV-500881 oil mist lubricator |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-06-23 | 2020-11-20 | 30 |  |  | DF /G /27/DFGA-XCV-500881 | Isolate XCV-500881 oil mist lubricator | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400244900 | 6M POT WATER TANK/PUMP MAINT-DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-29 | 2023-05-18 | 10 |  |  | DF /C /85/DFCC-T-1001 | POT WATER TANK/PUMP MAINT-DFCC-T-1001 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100034507 | DFFA-ESDV-330004 SOV internal leaking re | Build and remove scaffolding | PCNF | PCNF | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-07-09 | 2020-07-29 | 10 | PCNF | PCNF | DF /F /10/DFFA-ESDV-330004 | Build and remove scaffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100034507 | DFFA-ESDV-330004 SOV internal leaking re | Build and remove scaffolding | PCNF | PCNF | 4 | 10 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-07-09 | 2020-07-29 | 20 | PCNF | PCNF | DF /F /10/DFFA-ESDV-330004 | Build and remove scaffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100034507 | DFFA-ESDV-330004 SOV internal leaking re | Build and remove scaffolding | PCNF | PCNF | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-07-09 | 2020-07-29 | 30 | PCNF | PCNF | DF /F /10/DFFA-ESDV-330004 | Build and remove scaffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100034507 | DFFA-ESDV-330004 SOV internal leaking re | Build and remove scaffolding | PCNF | PCNF | 8 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-07-09 | 2020-07-29 | 35 | PCNF | PCNF | DF /F /10/DFFA-ESDV-330004 | Build and remove scaffolding | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100034507 | DFFA-ESDV-330004 SOV internal leaking re | Build and remove scaffolding | PCNF | PCNF | 5 | 4 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-07-09 | 2020-07-29 | 40 | PCNF | PCNF | DF /F /10/DFFA-ESDV-330004 | Build and remove scaffolding | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235722 | 4Y 380V E-SWB MAINT DFCI-N-1812-R03 | 380V E-SWB MAINT DFCI-N-1812-R03 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 2 | W21-W22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2023-03-01 | 2023-05-13 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R03 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235722 | 4Y 380V E-SWB MAINT DFCI-N-1812-R03 | 380V E-SWB MAINT DFCI-N-1812-R03 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 11 | W21-W22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2023-03-01 | 2023-05-13 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R03 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235722 | 4Y 380V E-SWB MAINT DFCI-N-1812-R03 | 380V E-SWB MAINT DFCI-N-1812-R03 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 22 | 0 | W21-W22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2023-03-01 | 2023-05-13 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R03 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235722 | 4Y 380V E-SWB MAINT DFCI-N-1812-R03 | 380V E-SWB MAINT DFCI-N-1812-R03 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | W21-W22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2023-03-01 | 2023-05-13 | 35 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R03 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235722 | 4Y 380V E-SWB MAINT DFCI-N-1812-R03 | 380V E-SWB MAINT DFCI-N-1812-R03 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | W21-W22 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2023-03-01 | 2023-05-13 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R03 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030523 | Replace DFGA-XCV-500866 (leaking from st | Replace DFGA-XCV-500866 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2020-04-24 | 2020-07-23 | 10 |  |  | DF /G /27/DFGA-XCV-500866 | Replace DFGA-XCV-500866 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100030523 | Replace DFGA-XCV-500866 (leaking from st | Replace DFGA-XCV-500866 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2020-04-24 | 2020-07-23 | 20 |  |  | DF /G /27/DFGA-XCV-500866 | Replace DFGA-XCV-500866 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100030523 | Replace DFGA-XCV-500866 (leaking from st | Replace DFGA-XCV-500866 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2020-04-24 | 2020-07-23 | 30 |  |  | DF /G /27/DFGA-XCV-500866 | Replace DFGA-XCV-500866 | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044259 | DFC-XCV-50407 SIDDER FAST | Vendor to Troubleshoot on XCV-50407 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-04 | 2022-04-30 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50407 | Vendor to Troubleshoot on XCV-50407 | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044259 | DFC-XCV-50407 SIDDER FAST | Vendor to Troubleshoot on XCV-50407 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-04 | 2022-04-30 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50407 | Vendor to Troubleshoot on XCV-50407 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344037 | 1Y CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | SECE | SECE | 3 | 0 | Empty | 2024-08-18 | 2024-08-26 | 2024-08-18 | 2024-08-18 | 2024-08-18 | 2024-09-17 | 10 | SECE | SECE | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344037 | 1Y CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | SECE | SECE | 20 | 0 | Empty | 2024-08-18 | 2024-08-26 | 2024-08-18 | 2024-08-23 | 2024-08-18 | 2024-09-17 | 20 | SECE | SECE | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344037 | 1Y CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | SECE | SECE | 4 | 0 | Empty | 2024-08-18 | 2024-08-26 | 2024-08-23 | 2024-08-24 | 2024-08-18 | 2024-09-17 | 30 | SECE | SECE | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344037 | 1Y CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | SECE | SECE | 4 | 0 | Empty | 2024-08-18 | 2024-08-26 | 2024-08-24 | 2024-08-25 | 2024-08-18 | 2024-09-17 | 40 | SECE | SECE | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344037 | 1Y CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | SECE | SECE | 3 | 0 | Empty | 2024-08-18 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2024-08-18 | 2024-09-17 | 50 | SECE | SECE | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-11 | 2024-03-11 | 2018-04-04 | 2018-09-01 | 10 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-11 | 2024-03-11 | 2018-04-04 | 2018-09-01 | 20 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 26.100000000000001421085471512 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-11 | 2024-03-14 | 2018-04-04 | 2018-09-01 | 30 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-14 | 2024-03-15 | 2018-04-04 | 2018-09-01 | 40 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 4 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-15 | 2024-03-16 | 2018-04-04 | 2018-09-01 | 50 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-16 | 2024-03-17 | 2018-04-04 | 2018-09-01 | 60 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-17 | 2024-03-17 | 2018-04-04 | 2018-09-01 | 70 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 13.400000000000000355271367876 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-17 | 2024-03-18 | 2018-04-04 | 2018-09-01 | 80 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-18 | 2024-03-19 | 2018-04-04 | 2018-09-01 | 85 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 21.39999999999999857891452847 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-19 | 2024-03-22 | 2018-04-04 | 2018-09-01 | 90 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 57 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-22 | 2024-03-25 | 2018-04-04 | 2018-09-01 | 100 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 4 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-25 | 2024-03-26 | 2018-04-04 | 2018-09-01 | 110 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100027606 | ANOP DFC Replacement of spools at P-5015 | L3 Tools are checked for defects before |  |  | 26.100000000000001421085471512 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-26 | 2024-03-29 | 2018-04-04 | 2018-09-01 | 120 |  |  | DF /C /28 | L3 Tools are checked for defects before | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015379 | Replace LB2 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015379 | Replace LB2 coolant with GlysantinG30 | Isolate lifeboat |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015379 | Replace LB2 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /C /02/DFCI-X-0702 | Isolate lifeboat | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000783 | DK46 "BURET"CAMPAIGN MATERIAL ORDER 2019 | DK46 "BURET"CAMPAIGN MATERIAL ORDER 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-01-01 | 2019-12-31 | 10 |  |  | DF /F | DK46 "BURET"CAMPAIGN MATERIAL ORDER 2019 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000783 | DK46 "BURET"CAMPAIGN MATERIAL ORDER 2019 | DK46 "BURET"CAMPAIGN MATERIAL ORDER 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-01-01 | 2019-12-31 | 20 |  |  | DF /F | DK46 "BURET"CAMPAIGN MATERIAL ORDER 2019 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400325769 | 2Y LIFERAFT RECERTIFICATE - DFG | SCAFFOLD AND RIGGING | SECE | SECE | 8 | 8 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-04-16 | 2024-06-01 | 10 | SECE | SECE | DF /G /02/LIFE-RAFT | SCAFFOLD AND RIGGING | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400325769 | 2Y LIFERAFT RECERTIFICATE - DFG | SCAFFOLD AND RIGGING | SECE | SECE | 16 | 10 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-04-16 | 2024-06-01 | 20 | SECE | SECE | DF /G /02/LIFE-RAFT | SCAFFOLD AND RIGGING | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235554 | 4Y 3KV N-SWB MAINT DFCI-N-1801-13 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-29 | 10 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-13-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235554 | 4Y 3KV N-SWB MAINT DFCI-N-1801-13 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 40 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-19 | 2022-12-31 | 2023-03-29 | 20 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-13-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235554 | 4Y 3KV N-SWB MAINT DFCI-N-1801-13 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 13 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-22 | 2022-12-31 | 2023-03-29 | 30 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-13-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235554 | 4Y 3KV N-SWB MAINT DFCI-N-1801-13 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2022-12-31 | 2023-03-29 | 40 | AWSCSCH | AWSCSCH | DF /C /61/DFCI-N-1801-13-01 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235832 | 4Y 380V E-SWB MAINT DFFA-N-1813-02 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235832 | 4Y 380V E-SWB MAINT DFFA-N-1813-02 | ISOLATION BY PRODUCTION | SCH | SCH | 6 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235832 | 4Y 380V E-SWB MAINT DFFA-N-1813-02 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235832 | 4Y 380V E-SWB MAINT DFFA-N-1813-02 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1813-03 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-01 | 2025-01-03 | 2019-09-21 | 2019-12-20 | 5 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-03 | 2025-01-04 | 2019-09-21 | 2019-12-20 | 10 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-04 | 2025-01-05 | 2019-09-21 | 2019-12-20 | 20 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-INST | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2025-01-06 | 2019-09-21 | 2019-12-20 | 25 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-06 | 2025-01-08 | 2019-09-21 | 2019-12-20 | 30 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-05 | 2025-01-08 | 2019-09-21 | 2019-12-20 | 40 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-INST | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-08 | 2025-01-08 | 2019-09-21 | 2019-12-20 | 45 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-08 | 2025-01-09 | 2019-09-21 | 2019-12-20 | 50 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-09 | 2025-01-10 | 2019-09-21 | 2019-12-20 | 60 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
3 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100026134 | Replace DFFA-XCV-380604 (Halfdan riser) | L3 Rig-up hoist for rigging | AWSC | AWSC | 21 | 0 | Empty | 2025-01-01 | 2025-01-12 | 2025-01-10 | 2025-01-12 | 2019-09-21 | 2019-12-20 | 70 | AWSC | AWSC | DF /F /54/DFFA-XCV-380604 | L3 Rig-up hoist for rigging | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400352435 | 1Y FIRE DAMPER CHECK - DFCC | FIRE DAMPER CHECK - DFCC | SECE | SECE | 25 | 0 | W39-W40 | 2024-09-23 | 2024-09-29 | 2024-09-23 | 2024-09-29 | 2024-09-23 | 2024-10-23 | 10 | SECE | SECE | DF /C /09/FIRE-DAMPERS | FIRE DAMPER CHECK - DFCC | Unknown
4 | NE | WRO | MTN-ELEC | MTN-ELEC | 2300004012 | DK40 - CONSUMABLE-GALLEY | DK40 - CONSUMABLE-GALLEY |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-12-24 | 2025-06-11 | 10 |  |  | DF /C /82/CATERING-EQUIPMENT | DK40 - CONSUMABLE-GALLEY | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 773 | 487.5099999999999909050529821 | Empty | 2020-12-31 | 2021-11-17 | 2020-12-31 | 2021-03-22 | 2020-07-07 | 2020-08-16 | 10 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 136 | 214 | Empty | 2020-12-31 | 2021-11-17 | 2021-03-22 | 2021-04-06 | 2020-07-07 | 2020-08-16 | 20 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 155 | 14.5 | Empty | 2020-12-31 | 2021-11-17 | 2021-04-06 | 2021-04-22 | 2020-07-07 | 2020-08-16 | 30 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 102 | 148 | Empty | 2020-12-31 | 2021-11-17 | 2021-04-22 | 2021-05-03 | 2020-07-07 | 2020-08-16 | 40 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 619 | 229.5 | Empty | 2020-12-31 | 2021-11-17 | 2021-05-03 | 2021-07-07 | 2020-07-07 | 2020-08-16 | 50 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 93 | 326.5 | Empty | 2020-12-31 | 2021-11-17 | 2021-07-07 | 2021-07-17 | 2020-07-07 | 2020-08-16 | 60 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 62 | 25 | Empty | 2020-12-31 | 2021-11-17 | 2021-07-17 | 2021-07-23 | 2020-07-07 | 2020-08-16 | 70 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 62 | 36 | Empty | 2020-12-31 | 2021-11-17 | 2021-07-23 | 2021-07-30 | 2020-07-07 | 2020-08-16 | 80 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 309 | 118 | Empty | 2020-12-31 | 2021-11-17 | 2021-07-30 | 2021-08-31 | 2020-07-07 | 2020-08-16 | 90 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 365 | 153 | Empty | 2020-12-31 | 2021-11-17 | 2021-08-31 | 2021-10-09 | 2020-07-07 | 2020-08-16 | 100 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 62 | 5 | Empty | 2020-12-31 | 2021-11-17 | 2021-10-09 | 2021-10-15 | 2020-07-07 | 2020-08-16 | 110 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001736 | DAF OCG NPT 2700000146,7,9,53,4,5/DFCPCR | Meals & breaks | PCNF | PCNF | 309 | 42 | Empty | 2020-12-31 | 2021-11-17 | 2021-10-15 | 2021-11-17 | 2020-07-07 | 2020-08-16 | 120 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 10 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-17 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 20 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 30 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-19 | 2021-02-18 | 2021-05-19 | 40 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-19 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 50 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 60 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-21 | 2021-02-18 | 2021-05-19 | 70 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-23 | 2021-02-18 | 2021-05-19 | 80 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 90 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 100 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 110 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 120 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044919 | DFG PDCV-500652 Dårlig integritet | Demount Actuator |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-27 | 2021-02-18 | 2021-05-19 | 130 |  |  | DF /G /27/DFGA-PDCV-500652 | Demount Actuator | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269335 | 1Y HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2023-08-16 | 10 | SECE | SECE | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269335 | 1Y HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2023-07-17 | 2023-08-16 | 20 | SECE | SECE | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400269335 | 1Y HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2023-07-17 | 2023-08-16 | 30 | SECE | SECE | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400269335 | 1Y HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2023-07-17 | 2023-08-16 | 40 | SECE | SECE | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269335 | 1Y HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-07-17 | 2023-08-16 | 50 | SECE | SECE | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100040471 | Replace socket outlet DFG WO-1883 | Isolate accordingly |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-01-24 | 2021-06-23 | 10 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040471 | Replace socket outlet DFG WO-1883 | Isolate accordingly |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-01-24 | 2021-06-23 | 20 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100040471 | Replace socket outlet DFG WO-1883 | Isolate accordingly |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-01-24 | 2021-06-23 | 30 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040471 | Replace socket outlet DFG WO-1883 | Isolate accordingly |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-01-24 | 2021-06-23 | 40 |  |  | DF /G /61 | Isolate accordingly | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235754 | 4Y 110V UPS-DP-F.TEST-DFEZ-DP-1903 | 110V UPS-DP-F.TEST-DFEZ-DP-1903 | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-30 | 2023-04-13 | 10 | AWSCSECE | AWSCSECE | DF /E /06/DFEZ-DP-1903 | 110V UPS-DP-F.TEST-DFEZ-DP-1903 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235754 | 4Y 110V UPS-DP-F.TEST-DFEZ-DP-1903 | 110V UPS-DP-F.TEST-DFEZ-DP-1903 | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-30 | 2023-04-13 | 20 | AWSCSECE | AWSCSECE | DF /E /06/DFEZ-DP-1903 | 110V UPS-DP-F.TEST-DFEZ-DP-1903 | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 146 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-02-01 | 2028-02-16 | 2021-02-01 | 2021-03-13 | 10 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 26 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-02-16 | 2028-02-19 | 2021-02-01 | 2021-03-13 | 20 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 29 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-02-19 | 2028-02-22 | 2021-02-01 | 2021-03-13 | 30 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 19 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-02-22 | 2028-02-24 | 2021-02-01 | 2021-03-13 | 40 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 116 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-02-24 | 2028-03-07 | 2021-02-01 | 2021-03-13 | 50 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 17 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-07 | 2028-03-09 | 2021-02-01 | 2021-03-13 | 60 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 12 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-09 | 2028-03-10 | 2021-02-01 | 2021-03-13 | 70 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 12 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-10 | 2028-03-12 | 2021-02-01 | 2021-03-13 | 80 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 58 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-12 | 2028-03-18 | 2021-02-01 | 2021-03-13 | 90 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 69 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-18 | 2028-03-25 | 2021-02-01 | 2021-03-13 | 100 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 12 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-25 | 2028-03-26 | 2021-02-01 | 2021-03-13 | 110 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 58 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-03-26 | 2028-04-01 | 2021-02-01 | 2021-03-13 | 120 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002468 | DAF OCG NPT order - DFGA-V-5741 - FUEL G | Clean-up & housekeeping |  |  | 0 | 0 | Empty | 2028-02-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2021-02-01 | 2021-03-13 | 130 |  |  | DF /G /70/DFGA-V-5741 | Clean-up & housekeeping | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-15 | 2024-09-16 | 2023-06-21 | 2023-08-05 | 10 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-16 | 2024-09-17 | 2023-06-21 | 2023-08-05 | 20 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-17 | 2024-09-18 | 2023-06-21 | 2023-08-05 | 30 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-18 | 2024-09-19 | 2023-06-21 | 2023-08-05 | 40 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-19 | 2024-09-20 | 2023-06-21 | 2023-08-05 | 50 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-20 | 2024-09-21 | 2023-06-21 | 2023-08-05 | 60 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-21 | 2024-09-21 | 2023-06-21 | 2023-08-05 | 70 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-21 | 2024-09-21 | 2023-06-21 | 2023-08-05 | 80 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-21 | 2024-09-21 | 2023-06-21 | 2023-08-05 | 90 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-21 | 2024-09-21 | 2023-06-21 | 2023-08-05 | 100 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-21 | 2024-09-22 | 2023-06-21 | 2023-08-05 | 110 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-22 | 2024-09-24 | 2023-06-21 | 2023-08-05 | 120 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-24 | 2024-09-26 | 2023-06-21 | 2023-08-05 | 130 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-26 | 2024-09-28 | 2023-06-21 | 2023-08-05 | 140 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-28 | 2024-09-30 | 2023-06-21 | 2023-08-05 | 150 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-09-30 | 2024-10-01 | 2023-06-21 | 2023-08-05 | 160 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-INST | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-01 | 2024-10-02 | 2023-06-21 | 2023-08-05 | 170 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-02 | 2024-10-02 | 2023-06-21 | 2023-08-05 | 180 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-02 | 2024-10-03 | 2023-06-21 | 2023-08-05 | 190 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-03 | 2024-10-04 | 2023-06-21 | 2023-08-05 | 200 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2023-06-21 | 2023-08-05 | 210 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2023-06-21 | 2023-08-05 | 220 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
2 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100093696 | DFG-PCV-340024 Internal leak | Line for missing bolts/Gaskets |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2023-06-21 | 2023-08-05 | 230 |  |  | DF /G /32/DFGA-PCV-340024 | Line for missing bolts/Gaskets | Unknown
A | DFG20MPH | WPM | MTN-INST | PRODTECH | 2400344066 | 1Y HIPPS SYSTEM MAINT - DAN FG | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-24 | 2024-08-27 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-09-23 | 10 | AWSCSECE | AWSCSECE | DF /G /03/HIPS-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | DFG20MPH | WPM | MTN-INST | MTN-INST | 2400344066 | 1Y HIPPS SYSTEM MAINT - DAN FG | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 8 | 0 | W33-W34 | 2024-08-24 | 2024-08-27 | 2024-08-25 | 2024-08-26 | 2024-08-24 | 2024-09-23 | 20 | AWSCSECE | AWSCSECE | DF /G /03/HIPS-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | DFG20MPH | WPM | MTN-INST | PRODTECH | 2400344066 | 1Y HIPPS SYSTEM MAINT - DAN FG | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-24 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-24 | 2024-09-23 | 30 | AWSCSECE | AWSCSECE | DF /G /03/HIPS-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286626 | 1Y WATER MIST SKID MAINT-DFGA-A-0460 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-26 | 2024-08-27 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /G /01/DFGA-A-0460 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286626 | 1Y WATER MIST SKID MAINT-DFGA-A-0460 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-27 | 2024-08-29 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /G /01/DFGA-A-0460 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286626 | 1Y WATER MIST SKID MAINT-DFGA-A-0460 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-29 | 2024-08-31 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /G /01/DFGA-A-0460 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286626 | 1Y WATER MIST SKID MAINT-DFGA-A-0460 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-08-31 | 2024-09-01 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /G /01/DFGA-A-0460 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286626 | 1Y WATER MIST SKID MAINT-DFGA-A-0460 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /G /01/DFGA-A-0460 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286626 | 1Y WATER MIST SKID MAINT-DFGA-A-0460 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /G /01/DFGA-A-0460 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 8 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-02 | 2021-05-13 | 2021-06-22 | 20 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 30 | 36 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-02 | 2024-01-04 | 2021-05-13 | 2021-06-22 | 30 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 4 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-04 | 2024-01-05 | 2021-05-13 | 2021-06-22 | 40 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 6 | 6 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2022-06-19 | 2022-06-20 | 2021-05-13 | 2021-06-22 | 50 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 10 | 8 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2022-06-19 | 2022-06-20 | 2021-05-13 | 2021-06-22 | 60 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 0 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 70 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 0 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 80 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 0 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 90 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 8 | 6 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 100 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 12 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-02 | 2021-05-13 | 2021-06-22 | 110 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 8 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 120 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 6 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 130 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 12 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-03 | 2021-05-13 | 2021-06-22 | 140 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 10 | 30 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-02 | 2021-05-13 | 2021-06-22 | 150 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 36 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-05 | 2021-05-13 | 2021-06-22 | 160 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 8 | 26 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-02 | 2021-05-13 | 2021-06-22 | 170 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 16 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-02 | 2021-05-13 | 2021-06-22 | 180 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 2 | 2 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 190 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 4 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 200 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 4 | 4 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 210 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049331 | P-3921 Biocide pump internal leak | Isolate P-3921 | SCH | SCH | 4 | 0 | 24-W01-02 | 2024-01-01 | 2024-01-05 | 2024-01-01 | 2024-01-01 | 2021-05-13 | 2021-06-22 | 220 | SCH | SCH | DF /F /75/DFFA-P-3921 | Isolate P-3921 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100073894 | Fejl udløsning af deluge ventil XCV-0313 | Leak find on fussible loop | SCH | SCH | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-13 | 2022-10-08 | 2023-02-20 | 10 | SCH | SCH | DF /A /01/DFAA-XCV-0313 | Leak find on fussible loop | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100073894 | Fejl udløsning af deluge ventil XCV-0313 | Leak find on fussible loop | SCH | SCH | 20 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-15 | 2022-10-08 | 2023-02-20 | 20 | SCH | SCH | DF /A /01/DFAA-XCV-0313 | Leak find on fussible loop | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322225 | DFA-75-CI-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 27 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215389 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | PO Conixi |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2022-10-14 | 2022-11-19 | 10 |  |  | DF /C /09/DFCC-A-1216 | PO Conixi | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215389 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | PO Conixi |  |  | 10 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 20 |  |  | DF /C /09/DFCC-A-1216 | PO Conixi | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215389 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | PO Conixi |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 30 |  |  | DF /C /09/DFCC-A-1216 | PO Conixi | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215389 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | PO Conixi |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 40 |  |  | DF /C /09/DFCC-A-1216 | PO Conixi | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215389 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | PO Conixi |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 50 |  |  | DF /C /09/DFCC-A-1216 | PO Conixi | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215389 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | PO Conixi |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 60 |  |  | DF /C /09/DFCC-A-1216 | PO Conixi | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263067 | 6M SDV LUB/MAINT HPSEP - DFF | SDV LUB/INSP HPSEP - DFF |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-06-21 | 2023-07-07 | 10 |  |  | DF /F /03/SDV-VALVES | SDV LUB/INSP HPSEP - DFF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022852 | MODIFICATION ON DFE WELL HYDRAULIC CONTR | L3 isolate pipe |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2019-07-06 | 2019-10-04 | 10 |  |  | DF /E /10 | L3 isolate pipe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022852 | MODIFICATION ON DFE WELL HYDRAULIC CONTR | L3 isolate pipe |  |  | 14 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2019-07-06 | 2019-10-04 | 20 |  |  | DF /E /10 | L3 isolate pipe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022852 | MODIFICATION ON DFE WELL HYDRAULIC CONTR | L3 isolate pipe |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2019-07-06 | 2019-10-04 | 30 |  |  | DF /E /10 | L3 isolate pipe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-02-12 | 2020-05-12 | 5 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-02-12 | 2020-05-12 | 10 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 15 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 20 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 30 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-02-12 | 2020-05-12 | 40 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 50 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025197 | DFGA-LG-410494 changeout of LG and HCV's | Isolate DFGA-LG-410494 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 60 |  |  | DF /G /30/DFGA-LG-410494 | Isolate DFGA-LG-410494 LG and HCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104198 | DFFA-EMS-0606 Replace valve switch | The right type of fittings for gooseneck |  |  | 3 | 0 | Empty | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2023-10-25 | 2023-12-09 | 10 |  |  | DF /F /02/DFFA-EMS-0606 | The right type of fittings for gooseneck | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104198 | DFFA-EMS-0606 Replace valve switch | The right type of fittings for gooseneck |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2023-10-25 | 2023-12-09 | 20 |  |  | DF /F /02/DFFA-EMS-0606 | The right type of fittings for gooseneck | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337665 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-08-20 | 10 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337665 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-08-20 | 20 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337665 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-07-21 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-21 | 2024-08-20 | 30 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400337665 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-07-21 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-21 | 2024-08-20 | 40 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337665 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-07-21 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-21 | 2024-08-20 | 50 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
4 | NE | WRO | MTN-MECH | VEN-MECH | 2300000707 | Dan F Production Chemistry | Dan F Production Chemistry |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-03-09 | 2018-12-31 | 10 |  |  | DF /F | Dan F Production Chemistry | Unknown
4 | NE | WRO | MTN-MECH | MTN-MECH | 2300000707 | Dan F Production Chemistry | Dan F Production Chemistry |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2018-03-09 | 2018-12-31 | 20 |  |  | DF /F | Dan F Production Chemistry | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344328 | 6M INSTR AIR SYSTEM MAINT - DFCM-A-5401 | INSTR AIR SYSTEM MAINT - DFCM-A-5401 |  |  | 11 | 0 | Empty | 2024-09-10 | 2024-09-12 | 2024-09-10 | 2024-09-12 | 2024-09-10 | 2024-09-29 | 10 |  |  | DF /C /07/INSTRUMENT-AIR-SYSTEM | INSTR AIR SYSTEM MAINT - DFCM-A-5401 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100087417 | ANOCR DFA-DFB Bridge - Paint Crane Boom | Set up equipment |  |  | 0 | 0 | Empty | 2023-09-11 | 2023-09-21 | 2023-09-11 | 2023-09-11 | 2023-09-11 | 2025-12-31 | 10 |  |  | DF /B /86/BRIDGE-DFB-DFA | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100087417 | ANOCR DFA-DFB Bridge - Paint Crane Boom | Set up equipment |  |  | 12 | 0 | Empty | 2023-09-11 | 2023-09-21 | 2023-09-11 | 2023-09-12 | 2023-09-11 | 2025-12-31 | 20 |  |  | DF /B /86/BRIDGE-DFB-DFA | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100087417 | ANOCR DFA-DFB Bridge - Paint Crane Boom | Set up equipment |  |  | 6 | 0 | Empty | 2023-09-11 | 2023-09-21 | 2023-09-12 | 2023-09-12 | 2023-09-11 | 2025-12-31 | 30 |  |  | DF /B /86/BRIDGE-DFB-DFA | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100087417 | ANOCR DFA-DFB Bridge - Paint Crane Boom | Set up equipment |  |  | 161 | 0 | Empty | 2023-09-11 | 2023-09-21 | 2023-09-12 | 2023-09-20 | 2023-09-11 | 2025-12-31 | 40 |  |  | DF /B /86/BRIDGE-DFB-DFA | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100087417 | ANOCR DFA-DFB Bridge - Paint Crane Boom | Set up equipment |  |  | 12 | 0 | Empty | 2023-09-11 | 2023-09-21 | 2023-09-20 | 2023-09-21 | 2023-09-11 | 2025-12-31 | 50 |  |  | DF /B /86/BRIDGE-DFB-DFA | Set up equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050107 | DFE-3102B Hydr.cabinet minor leak inside | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 24 | 0 | W27-28 IOP 6-13/7 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-27 | 2021-06-10 | 2021-09-08 | 10 | AWSC | AWSC | DF /E /07/DFEZ-A-3102 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059756 | FLMR DFC - Repl of gratings EL +57350 | DFC - Replacement of gratings EL +57350 |  |  | 0 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +57350 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059756 | FLMR DFC - Repl of gratings EL +57350 | DFC - Replacement of gratings EL +57350 |  |  | 2 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +57350 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059756 | FLMR DFC - Repl of gratings EL +57350 | DFC - Replacement of gratings EL +57350 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +57350 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059756 | FLMR DFC - Repl of gratings EL +57350 | DFC - Replacement of gratings EL +57350 |  |  | 6 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +57350 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059756 | FLMR DFC - Repl of gratings EL +57350 | DFC - Replacement of gratings EL +57350 |  |  | 4 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 50 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +57350 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059756 | FLMR DFC - Repl of gratings EL +57350 | DFC - Replacement of gratings EL +57350 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-01-01 | 2022-04-01 | 60 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +57350 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400342711 | DFF-12-PHS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 12 | 0.5 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /12/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339261 | DFF_1Y_JACKET ABOVE WATER INSPECTION | DFF_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/JACKET - L.A.T. TO EL 22000 | DFF_1Y_JACKET ABOVE WATER INSPECTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235773 | 4Y 400V N-SWB MAINT-DFFB-N-1828-2 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828-02 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235773 | 4Y 400V N-SWB MAINT-DFFB-N-1828-2 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828-02 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235773 | 4Y 400V N-SWB MAINT-DFFB-N-1828-2 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828-02 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235773 | 4Y 400V N-SWB MAINT-DFFB-N-1828-2 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828-02 | DE-ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342430 | 1Y CATALYTIC GAS DETECTORS - DFC LVL 4 | CATALYTIC GAS DETECTORS CHECK | SECE | SECE | 23.5 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-26 | 2024-09-01 | 2024-07-29 | 2024-08-28 | 10 | SECE | SECE | DF /C /03/FGS-DETECTORS | CATALYTIC GAS DETECTORS CHECK | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344063 | 3Y FIRE DAMPER CHECK LEVEL 2 - DFG | PERSONAL ISOLATION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-12 | 2024-08-12 | 2024-07-23 | 2024-09-23 | 10 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344063 | 3Y FIRE DAMPER CHECK LEVEL 2 - DFG | PERSONAL ISOLATION | SECE | SECE | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-13 | 2024-08-15 | 2024-07-23 | 2024-09-23 | 20 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344063 | 3Y FIRE DAMPER CHECK LEVEL 2 - DFG | PERSONAL ISOLATION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-16 | 2024-08-16 | 2024-07-23 | 2024-09-23 | 30 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344063 | 3Y FIRE DAMPER CHECK LEVEL 2 - DFG | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-17 | 2024-08-17 | 2024-07-23 | 2024-09-23 | 40 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400344063 | 3Y FIRE DAMPER CHECK LEVEL 2 - DFG | PERSONAL ISOLATION | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-17 | 2024-08-18 | 2024-07-23 | 2024-09-23 | 50 | SECE | SECE | DF /G /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038737 | PCV-39607A has a leakage. | Isolate PCV-39607A |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2020-12-21 | 2021-05-20 | 10 |  |  | DF /E /75/DFEZ-PCV-39607A | Isolate PCV-39607A | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038737 | PCV-39607A has a leakage. | Isolate PCV-39607A |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-12-21 | 2021-05-20 | 20 |  |  | DF /E /75/DFEZ-PCV-39607A | Isolate PCV-39607A | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038737 | PCV-39607A has a leakage. | Isolate PCV-39607A |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2020-12-21 | 2021-05-20 | 30 |  |  | DF /E /75/DFEZ-PCV-39607A | Isolate PCV-39607A | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038737 | PCV-39607A has a leakage. | Isolate PCV-39607A |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-12-21 | 2021-05-20 | 40 |  |  | DF /E /75/DFEZ-PCV-39607A | Isolate PCV-39607A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071667 | Replace Light Fixture LE-1813-3903-L3L | Set personal isolation |  |  | 1 | 0 | Hold Step | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-07-28 | 2022-12-10 | 10 |  |  | DF /F /62/EMERGENCY-LIGHTING-LEVEL-1 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071667 | Replace Light Fixture LE-1813-3903-L3L | Set personal isolation |  |  | 4 | 0 | Hold Step | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-07-28 | 2022-12-10 | 20 |  |  | DF /F /62/EMERGENCY-LIGHTING-LEVEL-1 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100071667 | Replace Light Fixture LE-1813-3903-L3L | Set personal isolation |  |  | 1 | 0 | Hold Step | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-07-28 | 2022-12-10 | 30 |  |  | DF /F /62/EMERGENCY-LIGHTING-LEVEL-1 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-31 | 2021-02-20 | 2021-05-21 | 10 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-31 | 2024-08-01 | 2021-02-20 | 2021-05-21 | 20 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-01 | 2021-02-20 | 2021-05-21 | 30 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-02 | 2021-02-20 | 2021-05-21 | 40 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-03 | 2021-02-20 | 2021-05-21 | 50 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-03 | 2021-02-20 | 2021-05-21 | 60 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-04 | 2021-02-20 | 2021-05-21 | 70 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-06 | 2021-02-20 | 2021-05-21 | 80 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-06 | 2024-08-07 | 2021-02-20 | 2021-05-21 | 90 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-07 | 2021-02-20 | 2021-05-21 | 100 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-08 | 2021-02-20 | 2021-05-21 | 110 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2021-02-20 | 2021-05-21 | 120 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045000 | Hole in actuator for DFGA-FCV-500878. | Isolate FCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-10 | 2021-02-20 | 2021-05-21 | 130 |  |  | DF /G /27/DFGA-FCV-500878 | Isolate FCV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286624 | 1Y HI-FOG SKID MAINT-DFEZ-A-0450 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-26 | 2024-08-27 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /E /01/DFEZ-A-0450 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286624 | 1Y HI-FOG SKID MAINT-DFEZ-A-0450 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-27 | 2024-08-29 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /E /01/DFEZ-A-0450 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286624 | 1Y HI-FOG SKID MAINT-DFEZ-A-0450 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-29 | 2024-08-31 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /E /01/DFEZ-A-0450 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286624 | 1Y HI-FOG SKID MAINT-DFEZ-A-0450 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-31 | 2024-08-31 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /E /01/DFEZ-A-0450 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286624 | 1Y HI-FOG SKID MAINT-DFEZ-A-0450 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-31 | 2024-09-01 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /E /01/DFEZ-A-0450 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286624 | 1Y HI-FOG SKID MAINT-DFEZ-A-0450 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /E /01/DFEZ-A-0450 | ISOLATION BY PRODUCTION | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400342610 | PIGGING, P3014 16" DFF-HDA WI 2W | P3014_DFF-HDA | AWSC | AWSC | 4 | 0 | Empty | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-09-07 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673014 | P3014_DFF-HDA | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400316058 | 1Y OILMETER SWITCH SUMMER TIME-METERING | OILMETER SWITCH SUMMER TIME-METERING | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-03-13 | 2024-04-29 | 10 | AWSC | AWSC | DF /C /26 | OILMETER SWITCH SUMMER TIME-METERING | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400316058 | 1Y OILMETER SWITCH SUMMER TIME-METERING | OILMETER SWITCH SUMMER TIME-METERING | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-03-13 | 2024-04-29 | 20 | AWSC | AWSC | DF /C /26 | OILMETER SWITCH SUMMER TIME-METERING | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053304 | Replace DFFA-PDI-360001 | New diff pressure gauge | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-08-25 | 2021-11-23 | 10 | PCNFSCH | PCNFSCH | DF /F /21/INSTRUMENTS | New diff pressure gauge | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053304 | Replace DFFA-PDI-360001 | New diff pressure gauge | PCNFSCH | PCNFSCH | 2 | 6 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-08-25 | 2021-11-23 | 20 | PCNFSCH | PCNFSCH | DF /F /21/INSTRUMENTS | New diff pressure gauge | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053304 | Replace DFFA-PDI-360001 | New diff pressure gauge | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-08-25 | 2021-11-23 | 30 | PCNFSCH | PCNFSCH | DF /F /21/INSTRUMENTS | New diff pressure gauge | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053304 | Replace DFFA-PDI-360001 | New diff pressure gauge | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-08-25 | 2021-11-23 | 40 | PCNFSCH | PCNFSCH | DF /F /21/INSTRUMENTS | New diff pressure gauge | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053304 | Replace DFFA-PDI-360001 | New diff pressure gauge | PCNFSCH | PCNFSCH | 4 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-08-25 | 2021-11-23 | 50 | PCNFSCH | PCNFSCH | DF /F /21/INSTRUMENTS | New diff pressure gauge | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053304 | Replace DFFA-PDI-360001 | New diff pressure gauge | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-08-25 | 2021-11-23 | 60 | PCNFSCH | PCNFSCH | DF /F /21/INSTRUMENTS | New diff pressure gauge | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235642 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L04A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235642 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L04 | ISOLATION ELECTRICAL | AWSC | AWSC | 26 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-28 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L04A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235642 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L04 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-28 | 2024-09-30 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L04A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235642 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L04A1 | ISOLATION ELECTRICAL | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ROPE | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 24 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-15 | 2024-07-18 | 2024-05-31 | 2024-07-15 | 10 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-MECH | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 24 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-18 | 2024-07-21 | 2024-05-31 | 2024-07-15 | 20 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 8 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-21 | 2024-07-23 | 2024-05-31 | 2024-07-15 | 30 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 2 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-23 | 2024-07-23 | 2024-05-31 | 2024-07-15 | 40 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 4 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-23 | 2024-07-24 | 2024-05-31 | 2024-07-15 | 50 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 0 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-24 | 2024-07-24 | 2024-05-31 | 2024-07-15 | 60 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 2 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-24 | 2024-07-25 | 2024-05-31 | 2024-07-15 | 70 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 2 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-25 | 2024-07-25 | 2024-05-31 | 2024-07-15 | 80 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 8 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-25 | 2024-07-27 | 2024-05-31 | 2024-07-15 | 90 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-MECH | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 24 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-27 | 2024-07-30 | 2024-05-31 | 2024-07-15 | 100 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ROPE | 2200018790 | FMC and GMC assist PVI V-5072 | Remove spool from pump, hook up temp. pu | SECE | SECE | 24 | 0 | W33-W34 | 2024-07-15 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2024-05-31 | 2024-07-15 | 110 | SECE | SECE | DF /G /28/DFGA-V-5072 | Remove spool from pump, hook up temp. pu | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2022-12-25 | 2023-05-09 | 10 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 15 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-23 | 2022-12-25 | 2023-05-09 | 20 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-23 | 2022-12-25 | 2023-05-09 | 30 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-24 | 2022-12-25 | 2023-05-09 | 40 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-23 | 2022-12-25 | 2023-05-09 | 50 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-23 | 2022-12-25 | 2023-05-09 | 60 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-24 | 2022-12-25 | 2023-05-09 | 70 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-24 | 2022-12-25 | 2023-05-09 | 80 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 3 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-24 | 2022-12-25 | 2023-05-09 | 90 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-24 | 2022-12-25 | 2023-05-09 | 100 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2022-12-25 | 2023-05-09 | 110 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2022-12-25 | 2023-05-09 | 120 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2022-12-25 | 2023-05-09 | 130 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078021 | Exchange of Hypochlorite pump P-3918 | Prepare for rigging |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2022-12-25 | 2023-05-09 | 140 |  |  | DF /F /75/DFFA-P-3918 | Prepare for rigging | Unknown
A | DFF-1610 | WPM | MTN-TELE | PRODTECH | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-10-19 | 10 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-TELE | MTN-TELE | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-20 | 2024-09-20 | 2024-09-19 | 2024-10-19 | 20 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-TELE | MTN-TELE | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-20 | 2024-09-20 | 2024-09-19 | 2024-10-19 | 30 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-TELE | MTN-TELE | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2024-09-19 | 2024-10-19 | 40 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-TELE | MTN-TELE | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2024-09-19 | 2024-10-19 | 50 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-TELE | MTN-TELE | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-21 | 2024-09-21 | 2024-09-19 | 2024-10-19 | 60 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1610 | WPM | MTN-TELE | PRODTECH | 2400352046 | 8KH F&G DETECTORS DFFA-A-1610 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-09-19 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2024-09-19 | 2024-10-19 | 70 | AWSCSECE | AWSCSECE | DF /F /03/FZ-242-GENER-G-1610-LEVEL-3 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100035413 | DFV/78: ROPE change out bracket for boom | Order new brackets |  |  | 1 | 0 | Empty | 2023-06-24 | 2023-06-27 | 2023-06-24 | 2023-06-24 | 2020-07-31 | 2020-09-09 | 10 |  |  | DF /F /78/DFFA-A-6102 | Order new brackets | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100035413 | DFV/78: ROPE change out bracket for boom | Order new brackets |  |  | 1 | 0 | Empty | 2023-06-24 | 2023-06-27 | 2023-06-24 | 2023-06-24 | 2020-07-31 | 2020-09-09 | 20 |  |  | DF /F /78/DFFA-A-6102 | Order new brackets | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100035413 | DFV/78: ROPE change out bracket for boom | Order new brackets |  |  | 30 | 0 | Empty | 2023-06-24 | 2023-06-27 | 2023-06-24 | 2023-06-27 | 2020-07-31 | 2020-09-09 | 30 |  |  | DF /F /78/DFFA-A-6102 | Order new brackets | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100035413 | DFV/78: ROPE change out bracket for boom | Order new brackets |  |  | 1 | 0 | Empty | 2023-06-24 | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2020-07-31 | 2020-09-09 | 40 |  |  | DF /F /78/DFFA-A-6102 | Order new brackets | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100035413 | DFV/78: ROPE change out bracket for boom | Order new brackets |  |  | 1 | 0 | Empty | 2023-06-24 | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2020-07-31 | 2020-09-09 | 50 |  |  | DF /F /78/DFFA-A-6102 | Order new brackets | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100035413 | DFV/78: ROPE change out bracket for boom | Order new brackets |  |  | 0 | 0 | Empty | 2023-06-24 | 2023-06-27 | 2023-06-24 | 2023-06-24 | 2020-07-31 | 2020-09-09 | 60 |  |  | DF /F /78/DFFA-A-6102 | Order new brackets | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241154 | 1Y SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2023-03-05 | 2023-04-10 | 10 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400241154 | 1Y SEWER TREAT. UNIT MAINT DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-02 | 2023-03-05 | 2023-04-10 | 20 |  |  | DF /G /82/DFGA-A-5140 | SEWER TREAT. UNIT MAINT DFGA-A-5140 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-17 | 2020-10-26 | 2021-03-25 | 10 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-17 | 2020-10-26 | 2021-03-25 | 20 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-17 | 2020-10-26 | 2021-03-25 | 30 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-19 | 2020-10-26 | 2021-03-25 | 40 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2020-10-26 | 2021-03-25 | 50 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2020-10-26 | 2021-03-25 | 60 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100036054 | Defect Vent Valve DFFA-V-4002 | Prepare Permit/Tools/Matr |  |  | 21 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-21 | 2020-10-26 | 2021-03-25 | 70 |  |  | DF /F /36/DFFA-V-4002 | Prepare Permit/Tools/Matr | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104207 | DFFA-STR-0604 Replace rusty and blanket | DFFA-STR-0604 Replace rusty and blanket |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-14 | 2023-08-27 | 10 |  |  | DF /F /02/DFFA-STR-0604 | DFFA-STR-0604 Replace rusty and blanket | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009239 | Insulation assits FORCE 21280(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /54/DFF-10-WI-035-9150-BB-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009239 | Insulation assits FORCE 21280(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-27 | 2023-03-29 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /54/DFF-10-WI-035-9150-BB-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009239 | Insulation assits FORCE 21280(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-30 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /54/DFF-10-WI-035-9150-BB-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009239 | Insulation assits FORCE 21280(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-31 | 2023-03-31 | 2022-02-07 | 2022-07-07 | 35 |  |  | DF /F /54/DFF-10-WI-035-9150-BB-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009239 | Insulation assits FORCE 21280(COMP) | Bilfinger inspection |  |  | 60 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-31 | 2023-04-04 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /54/DFF-10-WI-035-9150-BB-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009239 | Insulation assits FORCE 21280(COMP) | Bilfinger inspection |  |  | 18 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-04-04 | 2023-04-06 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /54/DFF-10-WI-035-9150-BB-F | Bilfinger inspection | Unknown
4 | DFA-W11 | WDF | MTN-INST | PRODTECH | 2100076550 | DFA-11 Choke ZSC active when bean up | Calibrate Position Measurement Device |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-19 | 2025-10-05 | 10 |  |  | DF /A /55/DFAA-ZT-30011 | Calibrate Position Measurement Device | Unknown
4 | DFA-W11 | WDF | MTN-INST | MTN-INST | 2100076550 | DFA-11 Choke ZSC active when bean up | Calibrate Position Measurement Device |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-19 | 2025-10-05 | 20 |  |  | DF /A /55/DFAA-ZT-30011 | Calibrate Position Measurement Device | Unknown
4 | DFA-W11 | WDF | MTN-INST | MTN-INST | 2100076550 | DFA-11 Choke ZSC active when bean up | Calibrate Position Measurement Device |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-19 | 2025-10-05 | 25 |  |  | DF /A /55/DFAA-ZT-30011 | Calibrate Position Measurement Device | Unknown
4 | DFA-W11 | WDF | MTN-INST | PRODTECH | 2100076550 | DFA-11 Choke ZSC active when bean up | Calibrate Position Measurement Device |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-19 | 2025-10-05 | 30 |  |  | DF /A /55/DFAA-ZT-30011 | Calibrate Position Measurement Device | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053995 | DFC-FT5241 Noz sealing face corro (HOLD) | DFC-FT5241 Nozzle sealing face corrosion |  |  | 1 | 0 | W25-W26 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-09-11 | 2021-12-10 | 10 |  |  | DF /C /51/DFCM-FT-5241 | DFC-FT5241 Nozzle sealing face corrosion | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346572 | 6M BIOCIDE INJ PUMPS MAINT-DFGA-P-3958/9 | BIOCIDE INJ PUMPS MAINT-DFGA-P-3958/9 |  |  | 2 | 0 | Empty | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-30 | 10 |  |  | DF /G /75/DFGA-A-3956 | BIOCIDE INJ PUMPS MAINT-DFGA-P-3958/9 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400344072 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-13 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 26 | 0 | Empty | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-07-17 | 2024-07-16 | 2024-09-16 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-13 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100070305 | Fault on stop button to LCP DFFA-PM-3914 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-08-06 | 2022-12-19 | 10 |  |  | DF /A /75/DFAA-P-3914 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100070305 | Fault on stop button to LCP DFFA-PM-3914 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-08-06 | 2022-12-19 | 20 |  |  | DF /A /75/DFAA-P-3914 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100070305 | Fault on stop button to LCP DFFA-PM-3914 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-08-06 | 2022-12-19 | 30 |  |  | DF /A /75/DFAA-P-3914 | Isolate and prove dead | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200015785 | Sailor batt for replacement of old DAF | Sailor batt for replacement of old DAF |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-09-19 | 2023-11-03 | 10 |  |  | DF /C /08 | Sailor batt for replacement of old DAF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 1 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 3 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 4 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 6 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 10 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 11 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 12 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-23 | 2021-12-07 | 2022-01-16 | 20 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-23 | 2021-12-07 | 2022-01-16 | 30 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 31 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-26 | 2021-12-07 | 2022-01-16 | 40 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2021-12-07 | 2022-01-16 | 42 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 18 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 43 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 18 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 44 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-26 | 2021-12-07 | 2022-01-16 | 50 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2021-12-07 | 2022-01-16 | 51 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 55 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 56 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2021-12-07 | 2022-01-16 | 60 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-27 | 2021-12-07 | 2022-01-16 | 65 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2021-12-07 | 2022-01-16 | 70 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 40 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2021-12-07 | 2022-01-16 | 80 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059078 | Repair of DFCM-FT-5221 | Replace valve on vent line on top of lid |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-12-07 | 2022-01-16 | 90 |  |  | DF /C /51/DFCM-FT-5221 | Replace valve on vent line on top of lid | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400293731 | 4Y DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-17 | 2023-10-17 | 2023-12-29 | 10 | SCHSECE | SCHSECE | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400293731 | 4Y DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 7 | 24 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-19 | 2023-10-17 | 2023-12-29 | 20 | SCHSECE | SCHSECE | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400293731 | 4Y DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-19 | 2024-06-20 | 2023-10-17 | 2023-12-29 | 30 | SCHSECE | SCHSECE | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400293731 | 4Y DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-20 | 2023-10-17 | 2023-12-29 | 40 | SCHSECE | SCHSECE | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400293731 | 4Y DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-21 | 2023-10-17 | 2023-12-29 | 50 | SCHSECE | SCHSECE | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400344074 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-15 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 27 | 0 | Empty | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-07-26 | 2024-07-25 | 2024-09-25 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-15 | ATEX EQUIPMENT INSPECTION | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086689 | HCV to CD from EP-3802 stuck 50% | Isolate HCV | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-03 | 2023-03-04 | 2023-04-18 | 10 | SCH | SCH | DF /F /23/DFFA-EP-3802 | Isolate HCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100086689 | HCV to CD from EP-3802 stuck 50% | Isolate HCV | SCH | SCH | 1 | 1 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-03 | 2023-03-04 | 2023-04-18 | 20 | SCH | SCH | DF /F /23/DFFA-EP-3802 | Isolate HCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086689 | HCV to CD from EP-3802 stuck 50% | Isolate HCV | SCH | SCH | 1 | 5 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-03 | 2023-03-04 | 2023-04-18 | 30 | SCH | SCH | DF /F /23/DFFA-EP-3802 | Isolate HCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100086689 | HCV to CD from EP-3802 stuck 50% | Isolate HCV | SCH | SCH | 1 | 1 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-03-04 | 2023-04-18 | 40 | SCH | SCH | DF /F /23/DFFA-EP-3802 | Isolate HCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086689 | HCV to CD from EP-3802 stuck 50% | Isolate HCV | SCH | SCH | 1 | 5 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-03-04 | 2023-04-18 | 50 | SCH | SCH | DF /F /23/DFFA-EP-3802 | Isolate HCV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086689 | HCV to CD from EP-3802 stuck 50% | Isolate HCV | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2023-03-04 | 2023-04-18 | 60 | SCH | SCH | DF /F /23/DFFA-EP-3802 | Isolate HCV | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235608 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-14 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-14 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235608 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-14 | ISOLATION ELECTRICAL |  |  | 23 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-21 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-14 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235608 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-14 | ISOLATION ELECTRICAL |  |  | 7 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2024-09-23 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-14 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235608 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-14 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-14 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059766 | FLMR DFF - Repl of gratings EL +42600 | DFF - Replacement of gratings EL +42600 |  |  | 0 | 0 | Empty | 2022-01-02 | 2022-01-03 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-04-02 | 10 |  |  | DF /F /86/42600 - GRATINGS | DFF - Replacement of gratings EL +42600 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059766 | FLMR DFF - Repl of gratings EL +42600 | DFF - Replacement of gratings EL +42600 |  |  | 3 | 0 | Empty | 2022-01-02 | 2022-01-03 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-04-02 | 20 |  |  | DF /F /86/42600 - GRATINGS | DFF - Replacement of gratings EL +42600 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059766 | FLMR DFF - Repl of gratings EL +42600 | DFF - Replacement of gratings EL +42600 |  |  | 1 | 0 | Empty | 2022-01-02 | 2022-01-03 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-04-02 | 30 |  |  | DF /F /86/42600 - GRATINGS | DFF - Replacement of gratings EL +42600 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059766 | FLMR DFF - Repl of gratings EL +42600 | DFF - Replacement of gratings EL +42600 |  |  | 4 | 0 | Empty | 2022-01-02 | 2022-01-03 | 2022-01-02 | 2022-01-02 | 2022-01-02 | 2022-04-02 | 40 |  |  | DF /F /86/42600 - GRATINGS | DFF - Replacement of gratings EL +42600 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059766 | FLMR DFF - Repl of gratings EL +42600 | DFF - Replacement of gratings EL +42600 |  |  | 18 | 0 | Empty | 2022-01-02 | 2022-01-03 | 2022-01-02 | 2022-01-03 | 2022-01-02 | 2022-04-02 | 50 |  |  | DF /F /86/42600 - GRATINGS | DFF - Replacement of gratings EL +42600 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059766 | FLMR DFF - Repl of gratings EL +42600 | DFF - Replacement of gratings EL +42600 |  |  | 1 | 0 | Empty | 2022-01-02 | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-01-02 | 2022-04-02 | 60 |  |  | DF /F /86/42600 - GRATINGS | DFF - Replacement of gratings EL +42600 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263069 | 1Y HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2023-06-07 | 2023-07-07 | 10 | SECE | SECE | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263069 | 1Y HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-18 | 2023-06-07 | 2023-07-07 | 20 | SECE | SECE | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263069 | 1Y HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-06-07 | 2023-07-07 | 30 | SECE | SECE | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263069 | 1Y HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2023-06-07 | 2023-07-07 | 40 | SECE | SECE | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263069 | 1Y HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-06-07 | 2023-07-07 | 50 | SECE | SECE | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 6 | 22 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 10 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 20 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 30 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 40 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 50 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 60 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079502 | DFC N2 comp-5408 bliver varm. | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2023-01-27 | 2023-06-11 | 70 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-A-5408 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2022-04-27 | 2023-02-21 | 10 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 5 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2022-04-27 | 2023-02-21 | 20 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2022-04-27 | 2023-02-21 | 30 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 16 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2022-04-27 | 2023-02-21 | 40 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2022-04-27 | 2023-02-21 | 50 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2022-04-27 | 2023-02-21 | 60 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2022-04-27 | 2023-02-21 | 90 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 5 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2022-04-27 | 2023-02-21 | 100 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2022-04-27 | 2023-02-21 | 110 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-07-31 | 2022-04-27 | 2023-02-21 | 120 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2022-04-27 | 2023-02-21 | 130 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 4 | 4 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-01-27 | 2024-01-27 | 2022-04-27 | 2023-02-21 | 140 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100058083 | DFFA-P-3901 Demultifier Kemikalieunit sk | Isolate DFFA-P-3901 | PCNFSCH | PCNFSCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2022-04-27 | 2023-02-21 | 150 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-P-3901 | Isolate DFFA-P-3901 | Unknown
3 | NE | WRO | MTN-MECH | MTN-MECH | 2300000842 | Setpoint Change DFE-PAHH-30018 | Setpoint Change DFE-PAHH-30018 |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2010-01-01 | 2030-12-31 | 10 |  |  | DF /E /10/DFEZ-PT-30018 | Setpoint Change DFE-PAHH-30018 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400350908 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-21 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 13 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-10-13 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-21 | ATEX EQUIPMENT INSPECTION | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-RIGG | 2100025153 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 12 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-18 | 2024-09-19 | 2019-09-13 | 2019-10-03 | 5 | AWSC | AWSC | DF /G /76/DFGA-E-5344 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | PRODTECH | 2100025153 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 6 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-19 | 2024-09-21 | 2019-09-13 | 2019-10-03 | 10 | AWSC | AWSC | DF /G /76/DFGA-E-5344 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-MECH | 2100025153 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 14 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-21 | 2024-09-23 | 2019-09-13 | 2019-10-03 | 20 | AWSC | AWSC | DF /G /76/DFGA-E-5344 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-RIGG | 2100025153 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 6 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-23 | 2024-09-23 | 2019-09-13 | 2019-10-03 | 30 | AWSC | AWSC | DF /G /76/DFGA-E-5344 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | PRODTECH | 2100025153 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 6 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-23 | 2024-09-25 | 2019-09-13 | 2019-10-03 | 40 | AWSC | AWSC | DF /G /76/DFGA-E-5344 | L3 Rigg up for replace valve(s) | Unknown
3 | DFG-COOL | WDF | MTN-MECH | MTN-RIGG | 2100025153 | Replace inlet/outlet 16" valves DFGA-E-5 | L3 Rigg up for replace valve(s) | AWSC | AWSC | 8 | 0 | Hold Step | 2024-09-18 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2019-09-13 | 2019-10-03 | 50 | AWSC | AWSC | DF /G /76/DFGA-E-5344 | L3 Rigg up for replace valve(s) | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 3 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-03 | 2024-06-16 | 2023-06-07 | 2025-11-23 | 9 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | PRODTECH | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-RIGG | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-RIGG | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 12 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | PRODTECH | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-SCAF | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 8 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-03 | 2024-06-16 | 2023-06-07 | 2025-11-23 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-SCAF | 2100079223 | HCV-440132 IS PASSING. | Erect and dismantle scaffold | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 6 | Empty | 2024-06-07 | 2024-06-16 | 2024-06-07 | 2024-06-07 | 2023-06-07 | 2025-11-23 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-HCV-440132 | Erect and dismantle scaffold | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200002978 | DFC DFCM-LT-50750 calibrate transmitt | koordinate with control room |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2018-04-14 | 2018-07-13 | 10 |  |  | DF /C /28/DFCM-LT-50750 | koordinate with control room | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-INST | 2200002978 | DFC DFCM-LT-50750 calibrate transmitt | koordinate with control room |  |  | 10 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2018-04-14 | 2018-07-13 | 30 |  |  | DF /C /28/DFCM-LT-50750 | koordinate with control room | Unknown
3 | NOSD | WDF | MTN-TURB | MTN-TELE | 2100099271 | Defect power supply X1P05 | Replace power supply X1P05 |  |  | 4 | 4 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-18 | 2024-04-01 | 10 |  |  | DF /F /31/DFFA-FP-4301 | Replace power supply X1P05 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104196 | Winter Bleed Blocked up | Isolate water supply |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2023-12-03 | 2024-01-17 | 10 |  |  | DF /C /01/DFCM-HCV-03054 | Isolate water supply | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104196 | Winter Bleed Blocked up | Isolate water supply |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2023-12-03 | 2024-01-17 | 20 |  |  | DF /C /01/DFCM-HCV-03054 | Isolate water supply | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100104196 | Winter Bleed Blocked up | Isolate water supply |  |  | 36 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2023-12-03 | 2024-01-17 | 30 |  |  | DF /C /01/DFCM-HCV-03054 | Isolate water supply | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104196 | Winter Bleed Blocked up | Isolate water supply |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2023-12-03 | 2024-01-17 | 40 |  |  | DF /C /01/DFCM-HCV-03054 | Isolate water supply | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200005231 | DFGA-PRV-545101 Replace DUE 31-12-2020 | Replace valve |  |  | 2 | 0 | W25-W26 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-03-14 | 2022-01-08 | 10 |  |  | DF /G /07/DFGA-PRV-545101 | Replace valve | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005231 | DFGA-PRV-545101 Replace DUE 31-12-2020 | Replace valve |  |  | 4 | 0 | W25-W26 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-03-14 | 2022-01-08 | 20 |  |  | DF /G /07/DFGA-PRV-545101 | Replace valve | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200005231 | DFGA-PRV-545101 Replace DUE 31-12-2020 | Replace valve |  |  | 2 | 0 | W25-W26 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-03-14 | 2022-01-08 | 30 |  |  | DF /G /07/DFGA-PRV-545101 | Replace valve | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | PRODTECH | 2100110802 | Very low vibrations on 27VT1486 | Isolate DFGA-GT-4302 - PROD |  |  | 2 | 0 | Empty | 2024-07-14 | 2024-07-20 | 2024-07-14 | 2024-07-15 | 2024-05-23 | 2024-10-05 | 10 |  |  | DF /G /31/DFGA-GT-4302 | Isolate DFGA-GT-4302 - PROD | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-ELEC | 2100110802 | Very low vibrations on 27VT1486 | Isolate DFGA-GT-4302 - PROD |  |  | 2 | 0 | Empty | 2024-07-14 | 2024-07-20 | 2024-07-15 | 2024-07-15 | 2024-05-23 | 2024-10-05 | 20 |  |  | DF /G /31/DFGA-GT-4302 | Isolate DFGA-GT-4302 - PROD | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100110802 | Very low vibrations on 27VT1486 | Isolate DFGA-GT-4302 - PROD |  |  | 8 | 0 | Empty | 2024-07-14 | 2024-07-20 | 2024-07-15 | 2024-07-17 | 2024-05-23 | 2024-10-05 | 30 |  |  | DF /G /31/DFGA-GT-4302 | Isolate DFGA-GT-4302 - PROD | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100110802 | Very low vibrations on 27VT1486 | Isolate DFGA-GT-4302 - PROD |  |  | 8 | 0 | Empty | 2024-07-14 | 2024-07-20 | 2024-07-17 | 2024-07-19 | 2024-05-23 | 2024-10-05 | 40 |  |  | DF /G /31/DFGA-GT-4302 | Isolate DFGA-GT-4302 - PROD | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-ELEC | 2100110802 | Very low vibrations on 27VT1486 | Isolate DFGA-GT-4302 - PROD |  |  | 2 | 0 | Empty | 2024-07-14 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2024-05-23 | 2024-10-05 | 50 |  |  | DF /G /31/DFGA-GT-4302 | Isolate DFGA-GT-4302 - PROD | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | PRODTECH | 2100110802 | Very low vibrations on 27VT1486 | Isolate DFGA-GT-4302 - PROD |  |  | 2 | 0 | Empty | 2024-07-14 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-05-23 | 2024-10-05 | 60 |  |  | DF /G /31/DFGA-GT-4302 | Isolate DFGA-GT-4302 - PROD | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100025201 | PVI LG-410413 changeout of LG and HCV's | Isolate DFGA-LG-410413 LG and HCV | AWSC | AWSC | 12 | 0 | Campaign - ENG548 | 2024-06-01 | 2024-06-07 | 2024-06-01 | 2024-06-02 | 2020-02-12 | 2020-05-12 | 5 | AWSC | AWSC | DF /G /30/DFGA-LG-410413 | Isolate DFGA-LG-410413 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100025201 | PVI LG-410413 changeout of LG and HCV's | Isolate DFGA-LG-410413 LG and HCV | AWSC | AWSC | 3 | 0 | Campaign - ENG548 | 2024-06-01 | 2024-06-07 | 2024-06-02 | 2024-06-03 | 2020-02-12 | 2020-05-12 | 10 | AWSC | AWSC | DF /G /30/DFGA-LG-410413 | Isolate DFGA-LG-410413 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100025201 | PVI LG-410413 changeout of LG and HCV's | Isolate DFGA-LG-410413 LG and HCV | AWSC | AWSC | 10 | 0 | Campaign - ENG548 | 2024-06-01 | 2024-06-07 | 2024-06-03 | 2024-06-05 | 2020-02-12 | 2020-05-12 | 15 | AWSC | AWSC | DF /G /30/DFGA-LG-410413 | Isolate DFGA-LG-410413 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100025201 | PVI LG-410413 changeout of LG and HCV's | Isolate DFGA-LG-410413 LG and HCV | AWSC | AWSC | 10 | 0 | Campaign - ENG548 | 2024-06-01 | 2024-06-07 | 2024-06-03 | 2024-06-05 | 2020-02-12 | 2020-05-12 | 20 | AWSC | AWSC | DF /G /30/DFGA-LG-410413 | Isolate DFGA-LG-410413 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100025201 | PVI LG-410413 changeout of LG and HCV's | Isolate DFGA-LG-410413 LG and HCV | AWSC | AWSC | 3 | 0 | Campaign - ENG548 | 2024-06-01 | 2024-06-07 | 2024-06-05 | 2024-06-06 | 2020-02-12 | 2020-05-12 | 30 | AWSC | AWSC | DF /G /30/DFGA-LG-410413 | Isolate DFGA-LG-410413 LG and HCV | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100025201 | PVI LG-410413 changeout of LG and HCV's | Isolate DFGA-LG-410413 LG and HCV | AWSC | AWSC | 8 | 0 | Campaign - ENG548 | 2024-06-01 | 2024-06-07 | 2024-06-06 | 2024-06-07 | 2020-02-12 | 2020-05-12 | 40 | AWSC | AWSC | DF /G /30/DFGA-LG-410413 | Isolate DFGA-LG-410413 LG and HCV | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300003816 | DO NOT USE - Replaced by 2300007175 | DK40 - CONSUMABLE PROD - OFFICE |  |  | 0 | 0 | Empty | 2022-09-11 | 2022-09-11 | 2022-09-11 | 2022-09-11 | 2022-09-11 | 2023-07-08 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OFFICE | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100023909 | Change DFCC-SOV-12842. | L3 isolate SOV. | PCNF | PCNF | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2018-11-04 | 2019-02-02 | 10 | PCNF | PCNF | DF /C /09/DFCC-FD-12842 | L3 isolate SOV. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100023909 | Change DFCC-SOV-12842. | L3 isolate SOV. | PCNF | PCNF | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2018-11-04 | 2019-02-02 | 20 | PCNF | PCNF | DF /C /09/DFCC-FD-12842 | L3 isolate SOV. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100023909 | Change DFCC-SOV-12842. | L3 isolate SOV. | PCNF | PCNF | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2018-11-04 | 2019-02-02 | 30 | PCNF | PCNF | DF /C /09/DFCC-FD-12842 | L3 isolate SOV. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100023909 | Change DFCC-SOV-12842. | L3 isolate SOV. | PCNF | PCNF | 1 | 2 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2018-11-04 | 2019-02-02 | 40 | PCNF | PCNF | DF /C /09/DFCC-FD-12842 | L3 isolate SOV. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100023909 | Change DFCC-SOV-12842. | L3 isolate SOV. | PCNF | PCNF | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2018-11-04 | 2019-02-02 | 50 | PCNF | PCNF | DF /C /09/DFCC-FD-12842 | L3 isolate SOV. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100023909 | Change DFCC-SOV-12842. | L3 isolate SOV. | PCNF | PCNF | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2018-11-04 | 2019-02-02 | 60 | PCNF | PCNF | DF /C /09/DFCC-FD-12842 | L3 isolate SOV. | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400294027 | 6M HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-12-22 | 2024-01-07 | 10 |  |  | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400294027 | 6M HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-12-22 | 2024-01-07 | 20 |  |  | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400294027 | 6M HYD POWER PACKAGE MAINT - DFFA-A-5901 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-12-22 | 2024-01-07 | 30 |  |  | DF /F /07/DFFA-A-5901 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100079751 | PIT-02477 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-02 | 2023-02-02 | 2023-06-17 | 10 |  |  | DF /G /34/DFGA-PIT-02477 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100079751 | PIT-02477 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 20 |  |  | DF /G /34/DFGA-PIT-02477 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-LAGG | 2100079751 | PIT-02477 is missing insulation | Isolate Heat Tracing |  |  | 8 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 30 |  |  | DF /G /34/DFGA-PIT-02477 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100079751 | PIT-02477 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 40 |  |  | DF /G /34/DFGA-PIT-02477 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100079751 | PIT-02477 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 50 |  |  | DF /G /34/DFGA-PIT-02477 | Isolate Heat Tracing | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400282098 | 1Y STEAM CLEANER CHECK-DFFA-A-1110 | Hours for executing PM check | AWSC | AWSC | 24 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-07-25 | 2024-07-25 | 2023-09-09 | 2023-10-26 | 10 | AWSC | AWSC | DF /F /72/DFFA-A-1110 | Hours for executing PM check | Unknown
D | NOSD | WPM | MTN-INST | MTN-MECH | 2400282098 | 1Y STEAM CLEANER CHECK-DFFA-A-1110 | Hours for executing PM check | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-07-25 | 2024-07-25 | 2023-09-09 | 2023-10-26 | 20 | AWSC | AWSC | DF /F /72/DFFA-A-1110 | Hours for executing PM check | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400282098 | 1Y STEAM CLEANER CHECK-DFFA-A-1110 | Hours for executing PM check | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-09-09 | 2023-10-26 | 30 | AWSC | AWSC | DF /F /72/DFFA-A-1110 | Hours for executing PM check | Unknown
D | NOSD | WPM | MTN-INST | MTN-MECH | 2400282098 | 1Y STEAM CLEANER CHECK-DFFA-A-1110 | Hours for executing PM check | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-09-09 | 2023-10-26 | 40 | AWSC | AWSC | DF /F /72/DFFA-A-1110 | Hours for executing PM check | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235660 | 4Y 400V N-SWB MAINT DFCI-N-1802-R07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R07A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235660 | 4Y 400V N-SWB MAINT DFCI-N-1802-R07 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R07A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235660 | 4Y 400V N-SWB MAINT DFCI-N-1802-R07 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R07A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235660 | 4Y 400V N-SWB MAINT DFCI-N-1802-R07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R07A | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269342 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-07-21 | 2023-08-20 | 10 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269342 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2023-07-21 | 2023-08-20 | 20 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400269342 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-23 | 2024-09-23 | 2023-07-21 | 2023-08-20 | 30 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400269342 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-07-21 | 2023-08-20 | 40 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269342 | 1Y DIESEL STORAGE TANK & PUMP MAINT -DFG | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-07-21 | 2023-08-20 | 50 | SECE | SECE | DF /G /71/DFGA-T-5750 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316057 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 1 | 0 | W35-W36 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2024-03-25 | 2024-04-30 | 10 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316057 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 8 | 0 | W35-W36 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-24 | 2024-03-25 | 2024-04-30 | 20 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316057 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 3 | 0 | W35-W36 | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2024-03-25 | 2024-04-30 | 30 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400316057 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 12 | 0 | W35-W36 | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-26 | 2024-03-25 | 2024-04-30 | 40 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316057 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 1 | 0 | W35-W36 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2024-03-25 | 2024-04-30 | 50 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400316057 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 2 | 0 | W35-W36 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2024-03-25 | 2024-04-30 | 60 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339046 | DFB_1Y_26200 INT STRUCT INSP - GVI | DFB_1Y_26200 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_26200 (MEZZANINE DECK) | DFB_1Y_26200 INT STRUCT INSP - GVI | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018133 | Replace Motor protection 1841-M109 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M109-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018133 | Replace Motor protection 1841-M109 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M109-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018133 | Replace Motor protection 1841-M109 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M109-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018133 | Replace Motor protection 1841-M109 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M109-02 | New mat num | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000954 | SCADA SW for ENG469B | SCADA SW for ENG469B | AWSC | AWSC | 12 | 0 | 2020 DATE TBC | 2024-10-05 | 2024-10-07 | 2024-10-05 | 2024-10-06 | 2019-06-09 | 2019-11-06 | 10 | AWSC | AWSC | DF /B /04/DFBA-FP-2039 | SCADA SW for ENG469B | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000954 | SCADA SW for ENG469B | SCADA SW for ENG469B | AWSC | AWSC | 5 | 0 | 2020 DATE TBC | 2024-10-05 | 2024-10-07 | 2024-10-06 | 2024-10-07 | 2019-06-09 | 2019-11-06 | 20 | AWSC | AWSC | DF /B /04/DFBA-FP-2039 | SCADA SW for ENG469B | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000954 | SCADA SW for ENG469B | SCADA SW for ENG469B | AWSC | AWSC | 0 | 0 | 2020 DATE TBC | 2024-10-05 | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2019-06-09 | 2019-11-06 | 30 | AWSC | AWSC | DF /B /04/DFBA-FP-2039 | SCADA SW for ENG469B | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230509 | 1Y SYS 51 CTRL VALVES/INST MAINT-DAN FG | SYS 51 CTRL VALVES/INST MAINT-DAN FG |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2023-01-18 | 2023-02-23 | 10 |  |  | DF /G /51/INSTRUMENTS | SYS 51 CTRL VALVES/INST MAINT-DAN FG | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400230509 | 1Y SYS 51 CTRL VALVES/INST MAINT-DAN FG | SYS 51 CTRL VALVES/INST MAINT-DAN FG |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2023-01-18 | 2023-02-23 | 20 |  |  | DF /G /51/INSTRUMENTS | SYS 51 CTRL VALVES/INST MAINT-DAN FG | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024834 | DFC Isolering i skotgennemføring itu. | Tools are checked for defects befor use |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-13 | 2023-02-13 | 2017-12-17 | 2018-03-17 | 10 |  |  | DF /C /79 | Tools are checked for defects befor use | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024834 | DFC Isolering i skotgennemføring itu. | Tools are checked for defects befor use |  |  | 31.5 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-13 | 2023-02-21 | 2017-12-17 | 2018-03-17 | 20 |  |  | DF /C /79 | Tools are checked for defects befor use | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100024834 | DFC Isolering i skotgennemføring itu. | Tools are checked for defects befor use |  |  | 17.399999999999998578914528472 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-21 | 2023-02-22 | 2017-12-17 | 2018-03-17 | 30 |  |  | DF /C /79 | Tools are checked for defects befor use | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024834 | DFC Isolering i skotgennemføring itu. | Tools are checked for defects befor use |  |  | 17.399999999999998578914528472 | 0 | Empty | 2023-02-13 | 2023-02-25 | 2023-02-22 | 2023-02-25 | 2017-12-17 | 2018-03-17 | 40 |  |  | DF /C /79 | Tools are checked for defects befor use | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322232 | DFB-75-CB-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 10 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NE | WRO | MTN-TURB | MTN-TURB | 2300000936 | FISKAL-gasdensitet i flowberegning | FISKAL - gasdensitet i flowberegning |  |  | 0 | 0 | W21-W22 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2013-12-01 | 2013-12-21 | 10 |  |  | DF /G /54/DFGA-FIT-570036 | FISKAL - gasdensitet i flowberegning | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308980 | 1Y FIRE DOORS TEST - DFG | FIRE DOORS TEST- DFG | SECE | SECE | 23 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-02-21 | 2024-03-22 | 10 | SECE | SECE | DF /G /02/FIRE-DOORS | FIRE DOORS TEST- DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-08-26 | 2024-08-26 | 2024-03-01 | 2024-07-14 | 10 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-08-26 | 2024-08-27 | 2024-03-01 | 2024-07-14 | 20 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-08-27 | 2024-08-27 | 2024-03-01 | 2024-07-14 | 30 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 24 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-08-27 | 2024-08-30 | 2024-03-01 | 2024-07-14 | 40 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 36 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-08-30 | 2024-09-02 | 2024-03-01 | 2024-07-14 | 50 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 24 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-09-02 | 2024-09-05 | 2024-03-01 | 2024-07-14 | 60 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 36 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-09-05 | 2024-09-08 | 2024-03-01 | 2024-07-14 | 70 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-09-08 | 2024-09-09 | 2024-03-01 | 2024-07-14 | 80 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100105561 | Riser spool replacement DFCM-P-0304 | Isolate FWP electrically High Voltage |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-10 | 2024-09-09 | 2024-09-10 | 2024-03-01 | 2024-07-14 | 90 |  |  | DF /C /01/DFCM-P-0304 | Isolate FWP electrically High Voltage | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045946 | DFGA-A-5352 Twin filter downstream P-537 | Isolate DFCM-CM-5408 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-02-22 | 2021-03-14 | 10 |  |  | DF /G /50/DFGA-A-5352 | Isolate DFCM-CM-5408 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045946 | DFGA-A-5352 Twin filter downstream P-537 | Isolate DFCM-CM-5408 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-02-22 | 2021-03-14 | 20 |  |  | DF /G /50/DFGA-A-5352 | Isolate DFCM-CM-5408 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045946 | DFGA-A-5352 Twin filter downstream P-537 | Isolate DFCM-CM-5408 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-02-22 | 2021-03-14 | 30 |  |  | DF /G /50/DFGA-A-5352 | Isolate DFCM-CM-5408 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100045946 | DFGA-A-5352 Twin filter downstream P-537 | Isolate DFCM-CM-5408 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-02-22 | 2021-03-14 | 40 |  |  | DF /G /50/DFGA-A-5352 | Isolate DFCM-CM-5408 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2020-03-25 | 2020-05-04 | 5 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2020-03-25 | 2020-05-04 | 10 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2020-03-25 | 2020-05-04 | 30 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2020-03-25 | 2020-05-04 | 40 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2020-03-25 | 2020-05-04 | 50 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2020-03-25 | 2020-05-04 | 60 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029689 | Replace Actuator DFFA-XCV-301103 (Ekst. | Isolate hydraulik supply DFFA-XCV-301103 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2020-03-25 | 2020-05-04 | 70 |  |  | DF /F /10/DFFA-XCV-301103 | Isolate hydraulik supply DFFA-XCV-301103 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235668 | 4Y 380V N-SWB MAINT-DFCI-N-1821/22/23 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1821 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235668 | 4Y 380V N-SWB MAINT-DFCI-N-1821/22/23 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1821 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235668 | 4Y 380V N-SWB MAINT-DFCI-N-1821/22/23 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1821 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235668 | 4Y 380V N-SWB MAINT-DFCI-N-1821/22/23 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1821 | ISOLATION ELECTRICAL | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-ROPE | 2100097673 | FFSP: Add Tempr Repair to DFB16"9001 | PO EMS |  |  | 0 | 0 | Empty | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 10 |  |  | DF /B /12/DFB-16-PHS-033-9001-BD-U | PO EMS | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-PIPF | 2100097673 | FFSP: Add Tempr Repair to DFB16"9001 | PO EMS |  |  | 0 | 0 | Empty | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-02 | 2023-10-03 | 20 |  |  | DF /B /12/DFB-16-PHS-033-9001-BD-U | PO EMS | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322235 | DFB-36-CO-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-20 | 2024-06-22 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-22 | 2024-06-22 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 8 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-22 | 2024-06-22 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-22 | 2024-06-22 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-22 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284309 | PSV Calibration - DFGA-PSV-430008B | Scaffolding | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 10 | 4 | W25-W26 | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /32/DFGA-PSV-430008B | Scaffolding | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-12-06 | 2022-05-05 | 10 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-12-06 | 2022-05-05 | 11 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-12-06 | 2022-05-05 | 20 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-12-06 | 2022-05-05 | 21 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-12-06 | 2022-05-05 | 30 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-12-06 | 2022-05-05 | 31 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-12-06 | 2022-05-05 | 40 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100055401 | DFF-17 chem inj. flow control defective | Isolate chemical inj. well 17 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-12-06 | 2022-05-05 | 41 |  |  | DF /F /75/DFFA-FIT-390187 | Isolate chemical inj. well 17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235607 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-13 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-13 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235607 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-13 | ISOLATION ELECTRICAL |  |  | 21 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-20 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-13 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235607 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-13 | ISOLATION ELECTRICAL |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-13 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235607 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-13 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-13 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089845 | Unable to regulate backpressure | Safing |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | 2023-06-09 | 2023-10-22 | 5 |  |  | DF /G /51/DFGA-PCV-530061 | Safing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089845 | Unable to regulate backpressure | Safing |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-22 | 2023-06-09 | 2023-10-22 | 10 |  |  | DF /G /51/DFGA-PCV-530061 | Safing | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100089845 | Unable to regulate backpressure | Safing |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2023-06-09 | 2023-10-22 | 20 |  |  | DF /G /51/DFGA-PCV-530061 | Safing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089845 | Unable to regulate backpressure | Safing |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-23 | 2024-08-23 | 2023-06-09 | 2023-10-22 | 30 |  |  | DF /G /51/DFGA-PCV-530061 | Safing | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400330004 | 6M PORTABLE GAS DETECTORS DFC | PORTABLE GAS DETECTORS CHECK - DFC | SECE | SECE | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2024-06-11 | 2024-06-27 | 10 | SECE | SECE | DF /C /03/PORTABLE-GAS-DETECTORS | PORTABLE GAS DETECTORS CHECK - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095635 | valve to the foam hose reel defect | Replace HCV | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-09-17 | 2024-01-30 | 10 | SECE | SECE | DF /B /01/DFBA-HR-0448 | Replace HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095635 | valve to the foam hose reel defect | Replace HCV | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-09-17 | 2024-01-30 | 20 | SECE | SECE | DF /B /01/DFBA-HR-0448 | Replace HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095635 | valve to the foam hose reel defect | Replace HCV | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-09-17 | 2024-01-30 | 30 | SECE | SECE | DF /B /01/DFBA-HR-0448 | Replace HCV | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337635 | 6M VISUAL INSPECT OF ESDV (DHDHPGAS) | ESDV VISUAL INSPECTION | SCH | SCH | 1 | 0 | W23-W24 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-08-19 | 10 | SCH | SCH | DF /F /34/DFFA-ESDV-380304 | ESDV VISUAL INSPECTION | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101566 | Wind speed sensor defective | Isolate wind speed sensor | PCNF | PCNF | 5 | 5 | Empty | 2024-08-17 | 2024-08-17 | 2024-06-17 | 2024-06-21 | 2023-12-11 | 2024-04-24 | 10 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Isolate wind speed sensor | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101566 | Wind speed sensor defective | Isolate wind speed sensor | PCNF | PCNF | 0 | 0 | Empty | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-12-11 | 2024-04-24 | 15 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Isolate wind speed sensor | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101566 | Wind speed sensor defective | Isolate wind speed sensor | PCNF | PCNF | 0.5 | 0 | Empty | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-12-11 | 2024-04-24 | 20 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Isolate wind speed sensor | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101566 | Wind speed sensor defective | Isolate wind speed sensor | PCNF | PCNF | 2 | 0 | Empty | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-12-11 | 2024-04-24 | 30 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Isolate wind speed sensor | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100101566 | Wind speed sensor defective | Isolate wind speed sensor | PCNF | PCNF | 0.5 | 0 | Empty | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-12-11 | 2024-04-24 | 40 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | Isolate wind speed sensor | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235734 | 4Y 380V E-SWB MAINT DFEZ-N-1804 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 10 | AWSCSECE | AWSCSECE | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235734 | 4Y 380V E-SWB MAINT DFEZ-N-1804 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 20 | AWSCSECE | AWSCSECE | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235734 | 4Y 380V E-SWB MAINT DFEZ-N-1804 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-01-30 | 2023-04-13 | 30 | AWSCSECE | AWSCSECE | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235734 | 4Y 380V E-SWB MAINT DFEZ-N-1804 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-01-30 | 2023-04-13 | 40 | AWSCSECE | AWSCSECE | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093130 | ANOCR DFC-DFF Bridge - Paint Prim. Str. | Set up equipment |  |  | 0 | 0 | Empty | 2023-07-30 | 2023-08-07 | 2023-07-30 | 2023-07-30 | 2023-07-30 | 2023-12-12 | 10 |  |  | DF /F /86/BRIDGE-DFF-DFC | Set up equipment | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093130 | ANOCR DFC-DFF Bridge - Paint Prim. Str. | Set up equipment |  |  | 12 | 0 | Empty | 2023-07-30 | 2023-08-07 | 2023-07-30 | 2023-07-31 | 2023-07-30 | 2023-12-12 | 20 |  |  | DF /F /86/BRIDGE-DFF-DFC | Set up equipment | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093130 | ANOCR DFC-DFF Bridge - Paint Prim. Str. | Set up equipment |  |  | 12 | 0 | Empty | 2023-07-30 | 2023-08-07 | 2023-07-31 | 2023-07-31 | 2023-07-30 | 2023-12-12 | 30 |  |  | DF /F /86/BRIDGE-DFF-DFC | Set up equipment | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093130 | ANOCR DFC-DFF Bridge - Paint Prim. Str. | Set up equipment |  |  | 108 | 0 | Empty | 2023-07-30 | 2023-08-07 | 2023-07-31 | 2023-08-06 | 2023-07-30 | 2023-12-12 | 40 |  |  | DF /F /86/BRIDGE-DFF-DFC | Set up equipment | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093130 | ANOCR DFC-DFF Bridge - Paint Prim. Str. | Set up equipment |  |  | 12 | 0 | Empty | 2023-07-30 | 2023-08-07 | 2023-08-06 | 2023-08-07 | 2023-07-30 | 2023-12-12 | 50 |  |  | DF /F /86/BRIDGE-DFF-DFC | Set up equipment | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093130 | ANOCR DFC-DFF Bridge - Paint Prim. Str. | Set up equipment |  |  | 0 | 0 | Empty | 2023-07-30 | 2023-08-07 | 2023-08-07 | 2023-08-07 | 2023-07-30 | 2023-12-12 | 60 |  |  | DF /F /86/BRIDGE-DFF-DFC | Set up equipment | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024273 | ANOS Remove 6 pad eyes DFF, Lev 0, WH N/ | L3 Permit & preparation |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-15 | 2019-03-27 | 2019-04-16 | 10 |  |  | DF /F /86/22000 - PRIM AND SEC STRUCT | L3 Permit & preparation | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024273 | ANOS Remove 6 pad eyes DFF, Lev 0, WH N/ | L3 Permit & preparation |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-15 | 2024-03-16 | 2024-03-15 | 2024-03-16 | 2019-03-27 | 2019-04-16 | 20 |  |  | DF /F /86/22000 - PRIM AND SEC STRUCT | L3 Permit & preparation | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 24 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-10-31 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-03 | 2024-11-04 | 2024-10-30 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-04 | 2024-11-04 | 2024-10-30 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-04 | 2024-11-05 | 2024-10-30 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 12 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-05 | 2024-11-07 | 2024-10-30 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-07 | 2024-11-07 | 2024-10-30 | 2024-12-31 | 80 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-07 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 90 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-09 | 2024-11-09 | 2024-10-30 | 2024-12-31 | 100 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-09 | 2024-11-09 | 2024-10-30 | 2024-12-31 | 110 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284318 | PSV Exchange - DFGA-PSV-530050A | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-30 | 2024-11-10 | 2024-11-10 | 2024-11-10 | 2024-10-30 | 2024-12-31 | 120 | AWSC | AWSC | DF /G /76/DFGA-PSV-530050A | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085364 | Light fixtures DFEZ-LN-1803-6-L3C | Replace light fixture |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-20 | 2023-08-02 | 10 |  |  | DF /E /61/DFEZ-N-1803 | Replace light fixture | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085364 | Light fixtures DFEZ-LN-1803-6-L3C | Replace light fixture |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-20 | 2023-08-02 | 20 |  |  | DF /E /61/DFEZ-N-1803 | Replace light fixture | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085364 | Light fixtures DFEZ-LN-1803-6-L3C | Replace light fixture |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-20 | 2023-08-02 | 30 |  |  | DF /E /61/DFEZ-N-1803 | Replace light fixture | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 21 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2024-12-31 | 2025-01-02 | 2021-01-24 | 2021-06-23 | 10 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 2 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2024-12-31 | 2024-12-31 | 2021-01-24 | 2021-06-23 | 20 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 3 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2025-01-02 | 2025-01-03 | 2021-01-24 | 2021-06-23 | 30 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 8 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2025-01-03 | 2025-01-04 | 2021-01-24 | 2021-06-23 | 40 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 4 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2025-01-04 | 2025-01-05 | 2021-01-24 | 2021-06-23 | 50 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 3 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2025-01-05 | 2025-01-05 | 2021-01-24 | 2021-06-23 | 60 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 2 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2025-01-05 | 2025-01-06 | 2021-01-24 | 2021-06-23 | 70 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
4 | DFG-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100040410 | DFG-HCV-440412B not able to close | Prepare permit/tools/matr | AWSC | AWSC | 15 | 0 | Empty | 2024-12-31 | 2025-01-07 | 2025-01-06 | 2025-01-07 | 2021-01-24 | 2021-06-23 | 80 | AWSC | AWSC | DF /G /32/DFGA-HCV-440412B-I | Prepare permit/tools/matr | Unknown
3 | DFCHPSEP | WDF | MTN-INST | MTN-LAGG | 2100059695 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Prepare matr/tool | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2021-12-22 | 2022-01-31 | 10 | AWSC | AWSC | DF /C /20/DFCI-LT-34014 | Prepare matr/tool | Unknown
3 | DFCHPSEP | WDF | MTN-INST | MTN-MECH | 2100059695 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Prepare matr/tool | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2021-12-22 | 2022-01-31 | 20 | AWSC | AWSC | DF /C /20/DFCI-LT-34014 | Prepare matr/tool | Unknown
3 | DFCHPSEP | WDF | MTN-INST | PRODTECH | 2100059695 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Prepare matr/tool | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2021-12-22 | 2022-01-31 | 30 | AWSC | AWSC | DF /C /20/DFCI-LT-34014 | Prepare matr/tool | Unknown
3 | DFCHPSEP | WDF | MTN-INST | MTN-MECH | 2100059695 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Prepare matr/tool | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2021-12-22 | 2022-01-31 | 40 | AWSC | AWSC | DF /C /20/DFCI-LT-34014 | Prepare matr/tool | Unknown
3 | DFCHPSEP | WDF | MTN-INST | PRODTECH | 2100059695 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Prepare matr/tool | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2021-12-22 | 2022-01-31 | 50 | AWSC | AWSC | DF /C /20/DFCI-LT-34014 | Prepare matr/tool | Unknown
3 | DFCHPSEP | WDF | MTN-INST | MTN-LAGG | 2100059695 | HP SEP. DFC-V-3402 VALVE STUCK FROM N9 | Prepare matr/tool | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2021-12-22 | 2022-01-31 | 60 | AWSC | AWSC | DF /C /20/DFCI-LT-34014 | Prepare matr/tool | Unknown
4 | Empty | WRO | UNKNOWN | WELLSUPV | 2300004026 | IRP Transport order. | IRP TRansport order |  |  | 0 | 0 | Empty | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2023-01-02 | 2025-06-20 | 10 |  |  | DF | IRP TRansport order | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286637 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PERSONAL ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-10-14 | 2023-11-19 | 10 |  |  | DF /C /09/A-1217 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286637 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PERSONAL ISOLATION |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-15 | 2023-10-14 | 2023-11-19 | 20 |  |  | DF /C /09/A-1217 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286637 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PERSONAL ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2023-10-14 | 2023-11-19 | 30 |  |  | DF /C /09/A-1217 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286637 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PERSONAL ISOLATION |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-10-14 | 2023-11-19 | 40 |  |  | DF /C /09/A-1217 | PERSONAL ISOLATION | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2020-08-16 | 2021-04-13 | 10 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2020-08-16 | 2021-04-13 | 20 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2020-08-16 | 2021-04-13 | 30 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-03 | 2020-08-16 | 2021-04-13 | 40 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2020-08-16 | 2021-04-13 | 50 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-04 | 2020-08-16 | 2021-04-13 | 60 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-05 | 2020-08-16 | 2021-04-13 | 70 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2020-08-16 | 2021-04-13 | 80 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
4 | DFG-FUEL | WDF | MTN-MECH | MTN-LAGG | 2100031501 | DFG US HCV-440140 intern læk mod pcv | Prepare Rigging equip. | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2020-08-16 | 2021-04-13 | 90 | AWSC | AWSC | DF /G /34/DFGA-HCV-440140 | Prepare Rigging equip. | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024898 | @DFB Gasliftmanifold HCVér til PI int | DFB, Udskift 2" 1500# HCV ventil Weld | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2016-01-01 | 2016-02-10 | 10 | AWSC | AWSC | DF /B /37/LIFT-GAS-MANIFOLD | DFB, Udskift 2" 1500# HCV ventil Weld | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-PIPF | 2100024898 | @DFB Gasliftmanifold HCVér til PI int | DFB, Udskift 2" 1500# HCV ventil Weld | AWSC | AWSC | 16.100000000000001421085471515 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2016-01-01 | 2016-02-10 | 20 | AWSC | AWSC | DF /B /37/LIFT-GAS-MANIFOLD | DFB, Udskift 2" 1500# HCV ventil Weld | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235793 | 4Y 380V N-SWB MAINT-DFAA-N-1800 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-07-24 | 2024-07-28 | 2024-07-24 | 2024-07-24 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /A /61/DFAA-N-1800 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235793 | 4Y 380V N-SWB MAINT-DFAA-N-1800 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-07-24 | 2024-07-28 | 2024-07-24 | 2024-07-27 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /A /61/DFAA-N-1800 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235793 | 4Y 380V N-SWB MAINT-DFAA-N-1800 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-07-24 | 2024-07-28 | 2024-07-27 | 2024-07-28 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /A /61/DFAA-N-1800 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235793 | 4Y 380V N-SWB MAINT-DFAA-N-1800 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /A /61/DFAA-N-1800 | DE-ISOLATION ELECTRICAL | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-05-17 | 2022-10-14 | 10 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-16 | 2022-05-17 | 2022-10-14 | 20 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-RIGG | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-17 | 2022-05-17 | 2022-10-14 | 30 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-18 | 2022-05-17 | 2022-10-14 | 40 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-RIGG | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-05-17 | 2022-10-14 | 50 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2022-05-17 | 2022-10-14 | 60 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-INST | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2022-05-17 | 2022-10-14 | 70 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2022-05-17 | 2022-10-14 | 80 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-MECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2022-05-17 | 2022-10-14 | 90 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100063873 | DFFA-ESDV-570210 & DFFA-ESDV-570217 inte | Isolate Hydr. and controls | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2022-05-17 | 2022-10-14 | 100 | SECE | SECE | DF /F /70 | Isolate Hydr. and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094836 | Replace knotted rope DFBA-CLR-0617 | Over the board work for rope replace |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-09-01 | 2024-01-14 | 10 |  |  | DF /B /02/DFBA-CLR-0617 | Over the board work for rope replace | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100094836 | Replace knotted rope DFBA-CLR-0617 | Over the board work for rope replace |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-09-01 | 2024-01-14 | 20 |  |  | DF /B /02/DFBA-CLR-0617 | Over the board work for rope replace | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023564 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 3.399999999999999911182158029 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2018-03-10 | 2018-06-08 | 5 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100023564 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 10 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023564 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 1 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 15 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023564 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 20 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023564 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-15 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 25 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100023564 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-15 | 2023-02-16 | 2018-03-10 | 2018-06-08 | 30 |  |  | DF /F /61/DFFA-N-1802 | permit prep | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235811 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF03 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF03-01 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235811 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF03 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF03-01 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235811 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF03 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF03-01 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235811 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF03 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF03-01 | DE-ISOLATION ELECTRICAL | Unknown
B | DHDHPGAS | WPM | MTN-MECH | PRODTECH | 2400230348 | 1Y FUNCT AND VISUAL INSP ESDV (DHDHPGAS) | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 1 | 0 | W17-18 | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-01-20 | 2023-02-19 | 10 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
B | DHDHPGAS | WPM | MTN-MECH | MTN-MECH | 2400230348 | 1Y FUNCT AND VISUAL INSP ESDV (DHDHPGAS) | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 3 | 0 | W17-18 | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-01-20 | 2023-02-19 | 20 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
B | DHDHPGAS | WPM | MTN-MECH | PRODTECH | 2400230348 | 1Y FUNCT AND VISUAL INSP ESDV (DHDHPGAS) | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 1 | 0 | W17-18 | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2023-01-20 | 2023-02-19 | 30 | AWSC | AWSC | DF /F /34/DFFA-ESDV-380304 | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018140 | Replace Motor protection 1841-M117 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M117-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018140 | Replace Motor protection 1841-M117 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M117-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018140 | Replace Motor protection 1841-M117 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M117-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018140 | Replace Motor protection 1841-M117 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M117-02 | New mat num | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081337 | Transmitterhus er defekt dfga-ft-550021 | Isolate Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 10 |  |  | DF /G /52/DFGA-FT-550021 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081337 | Transmitterhus er defekt dfga-ft-550021 | Isolate Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 20 |  |  | DF /G /52/DFGA-FT-550021 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100081337 | Transmitterhus er defekt dfga-ft-550021 | Isolate Flow meter |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 30 |  |  | DF /G /52/DFGA-FT-550021 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081337 | Transmitterhus er defekt dfga-ft-550021 | Isolate Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 40 |  |  | DF /G /52/DFGA-FT-550021 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081337 | Transmitterhus er defekt dfga-ft-550021 | Isolate Flow meter |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 50 |  |  | DF /G /52/DFGA-FT-550021 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081337 | Transmitterhus er defekt dfga-ft-550021 | Isolate Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 60 |  |  | DF /G /52/DFGA-FT-550021 | Isolate Flow meter | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235771 | 4Y 380V N-SWB MAINT-DFEZ-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-N-1803 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235771 | 4Y 380V N-SWB MAINT-DFEZ-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-N-1803 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235771 | 4Y 380V N-SWB MAINT-DFEZ-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /61/DFEZ-N-1803 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235771 | 4Y 380V N-SWB MAINT-DFEZ-N-1803 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /61/DFEZ-N-1803 | ISOLATION ELECTRICAL | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 0 | 195 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-06-15 | 2023-06-26 | 2023-06-15 | 2023-07-30 | 10 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-ROPE | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 4 | 4 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-06-15 | 2023-06-26 | 2023-06-15 | 2023-07-30 | 20 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 0 | 0 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-06-15 | 2023-06-26 | 2023-06-15 | 2023-07-30 | 30 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 0 | 56 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-06-26 | 2023-06-26 | 2023-06-15 | 2023-07-30 | 40 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-ROPE | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 4 | 4 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-07-31 | 2023-08-01 | 2023-06-15 | 2023-07-30 | 50 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 20 | 13 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-08-01 | 2023-08-06 | 2023-06-15 | 2023-07-30 | 60 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 36 | 30 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-08-06 | 2023-08-15 | 2023-06-15 | 2023-07-30 | 70 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
2 | DFF-IPHP | WDF | MTN-TURB | VEN-MECH | 2100092716 | Vibration/Seal Issues IP/HP-FF | Setup rigging equipment | SCH | SCH | 36 | 36 | W31 DK40-M-7760 | 2023-07-31 | 2023-08-19 | 2023-08-15 | 2023-08-19 | 2023-06-15 | 2023-07-30 | 80 | SCH | SCH | DF /F /31/DFFA-C-4301 | Setup rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104205 | XCV internal leaking on watermaker | Replace valve and act. (AV 1-6) |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-02-04 | 2024-06-18 | 10 |  |  | DF /C /85/DFCM-A-1027 | Replace valve and act. (AV 1-6) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104205 | XCV internal leaking on watermaker | Replace valve and act. (AV 1-6) |  |  | 4 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-02-04 | 2024-06-18 | 20 |  |  | DF /C /85/DFCM-A-1027 | Replace valve and act. (AV 1-6) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100104205 | XCV internal leaking on watermaker | Replace valve and act. (AV 1-6) |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2024-02-04 | 2024-06-18 | 30 |  |  | DF /C /85/DFCM-A-1027 | Replace valve and act. (AV 1-6) | Unknown
3 | DFF-1610 | WDF | MTN-TURB | MTN-TURB | 2100024918 | DFFA-E-1610 oilcooles, to be exchanged | Isolate DFFA-E-1610 | PCNFAWSC | PCNFAWSC | 1 | 0 | Wrong cooler | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2019-09-28 | 2019-12-27 | 10 | PCNFAWSC | PCNFAWSC | DF /F /60/DFFA-E-1610 | Isolate DFFA-E-1610 | Unknown
3 | DFF-1610 | WDF | MTN-TURB | VEN-MECH | 2100024918 | DFFA-E-1610 oilcooles, to be exchanged | Isolate DFFA-E-1610 | PCNFAWSC | PCNFAWSC | 14 | 0 | Wrong cooler | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2019-09-28 | 2019-12-27 | 20 | PCNFAWSC | PCNFAWSC | DF /F /60/DFFA-E-1610 | Isolate DFFA-E-1610 | Unknown
3 | DFF-1610 | WDF | MTN-TURB | MTN-RIGG | 2100024918 | DFFA-E-1610 oilcooles, to be exchanged | Isolate DFFA-E-1610 | PCNFAWSC | PCNFAWSC | 8 | 8 | Wrong cooler | 2024-09-15 | 2024-09-16 | 2021-05-03 | 2021-05-09 | 2019-09-28 | 2019-12-27 | 25 | PCNFAWSC | PCNFAWSC | DF /F /60/DFFA-E-1610 | Isolate DFFA-E-1610 | Unknown
3 | DFF-1610 | WDF | MTN-TURB | MTN-TURB | 2100024918 | DFFA-E-1610 oilcooles, to be exchanged | Isolate DFFA-E-1610 | PCNFAWSC | PCNFAWSC | 1 | 0 | Wrong cooler | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2019-09-28 | 2019-12-27 | 30 | PCNFAWSC | PCNFAWSC | DF /F /60/DFFA-E-1610 | Isolate DFFA-E-1610 | Unknown
3 | DFF-1610 | WDF | MTN-TURB | MTN-SCAF | 2100024918 | DFFA-E-1610 oilcooles, to be exchanged | Isolate DFFA-E-1610 | PCNFAWSC | PCNFAWSC | 4 | 4 | Wrong cooler | 2024-09-15 | 2024-09-16 | 2021-05-03 | 2021-05-09 | 2019-09-28 | 2019-12-27 | 40 | PCNFAWSC | PCNFAWSC | DF /F /60/DFFA-E-1610 | Isolate DFFA-E-1610 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038175 | Replacement of RCDs | Prove dead |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2020-12-06 | 2021-05-05 | 10 |  |  | DF /G /61/DFGA-LP-1850 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038175 | Replacement of RCDs | Prove dead |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-23 | 2020-12-06 | 2021-05-05 | 20 |  |  | DF /G /61/DFGA-LP-1850 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038175 | Replacement of RCDs | Prove dead |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-29 | 2020-12-06 | 2021-05-05 | 30 |  |  | DF /G /61/DFGA-LP-1850 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038175 | Replacement of RCDs | Prove dead |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2020-12-06 | 2021-05-05 | 40 |  |  | DF /G /61/DFGA-LP-1850 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038175 | Replacement of RCDs | Prove dead |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2020-12-06 | 2021-05-05 | 50 |  |  | DF /G /61/DFGA-LP-1850 | Prove dead | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057175 | Defekte manometre.på esdv. | Dismount Pressure gauge |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-11-12 | 2022-02-10 | 10 |  |  | DF /C /27/DFCM-ESDV-50383 | Dismount Pressure gauge | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057175 | Defekte manometre.på esdv. | Dismount Pressure gauge |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-11-12 | 2022-02-10 | 30 |  |  | DF /C /27/DFCM-ESDV-50383 | Dismount Pressure gauge | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057175 | Defekte manometre.på esdv. | Dismount Pressure gauge |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-11-12 | 2022-02-10 | 40 |  |  | DF /C /27/DFCM-ESDV-50383 | Dismount Pressure gauge | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057175 | Defekte manometre.på esdv. | Dismount Pressure gauge |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-11-12 | 2022-02-10 | 60 |  |  | DF /C /27/DFCM-ESDV-50383 | Dismount Pressure gauge | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400321284 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-14 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 30 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2024-03-09 | 2024-05-10 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-14 | ATEX EQUIPMENT INSPECTION | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100102263 | DFFMM3551B spindle due not drive | Troubleshoot MM-3551B |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-18 | 2024-01-02 | 10 |  |  | DF /F /51/DFFB-MM-3551B | Troubleshoot MM-3551B | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100102263 | DFFMM3551B spindle due not drive | Troubleshoot MM-3551B |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-18 | 2024-01-02 | 20 |  |  | DF /F /51/DFFB-MM-3551B | Troubleshoot MM-3551B | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100102263 | DFFMM3551B spindle due not drive | Troubleshoot MM-3551B |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-18 | 2024-01-02 | 30 |  |  | DF /F /51/DFFB-MM-3551B | Troubleshoot MM-3551B | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400263360 | 1Y POT WATER MAKER SKID MAINT-A-1027/37 | ISOLATION BY PRODUCTION | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-07-29 | 2023-06-04 | 2023-07-10 | 10 | SCH | SCH | DF /C /85/DFCM-A-1027 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263360 | 1Y POT WATER MAKER SKID MAINT-A-1027/37 | ISOLATION BY PRODUCTION | SCH | SCH | 10 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-08-01 | 2023-06-04 | 2023-07-10 | 20 | SCH | SCH | DF /C /85/DFCM-A-1027 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400263360 | 1Y POT WATER MAKER SKID MAINT-A-1027/37 | ISOLATION BY PRODUCTION | SCH | SCH | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-01 | 2024-08-02 | 2023-06-04 | 2023-07-10 | 30 | SCH | SCH | DF /C /85/DFCM-A-1027 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263360 | 1Y POT WATER MAKER SKID MAINT-A-1027/37 | ISOLATION BY PRODUCTION | SCH | SCH | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-03 | 2023-06-04 | 2023-07-10 | 40 | SCH | SCH | DF /C /85/DFCM-A-1027 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400263360 | 1Y POT WATER MAKER SKID MAINT-A-1027/37 | ISOLATION BY PRODUCTION | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-03 | 2024-08-04 | 2023-06-04 | 2023-07-10 | 50 | SCH | SCH | DF /C /85/DFCM-A-1027 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084826 | PVI DAN F Level glass LG-500101 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 10 |  |  | DF /F /28/DFFA-LG-500101 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084826 | PVI DAN F Level glass LG-500101 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 20 |  |  | DF /F /28/DFFA-LG-500101 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084826 | PVI DAN F Level glass LG-500101 | Isolate Heat Tracing |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-08-02 | 2026-01-18 | 30 |  |  | DF /F /28/DFFA-LG-500101 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084826 | PVI DAN F Level glass LG-500101 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 40 |  |  | DF /F /28/DFFA-LG-500101 | Isolate Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084826 | PVI DAN F Level glass LG-500101 | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 50 |  |  | DF /F /28/DFFA-LG-500101 | Isolate Heat Tracing | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235669 | 4Y 380V N-SWB MAINT-DFCI-N-1821/2/3-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1821_2_3-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235669 | 4Y 380V N-SWB MAINT-DFCI-N-1821/2/3-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1821_2_3-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235669 | 4Y 380V N-SWB MAINT-DFCI-N-1821/2/3-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1821_2_3-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235669 | 4Y 380V N-SWB MAINT-DFCI-N-1821/2/3-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1821_2_3-1A01 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053772 | Replace valves for PCV | Production Isolation/Permit |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2021-11-07 | 2022-04-06 | 10 |  |  | DF /C /01 | Production Isolation/Permit | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053772 | Replace valves for PCV | Production Isolation/Permit |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2021-11-07 | 2022-04-06 | 20 |  |  | DF /C /01 | Production Isolation/Permit | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053772 | Replace valves for PCV | Production Isolation/Permit |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2021-11-07 | 2022-04-06 | 30 |  |  | DF /C /01 | Production Isolation/Permit | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053772 | Replace valves for PCV | Production Isolation/Permit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2021-11-07 | 2022-04-06 | 40 |  |  | DF /C /01 | Production Isolation/Permit | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053772 | Replace valves for PCV | Production Isolation/Permit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2021-11-07 | 2022-04-06 | 50 |  |  | DF /C /01 | Production Isolation/Permit | Unknown
A | DAB-LIFT | WPM | MTN-MECH | PRODTECH | 2400325544 | 1Y ESDV LEAK TEST DFFA-ESDV-380106 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-11-18 | 2024-11-19 | 2024-11-18 | 2024-11-18 | 2024-11-18 | 2024-12-18 | 5 | AWSCSECE | AWSCSECE | DF /F /34/DFFA-ESDV-380106 | ISOLATION BY PRODUCTION | Unknown
A | DAB-LIFT | WPM | MTN-MECH | PRODTECH | 2400325544 | 1Y ESDV LEAK TEST DFFA-ESDV-380106 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-11-18 | 2024-11-19 | 2024-11-18 | 2024-11-19 | 2024-11-18 | 2024-12-18 | 10 | AWSCSECE | AWSCSECE | DF /F /34/DFFA-ESDV-380106 | ISOLATION BY PRODUCTION | Unknown
A | DAB-LIFT | WPM | MTN-MECH | PRODTECH | 2400325544 | 1Y ESDV LEAK TEST DFFA-ESDV-380106 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-11-18 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-18 | 2024-12-18 | 20 | AWSCSECE | AWSCSECE | DF /F /34/DFFA-ESDV-380106 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339094 | DFC_1Y_41000 INT STRUCT INSP - GVI | DFC_1Y_41000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_41000 (LEVEL4) | DFC_1Y_41000 INT STRUCT INSP - GVI | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100025244 | 0FG Mount PRV on BDV control panel | Remove isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2017-12-29 | 2018-03-29 | 10 |  |  | DF /G /31/DFGA-BDV-440014 | Remove isolation | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100025244 | 0FG Mount PRV on BDV control panel | Remove isolation |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-18 | 2017-12-29 | 2018-03-29 | 20 |  |  | DF /G /31/DFGA-BDV-440014 | Remove isolation | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100025244 | 0FG Mount PRV on BDV control panel | Remove isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2017-12-29 | 2018-03-29 | 30 |  |  | DF /G /31/DFGA-BDV-440014 | Remove isolation | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100025244 | 0FG Mount PRV on BDV control panel | Remove isolation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2017-12-29 | 2018-03-29 | 40 |  |  | DF /G /31/DFGA-BDV-440014 | Remove isolation | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100025244 | 0FG Mount PRV on BDV control panel | Remove isolation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2017-12-29 | 2018-03-29 | 50 |  |  | DF /G /31/DFGA-BDV-440014 | Remove isolation | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259294 | 1Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W19-W20 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-05-20 | 2023-06-19 | 10 | SECE | SECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400259294 | 1Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-05-20 | 2023-06-19 | 20 | SECE | SECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259294 | 1Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2023-05-20 | 2023-06-19 | 30 | SECE | SECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259294 | 1Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W19-W20 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-05-20 | 2023-06-19 | 40 | SECE | SECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259294 | 1Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W19-W20 | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-05-20 | 2023-06-19 | 50 | SECE | SECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100068308 | DFA/78 Replace operator seat | Isolation/deisolation of crane |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-15 | 2022-08-08 | 2023-01-05 | 10 |  |  | DF /A /78/DFAA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100068308 | DFA/78 Replace operator seat | Isolation/deisolation of crane |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-19 | 2022-08-08 | 2023-01-05 | 20 |  |  | DF /A /78/DFAA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100068308 | DFA/78 Replace operator seat | Isolation/deisolation of crane |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-19 | 2022-08-08 | 2023-01-05 | 30 |  |  | DF /A /78/DFAA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100068308 | DFA/78 Replace operator seat | Isolation/deisolation of crane |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2022-08-08 | 2023-01-05 | 40 |  |  | DF /A /78/DFAA-X-6102 | Isolation/deisolation of crane | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | WELLSUPV | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 0 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 1 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 24 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 2 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 3 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-SCAF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 6 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 10 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 20 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | PRODTECH | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 6 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 30 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 40 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 50 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-RIGG | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 17.399999999999998578914528472 | 18 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 60 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 72 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 70 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 80 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 90 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 4.4000000000000003552713678785 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 100 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | PRODTECH | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 6 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 110 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-PIPF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 120 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-SCAF | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8.699999999999999289457264236 | 5 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 130 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-MECH | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 0 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2015-11-14 | 2016-12-24 | 140 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-MECH | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 0 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2015-11-14 | 2016-12-24 | 150 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-ROPE | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 8 | 8 | Empty | 2024-09-06 | 2024-09-06 | 2023-05-07 | 2023-08-17 | 2015-11-14 | 2016-12-24 | 160 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-MECH | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 0 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2015-11-14 | 2016-12-24 | 170 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
3 | DFF-OIL | WDF | MTN-PIPF | MTN-MECH | 2100023808 | XCV 301332 intern læk DFF prod manifold. | Line for new M. Set. (Can´t be found) |  |  | 0 | 0 | Empty | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2024-09-06 | 2015-11-14 | 2016-12-24 | 180 |  |  | DF /F /10/DFFA-XCV-301332 | Line for new M. Set. (Can´t be found) | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040473 | Replace 32A socketoutlet | Isolate accordingly |  |  | 1 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-01-24 | 2021-06-23 | 10 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040473 | Replace 32A socketoutlet | Isolate accordingly |  |  | 3 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2021-01-24 | 2021-06-23 | 20 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040473 | Replace 32A socketoutlet | Isolate accordingly |  |  | 1 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2021-01-24 | 2021-06-23 | 30 |  |  | DF /G /61 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040473 | Replace 32A socketoutlet | Isolate accordingly |  |  | 0 | 0 | BL-TEAM - parts required | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2021-01-24 | 2021-06-23 | 40 |  |  | DF /G /61 | Isolate accordingly | Unknown
2 | DFF-O32 | WDF | MTN-MECH | PRODTECH | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2024-05-02 | 2024-05-05 | 2023-08-19 | 2023-10-03 | 10 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 4 | 2 | Empty | 2025-01-01 | 2025-01-02 | 2024-05-02 | 2024-05-05 | 2023-08-19 | 2023-10-03 | 20 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | PRODTECH | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2024-05-02 | 2024-05-05 | 2023-08-19 | 2023-10-03 | 30 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2023-08-19 | 2023-10-03 | 40 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2023-08-19 | 2023-10-03 | 50 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2023-08-19 | 2023-10-03 | 60 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2023-08-19 | 2023-10-03 | 70 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2023-08-19 | 2023-10-03 | 80 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2023-08-19 | 2023-10-03 | 90 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100096905 | FF-FCV-290132 on DFF-32 | **************************************** | PCNFAWSC | PCNFAWSC | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2023-08-19 | 2023-10-03 | 100 | PCNFAWSC | PCNFAWSC | DF /F /37/DFFA-FCV-290132 | **************************************** | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087254 | Batteri fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /F /05/DFFA-N-1812-08 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087254 | Batteri fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /F /05/DFFA-N-1812-08 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087254 | Batteri fault on emergency light | Isolate and prove dead. |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /F /05/DFFA-N-1812-08 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087254 | Batteri fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /F /05/DFFA-N-1812-08 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097346 | DFGA-HRF-3203 Replace hose on reel foam | Replace hose on hosereel | SECE | SECE | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2023-10-21 | 2024-03-04 | 10 | SECE | SECE | DF /G /01/DFGA-HRF-03203 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097346 | DFGA-HRF-3203 Replace hose on reel foam | Replace hose on hosereel | SECE | SECE | 2 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-21 | 2024-03-04 | 20 | SECE | SECE | DF /G /01/DFGA-HRF-03203 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097346 | DFGA-HRF-3203 Replace hose on reel foam | Replace hose on hosereel | SECE | SECE | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-21 | 2024-03-04 | 30 | SECE | SECE | DF /G /01/DFGA-HRF-03203 | Replace hose on hosereel | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-01 | 2025-01-04 | 2021-02-08 | 2021-03-20 | 10 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-04 | 2025-01-05 | 2021-02-08 | 2021-03-20 | 20 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-05 | 2025-01-06 | 2021-02-08 | 2021-03-20 | 30 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-06 | 2025-01-06 | 2021-02-08 | 2021-03-20 | 40 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-06 | 2025-01-07 | 2021-02-08 | 2021-03-20 | 50 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-07 | 2025-01-08 | 2021-02-08 | 2021-03-20 | 60 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-08 | 2025-01-08 | 2021-02-08 | 2021-03-20 | 70 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-08 | 2025-01-10 | 2021-02-08 | 2021-03-20 | 80 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-10 | 2025-01-11 | 2021-02-08 | 2021-03-20 | 90 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2025-01-11 | 2021-02-08 | 2021-03-20 | 100 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-11 | 2025-01-12 | 2021-02-08 | 2021-03-20 | 110 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-12 | 2025-01-13 | 2021-02-08 | 2021-03-20 | 120 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044912 | DFG PCV-570437A Dårlig integritet | added new materials | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2021-02-08 | 2021-03-20 | 130 | AWSC | AWSC | DF /G /70/DFGA-PCV-570437A | added new materials | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235585 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1830-F102 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235585 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 27 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-28 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1830-F102 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235585 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1830-F102 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235585 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-01 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1830-F102 | DE-ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-08-01 | 2021-02-18 | 2021-05-19 | 10 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-02 | 2021-02-18 | 2021-05-19 | 20 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-02 | 2021-02-18 | 2021-05-19 | 30 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-03 | 2021-02-18 | 2021-05-19 | 40 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-04 | 2021-02-18 | 2021-05-19 | 50 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-04 | 2021-02-18 | 2021-05-19 | 60 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-05 | 2021-02-18 | 2021-05-19 | 70 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-05 | 2024-08-07 | 2021-02-18 | 2021-05-19 | 80 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-07 | 2021-02-18 | 2021-05-19 | 90 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-08 | 2021-02-18 | 2021-05-19 | 100 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2021-02-18 | 2021-05-19 | 110 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044914 | DFG PCV-570063 Dårlig integritet | Isolate pneumatic and controls |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-10 | 2021-02-18 | 2021-05-19 | 120 |  |  | DF /G /70/DFGA-PCV-570063 | Isolate pneumatic and controls | Unknown
4 | DFC-FUEL | WGN | MTN-MECH | MTN-MECH | 2200003051 | SMAT:DFCI-HCV-57120-U kan ikke opereres/ | HCV kan ikke opereres/defekt HCV | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2017-06-27 | 2017-11-24 | 10 | AWSC | AWSC | DF /C /70/DFCI-HCV-57120-U | HCV kan ikke opereres/defekt HCV | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-ELEC | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 4 | 2 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 10 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-SCAF | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 16 | 20 | Empty | 2024-07-17 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2023-04-14 | 2023-08-27 | 15 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-RIGG | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 8 | 5 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 16 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-MECH | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 48 | 0 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 17 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-RIGG | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 15 | 15 | Empty | 2024-07-17 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2023-04-14 | 2023-08-27 | 20 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-MECH | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 50 | 69 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-19 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 30 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-MECH | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 36 | 57 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-22 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 40 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-MECH | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 50 | 81 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-22 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 50 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | PRODTECH | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 4 | 0 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-22 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 60 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 2 | 3 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-22 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 70 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-RIGG | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 8 | 4 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-22 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 75 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-SCAF | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 16 | 16 | Empty | 2024-07-17 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2023-04-14 | 2023-08-27 | 76 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | VEN-MECH | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 0 | 0 | Empty | 2024-07-17 | 2024-08-11 | 2024-02-08 | 2024-02-08 | 2023-04-14 | 2023-08-27 | 80 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 25 | 25 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 90 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 0 | 0 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 100 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 30 | 30 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 110 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100086357 | 3590 Mech.Seal Leak WIP DE and NDE | Rectrify oil leaks |  |  | 40 | 40 | Empty | 2024-07-17 | 2024-08-11 | 2024-07-17 | 2024-08-07 | 2023-04-14 | 2023-08-27 | 120 |  |  | DF /G /54/DFGA-P-3590 | Rectrify oil leaks | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-ACCO | 2100041322 | Broken floor - trip hazard | Broken floor - trip hazard |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2020-12-01 | 2021-01-10 | 10 |  |  | DF /C /82 | Broken floor - trip hazard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100041322 | Broken floor - trip hazard | Broken floor - trip hazard |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2020-12-01 | 2021-01-10 | 20 |  |  | DF /C /82 | Broken floor - trip hazard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100041322 | Broken floor - trip hazard | Broken floor - trip hazard |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2020-12-01 | 2021-01-10 | 30 |  |  | DF /C /82 | Broken floor - trip hazard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100041322 | Broken floor - trip hazard | Broken floor - trip hazard |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2020-12-01 | 2021-01-10 | 40 |  |  | DF /C /82 | Broken floor - trip hazard | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-04-17 | 2021-07-16 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 70 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-06 | 2021-04-17 | 2021-07-16 | 80 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 90 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 100 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047712 | DFF HCV-030119 Intern leaking | Prepare freezing kit on site | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-04-17 | 2021-07-16 | 110 | AWSC | AWSC | DF /F /01/DFFA-HCV-030119 | Prepare freezing kit on site | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025023 | LCV 340031 does not open correctly | De-isolate & test function | PCNF | PCNF | 53 | 53 | W31-W32 | 2024-07-29 | 2024-08-01 | 2018-09-01 | 2019-11-14 | 2018-09-01 | 2018-09-03 | 10 | PCNF | PCNF | DF /F /27/DFFA-LCV-340031 | De-isolate & test function | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025023 | LCV 340031 does not open correctly | De-isolate & test function | PCNF | PCNF | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2018-09-01 | 2018-09-03 | 15 | PCNF | PCNF | DF /F /27/DFFA-LCV-340031 | De-isolate & test function | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025023 | LCV 340031 does not open correctly | De-isolate & test function | PCNF | PCNF | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2018-09-01 | 2018-09-03 | 20 | PCNF | PCNF | DF /F /27/DFFA-LCV-340031 | De-isolate & test function | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025023 | LCV 340031 does not open correctly | De-isolate & test function | PCNF | PCNF | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2018-09-01 | 2018-09-03 | 40 | PCNF | PCNF | DF /F /27/DFFA-LCV-340031 | De-isolate & test function | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025023 | LCV 340031 does not open correctly | De-isolate & test function | PCNF | PCNF | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2018-09-01 | 2018-09-03 | 50 | PCNF | PCNF | DF /F /27/DFFA-LCV-340031 | De-isolate & test function | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100078393 | ZSC not working - DFC-BDV-34045. | Deisolate and repeal inhibits Blow Down |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-02 | 2023-05-17 | 5 |  |  | DF /C /11/DFCI-BDV-34045 | Deisolate and repeal inhibits Blow Down | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100078393 | ZSC not working - DFC-BDV-34045. | Deisolate and repeal inhibits Blow Down |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-02 | 2023-05-17 | 10 |  |  | DF /C /11/DFCI-BDV-34045 | Deisolate and repeal inhibits Blow Down | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100078393 | ZSC not working - DFC-BDV-34045. | Deisolate and repeal inhibits Blow Down |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-02 | 2023-05-17 | 30 |  |  | DF /C /11/DFCI-BDV-34045 | Deisolate and repeal inhibits Blow Down | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100078393 | ZSC not working - DFC-BDV-34045. | Deisolate and repeal inhibits Blow Down |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-02 | 2023-05-17 | 35 |  |  | DF /C /11/DFCI-BDV-34045 | Deisolate and repeal inhibits Blow Down | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100078393 | ZSC not working - DFC-BDV-34045. | Deisolate and repeal inhibits Blow Down |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-02 | 2023-05-17 | 40 |  |  | DF /C /11/DFCI-BDV-34045 | Deisolate and repeal inhibits Blow Down | Unknown
4 | DFC-5037 | WGN | UNKNOWN | WELLSUPV | 2200003238 | CMAT:DFCM-V-5037 PVI Contingency valves | Recieve materials |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2019-04-14 | 2021-04-03 | 10 |  |  | DF /C /27/DFCM-V-5037 | Recieve materials | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200003176 | SMAT:Flow indikator def-Finding PPM-che | Flow indikator def. - Finding PPM-check |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2016-08-22 | 2016-11-20 | 10 |  |  | DF /F /70/DFFA-BDV-570228 | Flow indikator def. - Finding PPM-check | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085423 | Replace cable on circuit 33 1852 DFGA | Replace cable |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-15 | 2023-04-01 | 2023-08-14 | 10 |  |  | DF /G /62/EMERGENCY-LIGHTING-L3 | Replace cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085423 | Replace cable on circuit 33 1852 DFGA | Replace cable |  |  | 44 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-26 | 2023-04-01 | 2023-08-14 | 20 |  |  | DF /G /62/EMERGENCY-LIGHTING-L3 | Replace cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085423 | Replace cable on circuit 33 1852 DFGA | Replace cable |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-04-01 | 2023-08-14 | 30 |  |  | DF /G /62/EMERGENCY-LIGHTING-L3 | Replace cable | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-15 | 2022-03-28 | 2022-11-23 | 10 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-03-28 | 2022-11-23 | 20 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-17 | 2022-03-28 | 2022-11-23 | 30 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-17 | 2022-03-28 | 2022-11-23 | 40 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-18 | 2022-03-28 | 2022-11-23 | 50 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-03-28 | 2022-11-23 | 60 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2022-03-28 | 2022-11-23 | 70 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ELEC | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2022-03-28 | 2022-11-23 | 80 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-LAGG | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2022-03-28 | 2022-11-23 | 90 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008932 | Recertify DFFA-PSV-530134 DUE 09/03/2022 | Lagger |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2022-03-28 | 2022-11-23 | 100 |  |  | DF /F /76/DFFA-PSV-530134 | Lagger | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088896 | DFC High DP over Seawater Filter | Rigger Assistance |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2023-05-17 | 2023-09-29 | 10 |  |  | DF /C /51/DFCM-FT-5221 | Rigger Assistance | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088896 | DFC High DP over Seawater Filter | Rigger Assistance |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-24 | 2023-05-17 | 2023-09-29 | 20 |  |  | DF /C /51/DFCM-FT-5221 | Rigger Assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088896 | DFC High DP over Seawater Filter | Rigger Assistance |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-24 | 2024-09-25 | 2023-05-17 | 2023-09-29 | 30 |  |  | DF /C /51/DFCM-FT-5221 | Rigger Assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100088896 | DFC High DP over Seawater Filter | Rigger Assistance |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-25 | 2024-09-26 | 2023-05-17 | 2023-09-29 | 40 |  |  | DF /C /51/DFCM-FT-5221 | Rigger Assistance | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088896 | DFC High DP over Seawater Filter | Rigger Assistance |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2023-05-17 | 2023-09-29 | 50 |  |  | DF /C /51/DFCM-FT-5221 | Rigger Assistance | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088896 | DFC High DP over Seawater Filter | Rigger Assistance |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-05-17 | 2023-09-29 | 60 |  |  | DF /C /51/DFCM-FT-5221 | Rigger Assistance | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2021-01-01 | 2021-04-01 | 10 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-03 | 2021-01-01 | 2021-04-01 | 20 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-01-01 | 2021-04-01 | 30 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-01-01 | 2021-04-01 | 40 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-01-01 | 2021-04-01 | 50 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2021-01-01 | 2021-04-01 | 60 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-ROPE | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2021-01-01 | 2021-04-01 | 70 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-08 | 2021-01-01 | 2021-04-01 | 80 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042480 | ESD Afspæringsventil DFF-LIT-340102 | Scaffold Work PF erection | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2021-01-01 | 2021-04-01 | 90 | AWSC | AWSC | DF /F /20/DFFA-LIT-340102 | Scaffold Work PF erection | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044254 | DFCM-XCV-50367 SIDDER FAST | Vendor to Troubleshoot on XCV-50367 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-04 | 2022-04-30 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50367 | Vendor to Troubleshoot on XCV-50367 | Unknown
4 | DFC-5037 | WDF | MTN-MECH | MTN-MECH | 2100044254 | DFCM-XCV-50367 SIDDER FAST | Vendor to Troubleshoot on XCV-50367 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-04 | 2022-04-30 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50367 | Vendor to Troubleshoot on XCV-50367 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100114623 | DFA DELUGE SKID - PSH DEVIATION | Inhibit pressure switches |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-06-17 | 2024-08-01 | 10 |  |  | DF /A /01/DELUGE-SKIDS | Inhibit pressure switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100114623 | DFA DELUGE SKID - PSH DEVIATION | Inhibit pressure switches |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-06-17 | 2024-08-01 | 20 |  |  | DF /A /01/DELUGE-SKIDS | Inhibit pressure switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100114623 | DFA DELUGE SKID - PSH DEVIATION | Inhibit pressure switches |  |  | 2.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-06-17 | 2024-08-01 | 30 |  |  | DF /A /01/DELUGE-SKIDS | Inhibit pressure switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100114623 | DFA DELUGE SKID - PSH DEVIATION | Inhibit pressure switches |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-06-17 | 2024-08-01 | 40 |  |  | DF /A /01/DELUGE-SKIDS | Inhibit pressure switches | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325733 | 1Y CHEMICAL TANK SKID, A-39850 | 1Y CHEMICAL TANK SKID, A-39850 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /A /75/DFAA-A-39850 | 1Y CHEMICAL TANK SKID, A-39850 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235670 | 4Y 380V N-SWB MAINT-DFCI-N-1821-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1821-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235670 | 4Y 380V N-SWB MAINT-DFCI-N-1821-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1821-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235670 | 4Y 380V N-SWB MAINT-DFCI-N-1821-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1821-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235670 | 4Y 380V N-SWB MAINT-DFCI-N-1821-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1821-1A01 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 2 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | 2022-05-29 | 2022-10-26 | 9 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 2 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | 2022-05-29 | 2022-10-26 | 10 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 1 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 20 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 30 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 40 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 50 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 60 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 61 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 1 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | 2022-05-29 | 2022-10-26 | 70 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2022-05-29 | 2022-10-26 | 80 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 2 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | 2022-05-29 | 2022-10-26 | 90 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100064726 | PCV-530541 rust på aktuator,utæt extern. | Isolate PCV-530541 |  |  | 3 | 0 | Empty | 2024-08-29 | 2024-08-30 | 2024-08-29 | 2024-08-29 | 2022-05-29 | 2022-10-26 | 100 |  |  | DF /G /51/DFGA-PCV-530541 | Isolate PCV-530541 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322267 | DFC-01-WF-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 221 | 0 | Empty | 2024-10-30 | 2024-11-29 | 2024-10-30 | 2024-11-28 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235837 | 4Y 400V E-DP MAINT DFGA-LP-1852 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-LP-1852 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235837 | 4Y 400V E-DP MAINT DFGA-LP-1852 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 14 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 20 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-LP-1852 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235837 | 4Y 400V E-DP MAINT DFGA-LP-1852 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 30 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-LP-1852 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235837 | 4Y 400V E-DP MAINT DFGA-LP-1852 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 40 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-LP-1852 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100052236 | Replace SOV for Gally fan 1205-B | De-Isolate above |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2021-07-19 | 2021-08-28 | 10 |  |  | DF /C /09/DFCC-M-12052 | De-Isolate above | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100052236 | Replace SOV for Gally fan 1205-B | De-Isolate above |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2021-07-19 | 2021-08-28 | 20 |  |  | DF /C /09/DFCC-M-12052 | De-Isolate above | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100052236 | Replace SOV for Gally fan 1205-B | De-Isolate above |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2021-07-19 | 2021-08-28 | 30 |  |  | DF /C /09/DFCC-M-12052 | De-Isolate above | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044252 | div. fejl på DFCM-XCV-50353 | Vendor to Troubleshoot on XCV-50353 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-03 | 2021-07-04 | 2022-04-30 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50353 | Vendor to Troubleshoot on XCV-50353 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044252 | div. fejl på DFCM-XCV-50353 | Vendor to Troubleshoot on XCV-50353 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2021-07-04 | 2022-04-30 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50353 | Vendor to Troubleshoot on XCV-50353 | Unknown
4 | NOSD | WGN | MTN-INST | PRODTECH | 2200003212 | CMAT:DFF Replace 2 pcs. pressure gauge E | Hydraulic isolation ESDV-441330 | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2018-04-27 | 2019-04-22 | 10 | SCH | SCH | DF /F /31/DFFA-ESDV-441330 | Hydraulic isolation ESDV-441330 | Unknown
4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003212 | CMAT:DFF Replace 2 pcs. pressure gauge E | Hydraulic isolation ESDV-441330 | SCH | SCH | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2018-04-27 | 2019-04-22 | 20 | SCH | SCH | DF /F /31/DFFA-ESDV-441330 | Hydraulic isolation ESDV-441330 | Unknown
4 | NOSD | WGN | MTN-INST | PRODTECH | 2200003212 | CMAT:DFF Replace 2 pcs. pressure gauge E | Hydraulic isolation ESDV-441330 | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2018-04-27 | 2019-04-22 | 30 | SCH | SCH | DF /F /31/DFFA-ESDV-441330 | Hydraulic isolation ESDV-441330 | Unknown
4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003212 | CMAT:DFF Replace 2 pcs. pressure gauge E | Hydraulic isolation ESDV-441330 | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2018-04-27 | 2019-04-22 | 40 | SCH | SCH | DF /F /31/DFFA-ESDV-441330 | Hydraulic isolation ESDV-441330 | Unknown
4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003212 | CMAT:DFF Replace 2 pcs. pressure gauge E | Hydraulic isolation ESDV-441330 | SCH | SCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2018-04-27 | 2019-04-22 | 50 | SCH | SCH | DF /F /31/DFFA-ESDV-441330 | Hydraulic isolation ESDV-441330 | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2020-09-08 | 2020-09-08 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2020-09-07 | 2020-09-07 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 36 | 25.5 | Empty | 2020-08-23 | 2024-01-13 | 2020-08-21 | 2020-09-08 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 4 | 19.5 | Empty | 2020-08-23 | 2024-01-13 | 2020-08-26 | 2020-09-04 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 6 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 4 | 4 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-09 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 22 | 14 | Empty | 2020-08-23 | 2024-01-13 | 2022-04-07 | 2022-04-07 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 36 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-13 | 2019-09-12 | 2019-12-11 | 90 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 12 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-10 | 2019-09-12 | 2019-12-11 | 100 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 32 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-10 | 2019-09-12 | 2019-12-11 | 110 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 16 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-10 | 2019-09-12 | 2019-12-11 | 120 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002915 | DFF-Insulation assists FORCE 15971 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2020-08-23 | 2024-01-13 | 2024-01-09 | 2024-01-11 | 2019-09-12 | 2019-12-11 | 130 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7041-GF-U | BUILD SCAFFOLDING | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400337678 | 1Y DFFA-FT-340508 PROD WATER - METERING | DFFA-FT-340508 PROD WATER - METERING |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-07-06 | 2024-08-22 | 10 |  |  | DF /F /27/DFFA-FT-340508 | DFFA-FT-340508 PROD WATER - METERING | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-26 | 2023-12-18 | 2024-05-01 | 10 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-27 | 2023-12-18 | 2024-05-01 | 20 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-27 | 2024-08-28 | 2023-12-18 | 2024-05-01 | 30 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-28 | 2024-08-28 | 2023-12-18 | 2024-05-01 | 40 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-28 | 2024-08-29 | 2023-12-18 | 2024-05-01 | 50 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-29 | 2024-08-29 | 2023-12-18 | 2024-05-01 | 60 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-29 | 2024-08-30 | 2023-12-18 | 2024-05-01 | 70 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101420 | DFF-C-5401,Oil spild under the cooler | Isolate Cooler |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-30 | 2024-08-31 | 2023-12-18 | 2024-05-01 | 80 |  |  | DF /F /07/DFFA-C-5401 | Isolate Cooler | Unknown
4 | NE | WDF | MTN-INST | WELLSUPV | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-09-02 | 2024-07-26 | 2024-07-26 | 2021-12-13 | 2022-05-12 | 10 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-INST | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-09-02 | 2024-07-26 | 2024-07-26 | 2021-12-13 | 2022-05-12 | 20 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 36 | 55 | Empty | 2024-07-26 | 2024-09-02 | 2024-07-26 | 2024-07-30 | 2021-12-13 | 2022-05-12 | 30 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-ROPE | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 36 | 0 | Empty | 2024-07-26 | 2024-09-02 | 2024-07-30 | 2024-08-02 | 2021-12-13 | 2022-05-12 | 40 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-PIPF | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 416 | 93 | Empty | 2024-07-26 | 2024-09-02 | 2024-08-02 | 2024-08-24 | 2021-12-13 | 2022-05-12 | 50 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | PRODTECH | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-09-02 | 2024-08-24 | 2024-08-24 | 2021-12-13 | 2022-05-12 | 60 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-PIPF | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 64 | 0 | Empty | 2024-07-26 | 2024-09-02 | 2024-08-24 | 2024-08-31 | 2021-12-13 | 2022-05-12 | 70 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055840 | DGSPR: Utility & Instrument Air Batch-02 | Instrument air spools SCFM 8V corrosion | PCNF | PCNF | 18 | 5 | Empty | 2024-07-26 | 2024-09-02 | 2024-08-31 | 2024-09-02 | 2021-12-13 | 2022-05-12 | 80 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0806-A1-U | Instrument air spools SCFM 8V corrosion | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000753 | HLO/KONTORARTIKLER 01.01.19 TIL 31.12.19 | HLO 21.03.20 |  |  | 0 | 0 | Empty | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /C | HLO 21.03.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000753 | HLO/KONTORARTIKLER 01.01.19 TIL 31.12.19 | HLO 21.03.20 |  |  | 0 | 0 | Empty | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF /C | HLO 21.03.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000753 | HLO/KONTORARTIKLER 01.01.19 TIL 31.12.19 | HLO 21.03.20 |  |  | 0 | 0 | Empty | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2019-12-31 | 2019-12-31 | 30 |  |  | DF /C | HLO 21.03.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000753 | HLO/KONTORARTIKLER 01.01.19 TIL 31.12.19 | HLO 21.03.20 |  |  | 0 | 0 | Empty | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2019-12-31 | 2019-12-31 | 40 |  |  | DF /C | HLO 21.03.20 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235830 | 4Y 380V E-SWB MAINT DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | SCHSECE | SCHSECE | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCHSECE | SCHSECE | DF /F /05/DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235830 | 4Y 380V E-SWB MAINT DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | SCHSECE | SCHSECE | 8 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCHSECE | SCHSECE | DF /F /05/DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235830 | 4Y 380V E-SWB MAINT DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | SCHSECE | SCHSECE | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 | SCHSECE | SCHSECE | DF /F /05/DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235830 | 4Y 380V E-SWB MAINT DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | SCHSECE | SCHSECE | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 40 | SCHSECE | SCHSECE | DF /F /05/DFFA-N-1813 | 380V E-SWB MAINT DFFA-N-1813 | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100111334 | DFC-R-19020 Status lamp not funcional | Isolate & replace lamp DFC-R-19020 |  |  | 4 | 6 | Empty | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-10-20 | 10 |  |  | DF /C /03/DFCC-R-19020 | Isolate & replace lamp DFC-R-19020 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284298 | PSV Exchange - DFGA-PSV-590427 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /07/DFGA-PSV-590427 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284298 | PSV Exchange - DFGA-PSV-590427 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /07/DFGA-PSV-590427 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284298 | PSV Exchange - DFGA-PSV-590427 | Prod Assist (breaking containment) | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-13 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /07/DFGA-PSV-590427 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284298 | PSV Exchange - DFGA-PSV-590427 | Prod Assist (breaking containment) | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /07/DFGA-PSV-590427 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284298 | PSV Exchange - DFGA-PSV-590427 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /07/DFGA-PSV-590427 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284298 | PSV Exchange - DFGA-PSV-590427 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /07/DFGA-PSV-590427 | Prod Assist (breaking containment) | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 3 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-25 | 2024-08-25 | 2023-04-07 | 2023-08-20 | 10 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-25 | 2024-08-26 | 2023-04-07 | 2023-08-20 | 20 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-RIGG | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 6 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-26 | 2024-08-27 | 2023-04-07 | 2023-08-20 | 30 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-27 | 2024-08-28 | 2023-04-07 | 2023-08-20 | 40 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 4 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-28 | 2024-08-29 | 2023-04-07 | 2023-08-20 | 50 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-RIGG | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 6 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-29 | 2024-08-30 | 2023-04-07 | 2023-08-20 | 60 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 4 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-30 | 2024-08-31 | 2023-04-07 | 2023-08-20 | 70 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-08-31 | 2024-09-01 | 2023-04-07 | 2023-08-20 | 80 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2023-04-07 | 2023-08-20 | 90 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-09-01 | 2024-09-01 | 2023-04-07 | 2023-08-20 | 100 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100086065 | DFE-06 manifold HCV-30601 stuck open. | Isolate HCV/XCV-30601 |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-02 | 2024-09-01 | 2024-09-02 | 2023-04-07 | 2023-08-20 | 110 |  |  | DF /E /10/DFEZ-HCV-30601 | Isolate HCV/XCV-30601 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050871 | Door lock at WI launcer EP-3807 | Demount locking device |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2021-08-29 | 2022-01-26 | 10 |  |  | DF /F /54/DFFA-EP-3807 | Demount locking device | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050871 | Door lock at WI launcer EP-3807 | Demount locking device |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2021-08-29 | 2022-01-26 | 20 |  |  | DF /F /54/DFFA-EP-3807 | Demount locking device | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050871 | Door lock at WI launcer EP-3807 | Demount locking device |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2021-08-29 | 2022-01-26 | 30 |  |  | DF /F /54/DFFA-EP-3807 | Demount locking device | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050871 | Door lock at WI launcer EP-3807 | Demount locking device |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2021-08-29 | 2022-01-26 | 40 |  |  | DF /F /54/DFFA-EP-3807 | Demount locking device | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100087755 | FLMR DFB - Replace Handrail EL. 34.000 | DFB - Replace Handrail EL. 34.000 |  |  | 0 | 0 | Empty | 2023-09-12 | 2023-09-20 | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2025-12-31 | 10 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replace Handrail EL. 34.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100087755 | FLMR DFB - Replace Handrail EL. 34.000 | DFB - Replace Handrail EL. 34.000 |  |  | 4 | 0 | Empty | 2023-09-12 | 2023-09-20 | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2025-12-31 | 20 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replace Handrail EL. 34.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100087755 | FLMR DFB - Replace Handrail EL. 34.000 | DFB - Replace Handrail EL. 34.000 |  |  | 2 | 0 | Empty | 2023-09-12 | 2023-09-20 | 2023-09-13 | 2023-09-13 | 2023-09-12 | 2025-12-31 | 30 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replace Handrail EL. 34.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100087755 | FLMR DFB - Replace Handrail EL. 34.000 | DFB - Replace Handrail EL. 34.000 |  |  | 1 | 0 | Empty | 2023-09-12 | 2023-09-20 | 2023-09-13 | 2023-09-14 | 2023-09-12 | 2025-12-31 | 40 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replace Handrail EL. 34.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100087755 | FLMR DFB - Replace Handrail EL. 34.000 | DFB - Replace Handrail EL. 34.000 |  |  | 50 | 0 | Empty | 2023-09-12 | 2023-09-20 | 2023-09-14 | 2023-09-20 | 2023-09-12 | 2025-12-31 | 50 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replace Handrail EL. 34.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100087755 | FLMR DFB - Replace Handrail EL. 34.000 | DFB - Replace Handrail EL. 34.000 |  |  | 2 | 0 | Empty | 2023-09-12 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-12 | 2025-12-31 | 60 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replace Handrail EL. 34.000 | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400268063 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-07-22 | 2023-08-01 | 10 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400268063 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-07-22 | 2023-08-01 | 20 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400268063 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-07-22 | 2023-08-01 | 30 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322299 | DFG-28-DOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 54 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
D | NOSD | WPM | PRODLABO | PRODLABO | 2400281410 | 3M SAMPLING OF OiW CORRELATIONS | TL-3M SAMPLING OF OIW CORRELATIONS |  |  | 6 | 0 | Empty | 2023-10-01 | 2023-10-02 | 2023-10-01 | 2023-10-02 | 2023-09-30 | 2023-10-15 | 10 |  |  | DF /F /27/DFFA-A-5064 | TL-3M SAMPLING OF OIW CORRELATIONS | Unknown
4 | DFB-W05 | WDF | MTN-MECH | MTN-RIGG | 2100053942 | Change Check valve DFB-05 | Prepare matr/tools | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2021-11-10 | 2022-04-09 | 10 | AWSC | AWSC | DF /B /55/DFB05-WATER-INJECTION-LINE | Prepare matr/tools | Unknown
4 | DFB-W05 | WDF | MTN-MECH | MTN-MECH | 2100053942 | Change Check valve DFB-05 | Prepare matr/tools | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2021-11-10 | 2022-04-09 | 20 | AWSC | AWSC | DF /B /55/DFB05-WATER-INJECTION-LINE | Prepare matr/tools | Unknown
4 | DFB-W05 | WDF | MTN-MECH | PRODTECH | 2100053942 | Change Check valve DFB-05 | Prepare matr/tools | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2021-11-10 | 2022-04-09 | 30 | AWSC | AWSC | DF /B /55/DFB05-WATER-INJECTION-LINE | Prepare matr/tools | Unknown
4 | DFB-W05 | WDF | MTN-MECH | MTN-MECH | 2100053942 | Change Check valve DFB-05 | Prepare matr/tools | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-03 | 2021-11-10 | 2022-04-09 | 40 | AWSC | AWSC | DF /B /55/DFB05-WATER-INJECTION-LINE | Prepare matr/tools | Unknown
4 | DFB-W05 | WDF | MTN-MECH | PRODTECH | 2100053942 | Change Check valve DFB-05 | Prepare matr/tools | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2021-11-10 | 2022-04-09 | 50 | AWSC | AWSC | DF /B /55/DFB05-WATER-INJECTION-LINE | Prepare matr/tools | Unknown
4 | DFB-W05 | WDF | MTN-MECH | MTN-MECH | 2100053942 | Change Check valve DFB-05 | Prepare matr/tools | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2021-11-10 | 2022-04-09 | 60 | AWSC | AWSC | DF /B /55/DFB05-WATER-INJECTION-LINE | Prepare matr/tools | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040943 | Cable tray to be re-attached . DFF lvl 2 | Reestablish bonding |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-03-03 | 2021-10-29 | 10 |  |  | DF /F /61 | Reestablish bonding | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100040943 | Cable tray to be re-attached . DFF lvl 2 | Reestablish bonding |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-03-03 | 2021-10-29 | 20 |  |  | DF /F /61 | Reestablish bonding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 40 | 40 | Semco | 2024-08-26 | 2024-09-12 | 2017-10-09 | 2021-01-29 | 2016-05-20 | 2016-06-09 | 10 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 78.40000000000000568434188606 | 0 | Semco | 2024-08-26 | 2024-09-12 | 2024-08-26 | 2024-09-01 | 2016-05-20 | 2016-06-09 | 20 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 2 | 0 | Semco | 2024-08-26 | 2024-09-12 | 2024-09-01 | 2024-09-02 | 2016-05-20 | 2016-06-09 | 30 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 48 | 0 | Semco | 2024-08-26 | 2024-09-12 | 2024-09-02 | 2024-09-08 | 2016-05-20 | 2016-06-09 | 40 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 2 | 0 | Semco | 2024-08-26 | 2024-09-12 | 2024-09-08 | 2024-09-08 | 2016-05-20 | 2016-06-09 | 50 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 52.29999999999999715782905694 | 0 | Semco | 2024-08-26 | 2024-09-12 | 2024-09-08 | 2024-09-12 | 2016-05-20 | 2016-06-09 | 60 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027364 | Replacement of cable from 1854 to JB | L3 Previous work | PCNF | PCNF | 0 | 0 | Semco | 2024-08-26 | 2024-09-12 | 2024-08-26 | 2024-08-26 | 2016-05-20 | 2016-06-09 | 70 | PCNF | PCNF | DF /G /61/DFGA-DP-1854-53 | L3 Previous work | Unknown
3 | DFC-FUEL | WDF | MTN-INST | PRODTECH | 2100087407 | Replace SDBB valve and piping PT-57132 | Isolate Pressure transmitter |  |  | 1 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 10 |  |  | DF /C /70/DFCI-PT-57132 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100087407 | Replace SDBB valve and piping PT-57132 | Isolate Pressure transmitter |  |  | 0.5 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 20 |  |  | DF /C /70/DFCI-PT-57132 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-MECH | 2100087407 | Replace SDBB valve and piping PT-57132 | Isolate Pressure transmitter |  |  | 0.1000000000000000055511151231 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 30 |  |  | DF /C /70/DFCI-PT-57132 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-PIPF | 2100087407 | Replace SDBB valve and piping PT-57132 | Isolate Pressure transmitter |  |  | 6 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 40 |  |  | DF /C /70/DFCI-PT-57132 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100087407 | Replace SDBB valve and piping PT-57132 | Isolate Pressure transmitter |  |  | 1 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 50 |  |  | DF /C /70/DFCI-PT-57132 | Isolate Pressure transmitter | Unknown
3 | DFC-FUEL | WDF | MTN-INST | PRODTECH | 2100087407 | Replace SDBB valve and piping PT-57132 | Isolate Pressure transmitter |  |  | 1 | 0 | Empty | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-03 | 2023-12-18 | 60 |  |  | DF /C /70/DFCI-PT-57132 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073124 | DFGTT-53020 Overrange på G-1640 | Troubleshoot Temperature transmitter(wit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-09-26 | 2023-02-08 | 10 |  |  | DF /G /76/DFGA-TIT-530020 | Troubleshoot Temperature transmitter(wit | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073124 | DFGTT-53020 Overrange på G-1640 | Troubleshoot Temperature transmitter(wit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-09-26 | 2023-02-08 | 20 |  |  | DF /G /76/DFGA-TIT-530020 | Troubleshoot Temperature transmitter(wit | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073124 | DFGTT-53020 Overrange på G-1640 | Troubleshoot Temperature transmitter(wit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-09-26 | 2023-02-08 | 30 |  |  | DF /G /76/DFGA-TIT-530020 | Troubleshoot Temperature transmitter(wit | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100073124 | DFGTT-53020 Overrange på G-1640 | Troubleshoot Temperature transmitter(wit |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-09-26 | 2023-02-08 | 40 |  |  | DF /G /76/DFGA-TIT-530020 | Troubleshoot Temperature transmitter(wit | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077158 | FLMR DFA - Replace Handrail ST004 EL. 22 | DFA - Replace Handrail ST004 EL. 22.000 |  |  | 0 | 0 | Empty | 2023-04-29 | 2023-05-07 | 2023-04-29 | 2023-04-29 | 2023-04-29 | 2023-12-31 | 10 |  |  | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST004 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077158 | FLMR DFA - Replace Handrail ST004 EL. 22 | DFA - Replace Handrail ST004 EL. 22.000 |  |  | 3 | 0 | Empty | 2023-04-29 | 2023-05-07 | 2023-04-29 | 2023-04-30 | 2023-04-29 | 2023-12-31 | 20 |  |  | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST004 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077158 | FLMR DFA - Replace Handrail ST004 EL. 22 | DFA - Replace Handrail ST004 EL. 22.000 |  |  | 1 | 0 | Empty | 2023-04-29 | 2023-05-07 | 2023-04-30 | 2023-04-30 | 2023-04-29 | 2023-12-31 | 30 |  |  | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST004 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077158 | FLMR DFA - Replace Handrail ST004 EL. 22 | DFA - Replace Handrail ST004 EL. 22.000 |  |  | 50 | 0 | Empty | 2023-04-29 | 2023-05-07 | 2023-04-30 | 2023-05-06 | 2023-04-29 | 2023-12-31 | 40 |  |  | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST004 EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077158 | FLMR DFA - Replace Handrail ST004 EL. 22 | DFA - Replace Handrail ST004 EL. 22.000 |  |  | 2 | 0 | Empty | 2023-04-29 | 2023-05-07 | 2023-05-06 | 2023-05-07 | 2023-04-29 | 2023-12-31 | 50 |  |  | DF /A /86/22000 - HANDRAILS | DFA - Replace Handrail ST004 EL. 22.000 | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044422 | Intern lækage på ventil XCV-380202 | Material |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2021-05-11 | 10 |  |  | DF /F /23/DFFA-XCV-380202 | Material | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044422 | Intern lækage på ventil XCV-380202 | Material |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2021-05-11 | 20 |  |  | DF /F /23/DFFA-XCV-380202 | Material | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044422 | Intern lækage på ventil XCV-380202 | Material |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2021-05-11 | 30 |  |  | DF /F /23/DFFA-XCV-380202 | Material | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044422 | Intern lækage på ventil XCV-380202 | Material |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2021-05-11 | 40 |  |  | DF /F /23/DFFA-XCV-380202 | Material | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044422 | Intern lækage på ventil XCV-380202 | Material |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2021-05-11 | 50 |  |  | DF /F /23/DFFA-XCV-380202 | Material | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044422 | Intern lækage på ventil XCV-380202 | Material |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-02-10 | 2021-05-11 | 60 |  |  | DF /F /23/DFFA-XCV-380202 | Material | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235572 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235572 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 20 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235572 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-28 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235572 | 4Y 380V UPS-DP-MAINT-DFBA-DP-1834-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-DP-1834-A01 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400306659 | 6M FIELD PANEL LIFTGAS CONT MAINT | ISOALTION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-02-03 | 2024-02-19 | 10 |  |  | DF /F /07/DFFA-FP-5915 | ISOALTION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400306659 | 6M FIELD PANEL LIFTGAS CONT MAINT | ISOALTION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-02-03 | 2024-02-19 | 20 |  |  | DF /F /07/DFFA-FP-5915 | ISOALTION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400306659 | 6M FIELD PANEL LIFTGAS CONT MAINT | ISOALTION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-02-03 | 2024-02-19 | 30 |  |  | DF /F /07/DFFA-FP-5915 | ISOALTION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400344073 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-14 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 29 | 0 | Empty | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-07-22 | 2024-07-21 | 2024-09-21 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-14 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400244398 | 1Y FLARE SYSTEM MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 1.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-12 | 2023-04-11 | 2023-05-11 | 10 | SECE | SECE | DF /F /36/FLARE-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400244398 | 1Y FLARE SYSTEM MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2023-04-11 | 2023-05-11 | 20 | SECE | SECE | DF /F /36/FLARE-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400244398 | 1Y FLARE SYSTEM MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 1.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2023-04-11 | 2023-05-11 | 30 | SECE | SECE | DF /F /36/FLARE-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400244398 | 1Y FLARE SYSTEM MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2023-04-11 | 2023-05-11 | 40 | SECE | SECE | DF /F /36/FLARE-SYSTEM | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400244398 | 1Y FLARE SYSTEM MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 1.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2023-04-11 | 2023-05-11 | 50 | SECE | SECE | DF /F /36/FLARE-SYSTEM | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100095416 | DFC/78 Bom hoist DFC crane very slow | Isolate De-isolate crane | SCH | SCH | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2023-09-05 | 2024-01-18 | 10 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-TELE | 2100095416 | DFC/78 Bom hoist DFC crane very slow | Isolate De-isolate crane | SCH | SCH | 5 | 10 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2023-09-05 | 2024-01-18 | 20 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100095416 | DFC/78 Bom hoist DFC crane very slow | Isolate De-isolate crane | SCH | SCH | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2023-09-05 | 2024-01-18 | 30 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate De-isolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100095416 | DFC/78 Bom hoist DFC crane very slow | Isolate De-isolate crane | SCH | SCH | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2023-09-05 | 2024-01-18 | 40 | SCH | SCH | DF /C /78/DFCI-X-6101 | Isolate De-isolate crane | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400344056 | 1Y UHF PORTABLE FIRE RADIOS -DFC | UHF PORTABLE FIRE RADIOS -DFC | SECE | SECE | 2 | 2 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-23 | 2024-09-22 | 10 | SECE | SECE | DF /C /08/EXTERNAL-COMMUNICATION | UHF PORTABLE FIRE RADIOS -DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235569 | 4Y 400V N-DP-MAINT-DFEZ-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-DP-1831 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235569 | 4Y 400V N-DP-MAINT-DFEZ-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-DP-1831 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235569 | 4Y 400V N-DP-MAINT-DFEZ-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /61/DFEZ-DP-1831 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235569 | 4Y 400V N-DP-MAINT-DFEZ-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /61/DFEZ-DP-1831 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100094216 | DFGA-P-5076 VERY HIGH VIB LEVELS ON WHOL | Mechanical Scope |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-08-14 | 2023-12-27 | 10 |  |  | DF /G /28/DFGA-P-5076 | Mechanical Scope | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094216 | DFGA-P-5076 VERY HIGH VIB LEVELS ON WHOL | Mechanical Scope |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-08-14 | 2023-12-27 | 20 |  |  | DF /G /28/DFGA-P-5076 | Mechanical Scope | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100094216 | DFGA-P-5076 VERY HIGH VIB LEVELS ON WHOL | Mechanical Scope |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2023-08-14 | 2023-12-27 | 30 |  |  | DF /G /28/DFGA-P-5076 | Mechanical Scope | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100094216 | DFGA-P-5076 VERY HIGH VIB LEVELS ON WHOL | Mechanical Scope |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-08-14 | 2023-12-27 | 40 |  |  | DF /G /28/DFGA-P-5076 | Mechanical Scope | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400230369 | 6M HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-01-31 | 2023-02-16 | 10 |  |  | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230369 | 6M HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-31 | 2023-02-16 | 20 |  |  | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400230369 | 6M HYD POWER UNIT MAINT - DFCM-A-5901 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-01-31 | 2023-02-16 | 30 |  |  | DF /C /07/DFCM-A-5901 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235559 | 4Y 3KV N-SWB MAINT DFCI-N-1801-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-29 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801-20-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235559 | 4Y 3KV N-SWB MAINT DFCI-N-1801-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 16 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2022-12-31 | 2023-03-29 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801-20-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235559 | 4Y 3KV N-SWB MAINT DFCI-N-1801-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-29 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801-20-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235559 | 4Y 3KV N-SWB MAINT DFCI-N-1801-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2022-12-31 | 2023-03-29 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801-20-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235559 | 4Y 3KV N-SWB MAINT DFCI-N-1801-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 50 | AWSC | AWSC | DF /C /61/DFCI-N-1801-20-01 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400330007 | 6M PORTABLE INSTRUMENTS CALIBR - DFG | PORTABLE INSTRUMENTS CALIBR - DFG |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-06-03 | 2024-06-28 | 10 |  |  | DF /G /84 | PORTABLE INSTRUMENTS CALIBR - DFG | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346571 | 6M DEMULS INJ PUMPS MAINT-DFGA-P-3962/3 | DEMULS INJ PUMPS MAINT-DFGA-P-3962/3 |  |  | 1 | 0 | Empty | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-11 | 2024-09-30 | 10 |  |  | DF /G /75/DFGA-A-3956 | DEMULS INJ PUMPS MAINT-DFGA-P-3962/3 | Unknown
D | NOSD | WPM | MTN-TURB | MTN-TURB | 2400351931 | 1M DFGA-GT-4302 Silencer Thermography | SAFETY INFORMATION |  |  | 0 | 0 | Empty | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-18 | 1 |  |  | DF /G /31/DFGA-GT-4302 | SAFETY INFORMATION | Unknown
D | NOSD | WPM | MTN-TURB | MTN-TURB | 2400351931 | 1M DFGA-GT-4302 Silencer Thermography | SAFETY INFORMATION |  |  | 2 | 0 | Empty | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-10-18 | 10 |  |  | DF /G /31/DFGA-GT-4302 | SAFETY INFORMATION | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009240 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /F /54/DFF-16-WI-035-7003-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009240 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-13 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /F /54/DFF-16-WI-035-7003-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009240 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-14 | 2024-01-15 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /F /54/DFF-16-WI-035-7003-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009240 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-16 | 2022-02-08 | 2022-07-08 | 35 |  |  | DF /F /54/DFF-16-WI-035-7003-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009240 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-16 | 2024-01-20 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /F /54/DFF-16-WI-035-7003-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009240 | Insulation assits FORCE 20654 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-20 | 2024-01-23 | 2022-02-08 | 2022-07-08 | 50 |  |  | DF /F /54/DFF-16-WI-035-7003-AD-U | Bilfinger inspection | Unknown
4 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 4 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 10 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-INST | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 3 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-03 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 20 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 24 | 81 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 21 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 16 | 12 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 22 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 8 | 2 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 23 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 16 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 24 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 12 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-04 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 30 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 8 | 18 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-06 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 40 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 4 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-07 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 50 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 12 | 18 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 51 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 8 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-07 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 60 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 61 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-INST | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 5 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-07 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 70 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-INST | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 3 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-07 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 80 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 3 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-07 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 90 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 16 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 91 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 3 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-07 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 100 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | PRODTECH | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 3 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 101 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 6 | 9 | Empty | 2024-03-15 | 2024-03-15 | 2022-02-02 | 2022-03-03 | 2021-12-19 | 2022-05-18 | 102 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 16 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2021-12-19 | 2022-05-18 | 103 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 16 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2021-12-19 | 2022-05-18 | 104 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-ROPE | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 4 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2021-12-19 | 2022-05-18 | 110 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
4 | DFF-3580 | WDF | MTN-MECH | MTN-MECH | 2100056270 | FCV-357012 is internal leaking. | Line for returning FCV to DAN | AWSC | AWSC | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2021-12-19 | 2022-05-18 | 120 | AWSC | AWSC | DF /F /54/DFFB-FCV-357012 | Line for returning FCV to DAN | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100076707 | DFA open drain pump seal alarm. | Isolate Pressure transmitter |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-12-08 | 2023-04-22 | 10 |  |  | DF /A /28/DFAA-PT-50005 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076707 | DFA open drain pump seal alarm. | Isolate Pressure transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-12-08 | 2023-04-22 | 20 |  |  | DF /A /28/DFAA-PT-50005 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076707 | DFA open drain pump seal alarm. | Isolate Pressure transmitter |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-12-08 | 2023-04-22 | 30 |  |  | DF /A /28/DFAA-PT-50005 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100076707 | DFA open drain pump seal alarm. | Isolate Pressure transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-12-08 | 2023-04-22 | 40 |  |  | DF /A /28/DFAA-PT-50005 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100076707 | DFA open drain pump seal alarm. | Isolate Pressure transmitter |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-12-08 | 2023-04-22 | 50 |  |  | DF /A /28/DFAA-PT-50005 | Isolate Pressure transmitter | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 10 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 20 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 30 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 40 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 50 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 60 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-03-11 | 2020-11-11 | 2021-02-09 | 70 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 500 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-03-11 | 2024-05-12 | 2020-11-11 | 2021-02-09 | 90 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2020-11-11 | 2021-02-09 | 100 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2020-11-11 | 2021-02-09 | 110 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200005624 | DF Installation of temp supports | Increase of PO 4300016431 | AWSC | AWSC | 0 | 0 | Empty | 2024-03-11 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2020-11-11 | 2021-02-09 | 120 | AWSC | AWSC | DF | Increase of PO 4300016431 | Unknown
A | DFG-1740 | WPM | MTN-MECH | PRODTECH | 2400337667 | 2Y EMER. GENERATOR F.TEST DKDF-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | SECE | SECE | 5 | 0 | Empty | 2024-07-05 | 2024-07-16 | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2024-08-20 | 10 | SECE | SECE | DF /G /05/DFGA-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | Unknown
A | DFG-1740 | WPM | MTN-MECH | MTN-INST | 2400337667 | 2Y EMER. GENERATOR F.TEST DKDF-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | SECE | SECE | 1 | 0 | Empty | 2024-07-05 | 2024-07-16 | 2024-07-06 | 2024-07-06 | 2024-07-05 | 2024-08-20 | 20 | SECE | SECE | DF /G /05/DFGA-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | Unknown
A | DFG-1740 | WPM | MTN-MECH | MTN-MECH | 2400337667 | 2Y EMER. GENERATOR F.TEST DKDF-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | SECE | SECE | 48 | 0 | Empty | 2024-07-05 | 2024-07-16 | 2024-07-06 | 2024-07-12 | 2024-07-05 | 2024-08-20 | 30 | SECE | SECE | DF /G /05/DFGA-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | Unknown
A | DFG-1740 | WPM | MTN-MECH | MTN-ELEC | 2400337667 | 2Y EMER. GENERATOR F.TEST DKDF-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | SECE | SECE | 12 | 0 | Empty | 2024-07-05 | 2024-07-16 | 2024-07-12 | 2024-07-15 | 2024-07-05 | 2024-08-20 | 40 | SECE | SECE | DF /G /05/DFGA-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | Unknown
A | DFG-1740 | WPM | MTN-MECH | PRODTECH | 2400337667 | 2Y EMER. GENERATOR F.TEST DKDF-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | SECE | SECE | 5 | 0 | Empty | 2024-07-05 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2024-07-05 | 2024-08-20 | 50 | SECE | SECE | DF /G /05/DFGA-A-1740 | EMER. GENERATOR F.TEST DFGA-A-1740 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235686 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235686 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235686 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235686 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF04-BA001 | ISOLATION ELECTRICAL | Unknown
4 | D-FLARE | WDF | MTN-MECH | WELLSUPV | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-12 | 2024-07-12 | 2021-05-02 | 2021-09-29 | 10 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-12 | 2024-07-12 | 2021-05-02 | 2021-09-29 | 20 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 2 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-12 | 2024-07-12 | 2021-05-02 | 2021-09-29 | 30 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-12 | 2024-07-12 | 2021-05-02 | 2021-09-29 | 40 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 39 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-12 | 2024-07-16 | 2021-05-02 | 2021-09-29 | 50 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 8 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-16 | 2024-07-17 | 2021-05-02 | 2021-09-29 | 60 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 115 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-07-17 | 2024-08-01 | 2021-05-02 | 2021-09-29 | 70 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 12 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-01 | 2024-08-02 | 2021-05-02 | 2021-09-29 | 71 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-02 | 2024-08-03 | 2021-05-02 | 2021-09-29 | 80 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | PRODTECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 2 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-03 | 2024-08-03 | 2021-05-02 | 2021-09-29 | 90 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-03 | 2024-08-04 | 2021-05-02 | 2021-09-29 | 100 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-04 | 2024-08-05 | 2021-05-02 | 2021-09-29 | 110 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 6 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-05 | 2024-08-05 | 2021-05-02 | 2021-09-29 | 120 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | INP-SITE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-05 | 2024-08-07 | 2021-05-02 | 2021-09-29 | 130 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-07 | 2024-08-08 | 2021-05-02 | 2021-09-29 | 140 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-08 | 2024-08-10 | 2021-05-02 | 2021-09-29 | 150 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 26 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-10 | 2024-08-13 | 2021-05-02 | 2021-09-29 | 160 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 10 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-13 | 2024-08-14 | 2021-05-02 | 2021-09-29 | 170 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 13 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-14 | 2024-08-15 | 2021-05-02 | 2021-09-29 | 180 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 1 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-15 | 2024-08-15 | 2021-05-02 | 2021-09-29 | 181 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | PRODTECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 2 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-15 | 2024-08-16 | 2021-05-02 | 2021-09-29 | 190 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 12 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-16 | 2024-08-17 | 2021-05-02 | 2021-09-29 | 191 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 32 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-17 | 2024-08-21 | 2021-05-02 | 2021-09-29 | 200 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 3 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-21 | 2024-08-22 | 2021-05-02 | 2021-09-29 | 210 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 16 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-22 | 2024-08-24 | 2021-05-02 | 2021-09-29 | 220 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | VEN-MECH | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 6 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2021-05-02 | 2021-09-29 | 230 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2021-05-02 | 2021-09-29 | 240 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2021-05-02 | 2021-09-29 | 250 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | D-FLARE | WDF | MTN-MECH | MTN-ROPE | 2100045471 | ANOPR Replace 3/4" flarepipe on DFFA-V-4 | PAINT-ORDER-COATING |  |  | 0 | 0 | Empty | 2024-07-12 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2021-05-02 | 2021-09-29 | 260 |  |  | DF /F /32/DFFA-V-4401 | PAINT-ORDER-COATING | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009256 | Insulation assist bilfinger 20975 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-14 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /G /32/DFG-26-GPS-043-0009-DD-A | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009256 | Insulation assist bilfinger 20975 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-14 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /G /32/DFG-26-GPS-043-0009-DD-A | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009256 | Insulation assist bilfinger 20975 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-14 | 2024-01-10 | 2024-01-11 | 2022-02-09 | 2022-07-09 | 25 |  |  | DF /G /32/DFG-26-GPS-043-0009-DD-A | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009256 | Insulation assist bilfinger 20975 | Bilfinger inspection |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-14 | 2024-01-11 | 2024-01-14 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /G /32/DFG-26-GPS-043-0009-DD-A | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100072581 | Minor Ext. leak from stem on PCV-570211 | De-Isolate PCV-570211 |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2022-09-22 | 2023-02-04 | 10 |  |  | DF /F /70/DFFA-PCV-570211 | De-Isolate PCV-570211 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100072581 | Minor Ext. leak from stem on PCV-570211 | De-Isolate PCV-570211 |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2022-09-22 | 2023-02-04 | 20 |  |  | DF /F /70/DFFA-PCV-570211 | De-Isolate PCV-570211 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100072581 | Minor Ext. leak from stem on PCV-570211 | De-Isolate PCV-570211 |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2022-09-22 | 2023-02-04 | 30 |  |  | DF /F /70/DFFA-PCV-570211 | De-Isolate PCV-570211 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100072581 | Minor Ext. leak from stem on PCV-570211 | De-Isolate PCV-570211 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2022-09-22 | 2023-02-04 | 40 |  |  | DF /F /70/DFFA-PCV-570211 | De-Isolate PCV-570211 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056486 | DFFA-PRV-300133 Well-33 INTERNAL LEAK | Replace PRV |  |  | 1.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-10-19 | 2021-11-28 | 10 |  |  | DF /F /07/DFFA-PRV-300133 | Replace PRV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056486 | DFFA-PRV-300133 Well-33 INTERNAL LEAK | Replace PRV |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-10-19 | 2021-11-28 | 20 |  |  | DF /F /07/DFFA-PRV-300133 | Replace PRV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056486 | DFFA-PRV-300133 Well-33 INTERNAL LEAK | Replace PRV |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-10-19 | 2021-11-28 | 30 |  |  | DF /F /07/DFFA-PRV-300133 | Replace PRV | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093104 | DFGA-XCV-500668 Actuator due for repl | Add matr/New Actuator |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-06-07 | 2023-07-22 | 10 |  |  | DF /G /27/DFGA-XCV-500668 | Add matr/New Actuator | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093104 | DFGA-XCV-500668 Actuator due for repl | Add matr/New Actuator |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2023-06-07 | 2023-07-22 | 20 |  |  | DF /G /27/DFGA-XCV-500668 | Add matr/New Actuator | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093104 | DFGA-XCV-500668 Actuator due for repl | Add matr/New Actuator |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-06-07 | 2023-07-22 | 30 |  |  | DF /G /27/DFGA-XCV-500668 | Add matr/New Actuator | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093104 | DFGA-XCV-500668 Actuator due for repl | Add matr/New Actuator |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-06-07 | 2023-07-22 | 40 |  |  | DF /G /27/DFGA-XCV-500668 | Add matr/New Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2020-03-25 | 2020-05-04 | 5 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2020-03-25 | 2020-05-04 | 10 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2020-03-25 | 2020-05-04 | 30 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2020-03-25 | 2020-05-04 | 40 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2020-03-25 | 2020-05-04 | 50 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2020-03-25 | 2020-05-04 | 60 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029688 | Replace Actuator DFFA-XCV-301108 (Ekst. | Prepare rigging equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-03-25 | 2020-05-04 | 70 |  |  | DF /F /10/DFFA-XCV-301108 | Prepare rigging equipment | Unknown
3 | NOSD | WRO | VEN-MECH | MTN-MECH | 2300004771 | Renewal of dish in dutymess | Apply silicone sealant | PCNF | PCNF | 12 | 22 | Empty | 2024-06-11 | 2024-06-11 | 2023-03-27 | 2024-05-06 | 2023-03-27 | 2023-08-09 | 10 | PCNF | PCNF | DF /C /82 | Apply silicone sealant | Unknown
3 | NOSD | WRO | VEN-MECH | MTN-MECH | 2300004771 | Renewal of dish in dutymess | Apply silicone sealant | PCNF | PCNF | 4 | 0 | Empty | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2023-03-27 | 2023-08-09 | 20 | PCNF | PCNF | DF /C /82 | Apply silicone sealant | Unknown
3 | NOSD | WRO | VEN-MECH | VEN-MECH | 2300004771 | Renewal of dish in dutymess | Apply silicone sealant | PCNF | PCNF | 4 | 0 | Empty | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2024-06-11 | 2023-03-27 | 2023-08-09 | 30 | PCNF | PCNF | DF /C /82 | Apply silicone sealant | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329513 | 4Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2024-04-07 | 2024-06-19 | 10 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329513 | 4Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-31 | 2024-04-07 | 2024-06-19 | 20 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329513 | 4Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-02 | 2024-04-07 | 2024-06-19 | 30 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400329513 | 4Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-04-07 | 2024-06-19 | 40 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329513 | 4Y OXY SCAV INJ PUMP MAINT-DFGA-P-3960/1 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-04-07 | 2024-06-19 | 50 | SCHSECE | SCHSECE | DF /G /75/DFGA-A-3956 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096743 | udskiftning af ventiler og ventilhåndtag | replace valve |  |  | 1 | 0 | Empty | 2024-06-20 | 2024-06-22 | 2024-06-20 | 2024-06-20 | 2024-02-20 | 2026-08-08 | 10 |  |  | DF /C /01/DFCC-A-0304A | replace valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096743 | udskiftning af ventiler og ventilhåndtag | replace valve |  |  | 4 | 0 | Empty | 2024-06-20 | 2024-06-22 | 2024-06-20 | 2024-06-21 | 2024-02-20 | 2026-08-08 | 20 |  |  | DF /C /01/DFCC-A-0304A | replace valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096743 | udskiftning af ventiler og ventilhåndtag | replace valve |  |  | 1 | 0 | Empty | 2024-06-20 | 2024-06-22 | 2024-06-21 | 2024-06-22 | 2024-02-20 | 2026-08-08 | 30 |  |  | DF /C /01/DFCC-A-0304A | replace valve | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235796 | 4Y 380V N-SWB MAINT-DFAA-N-1800-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235796 | 4Y 380V N-SWB MAINT-DFAA-N-1800-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 14 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235796 | 4Y 380V N-SWB MAINT-DFAA-N-1800-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-26 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235796 | 4Y 380V N-SWB MAINT-DFAA-N-1800-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_20 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300003942 | DK40 - REplaced by 2300004162 | add materials |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2022-11-19 | 2023-09-15 | 10 |  |  | DF /C /84 | add materials | Unknown
4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300003942 | DK40 - REplaced by 2300004162 | add materials |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2022-11-19 | 2023-09-15 | 20 |  |  | DF /C /84 | add materials | Unknown
A | NOSD | WPM | VEN-INSP | MTN-MECH | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 238 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-05-01 | 2024-06-29 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 259 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-06-29 | 2024-09-02 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 34 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-02 | 2024-09-10 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PIPF | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-30 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PAIN | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 77 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-18 | 2024-10-30 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 20 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-18 | 2024-09-23 | 2024-10-30 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-23 | 2024-09-25 | 2024-10-30 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400298030 | PVI Major - DFFA-V-5012 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-10-30 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5012 | Material ordering | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235733 | 4Y 380V E-SWB MAINT DFCI-N-1812-R02 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235733 | 4Y 380V E-SWB MAINT DFCI-N-1812-R02 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 8 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235733 | 4Y 380V E-SWB MAINT DFCI-N-1812-R02 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235733 | 4Y 380V E-SWB MAINT DFCI-N-1812-R02 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 0 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 35 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235733 | 4Y 380V E-SWB MAINT DFCI-N-1812-R02 | ISOLATION BY EIA | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024737 | DAN FF Install of cover for HV cable | L3-install cover |  |  | 12 | 0 | NJF005 Campaign | 2023-11-01 | 2023-11-07 | 2023-11-01 | 2023-11-02 | 2018-04-25 | 2018-07-24 | 10 |  |  | DF /F /6 | L3-install cover | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100024737 | DAN FF Install of cover for HV cable | L3-install cover |  |  | 12 | 0 | NJF005 Campaign | 2023-11-01 | 2023-11-07 | 2023-11-02 | 2023-11-04 | 2018-04-25 | 2018-07-24 | 20 |  |  | DF /F /6 | L3-install cover | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024737 | DAN FF Install of cover for HV cable | L3-install cover |  |  | 12 | 0 | NJF005 Campaign | 2023-11-01 | 2023-11-07 | 2023-11-04 | 2023-11-05 | 2018-04-25 | 2018-07-24 | 30 |  |  | DF /F /6 | L3-install cover | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024737 | DAN FF Install of cover for HV cable | L3-install cover |  |  | 12 | 0 | NJF005 Campaign | 2023-11-01 | 2023-11-07 | 2023-11-05 | 2023-11-07 | 2018-04-25 | 2018-07-24 | 40 |  |  | DF /F /6 | L3-install cover | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-PIPF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-01 | 2024-08-01 | 2019-04-30 | 2019-05-20 | 10 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-01 | 2024-08-03 | 2019-04-30 | 2019-05-20 | 20 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-03 | 2024-08-05 | 2019-04-30 | 2019-05-20 | 25 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-05 | 2024-08-07 | 2019-04-30 | 2019-05-20 | 30 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 12 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-07 | 2024-08-09 | 2019-04-30 | 2019-05-20 | 40 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-PIPF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-09 | 2024-08-09 | 2019-04-30 | 2019-05-20 | 50 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-09 | 2024-08-11 | 2019-04-30 | 2019-05-20 | 60 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-11 | 2024-08-13 | 2019-04-30 | 2019-05-20 | 70 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-PIPF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-13 | 2024-08-14 | 2019-04-30 | 2019-05-20 | 80 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 12 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2019-04-30 | 2019-05-20 | 90 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100022650 | Exchange 24" valve HCV-340071 | L3 Pre. Permit and linewalk | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2024-08-01 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2019-04-30 | 2019-05-20 | 100 | AWSC | AWSC | DF /F /20/DFFA-HCV-340071 | L3 Pre. Permit and linewalk | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-29 | 2024-07-29 | 2021-12-13 | 2022-01-22 | 10 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-29 | 2024-07-29 | 2021-12-13 | 2022-01-22 | 30 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-29 | 2024-07-30 | 2021-12-13 | 2022-01-22 | 32 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-30 | 2024-07-31 | 2021-12-13 | 2022-01-22 | 34 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-31 | 2024-07-31 | 2021-12-13 | 2022-01-22 | 36 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-31 | 2024-08-01 | 2021-12-13 | 2022-01-22 | 40 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-01 | 2024-08-02 | 2021-12-13 | 2022-01-22 | 42 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-02 | 2024-08-02 | 2021-12-13 | 2022-01-22 | 44 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-02 | 2024-08-02 | 2021-12-13 | 2022-01-22 | 46 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-02 | 2024-08-03 | 2021-12-13 | 2022-01-22 | 50 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-03 | 2024-08-04 | 2021-12-13 | 2022-01-22 | 52 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-04 | 2024-08-04 | 2021-12-13 | 2022-01-22 | 54 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-04 | 2024-08-05 | 2021-12-13 | 2022-01-22 | 56 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-05 | 2024-08-05 | 2021-12-13 | 2022-01-22 | 60 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-05 | 2024-08-06 | 2021-12-13 | 2022-01-22 | 62 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-06 | 2024-08-06 | 2021-12-13 | 2022-01-22 | 64 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-06 | 2024-08-07 | 2021-12-13 | 2022-01-22 | 66 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-07 | 2024-08-07 | 2021-12-13 | 2022-01-22 | 70 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-07 | 2024-08-08 | 2021-12-13 | 2022-01-22 | 72 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-08 | 2024-08-09 | 2021-12-13 | 2022-01-22 | 74 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-09 | 2024-08-09 | 2021-12-13 | 2022-01-22 | 76 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-09 | 2024-08-10 | 2021-12-13 | 2022-01-22 | 80 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-10 | 2024-08-11 | 2021-12-13 | 2022-01-22 | 82 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-11 | 2024-08-11 | 2021-12-13 | 2022-01-22 | 84 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-11 | 2024-08-11 | 2021-12-13 | 2022-01-22 | 86 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-11 | 2024-08-12 | 2021-12-13 | 2022-01-22 | 90 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2021-12-13 | 2022-01-22 | 92 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2021-12-13 | 2022-01-22 | 94 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059288 | Replace to correct bolt spec. on FIT's | Replace faulty bolts on DFFA-FT-290102 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2021-12-13 | 2022-01-22 | 96 |  |  | DF /F /37/DFFA-FT-290102 | Replace faulty bolts on DFFA-FT-290102 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337671 | 1Y PROD WTR HP/LP SKD TEST-DFFA-A-5001 | PROD WTR HP/LP SKD TEST-DFFA-A-5001 |  |  | 18 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2024-07-18 | 2024-08-23 | 10 |  |  | DF /F /27/DFFA-A-5001 | PROD WTR HP/LP SKD TEST-DFFA-A-5001 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2018-05-13 | 2018-10-10 | 10 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2018-05-13 | 2018-10-10 | 20 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2018-05-13 | 2018-10-10 | 30 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2018-05-13 | 2018-10-10 | 40 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2018-05-13 | 2018-10-10 | 50 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2018-05-13 | 2018-10-10 | 60 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022438 | Exchange XCV-340513 | L3 Prepare rigging equipment |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2018-05-13 | 2018-10-10 | 70 |  |  | DF /F /20/DFFA-XCV-340513 | L3 Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 2 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 3 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 4 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 5 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 10 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 20 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 30 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-01 | 2020-04-07 | 2020-05-17 | 40 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 90 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-01 | 2023-04-08 | 2020-04-07 | 2020-05-17 | 50 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-08 | 2023-04-08 | 2020-04-07 | 2020-05-17 | 60 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ELEC | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-08 | 2023-04-08 | 2020-04-07 | 2020-05-17 | 62 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 12 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-09 | 2023-04-09 | 2020-04-07 | 2020-05-17 | 65 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 24 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-09 | 2023-04-10 | 2020-04-07 | 2020-05-17 | 67 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 4 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-10 | 2023-04-10 | 2020-04-07 | 2020-05-17 | 70 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-10 | 2023-04-10 | 2020-04-07 | 2020-05-17 | 80 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 10 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-10 | 2023-04-11 | 2020-04-07 | 2020-05-17 | 90 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 2 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-11 | 2023-04-11 | 2020-04-07 | 2020-05-17 | 93 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 4 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-11 | 2023-04-12 | 2020-04-07 | 2020-05-17 | 94 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 24 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-12 | 2023-04-13 | 2020-04-07 | 2020-05-17 | 95 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ELEC | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-13 | 2023-04-13 | 2020-04-07 | 2020-05-17 | 98 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 12 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-13 | 2023-04-13 | 2020-04-07 | 2020-05-17 | 100 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 60 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-13 | 2023-04-18 | 2020-04-07 | 2020-05-17 | 110 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 12 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2020-04-07 | 2020-05-17 | 120 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2020-04-07 | 2020-05-17 | 130 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030187 | SYNPR Replace partial. of 2" DO-spool un | New pic. of 2" DO-spool under DFF. |  |  | 0 | 0 | Empty | 2023-04-01 | 2023-04-18 | 2023-04-18 | 2023-04-18 | 2020-04-07 | 2020-05-17 | 140 |  |  | DF /F /28/DFF-2-DO-050-8195-AB-T | New pic. of 2" DO-spool under DFF. | Unknown
B | DFG-1640 | WPM | MTN-MECH | MTN-MECH | 2400282168 | 4KH SDV/BDV MAINT, COUNTER-A-1640 | SDV/BDV MAINT, COUNTER-A-1640 | AWSC | AWSC | 2 | 0 | W21-W22 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-10-04 | 2023-10-20 | 10 | AWSC | AWSC | DF /G /60/DFGA-A-1640 | SDV/BDV MAINT, COUNTER-A-1640 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-08-01 | 2021-02-07 | 2021-03-19 | 10 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-02 | 2021-02-07 | 2021-03-19 | 20 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-02 | 2021-02-07 | 2021-03-19 | 30 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-03 | 2021-02-07 | 2021-03-19 | 40 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-04 | 2021-02-07 | 2021-03-19 | 50 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-04 | 2021-02-07 | 2021-03-19 | 60 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-05 | 2021-02-07 | 2021-03-19 | 70 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-05 | 2024-08-07 | 2021-02-07 | 2021-03-19 | 80 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-07 | 2021-02-07 | 2021-03-19 | 90 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-08 | 2021-02-07 | 2021-03-19 | 100 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2021-02-07 | 2021-03-19 | 110 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044851 | DFG PCV-570013 Dårlig integritet | Isolate pneumatic and controls |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-10 | 2021-02-07 | 2021-03-19 | 120 |  |  | DF /G /70/DFGA-PCV-570013 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0 | 0.5 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-06-17 | 2024-07-03 | 2024-03-07 | 2024-07-20 | 5 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0 | 0.5 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-06-17 | 2024-07-03 | 2024-03-07 | 2024-07-20 | 10 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0 | 16 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-06-17 | 2024-07-03 | 2024-03-07 | 2024-07-20 | 20 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0 | 0.5 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-06-17 | 2024-07-03 | 2024-03-07 | 2024-07-20 | 30 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0 | 0.5 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-06-17 | 2024-07-03 | 2024-03-07 | 2024-07-20 | 40 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-03-07 | 2024-07-20 | 50 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-03-07 | 2024-07-20 | 60 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106759 | There is a leak on PSL-04020 | Isolate pressure switch | SCHSECE | SCHSECE | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-03-07 | 2024-07-20 | 70 | SCHSECE | SCHSECE | DF /C /01/DFCI-A-0400 | Isolate pressure switch | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2022-04-01 | 2022-04-09 | 2020-10-21 | 2020-11-10 | 2019-06-27 | 2019-09-25 | 10 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 21 | Empty | 2022-04-01 | 2022-04-09 | 2020-10-05 | 2020-11-10 | 2019-06-27 | 2019-09-25 | 20 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 4 | 0 | Empty | 2022-04-01 | 2022-04-09 | 2022-04-01 | 2022-04-01 | 2019-06-27 | 2019-09-25 | 30 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 0 | Empty | 2022-04-01 | 2022-04-09 | 2022-04-01 | 2022-04-01 | 2019-06-27 | 2019-09-25 | 40 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 108 | 0 | Empty | 2022-04-01 | 2022-04-09 | 2022-04-01 | 2022-04-09 | 2019-06-27 | 2019-09-25 | 50 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 36 | 0 | Empty | 2022-04-01 | 2022-04-09 | 2022-04-01 | 2022-04-02 | 2019-06-27 | 2019-09-25 | 60 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003141 | scaff assist FORCE 15548(COMP) | BUILD SCAFFOLDING | PCNF | PCNF | 54 | 0 | Empty | 2022-04-01 | 2022-04-09 | 2022-04-01 | 2022-04-05 | 2019-06-27 | 2019-09-25 | 70 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8106-AB-U | BUILD SCAFFOLDING | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094509 | DFG/78 crane hydraulic leak | Assist |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-01-16 | 2023-03-02 | 10 |  |  | DF /G /78/DFGA-A-6140 | Assist | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094509 | DFG/78 crane hydraulic leak | Assist |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-01-16 | 2023-03-02 | 20 |  |  | DF /G /78/DFGA-A-6140 | Assist | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100094509 | DFG/78 crane hydraulic leak | Assist |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-01-16 | 2023-03-02 | 30 |  |  | DF /G /78/DFGA-A-6140 | Assist | Unknown
A | DFC-1610 | WPM | MTN-TURB | MTN-TURB | 2400329954 | 18M DFCI-G-1610 CHECK SOLAR TURBINES | TL-18M DFCI-G-1610 CHECK SOLAR TURBINES | SCHSECE | SCHSECE | 18 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-16 | 2024-05-28 | 2024-06-27 | 10 | SCHSECE | SCHSECE | DF /C /60/DFCI-G-1610 | TL-18M DFCI-G-1610 CHECK SOLAR TURBINES | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 10 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 8 | 14 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 20 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 30 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 40 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 50 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 60 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 70 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 80 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 6 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 90 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 100 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015763 | Cooking oven Synegi DFCC ordering mat. | Vendor Follow up materials added | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-09-18 | 2023-11-02 | 110 | PCNFSCH | PCNFSCH | DF /C /82/DFCC-X-13017 | Vendor Follow up materials added | Unknown
2 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100086057 | Changeout vacuum ejectors on P-3520 | Production isolation | PCNFSCH | PCNFSCH | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-02-22 | 2023-04-08 | 5 | PCNFSCH | PCNFSCH | DF /F /53/DFFA-X-3502 | Production isolation | Unknown
2 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100086057 | Changeout vacuum ejectors on P-3520 | Production isolation | PCNFSCH | PCNFSCH | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-02-22 | 2023-04-08 | 10 | PCNFSCH | PCNFSCH | DF /F /53/DFFA-X-3502 | Production isolation | Unknown
2 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100086057 | Changeout vacuum ejectors on P-3520 | Production isolation | PCNFSCH | PCNFSCH | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-02-22 | 2023-04-08 | 20 | PCNFSCH | PCNFSCH | DF /F /53/DFFA-X-3502 | Production isolation | Unknown
2 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100086057 | Changeout vacuum ejectors on P-3520 | Production isolation | PCNFSCH | PCNFSCH | 0 | 3 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-02-22 | 2023-04-08 | 30 | PCNFSCH | PCNFSCH | DF /F /53/DFFA-X-3502 | Production isolation | Unknown
2 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100086057 | Changeout vacuum ejectors on P-3520 | Production isolation | PCNFSCH | PCNFSCH | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-02-22 | 2023-04-08 | 40 | PCNFSCH | PCNFSCH | DF /F /53/DFFA-X-3502 | Production isolation | Unknown
2 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100086057 | Changeout vacuum ejectors on P-3520 | Production isolation | PCNFSCH | PCNFSCH | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2023-02-22 | 2023-04-08 | 50 | PCNFSCH | PCNFSCH | DF /F /53/DFFA-X-3502 | Production isolation | Unknown
D | Empty | WPM | PRODTECH | MTN-MECH | 2400343722 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 0 | 0 | Empty | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-09-09 | 2024-09-15 | 1 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400343722 | PIGGING, P3011 - 16" DAD-DFF MULTI 2W | GENERAL INFO VEDLIGEHOLD UDEN ASSU | AWSC | AWSC | 4 | 10 | Empty | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-09-09 | 2024-09-15 | 2 | AWSC | AWSC | DF /F /12/DFFY-PL-673011 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344045 | 1Y DEMULSIFIER INJ. PUMPS MAINT-DFA | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-20 | 2024-08-24 | 2024-08-20 | 2024-08-20 | 2024-08-20 | 2024-09-25 | 10 |  |  | DF /A /75/DEMULSIFIER-INJ-PUMP-SKID | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344045 | 1Y DEMULSIFIER INJ. PUMPS MAINT-DFA | ISOLATION BY PRODUCTION |  |  | 11 | 0 | Empty | 2024-08-20 | 2024-08-24 | 2024-08-20 | 2024-08-22 | 2024-08-20 | 2024-09-25 | 20 |  |  | DF /A /75/DEMULSIFIER-INJ-PUMP-SKID | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344045 | 1Y DEMULSIFIER INJ. PUMPS MAINT-DFA | ISOLATION BY PRODUCTION |  |  | 6 | 0 | Empty | 2024-08-20 | 2024-08-24 | 2024-08-23 | 2024-08-24 | 2024-08-20 | 2024-09-25 | 30 |  |  | DF /A /75/DEMULSIFIER-INJ-PUMP-SKID | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344045 | 1Y DEMULSIFIER INJ. PUMPS MAINT-DFA | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-20 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-08-20 | 2024-09-25 | 40 |  |  | DF /A /75/DEMULSIFIER-INJ-PUMP-SKID | ISOLATION BY PRODUCTION | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-07 | 2024-06-07 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-07 | 2024-06-08 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 17 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-08 | 2024-06-11 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 4 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-11 | 2024-06-12 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 2 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-12 | 2024-06-13 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-13 | 2024-06-14 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-14 | 2024-06-15 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-15 | 2024-06-16 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-16 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | PRODTECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-17 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-17 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-18 | 2024-06-18 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | DFG-IPHP | WPM | MTN-MECH | MTN-SCAF | 2400284306 | PSV Calibration - DFGA-PSV-430027A | Install rigging equipment | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 8 | W23-W24 | 2024-06-07 | 2024-06-19 | 2024-06-18 | 2024-06-19 | 2024-10-19 | 2024-12-31 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /G /31/DFGA-PSV-430027A | Install rigging equipment | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337658 | 4Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 4 | 0 | W31-W32 | 2024-08-01 | 2024-08-16 | 2024-08-01 | 2024-08-01 | 2024-06-12 | 2024-08-24 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337658 | 4Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 40 | 5 | W31-W32 | 2024-08-01 | 2024-08-16 | 2024-08-02 | 2024-08-11 | 2024-06-12 | 2024-08-24 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337658 | 4Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 10 | 0 | W31-W32 | 2024-08-01 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2024-06-12 | 2024-08-24 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400337658 | 4Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 4 | 5 | W31-W32 | 2024-08-01 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2024-06-12 | 2024-08-24 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337658 | 4Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | AWSCSCHSECE | AWSCSCHSECE | 4 | 0 | W31-W32 | 2024-08-01 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2024-06-12 | 2024-08-24 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291638 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-11-04 | 2023-12-04 | 10 | SECE | SECE | DF /F /34/DFFA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400291638 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 1.5 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2023-11-04 | 2023-12-04 | 20 | SECE | SECE | DF /F /34/DFFA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291638 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 10 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2023-11-04 | 2023-12-04 | 30 | SECE | SECE | DF /F /34/DFFA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291638 | 1Y PIG LAUNCHER MAINT-DFFA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2023-11-04 | 2023-12-04 | 40 | SECE | SECE | DF /F /34/DFFA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-17 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 24 | 6 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-17 | 2024-07-20 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 5 | 5 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 2 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 12 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2024-10-12 | 2024-12-31 | 80 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 5 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-25 | 2024-07-26 | 2024-10-12 | 2024-12-31 | 90 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-26 | 2024-10-12 | 2024-12-31 | 100 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-10-12 | 2024-12-31 | 110 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284295 | PSV Calibration - DFGA-PSV-540402B | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2024-10-12 | 2024-12-31 | 120 | AWSC | AWSC | DF /G /07/DFGA-PSV-540402B | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337266 | 4Y HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2024-07-30 | 2024-05-31 | 2024-08-12 | 10 | AWSCSECE | AWSCSECE | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400337266 | 4Y HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2024-07-30 | 2024-05-31 | 2024-08-12 | 20 | AWSCSECE | AWSCSECE | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337266 | 4Y HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 10 | 0 | Empty | 2024-07-30 | 2024-08-03 | 2024-07-30 | 2024-08-02 | 2024-05-31 | 2024-08-12 | 30 | AWSCSECE | AWSCSECE | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337266 | 4Y HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-30 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2024-05-31 | 2024-08-12 | 40 | AWSCSECE | AWSCSECE | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337266 | 4Y HPU FOR ESDV CTRL MAINT - DFBA-A-5903 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-07-30 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-05-31 | 2024-08-12 | 50 | AWSCSECE | AWSCSECE | DF /B /07/DFBA-A-5903 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344330 | 6M INSTRUMENT AIR SYSTEM MAINT - DFF | INSTRUMENT AIR SYSTEM MAINT - DFF | AWSC | AWSC | 5 | 0 | Empty | 2024-09-13 | 2024-09-14 | 2024-09-13 | 2024-09-14 | 2024-09-13 | 2024-09-29 | 10 | AWSC | AWSC | DF /F /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM MAINT - DFF | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344330 | 6M INSTRUMENT AIR SYSTEM MAINT - DFF | INSTRUMENT AIR SYSTEM MAINT - DFF | AWSC | AWSC | 2 | 0 | Empty | 2024-09-13 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-13 | 2024-09-29 | 20 | AWSC | AWSC | DF /F /07/INSTRUMENT-AIR-SYSTEM | INSTRUMENT AIR SYSTEM MAINT - DFF | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342397 | 3M FIREWATER PUMP PKG MAINT-DFGA-A-0351 | FIREWATER PUMP PKG MAINT-DFGA-A-0351 | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-08-25 | 2024-09-04 | 10 | SECE | SECE | DF /G /01/DFGA-A-0351 | FIREWATER PUMP PKG MAINT-DFGA-A-0351 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088247 | Hydraulic leak on DFAA-FT-59077 | Hydraulic leak on DFAA-FT-59077 |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-29 | 2023-05-13 | 10 |  |  | DF /A /07/DFAA-FT-59077 | Hydraulic leak on DFAA-FT-59077 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235584 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1830-02B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235584 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 21 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-27 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1830-02B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235584 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-27 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1830-02B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235584 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1830-02B1 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WGN | MTN-MECH | WELLSUPV | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 3 | 3 | Empty | 2024-07-15 | 2024-08-07 | 2021-07-01 | 2024-06-03 | 2020-12-10 | 2021-05-09 | 10 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-15 | 2020-12-10 | 2021-05-09 | 20 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-16 | 2020-12-10 | 2021-05-09 | 30 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-16 | 2024-07-16 | 2020-12-10 | 2021-05-09 | 40 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 3 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-16 | 2024-07-16 | 2020-12-10 | 2021-05-09 | 50 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-15 | 2020-12-10 | 2021-05-09 | 55 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 5 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2020-12-10 | 2021-05-09 | 60 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 1 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2020-12-10 | 2021-05-09 | 70 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 4 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2020-12-10 | 2021-05-09 | 80 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 2 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2020-12-10 | 2021-05-09 | 90 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 3 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2020-12-10 | 2021-05-09 | 100 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-08-07 | 2024-08-07 | 2020-12-10 | 2021-05-09 | 110 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-15 | 2020-12-10 | 2021-05-09 | 120 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-15 | 2020-12-10 | 2021-05-09 | 130 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-15 | 2020-12-10 | 2021-05-09 | 140 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200004863 | Exchange DFCM-PSV-53012 - PSV 2023 | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2024-07-15 | 2024-08-07 | 2024-07-15 | 2024-07-15 | 2020-12-10 | 2021-05-09 | 150 | PCNF | PCNF | DF /C /76/DFCM-PSV-53012 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075995 | DFFE/78: Light check and repair all over | Isolate/de-isolate of crane DFFA-A-6101 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-11-21 | 2023-04-05 | 10 |  |  | DF /F /78/DFFA-A-6101 | Isolate/de-isolate of crane DFFA-A-6101 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075995 | DFFE/78: Light check and repair all over | Isolate/de-isolate of crane DFFA-A-6101 |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2022-11-21 | 2023-04-05 | 20 |  |  | DF /F /78/DFFA-A-6101 | Isolate/de-isolate of crane DFFA-A-6101 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075995 | DFFE/78: Light check and repair all over | Isolate/de-isolate of crane DFFA-A-6101 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2022-11-21 | 2023-04-05 | 30 |  |  | DF /F /78/DFFA-A-6101 | Isolate/de-isolate of crane DFFA-A-6101 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075995 | DFFE/78: Light check and repair all over | Isolate/de-isolate of crane DFFA-A-6101 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2022-11-21 | 2023-04-05 | 40 |  |  | DF /F /78/DFFA-A-6101 | Isolate/de-isolate of crane DFFA-A-6101 | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-TURB | 2400291777 | 9M DFEY-P-3551 | Visual inspection | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-11-28 | 2023-12-14 | 30 | SECE | SECE | DF /E /54/DFEY-P-3551 | Visual inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100062998 | Failed handle on 2" globe valve | Isolate 2" Globe HCV |  |  | 15 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-19 | 2022-06-03 | 2023-01-29 | 10 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Isolate 2" Globe HCV | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100062998 | Failed handle on 2" globe valve | Isolate 2" Globe HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-19 | 2022-06-03 | 2023-01-29 | 20 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Isolate 2" Globe HCV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100062998 | Failed handle on 2" globe valve | Isolate 2" Globe HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-20 | 2022-06-03 | 2023-01-29 | 30 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Isolate 2" Globe HCV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100062998 | Failed handle on 2" globe valve | Isolate 2" Globe HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-20 | 2024-09-20 | 2022-06-03 | 2023-01-29 | 40 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Isolate 2" Globe HCV | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100062998 | Failed handle on 2" globe valve | Isolate 2" Globe HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-20 | 2024-09-21 | 2022-06-03 | 2023-01-29 | 50 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Isolate 2" Globe HCV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100062998 | Failed handle on 2" globe valve | Isolate 2" Globe HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-21 | 2024-09-23 | 2022-06-03 | 2023-01-29 | 60 |  |  | DF /F /36/SYSTEM-36-MANUAL-VALVES | Isolate 2" Globe HCV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049807 | FLM DFA - Missing safety chain escape to | DFA - Missing safety chain escape to sea |  |  | 4 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2021-08-21 | 2022-04-18 | 10 |  |  | DF /A /86/JACKET - HANDRAILS | DFA - Missing safety chain escape to sea | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100049807 | FLM DFA - Missing safety chain escape to | DFA - Missing safety chain escape to sea |  |  | 4 | 0 | Empty | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2021-08-21 | 2022-04-18 | 20 |  |  | DF /A /86/JACKET - HANDRAILS | DFA - Missing safety chain escape to sea | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339277 | DFF_1Y_34300 INT STRUCT INSP - GVI | DFF_1Y_34300 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_34300 (ACCESS PLATFORM) | DFF_1Y_34300 INT STRUCT INSP - GVI | Unknown
4 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100074856 | Seawater valves Internal Leak. | L2 Isolate |  |  | 12 | 0 | Empty | 2024-09-18 | 2024-10-01 | 2024-09-18 | 2024-09-21 | 2023-03-18 | 2025-09-03 | 10 |  |  | DF /G /51/DFGA-TCV-530459B | L2 Isolate | Unknown
4 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100074856 | Seawater valves Internal Leak. | L2 Isolate |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-10-01 | 2024-09-21 | 2024-09-22 | 2023-03-18 | 2025-09-03 | 20 |  |  | DF /G /51/DFGA-TCV-530459B | L2 Isolate | Unknown
4 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100074856 | Seawater valves Internal Leak. | L2 Isolate |  |  | 14 | 0 | Empty | 2024-09-18 | 2024-10-01 | 2024-09-22 | 2024-09-26 | 2023-03-18 | 2025-09-03 | 30 |  |  | DF /G /51/DFGA-TCV-530459B | L2 Isolate | Unknown
4 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100074856 | Seawater valves Internal Leak. | L2 Isolate |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-10-01 | 2024-09-26 | 2024-09-27 | 2023-03-18 | 2025-09-03 | 40 |  |  | DF /G /51/DFGA-TCV-530459B | L2 Isolate | Unknown
4 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100074856 | Seawater valves Internal Leak. | L2 Isolate |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-10-01 | 2024-09-27 | 2024-09-29 | 2023-03-18 | 2025-09-03 | 50 |  |  | DF /G /51/DFGA-TCV-530459B | L2 Isolate | Unknown
4 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100074856 | Seawater valves Internal Leak. | L2 Isolate |  |  | 8 | 0 | Empty | 2024-09-18 | 2024-10-01 | 2024-09-29 | 2024-10-01 | 2023-03-18 | 2025-09-03 | 60 |  |  | DF /G /51/DFGA-TCV-530459B | L2 Isolate | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339271 | DFF_1Y_27500 INT STRUCT INSP - GVI | DFF_1Y_27500 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_27500 (LEVEL2 LOWER DECK) | DFF_1Y_27500 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235834 | 4Y 400V E-SWB MAINT DFFB-N-1829 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /05/DFFB-N-1829 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235834 | 4Y 400V E-SWB MAINT DFFB-N-1829 | ISOLATION BY PRODUCTION | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /05/DFFB-N-1829 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235834 | 4Y 400V E-SWB MAINT DFFB-N-1829 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /05/DFFB-N-1829 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235834 | 4Y 400V E-SWB MAINT DFFB-N-1829 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /05/DFFB-N-1829 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112080 | DFBA-A-0461 for A-3550 N2 botles replace | Disconnect N2 bottle |  |  | 1 | 0 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-19 | 2024-08-19 | 2024-06-19 | 2024-11-01 | 10 |  |  | DF /B /01/DFBA-A-0461 | Disconnect N2 bottle | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112080 | DFBA-A-0461 for A-3550 N2 botles replace | Disconnect N2 bottle |  |  | 3 | 0 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-19 | 2024-08-19 | 2024-06-19 | 2024-11-01 | 20 |  |  | DF /B /01/DFBA-A-0461 | Disconnect N2 bottle | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100112080 | DFBA-A-0461 for A-3550 N2 botles replace | Disconnect N2 bottle |  |  | 6 | 0 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-20 | 2024-08-20 | 2024-06-19 | 2024-11-01 | 30 |  |  | DF /B /01/DFBA-A-0461 | Disconnect N2 bottle | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112080 | DFBA-A-0461 for A-3550 N2 botles replace | Disconnect N2 bottle |  |  | 3 | 0 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-20 | 2024-08-21 | 2024-06-19 | 2024-11-01 | 40 |  |  | DF /B /01/DFBA-A-0461 | Disconnect N2 bottle | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112080 | DFBA-A-0461 for A-3550 N2 botles replace | Disconnect N2 bottle |  |  | 1 | 0 | Empty | 2024-08-19 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-06-19 | 2024-11-01 | 50 |  |  | DF /B /01/DFBA-A-0461 | Disconnect N2 bottle | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269616 | 1Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-17 | 2024-06-03 | 2024-06-04 | 2023-07-25 | 2023-08-24 | 10 | SCHSECE | SCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269616 | 1Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 40 | 0 | W23-W24 | 2024-06-03 | 2024-06-17 | 2024-06-04 | 2024-06-14 | 2023-07-25 | 2023-08-24 | 20 | SCHSECE | SCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400269616 | 1Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-17 | 2024-06-14 | 2024-06-15 | 2023-07-25 | 2023-08-24 | 30 | SCHSECE | SCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400269616 | 1Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-17 | 2024-06-15 | 2024-06-16 | 2023-07-25 | 2023-08-24 | 40 | SCHSECE | SCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269616 | 1Y CRUD OL BOSTR PMP MAIN-DFCM-P-3620/10 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-17 | 2024-06-16 | 2024-06-17 | 2023-07-25 | 2023-08-24 | 50 | SCHSECE | SCHSECE | DF /C /23/DFCM-P-3620 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400309008 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-5 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 27 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2024-01-19 | 2024-03-21 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-5 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400337681 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-6 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 26 | 0 | Empty | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-08-18 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-6 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100060421 | Change of Heat Element | De-isolate accordingly and test |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2022-01-15 | 2022-04-15 | 10 |  |  | DF /G /72/DFGA-XE-1140 | De-isolate accordingly and test | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060421 | Change of Heat Element | De-isolate accordingly and test |  |  | 12 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2022-01-15 | 2022-04-15 | 20 |  |  | DF /G /72/DFGA-XE-1140 | De-isolate accordingly and test | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100060421 | Change of Heat Element | De-isolate accordingly and test |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2022-01-15 | 2022-04-15 | 30 |  |  | DF /G /72/DFGA-XE-1140 | De-isolate accordingly and test | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258780 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-04-26 | 2023-06-01 | 10 |  |  | DF /F /75/DFFA-A-39705 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 | Unknown
4 | DFB-O08 | WDF | MTN-INST | MTN-INST | 2100024609 | CMAT:Replace of ball valve HCV 40117 | L3 Isolate B & B | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2024-12-31 | 2025-01-01 | 2019-07-20 | 2020-07-14 | 10 | AWSC | AWSC | DF /B /37/DFBA-HCV-40117 | L3 Isolate B & B | Unknown
4 | DFB-O08 | WDF | MTN-INST | MTN-INST | 2100024609 | CMAT:Replace of ball valve HCV 40117 | L3 Isolate B & B | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2019-07-20 | 2020-07-14 | 20 | AWSC | AWSC | DF /B /37/DFBA-HCV-40117 | L3 Isolate B & B | Unknown
4 | DFB-O08 | WDF | MTN-INST | MTN-INST | 2100024609 | CMAT:Replace of ball valve HCV 40117 | L3 Isolate B & B | AWSC | AWSC | 8 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-07-20 | 2020-07-14 | 30 | AWSC | AWSC | DF /B /37/DFBA-HCV-40117 | L3 Isolate B & B | Unknown
4 | DFB-O08 | WDF | MTN-INST | MTN-INST | 2100024609 | CMAT:Replace of ball valve HCV 40117 | L3 Isolate B & B | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2019-07-20 | 2020-07-14 | 40 | AWSC | AWSC | DF /B /37/DFBA-HCV-40117 | L3 Isolate B & B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086704 | Replace broken cover for DFGA-WO-1823 | Replace 63 A outlet |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-18 | 2023-08-31 | 10 |  |  | DF /G /61/DFGA-N-1842A-AR06-FA001 | Replace 63 A outlet | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086704 | Replace broken cover for DFGA-WO-1823 | Replace 63 A outlet |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-18 | 2023-08-31 | 20 |  |  | DF /G /61/DFGA-N-1842A-AR06-FA001 | Replace 63 A outlet | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100086704 | Replace broken cover for DFGA-WO-1823 | Replace 63 A outlet |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-04-18 | 2023-08-31 | 30 |  |  | DF /G /61/DFGA-N-1842A-AR06-FA001 | Replace 63 A outlet | Unknown
1 | Empty | WRO | MTN-TELE | MTN-TELE | 2300008724 | TME1863 shipping ABB equip. part 1 | TME1863 Notifi for shipping part 1 offsh |  |  | 1 | 0 | Empty | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-04-30 | 2024-05-15 | 10 |  |  | DF /C | TME1863 Notifi for shipping part 1 offsh | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235743 | 4Y 400V UPS-DB F.TEST-DFFA-DP-1907 | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /06/DFFA-DP-1907 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235743 | 4Y 400V UPS-DB F.TEST-DFFA-DP-1907 | ISOLATION ELECTRICAL | SECE | SECE | 14 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /06/DFFA-DP-1907 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235743 | 4Y 400V UPS-DB F.TEST-DFFA-DP-1907 | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /06/DFFA-DP-1907 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235743 | 4Y 400V UPS-DB F.TEST-DFFA-DP-1907 | ISOLATION ELECTRICAL | SECE | SECE | 1 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /06/DFFA-DP-1907 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400321768 | DFC-36-GF-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 14 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235717 | 4Y 380V E-SWB MAINT DFCC-N-1813-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235717 | 4Y 380V E-SWB MAINT DFCC-N-1813-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 12 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235717 | 4Y 380V E-SWB MAINT DFCC-N-1813-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235717 | 4Y 380V E-SWB MAINT DFCC-N-1813-02 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106304 | Wires must be removed. | Close holes in Junc. boxes. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-07-22 | 2027-01-08 | 20 |  |  | DF /F /10/DFFA-XCV-301307 | Close holes in Junc. boxes. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106304 | Wires must be removed. | Close holes in Junc. boxes. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-07-22 | 2027-01-08 | 30 |  |  | DF /F /10/DFFA-XCV-301307 | Close holes in Junc. boxes. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106304 | Wires must be removed. | Close holes in Junc. boxes. |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2024-07-22 | 2027-01-08 | 40 |  |  | DF /F /10/DFFA-XCV-301307 | Close holes in Junc. boxes. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106304 | Wires must be removed. | Close holes in Junc. boxes. |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-07-22 | 2027-01-08 | 50 |  |  | DF /F /10/DFFA-XCV-301307 | Close holes in Junc. boxes. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059759 | FLM DFE - Repl of gratings EL +26200 | DFE - Replacement of gratings EL +26200 | PCNF | PCNF | 0 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2022-01-01 | 2022-04-01 | 10 | PCNF | PCNF | DF /E /86/26200 - GRATINGS | DFE - Replacement of gratings EL +26200 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100059759 | FLM DFE - Repl of gratings EL +26200 | DFE - Replacement of gratings EL +26200 | PCNF | PCNF | 2 | 2 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2022-01-01 | 2022-04-01 | 20 | PCNF | PCNF | DF /E /86/26200 - GRATINGS | DFE - Replacement of gratings EL +26200 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100059759 | FLM DFE - Repl of gratings EL +26200 | DFE - Replacement of gratings EL +26200 | PCNF | PCNF | 1 | 1 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2022-01-01 | 2022-04-01 | 30 | PCNF | PCNF | DF /E /86/26200 - GRATINGS | DFE - Replacement of gratings EL +26200 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100059759 | FLM DFE - Repl of gratings EL +26200 | DFE - Replacement of gratings EL +26200 | PCNF | PCNF | 12 | 18 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-27 | 2022-01-01 | 2022-04-01 | 40 | PCNF | PCNF | DF /E /86/26200 - GRATINGS | DFE - Replacement of gratings EL +26200 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322292 | DFF-27-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 104 | 18.75 | Empty | 2024-10-30 | 2024-11-29 | 2024-10-30 | 2024-11-28 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-RIGG | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 6 | 6 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-03 | 2024-07-03 | 2023-03-09 | 2023-07-22 | 10 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | PRODTECH | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-03 | 2024-07-04 | 2023-03-09 | 2023-07-22 | 20 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-INST | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-04 | 2024-07-04 | 2023-03-09 | 2023-07-22 | 30 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-MECH | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 12 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-04 | 2024-07-06 | 2023-03-09 | 2023-07-22 | 40 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-RIGG | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 12 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-04 | 2024-07-06 | 2023-03-09 | 2023-07-22 | 50 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-INST | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-06 | 2024-07-06 | 2023-03-09 | 2023-07-22 | 60 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | PRODTECH | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-06 | 2024-07-06 | 2023-03-09 | 2023-07-22 | 70 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-MECH | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-06 | 2024-07-07 | 2023-03-09 | 2023-07-22 | 80 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-RIGG | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2024-07-03 | 2024-07-08 | 2024-07-07 | 2024-07-08 | 2023-03-09 | 2023-07-22 | 90 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
3 | DFF-W11 | WDF | MTN-MECH | MTN-ROPE | 2100081553 | Change out Choke DFF-11 | Setup/de-rig rigg. equipment | PCNFAWSC | PCNFAWSC | 4 | 4 | Empty | 2024-07-03 | 2024-07-08 | 2024-06-29 | 2024-06-29 | 2023-03-09 | 2023-07-22 | 100 | PCNFAWSC | PCNFAWSC | DF /F /55/DFFA-CVA-300711 | Setup/de-rig rigg. equipment | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 10 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-22 | 2024-10-23 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 0 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284247 | PSV Exchange - DFCI-PSV-57122 | test jacob | AWSC | AWSC | 0 | 0 | Empty | 2024-10-19 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /C /70/DFCI-PSV-57122 | test jacob | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 12 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 10 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 24 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 11 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 20 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 30 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 40 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 50 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 6 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 60 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 10 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 70 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 20 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 80 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 20 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 90 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 24 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 100 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 110 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 20 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 120 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 60 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 130 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 20 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 140 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 20 | 14 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 150 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 5 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 160 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 6 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 170 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 8 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 180 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 20 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 190 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 200 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 210 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100066359 | B-3567. Metalspåner i olie, drive-end. | BUSCH, Troubleshooting survey-inspection |  |  | 0 | 0 | RCE | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2023-11-01 | 2022-04-25 | 2022-06-04 | 300 |  |  | DF /F /53/DFFB-B-3567 | BUSCH, Troubleshooting survey-inspection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 36 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-29 | 2017-06-22 | 2017-09-20 | 5 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 7 | 7 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-26 | 2017-06-22 | 2017-09-20 | 10 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 22 | 22 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-29 | 2024-09-01 | 2017-06-22 | 2017-09-20 | 20 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 20 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-29 | 2024-09-03 | 2017-06-22 | 2017-09-20 | 25 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 1 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-01 | 2024-09-02 | 2017-06-22 | 2017-09-20 | 30 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 18 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2017-06-22 | 2017-09-20 | 40 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027395 | SMAT:Udskiftning af LS-JB-1830-57-L3A | Construction of scaffolding | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-26 | 2017-06-22 | 2017-09-20 | 50 | PCNF | PCNF | DF /B /61/DFBA-N-1810-C_57 | Construction of scaffolding | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100042829 | ANOP HCV sidder fast og kan ikke oper. | Test ringmain valve open/closing functio |  |  | 6 | 0 | W49-50 OIM FW MPM | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2020-12-17 | 2021-01-06 | 10 |  |  | DF /C /01/DFCM-HCV-03062 | Test ringmain valve open/closing functio | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100042829 | ANOP HCV sidder fast og kan ikke oper. | Test ringmain valve open/closing functio |  |  | 1 | 0 | W49-50 OIM FW MPM | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-14 | 2020-12-17 | 2021-01-06 | 20 |  |  | DF /C /01/DFCM-HCV-03062 | Test ringmain valve open/closing functio | Unknown
3 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100082298 | Gear LSS Rad Vibr. DE X Signalfail (XE 4 | Gear LSS Rad Vibr. DE X Signalfail | SCH | SCH | 4 | 0 | W47-48 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-03-10 | 2023-07-23 | 10 | SCH | SCH | DF /G /31/DFGA-XT-430266 | Gear LSS Rad Vibr. DE X Signalfail | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 10 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 1 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-11-06 | 2015-02-04 | 20 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-11-06 | 2015-02-04 | 30 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | VEN-ELEC | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-11-06 | 2015-02-04 | 40 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | VEN-ELEC | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-11-06 | 2015-02-04 | 50 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2014-11-06 | 2015-02-04 | 60 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 70 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 80 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | VEN-ELEC | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 90 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | VEN-ELEC | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 100 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 110 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 4.700000000000000177635683938 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-11-06 | 2015-02-04 | 120 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027950 | DFF-05 OIL XCV-301205 intern læk. | Preparation for rigging | PCNFAWSC | PCNFAWSC | 4.700000000000000177635683938 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2014-11-06 | 2015-02-04 | 130 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301205 | Preparation for rigging | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100082300 | DFC HP manifold PT transmitter faulty | Troubleshoot Pressure transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-07-30 | 2026-01-15 | 10 |  |  | DF /C /12/DFCI-PIT-33066 | Troubleshoot Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100082300 | DFC HP manifold PT transmitter faulty | Troubleshoot Pressure transmitter |  |  | 1.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-07-30 | 2026-01-15 | 20 |  |  | DF /C /12/DFCI-PIT-33066 | Troubleshoot Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100082300 | DFC HP manifold PT transmitter faulty | Troubleshoot Pressure transmitter |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-07-30 | 2026-01-15 | 30 |  |  | DF /C /12/DFCI-PIT-33066 | Troubleshoot Pressure transmitter | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-ROPE | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 2 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-ROPE | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 4 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 10 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-RIGG | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 20 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 30 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 40 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-17 | 2022-02-02 | 2022-09-30 | 50 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-19 | 2022-02-02 | 2022-09-30 | 60 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-RIGG | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-20 | 2022-02-02 | 2022-09-30 | 70 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-20 | 2022-02-02 | 2022-09-30 | 80 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-20 | 2024-09-22 | 2022-02-02 | 2022-09-30 | 90 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2022-02-02 | 2022-09-30 | 100 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-ROPE | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 105 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2022-02-02 | 2022-09-30 | 110 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 120 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 130 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-ROPE | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 150 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-ROPE | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 160 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 170 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-RIGG | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 180 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 190 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 200 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-RIGG | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 210 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 220 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 230 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 240 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2022-02-02 | 2022-09-30 | 250 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
4 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100056737 | Internal leak DFGA-HCV-030128 | Plan B - Freezing JOB |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2022-02-02 | 2022-09-30 | 260 |  |  | DF /G /01/DFGA-HCV-030128 | Plan B - Freezing JOB | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337673 | 3Y FIRE DAMPER CHECK - DFB | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2024-06-22 | 2024-08-23 | 10 | SECE | SECE | DF /B /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337673 | 3Y FIRE DAMPER CHECK - DFB | PERSONAL ISOLATION | SECE | SECE | 8 | 10 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-17 | 2024-06-22 | 2024-08-23 | 20 | SECE | SECE | DF /B /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337673 | 3Y FIRE DAMPER CHECK - DFB | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-17 | 2024-06-22 | 2024-08-23 | 30 | SECE | SECE | DF /B /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400337673 | 3Y FIRE DAMPER CHECK - DFB | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2024-06-22 | 2024-08-23 | 40 | SECE | SECE | DF /B /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 567 | 20 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-01 | 2020-07-01 | 2020-07-07 | 2020-08-16 | 10 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 100 | 9 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-01 | 2020-07-01 | 2020-07-07 | 2020-08-16 | 20 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 113 | 0 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-01 | 2020-07-12 | 2020-07-07 | 2020-08-16 | 30 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 75 | 6 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-12 | 2020-07-17 | 2020-07-07 | 2020-08-16 | 40 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 454 | 7.5 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-17 | 2020-07-17 | 2020-07-07 | 2020-08-16 | 50 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 68 | 6 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-17 | 2020-07-17 | 2020-07-07 | 2020-08-16 | 60 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 45 | 0 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-17 | 2020-07-22 | 2020-07-07 | 2020-08-16 | 70 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 45 | 0 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-22 | 2020-07-27 | 2020-07-07 | 2020-08-16 | 80 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 227 | 2 | Empty | 2020-07-01 | 2020-10-11 | 2020-07-27 | 2020-08-19 | 2020-07-07 | 2020-08-16 | 90 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 268 | 6 | Empty | 2020-07-01 | 2020-10-11 | 2020-08-19 | 2020-09-15 | 2020-07-07 | 2020-08-16 | 100 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 45 | 0 | Empty | 2020-07-01 | 2020-10-11 | 2020-09-15 | 2020-09-20 | 2020-07-07 | 2020-08-16 | 110 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001763 | DAF OCG NPT order -99000002-0170/FF 3520 | Planned drills & meetings | PCNF | PCNF | 227 | 11 | Empty | 2020-07-01 | 2020-10-11 | 2020-09-20 | 2020-10-11 | 2020-07-07 | 2020-08-16 | 120 | PCNF | PCNF | DF /F | Planned drills & meetings | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339051 | DFB_1Y_FLARE INT STRUCT INSP - GVI | DFB_1Y_FLARE INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/FLARE TOWER | DFB_1Y_FLARE INT STRUCT INSP - GVI | Unknown
4 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200003264 | FCV-290134 er meget rusten oven på | Cleaning ved MBX and Paint | PCNF | PCNF | 20.100000000000001421085471515 | 0 | W17-18 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 | 2018-04-28 | 2020-04-17 | 10 | PCNF | PCNF | DF /F /37/DFFA-FCV-290134 | Cleaning ved MBX and Paint | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344067 | 6M BDV LUB/MAINT- DFF | BDV LUB/MAINT- DFF |  |  | 13 | 0 | Empty | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2024-09-06 | 2024-09-03 | 2024-09-19 | 10 |  |  | DF /F /70/BDV | BDV LUB/MAINT- DFF | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 2 | 0 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-10-09 | 2024-02-21 | 10 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 8 | 8 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-06-03 | 2024-06-03 | 2023-10-09 | 2024-02-21 | 20 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 16 | 0 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-10-09 | 2024-02-21 | 21 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-RIGG | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 10 | 0 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-10-09 | 2024-02-21 | 25 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 2 | 0 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-10-09 | 2024-02-21 | 30 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 1 | 0 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-10-09 | 2024-02-21 | 40 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100096908 | IP/HP-FF Starter rpm. below 2000 | Replace starter - Mech | PCNF | PCNF | 0 | 0 | W25-W26 | 2024-06-02 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-10-09 | 2024-02-21 | 50 | PCNF | PCNF | DF /F /31/DFFA-P-4301 | Replace starter - Mech | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047992 | PSV-410540 downstream Bleed Vlvhandle co | Return data sheet back to onshore |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-04-23 | 2021-07-22 | 10 |  |  | DF /F /30/DFFA-PSV-410540 | Return data sheet back to onshore | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047992 | PSV-410540 downstream Bleed Vlvhandle co | Return data sheet back to onshore |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-04-23 | 2021-07-22 | 20 |  |  | DF /F /30/DFFA-PSV-410540 | Return data sheet back to onshore | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2022-12-05 | 2023-04-19 | 10 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2022-12-05 | 2023-04-19 | 20 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2022-12-05 | 2023-04-19 | 30 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2022-12-05 | 2023-04-19 | 40 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2022-12-05 | 2023-04-19 | 50 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2022-12-05 | 2023-04-19 | 60 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2022-12-05 | 2023-04-19 | 70 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100076858 | Change of batteries and condensator | Isolate - DFGA-AE-1740B LAUS WORK | SECE | SECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-18 | 2024-06-18 | 2024-06-18 | 2022-12-05 | 2023-04-19 | 80 | SECE | SECE | DF /G /05/DFGA-AE-1740 | Isolate - DFGA-AE-1740B LAUS WORK | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400316038 | 1Y PRIME MOVER DFGA-MD-6140 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-19 | 2024-09-25 | 2024-09-19 | 2024-09-19 | 2024-06-20 | 2024-07-20 | 10 | AWSC | AWSC | DF /G /78/DFGA-MD-6140 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400316038 | 1Y PRIME MOVER DFGA-MD-6140 | ISOLATION BY PRODUCTION | AWSC | AWSC | 30 | 0 | Empty | 2024-09-19 | 2024-09-25 | 2024-09-19 | 2024-09-23 | 2024-06-20 | 2024-07-20 | 20 | AWSC | AWSC | DF /G /78/DFGA-MD-6140 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400316038 | 1Y PRIME MOVER DFGA-MD-6140 | ISOLATION BY PRODUCTION | AWSC | AWSC | 8 | 0 | Empty | 2024-09-19 | 2024-09-25 | 2024-09-23 | 2024-09-25 | 2024-06-20 | 2024-07-20 | 30 | AWSC | AWSC | DF /G /78/DFGA-MD-6140 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400316038 | 1Y PRIME MOVER DFGA-MD-6140 | ISOLATION BY PRODUCTION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-19 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-06-20 | 2024-07-20 | 40 | AWSC | AWSC | DF /G /78/DFGA-MD-6140 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WGN | MTN-INST | MTN-TELE | 2200007847 | OT segregation: Investigation and cables | See mail for tasks | PCNF | PCNF | 25 | 8 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-09-08 | 2021-10-18 | 10 | PCNF | PCNF | DF /C /08 | See mail for tasks | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-CRAN | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 1 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2022-07-18 | 2022-07-29 | 2020-11-10 | 2021-04-09 | 10 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 36 | 9 | Empty | 2023-02-24 | 2023-02-27 | 2022-07-18 | 2022-07-27 | 2020-11-10 | 2021-04-09 | 20 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-CRAN | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 3 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2022-07-18 | 2022-07-29 | 2020-11-10 | 2021-04-09 | 25 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-CRAN | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 1 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2022-07-21 | 2022-07-29 | 2020-11-10 | 2021-04-09 | 30 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 1 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2023-02-24 | 2023-02-24 | 2020-11-10 | 2021-04-09 | 40 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 30 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2023-02-24 | 2023-02-26 | 2020-11-10 | 2021-04-09 | 50 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 1 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2023-02-26 | 2023-02-26 | 2020-11-10 | 2021-04-09 | 60 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 6 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2023-02-26 | 2023-02-27 | 2020-11-10 | 2021-04-09 | 70 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-CRAN | 2100036823 | DFFW/78: Replace protection grid top win | Replace protection grid top window cabin | PCNF | PCNF | 0 | 0 | Empty | 2023-02-24 | 2023-02-27 | 2023-02-24 | 2023-02-24 | 2020-11-10 | 2021-04-09 | 80 | PCNF | PCNF | DF /F /78/DFFA-A-6102 | Replace protection grid top window cabin | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235693 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR06 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR06-BA001 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235693 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR06 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR06-BA001 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235693 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR06 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR06-BA001 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235693 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR06 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR06-BA001 | DE-ISOLATION ELECTRICAL | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 0 | 2 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-03-05 | 2024-03-05 | 2024-04-04 | 2024-08-17 | 10 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 5 | 5 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-03-05 | 2024-03-05 | 2024-04-04 | 2024-08-17 | 20 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 24 | 60 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-03-05 | 2024-03-05 | 2024-04-04 | 2024-08-17 | 30 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 10 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-26 | 2024-08-28 | 2024-04-04 | 2024-08-17 | 40 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-28 | 2024-08-28 | 2024-04-04 | 2024-08-17 | 50 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 16 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-08-28 | 2024-09-01 | 2024-04-04 | 2024-08-17 | 60 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107715 | Earth Fault on DFG-CM-1203 | Shipping of refurbish. motor | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-01 | 2024-09-01 | 2024-09-01 | 2024-04-04 | 2024-08-17 | 70 | PCNF | PCNF | DF /G /09/DFGA-CM-1203 | Shipping of refurbish. motor | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235788 | 4Y 400V N-SWB MAINT-DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235788 | 4Y 400V N-SWB MAINT-DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235788 | 4Y 400V N-SWB MAINT-DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235788 | 4Y 400V N-SWB MAINT-DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802 | 400V N-SWB INSP-DFCI-N-1802 | Unknown
3 | DFA-O05 | WGN | MTN-MECH | PRODTECH | 2200003013 | DFA 05 Intern lækage i hydraulikskuf | L3 safing of DFAA-A-3102 | AWSCSCH | AWSCSCH | 3 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2024-12-31 | 2025-01-01 | 2018-03-02 | 2018-03-22 | 10 | AWSCSCH | AWSCSCH | DF /A /07/DFAA-A-3102 | L3 safing of DFAA-A-3102 | Unknown
3 | DFA-O05 | WGN | MTN-MECH | MTN-MECH | 2200003013 | DFA 05 Intern lækage i hydraulikskuf | L3 safing of DFAA-A-3102 | AWSCSCH | AWSCSCH | 3 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-03-02 | 2018-03-22 | 20 | AWSCSCH | AWSCSCH | DF /A /07/DFAA-A-3102 | L3 safing of DFAA-A-3102 | Unknown
3 | DFA-O05 | WGN | MTN-MECH | PRODTECH | 2200003013 | DFA 05 Intern lækage i hydraulikskuf | L3 safing of DFAA-A-3102 | AWSCSCH | AWSCSCH | 3 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2018-03-02 | 2018-03-22 | 30 | AWSCSCH | AWSCSCH | DF /A /07/DFAA-A-3102 | L3 safing of DFAA-A-3102 | Unknown
3 | DFA-O05 | WGN | MTN-MECH | MTN-MECH | 2200003013 | DFA 05 Intern lækage i hydraulikskuf | L3 safing of DFAA-A-3102 | AWSCSCH | AWSCSCH | 1 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2018-03-02 | 2018-03-22 | 35 | AWSCSCH | AWSCSCH | DF /A /07/DFAA-A-3102 | L3 safing of DFAA-A-3102 | Unknown
3 | DFA-O05 | WGN | MTN-MECH | MTN-MECH | 2200003013 | DFA 05 Intern lækage i hydraulikskuf | L3 safing of DFAA-A-3102 | AWSCSCH | AWSCSCH | 1 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2018-03-02 | 2018-03-22 | 40 | AWSCSCH | AWSCSCH | DF /A /07/DFAA-A-3102 | L3 safing of DFAA-A-3102 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087415 | Turbo Pressure and exhaust gauge defecti | Isolate DFFA-GM-1751 - EIA |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-10 | 2024-08-11 | 2023-09-10 | 2026-02-26 | 10 |  |  | DF /F /05/DFFA-GM-1751 | Isolate DFFA-GM-1751 - EIA | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100087415 | Turbo Pressure and exhaust gauge defecti | Isolate DFFA-GM-1751 - EIA |  |  | 4 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-11 | 2024-08-12 | 2023-09-10 | 2026-02-26 | 20 |  |  | DF /F /05/DFFA-GM-1751 | Isolate DFFA-GM-1751 - EIA | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100087415 | Turbo Pressure and exhaust gauge defecti | Isolate DFFA-GM-1751 - EIA |  |  | 15 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2023-09-10 | 2026-02-26 | 30 |  |  | DF /F /05/DFFA-GM-1751 | Isolate DFFA-GM-1751 - EIA | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100087415 | Turbo Pressure and exhaust gauge defecti | Isolate DFFA-GM-1751 - EIA |  |  | 4 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2023-09-10 | 2026-02-26 | 40 |  |  | DF /F /05/DFFA-GM-1751 | Isolate DFFA-GM-1751 - EIA | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100087415 | Turbo Pressure and exhaust gauge defecti | Isolate DFFA-GM-1751 - EIA |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2023-09-10 | 2026-02-26 | 50 |  |  | DF /F /05/DFFA-GM-1751 | Isolate DFFA-GM-1751 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 6 | 2 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 10 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 12 | 12 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 20 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 18 | 18 | W25-26 | 2022-01-29 | 2023-10-22 | 2023-10-09 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 22 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 12 | 34 | W25-26 | 2022-01-29 | 2023-10-22 | 2023-10-09 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 25 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 18 | 10 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 30 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 48 | 48 | W25-26 | 2022-01-29 | 2023-10-22 | 2023-10-09 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 35 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 24 | 24 | W25-26 | 2022-01-29 | 2023-10-22 | 2023-10-09 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 38 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 48 | 45 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 40 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 6 | 2 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 50 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-TURB | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 0 | 0 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 60 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-TURB | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 0 | 20 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 70 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-TURB | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 0 | 0 | W25-26 | 2022-01-29 | 2023-10-22 | 2023-10-22 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 80 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-TURB | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 0 | 0 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-29 | 2022-01-29 | 2021-07-07 | 2021-07-12 | 90 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 0 | 0 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-29 | 2023-10-22 | 2021-07-07 | 2021-07-12 | 100 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 6 | 0 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-29 | 2022-01-29 | 2021-07-07 | 2021-07-12 | 110 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100053939 | Exhaust leak af DFE FWP | order new binding wire | SCH | SCH | 6 | 30 | W25-26 | 2022-01-29 | 2023-10-22 | 2022-01-30 | 2022-01-31 | 2021-07-07 | 2021-07-12 | 120 | SCH | SCH | DF /E /01/DFEY-DM-0320 | order new binding wire | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107879 | Change of defect MCB Q14 | operation_description_not_present |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-08-10 | 2027-01-27 | 10 |  |  | DF /F /61/DFFB-N-1831-06-01 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107879 | Change of defect MCB Q14 | operation_description_not_present |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-08-10 | 2027-01-27 | 20 |  |  | DF /F /61/DFFB-N-1831-06-01 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107879 | Change of defect MCB Q14 | operation_description_not_present |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-08-10 | 2027-01-27 | 30 |  |  | DF /F /61/DFFB-N-1831-06-01 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100107879 | Change of defect MCB Q14 | operation_description_not_present |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-10 | 2027-01-27 | 40 |  |  | DF /F /61/DFFB-N-1831-06-01 | operation_description_not_present | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235766 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-03 | 380V N-SWB INSP-DFEZ-N-1803-03 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-03B1 | 380V N-SWB INSP-DFEZ-N-1803-03 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235766 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-03 | 380V N-SWB INSP-DFEZ-N-1803-03 | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-03B1 | 380V N-SWB INSP-DFEZ-N-1803-03 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235766 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-03 | 380V N-SWB INSP-DFEZ-N-1803-03 | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-03B1 | 380V N-SWB INSP-DFEZ-N-1803-03 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235766 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-03 | 380V N-SWB INSP-DFEZ-N-1803-03 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-03B1 | 380V N-SWB INSP-DFEZ-N-1803-03 | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003037 | Isolation assists FORCE 9077 | L3 Force insp | PCNF | PCNF | 8.699999999999999289457264236 | 5 | Empty | 2020-10-22 | 2021-01-12 | 2020-10-14 | 2020-10-19 | 2018-12-27 | 2019-03-27 | 10 | PCNF | PCNF | DF /F /53/P-G | L3 Force insp | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003037 | Isolation assists FORCE 9077 | L3 Force insp | PCNF | PCNF | 6.700000000000000177635683938 | 0 | Empty | 2020-10-22 | 2021-01-12 | 2020-10-19 | 2020-10-19 | 2018-12-27 | 2019-03-27 | 30 | PCNF | PCNF | DF /F /53/P-G | L3 Force insp | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003037 | Isolation assists FORCE 9077 | L3 Force insp | PCNF | PCNF | 5 | 0 | Empty | 2020-10-22 | 2021-01-12 | 2020-10-22 | 2020-10-23 | 2018-12-27 | 2019-03-27 | 40 | PCNF | PCNF | DF /F /53/P-G | L3 Force insp | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003037 | Isolation assists FORCE 9077 | L3 Force insp | PCNF | PCNF | 5.4000000000000003552713678785 | 9.5 | Empty | 2020-10-22 | 2021-01-12 | 2020-10-16 | 2021-01-12 | 2018-12-27 | 2019-03-27 | 50 | PCNF | PCNF | DF /F /53/P-G | L3 Force insp | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100103978 | Pin hole in valve WHS-03202 | Isolate firehydant | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-12-21 | 2024-02-04 | 10 | SECE | SECE | DF /G /01/DFGA-WHS-03202 | Isolate firehydant | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100103978 | Pin hole in valve WHS-03202 | Isolate firehydant | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-12-21 | 2024-02-04 | 20 | SECE | SECE | DF /G /01/DFGA-WHS-03202 | Isolate firehydant | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100103978 | Pin hole in valve WHS-03202 | Isolate firehydant | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-12-21 | 2024-02-04 | 30 | SECE | SECE | DF /G /01/DFGA-WHS-03202 | Isolate firehydant | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 10 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 20 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 30 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 6 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 40 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 50 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 60 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100022728 | ANOP Missing support on LP manifold | Missing support on LP manifold |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2019-04-15 | 2019-07-14 | 70 |  |  | DF /C /25 | Missing support on LP manifold | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 13 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 5 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 24 | 10 | Empty | 2024-09-15 | 2024-09-22 | 2021-08-06 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 10 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 8 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 20 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 25 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 24 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 30 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 8 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 40 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 50 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 12 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 60 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 70 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 75 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 80 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 8 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 90 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 30 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 100 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 110 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 18 | 10 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-11-15 | 2019-08-01 | 2019-08-21 | 120 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2021-09-13 | 2021-09-13 | 2019-08-01 | 2019-08-21 | 130 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022493 | Spool til monitor wm-0343 er extern utæt | Permit and preparation | PCNF | PCNF | 60 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-22 | 2019-08-01 | 2019-08-21 | 140 | PCNF | PCNF | DF /B /01/DFBA-WM-0343 | Permit and preparation | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 0 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 25 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 27 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 5 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 4 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
A | DFF-3580 | WPM | MTN-MECH | VEN-INSP | 2400284283 | PSV Exchange - DFFB-PSV-358016 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /54/DFFB-PSV-358016 | Remove PSV and Install blinds | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235841 | 4Y 400V E-SWB MAINT DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235841 | 4Y 400V E-SWB MAINT DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | AWSC | AWSC | 24 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235841 | 4Y 400V E-SWB MAINT DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235841 | 4Y 400V E-SWB MAINT DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A03 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076957 | gear defective on HCV-530136, is removed | Mount new gearbox |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-12-09 | 2023-04-23 | 10 |  |  | DF /F /76/DFFA-HCV-530136 | Mount new gearbox | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087259 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /G /05/DFGA-LP-1852-41 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087259 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /G /05/DFGA-LP-1852-41 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087259 | Battery fault on emergency light | Isolate and prove dead. |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /G /05/DFGA-LP-1852-41 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087259 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /G /05/DFGA-LP-1852-41 | Isolate and prove dead. | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-MECH | 2100024624 | DFFA-LG-410014 Replace of valves on leve | Replace of valves on level glass | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 10 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-V-4101 | Replace of valves on level glass | Unknown
3 | D-FLARE | WDF | MTN-MECH | PRODTECH | 2100024624 | DFFA-LG-410014 Replace of valves on leve | Replace of valves on level glass | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 20 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-V-4101 | Replace of valves on level glass | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-MECH | 2100024624 | DFFA-LG-410014 Replace of valves on leve | Replace of valves on level glass | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 30 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-V-4101 | Replace of valves on level glass | Unknown
3 | D-FLARE | WDF | MTN-MECH | PRODTECH | 2100024624 | DFFA-LG-410014 Replace of valves on leve | Replace of valves on level glass | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 40 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-V-4101 | Replace of valves on level glass | Unknown
3 | D-FLARE | WDF | MTN-MECH | MTN-SCAF | 2100024624 | DFFA-LG-410014 Replace of valves on leve | Replace of valves on level glass | PCNFAWSC | PCNFAWSC | 10 | 12 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-06-30 | 2019-09-28 | 50 | PCNFAWSC | PCNFAWSC | DF /F /30/DFFA-V-4101 | Replace of valves on level glass | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100044253 | DFC LEVEL 1. DFC-XCV-50360 SIDDER FAST | Increase of PO 4500035297 | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50360 | Increase of PO 4500035297 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100044253 | DFC LEVEL 1. DFC-XCV-50360 SIDDER FAST | Increase of PO 4500035297 | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50360 | Increase of PO 4500035297 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100044253 | DFC LEVEL 1. DFC-XCV-50360 SIDDER FAST | Increase of PO 4500035297 | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-05 | 2022-05-01 | 30 | AWSC | AWSC | DF /C /27/DFCM-XCV-50360 | Increase of PO 4500035297 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100044253 | DFC LEVEL 1. DFC-XCV-50360 SIDDER FAST | Increase of PO 4500035297 | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2021-07-05 | 2022-05-01 | 40 | AWSC | AWSC | DF /C /27/DFCM-XCV-50360 | Increase of PO 4500035297 | Unknown
3 | DHDLPGAS | WGN | MTN-INST | PRODTECH | 2200003227 | CMAT:DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2017-12-29 | 2018-03-29 | 10 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380140 | Mount PRV on ESDV control panel | Unknown
3 | DHDLPGAS | WGN | MTN-INST | MTN-INST | 2200003227 | CMAT:DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-04 | 2017-12-29 | 2018-03-29 | 20 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380140 | Mount PRV on ESDV control panel | Unknown
3 | DHDLPGAS | WGN | MTN-INST | PRODTECH | 2200003227 | CMAT:DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2017-12-29 | 2018-03-29 | 30 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380140 | Mount PRV on ESDV control panel | Unknown
3 | DHDLPGAS | WGN | MTN-INST | MTN-INST | 2200003227 | CMAT:DFG Mount PRV on ESDV control panel | Mount PRV on ESDV control panel | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2017-12-29 | 2018-03-29 | 40 | AWSC | AWSC | DF /G /34/DFGA-ESDV-380140 | Mount PRV on ESDV control panel | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400342423 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-9 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 27 | 0 | Empty | 2024-06-29 | 2024-06-30 | 2024-06-29 | 2024-06-30 | 2024-06-29 | 2024-08-30 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-9 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-06-24 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 10 | Empty | 2024-08-12 | 2024-08-13 | 2024-06-25 | 2024-06-27 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284232 | PSV Calibration - DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /B /70/DFBA-PSV-57037 | DFGA-PSV-57037 Offshore from WS Måde | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400342406 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3804 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-09-03 | 10 |  |  | DF /F /54/DFFA-EP-3804 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400342406 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3804 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-09-03 | 20 |  |  | DF /F /54/DFFA-EP-3804 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342406 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3804 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-09-03 | 30 |  |  | DF /F /54/DFFA-EP-3804 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400342406 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3804 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-04 | 2024-09-03 | 40 |  |  | DF /F /54/DFFA-EP-3804 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044101 | DFFA-P-4101 Bleed ventiler blokkeret /si | Isolate bleed valves f/DFFA-P-4101 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2021-04-04 | 2021-09-01 | 10 |  |  | DF /F /30/DFFA-P-4101 | Isolate bleed valves f/DFFA-P-4101 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044101 | DFFA-P-4101 Bleed ventiler blokkeret /si | Isolate bleed valves f/DFFA-P-4101 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2021-04-04 | 2021-09-01 | 20 |  |  | DF /F /30/DFFA-P-4101 | Isolate bleed valves f/DFFA-P-4101 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044101 | DFFA-P-4101 Bleed ventiler blokkeret /si | Isolate bleed valves f/DFFA-P-4101 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2021-04-04 | 2021-09-01 | 30 |  |  | DF /F /30/DFFA-P-4101 | Isolate bleed valves f/DFFA-P-4101 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044101 | DFFA-P-4101 Bleed ventiler blokkeret /si | Isolate bleed valves f/DFFA-P-4101 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2021-04-04 | 2021-09-01 | 40 |  |  | DF /F /30/DFFA-P-4101 | Isolate bleed valves f/DFFA-P-4101 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100087419 | Biocide inj tubing weeping (INST-TUBF) | Isolate Biocide injection/drain lines |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2023-08-04 | 2023-10-01 | 10 |  |  | DF /F /75/DFF-0.75-CB-039-9103-XX-U | Isolate Biocide injection/drain lines | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100087419 | Biocide inj tubing weeping (INST-TUBF) | Isolate Biocide injection/drain lines |  |  | 1.5 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2023-08-04 | 2023-10-01 | 20 |  |  | DF /F /75/DFF-0.75-CB-039-9103-XX-U | Isolate Biocide injection/drain lines | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100087419 | Biocide inj tubing weeping (INST-TUBF) | Isolate Biocide injection/drain lines |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2023-08-04 | 2023-10-01 | 30 |  |  | DF /F /75/DFF-0.75-CB-039-9103-XX-U | Isolate Biocide injection/drain lines | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100087419 | Biocide inj tubing weeping (INST-TUBF) | Isolate Biocide injection/drain lines |  |  | 1.5 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-08-04 | 2023-10-01 | 40 |  |  | DF /F /75/DFF-0.75-CB-039-9103-XX-U | Isolate Biocide injection/drain lines | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100087419 | Biocide inj tubing weeping (INST-TUBF) | Isolate Biocide injection/drain lines |  |  | 0.5 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-08-04 | 2023-10-01 | 50 |  |  | DF /F /75/DFF-0.75-CB-039-9103-XX-U | Isolate Biocide injection/drain lines | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024811 | SMAT:CHNG out MCB&swich DFCI-N-1811-01-0 | L3 Isolate DFCI-N-1811 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2018-12-17 | 2019-05-16 | 10 |  |  | DF /C /05/DFCI-N-1811-01-01 | L3 Isolate DFCI-N-1811 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100024811 | SMAT:CHNG out MCB&swich DFCI-N-1811-01-0 | L3 Isolate DFCI-N-1811 |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2018-12-17 | 2019-05-16 | 20 |  |  | DF /C /05/DFCI-N-1811-01-01 | L3 Isolate DFCI-N-1811 | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100024811 | SMAT:CHNG out MCB&swich DFCI-N-1811-01-0 | L3 Isolate DFCI-N-1811 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2018-12-17 | 2019-05-16 | 30 |  |  | DF /C /05/DFCI-N-1811-01-01 | L3 Isolate DFCI-N-1811 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400337277 | 6M CRANE HOIST EQUIP, DFA | CRANE HOIST EQUIP, DFA |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-10-13 | 2024-11-01 | 10 |  |  | DF /A /78/DFA-LIFTING | CRANE HOIST EQUIP, DFA | Unknown
2 | DFB-W04 | WDF | MTN-INST | MTN-INST | 2100092305 | FB-04 Hydrailic drawer missing | install FB-04 Hydrailic drawer |  |  | 8 | 0 | Empty | 2024-08-22 | 2024-08-23 | 2024-08-22 | 2024-08-23 | 2023-06-09 | 2023-07-24 | 10 |  |  | DF /B /07/DFBA-A-3101 | install FB-04 Hydrailic drawer | Unknown
2 | NE | WRO | MTN-TELE | MTN-TELE | 2300004309 | MB300 MAU test 100MBit FO to 10MBit AUI | MB300 MAU test 100MBit FO to 10MBit AUI |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-12-06 | 2023-01-20 | 10 |  |  | DF /C /04 | MB300 MAU test 100MBit FO to 10MBit AUI | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400290947 | 1Y SEAWATER FILT PKG MAINT-DFFB-A-3550 | SEAWATER FILT PKG MAINT-DFFB-A-3550 |  |  | 4 | 0 | W25-W26 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-10-24 | 2023-11-29 | 10 |  |  | DF /F /51/DFFB-A-3550 | SEAWATER FILT PKG MAINT-DFFB-A-3550 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400290947 | 1Y SEAWATER FILT PKG MAINT-DFFB-A-3550 | SEAWATER FILT PKG MAINT-DFFB-A-3550 |  |  | 4 | 0 | W25-W26 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-10-24 | 2023-11-29 | 20 |  |  | DF /F /51/DFFB-A-3550 | SEAWATER FILT PKG MAINT-DFFB-A-3550 | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-06-14 | 2024-06-14 | 2024-10-19 | 2024-12-31 | 10 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-06-14 | 2024-06-14 | 2024-10-19 | 2024-12-31 | 20 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-RIGG | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 24 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-06-14 | 2024-06-16 | 2024-10-19 | 2024-12-31 | 30 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 5 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-06-15 | 2024-06-16 | 2024-10-19 | 2024-12-31 | 40 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-06-16 | 2024-06-16 | 2024-10-19 | 2024-12-31 | 50 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-06-16 | 2024-06-17 | 2024-10-19 | 2024-12-31 | 60 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-RIGG | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 12 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2024-10-19 | 2024-12-31 | 70 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2024-10-19 | 2024-12-31 | 80 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 5 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2024-10-19 | 2024-12-31 | 90 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2024-10-19 | 2024-12-31 | 100 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2024-10-19 | 2024-12-31 | 110 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
A | DFF-3580 | WPM | MTN-MECH | VEN-INSP | 2400284282 | PSV Exchange - DFFB-PSV-358007 | Isolation of PSV | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-14 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2024-10-19 | 2024-12-31 | 120 | AWSCSCH | AWSCSCH | DF /F /54/DFFB-PSV-358007 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024119 | SMAT:REPL vlv and gasket DFC E-53333(In | L3 Erect scaffold for reacing T-part | PCNF | PCNF | 24 | 24 | W7? | 2024-09-15 | 2024-09-17 | 2020-07-19 | 2020-07-19 | 2019-01-05 | 2019-04-05 | 10 | PCNF | PCNF | DF /C /76 | L3 Erect scaffold for reacing T-part | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024119 | SMAT:REPL vlv and gasket DFC E-53333(In | L3 Erect scaffold for reacing T-part | PCNF | PCNF | 3 | 0 | W7? | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2019-01-05 | 2019-04-05 | 20 | PCNF | PCNF | DF /C /76 | L3 Erect scaffold for reacing T-part | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024119 | SMAT:REPL vlv and gasket DFC E-53333(In | L3 Erect scaffold for reacing T-part | PCNF | PCNF | 19 | 19 | W7? | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2019-01-05 | 2019-04-05 | 30 | PCNF | PCNF | DF /C /76 | L3 Erect scaffold for reacing T-part | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024119 | SMAT:REPL vlv and gasket DFC E-53333(In | L3 Erect scaffold for reacing T-part | PCNF | PCNF | 3 | 0 | W7? | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2019-01-05 | 2019-04-05 | 40 | PCNF | PCNF | DF /C /76 | L3 Erect scaffold for reacing T-part | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024119 | SMAT:REPL vlv and gasket DFC E-53333(In | L3 Erect scaffold for reacing T-part | PCNF | PCNF | 16 | 16 | W7? | 2024-09-15 | 2024-09-17 | 2020-07-19 | 2020-07-19 | 2019-01-05 | 2019-04-05 | 50 | PCNF | PCNF | DF /C /76 | L3 Erect scaffold for reacing T-part | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400351951 | 1Y F&G SHOP CONT. ROOF DECK CHECK - DFF | F&G SHOP CONT. ROOF DECK CHECK - DFF | SECE | SECE | 8 | 0 | Empty | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2024-09-19 | 2024-10-19 | 10 | SECE | SECE | DF /F /03/VISUAL-AUDIBLE-ALARM | F&G SHOP CONT. ROOF DECK CHECK - DFF | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-01-01 | 2021-04-01 | 10 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 16 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2021-01-01 | 2021-04-01 | 20 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-24 | 2024-09-24 | 2021-01-01 | 2021-04-01 | 30 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-24 | 2021-01-01 | 2021-04-01 | 40 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-24 | 2024-09-25 | 2021-01-01 | 2021-04-01 | 50 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-25 | 2024-09-25 | 2021-01-01 | 2021-04-01 | 60 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-ROPE | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2021-01-01 | 2021-04-01 | 70 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2021-01-01 | 2021-04-01 | 80 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-01-01 | 2021-04-01 | 90 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
3 | DFFLPSEP | WDF | MTN-MECH | MTN-INST | 2100042481 | ESD Afspæringsventil DFF-LIT-340108 | arlie | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2021-01-01 | 2021-04-01 | 100 | AWSC | AWSC | DF /F /20/DFFA-LIT-340108 | arlie | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400290934 | 6M PRIME MOVER DFFA-MD-6101 | order oil fill cover |  |  | 18 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2024-03-13 | 2024-03-29 | 10 |  |  | DF /F /78/DFFA-MD-6101 | order oil fill cover | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400290934 | 6M PRIME MOVER DFFA-MD-6101 | order oil fill cover |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-03-13 | 2024-03-29 | 20 |  |  | DF /F /78/DFFA-MD-6101 | order oil fill cover | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057918 | Change Socketoutlet DFCI-SO-1808-24L3A | Prove circuit is dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-23 | 2022-02-21 | 10 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057918 | Change Socketoutlet DFCI-SO-1808-24L3A | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-23 | 2022-02-21 | 20 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057918 | Change Socketoutlet DFCI-SO-1808-24L3A | Prove circuit is dead |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-11-23 | 2022-02-21 | 30 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057918 | Change Socketoutlet DFCI-SO-1808-24L3A | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-11-23 | 2022-02-21 | 40 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057918 | Change Socketoutlet DFCI-SO-1808-24L3A | Prove circuit is dead |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-23 | 2022-02-21 | 50 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 2 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-08-09 | 2024-08-09 | 2024-03-30 | 2024-04-29 | 10 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 72 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-08-09 | 2024-08-18 | 2024-03-30 | 2024-04-29 | 20 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 12 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-08-18 | 2024-08-21 | 2024-03-30 | 2024-04-29 | 30 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 2 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-08-21 | 2024-08-21 | 2024-03-30 | 2024-04-29 | 40 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 24 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-08-22 | 2024-08-27 | 2024-03-30 | 2024-04-29 | 50 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 24 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-08-28 | 2024-09-02 | 2024-03-30 | 2024-04-29 | 60 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-SCAF | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 12 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-09-03 | 2024-09-05 | 2024-03-30 | 2024-04-29 | 70 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 12 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-09-06 | 2024-09-08 | 2024-03-30 | 2024-04-29 | 80 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 16 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-09-09 | 2024-09-12 | 2024-03-30 | 2024-04-29 | 90 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400302333 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6102 | Minor scaf for access | AWSC | AWSC | 0 | 0 | Empty | 2024-08-09 | 2024-09-12 | 2024-09-12 | 2024-09-12 | 2024-03-30 | 2024-04-29 | 100 | AWSC | AWSC | DF /F /78/DFFA-A-6102 | Minor scaf for access | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009225 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /C /27/DFC-6-WOS-050-9035-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009225 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /C /27/DFC-6-WOS-050-9035-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009225 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2024-01-11 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /C /27/DFC-6-WOS-050-9035-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009225 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-11 | 2024-01-12 | 2022-02-08 | 2022-07-08 | 32 |  |  | DF /C /27/DFC-6-WOS-050-9035-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009225 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-12 | 2024-01-16 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /C /27/DFC-6-WOS-050-9035-AB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009225 | Insulation assits FORCE 14246 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-16 | 2024-01-18 | 2022-02-08 | 2022-07-08 | 50 |  |  | DF /C /27/DFC-6-WOS-050-9035-AB-U | Bilfinger inspection | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235673 | 4Y 380V N-SWB MAINT-DFCI-N-1822-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1822-2A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235673 | 4Y 380V N-SWB MAINT-DFCI-N-1822-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1822-2A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235673 | 4Y 380V N-SWB MAINT-DFCI-N-1822-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1822-2A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235673 | 4Y 380V N-SWB MAINT-DFCI-N-1822-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1822-2A01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100077768 | Deluge nozzle replace/clean/adjust | DFC, Deluge nozzle acc to attach | PCNFSCH | PCNFSCH | 18 | 6 | W41-42 | 2023-10-09 | 2023-10-10 | 2023-10-09 | 2023-10-09 | 2022-12-23 | 2023-05-07 | 10 | PCNFSCH | PCNFSCH | DF /C /01 | DFC, Deluge nozzle acc to attach | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100077768 | Deluge nozzle replace/clean/adjust | DFC, Deluge nozzle acc to attach | PCNFSCH | PCNFSCH | 36 | 6 | W41-42 | 2023-10-09 | 2023-10-10 | 2023-10-09 | 2023-10-09 | 2022-12-23 | 2023-05-07 | 20 | PCNFSCH | PCNFSCH | DF /C /01 | DFC, Deluge nozzle acc to attach | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100077768 | Deluge nozzle replace/clean/adjust | DFC, Deluge nozzle acc to attach | PCNFSCH | PCNFSCH | 30 | 6 | W41-42 | 2023-10-09 | 2023-10-10 | 2023-10-09 | 2023-10-09 | 2022-12-23 | 2023-05-07 | 30 | PCNFSCH | PCNFSCH | DF /C /01 | DFC, Deluge nozzle acc to attach | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100077768 | Deluge nozzle replace/clean/adjust | DFC, Deluge nozzle acc to attach | PCNFSCH | PCNFSCH | 9 | 6 | W41-42 | 2023-10-09 | 2023-10-10 | 2023-10-09 | 2023-10-09 | 2022-12-23 | 2023-05-07 | 40 | PCNFSCH | PCNFSCH | DF /C /01 | DFC, Deluge nozzle acc to attach | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100077768 | Deluge nozzle replace/clean/adjust | DFC, Deluge nozzle acc to attach | PCNFSCH | PCNFSCH | 12 | 0 | W41-42 | 2023-10-09 | 2023-10-10 | 2023-10-09 | 2023-10-10 | 2022-12-23 | 2023-05-07 | 50 | PCNFSCH | PCNFSCH | DF /C /01 | DFC, Deluge nozzle acc to attach | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 24 | 24 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 10 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 12 | 12 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 20 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 3 | 3 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 30 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 12 | 31 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 40 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 4 | 4 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 50 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 8 | 10 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 60 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 4 | 3 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 70 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 8 | 8 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 80 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 12 | 25 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 90 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 16 | 12 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 100 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 8 | 8 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 110 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 8 | 8 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 120 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 4 | 4 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 130 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 12 | 22 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 140 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 4 | 3 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 150 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 3 | 3 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 160 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 2 | 2 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 170 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 10 | 10 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 180 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 18 | 36 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 190 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 2 | 2 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-19 | 2023-07-24 | 2023-02-18 | 2023-04-04 | 200 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085817 | DFF-FT-5310 filter element do not drive | Rigger Assist/Prep. & Lifting out/in | SCH | SCH | 0 | 0 | W29-30 | 2023-07-17 | 2023-07-24 | 2023-07-24 | 2023-07-24 | 2023-02-18 | 2023-04-04 | 210 | SCH | SCH | DF /F /51/DFFA-FT-5310 | Rigger Assist/Prep. & Lifting out/in | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077774 | DFC LB3 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-09 | 2025-10-25 | 10 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077774 | DFC LB3 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 20 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077774 | DFC LB3 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 30 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077774 | DFC LB3 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 35 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat in maintenance wires | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100077774 | DFC LB3 replace foundation bolts | Isolate lifeboat in maintenance wires |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 40 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat in maintenance wires | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-SCAF | 2100022631 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | AWSC | AWSC | 6 | 0 | w18-19? | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2019-05-26 | 2019-10-23 | 10 | AWSC | AWSC | DF /C /11/DFCI-ESDV-34009 | L3 Remove rigging equipment | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | PRODTECH | 2100022631 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | AWSC | AWSC | 4 | 0 | w18-19? | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2019-05-26 | 2019-10-23 | 20 | AWSC | AWSC | DF /C /11/DFCI-ESDV-34009 | L3 Remove rigging equipment | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100022631 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | AWSC | AWSC | 4 | 0 | w18-19? | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2019-05-26 | 2019-10-23 | 30 | AWSC | AWSC | DF /C /11/DFCI-ESDV-34009 | L3 Remove rigging equipment | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-RIGG | 2100022631 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | AWSC | AWSC | 4 | 0 | w18-19? | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2019-05-26 | 2019-10-23 | 40 | AWSC | AWSC | DF /C /11/DFCI-ESDV-34009 | L3 Remove rigging equipment | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100022631 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | AWSC | AWSC | 4 | 0 | w18-19? | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2019-05-26 | 2019-10-23 | 50 | AWSC | AWSC | DF /C /11/DFCI-ESDV-34009 | L3 Remove rigging equipment | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-RIGG | 2100022631 | Exchange actuator ESDV-34009 | L3 Remove rigging equipment | AWSC | AWSC | 4 | 0 | w18-19? | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2019-05-26 | 2019-10-23 | 60 | AWSC | AWSC | DF /C /11/DFCI-ESDV-34009 | L3 Remove rigging equipment | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341924 | DFG_1Y_42000 INT STRUCT INSP - GVI | DFG_1Y_42000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/EL_42000 (MEZZANINE DECK) | DFG_1Y_42000 INT STRUCT INSP - GVI | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400232966 | 1Y DEMULSIFIER SKID MAINT - DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-01-28 | 2023-02-27 | 10 |  |  | DF /F /75/DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400232966 | 1Y DEMULSIFIER SKID MAINT - DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 |  |  | 7 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2023-01-28 | 2023-02-27 | 20 |  |  | DF /F /75/DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400232966 | 1Y DEMULSIFIER SKID MAINT - DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-01-28 | 2023-02-27 | 30 |  |  | DF /F /75/DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400232966 | 1Y DEMULSIFIER SKID MAINT - DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-01-28 | 2023-02-27 | 40 |  |  | DF /F /75/DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018139 | Replace Motor protection 1841-M116 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M116-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018139 | Replace Motor protection 1841-M116 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M116-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018139 | Replace Motor protection 1841-M116 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M116-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018139 | Replace Motor protection 1841-M116 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M116-02 | New mat num | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346563 | 1Y DELUGE SKIDS, SMOKE TEST-DFB | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /B /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346563 | 1Y DELUGE SKIDS, SMOKE TEST-DFB | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /B /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346563 | 1Y DELUGE SKIDS, SMOKE TEST-DFB | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /B /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346563 | 1Y DELUGE SKIDS, SMOKE TEST-DFB | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /B /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346563 | 1Y DELUGE SKIDS, SMOKE TEST-DFB | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-18 | 2024-08-17 | 2024-08-18 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /B /01/DELUGE-SKIDS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400325770 | 1Y INST AIR SYSTEM MAINT- DFGA-A-5453/54 | INST AIR SYSTEM MAINT- DFGA-A-5453/54 | SECE | SECE | 4 | 0 | W21-W22 | 2024-05-20 | 2024-05-22 | 2024-05-20 | 2024-05-21 | 2024-04-30 | 2024-05-30 | 10 | SECE | SECE | DF /G /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYSTEM MAINT- DFGA-A-5453/54 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325770 | 1Y INST AIR SYSTEM MAINT- DFGA-A-5453/54 | INST AIR SYSTEM MAINT- DFGA-A-5453/54 | SECE | SECE | 6 | 0 | W21-W22 | 2024-05-20 | 2024-05-22 | 2024-05-21 | 2024-05-22 | 2024-04-30 | 2024-05-30 | 20 | SECE | SECE | DF /G /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYSTEM MAINT- DFGA-A-5453/54 | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100085214 | DAB ESDV inlet to DFF HP-sep F.T.C. | DAB ESDV inlet to DFF HP-sep F.T.C. | SECE | SECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-28 | 2023-08-10 | 10 | SECE | SECE | DF /F /23/DFFA-ESDV-380216 | DAB ESDV inlet to DFF HP-sep F.T.C. | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100085214 | DAB ESDV inlet to DFF HP-sep F.T.C. | DAB ESDV inlet to DFF HP-sep F.T.C. | SECE | SECE | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-28 | 2023-08-10 | 20 | SECE | SECE | DF /F /23/DFFA-ESDV-380216 | DAB ESDV inlet to DFF HP-sep F.T.C. | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100085214 | DAB ESDV inlet to DFF HP-sep F.T.C. | DAB ESDV inlet to DFF HP-sep F.T.C. | SECE | SECE | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-28 | 2023-08-10 | 30 | SECE | SECE | DF /F /23/DFFA-ESDV-380216 | DAB ESDV inlet to DFF HP-sep F.T.C. | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339272 | DFF_1Y_30250 INT STRUCT INSP - GVI | DFF_1Y_30250 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_30250 (WH ACCES PF) | DFF_1Y_30250 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077618 | Findning RA-01 1Y insp helifuel. | Isolate heli fuel system | PCNFSCH | PCNFSCH | 2 | 0 | W27-W28 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-15 | 2023-04-30 | 2025-10-16 | 20 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077618 | Findning RA-01 1Y insp helifuel. | Isolate heli fuel system | PCNFSCH | PCNFSCH | 4 | 0 | W27-W28 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-04-30 | 2025-10-16 | 30 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077618 | Findning RA-01 1Y insp helifuel. | Isolate heli fuel system | PCNFSCH | PCNFSCH | 4 | 0 | W27-W28 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-04-30 | 2025-10-16 | 40 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077618 | Findning RA-01 1Y insp helifuel. | Isolate heli fuel system | PCNFSCH | PCNFSCH | 2 | 0 | W27-W28 | 2024-07-15 | 2024-07-17 | 2024-07-16 | 2024-07-17 | 2023-04-30 | 2025-10-16 | 50 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate heli fuel system | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100064128 | Deluge XCV-3010. Sov and splitter leak | material |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-06-23 | 2023-02-18 | 10 |  |  | DF /E /01/DFEZ-XCV-03010 | material | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064128 | Deluge XCV-3010. Sov and splitter leak | material |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-23 | 2023-02-18 | 40 |  |  | DF /E /01/DFEZ-XCV-03010 | material | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100064128 | Deluge XCV-3010. Sov and splitter leak | material |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-23 | 2023-02-18 | 50 |  |  | DF /E /01/DFEZ-XCV-03010 | material | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100064128 | Deluge XCV-3010. Sov and splitter leak | material |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-06-23 | 2023-02-18 | 60 |  |  | DF /E /01/DFEZ-XCV-03010 | material | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064128 | Deluge XCV-3010. Sov and splitter leak | material |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-06-23 | 2023-02-18 | 70 |  |  | DF /E /01/DFEZ-XCV-03010 | material | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269628 | 6M BDV LUB/INSP IPHP - DFF | BDV LUB/MAINT IPHP - DFF |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-08-12 | 2023-08-28 | 10 |  |  | DF /F /30/BDV | BDV LUB/MAINT IPHP - DFF | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100067490 | FLMR DFF - Replace Handrail EL +30250 | DFF - Replace Handrail EL +30250 |  |  | 0 | 0 | Empty | 2022-07-21 | 2022-07-29 | 2022-07-21 | 2022-07-21 | 2022-07-21 | 2022-12-18 | 10 |  |  | DF /F /86/32000 - HANDRAILS | DFF - Replace Handrail EL +30250 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-MECH | 2100067490 | FLMR DFF - Replace Handrail EL +30250 | DFF - Replace Handrail EL +30250 |  |  | 6 | 0 | Empty | 2022-07-21 | 2022-07-29 | 2022-07-21 | 2022-07-23 | 2022-07-21 | 2022-12-18 | 20 |  |  | DF /F /86/32000 - HANDRAILS | DFF - Replace Handrail EL +30250 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-MECH | 2100067490 | FLMR DFF - Replace Handrail EL +30250 | DFF - Replace Handrail EL +30250 |  |  | 24 | 0 | Empty | 2022-07-21 | 2022-07-29 | 2022-07-23 | 2022-07-29 | 2022-07-21 | 2022-12-18 | 30 |  |  | DF /F /86/32000 - HANDRAILS | DFF - Replace Handrail EL +30250 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100103963 | Replace PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-01-10 | 2024-05-24 | 10 | SECE | SECE | DF /F /10/DFFA-PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-LAGG | 2100103963 | Replace PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | SECE | SECE | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-01-10 | 2024-05-24 | 20 | SECE | SECE | DF /F /10/DFFA-PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100103963 | Replace PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2024-01-10 | 2024-05-24 | 30 | SECE | SECE | DF /F /10/DFFA-PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100103963 | Replace PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | SECE | SECE | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2024-01-10 | 2024-05-24 | 40 | SECE | SECE | DF /F /10/DFFA-PIT-300609 | Inhibit / Repeal inhibition PIT-300609 | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300007616 | DFCSWL2 - ABB SCADA SW | Dan F telecom assistance |  |  | 0 | 4 | W27-W28 | 2024-07-03 | 2024-07-07 | 2024-07-03 | 2024-07-03 | 2024-01-10 | 2024-02-24 | 10 |  |  | DF /C /04/DFCI-FP-2004 | Dan F telecom assistance | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300007616 | DFCSWL2 - ABB SCADA SW | Dan F telecom assistance |  |  | 20 | 10 | W27-W28 | 2024-07-03 | 2024-07-07 | 2024-07-03 | 2024-07-07 | 2024-01-10 | 2024-02-24 | 20 |  |  | DF /C /04/DFCI-FP-2004 | Dan F telecom assistance | Unknown
C | DFB-3550 | WPM | MTN-ELEC | PRODTECH | 2400235815 | 4Y 3KV N-SWB-MAINT-DFCI-N-1840 | Additional Materials | AWSC | AWSC | 1 | 0 | W49-50 | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2022-12-31 | 2023-03-29 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1840 | Additional Materials | Unknown
C | DFB-3550 | WPM | MTN-ELEC | VEN-ELEC | 2400235815 | 4Y 3KV N-SWB-MAINT-DFCI-N-1840 | Additional Materials | AWSC | AWSC | 21 | 0 | W49-50 | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2022-12-31 | 2023-03-29 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1840 | Additional Materials | Unknown
C | DFB-3550 | WPM | MTN-ELEC | VEN-ELEC | 2400235815 | 4Y 3KV N-SWB-MAINT-DFCI-N-1840 | Additional Materials | AWSC | AWSC | 5 | 0 | W49-50 | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2022-12-31 | 2023-03-29 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1840 | Additional Materials | Unknown
C | DFB-3550 | WPM | MTN-ELEC | PRODTECH | 2400235815 | 4Y 3KV N-SWB-MAINT-DFCI-N-1840 | Additional Materials | AWSC | AWSC | 1 | 0 | W49-50 | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2022-12-31 | 2023-03-29 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1840 | Additional Materials | Unknown
C | DFB-3550 | WPM | MTN-ELEC | MTN-ELEC | 2400235815 | 4Y 3KV N-SWB-MAINT-DFCI-N-1840 | Additional Materials | AWSC | AWSC | 0 | 0 | W49-50 | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2022-12-31 | 2023-03-29 | 50 | AWSC | AWSC | DF /C /61/DFCI-N-1840 | Additional Materials | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093141 | ANOCR DFF - Paint of Brace EL. 53.000 | Set up equipment | PCNF | PCNF | 0 | 0 | Empty | 2023-12-13 | 2024-06-25 | 2023-12-13 | 2023-12-13 | 2023-12-13 | 2026-05-31 | 10 | PCNF | PCNF | DF /F /86/53000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093141 | ANOCR DFF - Paint of Brace EL. 53.000 | Set up equipment | PCNF | PCNF | 12 | 8 | Empty | 2023-12-13 | 2024-06-25 | 2023-12-13 | 2024-06-25 | 2023-12-13 | 2026-05-31 | 20 | PCNF | PCNF | DF /F /86/53000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093141 | ANOCR DFF - Paint of Brace EL. 53.000 | Set up equipment | PCNF | PCNF | 6 | 6 | Empty | 2023-12-13 | 2024-06-25 | 2023-12-14 | 2024-06-25 | 2023-12-13 | 2026-05-31 | 30 | PCNF | PCNF | DF /F /86/53000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093141 | ANOCR DFF - Paint of Brace EL. 53.000 | Set up equipment | PCNF | PCNF | 135 | 64 | Empty | 2023-12-13 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2023-12-13 | 2026-05-31 | 40 | PCNF | PCNF | DF /F /86/53000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100093141 | ANOCR DFF - Paint of Brace EL. 53.000 | Set up equipment | PCNF | PCNF | 12 | 0 | Empty | 2023-12-13 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2023-12-13 | 2026-05-31 | 50 | PCNF | PCNF | DF /F /86/53000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-SCAF | 2100093141 | ANOCR DFF - Paint of Brace EL. 53.000 | Set up equipment | PCNF | PCNF | 0 | 12 | Empty | 2023-12-13 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2023-12-13 | 2026-05-31 | 60 | PCNF | PCNF | DF /F /86/53000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339284 | DFF_1Y_53000 INT STRUCT INSP - GVI | DFF_1Y_53000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_53000 (WL MODULE DECK) | DFF_1Y_53000 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 18 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-10-31 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 10 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 20 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 30 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 40 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 50 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 60 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 70 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400291289 | FLEXIBLE HOSES INSPECTION | DF_FLEXIBLE HOSES INSP. | AWSC | AWSC | 0 | 0 | Empty | 2023-10-31 | 2023-12-30 | 2023-12-29 | 2023-12-29 | 2023-10-31 | 2023-11-30 | 80 | AWSC | AWSC | DF /C /86/INSP-FLEXIBLE-HOSES | DF_FLEXIBLE HOSES INSP. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080940 | Batteries for P-3551 inverter opened | Backload batteries |  |  | 24 | 18 | Empty | 2023-02-24 | 2023-02-28 | 2023-02-24 | 2023-02-27 | 2023-02-24 | 2023-07-09 | 10 |  |  | DF /E /54/DFEY-P-3551 | Backload batteries | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080940 | Batteries for P-3551 inverter opened | Backload batteries |  |  | 1 | 1 | Empty | 2023-02-24 | 2023-02-28 | 2023-02-27 | 2023-02-28 | 2023-02-24 | 2023-07-09 | 20 |  |  | DF /E /54/DFEY-P-3551 | Backload batteries | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235712 | 4Y 380V E-SWB MAINT-DFBA-N-1831-03 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W09-10 | 2024-07-24 | 2024-07-28 | 2024-07-24 | 2024-07-24 | 2023-02-14 | 2023-04-28 | 10 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235712 | 4Y 380V E-SWB MAINT-DFBA-N-1831-03 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W09-10 | 2024-07-24 | 2024-07-28 | 2024-07-24 | 2024-07-25 | 2023-02-14 | 2023-04-28 | 20 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235712 | 4Y 380V E-SWB MAINT-DFBA-N-1831-03 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 26 | 0 | W09-10 | 2024-07-24 | 2024-07-28 | 2024-07-25 | 2024-07-28 | 2023-02-14 | 2023-04-28 | 30 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235712 | 4Y 380V E-SWB MAINT-DFBA-N-1831-03 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W09-10 | 2024-07-24 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2023-02-14 | 2023-04-28 | 40 | AWSCSECE | AWSCSECE | DF /B /05/DFBA-N-1831 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400325771 | 4Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | AWSCSECE | AWSCSECE | 56 | 0 | Empty | 2024-06-10 | 2024-06-13 | 2024-06-10 | 2024-06-12 | 2024-03-20 | 2024-06-01 | 10 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325771 | 4Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-06-10 | 2024-06-13 | 2024-06-12 | 2024-06-13 | 2024-03-20 | 2024-06-01 | 20 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400325771 | 4Y LIFE BOAT MAINT - DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-06-10 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-03-20 | 2024-06-01 | 30 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0701 | LIFE BOAT MAINT - DFGA-X-0701 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400321781 | DFC-26-OCS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | PCNFAWSCSECE | PCNFAWSCSECE | 14 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | PCNFAWSCSECE | PCNFAWSCSECE | DF /C /26/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235317 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL ISOLATION | SCH | SCH | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-26 | 2023-02-17 | 2023-03-19 | 10 | SCH | SCH | DF /C /09/DFCI-A-1221 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235317 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL ISOLATION | SCH | SCH | 12 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-29 | 2023-02-17 | 2023-03-19 | 20 | SCH | SCH | DF /C /09/DFCI-A-1221 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235317 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL ISOLATION | SCH | SCH | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-29 | 2023-02-17 | 2023-03-19 | 30 | SCH | SCH | DF /C /09/DFCI-A-1221 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235317 | 1Y HVAC SUPPLY AHU CHECK DFCI-A-1221 | PERSONAL ISOLATION | SCH | SCH | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2023-02-17 | 2023-03-19 | 40 | SCH | SCH | DF /C /09/DFCI-A-1221 | PERSONAL ISOLATION | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012612 | Replace DFBA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-03 | 2024-06-06 | 2024-06-03 | 2024-06-03 | 2023-06-03 | 2025-11-19 | 10 | SCH | SCH | DF /B /07/DFBA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012612 | Replace DFBA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-03 | 2024-06-06 | 2024-06-03 | 2024-06-04 | 2023-06-03 | 2025-11-19 | 20 | SCH | SCH | DF /B /07/DFBA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012612 | Replace DFBA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 5 | 0 | W23-W24 | 2024-06-03 | 2024-06-06 | 2024-06-04 | 2024-06-05 | 2023-06-03 | 2025-11-19 | 30 | SCH | SCH | DF /B /07/DFBA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012612 | Replace DFBA-PSV-59071 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-06 | 2024-06-05 | 2024-06-06 | 2023-06-03 | 2025-11-19 | 40 | SCH | SCH | DF /B /07/DFBA-PSV-59071 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058036 | Replace def. socketoutlet DFB1810-52-L2E | Deisolate Group aftr change |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2022-01-20 | 2022-06-19 | 10 |  |  | DF /B /61/DFBA-N-1810-C_52 | Deisolate Group aftr change | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058036 | Replace def. socketoutlet DFB1810-52-L2E | Deisolate Group aftr change |  |  | 4 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2022-01-20 | 2022-06-19 | 20 |  |  | DF /B /61/DFBA-N-1810-C_52 | Deisolate Group aftr change | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058036 | Replace def. socketoutlet DFB1810-52-L2E | Deisolate Group aftr change |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-02 | 2022-01-20 | 2022-06-19 | 30 |  |  | DF /B /61/DFBA-N-1810-C_52 | Deisolate Group aftr change | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058036 | Replace def. socketoutlet DFB1810-52-L2E | Deisolate Group aftr change |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2022-01-20 | 2022-06-19 | 40 |  |  | DF /B /61/DFBA-N-1810-C_52 | Deisolate Group aftr change | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100106407 | DFG leak oxygen scav. PSV-390616 | Replace PSV-390616 |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2024-03-15 | 2024-07-28 | 10 |  |  | DF /G /75/DFGA-PSV-390616 | Replace PSV-390616 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106407 | DFG leak oxygen scav. PSV-390616 | Replace PSV-390616 |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2024-03-15 | 2024-07-28 | 20 |  |  | DF /G /75/DFGA-PSV-390616 | Replace PSV-390616 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100106407 | DFG leak oxygen scav. PSV-390616 | Replace PSV-390616 |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2024-03-15 | 2024-07-28 | 30 |  |  | DF /G /75/DFGA-PSV-390616 | Replace PSV-390616 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009237 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /28/DFF-4-DO-050-8001-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009237 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /28/DFF-4-DO-050-8001-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009237 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-08 | 2024-01-11 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /28/DFF-4-DO-050-8001-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009237 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-11 | 2024-01-12 | 2022-02-07 | 2022-07-07 | 35 |  |  | DF /F /28/DFF-4-DO-050-8001-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009237 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-12 | 2024-01-16 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /28/DFF-4-DO-050-8001-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009237 | Insulation assist FORCE 19490 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-18 | 2024-01-16 | 2024-01-18 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /28/DFF-4-DO-050-8001-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100027355 | 1802A F6 tripper Rope | L3 Erect scaffold for replacing HT | PCNF | PCNF | 70 | 0 | W43-44?? BL-TEAM | 2024-07-15 | 2024-08-28 | 2024-07-15 | 2024-08-01 | 2018-11-22 | 2019-01-01 | 10 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100027355 | 1802A F6 tripper Rope | L3 Erect scaffold for replacing HT | PCNF | PCNF | 34.799999999999997157829056945 | 4 | W43-44?? BL-TEAM | 2024-07-15 | 2024-08-28 | 2024-08-01 | 2024-08-01 | 2018-11-22 | 2019-01-01 | 15 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027355 | 1802A F6 tripper Rope | L3 Erect scaffold for replacing HT | PCNF | PCNF | 60 | 0 | W43-44?? BL-TEAM | 2024-07-15 | 2024-08-28 | 2024-08-01 | 2024-08-16 | 2018-11-22 | 2019-01-01 | 20 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100027355 | 1802A F6 tripper Rope | L3 Erect scaffold for replacing HT | PCNF | PCNF | 20.100000000000001421085471515 | 0 | W43-44?? BL-TEAM | 2024-07-15 | 2024-08-28 | 2024-08-16 | 2024-08-18 | 2018-11-22 | 2019-01-01 | 25 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100027355 | 1802A F6 tripper Rope | L3 Erect scaffold for replacing HT | PCNF | PCNF | 40 | 0 | W43-44?? BL-TEAM | 2024-07-15 | 2024-08-28 | 2024-08-18 | 2024-08-28 | 2018-11-22 | 2019-01-01 | 30 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027355 | 1802A F6 tripper Rope | L3 Erect scaffold for replacing HT | PCNF | PCNF | 0 | 0 | W43-44?? BL-TEAM | 2024-07-15 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2018-11-22 | 2019-01-01 | 40 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | L3 Erect scaffold for replacing HT | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2022-03-28 | 2022-11-23 | 10 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2022-03-28 | 2022-11-23 | 20 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-31 | 2022-03-28 | 2022-11-23 | 30 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-07-31 | 2022-03-28 | 2022-11-23 | 40 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2022-03-28 | 2022-11-23 | 45 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-01 | 2022-03-28 | 2022-11-23 | 50 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-03 | 2022-03-28 | 2022-11-23 | 60 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2022-03-28 | 2022-11-23 | 70 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008708 | PSV Calibration - DFGA-PSV-350903B | Paint of valve |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2022-03-28 | 2022-11-23 | 80 |  |  | DF /G /54/DFGA-PSV-350903B | Paint of valve | Unknown
2 | NOSD | WDF | MTN-INST | PRODTECH | 2100103979 | DFF26 Chem FCV over inj. | Bay materials |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-12-21 | 2024-02-04 | 10 |  |  | DF /F /75/DFFA-FCV-390194 | Bay materials | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100103979 | DFF26 Chem FCV over inj. | Bay materials |  |  | 4.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-12-21 | 2024-02-04 | 20 |  |  | DF /F /75/DFFA-FCV-390194 | Bay materials | Unknown
2 | NOSD | WDF | MTN-INST | MTN-MECH | 2100103979 | DFF26 Chem FCV over inj. | Bay materials |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-12-21 | 2024-02-04 | 30 |  |  | DF /F /75/DFFA-FCV-390194 | Bay materials | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100103979 | DFF26 Chem FCV over inj. | Bay materials |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-12-21 | 2024-02-04 | 40 |  |  | DF /F /75/DFFA-FCV-390194 | Bay materials | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269618 | 6M WELL CONT PANEL MAINT - DFFA-FP-3101 | WELL CONT PANEL MAINT - DFFA-FP-3101 |  |  | 4 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-09 | 2023-08-25 | 10 |  |  | DF /F /07/DFFA-FP-3101 | WELL CONT PANEL MAINT - DFFA-FP-3101 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095453 | Replace lighting on stair well DFFA east | Isolate and prove dead |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 10 |  |  | DF /F /61/DFFA-DP-180BA-5-F06 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095453 | Replace lighting on stair well DFFA east | Isolate and prove dead |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 20 |  |  | DF /F /61/DFFA-DP-180BA-5-F06 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095453 | Replace lighting on stair well DFFA east | Isolate and prove dead |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-09-09 | 2024-01-22 | 30 |  |  | DF /F /61/DFFA-DP-180BA-5-F06 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095453 | Replace lighting on stair well DFFA east | Isolate and prove dead |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-09-09 | 2024-01-22 | 40 |  |  | DF /F /61/DFFA-DP-180BA-5-F06 | Isolate and prove dead | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235822 | 4Y 380V E-SWB MAINT DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235822 | 4Y 380V E-SWB MAINT DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | SCH | SCH | 8 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235822 | 4Y 380V E-SWB MAINT DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235822 | 4Y 380V E-SWB MAINT DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | 380V E-SWB MAINT DFFA-N-1812-03 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400321756 | DFB-11-PHS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 0 | Empty | 2024-11-15 | 2024-11-25 | 2024-11-15 | 2024-11-24 | 2024-11-15 | 2024-12-31 | 10 | PCNFAWSCSECE | PCNFAWSCSECE | DF /B /11/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400281089 | 3M HYD POWER PACKAGE MAINT - DFFA-A-5901 | HYD POWER PACKAGE MAINT - DFFA-A-5901 | PCNF | PCNF | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-09-27 | 2023-10-07 | 10 | PCNF | PCNF | DF /F /07/DFFA-A-5901 | HYD POWER PACKAGE MAINT - DFFA-A-5901 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235621 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-9-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235621 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-9-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235621 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-9-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235621 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-9 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-9-5 | ISOLATION ELECTRICAL | Unknown
4 | DFG-IGF | WDF | MTN-MECH | MTN-LAGG | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-08-01 | 2026-01-17 | 10 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | PRODTECH | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-08-01 | 2026-01-17 | 20 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | MTN-RIGG | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-23 | 2023-08-01 | 2026-01-17 | 30 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2023-08-01 | 2026-01-17 | 40 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | MTN-RIGG | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-25 | 2023-08-01 | 2026-01-17 | 50 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | MTN-MECH | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-26 | 2023-08-01 | 2026-01-17 | 60 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | PRODTECH | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2023-08-01 | 2026-01-17 | 70 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
4 | DFG-IGF | WDF | MTN-MECH | MTN-LAGG | 2100084632 | By.pass over DFG-LCV-500813 Stuck closed | Isolate HCV |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-08-01 | 2026-01-17 | 80 |  |  | DF /G /27/DFGA-HCV-500813-B | Isolate HCV | Unknown
A | DFF-1620 | WPM | MTN-TURB | MTN-TURB | 2400352045 | 1500H TURBINE WASH, COUNTER-DFFA-A-1620 | TURBINE WASH, COUNTER-DFFA-A-1620 | AWSC | AWSC | 8 | 12 | Empty | 2024-08-04 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2024-08-04 | 2024-08-14 | 10 | AWSC | AWSC | DF /F /60/DFFA-A-1620 | TURBINE WASH, COUNTER-DFFA-A-1620 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100097384 | DFB/78 Water leak coolant line | assist with replacement |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-14 | 2024-02-26 | 10 |  |  | DF /B /78/DFBA-MD-6102 | assist with replacement | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100097384 | DFB/78 Water leak coolant line | assist with replacement |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-14 | 2024-02-26 | 20 |  |  | DF /B /78/DFBA-MD-6102 | assist with replacement | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100097384 | DFB/78 Water leak coolant line | assist with replacement |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-14 | 2024-02-26 | 30 |  |  | DF /B /78/DFBA-MD-6102 | assist with replacement | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100097384 | DFB/78 Water leak coolant line | assist with replacement |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-14 | 2024-02-26 | 40 |  |  | DF /B /78/DFBA-MD-6102 | assist with replacement | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-MECH | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 0 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 10 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-PIPF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 8 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 20 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-SCAF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 52 | 52 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 30 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | PRODTECH | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 8 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 35 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-RIGG | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 40 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-PIPF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 36 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 50 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-RIGG | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 60 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-PIPF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 8 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 61 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-RIGG | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 6 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 62 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-MECH | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 16 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 70 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-PIPF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 16 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 80 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-RIGG | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 90 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-MECH | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 100 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | PRODTECH | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 105 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | PRODTECH | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 12 | 10 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-24 | 2024-05-01 | 2023-05-09 | 2023-09-21 | 110 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-RIGG | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 18 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 120 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-SCAF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 26 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-08 | 2023-05-09 | 2023-09-21 | 130 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
3 | DFF-O28 | WDF | MTN-PIPF | MTN-PIPF | 2100088068 | FFSPR Replacement spool DFF-6-PHS-030-72 | Clean up gasket surface | PCNF | PCNF | 8 | 0 | Empty | 2024-01-08 | 2024-05-01 | 2024-01-08 | 2024-01-09 | 2023-05-09 | 2023-09-21 | 140 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7281-GF-U | Clean up gasket surface | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400351954 | 6M TRANSP AIR COMP MAINT - DFEZ-C-5402 | TRANSP AIR COMP MAINT - DFEZ-C-5402 |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-10-17 | 10 |  |  | DF /E /07/DFEZ-C-5402 | TRANSP AIR COMP MAINT - DFEZ-C-5402 | Unknown
D | NOSD | WPM | MTN-MECH | MTN-INST | 2400351954 | 6M TRANSP AIR COMP MAINT - DFEZ-C-5402 | TRANSP AIR COMP MAINT - DFEZ-C-5402 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-09-22 | 2024-10-17 | 20 |  |  | DF /E /07/DFEZ-C-5402 | TRANSP AIR COMP MAINT - DFEZ-C-5402 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235612 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-20 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235612 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-20 | ISOLATION ELECTRICAL |  |  | 9 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235612 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-20 | ISOLATION ELECTRICAL |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235612 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-20 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259589 | 1Y SW FILTERS & BLOWERS MAINT - DFE | SW FILTERS & BLOWERS MAINT - DFE | AWSC | AWSC | 2 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-05-18 | 2023-06-23 | 10 | AWSC | AWSC | DF /E /51/DFEY-FT-3511 | SW FILTERS & BLOWERS MAINT - DFE | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259589 | 1Y SW FILTERS & BLOWERS MAINT - DFE | SW FILTERS & BLOWERS MAINT - DFE | AWSC | AWSC | 2 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-05-18 | 2023-06-23 | 20 | AWSC | AWSC | DF /E /51/DFEY-FT-3511 | SW FILTERS & BLOWERS MAINT - DFE | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400342403 | 6M COOLING WATER SYSTEM MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-08-21 | 2024-09-09 | 10 |  |  | DF /G /76/DFGA-V-5350 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342403 | 6M COOLING WATER SYSTEM MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 7 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2024-08-21 | 2024-09-09 | 20 |  |  | DF /G /76/DFGA-V-5350 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400342403 | 6M COOLING WATER SYSTEM MAINT-DFG | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-08-21 | 2024-09-09 | 30 |  |  | DF /G /76/DFGA-V-5350 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235575 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235575 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-02-14 | 2023-05-13 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235575 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-02-14 | 2023-05-13 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235575 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-02-14 | 2023-05-13 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-03-01 | ISOLATION ELECTRICAL | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 10 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 20 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 30 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 40 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 50 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 60 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 70 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 80 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 90 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 100 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 110 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 120 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 130 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 140 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 150 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002692 | DAN MATRIALE BESTILLING WELDER 2021 | 2300002692 26.08 DFF MAT ARGON |  |  | 0 | 0 | Empty | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-03-22 | 2021-05-01 | 160 |  |  | DF /F | 2300002692 26.08 DFF MAT ARGON | Unknown
4 | DFGHPSEP | WDF | MTN-INST | PRODTECH | 2100058252 | DFG Fuelgas HV valve ZSC faulty | Troubleshoot Position switch |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2022-01-30 | 2022-06-29 | 10 |  |  | DF /G /70/DFGA-HCV-570065 | Troubleshoot Position switch | Unknown
4 | DFGHPSEP | WDF | MTN-INST | MTN-INST | 2100058252 | DFG Fuelgas HV valve ZSC faulty | Troubleshoot Position switch |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2022-01-30 | 2022-06-29 | 20 |  |  | DF /G /70/DFGA-HCV-570065 | Troubleshoot Position switch | Unknown
4 | DFGHPSEP | WDF | MTN-INST | PRODTECH | 2100058252 | DFG Fuelgas HV valve ZSC faulty | Troubleshoot Position switch |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2022-01-30 | 2022-06-29 | 30 |  |  | DF /G /70/DFGA-HCV-570065 | Troubleshoot Position switch | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328716 | 6M SDV LUB/MAINT FUEL - DFC | SDV LUB/INSP FUEL - DFC |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-19 | 2024-06-04 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP FUEL - DFC | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100023450 | SMAT:Korroderede bolte på Transmitter DF | leak test | PCNFAWSC | PCNFAWSC | 26 | 6 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2018-04-01 | 2018-04-21 | 10 | PCNFAWSC | PCNFAWSC | DF /C /70/DFCI-PDT-57127 | leak test | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100023450 | SMAT:Korroderede bolte på Transmitter DF | leak test | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2018-04-01 | 2018-04-21 | 20 | PCNFAWSC | PCNFAWSC | DF /C /70/DFCI-PDT-57127 | leak test | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100023450 | SMAT:Korroderede bolte på Transmitter DF | leak test | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2018-04-01 | 2018-04-21 | 30 | PCNFAWSC | PCNFAWSC | DF /C /70/DFCI-PDT-57127 | leak test | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100081834 | Seawater FT-5310 inlet HCV gearseal leak | Isolate FT-5310 inlet HCV |  |  | 2 | 0 | Empty | 2024-07-26 | 2024-07-30 | 2024-07-26 | 2024-07-26 | 2023-07-26 | 2026-01-11 | 10 |  |  | DF /F /51/DFFA-FT-5310 | Isolate FT-5310 inlet HCV | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100081834 | Seawater FT-5310 inlet HCV gearseal leak | Isolate FT-5310 inlet HCV |  |  | 4 | 0 | Empty | 2024-07-26 | 2024-07-30 | 2024-07-26 | 2024-07-27 | 2023-07-26 | 2026-01-11 | 20 |  |  | DF /F /51/DFFA-FT-5310 | Isolate FT-5310 inlet HCV | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100081834 | Seawater FT-5310 inlet HCV gearseal leak | Isolate FT-5310 inlet HCV |  |  | 4 | 0 | Empty | 2024-07-26 | 2024-07-30 | 2024-07-27 | 2024-07-28 | 2023-07-26 | 2026-01-11 | 30 |  |  | DF /F /51/DFFA-FT-5310 | Isolate FT-5310 inlet HCV | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100081834 | Seawater FT-5310 inlet HCV gearseal leak | Isolate FT-5310 inlet HCV |  |  | 4 | 0 | Empty | 2024-07-26 | 2024-07-30 | 2024-07-28 | 2024-07-29 | 2023-07-26 | 2026-01-11 | 40 |  |  | DF /F /51/DFFA-FT-5310 | Isolate FT-5310 inlet HCV | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100081834 | Seawater FT-5310 inlet HCV gearseal leak | Isolate FT-5310 inlet HCV |  |  | 2 | 0 | Empty | 2024-07-26 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-07-26 | 2026-01-11 | 50 |  |  | DF /F /51/DFFA-FT-5310 | Isolate FT-5310 inlet HCV | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100081834 | Seawater FT-5310 inlet HCV gearseal leak | Isolate FT-5310 inlet HCV |  |  | 2 | 0 | Empty | 2024-07-26 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-26 | 2026-01-11 | 60 |  |  | DF /F /51/DFFA-FT-5310 | Isolate FT-5310 inlet HCV | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235617 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-5 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-30 | 2023-07-27 | 10 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235617 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-5 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 6 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-20 | 2023-04-30 | 2023-07-27 | 20 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235617 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-5 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2023-04-30 | 2023-07-27 | 30 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-5 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235617 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-5 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2023-04-30 | 2023-07-27 | 40 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-5 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004020 | DK40 - REPLACED BY 2300007131 | Add mats for PVI. |  |  | 0 | 0 | Empty | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2025-06-15 | 10 |  |  | DF /C /84 | Add mats for PVI. | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004020 | DK40 - REPLACED BY 2300007131 | Add mats for PVI. |  |  | 0 | 0 | Empty | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2025-06-15 | 20 |  |  | DF /C /84 | Add mats for PVI. | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004020 | DK40 - REPLACED BY 2300007131 | Add mats for PVI. |  |  | 0 | 0 | Empty | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2022-12-28 | 2025-06-15 | 30 |  |  | DF /C /84 | Add mats for PVI. | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100026510 | 1" HCV to PI-381302 internal leak | Prod prepare permit/isolation | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-04-01 | 2020-08-29 | 10 | AWSC | AWSC | DF /G /34/DFGA-EP-3813 | Prod prepare permit/isolation | Unknown
4 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100026510 | 1" HCV to PI-381302 internal leak | Prod prepare permit/isolation | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2020-04-01 | 2020-08-29 | 20 | AWSC | AWSC | DF /G /34/DFGA-EP-3813 | Prod prepare permit/isolation | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100026510 | 1" HCV to PI-381302 internal leak | Prod prepare permit/isolation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2020-04-01 | 2020-08-29 | 30 | AWSC | AWSC | DF /G /34/DFGA-EP-3813 | Prod prepare permit/isolation | Unknown
4 | DFG20MPH | WDF | MTN-MECH | PRODTECH | 2100026510 | 1" HCV to PI-381302 internal leak | Prod prepare permit/isolation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2020-04-01 | 2020-08-29 | 40 | AWSC | AWSC | DF /G /34/DFGA-EP-3813 | Prod prepare permit/isolation | Unknown
4 | DFG20MPH | WDF | MTN-MECH | MTN-MECH | 2100026510 | 1" HCV to PI-381302 internal leak | Prod prepare permit/isolation | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2020-04-01 | 2020-08-29 | 50 | AWSC | AWSC | DF /G /34/DFGA-EP-3813 | Prod prepare permit/isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038219 | DFF Scale inj Filter replacement. | More materials | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-09-13 | 2020-09-18 | 10 | PCNF | PCNF | DF /F /75/DFFA-P-3911 | More materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038219 | DFF Scale inj Filter replacement. | More materials | PCNF | PCNF | 12 | 10 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2020-09-13 | 2020-09-18 | 20 | PCNF | PCNF | DF /F /75/DFFA-P-3911 | More materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038219 | DFF Scale inj Filter replacement. | More materials | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-09-13 | 2020-09-18 | 30 | PCNF | PCNF | DF /F /75/DFFA-P-3911 | More materials | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038219 | DFF Scale inj Filter replacement. | More materials | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-09-13 | 2020-09-18 | 40 | PCNF | PCNF | DF /F /75/DFFA-P-3911 | More materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038219 | DFF Scale inj Filter replacement. | More materials | PCNF | PCNF | 4 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2020-09-13 | 2020-09-18 | 50 | PCNF | PCNF | DF /F /75/DFFA-P-3911 | More materials | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038219 | DFF Scale inj Filter replacement. | More materials | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2020-09-13 | 2020-09-18 | 60 | PCNF | PCNF | DF /F /75/DFFA-P-3911 | More materials | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339279 | DFF_1Y_37000 INT STRUCT INSP - GVI | DFF_1Y_37000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_37000 (LEVEL3) | DFF_1Y_37000 INT STRUCT INSP - GVI | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-SCAF | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-29 | 2024-07-31 | 2020-04-11 | 2020-05-21 | 10 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-31 | 2024-08-01 | 2020-04-11 | 2020-05-21 | 20 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-01 | 2024-08-02 | 2020-04-11 | 2020-05-21 | 30 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-02 | 2024-08-03 | 2020-04-11 | 2020-05-21 | 40 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-03 | 2024-08-04 | 2020-04-11 | 2020-05-21 | 50 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-04 | 2024-08-05 | 2020-04-11 | 2020-05-21 | 60 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-05 | 2024-08-06 | 2020-04-11 | 2020-05-21 | 70 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-06 | 2024-08-07 | 2020-04-11 | 2020-05-21 | 80 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-07 | 2024-08-07 | 2020-04-11 | 2020-05-21 | 90 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-07 | 2024-08-08 | 2020-04-11 | 2020-05-21 | 100 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-08 | 2024-08-08 | 2020-04-11 | 2020-05-21 | 110 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-08-08 | 2024-08-09 | 2020-04-11 | 2020-05-21 | 120 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100030527 | External leak on LCV-350401 stuffing box | Build Scaffolding |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-09 | 2024-07-29 | 2024-07-29 | 2020-04-11 | 2020-05-21 | 130 |  |  | DF /G /54/DFGA-LCV-350401 | Build Scaffolding | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235675 | 4Y 380V N-SWB MAINT DFCI-N-1823-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1823-02A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235675 | 4Y 380V N-SWB MAINT DFCI-N-1823-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1823-02A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235675 | 4Y 380V N-SWB MAINT DFCI-N-1823-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1823-02A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235675 | 4Y 380V N-SWB MAINT DFCI-N-1823-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1823-02A | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093868 | DFB17 Chem FCV-397104 internal leaking | Replace DFB-FCV-397104 |  |  | 2 | 0 | Empty | 2024-06-11 | 2024-06-13 | 2024-06-11 | 2024-06-12 | 2023-08-11 | 2023-12-24 | 10 |  |  | DF /B /75/DFBA-FCV-397104 | Replace DFB-FCV-397104 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093868 | DFB17 Chem FCV-397104 internal leaking | Replace DFB-FCV-397104 |  |  | 4 | 0 | Empty | 2024-06-11 | 2024-06-13 | 2024-06-12 | 2024-06-13 | 2023-08-11 | 2023-12-24 | 20 |  |  | DF /B /75/DFBA-FCV-397104 | Replace DFB-FCV-397104 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093868 | DFB17 Chem FCV-397104 internal leaking | Replace DFB-FCV-397104 |  |  | 2 | 0 | Empty | 2024-06-11 | 2024-06-13 | 2024-06-11 | 2024-06-12 | 2023-08-11 | 2023-12-24 | 30 |  |  | DF /B /75/DFBA-FCV-397104 | Replace DFB-FCV-397104 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 8 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2021-02-18 | 2021-05-19 | 10 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-16 | 2021-02-18 | 2021-05-19 | 20 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-16 | 2021-02-18 | 2021-05-19 | 30 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 40 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 50 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 60 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 70 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 80 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 90 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 100 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 110 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 120 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2021-02-18 | 2021-05-19 | 130 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-SCAF | 2100044921 | DFG TCV-440008 Dårlig integritet | Isolate TCV | PCNF | PCNF | 5 | 5 | Empty | 2024-09-15 | 2024-09-19 | 2024-02-09 | 2024-02-09 | 2021-02-18 | 2021-05-19 | 140 | PCNF | PCNF | DF /G /31/DFGA-TCV-440008 | Isolate TCV | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100092670 | RESET PB DFFA-PB-021352 NEED TO REPLACE | Replace pushbutton and test |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-07-26 | 2023-12-08 | 10 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100092670 | RESET PB DFFA-PB-021352 NEED TO REPLACE | Replace pushbutton and test |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-07-26 | 2023-12-08 | 20 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100092670 | RESET PB DFFA-PB-021352 NEED TO REPLACE | Replace pushbutton and test |  |  | 0.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-07-26 | 2023-12-08 | 30 |  |  | DF /F /03 | Replace pushbutton and test | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400329526 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-05-09 | 2024-06-14 | 10 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329526 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2024-05-09 | 2024-06-14 | 20 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400329526 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2024-05-09 | 2024-06-14 | 30 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329526 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-05-09 | 2024-06-14 | 40 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400329526 | 1Y POT WATER SAMPLE PUMP MAINT-P-5009 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2024-05-09 | 2024-06-14 | 50 |  |  | DF /C /85/DFCM-P-5009 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 12 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-07-22 | 2024-07-23 | 2024-06-19 | 2024-11-01 | 5 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 3 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-07-23 | 2024-07-24 | 2024-06-19 | 2024-11-01 | 10 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 4 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-07-24 | 2024-07-25 | 2024-06-19 | 2024-11-01 | 20 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 4 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-07-24 | 2024-07-24 | 2024-06-19 | 2024-11-01 | 30 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 4 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-09-23 | 2024-09-24 | 2024-06-19 | 2024-11-01 | 40 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 4 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-09-23 | 2024-09-23 | 2024-06-19 | 2024-11-01 | 50 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 3 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2024-06-19 | 2024-11-01 | 60 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100112084 | DFCM-PSV-03470 internal leaking | Scaffolding Step-up erection |  |  | 8 | 0 | Empty | 2024-07-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-06-19 | 2024-11-01 | 70 |  |  | DF /C /01/DFCM-PSV-03470 | Scaffolding Step-up erection | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400214932 | 6M WELLHEAD CONTROL PANELS MAINT - DFB | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-10-26 | 2022-11-11 | 10 |  |  | DF /B /07/WELLHEAD-CONTROL-PANELS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400214932 | 6M WELLHEAD CONTROL PANELS MAINT - DFB | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-10-26 | 2022-11-11 | 20 |  |  | DF /B /07/WELLHEAD-CONTROL-PANELS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400214932 | 6M WELLHEAD CONTROL PANELS MAINT - DFB | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-10-26 | 2022-11-11 | 30 |  |  | DF /B /07/WELLHEAD-CONTROL-PANELS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400190538 | 1Y NITROGEN AIR COMPRESSOR, DFCM-C-5408/ | GENERAL INFO VEDLIGEHOLD MED ASSU |  |  | 0 | 0 | Empty | 2023-12-26 | 2023-12-31 | 2023-12-26 | 2023-12-26 | 2022-02-21 | 2022-03-29 | 1 |  |  | DF /C /07/DFCM-C-5408 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400190538 | 1Y NITROGEN AIR COMPRESSOR, DFCM-C-5408/ | GENERAL INFO VEDLIGEHOLD MED ASSU |  |  | 13 | 24 | Empty | 2023-12-26 | 2023-12-31 | 2023-12-26 | 2023-12-28 | 2022-02-21 | 2022-03-29 | 10 |  |  | DF /C /07/DFCM-C-5408 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400190538 | 1Y NITROGEN AIR COMPRESSOR, DFCM-C-5408/ | GENERAL INFO VEDLIGEHOLD MED ASSU |  |  | 7 | 0 | Empty | 2023-12-26 | 2023-12-31 | 2023-12-28 | 2023-12-29 | 2022-02-21 | 2022-03-29 | 12 |  |  | DF /C /07/DFCM-C-5408 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
C | NOSD | WPM | MTN-MECH | VEN-MECH | 2400190538 | 1Y NITROGEN AIR COMPRESSOR, DFCM-C-5408/ | GENERAL INFO VEDLIGEHOLD MED ASSU |  |  | 25 | 24 | Empty | 2023-12-26 | 2023-12-31 | 2023-12-29 | 2023-12-31 | 2022-02-21 | 2022-03-29 | 14 |  |  | DF /C /07/DFCM-C-5408 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400190538 | 1Y NITROGEN AIR COMPRESSOR, DFCM-C-5408/ | GENERAL INFO VEDLIGEHOLD MED ASSU |  |  | 0 | 0 | Empty | 2023-12-26 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2022-02-21 | 2022-03-29 | 24 |  |  | DF /C /07/DFCM-C-5408 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106934 | DFF HP-sep sandtrap XCV indication fault | XCV limit switches investigation |  |  | 2 | 2 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-03-22 | 2024-08-04 | 10 |  |  | DF /F /20/DFFA-XCV-340516 | XCV limit switches investigation | Unknown
4 | DFF-1751 | WDF | MTN-ELEC | PRODTECH | 2100023494 | EM Generator 1751 Switchboard service. | Isolate power to switchboard for G-1751 | AWSC | AWSC | 2 | 0 | Empty | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2018-06-13 | 2018-11-10 | 10 | AWSC | AWSC | DF /F /05/DFFA-FP-1751 | Isolate power to switchboard for G-1751 | Unknown
4 | DFF-1751 | WDF | MTN-ELEC | MTN-ELEC | 2100023494 | EM Generator 1751 Switchboard service. | Isolate power to switchboard for G-1751 | AWSC | AWSC | 5 | 0 | Empty | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2018-06-13 | 2018-11-10 | 20 | AWSC | AWSC | DF /F /05/DFFA-FP-1751 | Isolate power to switchboard for G-1751 | Unknown
4 | DFF-1751 | WDF | MTN-ELEC | PRODTECH | 2100023494 | EM Generator 1751 Switchboard service. | Isolate power to switchboard for G-1751 | AWSC | AWSC | 2 | 0 | Empty | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2018-06-13 | 2018-11-10 | 30 | AWSC | AWSC | DF /F /05/DFFA-FP-1751 | Isolate power to switchboard for G-1751 | Unknown
3 | Empty | WDF | MTN-ELEC | MTN-ELEC | 2100111007 | Perf. Std defect for SECE-id: E3.1 | operation_description_not_present | SECE | SECE | 0 | 0 | Empty | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-07-26 | 2024-12-08 | 10 | SECE | SECE | DF /G /62/EMERGENCY-LIGHTING-L2 | operation_description_not_present | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-01 | 2020-01-26 | 2020-02-15 | 10 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 52 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-06 | 2020-01-26 | 2020-02-15 | 20 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 102 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-06 | 2024-08-14 | 2020-01-26 | 2020-02-15 | 30 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 26 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-11 | 2024-08-14 | 2020-01-26 | 2020-02-15 | 35 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-14 | 2024-08-16 | 2020-01-26 | 2020-02-15 | 36 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 8 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-14 | 2024-08-16 | 2020-01-26 | 2020-02-15 | 37 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-16 | 2024-08-17 | 2020-01-26 | 2020-02-15 | 40 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 51 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-17 | 2024-08-21 | 2020-01-26 | 2020-02-15 | 50 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2020-01-26 | 2020-02-15 | 60 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2020-01-26 | 2020-02-15 | 70 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-01 | 2020-01-26 | 2020-02-15 | 80 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-01 | 2020-01-26 | 2020-02-15 | 90 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-01 | 2020-01-26 | 2020-02-15 | 100 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 0 | 0 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-01 | 2020-01-26 | 2020-02-15 | 110 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100025202 | DFGA-FIL-5358, Replac. filter internals | Setup/de-rig rigg. equipment | AWSC | AWSC | 36 | 24 | Empty | 2024-08-01 | 2024-08-21 | 2024-08-01 | 2024-08-09 | 2020-01-26 | 2020-02-15 | 120 | AWSC | AWSC | DF /G /51/DFGA-FIL-5358 | Setup/de-rig rigg. equipment | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095425 | udskife batterier/spoler efter lystjek | Isolate and prove dead |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2023-09-05 | 2024-01-18 | 10 |  |  | DF /C /05/DFCC-N-1813 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095425 | udskife batterier/spoler efter lystjek | Isolate and prove dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2023-09-05 | 2024-01-18 | 20 |  |  | DF /C /05/DFCC-N-1813 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095425 | udskife batterier/spoler efter lystjek | Isolate and prove dead |  |  | 12 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2023-09-05 | 2024-01-18 | 30 |  |  | DF /C /05/DFCC-N-1813 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095425 | udskife batterier/spoler efter lystjek | Isolate and prove dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2023-09-05 | 2024-01-18 | 40 |  |  | DF /C /05/DFCC-N-1813 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 1 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-25 | 2024-09-25 | 2024-07-25 | 2024-12-07 | 10 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 5 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-25 | 2024-09-26 | 2024-07-25 | 2024-12-07 | 20 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 12 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-25 | 2024-09-26 | 2024-07-25 | 2024-12-07 | 30 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 5 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-25 | 2024-09-26 | 2024-07-25 | 2024-12-07 | 40 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 5 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2024-07-25 | 2024-12-07 | 50 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 5 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2024-07-25 | 2024-12-07 | 60 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100114311 | DFFW/78 Fault on upper limit whip hoist | Assist with replacement (work at heigt) |  |  | 12 | 0 | Empty | 2024-09-25 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2024-07-25 | 2024-12-07 | 70 |  |  | DF /F /78/DFFA-A-6102 | Assist with replacement (work at heigt) | Unknown
2 | NE | WGN | MTN-INST | MTN-TELE | 2200016567 | DAF - Nutanix server replacement | Telecom assistance Install of server | PCNFSCH | PCNFSCH | 0 | 16 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-01-29 | 2024-02-21 | 2023-11-22 | 2024-01-06 | 10 | PCNFSCH | PCNFSCH | DF /C /08 | Telecom assistance Install of server | Unknown
2 | NE | WGN | MTN-INST | MTN-TELE | 2200016567 | DAF - Nutanix server replacement | Telecom assistance Install of server | PCNFSCH | PCNFSCH | 20 | 10 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-11-22 | 2024-01-06 | 20 | PCNFSCH | PCNFSCH | DF /C /08 | Telecom assistance Install of server | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-01 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 6 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-01 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 8 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-01 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 4 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-02 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 0.5 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-02 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 50 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 1 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-02 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 60 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 1 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-02 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 70 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 1 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-02 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 80 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 1 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-03 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 90 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 6 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-03 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 100 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 6 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 120 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 130 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 7 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 140 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 1.5 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 150 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 160 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 170 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 0.5 | 1.5 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 180 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 1 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 190 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 6 | 6 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-03-11 | 2023-11-15 | 2023-12-30 | 200 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 6 | 24 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-11-15 | 2023-12-30 | 210 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 2 | 5 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 220 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 2 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-01-04 | 2024-01-17 | 2023-11-15 | 2023-12-30 | 230 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 6 | 5 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-11-15 | 2023-12-30 | 240 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100102025 | DFC-FD-12384 | DFCI-FD-12384 mount new actuator | PCNFSCHSECE | PCNFSCHSECE | 24 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-11-15 | 2023-12-30 | 250 | PCNFSCHSECE | PCNFSCHSECE | DF /C /09/DFCI-FD-12251 | DFCI-FD-12384 mount new actuator | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235812 | 1Y 24VDC UPS SYSTEM F.TEST-DFC | 24VDC UPS SYSTEM F.TEST-DFC | SECE | SECE | 12 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 2023-08-02 | 2023-09-01 | 10 | SECE | SECE | DF /C /06/UPS-SYSTEMS | 24VDC UPS SYSTEM F.TEST-DFC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088054 | Replace Basket stretcher rusty hook | Replace basket stretcher rusty hook |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-10 | 2023-09-22 | 10 |  |  | DF /C /02/DFCI-STR-0622 | Replace basket stretcher rusty hook | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322236 | DFB-11-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /11/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 10 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-01 | 2024-08-02 | 2020-11-30 | 2021-04-29 | 10 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 3 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-02 | 2024-08-02 | 2020-11-30 | 2021-04-29 | 15 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 1 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-03 | 2024-08-03 | 2020-11-30 | 2021-04-29 | 20 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 2 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-03 | 2024-08-03 | 2020-11-30 | 2021-04-29 | 30 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 48 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-03 | 2024-08-06 | 2020-11-30 | 2021-04-29 | 40 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 50 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-06 | 2024-08-12 | 2020-11-30 | 2021-04-29 | 50 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 48 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-12 | 2024-08-15 | 2020-11-30 | 2021-04-29 | 60 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 3 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-15 | 2024-08-15 | 2020-11-30 | 2021-04-29 | 70 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 1 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-15 | 2024-08-16 | 2020-11-30 | 2021-04-29 | 80 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 8 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-16 | 2024-08-16 | 2020-11-30 | 2021-04-29 | 90 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 8 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-16 | 2024-08-18 | 2020-11-30 | 2021-04-29 | 92 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 3 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-16 | 2024-08-17 | 2020-11-30 | 2021-04-29 | 100 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100038733 | DFG/78: Replace hydr. pumps splittergear | Backload old pumps to crane specialist |  |  | 3 | 0 | Empty | 2024-08-01 | 2024-08-18 | 2024-08-17 | 2024-08-17 | 2020-11-30 | 2021-04-29 | 105 |  |  | DF /G /78/DFGA-A-6140 | Backload old pumps to crane specialist | Unknown
3 | NOSD | WGN | MTN-INST | PRODTECH | 2200003181 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-430002 |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2017-12-29 | 2018-03-29 | 10 |  |  | DF /G /34/DFGA-ESDV-430002 | Hydraulic isolation DFGA-ESDV-430002 | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200003181 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-430002 |  |  | 8 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2017-12-29 | 2018-03-29 | 20 |  |  | DF /G /34/DFGA-ESDV-430002 | Hydraulic isolation DFGA-ESDV-430002 | Unknown
3 | NOSD | WGN | MTN-INST | PRODTECH | 2200003181 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-430002 |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2017-12-29 | 2018-03-29 | 30 |  |  | DF /G /34/DFGA-ESDV-430002 | Hydraulic isolation DFGA-ESDV-430002 | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200003181 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-430002 |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2017-12-29 | 2018-03-29 | 40 |  |  | DF /G /34/DFGA-ESDV-430002 | Hydraulic isolation DFGA-ESDV-430002 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235913 | 6M HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 | HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-07 | 2023-03-26 | 10 |  |  | DF /F /75/DFFA-FP-3990 | HYD V/CTRL PAN MAINT-DFFA-FP-3990/1/2 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086266 | PM-3119 makes no pressure | Spare pump from onshore stock |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2023-04-13 | 2023-08-26 | 20 |  |  | DF /F /07/DFFA-P-3119 | Spare pump from onshore stock | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086266 | PM-3119 makes no pressure | Spare pump from onshore stock |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2023-04-13 | 2023-08-26 | 30 |  |  | DF /F /07/DFFA-P-3119 | Spare pump from onshore stock | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086266 | PM-3119 makes no pressure | Spare pump from onshore stock |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2023-04-13 | 2023-08-26 | 40 |  |  | DF /F /07/DFFA-P-3119 | Spare pump from onshore stock | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086266 | PM-3119 makes no pressure | Spare pump from onshore stock |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2023-04-13 | 2023-08-26 | 50 |  |  | DF /F /07/DFFA-P-3119 | Spare pump from onshore stock | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086266 | PM-3119 makes no pressure | Spare pump from onshore stock |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2023-04-13 | 2023-08-26 | 60 |  |  | DF /F /07/DFFA-P-3119 | Spare pump from onshore stock | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 6 | 6 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-12 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 3 | 1 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-22 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 6 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-23 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 6 | 5 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-23 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 3 | 5 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-23 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 50 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 3 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-23 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 60 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 1 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-22 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 70 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 15 | 16 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-11 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 80 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 8 | 8 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-22 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 90 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-04-22 | 2024-04-28 | 2023-10-17 | 2023-12-01 | 100 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 110 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 120 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 130 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 140 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 150 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 160 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 170 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 180 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100100114 | DFE FW booster P-0303 leaking shaft seal | Build scaff gallows | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | W17-W18 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-17 | 2023-12-01 | 190 | PCNFSCHSECE | PCNFSCHSECE | DF /E /01/DFEY-P-0303 | Build scaff gallows | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042845 | Deluge DFF leaking pilot valve xv-035354 | replace/repair pilot valve | SCHSECE | SCHSECE | 2 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2021-03-03 | 2021-07-31 | 10 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035354 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042845 | Deluge DFF leaking pilot valve xv-035354 | replace/repair pilot valve | SCHSECE | SCHSECE | 8 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-24 | 2021-03-03 | 2021-07-31 | 20 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035354 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100042845 | Deluge DFF leaking pilot valve xv-035354 | replace/repair pilot valve | SCHSECE | SCHSECE | 2 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2021-03-03 | 2021-07-31 | 30 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035354 | replace/repair pilot valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042845 | Deluge DFF leaking pilot valve xv-035354 | replace/repair pilot valve | SCHSECE | SCHSECE | 0 | 0 | 24-W03-04 | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2021-03-03 | 2021-07-31 | 40 | SCHSECE | SCHSECE | DF /F /01/DFFA-XV-035354 | replace/repair pilot valve | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322273 | DFC-01-WW-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342396 | 6M CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | SECE | SECE | 5 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-08-24 | 2024-09-09 | 10 | SECE | SECE | DF /B /01/CO2-SNUFFING-SYSTEM | CO2-SNUFFING-SYSTEM MAINT-DFBA-A-0411 | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | PRODTECH | 2400329508 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | SECE | SECE | 1 | 0 | Empty | 2024-05-21 | 2024-05-22 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-20 | 10 | SECE | SECE | DF /G /70/DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | MTN-ELEC | 2400329508 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | SECE | SECE | 2 | 0 | Empty | 2024-05-21 | 2024-05-22 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-20 | 20 | SECE | SECE | DF /G /70/DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | MTN-INST | 2400329508 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | SECE | SECE | 1 | 0 | Empty | 2024-05-21 | 2024-05-22 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2024-06-20 | 30 | SECE | SECE | DF /G /70/DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | Unknown
A | DFG-FUEL | WPM | MTN-ELEC | PRODTECH | 2400329508 | 1Y FUEL GAS HEATER MAINT-DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | SECE | SECE | 1 | 0 | Empty | 2024-05-21 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2024-05-21 | 2024-06-20 | 40 | SECE | SECE | DF /G /70/DFGA-XE-5742 | FUEL GAS HEATER MAINT-DFGA-XE-5742 | Unknown
3 | NE | WRO | MTN-INST | MTN-INST | 2300001067 | Adjustment of Level Transmitter LT-34076 | Ajustment of wrong ESD HMI level illustr |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2024-01-08 | 2010-01-01 | 2030-12-31 | 10 |  |  | DF /C /20/DFCM-LT-34076 | Ajustment of wrong ESD HMI level illustr | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100061673 | ANOV Repair of DFFA-V-3403 Sand Trap | Sandtrap |  |  | 0 | 0 | Empty | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-01-22 | 2022-02-11 | 10 |  |  | DF /F /11/DFFA-V-3403 | Sandtrap | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100061673 | ANOV Repair of DFFA-V-3403 Sand Trap | Sandtrap |  |  | 0 | 0 | Empty | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-04-25 | 2022-01-22 | 2022-02-11 | 20 |  |  | DF /F /11/DFFA-V-3403 | Sandtrap | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062917 | ANOCR DFA - Repair Primary structure EL | Set up equipment |  |  | 0 | 0 | Empty | 2022-05-02 | 2022-06-06 | 2022-05-02 | 2022-05-02 | 2022-05-02 | 2022-09-29 | 10 |  |  | DF /A /86/22000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062917 | ANOCR DFA - Repair Primary structure EL | Set up equipment |  |  | 6 | 0 | Empty | 2022-05-02 | 2022-06-06 | 2022-05-02 | 2022-05-03 | 2022-05-02 | 2022-09-29 | 20 |  |  | DF /A /86/22000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062917 | ANOCR DFA - Repair Primary structure EL | Set up equipment |  |  | 132 | 0 | Empty | 2022-05-02 | 2022-06-06 | 2022-05-03 | 2022-05-19 | 2022-05-02 | 2022-09-29 | 30 |  |  | DF /A /86/22000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062917 | ANOCR DFA - Repair Primary structure EL | Set up equipment |  |  | 132.59999999999999431565811388 | 0 | Empty | 2022-05-02 | 2022-06-06 | 2022-05-19 | 2022-06-05 | 2022-05-02 | 2022-09-29 | 40 |  |  | DF /A /86/22000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100062917 | ANOCR DFA - Repair Primary structure EL | Set up equipment |  |  | 6 | 0 | Empty | 2022-05-02 | 2022-06-06 | 2022-06-05 | 2022-06-06 | 2022-05-02 | 2022-09-29 | 50 |  |  | DF /A /86/22000 - PRIM AND SEC STRUCT | Set up equipment | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235835 | 4Y 400V E-SWB MAINT DFFB-N-1829-01 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFB-N-1829-01 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235835 | 4Y 400V E-SWB MAINT DFFB-N-1829-01 | ISOLATION BY PRODUCTION |  |  | 14 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFB-N-1829-01 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235835 | 4Y 400V E-SWB MAINT DFFB-N-1829-01 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFB-N-1829-01 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235835 | 4Y 400V E-SWB MAINT DFFB-N-1829-01 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFB-N-1829-01 | ISOLATION BY PRODUCTION | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 0 | 0 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-01-01 | 2024-02-15 | 10 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 1 | 1 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-01-01 | 2024-02-15 | 20 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 1 | 1 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-01-01 | 2024-02-15 | 30 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 6 | 2 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2024-01-01 | 2024-02-15 | 31 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 2 | 2 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2024-01-01 | 2024-02-15 | 40 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 2 | 1 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2024-01-01 | 2024-02-15 | 50 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 1 | 1 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2024-01-01 | 2024-02-15 | 60 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 1 | 1 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-01-01 | 2024-02-15 | 70 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 1 | 1 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-01-01 | 2024-02-15 | 80 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100104498 | Seawater leak Condenser DFFA-C-1202 | Seawater leak Condenser DFFA-C-1202 |  |  | 2 | 2 | W19-W20 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-01-01 | 2024-02-15 | 90 |  |  | DF /F /09/DFFA-A-1202 | Seawater leak Condenser DFFA-C-1202 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088057 | Replace Escape climbing rope | Replace Escape climbing rope | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-10 | 2023-09-22 | 10 | SCH | SCH | DF /C /02/DFCM-KNR-0613 | Replace Escape climbing rope | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002965 | CMAT:Insulation assists FORCE 15421 | L3 build scaff. | PCNF | PCNF | 8.699999999999999289457264236 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-12 | 2026-01-01 | 2026-01-01 | 2019-06-27 | 2019-09-25 | 10 | PCNF | PCNF | DF /B /27/DFB-6-WOS-050-4135-AD-F | L3 build scaff. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002965 | CMAT:Insulation assists FORCE 15421 | L3 build scaff. | PCNF | PCNF | 26.800000000000000710542735752 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-12 | 2026-01-01 | 2026-01-03 | 2019-06-27 | 2019-09-25 | 20 | PCNF | PCNF | DF /B /27/DFB-6-WOS-050-4135-AD-F | L3 build scaff. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002965 | CMAT:Insulation assists FORCE 15421 | L3 build scaff. | PCNF | PCNF | 40.20000000000000284217094303 | 15 | CON-ELEC req'd | 2026-01-01 | 2026-01-12 | 2020-08-19 | 2020-08-25 | 2019-06-27 | 2019-09-25 | 30 | PCNF | PCNF | DF /B /27/DFB-6-WOS-050-4135-AD-F | L3 build scaff. | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002965 | CMAT:Insulation assists FORCE 15421 | L3 build scaff. | PCNF | PCNF | 48 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-12 | 2026-01-01 | 2026-01-06 | 2019-06-27 | 2019-09-25 | 40 | PCNF | PCNF | DF /B /27/DFB-6-WOS-050-4135-AD-F | L3 build scaff. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002965 | CMAT:Insulation assists FORCE 15421 | L3 build scaff. | PCNF | PCNF | 40.20000000000000284217094303 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-12 | 2026-01-06 | 2026-01-11 | 2019-06-27 | 2019-09-25 | 50 | PCNF | PCNF | DF /B /27/DFB-6-WOS-050-4135-AD-F | L3 build scaff. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002965 | CMAT:Insulation assists FORCE 15421 | L3 build scaff. | PCNF | PCNF | 20.100000000000001421085471515 | 0 | CON-ELEC req'd | 2026-01-01 | 2026-01-12 | 2026-01-11 | 2026-01-12 | 2019-06-27 | 2019-09-25 | 60 | PCNF | PCNF | DF /B /27/DFB-6-WOS-050-4135-AD-F | L3 build scaff. | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-01 | 2024-05-01 | 2018-07-19 | 2018-12-16 | 10 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 8 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-01 | 2024-05-01 | 2018-07-19 | 2018-12-16 | 11 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 144 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-01 | 2024-05-13 | 2018-07-19 | 2018-12-16 | 20 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 16 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-13 | 2024-05-14 | 2018-07-19 | 2018-12-16 | 21 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 4 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-14 | 2024-05-14 | 2018-07-19 | 2018-12-16 | 22 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 24 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-14 | 2024-05-15 | 2018-07-19 | 2018-12-16 | 23 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 12 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-15 | 2024-05-17 | 2018-07-19 | 2018-12-16 | 24 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 12 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-17 | 2024-05-18 | 2018-07-19 | 2018-12-16 | 25 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 8 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-18 | 2024-05-18 | 2018-07-19 | 2018-12-16 | 26 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | QAQCMECH | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 2 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-18 | 2024-05-18 | 2018-07-19 | 2018-12-16 | 27 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 32 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-18 | 2024-05-19 | 2018-07-19 | 2018-12-16 | 28 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | QAQCPAIN | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 2 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-19 | 2024-05-19 | 2018-07-19 | 2018-12-16 | 29 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 12 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-19 | 2024-05-20 | 2018-07-19 | 2018-12-16 | 30 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 90 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-20 | 2024-05-27 | 2018-07-19 | 2018-12-16 | 31 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 4 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-27 | 2024-05-28 | 2018-07-19 | 2018-12-16 | 32 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2018-07-19 | 2018-12-16 | 40 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2018-07-19 | 2018-12-16 | 50 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100024395 | FFSPR DAN FF replace DFF-4-DO-050-8032-A | R4 replace DFF-4-DO-050-8032-AB | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-05-28 | 2024-05-28 | 2024-05-28 | 2018-07-19 | 2018-12-16 | 60 | AWSC | AWSC | DF /F /28/DFF-4-DO-050-8032-AB-U | R4 replace DFF-4-DO-050-8032-AB | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-03-27 | 2023-04-01 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-04-02 | 2023-04-03 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-04-03 | 2023-04-03 | 2022-02-09 | 2022-07-09 | 33 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-04-03 | 2023-04-06 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-04-06 | 2023-04-09 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009250 | Insulation assist Bilfinger 21488(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-09 | 2023-04-09 | 2023-04-09 | 2022-02-09 | 2022-07-09 | 60 |  |  | DF /F /55/DFF-6-WI-035-7107-GF-U | Bilfinger inspection | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215386 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PO Ce-tec |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-20 | 2022-10-14 | 2022-11-19 | 10 |  |  | DF /C /09/A-1217 | PO Ce-tec | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215386 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PO Ce-tec |  |  | 12 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 20 |  |  | DF /C /09/A-1217 | PO Ce-tec | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215386 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PO Ce-tec |  |  | 1 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 30 |  |  | DF /C /09/A-1217 | PO Ce-tec | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400215386 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PO Ce-tec |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 40 |  |  | DF /C /09/A-1217 | PO Ce-tec | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215386 | 1Y HVAC SUPPLY AHU CHECK DFCI-B-1217A/B | PO Ce-tec |  |  | 0 | 0 | Empty | 2024-05-20 | 2024-05-21 | 2024-05-21 | 2024-05-21 | 2022-10-14 | 2022-11-19 | 50 |  |  | DF /C /09/A-1217 | PO Ce-tec | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 5 | 2 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 0 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 2 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 5 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 60 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 4 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 70 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 0 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-06-03 | 2025-11-19 | 80 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 0 | 20 | Empty | 2024-07-01 | 2024-07-02 | 2023-12-11 | 2024-01-17 | 2023-06-03 | 2025-11-19 | 90 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 0 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-06-03 | 2025-11-19 | 100 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-INST | 2200012587 | Replace DFFA-PSV-435005 - PSV 2023 | DFFA-PSV-435005 Offshore from WS Måde |  |  | 12 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-06-03 | 2025-11-19 | 110 |  |  | DF /F /32/DFFA-PSV-435005 | DFFA-PSV-435005 Offshore from WS Måde | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308994 | 6M LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-03-01 | 2024-03-20 | 10 |  |  | DF /F /50/SEAWATER-LIFTPUMPS | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | Unknown
B | NOSD | WPM | MTN-INST | MTN-TELE | 2400316039 | 4Y MANUAL CALL POINTS MAINT - DFE | MANUAL CALL POINTS TEST - DFE | SCH | SCH | 12 | 24 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-05 | 2024-02-21 | 2024-05-04 | 10 | SCH | SCH | DF /E /03/FZ-93-MANUAL-CALL-POINTS | MANUAL CALL POINTS TEST - DFE | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 149 | 375.5 | Empty | 2022-07-01 | 2022-08-31 | 2022-07-01 | 2022-07-16 | 2021-02-17 | 2021-02-22 | 10 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 26 | 42 | Empty | 2022-07-01 | 2022-08-31 | 2022-07-16 | 2022-07-19 | 2021-02-17 | 2021-02-22 | 20 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 30 | 0 | Empty | 2022-07-01 | 2022-08-31 | 2022-07-19 | 2022-07-22 | 2021-02-17 | 2021-02-22 | 30 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 20 | 44.5 | Empty | 2022-07-01 | 2022-08-31 | 2022-07-22 | 2022-07-24 | 2021-02-17 | 2021-02-22 | 40 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 119 | 65 | Empty | 2022-07-01 | 2022-08-31 | 2022-07-24 | 2022-08-06 | 2021-02-17 | 2021-02-22 | 50 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 18 | 173 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-06 | 2022-08-08 | 2021-02-17 | 2021-02-22 | 60 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 12 | 54 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-08 | 2022-08-09 | 2021-02-17 | 2021-02-22 | 70 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 12 | 0 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-09 | 2022-08-10 | 2021-02-17 | 2021-02-22 | 80 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 60 | 66 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-10 | 2022-08-16 | 2021-02-17 | 2021-02-22 | 90 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 70 | 4 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-16 | 2022-08-24 | 2021-02-17 | 2021-02-22 | 100 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 12 | 0 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-24 | 2022-08-25 | 2021-02-17 | 2021-02-22 | 110 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 60 | 91.5 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-25 | 2022-08-31 | 2021-02-17 | 2021-02-22 | 120 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002649 | DAF OCG NPT order - DFCSWL, DFC-P-5304. | operation_description_not_present | PCNF | PCNF | 0 | 0 | Empty | 2022-07-01 | 2022-08-31 | 2022-08-31 | 2022-08-31 | 2021-02-17 | 2021-02-22 | 130 | PCNF | PCNF | DF /C | operation_description_not_present | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400350901 | 3M SMOKE CABINS AIR FILT.REPLACE -DFC/G | SMOKE CABINS AIR FILT.REPLACE -DFC/G |  |  | 4 | 0 | Empty | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-10-12 | 10 |  |  | DF /C /82/DFCC-A-1332 | SMOKE CABINS AIR FILT.REPLACE -DFC/G | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-04-22 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 10 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 20 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 20 | 20 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 30 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 40 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 50 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 60 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 70 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 80 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 90 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 100 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 110 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 120 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 130 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 140 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 150 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 160 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 170 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 180 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-04-22 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 190 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-04-22 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 200 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064894 | DWESR 673316 Broken Cabin windows DFC | Replace window in level 2 lounge | PCNF | PCNF | 0 | 0 | Empty | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2024-05-07 | 2022-06-04 | 2022-11-01 | 210 | PCNF | PCNF | DF /C /82 | Replace window in level 2 lounge | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064268 | FLM - Replace steps EL +26200 ST012 | Install new steps |  |  | 10 | 0 | Empty | 2022-05-24 | 2022-06-01 | 2022-05-24 | 2022-05-25 | 2022-05-24 | 2022-10-21 | 10 |  |  | DF /B /86/26200 - GRATINGS | Install new steps | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064268 | FLM - Replace steps EL +26200 ST012 | Install new steps |  |  | 24 | 0 | Empty | 2022-05-24 | 2022-06-01 | 2022-05-25 | 2022-05-28 | 2022-05-24 | 2022-10-21 | 20 |  |  | DF /B /86/26200 - GRATINGS | Install new steps | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064268 | FLM - Replace steps EL +26200 ST012 | Install new steps |  |  | 24 | 0 | Empty | 2022-05-24 | 2022-06-01 | 2022-05-28 | 2022-05-31 | 2022-05-24 | 2022-10-21 | 30 |  |  | DF /B /86/26200 - GRATINGS | Install new steps | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064268 | FLM - Replace steps EL +26200 ST012 | Install new steps |  |  | 10 | 0 | Empty | 2022-05-24 | 2022-06-01 | 2022-05-31 | 2022-06-01 | 2022-05-24 | 2022-10-21 | 40 |  |  | DF /B /86/26200 - GRATINGS | Install new steps | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 2 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-01 | 2024-07-01 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 2 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-01 | 2024-07-02 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 24 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-02 | 2024-07-05 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 5 | 3 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-05 | 2024-07-06 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 0 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-06 | 2024-07-06 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 12 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-06 | 2024-07-08 | 2023-06-03 | 2025-11-19 | 60 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 2 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-08 | 2024-07-08 | 2023-06-03 | 2025-11-19 | 70 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 5 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-08 | 2024-07-09 | 2023-06-03 | 2025-11-19 | 80 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012625 | PSV Calibration - DFBA-PSV-38007 - PSV 2 | Prod Assist (breaking containment) |  |  | 4 | 0 | W29-W30 | 2024-07-01 | 2024-07-10 | 2024-07-09 | 2024-07-10 | 2023-06-03 | 2025-11-19 | 90 |  |  | DF /B /34/DFBA-PSV-38007 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322659 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-15 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 44 | 0 | Empty | 2024-10-05 | 2024-10-07 | 2024-10-05 | 2024-10-07 | 2024-03-16 | 2024-05-17 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-15 | ATEX EQUIPMENT INSPECTION | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 10 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-02 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 20 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-02 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 30 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-02 | 2024-07-04 | 2022-01-25 | 2022-06-24 | 40 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-04 | 2024-07-04 | 2022-01-25 | 2022-06-24 | 50 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 12 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-04 | 2024-07-06 | 2022-01-25 | 2022-06-24 | 60 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058717 | Divide HT supply DFFA-N-1802A-6-5 | Divide heattrace supply |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-06 | 2024-07-07 | 2022-01-25 | 2022-06-24 | 70 |  |  | DF /F /61/DFFA-N-1802A-6-5 | Divide heattrace supply | Unknown
4 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100024572 | CMAT:Trouble shooting filter sand | L3 Remove manhole cover | AWSC | AWSC | 10 | 0 | W49-50 | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-02 | 2019-08-20 | 2019-09-09 | 10 | AWSC | AWSC | DF /F /51/DFFA-FT-3503 | L3 Remove manhole cover | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100024572 | CMAT:Trouble shooting filter sand | L3 Remove manhole cover | AWSC | AWSC | 4 | 0 | W49-50 | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2025-01-02 | 2019-08-20 | 2019-09-09 | 20 | AWSC | AWSC | DF /F /51/DFFA-FT-3503 | L3 Remove manhole cover | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100024572 | CMAT:Trouble shooting filter sand | L3 Remove manhole cover | AWSC | AWSC | 22 | 0 | W49-50 | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2025-01-05 | 2019-08-20 | 2019-09-09 | 30 | AWSC | AWSC | DF /F /51/DFFA-FT-3503 | L3 Remove manhole cover | Unknown
4 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100024572 | CMAT:Trouble shooting filter sand | L3 Remove manhole cover | AWSC | AWSC | 4 | 0 | W49-50 | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-01-05 | 2019-08-20 | 2019-09-09 | 40 | AWSC | AWSC | DF /F /51/DFFA-FT-3503 | L3 Remove manhole cover | Unknown
4 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100024572 | CMAT:Trouble shooting filter sand | L3 Remove manhole cover | AWSC | AWSC | 10 | 0 | W49-50 | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-01-07 | 2019-08-20 | 2019-09-09 | 50 | AWSC | AWSC | DF /F /51/DFFA-FT-3503 | L3 Remove manhole cover | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100110791 | Level transmitter goes into alarm | Replace level transmitter |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-05-18 | 2024-09-30 | 10 |  |  | DF /C /05/DFCI-LT-17560 | Replace level transmitter | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 24 | 12 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-07-16 | 2024-07-18 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 5 | 3 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-05-02 | 2024-05-03 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 2 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-05-02 | 2024-05-03 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 4 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 12 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 5 | 6 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 4 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 10 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-10-19 | 2024-12-31 | 130 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284280 | PSV Calibration - DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 0 | 0 | W29-W30 | 2024-05-02 | 2024-09-14 | 2024-07-16 | 2024-07-16 | 2024-10-19 | 2024-12-31 | 140 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354129 | DFFA-PSV-354129 Offshore from WS Måde | Unknown
3 | NOSD | WGN | MTN-TURB | MTN-MECH | 2200011580 | LP Comp. 3rd failure of instr. piping | Pipe vibration survey | SCH | SCH | 0 | 0 | W33-34 IOP 15-23/8-22 | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2022-09-22 | 2023-02-04 | 10 | SCH | SCH | DF /F /31/DFFA-XCV-420531 | Pipe vibration survey | Unknown
3 | NOSD | WGN | MTN-TURB | VEN-MECH | 2200011580 | LP Comp. 3rd failure of instr. piping | Pipe vibration survey | SCH | SCH | 96 | 0 | W33-34 IOP 15-23/8-22 | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-10-02 | 2022-09-22 | 2023-02-04 | 20 | SCH | SCH | DF /F /31/DFFA-XCV-420531 | Pipe vibration survey | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-04-28 | 2017-06-07 | 10 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2017-04-28 | 2017-06-07 | 20 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2017-04-28 | 2017-06-07 | 30 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2017-04-28 | 2017-06-07 | 40 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2017-04-28 | 2017-06-07 | 50 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2017-04-28 | 2017-06-07 | 60 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | MTN-MECH | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2017-04-28 | 2017-06-07 | 70 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DFGHPSEP | WDF | MTN-MECH | PRODTECH | 2100025284 | CMAT:Aktuator er Ekstern læk DFGA-ESDV-5 | Isolaton of valve | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2017-04-28 | 2017-06-07 | 80 | AWSC | AWSC | DF /G /27/DFGA-ESDV-500650 | Isolaton of valve | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-SCAF | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 48 | 10 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-07 | 2025-01-07 | 2021-07-31 | 2021-10-29 | 10 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 10 | 10 | Empty | 2025-01-07 | 2025-01-13 | 2023-05-16 | 2023-05-22 | 2021-07-31 | 2021-10-29 | 20 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-07 | 2025-01-07 | 2021-07-31 | 2021-10-29 | 30 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-07 | 2025-01-08 | 2021-07-31 | 2021-10-29 | 40 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 14 | 6 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-08 | 2025-01-08 | 2021-07-31 | 2021-10-29 | 50 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-08 | 2025-01-09 | 2021-07-31 | 2021-10-29 | 60 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-09 | 2025-01-09 | 2021-07-31 | 2021-10-29 | 70 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-10 | 2025-01-10 | 2021-07-31 | 2021-10-29 | 80 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-10 | 2025-01-10 | 2021-07-31 | 2021-10-29 | 90 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-10 | 2025-01-11 | 2021-07-31 | 2021-10-29 | 100 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-SCAF | 2100052320 | DFCM-E-3660 outlet HCV-361403 seized in | Prepare rigging equipment | PCNFAWSC | PCNFAWSC | 24 | 0 | Empty | 2025-01-07 | 2025-01-13 | 2025-01-11 | 2025-01-13 | 2021-07-31 | 2021-10-29 | 110 | PCNFAWSC | PCNFAWSC | DF /C /21/DFCM-HCV-361403 | Prepare rigging equipment | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 30 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 40 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 50 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 60 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 70 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 80 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 90 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001473 | DK40 PAINT MATERIAL ORDER 2020/2021 | DK40 - CONSUMABLE PRODTECH |  |  | 0 | 0 | Empty | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2020-09-09 | 2021-07-06 | 100 |  |  | DF /F | DK40 - CONSUMABLE PRODTECH | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241146 | 6M CHEM DISTR PANEL MAINT-DFFA-A-39708 | CHEM DISTR PANEL MAINT-DFFA-A-39708 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-03-13 | 2023-04-01 | 10 |  |  | DF /F /75/DFFA-A-39708 | CHEM DISTR PANEL MAINT-DFFA-A-39708 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100064723 | "Supersug" HCV externally leaking | Install new HCV |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2022-04-03 | 2022-07-02 | 10 |  |  | DF /C /82 | Install new HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064723 | "Supersug" HCV externally leaking | Install new HCV |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2022-04-03 | 2022-07-02 | 20 |  |  | DF /C /82 | Install new HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064723 | "Supersug" HCV externally leaking | Install new HCV |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2022-04-03 | 2022-07-02 | 30 |  |  | DF /C /82 | Install new HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100064723 | "Supersug" HCV externally leaking | Install new HCV |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2022-04-03 | 2022-07-02 | 40 |  |  | DF /C /82 | Install new HCV | Unknown
A | NOSD | WPM | MTN-INST | MTN-TELE | 2400344338 | 6M PAGA SYSTEM TEST - DFD | PAGA SYSTEM TEST - DFD | SECE | SECE | 6 | 6 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-09-13 | 2024-09-29 | 10 | SECE | SECE | DF /D /08/PA-SYSTEM | PAGA SYSTEM TEST - DFD | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 3 | 3 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-08-16 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 10 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 16 | 22 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-08-16 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 13 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 2 | 3 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-08-20 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 15 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 8 | 9 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-08-21 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 20 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 2 | 10 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-09-13 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 25 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 8 | 12 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-08-30 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 26 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 3 | 10 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-09-09 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 27 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 24 | 30 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2021-08-30 | 2021-12-19 | 2018-09-29 | 2018-12-28 | 37 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 12 | 0 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2018-09-29 | 2018-12-28 | 47 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023998 | Replace DFBA-HCV-35788-U | L3 mont and demont scaf |  |  | 0 | 0 | W33-34 Break-in MSI Req. | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2018-09-29 | 2018-12-28 | 57 |  |  | DF /B /55/DFBA-HCV-35788-U | L3 mont and demont scaf | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400269633 | 1Y DFFA-FT-340558 PROD WATER - METERING | DFFA-FT-340558 PROD WATER - METERING | SCH | SCH | 7 | 0 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-18 | 2023-07-06 | 2023-08-22 | 10 | SCH | SCH | DF /F /27/DFFA-FT-340558 | DFFA-FT-340558 PROD WATER - METERING | Unknown
D | NOSD | WPM | MTN-INST | MTN-RIGG | 2400269633 | 1Y DFFA-FT-340558 PROD WATER - METERING | DFFA-FT-340558 PROD WATER - METERING | SCH | SCH | 6 | 0 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-18 | 2024-06-20 | 2023-07-06 | 2023-08-22 | 20 | SCH | SCH | DF /F /27/DFFA-FT-340558 | DFFA-FT-340558 PROD WATER - METERING | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339131 | DFD_1Y_JACKET ABOVE WATER INSPECTION | DFD_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /D /86/JACKET - L.A.T. TO EL 22960 | DFD_1Y_JACKET ABOVE WATER INSPECTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235845 | 4Y 400V E-SWB MAINT DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235845 | 4Y 400V E-SWB MAINT DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235845 | 4Y 400V E-SWB MAINT DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235845 | 4Y 400V E-SWB MAINT DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A07 | DE-ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400342398 | 1Y GAS LIFT INST/VALVES MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-08-09 | 2024-09-08 | 10 | SECE | SECE | DF /E /37/LIFT-GAS-MANIFOLD | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | MTN-INST | 2400342398 | 1Y GAS LIFT INST/VALVES MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 5 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-08-09 | 2024-09-08 | 20 | SECE | SECE | DF /E /37/LIFT-GAS-MANIFOLD | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400342398 | 1Y GAS LIFT INST/VALVES MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-08-09 | 2024-09-08 | 30 | SECE | SECE | DF /E /37/LIFT-GAS-MANIFOLD | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235556 | 4Y 3KV N-SWB MAINT DFCI-N-1801-17 | 3KV N-SWB INSP DFCI-N-1801-17 | AWSC | AWSC | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-29 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801-17-01 | 3KV N-SWB INSP DFCI-N-1801-17 | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235556 | 4Y 3KV N-SWB MAINT DFCI-N-1801-17 | 3KV N-SWB INSP DFCI-N-1801-17 | AWSC | AWSC | 25 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801-17-01 | 3KV N-SWB INSP DFCI-N-1801-17 | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235556 | 4Y 3KV N-SWB MAINT DFCI-N-1801-17 | 3KV N-SWB INSP DFCI-N-1801-17 | AWSC | AWSC | 8 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801-17-01 | 3KV N-SWB INSP DFCI-N-1801-17 | Unknown
C | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235556 | 4Y 3KV N-SWB MAINT DFCI-N-1801-17 | 3KV N-SWB INSP DFCI-N-1801-17 | AWSC | AWSC | 1 | 0 | 24-W03-04 | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-12-31 | 2023-03-29 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801-17-01 | 3KV N-SWB INSP DFCI-N-1801-17 | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002917 | DFF-Insulation assists FORCE 13518. | L3 Carefully remove insulation | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-22 | 2020-09-10 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /F /31/DFF-6-GPS-043-7016-DB-P | L3 Carefully remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002917 | DFF-Insulation assists FORCE 13518. | L3 Carefully remove insulation | PCNF | PCNF | 2 | 4.5 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-15 | 2020-08-22 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /F /31/DFF-6-GPS-043-7016-DB-P | L3 Carefully remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002917 | DFF-Insulation assists FORCE 13518. | L3 Carefully remove insulation | PCNF | PCNF | 4 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /F /31/DFF-6-GPS-043-7016-DB-P | L3 Carefully remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002917 | DFF-Insulation assists FORCE 13518. | L3 Carefully remove insulation | PCNF | PCNF | 2 | 7 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /F /31/DFF-6-GPS-043-7016-DB-P | L3 Carefully remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002917 | DFF-Insulation assists FORCE 13518. | L3 Carefully remove insulation | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /F /31/DFF-6-GPS-043-7016-DB-P | L3 Carefully remove insulation | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000758 | MAX/MIN 01.01.19 TIL 31.12.20 | MAX/MIN 21.03 20 |  |  | 1 | 0 | Empty | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2019-07-07 | 2019-07-07 | 10 |  |  | DF /C | MAX/MIN 21.03 20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000758 | MAX/MIN 01.01.19 TIL 31.12.20 | MAX/MIN 21.03 20 |  |  | 0 | 0 | Empty | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2019-07-07 | 2019-07-07 | 20 |  |  | DF /C | MAX/MIN 21.03 20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000758 | MAX/MIN 01.01.19 TIL 31.12.20 | MAX/MIN 21.03 20 |  |  | 0 | 0 | Empty | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2019-07-07 | 2019-07-07 | 30 |  |  | DF /C | MAX/MIN 21.03 20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000758 | MAX/MIN 01.01.19 TIL 31.12.20 | MAX/MIN 21.03 20 |  |  | 0 | 0 | Empty | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2019-07-07 | 2019-07-07 | 40 |  |  | DF /C | MAX/MIN 21.03 20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000758 | MAX/MIN 01.01.19 TIL 31.12.20 | MAX/MIN 21.03 20 |  |  | 0 | 0 | Empty | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 | 2019-07-07 | 2019-07-07 | 50 |  |  | DF /C | MAX/MIN 21.03 20 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100868 | Pipe broken off fire monitor | Mount oscillation unit again with new |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2024-04-21 | 2026-10-08 | 10 |  |  | DF /A /01/DFAA-WM-0333 | Mount oscillation unit again with new | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100100868 | Pipe broken off fire monitor | Mount oscillation unit again with new |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2024-04-21 | 2026-10-08 | 20 |  |  | DF /A /01/DFAA-WM-0333 | Mount oscillation unit again with new | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100100868 | Pipe broken off fire monitor | Mount oscillation unit again with new |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-04-21 | 2026-10-08 | 30 |  |  | DF /A /01/DFAA-WM-0333 | Mount oscillation unit again with new | Unknown
2 | DFG-FUEL | WDF | MTN-ELEC | PRODTECH | 2100078159 | Replace relays for superheater | Replace relays for superheater |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-11-18 | 2023-01-02 | 10 |  |  | DF /G /70/DFGA-CP-5742 | Replace relays for superheater | Unknown
2 | DFG-FUEL | WDF | MTN-ELEC | MTN-ELEC | 2100078159 | Replace relays for superheater | Replace relays for superheater |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2022-11-18 | 2023-01-02 | 20 |  |  | DF /G /70/DFGA-CP-5742 | Replace relays for superheater | Unknown
2 | DFG-FUEL | WDF | MTN-ELEC | PRODTECH | 2100078159 | Replace relays for superheater | Replace relays for superheater |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-11-18 | 2023-01-02 | 30 |  |  | DF /G /70/DFGA-CP-5742 | Replace relays for superheater | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2020-10-24 | 2021-01-22 | 10 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-SCAF | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-02 | 2020-10-24 | 2021-01-22 | 20 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | PRODTECH | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2025-01-03 | 2020-10-24 | 2021-01-22 | 30 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-03 | 2020-10-24 | 2021-01-22 | 40 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-03 | 2020-10-24 | 2021-01-22 | 50 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-INST | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2025-01-05 | 2020-10-24 | 2021-01-22 | 60 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | PRODTECH | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-01-06 | 2020-10-24 | 2021-01-22 | 70 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2025-01-06 | 2020-10-24 | 2021-01-22 | 80 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | DFC-TSEP | WDF | MTN-MECH | MTN-SCAF | 2100038915 | Replace valves for LT 34002 TEST SEP. | Scaffold erection step-up Work PF | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2025-01-07 | 2020-10-24 | 2021-01-22 | 90 | AWSC | AWSC | DF /C /11/DFCI-V-3401 | Scaffold erection step-up Work PF | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080522 | LG ESDV not activate ZSO DFF440101 | Troubleshoot connection betwen Actuator |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-24 | 2023-05-08 | 10 |  |  | DF /F /31/DFFA-ESDV-440101 | Troubleshoot connection betwen Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080522 | LG ESDV not activate ZSO DFF440101 | Troubleshoot connection betwen Actuator |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-24 | 2023-05-08 | 20 |  |  | DF /F /31/DFFA-ESDV-440101 | Troubleshoot connection betwen Actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100080522 | LG ESDV not activate ZSO DFF440101 | Troubleshoot connection betwen Actuator |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-24 | 2023-05-08 | 30 |  |  | DF /F /31/DFFA-ESDV-440101 | Troubleshoot connection betwen Actuator | Unknown
A | DFF-1610 | WPM | MTN-TURB | MTN-TURB | 2400342643 | 1500H TURBINE WASH, COUNTER-DFFA-A-1610 | TURBINE WASH, COUNTER-DFFA-A-1610 | AWSC | AWSC | 8 | 0 | W33-W34 | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-16 | 2024-07-03 | 2024-07-13 | 10 | AWSC | AWSC | DF /F /60/DFFA-A-1610 | TURBINE WASH, COUNTER-DFFA-A-1610 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400263659 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3650 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2023-07-05 | 2023-07-21 | 10 |  |  | DF /C /23/DFCM-A-3650 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263659 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3650 | ISOLATION BY PRODUCTION |  |  | 20 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-08-03 | 2023-07-05 | 2023-07-21 | 20 |  |  | DF /C /23/DFCM-A-3650 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263659 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3650 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-04 | 2023-07-05 | 2023-07-21 | 30 |  |  | DF /C /23/DFCM-A-3650 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400263659 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3650 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-07-05 | 2023-07-21 | 40 |  |  | DF /C /23/DFCM-A-3650 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400284145 | 3Y DFFA-A-1610 FUEL - METERING | DFFA-A-1610 FUEL - METERING | AWSC | AWSC | 3 | 0 | Empty | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-08-17 | 2023-10-30 | 10 | AWSC | AWSC | DF /F /60/DFFA-A-1610 | DFFA-A-1610 FUEL - METERING | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100111616 | MIRQ DFG IPHP Water mist (Reserve bank) | Troubleshooting |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-16 | 2024-09-28 | 10 |  |  | DF /G /01/DFGA-WIT-043328B | Troubleshooting | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325735 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39250 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39250 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /A /75/DFAA-A-39250 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39250 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400269349 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-12 | 2023-07-18 | 2023-08-17 | 10 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269349 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL ISOLATION |  |  | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-14 | 2023-07-18 | 2023-08-17 | 20 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269349 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL ISOLATION |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-14 | 2024-08-15 | 2023-07-18 | 2023-08-17 | 30 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400269349 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL ISOLATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-15 | 2023-07-18 | 2023-08-17 | 40 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400269349 | 1Y HVAC AHU/EXH PAINT CONT. CHECK - DFFA | PERSONAL ISOLATION |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-15 | 2024-08-16 | 2023-07-18 | 2023-08-17 | 50 |  |  | DF /F /09/DFFA-A-1279 | PERSONAL ISOLATION | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009213 | Insulation assist Bilfinger 21674(COMP - | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /A /28/DFA-4-FHS-040-9128-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009213 | Insulation assist Bilfinger 21674(COMP - | Bilfinger inspection |  |  | 8 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /A /28/DFA-4-FHS-040-9128-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009213 | Insulation assist Bilfinger 21674(COMP - | Bilfinger inspection |  |  | 3 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 22 |  |  | DF /A /28/DFA-4-FHS-040-9128-AD-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009213 | Insulation assist Bilfinger 21674(COMP - | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-28 | 2023-03-29 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /A /28/DFA-4-FHS-040-9128-AD-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081336 | Transmitterhus er defekt dfga-ft-550020 | Replace Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 5 |  |  | DF /G /52/DFGA-FT-550020 | Replace Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081336 | Transmitterhus er defekt dfga-ft-550020 | Replace Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 10 |  |  | DF /G /52/DFGA-FT-550020 | Replace Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100081336 | Transmitterhus er defekt dfga-ft-550020 | Replace Flow meter |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-04 | 2023-07-17 | 20 |  |  | DF /G /52/DFGA-FT-550020 | Replace Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081336 | Transmitterhus er defekt dfga-ft-550020 | Replace Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 25 |  |  | DF /G /52/DFGA-FT-550020 | Replace Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081336 | Transmitterhus er defekt dfga-ft-550020 | Replace Flow meter |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 30 |  |  | DF /G /52/DFGA-FT-550020 | Replace Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081336 | Transmitterhus er defekt dfga-ft-550020 | Replace Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 40 |  |  | DF /G /52/DFGA-FT-550020 | Replace Flow meter | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 2 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 2 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-10-05 | 2024-10-05 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 5 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-10-05 | 2024-10-06 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 2 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-10-06 | 2024-10-06 | 2024-10-12 | 2024-12-31 | 24 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 4 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-10-06 | 2024-10-07 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 5 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-12-05 | 2024-12-06 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 4 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 2 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284234 | PSV Exchnage - DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | AWSC | AWSC | 2 | 0 | W15-W16 | 2024-10-05 | 2024-12-06 | 2024-12-06 | 2024-12-06 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /B /75/DFBA-PSV-39122 | Re-certify PSV (Backload PSV) | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 8 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-21 | 2024-06-22 | 2021-09-09 | 2022-02-06 | 5 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 4 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-23 | 2024-06-23 | 2021-09-09 | 2022-02-06 | 10 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 4 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-23 | 2024-06-23 | 2021-09-09 | 2022-02-06 | 11 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 6 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-24 | 2024-06-24 | 2021-09-09 | 2022-02-06 | 20 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 1 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-24 | 2024-06-24 | 2021-09-09 | 2022-02-06 | 30 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 24 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-25 | 2024-06-27 | 2021-09-09 | 2022-02-06 | 35 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 12 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-28 | 2024-06-29 | 2021-09-09 | 2022-02-06 | 40 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 75 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-29 | 2024-07-05 | 2021-09-09 | 2022-02-06 | 50 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 12 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-29 | 2024-06-30 | 2021-09-09 | 2022-02-06 | 80 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 20 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-01 | 2024-07-03 | 2021-09-09 | 2022-02-06 | 90 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 20 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-03 | 2024-07-05 | 2021-09-09 | 2022-02-06 | 100 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 10 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-06 | 2024-07-07 | 2021-09-09 | 2022-02-06 | 110 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 20 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-07 | 2024-07-09 | 2021-09-09 | 2022-02-06 | 120 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 24 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-09 | 2024-07-12 | 2021-09-09 | 2022-02-06 | 125 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 1 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-12 | 2024-07-12 | 2021-09-09 | 2022-02-06 | 130 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 10 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-13 | 2024-07-14 | 2021-09-09 | 2022-02-06 | 140 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 12 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-14 | 2024-07-15 | 2021-09-09 | 2022-02-06 | 150 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 24 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-15 | 2024-07-21 | 2021-09-09 | 2022-02-06 | 160 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 2 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-07-21 | 2024-07-22 | 2021-09-09 | 2022-02-06 | 170 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 0 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-21 | 2024-06-21 | 2021-09-09 | 2022-02-06 | 180 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 0 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-21 | 2024-06-21 | 2021-09-09 | 2022-02-06 | 190 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 50 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-21 | 2024-07-03 | 2021-09-09 | 2022-02-06 | 200 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100051373 | DFGA-A-6140: Replace boom winch | Order bulldog clamps and SAE blind flang |  |  | 0 | 0 | Empty | 2024-06-21 | 2024-07-22 | 2024-06-21 | 2024-06-21 | 2021-09-09 | 2022-02-06 | 210 |  |  | DF /G /78/DFGA-A-6140 | Order bulldog clamps and SAE blind flang | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 4.4000000000000003552713678785 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2020-08-10 | 2020-09-01 | 2019-07-18 | 2019-10-16 | 10 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 17.399999999999998578914528472 | 9 | Empty | 2021-12-16 | 2024-01-16 | 2020-08-28 | 2020-09-06 | 2019-07-18 | 2019-10-16 | 20 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 168 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2024-01-08 | 2024-01-16 | 2019-07-18 | 2019-10-16 | 30 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 34.799999999999997157829056945 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2021-12-16 | 2021-12-18 | 2019-07-18 | 2019-10-16 | 40 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 0 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2024-01-08 | 2024-01-08 | 2019-07-18 | 2019-10-16 | 50 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 12 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2024-01-08 | 2024-01-09 | 2019-07-18 | 2019-10-16 | 60 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 24 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2024-01-08 | 2024-01-09 | 2019-07-18 | 2019-10-16 | 70 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002955 | Insulation assists FORCE 14191 | REMOVE INSULATION | PCNF | PCNF | 16 | 0 | Empty | 2021-12-16 | 2024-01-16 | 2024-01-08 | 2024-01-09 | 2019-07-18 | 2019-10-16 | 80 | PCNF | PCNF | DF /C /27/DFC-10-WOS-050-9031-AB-U | REMOVE INSULATION | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049803 | FLMR DFC N/west stair Corroded stair tre | Material handling |  |  | 0 | 0 | Empty | 2021-09-14 | 2021-09-15 | 2021-09-14 | 2021-09-14 | 2021-06-02 | 2021-08-31 | 10 |  |  | DF /C /86/35000 - GRATINGS | Material handling | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049803 | FLMR DFC N/west stair Corroded stair tre | Material handling |  |  | 2 | 0 | Empty | 2021-09-14 | 2021-09-15 | 2021-09-14 | 2021-09-14 | 2021-06-02 | 2021-08-31 | 20 |  |  | DF /C /86/35000 - GRATINGS | Material handling | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049803 | FLMR DFC N/west stair Corroded stair tre | Material handling |  |  | 2 | 0 | Empty | 2021-09-14 | 2021-09-15 | 2021-09-14 | 2021-09-14 | 2021-06-02 | 2021-08-31 | 30 |  |  | DF /C /86/35000 - GRATINGS | Material handling | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049803 | FLMR DFC N/west stair Corroded stair tre | Material handling |  |  | 1 | 0 | Empty | 2021-09-14 | 2021-09-15 | 2021-09-14 | 2021-09-14 | 2021-06-02 | 2021-08-31 | 40 |  |  | DF /C /86/35000 - GRATINGS | Material handling | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049803 | FLMR DFC N/west stair Corroded stair tre | Material handling |  |  | 12 | 0 | Empty | 2021-09-14 | 2021-09-15 | 2021-09-14 | 2021-09-15 | 2021-06-02 | 2021-08-31 | 50 |  |  | DF /C /86/35000 - GRATINGS | Material handling | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100049803 | FLMR DFC N/west stair Corroded stair tre | Material handling |  |  | 1 | 0 | Empty | 2021-09-14 | 2021-09-15 | 2021-09-15 | 2021-09-15 | 2021-06-02 | 2021-08-31 | 60 |  |  | DF /C /86/35000 - GRATINGS | Material handling | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235919 | 1Y SW FILTERS & BLOWERS MAINT - DFB | SW FILTERS & BLOWERS MAINT - DFB |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-02-18 | 2023-03-26 | 10 |  |  | DF /B /51/DFBA-FT-3505 | SW FILTERS & BLOWERS MAINT - DFB | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235919 | 1Y SW FILTERS & BLOWERS MAINT - DFB | SW FILTERS & BLOWERS MAINT - DFB |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-02-18 | 2023-03-26 | 20 |  |  | DF /B /51/DFBA-FT-3505 | SW FILTERS & BLOWERS MAINT - DFB | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-24 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 10 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-25 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 20 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 7 | 6 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-25 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 30 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 7 | 16 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-25 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 40 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-27 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 80 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-27 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 100 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-27 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 110 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-24 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 996 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-24 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 997 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-24 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 998 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2022-10-24 | 2022-11-07 | 2022-12-11 | 2025-05-29 | 999 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 12 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2022-12-11 | 2025-05-29 | 1009 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-12-11 | 2025-05-29 | 1019 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100071671 | Change out XCV-500790 | Change Valve | PCNF | PCNF | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-12-11 | 2025-05-29 | 1029 | PCNF | PCNF | DF /F /27/DFFA-XCV-500790 | Change Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097350 | DFGA-HRF-03311 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 1 | 0 | W35-W36 | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 10 | SECE | SECE | DF /G /01/DFGA-HRF-03311 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097350 | DFGA-HRF-03311 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 2 | 0 | W35-W36 | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 20 | SECE | SECE | DF /G /01/DFGA-HRF-03311 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097350 | DFGA-HRF-03311 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 1 | 0 | W35-W36 | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 30 | SECE | SECE | DF /G /01/DFGA-HRF-03311 | Replace hose on hosereel | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329511 | 3M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-06-08 | 2024-06-18 | 10 |  |  | DF /G /07/DFGA-A-5940 | HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400346581 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | RETURN TO OPERATION | SECE | SECE | 1 | 0 | Empty | 2024-09-04 | 2024-09-07 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2024-10-04 | 10 | SECE | SECE | DF /E /01/DFEY-A-0303 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400346581 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | RETURN TO OPERATION | SECE | SECE | 12 | 0 | Empty | 2024-09-04 | 2024-09-07 | 2024-09-04 | 2024-09-07 | 2024-09-04 | 2024-10-04 | 20 | SECE | SECE | DF /E /01/DFEY-A-0303 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400346581 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | RETURN TO OPERATION | SECE | SECE | 1 | 0 | Empty | 2024-09-04 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-04 | 2024-10-04 | 30 | SECE | SECE | DF /E /01/DFEY-A-0303 | RETURN TO OPERATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400346581 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | RETURN TO OPERATION | SECE | SECE | 2 | 0 | Empty | 2024-09-04 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2024-09-04 | 2024-10-04 | 40 | SECE | SECE | DF /E /01/DFEY-A-0303 | RETURN TO OPERATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245863 | 1YL-AUS TOOLS DFC | L-AUS TOOLS MAINTENANCE CHECK |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-08 | 2023-05-25 | 10 |  |  | DF /C /61 | L-AUS TOOLS MAINTENANCE CHECK | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400245863 | 1YL-AUS TOOLS DFC | L-AUS TOOLS MAINTENANCE CHECK |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-08 | 2023-05-25 | 20 |  |  | DF /C /61 | L-AUS TOOLS MAINTENANCE CHECK | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329528 | 1Y BRIDGE TROLLEY 10T - DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | AWSC | AWSC | 7 | 0 | W31-W32 | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-02 | 2024-05-07 | 2024-06-12 | 10 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329528 | 1Y BRIDGE TROLLEY 10T - DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | AWSC | AWSC | 10 | 0 | W31-W32 | 2024-08-01 | 2024-08-05 | 2024-08-02 | 2024-08-05 | 2024-05-07 | 2024-06-12 | 20 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 0 | 24 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2022-04-27 | 2023-02-21 | 10 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 5 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2022-04-27 | 2023-02-21 | 20 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 3 | 1 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-16 | 2022-04-27 | 2023-02-21 | 30 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 16 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-18 | 2022-04-27 | 2023-02-21 | 40 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 10 | 3 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-19 | 2022-04-27 | 2023-02-21 | 50 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 10 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-19 | 2022-04-27 | 2023-02-21 | 60 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 8 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-17 | 2022-04-27 | 2023-02-21 | 90 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 5 | 3 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2022-04-27 | 2023-02-21 | 100 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 8 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-17 | 2022-04-27 | 2023-02-21 | 110 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 3 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2022-04-27 | 2023-02-21 | 120 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100058085 | DFFA-P-3902 Kemikalieunit to be overhaul | Mech installation new pumpskid+strainer |  |  | 3 | 0 | W47-48 SR MPM | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2022-04-27 | 2023-02-21 | 130 |  |  | DF /F /75/DFFA-P-3902 | Mech installation new pumpskid+strainer | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009234 | Insulation assist bilfinger 22073(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /F /27/DFF-3-DO-050-8070-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009234 | Insulation assist bilfinger 22073(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /F /27/DFF-3-DO-050-8070-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009234 | Insulation assist bilfinger 22073(COMP) | Bilfinger inspection |  |  | 3 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 22 |  |  | DF /F /27/DFF-3-DO-050-8070-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009234 | Insulation assist bilfinger 22073(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-29 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /F /27/DFF-3-DO-050-8070-AD-T | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023703 | DFC/78: SMAT:DFC øverste wireskiver kan | Remove Wire disc for cleaning |  |  | 3 | 0 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-15 | 2024-07-16 | 2018-01-06 | 2018-04-06 | 10 |  |  | DF /C /78/DFCI-X-6101 | Remove Wire disc for cleaning | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100023703 | DFC/78: SMAT:DFC øverste wireskiver kan | Remove Wire disc for cleaning |  |  | 48 | 0 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-16 | 2024-07-22 | 2018-01-06 | 2018-04-06 | 20 |  |  | DF /C /78/DFCI-X-6101 | Remove Wire disc for cleaning | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023703 | DFC/78: SMAT:DFC øverste wireskiver kan | Remove Wire disc for cleaning |  |  | 48 | 0 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-16 | 2024-07-22 | 2018-01-06 | 2018-04-06 | 30 |  |  | DF /C /78/DFCI-X-6101 | Remove Wire disc for cleaning | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023703 | DFC/78: SMAT:DFC øverste wireskiver kan | Remove Wire disc for cleaning |  |  | 3 | 0 | W29-W30 | 2024-07-15 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2018-01-06 | 2018-04-06 | 40 |  |  | DF /C /78/DFCI-X-6101 | Remove Wire disc for cleaning | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 150 | 112 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 10 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 3 | 3 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 20 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 3 | 3 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 30 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 80 | 205 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 40 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-INST | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 30 | 15 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 45 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-ELEC | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 30 | 10 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 46 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 10 | 24 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 50 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 10 | 24 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 60 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 80 | 189 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 70 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 30 | 89 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 80 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 3 | 56 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 90 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 3 | 3 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 100 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 3 | 6 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 110 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-LAGG | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 30 | 0 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 115 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 120 | 98 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 120 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 130 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 140 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 150 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 160 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-07-30 | 2022-12-27 | 170 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 12 | 12 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-04 | 2022-07-30 | 2022-12-27 | 180 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 24 | 24 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-07 | 2022-07-30 | 2022-12-27 | 190 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100067968 | ESDV-350100 internally leaking. | PO Altrad | PCNFSCH | PCNFSCH | 24 | 24 | Empty | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-07 | 2022-07-30 | 2022-12-27 | 200 | PCNFSCH | PCNFSCH | DF /F /54/DFFA-ESDV-350100 | PO Altrad | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 8 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-17 | 2021-02-07 | 2021-03-19 | 10 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-17 | 2024-09-18 | 2021-02-07 | 2021-03-19 | 20 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-18 | 2021-02-07 | 2021-03-19 | 30 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-19 | 2021-02-07 | 2021-03-19 | 40 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-19 | 2021-02-07 | 2021-03-19 | 50 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-RIGG | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-19 | 2024-09-20 | 2021-02-07 | 2021-03-19 | 60 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-19 | 2024-09-20 | 2021-02-07 | 2021-03-19 | 70 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-20 | 2024-09-21 | 2021-02-07 | 2021-03-19 | 80 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 4 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-21 | 2024-09-22 | 2021-02-07 | 2021-03-19 | 90 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-INST | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2021-02-07 | 2021-03-19 | 100 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-23 | 2024-09-24 | 2021-02-07 | 2021-03-19 | 110 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-24 | 2021-02-07 | 2021-03-19 | 120 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-26 | 2021-02-07 | 2021-03-19 | 130 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100044853 | DFG PCV-570437B Dårlig integritet | Isolate PCV |  |  | 0 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-15 | 2021-02-07 | 2021-03-19 | 140 |  |  | DF /G /70/DFGA-PCV-570437B | Isolate PCV | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-SCAF | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-01 | 2025-01-03 | 2019-06-21 | 2020-06-15 | 10 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-03 | 2025-01-05 | 2019-06-21 | 2020-06-15 | 15 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-05 | 2025-01-06 | 2019-06-21 | 2020-06-15 | 20 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-06 | 2025-01-08 | 2019-06-21 | 2020-06-15 | 30 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-06 | 2025-01-08 | 2019-06-21 | 2020-06-15 | 40 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | PRODTECH | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-08 | 2025-01-09 | 2019-06-21 | 2020-06-15 | 50 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-RIGG | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-09 | 2025-01-09 | 2019-06-21 | 2020-06-15 | 60 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-SCAF | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 16 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-09 | 2025-01-11 | 2019-06-21 | 2020-06-15 | 70 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
4 | DFX-WI | WDF | MTN-MECH | MTN-MECH | 2100025580 | DFBA-HCV-35730 has to be changed | Dummy line for missing bolting | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-11 | 2025-01-01 | 2025-01-01 | 2019-06-21 | 2020-06-15 | 80 | AWSC | AWSC | DF /B /55/DFBA-HCV-35730 | Dummy line for missing bolting | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 17 | 1.5 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-03 | 2023-04-04 | 2021-03-24 | 2021-03-29 | 10 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 3 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-04 | 2023-04-04 | 2021-03-24 | 2021-03-29 | 20 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 3 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-04 | 2023-04-05 | 2021-03-24 | 2021-03-29 | 30 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 2 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-05 | 2023-04-05 | 2021-03-24 | 2021-03-29 | 40 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 13 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-05 | 2023-04-06 | 2021-03-24 | 2021-03-29 | 50 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 2 | 3 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-06 | 2023-04-06 | 2021-03-24 | 2021-03-29 | 60 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 1 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-06 | 2023-04-06 | 2021-03-24 | 2021-03-29 | 70 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 1 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-06 | 2023-04-06 | 2021-03-24 | 2021-03-29 | 80 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 7 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-06 | 2023-04-07 | 2021-03-24 | 2021-03-29 | 90 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 8 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-07 | 2023-04-08 | 2021-03-24 | 2021-03-29 | 100 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 1 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-08 | 2023-04-08 | 2021-03-24 | 2021-03-29 | 110 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002823 | DAF OCG NPT order -ENG469O-PSV, METHANOL | Clean-up & housekeeping | PCNF | PCNF | 7 | 0 | Empty | 2023-04-03 | 2023-04-09 | 2023-04-08 | 2023-04-09 | 2021-03-24 | 2021-03-29 | 120 | PCNF | PCNF | DF /G | Clean-up & housekeeping | Unknown
3 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200010342 | Remove Insulation DFGA-V-3460 for Scan | Remove of insulation. | PCNFSCH | PCNFSCH | 0 | 0 | W21-22 MPM | 2023-01-16 | 2023-01-16 | 2022-05-31 | 2022-07-11 | 2022-04-11 | 2022-05-21 | 10 | PCNFSCH | PCNFSCH | DF /G /27/DFGA-V-3460 | Remove of insulation. | Unknown
3 | NOSD | WGN | VEN-INSP | MTN-ROPE | 2200010342 | Remove Insulation DFGA-V-3460 for Scan | Remove of insulation. | PCNFSCH | PCNFSCH | 12 | 25 | W21-22 MPM | 2023-01-16 | 2023-01-16 | 2022-05-31 | 2022-07-11 | 2022-04-11 | 2022-05-21 | 20 | PCNFSCH | PCNFSCH | DF /G /27/DFGA-V-3460 | Remove of insulation. | Unknown
3 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200010342 | Remove Insulation DFGA-V-3460 for Scan | Remove of insulation. | PCNFSCH | PCNFSCH | 24 | 0 | W21-22 MPM | 2023-01-16 | 2023-01-16 | 2022-06-01 | 2022-07-11 | 2022-04-11 | 2022-05-21 | 30 | PCNFSCH | PCNFSCH | DF /G /27/DFGA-V-3460 | Remove of insulation. | Unknown
3 | NOSD | WGN | VEN-INSP | MTN-ROPE | 2200010342 | Remove Insulation DFGA-V-3460 for Scan | Remove of insulation. | PCNFSCH | PCNFSCH | 20 | 0 | W21-22 MPM | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2022-04-11 | 2022-05-21 | 40 | PCNFSCH | PCNFSCH | DF /G /27/DFGA-V-3460 | Remove of insulation. | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 4 | 0 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-01 | 2024-07-02 | 2022-05-21 | 2022-10-18 | 10 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 8 | 8 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-02 | 2024-07-03 | 2022-05-21 | 2022-10-18 | 20 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 19 | 19 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-03 | 2024-07-08 | 2022-05-21 | 2022-10-18 | 30 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 12 | 12 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-08 | 2024-07-11 | 2022-05-21 | 2022-10-18 | 40 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 2 | 12 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-11 | 2024-07-11 | 2022-05-21 | 2022-10-18 | 50 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 19 | 19 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-11 | 2024-07-16 | 2022-05-21 | 2022-10-18 | 60 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 20 | 12 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-16 | 2024-07-21 | 2022-05-21 | 2022-10-18 | 70 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 3 | 12 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-21 | 2024-07-22 | 2022-05-21 | 2022-10-18 | 80 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 4 | 4 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2022-05-21 | 2022-10-18 | 90 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 0 | 0 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-01 | 2024-07-01 | 2022-05-21 | 2022-10-18 | 100 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 0 | 0 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-01 | 2024-07-01 | 2022-05-21 | 2022-10-18 | 110 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 10 | 10 | Empty | 2024-07-01 | 2024-07-22 | 2024-06-29 | 2024-06-29 | 2022-05-21 | 2022-10-18 | 120 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 0 | 0 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-01 | 2024-07-01 | 2022-05-21 | 2022-10-18 | 130 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100064010 | DFF-11 Manifold Vlv's replacement | Setup/de-rig rigg. equipment | PCNF | PCNF | 0 | 0 | Empty | 2024-07-01 | 2024-07-22 | 2024-07-01 | 2024-07-01 | 2022-05-21 | 2022-10-18 | 140 | PCNF | PCNF | DF /F /55/WATER-INJECTION-MANIFOLD | Setup/de-rig rigg. equipment | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400346574 | 1Y CHEM DIST PANEL MAINT-DFFA-A-39704 | CHEM DIST PANEL MAINT -DFFA-A-39704 |  |  | 16 | 0 | Empty | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-10-01 | 10 |  |  | DF /F /75/DFFA-A-39704 | CHEM DIST PANEL MAINT -DFFA-A-39704 | Unknown
C | NOSD | WPM | MTN-TURB | MTN-TURB | 2400321263 | 1M Preventive Turbine Idle Mode | OPSTART AF TURBINE I IDLE MODE. |  |  | 0 | 0 | W19-W20 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2024-05-03 | 2024-05-08 | 1 |  |  | DF /F /31/DFFA-CT-4301 | OPSTART AF TURBINE I IDLE MODE. | Unknown
C | NOSD | WPM | MTN-TURB | MTN-TURB | 2400321263 | 1M Preventive Turbine Idle Mode | OPSTART AF TURBINE I IDLE MODE. |  |  | 12 | 0 | W19-W20 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-04 | 2024-05-03 | 2024-05-08 | 10 |  |  | DF /F /31/DFFA-CT-4301 | OPSTART AF TURBINE I IDLE MODE. | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-29 | 2024-10-30 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-29 | 2024-10-30 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 24 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-07-30 | 2024-08-01 | 2024-10-30 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 5 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-03 | 2024-10-30 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-03 | 2024-10-30 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-04 | 2024-10-30 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 12 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-06 | 2024-10-30 | 2024-12-31 | 70 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-06 | 2024-08-06 | 2024-10-30 | 2024-12-31 | 80 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 5 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-06 | 2024-08-07 | 2024-10-30 | 2024-12-31 | 90 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 4 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2024-10-30 | 2024-12-31 | 100 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2024-10-30 | 2024-12-31 | 110 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-09 | 2024-08-09 | 2024-10-30 | 2024-12-31 | 120 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284242 | PSV Exchange - DFCI-PSV-50450 | Scaffolding | AWSC | AWSC | 10 | 0 | Empty | 2024-07-29 | 2024-08-10 | 2024-08-09 | 2024-08-10 | 2024-10-30 | 2024-12-31 | 130 | AWSC | AWSC | DF /C /27/DFCI-PSV-50450 | Scaffolding | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-SCAF | 2100098780 | E-5345 upstr.seawater 16"HCV intern leak | Build Scaffold |  |  | 6 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-23 | 2023-11-04 | 2024-03-18 | 10 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100098780 | E-5345 upstr.seawater 16"HCV intern leak | Build Scaffold |  |  | 2 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-23 | 2023-11-04 | 2024-03-18 | 20 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-RIGG | 2100098780 | E-5345 upstr.seawater 16"HCV intern leak | Build Scaffold |  |  | 4 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2023-11-04 | 2024-03-18 | 30 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-MECH | 2100098780 | E-5345 upstr.seawater 16"HCV intern leak | Build Scaffold |  |  | 4 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2023-11-04 | 2024-03-18 | 40 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | PRODTECH | 2100098780 | E-5345 upstr.seawater 16"HCV intern leak | Build Scaffold |  |  | 2 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2023-11-04 | 2024-03-18 | 50 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
3 | DFG-SW | WDF | MTN-MECH | MTN-SCAF | 2100098780 | E-5345 upstr.seawater 16"HCV intern leak | Build Scaffold |  |  | 4 | 0 | W43-44 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-11-04 | 2024-03-18 | 60 |  |  | DF /G /76/DFGA-E-5345 | Build Scaffold | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286645 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | HVAC SUPPLY GEN R. A-1211 CHECK - DFC |  |  | 1 | 0 | W33-W34 | 2024-08-22 | 2024-08-26 | 2024-08-22 | 2024-08-22 | 2023-10-20 | 2023-11-19 | 10 |  |  | DF /C /09/A-1211 | HVAC SUPPLY GEN R. A-1211 CHECK - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286645 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | HVAC SUPPLY GEN R. A-1211 CHECK - DFC |  |  | 12 | 0 | W33-W34 | 2024-08-22 | 2024-08-26 | 2024-08-22 | 2024-08-25 | 2023-10-20 | 2023-11-19 | 20 |  |  | DF /C /09/A-1211 | HVAC SUPPLY GEN R. A-1211 CHECK - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286645 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | HVAC SUPPLY GEN R. A-1211 CHECK - DFC |  |  | 1 | 0 | W33-W34 | 2024-08-22 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2023-10-20 | 2023-11-19 | 30 |  |  | DF /C /09/A-1211 | HVAC SUPPLY GEN R. A-1211 CHECK - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286645 | 1Y HVAC SUPPLY GEN R. A-1211 CHECK - DFC | HVAC SUPPLY GEN R. A-1211 CHECK - DFC |  |  | 2 | 0 | W33-W34 | 2024-08-22 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2023-10-20 | 2023-11-19 | 40 |  |  | DF /C /09/A-1211 | HVAC SUPPLY GEN R. A-1211 CHECK - DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235700 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF06-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235700 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF06-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235700 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF06-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235700 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF06-DA001 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339274 | DFF_1Y_32000 INT STRUCT INSP - GVI | DFF_1Y_32000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_32000 (MEZZANINE DECK) | DFF_1Y_32000 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-27 | 2023-03-30 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-03-30 | 2023-04-02 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-02 | 2023-04-02 | 2022-02-07 | 2022-07-07 | 42 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-02 | 2023-04-06 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-06 | 2023-04-11 | 2022-02-07 | 2022-07-07 | 60 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009233 | Insulation assist Bilfinger 22199(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-12 | 2023-04-11 | 2023-04-12 | 2022-02-07 | 2022-07-07 | 70 |  |  | DF /F /27/DFF-2-DPS-050-8073-AD-T | Bilfinger inspection | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400285957 | 6M WELLHEAD CONTROL PANELS MAINT - DFB | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-10-26 | 2023-11-11 | 10 |  |  | DF /B /07/WELLHEAD-CONTROL-PANELS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400285957 | 6M WELLHEAD CONTROL PANELS MAINT - DFB | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-10-26 | 2023-11-11 | 20 |  |  | DF /B /07/WELLHEAD-CONTROL-PANELS | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400285957 | 6M WELLHEAD CONTROL PANELS MAINT - DFB | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-26 | 2023-11-11 | 30 |  |  | DF /B /07/WELLHEAD-CONTROL-PANELS | ISOLATION BY PRODUCTION | Unknown
3 | NE | WRO | MTN-TURB | MTN-TURB | 2300000935 | FISKAL-gasdensitet i flowberegning | FISKAL - gasdensitet i flowberegning |  |  | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2013-12-01 | 2013-12-21 | 10 |  |  | DF /G /60/DFGA-CP-1640 | FISKAL - gasdensitet i flowberegning | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200010138 | Back-up of INSUM settings | Back-up of INSUM settings | PCNF | PCNF | 2 | 4 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-03-29 | 2022-05-08 | 10 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | Back-up of INSUM settings | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200010138 | Back-up of INSUM settings | Back-up of INSUM settings | PCNF | PCNF | 50 | 28 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-03-29 | 2022-05-08 | 20 | PCNF | PCNF | DF /F /61/DFFA-N-1802 | Back-up of INSUM settings | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-11 | 2024-01-12 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-ELEC | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-12 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 45 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-ELEC | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-19 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-19 | 2024-01-22 | 2022-02-09 | 2022-07-09 | 60 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-22 | 2024-01-23 | 2022-02-09 | 2022-07-09 | 70 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200009396 | Insulation assist Bilfinger 19727 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-23 | 2024-01-23 | 2022-02-09 | 2022-07-09 | 80 |  |  | DF /C /27/DFC-4-WOS-050-4099-AB-T | Bilfinger inspection | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400269602 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 0 | Empty | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-08-20 | 2023-08-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322280 | DFF-20-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /20/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400235305 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3961 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-07-29 | 2023-02-11 | 2023-03-19 | 10 |  |  | DF /F /75/DFFA-A-3961 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400235305 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3961 | ISOLATION BY PRODUCTION |  |  | 16 | 0 | W27-W28 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-08-02 | 2023-02-11 | 2023-03-19 | 20 |  |  | DF /F /75/DFFA-A-3961 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235305 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3961 | ISOLATION BY PRODUCTION |  |  | 7 | 0 | W27-W28 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-04 | 2023-02-11 | 2023-03-19 | 30 |  |  | DF /F /75/DFFA-A-3961 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400235305 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3961 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-08-04 | 2024-08-04 | 2024-08-04 | 2023-02-11 | 2023-03-19 | 40 |  |  | DF /F /75/DFFA-A-3961 | ISOLATION BY PRODUCTION | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087258 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /G /05/DFGA-LP-1852-32 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087258 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /G /05/DFGA-LP-1852-32 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087258 | Battery fault on emergency light | Isolate and prove dead. |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /G /05/DFGA-LP-1852-32 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087258 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /G /05/DFGA-LP-1852-32 | Isolate and prove dead. | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284286 | PSV Exchange - DFFA-PSV-570028 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /70/DFFA-PSV-570028 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284286 | PSV Exchange - DFFA-PSV-570028 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /70/DFFA-PSV-570028 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284286 | PSV Exchange - DFFA-PSV-570028 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /70/DFFA-PSV-570028 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284286 | PSV Exchange - DFFA-PSV-570028 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /70/DFFA-PSV-570028 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284286 | PSV Exchange - DFFA-PSV-570028 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /70/DFFA-PSV-570028 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284286 | PSV Exchange - DFFA-PSV-570028 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /70/DFFA-PSV-570028 | Isolation of PSV | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300005541 | Replaced by 2300005862 | New Seal for 3801 |  |  | 0 | 0 | Empty | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2026-04-16 | 10 |  |  | DF /C /84 | New Seal for 3801 | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300005541 | Replaced by 2300005862 | New Seal for 3801 |  |  | 1 | 0 | Empty | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2023-10-29 | 2026-04-16 | 20 |  |  | DF /C /84 | New Seal for 3801 | Unknown
D | Empty | WPM | PRODTECH | PRODTECH | 2400344167 | PIGGING, P3014 16" DFF-HDA WI 2W | P3014_DFF-HDA | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-21 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673014 | P3014_DFF-HDA | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342395 | 6M FW BTR PUMP HELIDEK MAINT-P-0305/06 | FW BTR PUMP HELIDEK MAINT-P-0305/06 | SECE | SECE | 6 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-08-24 | 2024-09-09 | 10 | SECE | SECE | DF /C /01/DFCC-P-0305 | FW BTR PUMP HELIDEK MAINT-P-0305/06 | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029882 | FB-09 intern læk i hydraulik skuffe | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2020-03-23 | 2020-05-02 | 10 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029882 | FB-09 intern læk i hydraulik skuffe | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2020-03-23 | 2020-05-02 | 20 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100029882 | FB-09 intern læk i hydraulik skuffe | Drawer to be sent onshore for repair | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2020-03-23 | 2020-05-02 | 25 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Drawer to be sent onshore for repair | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100029882 | FB-09 intern læk i hydraulik skuffe | Drawer to be sent onshore for repair | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2020-03-23 | 2020-05-02 | 30 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Drawer to be sent onshore for repair | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058042 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 99 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058042 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 4 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 200 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058042 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 4 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 202 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058042 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 299 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058042 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 400 |  |  | DF /F /62 | Isolate light group | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100094028 | DFF BDV-360077 indication fail | Isolate position switch | PCNFSCH | PCNFSCH | 2 | 3 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-01 | 2023-12-14 | 10 | PCNFSCH | PCNFSCH | DF /F /23/DFFA-BDV-360077 | Isolate position switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094028 | DFF BDV-360077 indication fail | Isolate position switch | PCNFSCH | PCNFSCH | 0.5 | 12 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-01 | 2023-12-14 | 20 | PCNFSCH | PCNFSCH | DF /F /23/DFFA-BDV-360077 | Isolate position switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094028 | DFF BDV-360077 indication fail | Isolate position switch | PCNFSCH | PCNFSCH | 2.5 | 3 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-01 | 2023-12-14 | 30 | PCNFSCH | PCNFSCH | DF /F /23/DFFA-BDV-360077 | Isolate position switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100094028 | DFF BDV-360077 indication fail | Isolate position switch | PCNFSCH | PCNFSCH | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-01 | 2023-12-14 | 40 | PCNFSCH | PCNFSCH | DF /F /23/DFFA-BDV-360077 | Isolate position switch | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100094028 | DFF BDV-360077 indication fail | Isolate position switch | PCNFSCH | PCNFSCH | 1.5 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-01 | 2023-12-14 | 50 | PCNFSCH | PCNFSCH | DF /F /23/DFFA-BDV-360077 | Isolate position switch | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2016-03-19 | 2016-04-28 | 1 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2016-03-19 | 2016-04-28 | 2 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2016-03-19 | 2016-04-28 | 10 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 9 | 1 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2016-03-19 | 2016-04-28 | 20 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2016-03-19 | 2016-04-28 | 30 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-05 | 2016-03-19 | 2016-04-28 | 40 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2016-03-19 | 2016-04-28 | 50 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2016-03-19 | 2016-04-28 | 60 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2016-03-19 | 2016-04-28 | 70 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023788 | DFF-29 OIL HCV nedstrømschoke | Prepare Permits Scaff | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2016-03-19 | 2016-04-28 | 80 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-HCV-303529 | Prepare Permits Scaff | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-30 | 2024-10-12 | 2024-12-31 | 24 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-07-31 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-07-31 | 2024-10-12 | 2024-12-31 | 28 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284311 | PSV Exchange - DFGA-PSV-530431 | Re-certify PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /51/DFGA-PSV-530431 | Re-certify PSV | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053997 | Replace. HT-cable on 1802-20413-L1E | Replace broken HT cable |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2021-11-11 | 2022-04-10 | 10 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Replace broken HT cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100053997 | Replace. HT-cable on 1802-20413-L1E | Replace broken HT cable |  |  | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2021-11-11 | 2022-04-10 | 15 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Replace broken HT cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053997 | Replace. HT-cable on 1802-20413-L1E | Replace broken HT cable |  |  | 4 | 0 | W25-W26 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-02 | 2021-11-11 | 2022-04-10 | 20 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Replace broken HT cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100053997 | Replace. HT-cable on 1802-20413-L1E | Replace broken HT cable |  |  | 6 | 0 | W25-W26 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-04 | 2021-11-11 | 2022-04-10 | 30 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Replace broken HT cable | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053997 | Replace. HT-cable on 1802-20413-L1E | Replace broken HT cable |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2021-11-11 | 2022-04-10 | 40 |  |  | DF /F /61/DFFA-N-1802A-20-4 | Replace broken HT cable | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093109 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-27 | 2023-12-09 | 10 |  |  | DF /B /03/DFBA-PB-02012 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093109 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-27 | 2023-12-09 | 20 |  |  | DF /B /03/DFBA-PB-02012 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093109 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 30 |  |  | DF /B /03/DFBA-PB-02012 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093109 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 40 |  |  | DF /B /03/DFBA-PB-02012 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093109 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 50 |  |  | DF /B /03/DFBA-PB-02012 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089241 | Damaged cable PU-0807 UPS supply DFAAed | Remove old cable. |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-09-05 | 2024-07-29 | 2024-07-29 | 2023-06-01 | 2023-10-14 | 10 |  |  | DF /A /06/DFAA-DP-1901A | Remove old cable. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100089241 | Damaged cable PU-0807 UPS supply DFAAed | Remove old cable. |  |  | 76 | 0 | Empty | 2024-07-29 | 2024-09-05 | 2024-07-29 | 2024-08-17 | 2023-06-01 | 2023-10-14 | 20 |  |  | DF /A /06/DFAA-DP-1901A | Remove old cable. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100089241 | Damaged cable PU-0807 UPS supply DFAAed | Remove old cable. |  |  | 76 | 0 | Empty | 2024-07-29 | 2024-09-05 | 2024-08-17 | 2024-09-05 | 2023-06-01 | 2023-10-14 | 30 |  |  | DF /A /06/DFAA-DP-1901A | Remove old cable. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058041 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 10 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058041 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 4 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 20 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058041 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 30 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058041 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 40 |  |  | DF /F /62 | Isolate light group | Unknown
A | NE | WPM | MTN-INST | MTN-MECH | 2400282072 | 3Y DFEY-P-3551, INSTRUMENT CHECK | DFEY-P-3551 INSTR CHECK | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-26 | 2023-10-27 | 10 | SECE | SECE | DF /E /54/DFEY-A-3551 | DFEY-P-3551 INSTR CHECK | Unknown
A | NE | WPM | MTN-INST | PRODTECH | 2400282072 | 3Y DFEY-P-3551, INSTRUMENT CHECK | DFEY-P-3551 INSTR CHECK | SECE | SECE | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-26 | 2023-10-27 | 20 | SECE | SECE | DF /E /54/DFEY-A-3551 | DFEY-P-3551 INSTR CHECK | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235924 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL ISOLATION | AWSC | AWSC | 1 | 1 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-04-26 | 2022-11-27 | 2023-03-24 | 10 | AWSC | AWSC | DF /C /09/HVAC-UTILITY | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235924 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL ISOLATION | AWSC | AWSC | 30 | 30 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-26 | 2024-04-29 | 2022-11-27 | 2023-03-24 | 20 | AWSC | AWSC | DF /C /09/HVAC-UTILITY | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400235924 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL ISOLATION | AWSC | AWSC | 6 | 6 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-29 | 2024-04-30 | 2022-11-27 | 2023-03-24 | 30 | AWSC | AWSC | DF /C /09/HVAC-UTILITY | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235924 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL ISOLATION | AWSC | AWSC | 1 | 1 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2024-04-30 | 2022-11-27 | 2023-03-24 | 40 | AWSC | AWSC | DF /C /09/HVAC-UTILITY | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400235924 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL ISOLATION | AWSC | AWSC | 2 | 2 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-04-30 | 2024-05-01 | 2022-11-27 | 2023-03-24 | 50 | AWSC | AWSC | DF /C /09/HVAC-UTILITY | PERSONAL ISOLATION | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235924 | 4Y HVAC COOL UNIT VEND DFCI-C-12803/903 | PERSONAL ISOLATION | AWSC | AWSC | 0 | 0 | W17-W18 | 2024-04-26 | 2024-05-01 | 2024-05-01 | 2024-05-01 | 2022-11-27 | 2023-03-24 | 60 | AWSC | AWSC | DF /C /09/HVAC-UTILITY | PERSONAL ISOLATION | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100067492 | FLMR ANOS DFF - Replace Handrail ST044 E | DFF - Replace Handrail ST044 EL +46975 |  |  | 0 | 0 | Empty | 2022-07-21 | 2024-03-21 | 2022-07-21 | 2024-03-21 | 2022-07-21 | 2022-12-18 | 10 |  |  | DF /F /86/46975 - HANDRAILS | DFF - Replace Handrail ST044 EL +46975 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-MECH | 2100067492 | FLMR ANOS DFF - Replace Handrail ST044 E | DFF - Replace Handrail ST044 EL +46975 |  |  | 4 | 4 | Empty | 2022-07-21 | 2024-03-21 | 2022-07-21 | 2024-03-21 | 2022-07-21 | 2022-12-18 | 20 |  |  | DF /F /86/46975 - HANDRAILS | DFF - Replace Handrail ST044 EL +46975 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-MECH | 2100067492 | FLMR ANOS DFF - Replace Handrail ST044 E | DFF - Replace Handrail ST044 EL +46975 |  |  | 12 | 12 | Empty | 2022-07-21 | 2024-03-21 | 2022-07-22 | 2024-03-21 | 2022-07-21 | 2022-12-18 | 30 |  |  | DF /F /86/46975 - HANDRAILS | DFF - Replace Handrail ST044 EL +46975 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078844 | DFG Nitrogen Gen membrane faulty (oil) | DFG Nitrgen Gen membrane faulty (oil) | SCH | SCH | 0 | 0 | W23-W24 | 2024-06-06 | 2024-06-09 | 2024-06-06 | 2024-06-06 | 2023-01-14 | 2023-05-29 | 10 | SCH | SCH | DF /G /74/DFGA-A-0850 | DFG Nitrgen Gen membrane faulty (oil) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078844 | DFG Nitrogen Gen membrane faulty (oil) | DFG Nitrgen Gen membrane faulty (oil) | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-06 | 2024-06-09 | 2024-06-06 | 2024-06-06 | 2023-01-14 | 2023-05-29 | 20 | SCH | SCH | DF /G /74/DFGA-A-0850 | DFG Nitrgen Gen membrane faulty (oil) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100078844 | DFG Nitrogen Gen membrane faulty (oil) | DFG Nitrgen Gen membrane faulty (oil) | SCH | SCH | 24 | 0 | W23-W24 | 2024-06-06 | 2024-06-09 | 2024-06-06 | 2024-06-09 | 2023-01-14 | 2023-05-29 | 30 | SCH | SCH | DF /G /74/DFGA-A-0850 | DFG Nitrgen Gen membrane faulty (oil) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100078844 | DFG Nitrogen Gen membrane faulty (oil) | DFG Nitrgen Gen membrane faulty (oil) | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-06 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2023-01-14 | 2023-05-29 | 40 | SCH | SCH | DF /G /74/DFGA-A-0850 | DFG Nitrgen Gen membrane faulty (oil) | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018128 | Replace Feeder protection 1841-M104 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M104-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018128 | Replace Feeder protection 1841-M104 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M104-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018128 | Replace Feeder protection 1841-M104 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M104-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018128 | Replace Feeder protection 1841-M104 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M104-02 | New mat num | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-17 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 24 | 6 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-17 | 2024-07-20 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 5 | 5 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 2 | 2 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 12 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2024-10-12 | 2024-12-31 | 80 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-25 | 2024-07-26 | 2024-10-12 | 2024-12-31 | 90 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-26 | 2024-10-12 | 2024-12-31 | 100 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-10-12 | 2024-12-31 | 110 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284296 | PSV Calibration - DFGA-PSV-540592B | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2024-10-12 | 2024-12-31 | 120 | AWSC | AWSC | DF /G /07/DFGA-PSV-540592B | Isolation of PSV | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-RIGG | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-23 | 2023-04-07 | 2023-08-20 | 10 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | PRODTECH | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-23 | 2024-09-24 | 2023-04-07 | 2023-08-20 | 20 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-INST | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-24 | 2024-09-24 | 2023-04-07 | 2023-08-20 | 30 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-MECH | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 12 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-24 | 2024-09-27 | 2023-04-07 | 2023-08-20 | 40 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-RIGG | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-24 | 2024-09-26 | 2023-04-07 | 2023-08-20 | 50 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-INST | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-27 | 2023-04-07 | 2023-08-20 | 60 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | PRODTECH | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-28 | 2023-04-07 | 2023-08-20 | 70 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-MECH | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-28 | 2023-04-07 | 2023-08-20 | 80 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
3 | DFF-W10 | WDF | MTN-MECH | MTN-RIGG | 2100085965 | DFF-10 choke to big for requested flow | Rig up hoist equipment |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-29 | 2023-04-07 | 2023-08-20 | 90 |  |  | DF /F /55/DFFA-CVA-300710 | Rig up hoist equipment | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000697 | SYS 03, FIRE WATER | SYS 03, FIRE WATER |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-11-19 | 2019-12-31 | 10 |  |  | DF /F | SYS 03, FIRE WATER | Unknown
3 | NOSD | WRO | MTN-MECH | MTN-MECH | 2300001090 | DFF37-SDS-301424 re-positioning | DFF37 - SDS-301424 re-positioning |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2000-01-01 | 2030-12-31 | 10 |  |  | DF /F /10 | DFF37 - SDS-301424 re-positioning | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 3 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2021-12-07 | 2022-01-16 | 10 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 2 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2021-12-07 | 2022-01-16 | 20 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 1 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-02 | 2021-12-07 | 2022-01-16 | 30 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 3 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2021-12-07 | 2022-01-16 | 40 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 1 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2021-12-07 | 2022-01-16 | 50 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 5 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-04 | 2021-12-07 | 2022-01-16 | 60 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 3 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-04 | 2025-01-05 | 2021-12-07 | 2022-01-16 | 70 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 2 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2021-12-07 | 2022-01-16 | 80 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 2 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2021-12-07 | 2022-01-16 | 90 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
3 | SIWL | WDF | MTN-MECH | PRODTECH | 2100059079 | DFF-29 Defekt aksel på Actuator FCV-2901 | Demount Actuator | AWSC | AWSC | 1 | 0 | Awaiting loss approval | 2025-01-01 | 2025-01-06 | 2025-01-06 | 2025-01-06 | 2021-12-07 | 2022-01-16 | 100 | AWSC | AWSC | DF /F /37/DFFA-FCV-290129 | Demount Actuator | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400268069 | 1Y DFC FUEL GAS - METERING | DFC FUEL GAS - METERING | AWSC | AWSC | 8 | 0 | Empty | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2023-07-03 | 2023-08-08 | 10 | AWSC | AWSC | DF /C /70/METERING | DFC FUEL GAS - METERING | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000926 | ESD SW for DFBWID2 | ESD SW for DFBWID2 | AWSC | AWSC | 36 | 0 | Empty | 2024-07-01 | 2024-07-08 | 2024-07-01 | 2024-07-04 | 2019-06-12 | 2019-11-09 | 10 | AWSC | AWSC | DF /B /03/DFBA-FP-0208A | ESD SW for DFBWID2 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000926 | ESD SW for DFBWID2 | ESD SW for DFBWID2 | AWSC | AWSC | 15 | 0 | Empty | 2024-07-01 | 2024-07-08 | 2024-07-04 | 2024-07-08 | 2019-06-12 | 2019-11-09 | 20 | AWSC | AWSC | DF /B /03/DFBA-FP-0208A | ESD SW for DFBWID2 | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000926 | ESD SW for DFBWID2 | ESD SW for DFBWID2 | AWSC | AWSC | 0 | 0 | Empty | 2024-07-01 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2019-06-12 | 2019-11-09 | 30 | AWSC | AWSC | DF /B /03/DFBA-FP-0208A | ESD SW for DFBWID2 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 10 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 20 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 30 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 40 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 50 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 60 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 70 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 80 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 90 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-06-26 | 2024-01-10 | 2024-02-24 | 100 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 110 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-05-21 | 2024-01-10 | 2024-02-24 | 120 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-06-02 | 2024-01-10 | 2024-02-24 | 130 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-09 | 2024-06-15 | 2024-01-10 | 2024-02-24 | 140 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-06-26 | 2024-01-10 | 2024-02-24 | 150 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 18 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-06-20 | 2024-01-10 | 2024-02-24 | 160 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-06-26 | 2024-01-10 | 2024-02-24 | 170 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-07-02 | 2024-01-10 | 2024-02-24 | 180 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-PIPF | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 16 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-05 | 2024-01-10 | 2024-02-24 | 190 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 200 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 210 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 220 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 12 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 230 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 240 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 250 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 260 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 270 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 280 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 290 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 300 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 310 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 320 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 330 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 340 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 350 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 360 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 370 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 380 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 390 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 400 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 410 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 420 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 12 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-07 | 2024-01-10 | 2024-02-24 | 430 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200017103 | Rope assist to service team_week check | 2024 | PCNF | PCNF | 0 | 0 | Empty | 2024-03-04 | 2024-07-02 | 2024-03-04 | 2024-03-04 | 2024-01-10 | 2024-02-24 | 440 | PCNF | PCNF | DF /C /78/DFCI-X-6101 | 2024 | Unknown
3 | DFF-W01 | WDF | MTN-MECH | PRODTECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 4 | 4 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-02 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 10 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | WELLSUPV | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 15 | 15 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-01 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 20 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | WELLSUPV | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 17 | 17 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-03 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 30 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | WELLSUPV | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 12 | 12 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-02 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 40 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | PRODTECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 4 | 4 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-04 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 50 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | WELLSUPV | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 6 | 6 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-01 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 60 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | WELLSUPV | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2019-03-04 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 70 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | PRODTECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2020-01-17 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 80 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | MTN-MECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 10 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2020-01-17 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 90 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | PRODTECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2020-01-17 | 2020-01-17 | 2019-02-23 | 2019-03-15 | 100 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | PRODTECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2019-02-23 | 2019-03-15 | 110 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | MTN-MECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 10 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2019-02-23 | 2019-03-15 | 120 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | MTN-MECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 16 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2019-02-23 | 2019-03-15 | 130 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
3 | DFF-W01 | WDF | MTN-MECH | PRODTECH | 2100024212 | DFF-01 Demontering af ventiler | Demontering af ventiler | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2019-02-23 | 2019-03-15 | 140 | AWSC | AWSC | DF /F /28 | Demontering af ventiler | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400344071 | 1Y DFGA-FIT-500820 PROD WATER-METERING | DFGA-FIT-500820 PROD WATER-METERING | AWSC | AWSC | 6 | 0 | Empty | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-09-19 | 10 | AWSC | AWSC | DF /G /27/DFGA-FIT-500820 | DFGA-FIT-500820 PROD WATER-METERING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325776 | 6M SEAWATER FILT PKG MAINT-DFFB-A-3550 | SEAWATER FILT PKG MAINT-DFFB-A-3550 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-10 | 2024-05-29 | 10 |  |  | DF /F /51/DFFB-A-3550 | SEAWATER FILT PKG MAINT-DFFB-A-3550 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286627 | 1Y WATER MIST SKID MAINT-DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | SECE | SECE | 3 | 3 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-16 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /G /01/DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286627 | 1Y WATER MIST SKID MAINT-DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | SECE | SECE | 10 | 10 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-18 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /G /01/DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286627 | 1Y WATER MIST SKID MAINT-DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | SECE | SECE | 6 | 6 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-18 | 2024-07-20 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /G /01/DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286627 | 1Y WATER MIST SKID MAINT-DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | SECE | SECE | 4 | 4 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-17 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /G /01/DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286627 | 1Y WATER MIST SKID MAINT-DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | SECE | SECE | 2 | 2 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-16 | 2024-07-16 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /G /01/DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286627 | 1Y WATER MIST SKID MAINT-DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | SECE | SECE | 3 | 3 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /G /01/DFGA-A-0461 | WATER MIST SKID MAINT-DFGA-A-0461 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060123 | Replace HTJB-1855-0009-C3-A1 | Prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-09 | 2022-04-09 | 10 |  |  | DF /G /61/DFGA-DP-1855-09 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100060123 | Replace HTJB-1855-0009-C3-A1 | Prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-09 | 2022-04-09 | 20 |  |  | DF /G /61/DFGA-DP-1855-09 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100060123 | Replace HTJB-1855-0009-C3-A1 | Prove dead |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-01-09 | 2022-04-09 | 30 |  |  | DF /G /61/DFGA-DP-1855-09 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100060123 | Replace HTJB-1855-0009-C3-A1 | Prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-09 | 2022-04-09 | 40 |  |  | DF /G /61/DFGA-DP-1855-09 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060123 | Replace HTJB-1855-0009-C3-A1 | Prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-09 | 2022-04-09 | 50 |  |  | DF /G /61/DFGA-DP-1855-09 | Prove dead | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084869 | PVI DAN F Level glass LG-50740 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 10 |  |  | DF /C /28/DFCM-LG-50740 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084869 | PVI DAN F Level glass LG-50740 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 20 |  |  | DF /C /28/DFCM-LG-50740 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084869 | PVI DAN F Level glass LG-50740 | Isolate Heat Tracing and Light |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-08-02 | 2026-01-18 | 30 |  |  | DF /C /28/DFCM-LG-50740 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084869 | PVI DAN F Level glass LG-50740 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 40 |  |  | DF /C /28/DFCM-LG-50740 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084869 | PVI DAN F Level glass LG-50740 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 50 |  |  | DF /C /28/DFCM-LG-50740 | Isolate Heat Tracing and Light | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 24 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-17 | 2024-07-20 | 2024-10-30 | 2024-12-31 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 5 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-20 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-21 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-21 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 60 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 12 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-21 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 70 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-23 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 80 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 5 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-23 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 90 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 4 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-24 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 100 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-24 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 110 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 120 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284262 | PSV Exchange - DFFA-PSV-340004 | PSV from GMC Workshop | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | Empty | 2024-07-16 | 2024-07-25 | 2024-07-25 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 130 | AWSCSCHSECE | AWSCSCHSECE | DF /F /10/DFFA-PSV-340004 | PSV from GMC Workshop | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040208 | Defekft gear på HCV-30017 | Production Assistance if necessary |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-01-19 | 2021-06-18 | 10 |  |  | DF /B /10/DFBA-HCV-300017 | Production Assistance if necessary | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040208 | Defekft gear på HCV-30017 | Production Assistance if necessary |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-01-19 | 2021-06-18 | 20 |  |  | DF /B /10/DFBA-HCV-300017 | Production Assistance if necessary | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040208 | Defekft gear på HCV-30017 | Production Assistance if necessary |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-01-19 | 2021-06-18 | 30 |  |  | DF /B /10/DFBA-HCV-300017 | Production Assistance if necessary | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040208 | Defekft gear på HCV-30017 | Production Assistance if necessary |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2021-01-19 | 2021-06-18 | 40 |  |  | DF /B /10/DFBA-HCV-300017 | Production Assistance if necessary | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322301 | DFG-28-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 148 | 0 | Empty | 2024-10-30 | 2024-11-29 | 2024-10-30 | 2024-11-28 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 10 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 15 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 20 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 2 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 30 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 24 | 33 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 40 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 12 | 10 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 50 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 60 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 24 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 70 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 2 | 2 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 80 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081341 | Overhaul of pump P-5075 | Reserve pump assembly | PCNF | PCNF | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-03-06 | 2023-07-19 | 90 | PCNF | PCNF | DF /G /28/DFGA-P-5075 | Reserve pump assembly | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009223 | Insulation assist FORCE 16152(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /C /27/DFC-3-CPS-050-6064-AD-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009223 | Insulation assist FORCE 16152(COMP) | Bilfinger inspection |  |  | 8 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /C /27/DFC-3-CPS-050-6064-AD-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009223 | Insulation assist FORCE 16152(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-27 | 2023-03-28 | 2022-02-07 | 2022-07-07 | 25 |  |  | DF /C /27/DFC-3-CPS-050-6064-AD-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009223 | Insulation assist FORCE 16152(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-29 | 2023-03-28 | 2023-03-29 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /C /27/DFC-3-CPS-050-6064-AD-F | Bilfinger inspection | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322294 | DFF-20-WOS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 7 | 2 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /20/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029616 | DFGA-PM-4158 has to be changeout | Isolate DFGA-PM-4158 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-03-24 | 2020-05-03 | 10 |  |  | DF /G /30/DFGA-PM-4158 | Isolate DFGA-PM-4158 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029616 | DFGA-PM-4158 has to be changeout | Isolate DFGA-PM-4158 |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2020-03-24 | 2020-05-03 | 15 |  |  | DF /G /30/DFGA-PM-4158 | Isolate DFGA-PM-4158 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100029616 | DFGA-PM-4158 has to be changeout | Isolate DFGA-PM-4158 |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2020-03-24 | 2020-05-03 | 20 |  |  | DF /G /30/DFGA-PM-4158 | Isolate DFGA-PM-4158 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029616 | DFGA-PM-4158 has to be changeout | Isolate DFGA-PM-4158 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2020-03-24 | 2020-05-03 | 30 |  |  | DF /G /30/DFGA-PM-4158 | Isolate DFGA-PM-4158 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100025245 | DFG Mount PRV on BDV control panel | Hydraulic isolation DFGA-BDV-430013 | SCHSECE | SCHSECE | 3 | 0 | W23-W24 | 2024-06-06 | 2024-06-10 | 2024-06-06 | 2024-06-06 | 2017-12-29 | 2018-03-29 | 10 | SCHSECE | SCHSECE | DF /G /31/DFGA-BDV-430013 | Hydraulic isolation DFGA-BDV-430013 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100025245 | DFG Mount PRV on BDV control panel | Hydraulic isolation DFGA-BDV-430013 | SCHSECE | SCHSECE | 8 | 0 | W23-W24 | 2024-06-06 | 2024-06-10 | 2024-06-06 | 2024-06-08 | 2017-12-29 | 2018-03-29 | 20 | SCHSECE | SCHSECE | DF /G /31/DFGA-BDV-430013 | Hydraulic isolation DFGA-BDV-430013 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100025245 | DFG Mount PRV on BDV control panel | Hydraulic isolation DFGA-BDV-430013 | SCHSECE | SCHSECE | 3 | 0 | W23-W24 | 2024-06-06 | 2024-06-10 | 2024-06-08 | 2024-06-09 | 2017-12-29 | 2018-03-29 | 30 | SCHSECE | SCHSECE | DF /G /31/DFGA-BDV-430013 | Hydraulic isolation DFGA-BDV-430013 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100025245 | DFG Mount PRV on BDV control panel | Hydraulic isolation DFGA-BDV-430013 | SCHSECE | SCHSECE | 4 | 0 | W23-W24 | 2024-06-06 | 2024-06-10 | 2024-06-09 | 2024-06-10 | 2017-12-29 | 2018-03-29 | 40 | SCHSECE | SCHSECE | DF /G /31/DFGA-BDV-430013 | Hydraulic isolation DFGA-BDV-430013 | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-INST | 2100025245 | DFG Mount PRV on BDV control panel | Hydraulic isolation DFGA-BDV-430013 | SCHSECE | SCHSECE | 0 | 0 | W23-W24 | 2024-06-06 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2017-12-29 | 2018-03-29 | 50 | SCHSECE | SCHSECE | DF /G /31/DFGA-BDV-430013 | Hydraulic isolation DFGA-BDV-430013 | Unknown
3 | DFA-O23 | WDF | MTN-MECH | PRODTECH | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-11-30 | 2024-04-13 | 10 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
3 | DFA-O23 | WDF | MTN-MECH | MTN-RIGG | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2023-11-30 | 2024-04-13 | 20 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
3 | DFA-O23 | WDF | MTN-MECH | MTN-MECH | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-24 | 2023-11-30 | 2024-04-13 | 30 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
3 | DFA-O23 | WDF | MTN-MECH | MTN-RIGG | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2023-11-30 | 2024-04-13 | 40 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
3 | DFA-O23 | WDF | MTN-MECH | MTN-MECH | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-11-30 | 2024-04-13 | 50 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
3 | DFA-O23 | WDF | MTN-MECH | PRODTECH | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-11-30 | 2024-04-13 | 60 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
3 | DFA-O23 | WDF | MTN-MECH | MTN-MECH | 2100100015 | DFA-23 bullhead line valves intern leak | Rigging assist. Rig in/out |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-11-30 | 2024-04-13 | 70 |  |  | DF /A /10/DFA23-PRODUCTION-LINE | Rigging assist. Rig in/out | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2024-02-14 | 2024-03-30 | 10 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2024-02-14 | 2024-03-30 | 20 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 6 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-07 | 2024-02-14 | 2024-03-30 | 30 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 4 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-07 | 2024-10-08 | 2024-02-14 | 2024-03-30 | 40 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 6 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-08 | 2024-10-09 | 2024-02-14 | 2024-03-30 | 50 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 2 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-09 | 2024-10-10 | 2024-02-14 | 2024-03-30 | 60 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100107862 | DFF Scale inj P-39425 no flow | Prepare for rigging |  |  | 1 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-02-14 | 2024-03-30 | 70 |  |  | DF /F /75/DFFA-P-39425 | Prepare for rigging | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329510 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SECE | SECE | 2 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-06-14 | 10 | SECE | SECE | DF /C /27/DFCM-P-5015 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329510 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SECE | SECE | 4 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-06-14 | 20 | SECE | SECE | DF /C /27/DFCM-P-5015 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329510 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SECE | SECE | 4 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-16 | 2024-05-17 | 2024-05-15 | 2024-06-14 | 30 | SECE | SECE | DF /C /27/DFCM-P-5015 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400329510 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SECE | SECE | 1 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-17 | 2024-05-17 | 2024-05-15 | 2024-06-14 | 40 | SECE | SECE | DF /C /27/DFCM-P-5015 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329510 | 1Y SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | SECE | SECE | 2 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-17 | 2024-05-18 | 2024-05-15 | 2024-06-14 | 50 | SECE | SECE | DF /C /27/DFCM-P-5015 | SLOP OIL PUMPS MAINT-DFCM-P-5015/16 | Unknown
3 | NOSD | WGN | MTN-PAIN | QAQCPAIN | 2200010214 | IRP DAF test for CHROMIUM-6 | IRP DAF test for CHROMIUM-6 |  |  | 2 | 0 | Empty | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2023-02-13 | 2022-03-19 | 2022-04-08 | 10 |  |  | DF /C /03/FZ-47-PAINT-STORE | IRP DAF test for CHROMIUM-6 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322250 | DFC-75-CB-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 15 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /75/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-25 | 2024-08-25 | 2023-08-21 | 2026-02-06 | 10 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-INST | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-25 | 2024-08-25 | 2023-08-21 | 2026-02-06 | 20 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 3 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-25 | 2024-08-26 | 2023-08-21 | 2026-02-06 | 30 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 3 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-26 | 2024-08-27 | 2023-08-21 | 2026-02-06 | 40 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 6 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-27 | 2024-08-28 | 2023-08-21 | 2026-02-06 | 50 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 6 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-28 | 2024-08-30 | 2023-08-21 | 2026-02-06 | 60 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-INST | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-30 | 2024-08-30 | 2023-08-21 | 2026-02-06 | 70 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-INST | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 4 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-30 | 2024-08-31 | 2023-08-21 | 2026-02-06 | 80 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-31 | 2024-08-31 | 2023-08-21 | 2026-02-06 | 90 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100086074 | PCV-440066 housing corroded. | Isolate PCV |  |  | 2 | 0 | Empty | 2024-08-25 | 2024-09-01 | 2024-08-31 | 2024-09-01 | 2023-08-21 | 2026-02-06 | 100 |  |  | DF /F /31/DFFA-PCV-440066 | Isolate PCV | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 4 | 3 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-01 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 4 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 12 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-01 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 5 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 8 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-01 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 6 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 12 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-01 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 10 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 3 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2022-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 11 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 8 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 18 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 8 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 19 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 8 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 20 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 2 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 40 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 12 | 2 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 50 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 8 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 51 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 10 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 60 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 10 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2021-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 61 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 0 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2022-06-02 | 2022-06-02 | 2019-04-14 | 2019-09-11 | 65 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 1 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2019-04-14 | 2019-09-11 | 71 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 3 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2019-04-14 | 2019-09-11 | 81 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024575 | Corroded hydraulic on winch DFGA-X-0702, | Prepare E-cow documents (permits, etc | PCNFAWSC | PCNFAWSC | 0 | 0 | W24 IOP 13-20/6 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2024-06-15 | 2019-04-14 | 2019-09-11 | 91 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Prepare E-cow documents (permits, etc | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400315827 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-11 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 35 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2024-02-21 | 2024-04-23 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-11 | ATEX EQUIPMENT INSPECTION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077776 | DFC LB4 replace foundation bolts | Replace winchfoundation bolts one by one |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2023-05-09 | 2025-10-25 | 10 |  |  | DF /C /02/DFCI-X-0704 | Replace winchfoundation bolts one by one | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077776 | DFC LB4 replace foundation bolts | Replace winchfoundation bolts one by one |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 20 |  |  | DF /C /02/DFCI-X-0704 | Replace winchfoundation bolts one by one | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077776 | DFC LB4 replace foundation bolts | Replace winchfoundation bolts one by one |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 30 |  |  | DF /C /02/DFCI-X-0704 | Replace winchfoundation bolts one by one | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077776 | DFC LB4 replace foundation bolts | Replace winchfoundation bolts one by one |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 35 |  |  | DF /C /02/DFCI-X-0704 | Replace winchfoundation bolts one by one | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100077776 | DFC LB4 replace foundation bolts | Replace winchfoundation bolts one by one |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-05-09 | 2025-10-25 | 40 |  |  | DF /C /02/DFCI-X-0704 | Replace winchfoundation bolts one by one | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235649 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L11 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L11B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235649 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L11 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L11B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235649 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L11 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L11B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235649 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L11 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L11B1 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2018-02-07 | 2018-07-07 | 5 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2018-02-07 | 2018-07-07 | 10 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-16 | 2018-02-07 | 2018-07-07 | 20 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2018-02-07 | 2018-07-07 | 30 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2018-02-07 | 2018-07-07 | 40 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2018-02-07 | 2018-07-07 | 50 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2018-02-07 | 2018-07-07 | 60 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2018-02-07 | 2018-07-07 | 70 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2018-02-07 | 2018-07-07 | 80 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100022723 | Change Actuator/valve DFGA-BDV-430010 | Line for purchasing new Valve |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2018-02-07 | 2018-07-07 | 90 |  |  | DF /G /34/DFGA-BDV-430010 | Line for purchasing new Valve | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 0 | 0 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-20 | 2024-05-20 | 2024-03-15 | 2024-07-28 | 10 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 1 | 4 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-20 | 2024-05-20 | 2024-03-15 | 2024-07-28 | 20 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 8 | 59 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-20 | 2024-05-20 | 2024-03-15 | 2024-07-28 | 30 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 1.5 | 48 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-20 | 2024-05-20 | 2024-03-15 | 2024-07-28 | 40 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 4 | 4 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-20 | 2024-05-21 | 2024-03-15 | 2024-07-28 | 41 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 0 | 10 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-21 | 2024-05-21 | 2024-03-15 | 2024-07-28 | 50 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 1 | 1 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-21 | 2024-05-21 | 2024-03-15 | 2024-07-28 | 51 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 6 | 6 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-21 | 2024-05-22 | 2024-03-15 | 2024-07-28 | 52 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 20 | 20 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-22 | 2024-05-24 | 2024-03-15 | 2024-07-28 | 53 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 4 | 4 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-24 | 2024-05-24 | 2024-03-15 | 2024-07-28 | 54 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 2 | 2 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-24 | 2024-05-24 | 2024-03-15 | 2024-07-28 | 55 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 2 | 2 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-24 | 2024-05-25 | 2024-03-15 | 2024-07-28 | 56 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 6 | 6 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-25 | 2024-05-25 | 2024-03-15 | 2024-07-28 | 57 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 1 | 1 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-25 | 2024-05-25 | 2024-03-15 | 2024-07-28 | 58 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 2 | 2 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-25 | 2024-05-26 | 2024-03-15 | 2024-07-28 | 59 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 0 | 0 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-03-15 | 2024-07-28 | 62 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 0 | 0 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-03-15 | 2024-07-28 | 70 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100106588 | Noise from DFG-CM-1202 | Shipping of refurbish. motor | SCH | SCH | 0 | 0 | Empty | 2024-05-20 | 2024-05-26 | 2024-05-26 | 2024-05-26 | 2024-03-15 | 2024-07-28 | 80 | SCH | SCH | DF /G /09/DFGA-CM-1202 | Shipping of refurbish. motor | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 3 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 10 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 10 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-23 | 2020-09-14 | 2020-10-24 | 15 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 5 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-23 | 2020-09-14 | 2020-10-24 | 20 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 6 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 25 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 3 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 30 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 3 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 40 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 15 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-26 | 2020-09-14 | 2020-10-24 | 50 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 5 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-26 | 2024-09-27 | 2020-09-14 | 2020-10-24 | 60 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 5 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-27 | 2024-09-28 | 2020-09-14 | 2020-10-24 | 70 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 5 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-29 | 2024-09-30 | 2020-09-14 | 2020-10-24 | 80 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 3 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-30 | 2024-09-30 | 2020-09-14 | 2020-10-24 | 90 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 3 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-10-01 | 2024-10-01 | 2020-09-14 | 2020-10-24 | 100 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 10 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-10-01 | 2024-10-04 | 2020-09-14 | 2020-10-24 | 110 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 3 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2020-09-14 | 2020-10-24 | 120 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038046 | HCV-57149-U Intern læk | Isolate Valve |  |  | 0 | 0 | D-FLARE | 2024-09-22 | 2024-10-04 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 130 |  |  | DF /C /70/DFCI-HCV-57149-U | Isolate Valve | Unknown
2 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076955 | Cable screen is crack for ZE-430260 | Replace Vibration Measurement Device | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-10-28 | 2022-12-12 | 10 | SCH | SCH | DF /G /31/DFGA-ZE-430260 | Replace Vibration Measurement Device | Unknown
2 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076955 | Cable screen is crack for ZE-430260 | Replace Vibration Measurement Device | SCH | SCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-10-28 | 2022-12-12 | 20 | SCH | SCH | DF /G /31/DFGA-ZE-430260 | Replace Vibration Measurement Device | Unknown
2 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076955 | Cable screen is crack for ZE-430260 | Replace Vibration Measurement Device | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-10-28 | 2022-12-12 | 30 | SCH | SCH | DF /G /31/DFGA-ZE-430260 | Replace Vibration Measurement Device | Unknown
2 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076955 | Cable screen is crack for ZE-430260 | Replace Vibration Measurement Device | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-10-28 | 2022-12-12 | 40 | SCH | SCH | DF /G /31/DFGA-ZE-430260 | Replace Vibration Measurement Device | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100025318 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 3.399999999999999911182158029 | 0 | Empty | 2023-02-13 | 2023-02-15 | 2023-02-13 | 2023-02-13 | 2018-03-10 | 2018-06-08 | 5 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100025318 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-15 | 2023-02-13 | 2023-02-13 | 2018-03-10 | 2018-06-08 | 10 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100025318 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-15 | 2023-02-13 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 20 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025318 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-15 | 2023-02-14 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 25 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100025318 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 5.4000000000000003552713678785 | 0 | Empty | 2023-02-13 | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 30 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101563 | SOV-030514 is malfunction | Isolate Solenoid valve |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-08 | 2023-12-23 | 10 |  |  | DF /G /01/DFGA-PCV-030514 | Isolate Solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101563 | SOV-030514 is malfunction | Isolate Solenoid valve |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-08 | 2023-12-23 | 20 |  |  | DF /G /01/DFGA-PCV-030514 | Isolate Solenoid valve | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101563 | SOV-030514 is malfunction | Isolate Solenoid valve |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-08 | 2023-12-23 | 30 |  |  | DF /G /01/DFGA-PCV-030514 | Isolate Solenoid valve | Unknown
3 | NE | WRO | MTN-INST | MTN-INST | 2300000868 | SW implementation for TMNE1159 | SW implementation for TMNE1159 |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2010-01-01 | 2030-12-31 | 10 |  |  | DF /C /11/DFCI-LT-34003 | SW implementation for TMNE1159 | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100056489 | Bruse kabine DFC ACC kammer 204. | Bruse kabine DFC ACC kammer 204. |  |  | 0 | 0 | Empty | 2021-12-28 | 2021-12-28 | 2021-12-28 | 2021-12-28 | 2021-12-28 | 2022-05-27 | 10 |  |  | DF /C /82 | Bruse kabine DFC ACC kammer 204. | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400330000 | 1Y WI INST/CHOKE VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-05-29 | 2024-06-04 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-06-28 | 5 | SECE | SECE | DF /A /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-INST | 2400330000 | 1Y WI INST/CHOKE VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | W19-W20 | 2024-05-29 | 2024-06-04 | 2024-05-29 | 2024-06-01 | 2024-05-29 | 2024-06-28 | 10 | SECE | SECE | DF /A /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400330000 | 1Y WI INST/CHOKE VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | W19-W20 | 2024-05-29 | 2024-06-04 | 2024-06-01 | 2024-06-04 | 2024-05-29 | 2024-06-28 | 20 | SECE | SECE | DF /A /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400330000 | 1Y WI INST/CHOKE VALVES MAINT-DFA | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W19-W20 | 2024-05-29 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-05-29 | 2024-06-28 | 30 | SECE | SECE | DF /A /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WGN | MTN-LAGG | WELLSUPV | 2200003247 | DFG vent kanaler tjekkes, forkert propni | Gennemgang af FG ventilations kanaler |  |  | 0 | 0 | Moved to 2022 | 2023-04-03 | 2023-04-10 | 2023-04-03 | 2023-04-03 | 2017-11-29 | 2018-04-28 | 10 |  |  | DF /G /09 | Gennemgang af FG ventilations kanaler | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200003247 | DFG vent kanaler tjekkes, forkert propni | Gennemgang af FG ventilations kanaler |  |  | 20.100000000000001421085471515 | 0 | Moved to 2022 | 2023-04-03 | 2023-04-10 | 2023-04-03 | 2023-04-05 | 2017-11-29 | 2018-04-28 | 20 |  |  | DF /G /09 | Gennemgang af FG ventilations kanaler | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200003247 | DFG vent kanaler tjekkes, forkert propni | Gennemgang af FG ventilations kanaler |  |  | 13.400000000000000355271367876 | 0 | Moved to 2022 | 2023-04-03 | 2023-04-10 | 2023-04-05 | 2023-04-06 | 2017-11-29 | 2018-04-28 | 30 |  |  | DF /G /09 | Gennemgang af FG ventilations kanaler | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200003247 | DFG vent kanaler tjekkes, forkert propni | Gennemgang af FG ventilations kanaler |  |  | 13.400000000000000355271367876 | 0 | Moved to 2022 | 2023-04-03 | 2023-04-10 | 2023-04-05 | 2023-04-06 | 2017-11-29 | 2018-04-28 | 32 |  |  | DF /G /09 | Gennemgang af FG ventilations kanaler | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-LAGG | 2200003247 | DFG vent kanaler tjekkes, forkert propni | Gennemgang af FG ventilations kanaler |  |  | 13.400000000000000355271367876 | 0 | Moved to 2022 | 2023-04-03 | 2023-04-10 | 2023-04-06 | 2023-04-08 | 2017-11-29 | 2018-04-28 | 40 |  |  | DF /G /09 | Gennemgang af FG ventilations kanaler | Unknown
4 | NOSD | WGN | MTN-LAGG | MTN-SCAF | 2200003247 | DFG vent kanaler tjekkes, forkert propni | Gennemgang af FG ventilations kanaler |  |  | 8.699999999999999289457264236 | 0 | Moved to 2022 | 2023-04-03 | 2023-04-10 | 2023-04-08 | 2023-04-10 | 2017-11-29 | 2018-04-28 | 50 |  |  | DF /G /09 | Gennemgang af FG ventilations kanaler | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 58 | 26 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2018-12-20 | 2019-03-20 | 10 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 26 | 26 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2018-12-20 | 2019-03-20 | 20 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 104.5 | 0 | Empty | 2022-06-10 | 2024-01-11 | 2022-06-11 | 2022-06-15 | 2018-12-20 | 2019-03-20 | 30 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 13 | 0 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-09 | 2024-01-10 | 2018-12-20 | 2019-03-20 | 40 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 0 | 77 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2018-12-20 | 2019-03-20 | 50 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 36 | 0 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-09 | 2024-01-11 | 2018-12-20 | 2019-03-20 | 60 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 24 | 0 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-09 | 2024-01-10 | 2018-12-20 | 2019-03-20 | 70 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200003246 | Scaff Assist to Force 5027 | BUILD SCAFFOLDING | PCNF | PCNF | 18 | 0 | Empty | 2022-06-10 | 2024-01-11 | 2024-01-09 | 2024-01-10 | 2018-12-20 | 2019-03-20 | 80 | PCNF | PCNF | DF /F /28/DFF-3-DO-050-8101-AB-U | BUILD SCAFFOLDING | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400350907 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-20 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-10-11 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-20 | ATEX EQUIPMENT INSPECTION | Unknown
2 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200018387 | Changing room facilities for W2W Campaig | Install Dressing room cabinets. | PCNF | PCNF | 18 | 9 | Empty | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-11 | 2024-05-01 | 2024-06-15 | 10 | PCNF | PCNF | DF /C /9 | Install Dressing room cabinets. | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400219094 | 6M PROD WTR HP/LP SKD MAINT-DFFA-A-5005 | PROD WTR HP/LP SKD INSP-DFFA-A-5005 |  |  | 8 | 8 | W21-W22 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-03 | 2022-11-25 | 2022-12-14 | 10 |  |  | DF /F /27/DFFA-A-5005 | PROD WTR HP/LP SKD INSP-DFFA-A-5005 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235653 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R14 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R14B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235653 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R14 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R14B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235653 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R14 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R14B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235653 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R14 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R14B | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400215520 | 1Y GYM EQUIPMENT CHECK - DFC (VENDOR) | PO Pedan | AWSCSCH | AWSCSCH | 24 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-10 | 2022-10-08 | 2022-11-24 | 10 | AWSCSCH | AWSCSCH | DF /C /82/GYM-EQUIPMENT | PO Pedan | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400215520 | 1Y GYM EQUIPMENT CHECK - DFC (VENDOR) | PO Pedan | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2022-10-08 | 2022-11-24 | 20 | AWSCSCH | AWSCSCH | DF /C /82/GYM-EQUIPMENT | PO Pedan | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 10 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 20 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 30 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 40 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 50 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 60 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 70 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 80 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 90 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 100 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 110 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 120 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 130 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 140 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 150 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 160 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 170 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NE | WRO | MTN-TURB | MTN-TURB | 2300004779 | DK40 - CONSUMABLE MTN - TURB (ROTATING) | Bently nevada kort udlånt til HBD |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-08-12 | 2026-01-28 | 180 |  |  | DF /C /84 | Bently nevada kort udlånt til HBD | Unknown
4 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 8 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2021-07-28 | 2021-12-25 | 10 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 1 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-07-28 | 2021-12-25 | 20 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 2 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2021-07-28 | 2021-12-25 | 30 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 10 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-07-28 | 2021-12-25 | 40 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 2 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2021-07-28 | 2021-12-25 | 50 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 1 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-07-28 | 2021-12-25 | 60 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 1 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2021-07-28 | 2021-12-25 | 70 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
4 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100049597 | Ingen flpw i FI-500827 (INST-TUBF) | Isolate flow indicator | AWSC | AWSC | 4 | 0 | Empty | 2024-08-25 | 2024-08-27 | 2024-08-25 | 2024-08-25 | 2021-07-28 | 2021-12-25 | 80 | AWSC | AWSC | DF /G /27/DFGA-X-5083 | Isolate flow indicator | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000851 | Install Applications Server | Install Applications Server |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2017-02-19 | 2017-05-20 | 10 |  |  | DF /C /04 | Install Applications Server | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400308986 | 6M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-03-02 | 2024-03-18 | 10 |  |  | DF /G /07/DFGA-A-5940 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308986 | 6M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-03-02 | 2024-03-18 | 20 |  |  | DF /G /07/DFGA-A-5940 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400308986 | 6M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-03-02 | 2024-03-18 | 30 |  |  | DF /G /07/DFGA-A-5940 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284254 | PSV Exchange - DFEZ-PSV-33058 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33058 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284254 | PSV Exchange - DFEZ-PSV-33058 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33058 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284254 | PSV Exchange - DFEZ-PSV-33058 | Isolation of PSV | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33058 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284254 | PSV Exchange - DFEZ-PSV-33058 | Isolation of PSV | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33058 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284254 | PSV Exchange - DFEZ-PSV-33058 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33058 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284254 | PSV Exchange - DFEZ-PSV-33058 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /E /10/DFEZ-PSV-33058 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2019-08-06 | 2019-08-26 | 2 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2019-08-06 | 2019-08-26 | 3 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 24 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-31 | 2019-08-06 | 2019-08-26 | 5 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-31 | 2024-08-01 | 2019-08-06 | 2019-08-26 | 10 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2019-08-06 | 2019-08-26 | 15 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2019-08-06 | 2019-08-26 | 17 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2019-08-06 | 2019-08-26 | 30 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2019-08-06 | 2019-08-26 | 31 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2019-08-06 | 2019-08-26 | 40 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-01 | 2024-08-02 | 2019-08-06 | 2019-08-26 | 50 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-30 | 2019-08-06 | 2019-08-26 | 53 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 18 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-02 | 2024-08-03 | 2019-08-06 | 2019-08-26 | 55 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-08-03 | 2024-08-05 | 2019-08-06 | 2019-08-26 | 65 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022500 | DFC Brandvands lækage ved 8" flange | Clean off, Backup-Wrap+Coating |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2019-08-06 | 2019-08-26 | 75 |  |  | DF /C /01 | Clean off, Backup-Wrap+Coating | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098337 | DFB/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-10-29 | 2024-03-12 | 10 |  |  | DF /B /78/DFBA-MD-6102 | Drain coolant & refill with new type | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098337 | DFB/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 8 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-10-29 | 2024-03-12 | 20 |  |  | DF /B /78/DFBA-MD-6102 | Drain coolant & refill with new type | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100098337 | DFB/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-10-29 | 2024-03-12 | 30 |  |  | DF /B /78/DFBA-MD-6102 | Drain coolant & refill with new type | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100098337 | DFB/78 Replace coolant with new type | Drain coolant & refill with new type |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-10-29 | 2024-03-12 | 40 |  |  | DF /B /78/DFBA-MD-6102 | Drain coolant & refill with new type | Unknown
4 | DFF-3520 | WGN | MTN-MECH | PRODTECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-03-28 | 2022-11-23 | 10 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | PRODTECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-02 | 2022-03-28 | 2022-11-23 | 20 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | MTN-MECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 5 | 6 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-02 | 2024-07-03 | 2022-03-28 | 2022-11-23 | 40 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | MTN-MECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 0 | 6 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-03 | 2024-07-03 | 2022-03-28 | 2022-11-23 | 50 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | PRODTECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-03 | 2024-07-04 | 2022-03-28 | 2022-11-23 | 70 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | MTN-MECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 5 | 4 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-04 | 2024-07-05 | 2022-03-28 | 2022-11-23 | 80 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | PRODTECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-05 | 2024-07-06 | 2022-03-28 | 2022-11-23 | 90 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | MTN-ELEC | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-06 | 2024-07-07 | 2022-03-28 | 2022-11-23 | 95 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | MTN-LAGG | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-07 | 2024-07-07 | 2022-03-28 | 2022-11-23 | 100 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
4 | DFF-3520 | WGN | MTN-MECH | MTN-MECH | 2200008918 | Exchange DFFA-PSV-350104 | Heat trace | SCH | SCH | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-07 | 2024-07-07 | 2022-03-28 | 2022-11-23 | 110 | SCH | SCH | DF /F /54/DFFA-PSV-350104 | Heat trace | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337676 | 3M SEWER TREATMENT UNIT DFCM-A-5101 | SEWER TREATMENT UNIT DFCM-A-5101 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-13 | 2024-08-24 | 10 |  |  | DF /C /82/DFCM-A-5160 | SEWER TREATMENT UNIT DFCM-A-5101 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235576 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCC-N-1803-04-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235576 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCC-N-1803-04-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235576 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCC-N-1803-04-02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235576 | 4Y 380V N-SWB-MAINT-DFCC-N-1803-04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCC-N-1803-04-02 | ISOLATION ELECTRICAL | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 5 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 4 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
A | NE | WPM | MTN-MECH | VEN-INSP | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400284259 | PSV Exchange - DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | AWSC | AWSC | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /07/DFFA-PSV-590112 | DFFA-PSV-590112 Offshore from WS Måde | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100022319 | ANOC Rebuild indulation in front of DFE- | L3 recheck heat tracing |  |  | 8.699999999999999289457264236 | 0 | PVI V-5012 April 2022 | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2019-07-07 | 2020-07-01 | 10 |  |  | DF /E /28/DFEZ-P-5012 | L3 recheck heat tracing | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100022319 | ANOC Rebuild indulation in front of DFE- | L3 recheck heat tracing |  |  | 0.6999999999999999555910790147 | 0 | PVI V-5012 April 2022 | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2019-07-07 | 2020-07-01 | 20 |  |  | DF /E /28/DFEZ-P-5012 | L3 recheck heat tracing | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100022319 | ANOC Rebuild indulation in front of DFE- | L3 recheck heat tracing |  |  | 6.700000000000000177635683938 | 0 | PVI V-5012 April 2022 | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-14 | 2019-07-07 | 2020-07-01 | 30 |  |  | DF /E /28/DFEZ-P-5012 | L3 recheck heat tracing | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100022319 | ANOC Rebuild indulation in front of DFE- | L3 recheck heat tracing |  |  | 0.6999999999999999555910790147 | 0 | PVI V-5012 April 2022 | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-14 | 2019-07-07 | 2020-07-01 | 40 |  |  | DF /E /28/DFEZ-P-5012 | L3 recheck heat tracing | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100022319 | ANOC Rebuild indulation in front of DFE- | L3 recheck heat tracing |  |  | 17.399999999999998578914528472 | 0 | PVI V-5012 April 2022 | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-16 | 2019-07-07 | 2020-07-01 | 50 |  |  | DF /E /28/DFEZ-P-5012 | L3 recheck heat tracing | Unknown
4 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076552 | HP CMPR AX alarm ZE440292 A/B | HP CMPR AX alarm ZE440292 A/B | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-19 | 2025-10-05 | 10 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-C-4402 | HP CMPR AX alarm ZE440292 A/B | Unknown
4 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076552 | HP CMPR AX alarm ZE440292 A/B | HP CMPR AX alarm ZE440292 A/B | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-19 | 2025-10-05 | 20 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-C-4402 | HP CMPR AX alarm ZE440292 A/B | Unknown
4 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076552 | HP CMPR AX alarm ZE440292 A/B | HP CMPR AX alarm ZE440292 A/B | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-19 | 2025-10-05 | 30 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-C-4402 | HP CMPR AX alarm ZE440292 A/B | Unknown
4 | DFG-IPHP | WDF | MTN-TURB | MTN-TURB | 2100076552 | HP CMPR AX alarm ZE440292 A/B | HP CMPR AX alarm ZE440292 A/B | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-19 | 2025-10-05 | 40 | AWSCSCH | AWSCSCH | DF /G /31/DFGA-C-4402 | HP CMPR AX alarm ZE440292 A/B | Unknown
B | DFG-3590 | WPM | MTN-MECH | MTN-MECH | 2400259643 | 4KH SDV/BDV LUB/MAINT WI DFGA-A-3590 | SDV/BDV LUB/INSP WI DFGA-A-3590 | AWSC | AWSC | 2.5 | 0 | W21-W22 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2023-06-08 | 2023-06-24 | 10 | AWSC | AWSC | DF /G /54/DFGA-A-3590 | SDV/BDV LUB/INSP WI DFGA-A-3590 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059336 | Reinstate N2 charge tubing on FP-3103 | Function Test |  |  | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2021-12-04 | 2021-12-24 | 10 |  |  | DF /F /07/DFFA-FP-3103 | Function Test | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059336 | Reinstate N2 charge tubing on FP-3103 | Function Test |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2021-12-04 | 2021-12-24 | 20 |  |  | DF /F /07/DFFA-FP-3103 | Function Test | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059336 | Reinstate N2 charge tubing on FP-3103 | Function Test |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2021-12-04 | 2021-12-24 | 30 |  |  | DF /F /07/DFFA-FP-3103 | Function Test | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059336 | Reinstate N2 charge tubing on FP-3103 | Function Test |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2021-12-04 | 2021-12-24 | 40 |  |  | DF /F /07/DFFA-FP-3103 | Function Test | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059336 | Reinstate N2 charge tubing on FP-3103 | Function Test |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2021-12-04 | 2021-12-24 | 50 |  |  | DF /F /07/DFFA-FP-3103 | Function Test | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400306677 | 1Y DFCM-FIT-500032 PROD WATER METERING | DFCM-FIT-500032 PROD WATER METERING | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2024-01-09 | 2024-02-25 | 10 | AWSC | AWSC | DF /C /27/DFCM-FIT-500032 | DFCM-FIT-500032 PROD WATER METERING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230507 | 6M PROD WTR HP/LP SKD MAINT-DFFA-A-5001 | PROD WTR HP/LP SKD INSP-DFFA-A-5001 |  |  | 10 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-02-04 | 2023-02-23 | 10 |  |  | DF /F /27/DFFA-A-5001 | PROD WTR HP/LP SKD INSP-DFFA-A-5001 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235637 | 4Y 380V N-SWB MAINT-DFFA-N-1803-6 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803-06 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235637 | 4Y 380V N-SWB MAINT-DFFA-N-1803-6 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803-06 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235637 | 4Y 380V N-SWB MAINT-DFFA-N-1803-6 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803-06 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235637 | 4Y 380V N-SWB MAINT-DFFA-N-1803-6 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803-06 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325731 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59170 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59170 |  |  | 3 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /A /07/DFAA-FP-59170 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59170 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400308551 | 6M CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | SCH | SCH | 5 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2024-03-01 | 2024-03-17 | 10 | SCH | SCH | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400308551 | 6M CRUD OL BOSTR PMP MAINT-DFFA-P-3601/2 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | SCH | SCH | 2 | 0 | 24-W05-06 | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2024-03-01 | 2024-03-17 | 20 | SCH | SCH | DF /F /21/DFFA-P-3601 | CRUD OL BOSTR PMPS MAINT-DFFA-P-3601/2 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400214934 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-10-08 | 2022-11-07 | 10 |  |  | DF /F /54/DFFA-EP-3807 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400214934 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-10-08 | 2022-11-07 | 20 |  |  | DF /F /54/DFFA-EP-3807 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400214934 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-10-08 | 2022-11-07 | 30 |  |  | DF /F /54/DFFA-EP-3807 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400214934 | 1Y WI PIG LAUNCHER MAINT DFFA-EP-3807 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2022-10-08 | 2022-11-07 | 40 |  |  | DF /F /54/DFFA-EP-3807 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300006565 | DK40 - REPLACED BY 230007985 CONSUMABLE | OIW Correlation |  |  | 0 | 0 | Empty | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2026-08-23 | 10 |  |  | DF /C /75 | OIW Correlation | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300006565 | DK40 - REPLACED BY 230007985 CONSUMABLE | OIW Correlation |  |  | 0 | 0 | Empty | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2026-08-23 | 20 |  |  | DF /C /75 | OIW Correlation | Unknown
4 | NOSD | WRO | PRODLABO | PRODLABO | 2300006565 | DK40 - REPLACED BY 230007985 CONSUMABLE | OIW Correlation |  |  | 0 | 0 | Empty | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2024-03-06 | 2026-08-23 | 30 |  |  | DF /C /75 | OIW Correlation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 8.699999999999999289457264236 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2019-09-19 | 2019-12-18 | 10 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 8 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2019-09-19 | 2019-12-18 | 11 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 60 | 14 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-09 | 2019-09-19 | 2019-12-18 | 20 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 6 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-09 | 2019-09-19 | 2019-12-18 | 30 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 2 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-10 | 2019-09-19 | 2019-12-18 | 40 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 6 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-10 | 2019-09-19 | 2019-12-18 | 50 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 30 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-10 | 2024-01-12 | 2019-09-19 | 2019-12-18 | 60 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002924 | scaff/insulation FORCE: 15961 | L3 Permit & Preparation | PCNF | PCNF | 0 | 0 | CON-ELEC req'd | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2019-09-19 | 2019-12-18 | 70 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7569-AD-T | L3 Permit & Preparation | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400350894 | 3Y SANDJET PUMP MAINT DFFA-P-3401/02/03 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-10-12 | 10 |  |  | DF /F /20/DFFA-P-3401 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400350894 | 3Y SANDJET PUMP MAINT DFFA-P-3401/02/03 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W31-W32 | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-10-12 | 20 |  |  | DF /F /20/DFFA-P-3401 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400350894 | 3Y SANDJET PUMP MAINT DFFA-P-3401/02/03 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W31-W32 | 2024-07-30 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-10-12 | 30 |  |  | DF /F /20/DFFA-P-3401 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400350894 | 3Y SANDJET PUMP MAINT DFFA-P-3401/02/03 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-30 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2024-07-30 | 2024-10-12 | 40 |  |  | DF /F /20/DFFA-P-3401 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400350894 | 3Y SANDJET PUMP MAINT DFFA-P-3401/02/03 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-30 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-07-30 | 2024-10-12 | 50 |  |  | DF /F /20/DFFA-P-3401 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100075700 | Backload/repair blower unit DFCI-B-1221A | Prep. blower unit for backload for rep. |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2022-11-17 | 2023-04-01 | 10 |  |  | DF /C /09/DFCI-B-1221A | Prep. blower unit for backload for rep. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100075700 | Backload/repair blower unit DFCI-B-1221A | Prep. blower unit for backload for rep. |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2022-11-17 | 2023-04-01 | 20 |  |  | DF /C /09/DFCI-B-1221A | Prep. blower unit for backload for rep. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100075700 | Backload/repair blower unit DFCI-B-1221A | Prep. blower unit for backload for rep. |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-03 | 2022-11-17 | 2023-04-01 | 30 |  |  | DF /C /09/DFCI-B-1221A | Prep. blower unit for backload for rep. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100075700 | Backload/repair blower unit DFCI-B-1221A | Prep. blower unit for backload for rep. |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-02 | 2022-11-17 | 2023-04-01 | 40 |  |  | DF /C /09/DFCI-B-1221A | Prep. blower unit for backload for rep. | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100075700 | Backload/repair blower unit DFCI-B-1221A | Prep. blower unit for backload for rep. |  |  | 20 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2022-11-17 | 2023-04-01 | 50 |  |  | DF /C /09/DFCI-B-1221A | Prep. blower unit for backload for rep. | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100075700 | Backload/repair blower unit DFCI-B-1221A | Prep. blower unit for backload for rep. |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2022-11-17 | 2023-04-01 | 60 |  |  | DF /C /09/DFCI-B-1221A | Prep. blower unit for backload for rep. | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ACCO | 2200007892 | DAN FC Galley Follow up | Increase of PO 4500046598 |  |  | 36 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-19 | 2021-09-15 | 2021-10-25 | 10 |  |  | DF /C /09/DFCC-M-12052 | Increase of PO 4500046598 | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ACCO | 2200007892 | DAN FC Galley Follow up | Increase of PO 4500046598 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2021-09-15 | 2021-10-25 | 20 |  |  | DF /C /09/DFCC-M-12052 | Increase of PO 4500046598 | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ACCO | 2200007892 | DAN FC Galley Follow up | Increase of PO 4500046598 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2021-09-15 | 2021-10-25 | 30 |  |  | DF /C /09/DFCC-M-12052 | Increase of PO 4500046598 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235691 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235691 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235691 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235691 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR04-BA001 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040043 | DFB-02 HCV Gear ruined on prod. manifold | Mount gearbox on valve |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2020-11-11 | 2021-02-09 | 10 |  |  | DF /B /10/DFBA-HCV-300017 | Mount gearbox on valve | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322259 | DFC-27-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
2 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200007781 | DFC Water Damage Cabins 205,206,207 & 20 | Rental equip |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-08-12 | 2021-08-17 | 10 |  |  | DF /C /82 | Rental equip | Unknown
2 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200007781 | DFC Water Damage Cabins 205,206,207 & 20 | Rental equip |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-08-12 | 2021-08-17 | 20 |  |  | DF /C /82 | Rental equip | Unknown
2 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200007781 | DFC Water Damage Cabins 205,206,207 & 20 | Rental equip |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-08-12 | 2021-08-17 | 30 |  |  | DF /C /82 | Rental equip | Unknown
2 | NOSD | WGN | MTN-ELEC | VEN-MECH | 2200007781 | DFC Water Damage Cabins 205,206,207 & 20 | Rental equip |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-08-12 | 2021-08-17 | 40 |  |  | DF /C /82 | Rental equip | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 0 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-02 | 2022-07-02 | 2022-07-02 | 2023-04-28 | 10 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 8 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-02 | 2022-07-02 | 2022-07-02 | 2023-04-28 | 20 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 32 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-02 | 2022-07-05 | 2022-07-02 | 2023-04-28 | 30 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 6 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-05 | 2022-07-05 | 2022-07-02 | 2023-04-28 | 31 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 9 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-05 | 2022-07-06 | 2022-07-02 | 2023-04-28 | 32 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 12 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-06 | 2022-07-07 | 2022-07-02 | 2023-04-28 | 40 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 8 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-07 | 2022-07-07 | 2022-07-02 | 2023-04-28 | 50 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 8 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-07 | 2022-07-08 | 2022-07-02 | 2023-04-28 | 60 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 8 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-08 | 2022-07-08 | 2022-07-02 | 2023-04-28 | 70 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 24 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-08 | 2022-07-10 | 2022-07-02 | 2023-04-28 | 80 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100061294 | FFSPR: Replace 2" Open Drain Sour line | Prepare work area |  |  | 8 | 0 | Empty | 2022-07-02 | 2022-07-11 | 2022-07-10 | 2022-07-11 | 2022-07-02 | 2023-04-28 | 90 |  |  | DF /G /28/DFG-2-DOS-050-4040-BS-U | Prepare work area | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342429 | 1Y CATALYTIC GAS DETECTORS - DFC LVL 3 | CATALYTIC GAS DETECTORS CHECK | SECE | SECE | 23 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-12 | 2024-08-18 | 2024-07-29 | 2024-08-28 | 10 | SECE | SECE | DF /C /03/FGS-DETECTORS | CATALYTIC GAS DETECTORS CHECK | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 0 | 0 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-06-12 | 10 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 15 | 0 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-13 | 2022-01-14 | 2022-01-13 | 2022-06-12 | 20 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 75 | 73 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-14 | 2022-01-20 | 2022-01-13 | 2022-06-12 | 30 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 50 | 24 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-20 | 2022-01-22 | 2022-01-13 | 2022-06-12 | 40 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 50 | 24 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-22 | 2022-01-23 | 2022-01-13 | 2022-06-12 | 50 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 50 | 0 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-23 | 2022-01-28 | 2022-01-13 | 2022-06-12 | 60 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057419 | SYNSR-667006 DFA - Replacement of Handra | DFA - Replacement of Handrail EL. 26.200 |  |  | 12 | 0 | Empty | 2022-01-13 | 2022-01-28 | 2022-01-28 | 2022-01-28 | 2022-01-13 | 2022-06-12 | 70 |  |  | DF /A /86/24720 - HANDRAILS | DFA - Replacement of Handrail EL. 26.200 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057915 | Change Out Socketoutlet 1805-12L3G | Prove circuit is dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-22 | 2022-02-20 | 10 |  |  | DF /C /61/DFCI-DP-1805-12 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057915 | Change Out Socketoutlet 1805-12L3G | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-22 | 2022-02-20 | 20 |  |  | DF /C /61/DFCI-DP-1805-12 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057915 | Change Out Socketoutlet 1805-12L3G | Prove circuit is dead |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-11-22 | 2022-02-20 | 30 |  |  | DF /C /61/DFCI-DP-1805-12 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057915 | Change Out Socketoutlet 1805-12L3G | Prove circuit is dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-11-22 | 2022-02-20 | 40 |  |  | DF /C /61/DFCI-DP-1805-12 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057915 | Change Out Socketoutlet 1805-12L3G | Prove circuit is dead |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-22 | 2022-02-20 | 50 |  |  | DF /C /61/DFCI-DP-1805-12 | Prove circuit is dead | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100102265 | DFC-BDV-44126 ZSO flipper | Isolate/Replace ZSO44126 | SCH | SCH | 2 | 10 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-11-18 | 2024-01-02 | 10 | SCH | SCH | DF /C /34/DFCI-BDV-44126 | Isolate/Replace ZSO44126 | Unknown
2 | NOSD | WDF | MTN-INST | PRODTECH | 2100102265 | DFC-BDV-44126 ZSO flipper | Isolate/Replace ZSO44126 | SCH | SCH | 2 | 2 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-11-18 | 2024-01-02 | 20 | SCH | SCH | DF /C /34/DFCI-BDV-44126 | Isolate/Replace ZSO44126 | Unknown
4 | DFF-OIL | WGN | MTN-MECH | PRODTECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 2 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-19 | 2024-06-19 | 2022-03-28 | 2022-11-23 | 10 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | PRODTECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 2 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-19 | 2024-06-20 | 2022-03-28 | 2022-11-23 | 20 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-RIGG | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 24 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-20 | 2024-06-23 | 2022-03-28 | 2022-11-23 | 30 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-MECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 5 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-23 | 2024-06-24 | 2022-03-28 | 2022-11-23 | 40 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-MECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 0 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-24 | 2024-06-24 | 2022-03-28 | 2022-11-23 | 50 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-RIGG | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 12 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-24 | 2024-06-26 | 2022-03-28 | 2022-11-23 | 60 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | PRODTECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 2 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-26 | 2024-06-26 | 2022-03-28 | 2022-11-23 | 70 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-MECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 5 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-26 | 2024-06-27 | 2022-03-28 | 2022-11-23 | 80 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | PRODTECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 4 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-27 | 2024-06-28 | 2022-03-28 | 2022-11-23 | 90 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-MECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 0 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2022-03-28 | 2022-11-23 | 100 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
4 | DFF-OIL | WGN | MTN-MECH | MTN-MECH | 2200008741 | PSV Exchange DFFA-PSV-340006 - 2022 | Rigging Assist (Install) | SECE | SECE | 0 | 0 | Empty | 2024-06-19 | 2024-06-28 | 2024-06-28 | 2024-06-28 | 2022-03-28 | 2022-11-23 | 110 | SECE | SECE | DF /F /10/DFFA-PSV-340006 | Rigging Assist (Install) | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322228 | DFA-28-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 51 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400263367 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-07-01 | 2023-07-12 | 20 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400263367 | 3M TEMP ELEC INSTALLATIONS CHECK - DFC | TEMP ELEC INSTALLATIONS CHECK - DFC |  |  | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2023-07-01 | 2023-07-12 | 30 |  |  | DF /C /84/TI | TEMP ELEC INSTALLATIONS CHECK - DFC | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339106 | DFC_1Y_FIRE AND BLAST-WALLS INSP | DFC_1Y_FIRE AND BLAST-WALLS INSP | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /02/FIRE AND BLAST-WALLS | DFC_1Y_FIRE AND BLAST-WALLS INSP | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235823 | 4Y 380V E-SWB MAINT DFFA-N-1812-04 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1812-04 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235823 | 4Y 380V E-SWB MAINT DFFA-N-1812-04 | ISOLATION BY PRODUCTION | SCH | SCH | 7 | 0 | W07-W08 | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1812-04 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235823 | 4Y 380V E-SWB MAINT DFFA-N-1812-04 | ISOLATION BY PRODUCTION | SCH | SCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1812-04 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235823 | 4Y 380V E-SWB MAINT DFFA-N-1812-04 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1812-04 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344032 | 1Y FW HR/HYD/MONIT MAINT-DFG | FW HR/HYD/MONIT MAINT-DFG | SECE | SECE | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-05 | 2024-08-26 | 2024-09-02 | 2024-08-18 | 2024-09-17 | 10 | SECE | SECE | DF /G /01/FW-HOSEREELS | FW HR/HYD/MONIT MAINT-DFG | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400344032 | 1Y FW HR/HYD/MONIT MAINT-DFG | FW HR/HYD/MONIT MAINT-DFG | SECE | SECE | 28 | 0 | W35-W36 | 2024-08-26 | 2024-09-05 | 2024-09-02 | 2024-09-05 | 2024-08-18 | 2024-09-17 | 20 | SECE | SECE | DF /G /01/FW-HOSEREELS | FW HR/HYD/MONIT MAINT-DFG | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344032 | 1Y FW HR/HYD/MONIT MAINT-DFG | FW HR/HYD/MONIT MAINT-DFG | SECE | SECE | 3 | 0 | W35-W36 | 2024-08-26 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-08-18 | 2024-09-17 | 30 | SECE | SECE | DF /G /01/FW-HOSEREELS | FW HR/HYD/MONIT MAINT-DFG | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400302348 | 1Y ANTIFOULING SYSTEM CHECK - DFF | ISOLATION BY PRODUCTION | SCH | SCH | 2 | 3 | W35-W36 | 2024-08-26 | 2024-09-29 | 2024-08-26 | 2024-08-26 | 2024-01-01 | 2024-02-06 | 10 | SCH | SCH | DF /F /52/DFFA-A-5301 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400302348 | 1Y ANTIFOULING SYSTEM CHECK - DFF | ISOLATION BY PRODUCTION | SCH | SCH | 12 | 0 | W35-W36 | 2024-08-26 | 2024-09-29 | 2024-08-26 | 2024-08-26 | 2024-01-01 | 2024-02-06 | 20 | SCH | SCH | DF /F /52/DFFA-A-5301 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400302348 | 1Y ANTIFOULING SYSTEM CHECK - DFF | ISOLATION BY PRODUCTION | SCH | SCH | 30 | 27 | W35-W36 | 2024-08-26 | 2024-09-29 | 2024-08-26 | 2024-08-29 | 2024-01-01 | 2024-02-06 | 30 | SCH | SCH | DF /F /52/DFFA-A-5301 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302348 | 1Y ANTIFOULING SYSTEM CHECK - DFF | ISOLATION BY PRODUCTION | SCH | SCH | 140 | 96 | W35-W36 | 2024-08-26 | 2024-09-29 | 2024-08-29 | 2024-09-29 | 2024-01-01 | 2024-02-06 | 40 | SCH | SCH | DF /F /52/DFFA-A-5301 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400302348 | 1Y ANTIFOULING SYSTEM CHECK - DFF | ISOLATION BY PRODUCTION | SCH | SCH | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2024-01-01 | 2024-02-06 | 50 | SCH | SCH | DF /F /52/DFFA-A-5301 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400302348 | 1Y ANTIFOULING SYSTEM CHECK - DFF | ISOLATION BY PRODUCTION | SCH | SCH | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2024-01-01 | 2024-02-06 | 60 | SCH | SCH | DF /F /52/DFFA-A-5301 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | PRODTECH | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 24 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-08-28 | 2023-08-30 | 2023-04-09 | 2023-08-22 | 10 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | PRODTECH | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 8 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-08-31 | 2023-09-01 | 2023-04-09 | 2023-08-22 | 20 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | MTN-INST | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 4 | 16 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-02 | 2023-09-02 | 2023-04-09 | 2023-08-22 | 30 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | VEN-MECH | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 4 | 17 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-03 | 2023-09-03 | 2023-04-09 | 2023-08-22 | 40 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | MTN-PIPF | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 24 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-03 | 2023-09-04 | 2023-04-09 | 2023-08-22 | 50 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | MTN-INST | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 2 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-04 | 2023-09-05 | 2023-04-09 | 2023-08-22 | 60 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | VEN-MECH | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 112 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-05 | 2023-09-16 | 2023-04-09 | 2023-08-22 | 70 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | PRODTECH | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 24 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-16 | 2023-09-19 | 2023-04-09 | 2023-08-22 | 80 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | MTN-TURB | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 16 | 16 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-19 | 2023-09-23 | 2023-04-09 | 2023-08-22 | 90 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | MTN-TURB | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 0 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-23 | 2023-09-23 | 2023-04-09 | 2023-08-22 | 100 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
3 | DFF-IPHP | WGN | MTN-TURB | MTN-TURB | 2200013652 | DFF; Rupture disc Primary vent line upgr | Isolation of Unit | SCHSECE | SCHSECE | 0 | 0 | W35-36 | 2023-08-28 | 2023-09-23 | 2023-09-23 | 2023-09-23 | 2023-04-09 | 2023-08-22 | 110 | SCHSECE | SCHSECE | DF /F /31/DFFA-C-4301 | Isolation of Unit | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235725 | 4Y 380V E-SWB MAINT DFCI-N-1812-R06 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-12 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235725 | 4Y 380V E-SWB MAINT DFCI-N-1812-R06 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-12 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235725 | 4Y 380V E-SWB MAINT DFCI-N-1812-R06 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 18 | 0 | W19-W20 | 2024-05-10 | 2024-05-12 | 2024-05-10 | 2024-05-12 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235725 | 4Y 380V E-SWB MAINT DFCI-N-1812-R06 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-12 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235725 | 4Y 380V E-SWB MAINT DFCI-N-1812-R06 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-03-30 | 2021-08-27 | 10 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-03-30 | 2021-08-27 | 20 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-03-30 | 2021-08-27 | 30 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-03-30 | 2021-08-27 | 40 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-03-30 | 2021-08-27 | 50 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-03-30 | 2021-08-27 | 60 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100043948 | DFFA-TI-410555 FAIL | Isolate DFFA-TI-410555 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-03-30 | 2021-08-27 | 70 |  |  | DF /F /30/DFFA-E-4102 | Isolate DFFA-TI-410555 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096110 | EMS-0602 Replace valve and actuator | Isolate to replace valve and actuator |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-01 | 2024-01-14 | 10 |  |  | DF /B /02/DFBA-EMS-0602 | Isolate to replace valve and actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096110 | EMS-0602 Replace valve and actuator | Isolate to replace valve and actuator |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-01 | 2024-01-14 | 20 |  |  | DF /B /02/DFBA-EMS-0602 | Isolate to replace valve and actuator | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100096110 | EMS-0602 Replace valve and actuator | Isolate to replace valve and actuator |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-01 | 2024-01-14 | 30 |  |  | DF /B /02/DFBA-EMS-0602 | Isolate to replace valve and actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100096110 | EMS-0602 Replace valve and actuator | Isolate to replace valve and actuator |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-01 | 2024-01-14 | 40 |  |  | DF /B /02/DFBA-EMS-0602 | Isolate to replace valve and actuator | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100096110 | EMS-0602 Replace valve and actuator | Isolate to replace valve and actuator |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-01 | 2024-01-14 | 50 |  |  | DF /B /02/DFBA-EMS-0602 | Isolate to replace valve and actuator | Unknown
D | NOSD | WPM | MTN-PAIN | MTN-ROUS | 2400342415 | 1Y HOSES/ROLLERS/HANDLES MAINT - DFF | HOSES/ROLLERS/HANDLES MAINT - DFF |  |  | 6 | 0 | Empty | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-09-05 | 10 |  |  | DF /F /84 | HOSES/ROLLERS/HANDLES MAINT - DFF | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291802 | 6M PROD WTR HP/LP SKD MAINT-DFFA-A-5005 | PROD WTR HP/LP SKD INSP-DFFA-A-5005 |  |  | 8 | 0 | W21-W22 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-03 | 2023-11-25 | 2023-12-14 | 10 |  |  | DF /F /27/DFFA-A-5005 | PROD WTR HP/LP SKD INSP-DFFA-A-5005 | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400325773 | 5Y LIFE BOAT LOAD TEST - DFGA-X-0701 | LIFEBOAT LOAD TEST - DFGA-X-0701 | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-03-13 | 2024-06-01 | 10 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0701 | LIFEBOAT LOAD TEST - DFGA-X-0701 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400325773 | 5Y LIFE BOAT LOAD TEST - DFGA-X-0701 | LIFEBOAT LOAD TEST - DFGA-X-0701 | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-03-13 | 2024-06-01 | 20 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0701 | LIFEBOAT LOAD TEST - DFGA-X-0701 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105560 | Swivel broken after flanges on HR-0340 | Production Isolation | SECE | SECE | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2024-02-29 | 2024-07-13 | 10 | SECE | SECE | DF /A /01/DFAA-HR-0340 | Production Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100105560 | Swivel broken after flanges on HR-0340 | Production Isolation | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2024-02-29 | 2024-07-13 | 20 | SECE | SECE | DF /A /01/DFAA-HR-0340 | Production Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105560 | Swivel broken after flanges on HR-0340 | Production Isolation | SECE | SECE | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-02-29 | 2024-07-13 | 30 | SECE | SECE | DF /A /01/DFAA-HR-0340 | Production Isolation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100105560 | Swivel broken after flanges on HR-0340 | Production Isolation | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-02-29 | 2024-07-13 | 40 | SECE | SECE | DF /A /01/DFAA-HR-0340 | Production Isolation | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339043 | DFA_1Y_FIRE AND BLAST-WALLS INSP | DFA_1Y_FIRE AND BLAST-WALLS INSP | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /02/FIRE AND BLAST-WALLS | DFA_1Y_FIRE AND BLAST-WALLS INSP | Unknown
3 | DFF-1630 | WDF | MTN-TURB | PRODTECH | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-04-19 | 2022-07-18 | 10 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | MTN-TURB | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-04-19 | 2022-07-18 | 20 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | MTN-TURB | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-04-19 | 2022-07-18 | 30 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | MTN-TURB | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-04-19 | 2022-07-18 | 40 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | MTN-TURB | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-04-19 | 2022-07-18 | 50 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | MTN-TURB | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-04-19 | 2022-07-18 | 60 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | PRODTECH | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2022-04-19 | 2022-07-18 | 70 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
3 | DFF-1630 | WDF | MTN-TURB | MTN-TURB | 2100065954 | Lube oil cooler extern leaking | Isolation of DFFA-A-1630 - PROD |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2022-04-19 | 2022-07-18 | 80 |  |  | DF /F /60/DFFA-E-1630 | Isolation of DFFA-A-1630 - PROD | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | PRODTECH | 2400259642 | 8KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 5 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-29 | 2024-09-18 | 2024-09-19 | 2023-05-26 | 2023-06-25 | 10 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | MTN-MECH | 2400259642 | 8KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 10 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-29 | 2024-09-19 | 2024-09-22 | 2023-05-26 | 2023-06-25 | 20 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | MTN-INST | 2400259642 | 8KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 18 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-29 | 2024-09-22 | 2024-09-26 | 2023-05-26 | 2023-06-25 | 30 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | MTN-ELEC | 2400259642 | 8KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 5 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-29 | 2024-09-26 | 2024-09-27 | 2023-05-26 | 2023-06-25 | 40 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
A | DFF-LP-1 | WPM | MTN-MECH | PRODTECH | 2400259642 | 8KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 5 | 0 | 24-W07-08 | 2024-09-18 | 2024-09-29 | 2024-09-27 | 2024-09-29 | 2023-05-26 | 2023-06-25 | 50 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
1 | NE | WDF | MTN-TURB | MTN-TURB | 2100107977 | DFFB-P-3580 Low lube oil pressure loss. | PO Solar Turbines |  |  | 60 | 90 | Empty | 2024-02-27 | 2024-03-08 | 2024-02-27 | 2024-03-05 | 2024-02-23 | 2024-03-09 | 10 |  |  | DF /F /54/DFFB-P-3580 | PO Solar Turbines | Unknown
1 | NE | WDF | MTN-TURB | MTN-TURB | 2100107977 | DFFB-P-3580 Low lube oil pressure loss. | PO Solar Turbines |  |  | 12 | 3 | Empty | 2024-02-27 | 2024-03-08 | 2024-03-05 | 2024-03-08 | 2024-02-23 | 2024-03-09 | 20 |  |  | DF /F /54/DFFB-P-3580 | PO Solar Turbines | Unknown
1 | NE | WDF | MTN-TURB | MTN-TURB | 2100107977 | DFFB-P-3580 Low lube oil pressure loss. | PO Solar Turbines |  |  | 0 | 0 | Empty | 2024-02-27 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-02-23 | 2024-03-09 | 30 |  |  | DF /F /54/DFFB-P-3580 | PO Solar Turbines | Unknown
1 | NE | WDF | MTN-TURB | MTN-TURB | 2100107977 | DFFB-P-3580 Low lube oil pressure loss. | PO Solar Turbines |  |  | 0 | 0 | Empty | 2024-02-27 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-02-23 | 2024-03-09 | 40 |  |  | DF /F /54/DFFB-P-3580 | PO Solar Turbines | Unknown
1 | NE | WDF | MTN-TURB | MTN-SCAF | 2100107977 | DFFB-P-3580 Low lube oil pressure loss. | PO Solar Turbines |  |  | 0 | 9 | Empty | 2024-02-27 | 2024-03-08 | 2024-03-08 | 2024-03-08 | 2024-02-23 | 2024-03-09 | 50 |  |  | DF /F /54/DFFB-P-3580 | PO Solar Turbines | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100082293 | DFA/78 Floating switch loose on cooling | Replace both switches on exp tanks | SCH | SCH | 1 | 2 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2023-03-16 | 2023-07-29 | 10 | SCH | SCH | DF /A /78/DFAA-X-6102 | Replace both switches on exp tanks | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100082293 | DFA/78 Floating switch loose on cooling | Replace both switches on exp tanks | SCH | SCH | 5 | 2 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2023-03-16 | 2023-07-29 | 20 | SCH | SCH | DF /A /78/DFAA-X-6102 | Replace both switches on exp tanks | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100082293 | DFA/78 Floating switch loose on cooling | Replace both switches on exp tanks | SCH | SCH | 3 | 7 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2023-03-16 | 2023-07-29 | 25 | SCH | SCH | DF /A /78/DFAA-X-6102 | Replace both switches on exp tanks | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100082293 | DFA/78 Floating switch loose on cooling | Replace both switches on exp tanks | SCH | SCH | 1 | 2 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2023-03-16 | 2023-07-29 | 30 | SCH | SCH | DF /A /78/DFAA-X-6102 | Replace both switches on exp tanks | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018143 | Replace Motor protection 1841-M120 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M120-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018143 | Replace Motor protection 1841-M120 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M120-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018143 | Replace Motor protection 1841-M120 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M120-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018143 | Replace Motor protection 1841-M120 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M120-02 | Isolation of Breaker section | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322303 | DFG-23-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 2 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /23/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235590 | 4Y 380V E/N-DP-MAINT-DFC-L/S POWER | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1802 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235590 | 4Y 380V E/N-DP-MAINT-DFC-L/S POWER | ISOLATION ELECTRICAL | AWSC | AWSC | 27 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-28 | 2023-03-16 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1802 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235590 | 4Y 380V E/N-DP-MAINT-DFC-L/S POWER | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2023-03-16 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1802 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235590 | 4Y 380V E/N-DP-MAINT-DFC-L/S POWER | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2023-03-16 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1802 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339210 | DFE_1Y_26200 INT STRUCT INSP - GVI | DFE_1Y_26200 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /86/EL_26200 (MEZZANINE DECK) | DFE_1Y_26200 INT STRUCT INSP - GVI | Unknown
B | SIWL | WPM | MTN-MECH | PRODTECH | 2400284118 | 1Y FUNCT AND VISUAL INSP ESDV (DFB-O02) | DE-ISOLATION |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-09-30 | 2023-10-30 | 10 |  |  | DF /B /03/SDV-VALVES | DE-ISOLATION | Unknown
B | SIWL | WPM | MTN-MECH | MTN-MECH | 2400284118 | 1Y FUNCT AND VISUAL INSP ESDV (DFB-O02) | DE-ISOLATION |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-09-30 | 2023-10-30 | 20 |  |  | DF /B /03/SDV-VALVES | DE-ISOLATION | Unknown
B | SIWL | WPM | MTN-MECH | PRODTECH | 2400284118 | 1Y FUNCT AND VISUAL INSP ESDV (DFB-O02) | DE-ISOLATION |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-09-30 | 2023-10-30 | 30 |  |  | DF /B /03/SDV-VALVES | DE-ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235704 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235704 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235704 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235704 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR03-01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 10 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 20 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 30 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-10-14 | 2021-01-12 | 40 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-10-14 | 2021-01-12 | 50 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2020-10-14 | 2021-01-12 | 60 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2020-10-14 | 2021-01-12 | 70 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-10-14 | 2021-01-12 | 80 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-10-14 | 2021-01-12 | 90 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100038441 | DFF - Replace XCV500462 Due to FFC | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2020-10-14 | 2021-01-12 | 100 |  |  | DF /G /28/DFGA-XCV-500462 | Remove Insulation | Unknown
A | D-GASTYE | WPM | MTN-MECH | PRODTECH | 2400230365 | 1Y GAS LINE SCRAPPER MAINT-DFBA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-19 | 2023-02-18 | 10 | SECE | SECE | DF /B /34/DFBA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | D-GASTYE | WPM | MTN-MECH | MTN-INST | 2400230365 | 1Y GAS LINE SCRAPPER MAINT-DFBA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-01-19 | 2023-02-18 | 20 | SECE | SECE | DF /B /34/DFBA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | D-GASTYE | WPM | MTN-MECH | MTN-MECH | 2400230365 | 1Y GAS LINE SCRAPPER MAINT-DFBA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-01-19 | 2023-02-18 | 30 | SECE | SECE | DF /B /34/DFBA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
A | D-GASTYE | WPM | MTN-MECH | PRODTECH | 2400230365 | 1Y GAS LINE SCRAPPER MAINT-DFBA-EP-3805 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-01-19 | 2023-02-18 | 40 | SECE | SECE | DF /B /34/DFBA-EP-3805 | ISOLATION BY PRODUCTION | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 156 | 5 | Empty | 2023-01-31 | 2023-04-05 | 2023-01-31 | 2023-02-16 | 2020-07-07 | 2020-08-16 | 10 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 27 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-02-16 | 2023-02-19 | 2020-07-07 | 2020-08-16 | 20 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 31 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-02-19 | 2023-02-22 | 2020-07-07 | 2020-08-16 | 30 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 21 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-02-22 | 2023-02-24 | 2020-07-07 | 2020-08-16 | 40 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 125 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-02-24 | 2023-03-10 | 2020-07-07 | 2020-08-16 | 50 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 19 | 3 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-10 | 2023-03-12 | 2020-07-07 | 2020-08-16 | 60 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 12 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-12 | 2023-03-13 | 2020-07-07 | 2020-08-16 | 70 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 12 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-13 | 2023-03-14 | 2020-07-07 | 2020-08-16 | 80 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 62 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-14 | 2023-03-21 | 2020-07-07 | 2020-08-16 | 90 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 74 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-21 | 2023-03-28 | 2020-07-07 | 2020-08-16 | 100 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 12 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-28 | 2023-03-30 | 2020-07-07 | 2020-08-16 | 110 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300001732 | DAF OCG NPT order - 2700001766,7/TME1897 | Clean-up & housekeeping | PCNF | PCNF | 62 | 0 | Empty | 2023-01-31 | 2023-04-05 | 2023-03-30 | 2023-04-05 | 2020-07-07 | 2020-08-16 | 120 | PCNF | PCNF | DF /C | Clean-up & housekeeping | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339209 | DFE_1Y_23000 INT STRUCT INSP - GVI | DFE_1Y_23000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /86/EL_23000 (CELLAR DECK) | DFE_1Y_23000 INT STRUCT INSP - GVI | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100022948 | CMAT:DFE defekt ventil i slimline ventil | L3 isolate valve | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-06-09 | 2019-09-07 | 10 | AWSC | AWSC | DF /E /75 | L3 isolate valve | Unknown
3 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100022948 | CMAT:DFE defekt ventil i slimline ventil | L3 isolate valve | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2019-06-09 | 2019-09-07 | 20 | AWSC | AWSC | DF /E /75 | L3 isolate valve | Unknown
3 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100022948 | CMAT:DFE defekt ventil i slimline ventil | L3 isolate valve | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2019-06-09 | 2019-09-07 | 30 | AWSC | AWSC | DF /E /75 | L3 isolate valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081459 | Leak on drain for water mist DFC ACC | Mech to dismount pipe |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 10 |  |  | DF /C /01/DFCC-HCV-030021 | Mech to dismount pipe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081459 | Leak on drain for water mist DFC ACC | Mech to dismount pipe |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2023-03-04 | 2023-07-17 | 20 |  |  | DF /C /01/DFCC-HCV-030021 | Mech to dismount pipe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081459 | Leak on drain for water mist DFC ACC | Mech to dismount pipe |  |  | 6 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2023-03-04 | 2023-07-17 | 30 |  |  | DF /C /01/DFCC-HCV-030021 | Mech to dismount pipe | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081459 | Leak on drain for water mist DFC ACC | Mech to dismount pipe |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2023-03-04 | 2023-07-17 | 40 |  |  | DF /C /01/DFCC-HCV-030021 | Mech to dismount pipe | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 0 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-05 | 2023-06-05 | 2023-06-05 | 2023-10-18 | 10 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 8 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-05 | 2023-06-06 | 2023-06-05 | 2023-10-18 | 20 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | PRODTECH | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 6 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-06 | 2023-06-06 | 2023-06-05 | 2023-10-18 | 30 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 84 | 34 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-06 | 2023-06-13 | 2023-06-05 | 2023-10-18 | 40 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 16 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-13 | 2023-06-14 | 2023-06-05 | 2023-10-18 | 50 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | INP-SITE | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 2 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-14 | 2023-06-14 | 2023-06-05 | 2023-10-18 | 60 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 12 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-14 | 2023-06-15 | 2023-06-05 | 2023-10-18 | 70 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 4 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-15 | 2023-06-15 | 2023-06-05 | 2023-10-18 | 80 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 4 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-15 | 2023-06-16 | 2023-06-05 | 2023-10-18 | 90 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | PRODTECH | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 6 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-16 | 2023-06-16 | 2023-06-05 | 2023-10-18 | 100 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100089593 | FFSPR Replacement Spool DFG-2"-DOS-50016 | Install new spool | PCNF | PCNF | 42 | 0 | Empty | 2023-06-05 | 2023-06-20 | 2023-06-16 | 2023-06-20 | 2023-06-05 | 2023-10-18 | 120 | PCNF | PCNF | DF /G /28/DFG-2-DOS-050-0169-AB-T | Install new spool | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 1 | 2 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 10 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 8 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 20 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 4 | 10 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 30 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 3 | 10 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 40 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 50 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 60 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 70 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 80 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400328727 | 1Y HVAC SUPP/EXH AHU CHECK - DFFA-A-1201 | operation_description_not_present | PCNFSCHSECE | PCNFSCHSECE | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-05-06 | 2024-06-05 | 90 | PCNFSCHSECE | PCNFSCHSECE | DF /F /09/DFFA-A-1201 | operation_description_not_present | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268044 | 6M SDV LUB/MAINT FUEL GAS - DFG | SDV LUB/INSP FUEL GAS - DFG |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-07-16 | 2023-08-01 | 10 |  |  | DF /G /03/SDV-VALVES | SDV LUB/INSP FUEL GAS - DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100056159 | Valve internal leaking on T-6102 N2/N6 | Production deisolation w leak test |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-17 | 2021-10-22 | 2022-01-20 | 10 |  |  | DF /F /75/DFFA-T-6102 | Production deisolation w leak test | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056159 | Valve internal leaking on T-6102 N2/N6 | Production deisolation w leak test |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-18 | 2021-10-22 | 2022-01-20 | 20 |  |  | DF /F /75/DFFA-T-6102 | Production deisolation w leak test | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056159 | Valve internal leaking on T-6102 N2/N6 | Production deisolation w leak test |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-17 | 2024-09-19 | 2021-10-22 | 2022-01-20 | 30 |  |  | DF /F /75/DFFA-T-6102 | Production deisolation w leak test | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056159 | Valve internal leaking on T-6102 N2/N6 | Production deisolation w leak test |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-20 | 2021-10-22 | 2022-01-20 | 40 |  |  | DF /F /75/DFFA-T-6102 | Production deisolation w leak test | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056159 | Valve internal leaking on T-6102 N2/N6 | Production deisolation w leak test |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-20 | 2021-10-22 | 2022-01-20 | 50 |  |  | DF /F /75/DFFA-T-6102 | Production deisolation w leak test | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100056159 | Valve internal leaking on T-6102 N2/N6 | Production deisolation w leak test |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-20 | 2024-09-22 | 2021-10-22 | 2022-01-20 | 60 |  |  | DF /F /75/DFFA-T-6102 | Production deisolation w leak test | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235752 | 4Y 400V E-DP INSPN.-DFFB-DP-1832-B | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /05/DFFB-DP-1832-B | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235752 | 4Y 400V E-DP INSPN.-DFFB-DP-1832-B | ISOLATION BY PRODUCTION | SECE | SECE | 18 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /05/DFFB-DP-1832-B | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235752 | 4Y 400V E-DP INSPN.-DFFB-DP-1832-B | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /05/DFFB-DP-1832-B | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235752 | 4Y 400V E-DP INSPN.-DFFB-DP-1832-B | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /05/DFFB-DP-1832-B | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039472 | HCV leak at DFCM-PCV-52201 | Prod prepare permit/isolation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2021-02-02 | 2021-09-30 | 10 |  |  | DF /C /50 | Prod prepare permit/isolation | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100039472 | HCV leak at DFCM-PCV-52201 | Prod prepare permit/isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2021-02-02 | 2021-09-30 | 20 |  |  | DF /C /50 | Prod prepare permit/isolation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039472 | HCV leak at DFCM-PCV-52201 | Prod prepare permit/isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2021-02-02 | 2021-09-30 | 30 |  |  | DF /C /50 | Prod prepare permit/isolation | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100039472 | HCV leak at DFCM-PCV-52201 | Prod prepare permit/isolation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2021-02-02 | 2021-09-30 | 40 |  |  | DF /C /50 | Prod prepare permit/isolation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100039472 | HCV leak at DFCM-PCV-52201 | Prod prepare permit/isolation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2021-02-02 | 2021-09-30 | 50 |  |  | DF /C /50 | Prod prepare permit/isolation | Unknown
4 | Empty | WRO | MTN-ROUS | MTN-ROUS | 2300001387 | DK40 - erstattes af 2300002310 - DECK | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
4 | Empty | WRO | MTN-ROUS | MTN-ROUS | 2300001387 | DK40 - erstattes af 2300002310 - DECK | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
4 | Empty | WRO | MTN-ROUS | MTN-ROUS | 2300001387 | DK40 - erstattes af 2300002310 - DECK | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-09-09 | 2021-07-06 | 30 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400344059 | 1Y ESD CONTROL PANELS CHECK - DFF/G | ESD CONTROL PANELS CHECK - DFF/G | SECE | SECE | 7 | 8 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-08-25 | 2024-09-24 | 10 | SECE | SECE | DF /F /03/ESD-CONTROL-PANELS | ESD CONTROL PANELS CHECK - DFF/G | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230497 | 3M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-02-10 | 2023-02-20 | 10 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2021-11-01 | 2022-03-31 | 10 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2021-11-01 | 2022-03-31 | 20 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-17 | 2021-11-01 | 2022-03-31 | 30 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2021-11-01 | 2022-03-31 | 40 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2021-11-01 | 2022-03-31 | 50 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-17 | 2024-09-19 | 2021-11-01 | 2022-03-31 | 60 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2021-11-01 | 2022-03-31 | 70 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2021-11-01 | 2022-03-31 | 80 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053823 | HT replace cable 1810-66-L3I | Remove insulation |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2021-11-01 | 2022-03-31 | 90 |  |  | DF /B /61/DFBA-N-1810-C_66 | Remove insulation | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400302019 | 6M DEAERATOR MAINT - DFFB-A-3560 - DFF | DEAERATOR MAINT - DFFB-A-3560 - DFF | AWSC | AWSC | 2 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-15 | 2024-01-16 | 2024-02-04 | 10 | AWSC | AWSC | DF /F /53 | DEAERATOR MAINT - DFFB-A-3560 - DFF | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-INST | 2400302019 | 6M DEAERATOR MAINT - DFFB-A-3560 - DFF | DEAERATOR MAINT - DFFB-A-3560 - DFF | AWSC | AWSC | 24 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-21 | 2024-01-16 | 2024-02-04 | 20 | AWSC | AWSC | DF /F /53 | DEAERATOR MAINT - DFFB-A-3560 - DFF | Unknown
C | DFF-3580 | WPM | MTN-MECH | MTN-INST | 2400302019 | 6M DEAERATOR MAINT - DFFB-A-3560 - DFF | DEAERATOR MAINT - DFFB-A-3560 - DFF | AWSC | AWSC | 20 | 0 | Empty | 2024-09-15 | 2024-09-26 | 2024-09-21 | 2024-09-26 | 2024-01-16 | 2024-02-04 | 30 | AWSC | AWSC | DF /F /53 | DEAERATOR MAINT - DFFB-A-3560 - DFF | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-20 | 2024-06-20 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-20 | 2024-06-23 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-23 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 10 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-24 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 51 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-06-24 | 2024-06-25 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-23 | 2024-08-25 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-24 | 2024-08-25 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400291846 | PSV Calibration - DFGA-PSV-410443B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 10 | 0 | Empty | 2024-06-20 | 2024-08-26 | 2024-08-25 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410443B | Backload PSV to Norspie Workshop | Unknown
4 | DFB-3560 | WDF | MTN-MECH | MTN-MECH | 2100023750 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | AWSC | AWSC | 52 | 0 | 3560 being decomissioned | 2024-12-05 | 2024-12-20 | 2024-12-05 | 2024-12-09 | 2017-12-20 | 2018-03-20 | 9 | AWSC | AWSC | DF /B /28/DFBA-XCV-35380 | L3 Rigger Assist to move/Mount Valve | Unknown
4 | DFB-3560 | WDF | MTN-MECH | PRODTECH | 2100023750 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | AWSC | AWSC | 3 | 0 | 3560 being decomissioned | 2024-12-05 | 2024-12-20 | 2024-12-09 | 2024-12-10 | 2017-12-20 | 2018-03-20 | 10 | AWSC | AWSC | DF /B /28/DFBA-XCV-35380 | L3 Rigger Assist to move/Mount Valve | Unknown
4 | DFB-3560 | WDF | MTN-MECH | MTN-MECH | 2100023750 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | AWSC | AWSC | 26 | 0 | 3560 being decomissioned | 2024-12-05 | 2024-12-20 | 2024-12-10 | 2024-12-13 | 2017-12-20 | 2018-03-20 | 20 | AWSC | AWSC | DF /B /28/DFBA-XCV-35380 | L3 Rigger Assist to move/Mount Valve | Unknown
4 | DFB-3560 | WDF | MTN-MECH | MTN-RIGG | 2100023750 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | AWSC | AWSC | 26 | 0 | 3560 being decomissioned | 2024-12-05 | 2024-12-20 | 2024-12-13 | 2024-12-16 | 2017-12-20 | 2018-03-20 | 30 | AWSC | AWSC | DF /B /28/DFBA-XCV-35380 | L3 Rigger Assist to move/Mount Valve | Unknown
4 | DFB-3560 | WDF | MTN-MECH | PRODTECH | 2100023750 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | AWSC | AWSC | 3 | 0 | 3560 being decomissioned | 2024-12-05 | 2024-12-20 | 2024-12-16 | 2024-12-17 | 2017-12-20 | 2018-03-20 | 40 | AWSC | AWSC | DF /B /28/DFBA-XCV-35380 | L3 Rigger Assist to move/Mount Valve | Unknown
4 | DFB-3560 | WDF | MTN-MECH | MTN-MECH | 2100023750 | CMAT:DFB WI xcv 35380 intern læk | L3 Rigger Assist to move/Mount Valve | AWSC | AWSC | 39 | 0 | 3560 being decomissioned | 2024-12-05 | 2024-12-20 | 2024-12-17 | 2024-12-20 | 2017-12-20 | 2018-03-20 | 50 | AWSC | AWSC | DF /B /28/DFBA-XCV-35380 | L3 Rigger Assist to move/Mount Valve | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300005055 | Replaced by 2300005539 | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2026-02-25 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300005055 | Replaced by 2300005539 | DK40 - CONSUMABLE PROD - OIL |  |  | 1 | 0 | Empty | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2026-02-25 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300005055 | Replaced by 2300005539 | DK40 - CONSUMABLE PROD - OIL |  |  | 1 | 0 | Empty | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2023-09-09 | 2026-02-25 | 30 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235689 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF07-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235689 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF07-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235689 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF07-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235689 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF07-BA001 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400221590 | 6M WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA |  |  | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-01-12 | 2023-01-28 | 10 |  |  | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284276 | PSV Exchange - DFFA-PSV-431323 | De-isolation and leak test | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431323 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284276 | PSV Exchange - DFFA-PSV-431323 | De-isolation and leak test | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431323 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284276 | PSV Exchange - DFFA-PSV-431323 | De-isolation and leak test | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-31 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431323 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284276 | PSV Exchange - DFFA-PSV-431323 | De-isolation and leak test | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431323 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284276 | PSV Exchange - DFFA-PSV-431323 | De-isolation and leak test | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431323 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284276 | PSV Exchange - DFFA-PSV-431323 | De-isolation and leak test | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-PSV-431323 | De-isolation and leak test | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009241 | Insulation assits FORCE 21281(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /54/DFF-18-WI-035-9144-BB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009241 | Insulation assits FORCE 21281(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-03-27 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /54/DFF-18-WI-035-9144-BB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009241 | Insulation assits FORCE 21281(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-02 | 2023-04-03 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /54/DFF-18-WI-035-9144-BB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009241 | Insulation assits FORCE 21281(COMP) | Bilfinger inspection |  |  | 42 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-03 | 2023-04-05 | 2022-02-07 | 2022-07-07 | 33 |  |  | DF /F /54/DFF-18-WI-035-9144-BB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009241 | Insulation assits FORCE 21281(COMP) | Bilfinger inspection |  |  | 60 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-05 | 2023-04-08 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /54/DFF-18-WI-035-9144-BB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009241 | Insulation assits FORCE 21281(COMP) | Bilfinger inspection |  |  | 18 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-08 | 2023-04-10 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /54/DFF-18-WI-035-9144-BB-U | Bilfinger inspection | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300007615 | DFCSWL2 - ABB ESD SW | Dan F telecom assistance | SECE | SECE | 0 | 28 | W27-W28 | 2024-07-03 | 2024-07-07 | 2024-07-03 | 2024-07-03 | 2024-01-10 | 2024-02-24 | 10 | SECE | SECE | DF /C /03/DFCI-FP-0202 | Dan F telecom assistance | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300007615 | DFCSWL2 - ABB ESD SW | Dan F telecom assistance | SECE | SECE | 20 | 34 | W27-W28 | 2024-07-03 | 2024-07-07 | 2024-07-03 | 2024-07-07 | 2024-01-10 | 2024-02-24 | 20 | SECE | SECE | DF /C /03/DFCI-FP-0202 | Dan F telecom assistance | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100076134 | DFA: Bolts + buffer under cabin | Build/demol of scaffold for access |  |  | 3 | 0 | Empty | 2023-02-12 | 2023-02-19 | 2023-02-12 | 2023-02-12 | 2022-11-19 | 2023-04-03 | 10 |  |  | DF /A /78/DFAA-X-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076134 | DFA: Bolts + buffer under cabin | Build/demol of scaffold for access |  |  | 40 | 0 | Empty | 2023-02-12 | 2023-02-19 | 2023-02-12 | 2023-02-16 | 2022-11-19 | 2023-04-03 | 20 |  |  | DF /A /78/DFAA-X-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100076134 | DFA: Bolts + buffer under cabin | Build/demol of scaffold for access |  |  | 12 | 0 | Empty | 2023-02-12 | 2023-02-19 | 2023-02-16 | 2023-02-19 | 2022-11-19 | 2023-04-03 | 30 |  |  | DF /A /78/DFAA-X-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076134 | DFA: Bolts + buffer under cabin | Build/demol of scaffold for access |  |  | 12 | 0 | Empty | 2023-02-12 | 2023-02-19 | 2023-02-16 | 2023-02-19 | 2022-11-19 | 2023-04-03 | 40 |  |  | DF /A /78/DFAA-X-6102 | Build/demol of scaffold for access | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100076134 | DFA: Bolts + buffer under cabin | Build/demol of scaffold for access |  |  | 12 | 0 | Empty | 2023-02-12 | 2023-02-19 | 2023-02-16 | 2023-02-19 | 2022-11-19 | 2023-04-03 | 50 |  |  | DF /A /78/DFAA-X-6102 | Build/demol of scaffold for access | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023383 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 10 |  |  | DF /C /07/DFCM-HCV-54390-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023383 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 20 |  |  | DF /C /07/DFCM-HCV-54390-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023383 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 30 |  |  | DF /C /07/DFCM-HCV-54390-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023383 | Missing handle on DF /C /07/DFCM-HCV-543 | Isolation of valve |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2019-07-21 | 2020-07-15 | 40 |  |  | DF /C /07/DFCM-HCV-54390-U | Isolation of valve | Unknown
4 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 12 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-10 | 2024-09-12 | 2023-11-10 | 2024-03-24 | 10 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 3 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-13 | 2024-09-13 | 2023-11-10 | 2024-03-24 | 20 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 8 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-13 | 2024-09-15 | 2023-11-10 | 2024-03-24 | 30 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 12 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-15 | 2024-09-18 | 2023-11-10 | 2024-03-24 | 40 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 8 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-18 | 2024-09-20 | 2023-11-10 | 2024-03-24 | 50 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 12 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-20 | 2024-09-23 | 2023-11-10 | 2024-03-24 | 60 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-MECH | 2100098850 | DFGA-LG-410431 changeout LG and HCV's | DE-ISOLATE/TEST DFGA-LG-410431 |  |  | 4 | 0 | Empty | 2024-09-10 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-11-10 | 2024-03-24 | 70 |  |  | DF /G /30/DFGA-LG-410431 | DE-ISOLATE/TEST DFGA-LG-410431 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015383 | Replace FFLB1 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /G /02/DFGA-X-0701 | Flush coolant system with Glysantin G30 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015383 | Replace FFLB1 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /G /02/DFGA-X-0701 | Flush coolant system with Glysantin G30 | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015383 | Replace FFLB1 coolant with GlysantinG30 | Flush coolant system with Glysantin G30 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /G /02/DFGA-X-0701 | Flush coolant system with Glysantin G30 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 18 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 10 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 20 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 30 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 16 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 40 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 50 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 60 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 70 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 80 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-11-03 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 90 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-12-11 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 100 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-12-11 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 110 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-12-11 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 120 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2022-12-11 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 130 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-07 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 140 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-07 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 150 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-07 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 160 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-07 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 170 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-07 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 180 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-07 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 190 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-20 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 200 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-20 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 210 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-02-20 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 220 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 230 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 240 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 250 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 260 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 270 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 280 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-04-06 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 290 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 300 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 310 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 320 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 330 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 16 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 340 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 350 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 16 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 360 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 370 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 380 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 390 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 400 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 410 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 420 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-05-10 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 430 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 440 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 450 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 460 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 470 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 18 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 480 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 490 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 500 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 510 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-08-21 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 520 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 530 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 16 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 540 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 16 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 550 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 560 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 570 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 580 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 6 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 590 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 600 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2023-10-28 | 2024-01-02 | 2022-10-12 | 2022-11-26 | 610 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2024-01-09 | 2024-01-12 | 2022-10-12 | 2022-11-26 | 620 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 20 | Empty | 2024-01-09 | 2024-04-01 | 2024-01-19 | 2024-01-22 | 2022-10-12 | 2022-11-26 | 630 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2024-01-29 | 2024-02-01 | 2022-10-12 | 2022-11-26 | 640 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2024-02-08 | 2024-02-11 | 2022-10-12 | 2022-11-26 | 650 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 16 | Empty | 2024-01-09 | 2024-04-01 | 2024-02-18 | 2024-02-21 | 2022-10-12 | 2022-11-26 | 660 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2024-02-28 | 2024-03-02 | 2022-10-12 | 2022-11-26 | 670 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2024-03-09 | 2024-03-12 | 2022-10-12 | 2022-11-26 | 680 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 12 | Empty | 2024-01-09 | 2024-04-01 | 2024-03-19 | 2024-03-22 | 2022-10-12 | 2022-11-26 | 690 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-ROPE | 2200012206 | Rope assist to service team_week check | Crane weekly check acc to attached W14 | SCH | SCH | 12 | 0 | Empty | 2024-01-09 | 2024-04-01 | 2024-03-29 | 2024-04-01 | 2022-10-12 | 2022-11-26 | 700 | SCH | SCH | DF /C /78/DFCI-X-6101 | Crane weekly check acc to attached W14 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-15 | 2024-07-19 | 2019-10-24 | 2020-01-22 | 20 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 8 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-19 | 2024-07-21 | 2019-10-24 | 2020-01-22 | 30 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 3 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-21 | 2024-07-21 | 2019-10-24 | 2020-01-22 | 40 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-21 | 2024-07-22 | 2019-10-24 | 2020-01-22 | 50 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 3 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-22 | 2024-07-23 | 2019-10-24 | 2020-01-22 | 60 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-23 | 2024-07-27 | 2019-10-24 | 2020-01-22 | 65 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-27 | 2024-07-27 | 2019-10-24 | 2020-01-22 | 70 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 10 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-27 | 2024-07-30 | 2019-10-24 | 2020-01-22 | 80 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-30 | 2024-07-30 | 2019-10-24 | 2020-01-22 | 90 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-07-30 | 2024-08-03 | 2019-10-24 | 2020-01-22 | 100 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-08-03 | 2024-08-03 | 2019-10-24 | 2020-01-22 | 110 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 10 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-08-03 | 2024-08-06 | 2019-10-24 | 2020-01-22 | 120 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023393 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 1 |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-08-06 | 2024-08-06 | 2024-08-06 | 2019-10-24 | 2020-01-22 | 130 |  |  | DF /A /03 | build scarffold for finding 1 | Unknown
B | NOSD | WPM | MTN-INST | MTN-TELE | 2400325767 | 2Y MANUAL CALL POINTS MAINT- DFG | MANUAL CALL POINTS MAINT- DFG | SCH | SCH | 12 | 12 | W27-W28 | 2024-07-03 | 2024-07-05 | 2024-07-03 | 2024-07-05 | 2024-04-11 | 2024-05-27 | 10 | SCH | SCH | DF /G /03/SYSTEM-03-MANUAL-ALARM-CALL | MANUAL CALL POINTS MAINT- DFG | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400316027 | 6M VISUAL INSPECT OF ESDV (DFB-O02) | ESDV VISUAL INSPECTION |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-04-14 | 2024-04-30 | 10 |  |  | DF /B /03/SDV-VALVES | ESDV VISUAL INSPECTION | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100033324 | DFC Fuelgas V-5710 LCV can`t open | Isolate LCV-57122 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-06-25 | 2020-08-04 | 10 |  |  | DF /C /70/DFCI-LY-57122 | Isolate LCV-57122 | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100033324 | DFC Fuelgas V-5710 LCV can`t open | Isolate LCV-57122 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-06-25 | 2020-08-04 | 20 |  |  | DF /C /70/DFCI-LY-57122 | Isolate LCV-57122 | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100033324 | DFC Fuelgas V-5710 LCV can`t open | Isolate LCV-57122 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-06-25 | 2020-08-04 | 30 |  |  | DF /C /70/DFCI-LY-57122 | Isolate LCV-57122 | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100033324 | DFC Fuelgas V-5710 LCV can`t open | Isolate LCV-57122 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-06-25 | 2020-08-04 | 40 |  |  | DF /C /70/DFCI-LY-57122 | Isolate LCV-57122 | Unknown
3 | DFC-FUEL | WDF | MTN-INST | MTN-INST | 2100033324 | DFC Fuelgas V-5710 LCV can`t open | Isolate LCV-57122 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2020-06-25 | 2020-08-04 | 50 |  |  | DF /C /70/DFCI-LY-57122 | Isolate LCV-57122 | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | PRODTECH | 2100085366 | FCV-430011A volume booster. | Isolate FCV-430011A |  |  | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2023-03-30 | 2023-08-12 | 10 |  |  | DF /F /32/DFFA-FCV-430011A | Isolate FCV-430011A | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100085366 | FCV-430011A volume booster. | Isolate FCV-430011A |  |  | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2023-03-30 | 2023-08-12 | 20 |  |  | DF /F /32/DFFA-FCV-430011A | Isolate FCV-430011A | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100085366 | FCV-430011A volume booster. | Isolate FCV-430011A |  |  | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2023-03-30 | 2023-08-12 | 30 |  |  | DF /F /32/DFFA-FCV-430011A | Isolate FCV-430011A | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100085366 | FCV-430011A volume booster. | Isolate FCV-430011A |  |  | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2023-03-30 | 2023-08-12 | 40 |  |  | DF /F /32/DFFA-FCV-430011A | Isolate FCV-430011A | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-TURB | 2100085366 | FCV-430011A volume booster. | Isolate FCV-430011A |  |  | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-03-30 | 2023-08-12 | 50 |  |  | DF /F /32/DFFA-FCV-430011A | Isolate FCV-430011A | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | PRODTECH | 2100085366 | FCV-430011A volume booster. | Isolate FCV-430011A |  |  | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-03-30 | 2023-08-12 | 60 |  |  | DF /F /32/DFFA-FCV-430011A | Isolate FCV-430011A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-26 | 2024-08-26 | 2023-09-15 | 2024-01-28 | 5 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-26 | 2024-08-26 | 2023-09-15 | 2024-01-28 | 6 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-26 | 2024-08-26 | 2023-09-15 | 2024-01-28 | 10 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 12 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-26 | 2024-08-27 | 2023-09-15 | 2024-01-28 | 20 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-27 | 2024-08-27 | 2023-09-15 | 2024-01-28 | 30 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-27 | 2024-08-27 | 2023-09-15 | 2024-01-28 | 40 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 4 | 146 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-27 | 2024-08-28 | 2023-09-15 | 2024-01-28 | 50 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 20 | 316.5 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-08-28 | 2024-09-02 | 2023-09-15 | 2024-01-28 | 60 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 2 | 146 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-02 | 2024-09-03 | 2023-09-15 | 2024-01-28 | 70 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-03 | 2024-09-04 | 2023-09-15 | 2024-01-28 | 80 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 30 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-04 | 2024-09-08 | 2023-09-15 | 2024-01-28 | 85 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-08 | 2024-09-10 | 2023-09-15 | 2024-01-28 | 90 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-10 | 2024-09-13 | 2023-09-15 | 2024-01-28 | 95 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2023-09-15 | 2024-01-28 | 100 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100096127 | DFF-4202:Bearing defect on motor | Prepare C-4202 for startup (mech) |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2023-09-15 | 2024-01-28 | 110 |  |  | DF /F /31/DFFA-CM-4202 | Prepare C-4202 for startup (mech) | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044258 | Fejl indikering på DFCM-XCV-50406 | Vendor to Troubleshoot on XCV-50406 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-03 | 2021-07-04 | 2022-04-30 | 10 | AWSC | AWSC | DF /C /27/DFCM-XCV-50406 | Vendor to Troubleshoot on XCV-50406 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044258 | Fejl indikering på DFCM-XCV-50406 | Vendor to Troubleshoot on XCV-50406 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2021-07-04 | 2022-04-30 | 20 | AWSC | AWSC | DF /C /27/DFCM-XCV-50406 | Vendor to Troubleshoot on XCV-50406 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400329999 | 6M DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2024-06-13 | 2024-06-29 | 10 |  |  | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329999 | 6M DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2024-06-13 | 2024-06-29 | 20 |  |  | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400329999 | 6M DIESEL FUEL TANK & PUMPS MAINT - DFC | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2024-06-13 | 2024-06-29 | 30 |  |  | DF /C /71/DFCI-T-5701 | ISOLATION BY PRODUCTION | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2021-02-10 | 2021-05-11 | 10 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-02-10 | 2021-05-11 | 20 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-02-10 | 2021-05-11 | 30 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | PRODTECH | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-02-10 | 2021-05-11 | 40 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-02-10 | 2021-05-11 | 50 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-02-10 | 2021-05-11 | 60 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2021-02-10 | 2021-05-11 | 70 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | PRODTECH | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2021-02-10 | 2021-05-11 | 80 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-02-10 | 2021-05-11 | 90 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2021-02-10 | 2021-05-11 | 100 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100044421 | Intern lækage på ventil HCV-380229 | Rigger preparation | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-02-10 | 2021-05-11 | 110 | AWSC | AWSC | DF /F /23/DFFA-HCV-380229 | Rigger preparation | Unknown
4 | NOSD | WGN | MTN-INST | PRODTECH | 2200003161 | CMAT:DFF Replace 2 pcs. pressure gauge E | Remove isolation | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2018-04-27 | 2019-04-22 | 10 | SCH | SCH | DF /F /11/DFFA-ESDV-501003 | Remove isolation | Unknown
4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003161 | CMAT:DFF Replace 2 pcs. pressure gauge E | Remove isolation | SCH | SCH | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2018-04-27 | 2019-04-22 | 20 | SCH | SCH | DF /F /11/DFFA-ESDV-501003 | Remove isolation | Unknown
4 | NOSD | WGN | MTN-INST | PRODTECH | 2200003161 | CMAT:DFF Replace 2 pcs. pressure gauge E | Remove isolation | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2018-04-27 | 2019-04-22 | 30 | SCH | SCH | DF /F /11/DFFA-ESDV-501003 | Remove isolation | Unknown
4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003161 | CMAT:DFF Replace 2 pcs. pressure gauge E | Remove isolation | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2018-04-27 | 2019-04-22 | 40 | SCH | SCH | DF /F /11/DFFA-ESDV-501003 | Remove isolation | Unknown
4 | NOSD | WGN | MTN-INST | MTN-INST | 2200003161 | CMAT:DFF Replace 2 pcs. pressure gauge E | Remove isolation | SCH | SCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2018-04-27 | 2019-04-22 | 50 | SCH | SCH | DF /F /11/DFFA-ESDV-501003 | Remove isolation | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344048 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3941 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-19 | 2024-08-26 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-09-24 | 10 |  |  | DF /F /75/DFFA-A-3941 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344048 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3941 | DE-ISOLATION BY PRODUCTION |  |  | 21 | 0 | Empty | 2024-08-19 | 2024-08-26 | 2024-08-19 | 2024-08-24 | 2024-08-19 | 2024-09-24 | 20 |  |  | DF /F /75/DFFA-A-3941 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344048 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3941 | DE-ISOLATION BY PRODUCTION |  |  | 8 | 0 | Empty | 2024-08-19 | 2024-08-26 | 2024-08-24 | 2024-08-26 | 2024-08-19 | 2024-09-24 | 30 |  |  | DF /F /75/DFFA-A-3941 | DE-ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344048 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3941 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-19 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-19 | 2024-09-24 | 40 |  |  | DF /F /75/DFFA-A-3941 | DE-ISOLATION BY PRODUCTION | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2015-11-14 | 2016-12-24 | 1 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2015-11-14 | 2016-12-24 | 2 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2015-11-14 | 2016-12-24 | 3 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 5 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2015-11-14 | 2016-12-24 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 4.4000000000000003552713678785 | 1 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2015-11-14 | 2016-12-24 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-ELEC | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2015-11-14 | 2016-12-24 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-ELEC | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2015-11-14 | 2016-12-24 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-07 | 2015-11-14 | 2016-12-24 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-05 | 2015-11-14 | 2016-12-24 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2015-11-14 | 2016-12-24 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-08 | 2015-11-14 | 2016-12-24 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-ELEC | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2015-11-14 | 2016-12-24 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-08 | 2015-11-14 | 2016-12-24 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2015-11-14 | 2016-12-24 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100027949 | DFF-08 OIL XCV-301308 intern leak | Prepare Permits Scaff | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-01 | 2015-11-14 | 2016-12-24 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-XCV-301308 | Prepare Permits Scaff | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 2 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 3 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 4 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 10 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 30 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 40 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 50 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 60 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-28 | 2018-06-07 | 2018-06-12 | 70 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 24 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-28 | 2024-03-30 | 2018-06-07 | 2018-06-12 | 100 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 24 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-03-31 | 2024-04-01 | 2018-06-07 | 2018-06-12 | 110 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 18 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-02 | 2024-04-03 | 2018-06-07 | 2018-06-12 | 120 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 18 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-03 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 130 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-04 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 140 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-04 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 150 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-04 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 151 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-04 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 160 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-04 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 170 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-04 | 2024-04-04 | 2018-06-07 | 2018-06-12 | 180 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 6 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-05 | 2024-04-05 | 2018-06-07 | 2018-06-12 | 190 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 2 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-05 | 2024-04-05 | 2018-06-07 | 2018-06-12 | 200 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 6 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-05 | 2024-04-05 | 2018-06-07 | 2018-06-12 | 210 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 2 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-05 | 2024-04-05 | 2018-06-07 | 2018-06-12 | 220 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 10 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-05 | 2024-04-07 | 2018-06-07 | 2018-06-12 | 230 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2018-06-07 | 2018-06-12 | 240 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024398 | FFSP Low wall thk on cooling water to Ge | Low wall thk on cooling water to Generat |  |  | 0 | 0 | Moved to 2022 | 2024-03-28 | 2024-04-07 | 2024-04-07 | 2024-04-07 | 2018-06-07 | 2018-06-12 | 250 |  |  | DF /C /76/DFC-4-WS-053-0203-A3-F | Low wall thk on cooling water to Generat | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241701 | 1Y COMP FOR BREATHING MAINT-DFCI-C-5401 | New Comp. |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-03-01 | 2023-04-17 | 10 |  |  | DF /C /07/DFCI-C-5401 | New Comp. | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241701 | 1Y COMP FOR BREATHING MAINT-DFCI-C-5401 | New Comp. |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-03-01 | 2023-04-17 | 20 |  |  | DF /C /07/DFCI-C-5401 | New Comp. | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241701 | 1Y COMP FOR BREATHING MAINT-DFCI-C-5401 | New Comp. |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2023-03-01 | 2023-04-17 | 30 |  |  | DF /C /07/DFCI-C-5401 | New Comp. | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-12-27 | 2024-05-10 | 10 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-27 | 2024-05-10 | 20 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-12-27 | 2024-05-10 | 30 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-27 | 2024-05-10 | 40 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-27 | 2024-05-10 | 50 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-12-27 | 2024-05-10 | 60 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-12-27 | 2024-05-10 | 70 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-12-27 | 2024-05-10 | 80 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100101812 | Very corroded actuator LCV IP Flash Drum | Isolate pneumatic and controls |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-12-27 | 2024-05-10 | 90 |  |  | DF /G /30/DFGA-LCV-410402 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-07-30 | 2021-08-22 | 2021-11-20 | 10 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-30 | 2024-07-30 | 2021-08-22 | 2021-11-20 | 20 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-30 | 2024-07-30 | 2021-08-22 | 2021-11-20 | 30 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-30 | 2024-07-31 | 2021-08-22 | 2021-11-20 | 40 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-31 | 2024-07-31 | 2021-08-22 | 2021-11-20 | 50 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-31 | 2024-08-01 | 2021-08-22 | 2021-11-20 | 60 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-01 | 2024-08-01 | 2021-08-22 | 2021-11-20 | 70 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-01 | 2024-08-02 | 2021-08-22 | 2021-11-20 | 80 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-02 | 2021-08-22 | 2021-11-20 | 90 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-03 | 2021-08-22 | 2021-11-20 | 100 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-03 | 2024-08-03 | 2021-08-22 | 2021-11-20 | 110 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-03 | 2024-08-03 | 2021-08-22 | 2021-11-20 | 120 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-08-03 | 2024-08-04 | 2021-08-22 | 2021-11-20 | 130 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053136 | Internal leaking LCV-500106 | Remove Insulation | SCH | SCH | 0 | 0 | W29-W30 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-07-29 | 2021-08-22 | 2021-11-20 | 140 | SCH | SCH | DF /F /28/DFFA-LCV-500106 | Remove Insulation | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235827 | 4Y 380V E-SWB MAINT DFFA-N-1812-08 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFA-N-1812-08 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235827 | 4Y 380V E-SWB MAINT DFFA-N-1812-08 | ISOLATION BY PRODUCTION |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-17 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFA-N-1812-08 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235827 | 4Y 380V E-SWB MAINT DFFA-N-1812-08 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFA-N-1812-08 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235827 | 4Y 380V E-SWB MAINT DFFA-N-1812-08 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFA-N-1812-08 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400337279 | 6M CRANE HOIST EQUIP, DFF | CRANE HOIST EQUIP, DFF |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-10-13 | 2024-11-01 | 10 |  |  | DF /F /78/DFF-LIFTING-1 | CRANE HOIST EQUIP, DFF | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 10 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 20 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 2 | Empty | 2024-07-16 | 2024-09-16 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 22 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 1 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 25 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-09-14 | 2024-09-15 | 2024-10-12 | 2024-12-31 | 26 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-09-14 | 2024-09-15 | 2024-10-12 | 2024-12-31 | 27 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 5 | 6 | Empty | 2024-07-16 | 2024-09-16 | 2024-09-14 | 2024-09-16 | 2024-10-12 | 2024-12-31 | 30 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 4 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-09-14 | 2024-09-15 | 2024-10-12 | 2024-12-31 | 40 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2024-10-12 | 2024-12-31 | 50 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2024-10-12 | 2024-12-31 | 60 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284317 | PSV Exchange - DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-07-16 | 2024-09-16 | 2024-07-16 | 2024-07-16 | 2024-10-12 | 2024-12-31 | 70 | AWSCSCH | AWSCSCH | DF /G /75/DFGA-PSV-760005 | DFGA-PSV-760005 Offshore from WS Måde | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284127 | 6M PRIME MOVER DFGA-MD-6140 | PRIME MOVER MAINTENANCE DFGA-MD-6140 |  |  | 15 | 0 | W27-W28 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2024-01-04 | 2024-01-20 | 10 |  |  | DF /G /78/DFGA-MD-6140 | PRIME MOVER MAINTENANCE DFGA-MD-6140 | Unknown
C | NOSD | WPM | MTN-TURB | MTN-TURB | 2400342368 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2024-09-03 | 2024-09-08 | 1 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-TURB | MTN-TURB | 2400342368 | 1M Preventive Turbine Idle Mode | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 12 | 0 | Empty | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2024-09-03 | 2024-09-08 | 10 |  |  | DF /F /31/DFFA-CT-4301 | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 8 | 20 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 10 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-ROPE | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 36 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2021-05-02 | 2021-09-29 | 20 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-ROPE | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 16 | 16 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 30 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2021-05-02 | 2021-09-29 | 40 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-ROPE | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 16 | 12 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 50 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 16 | 15 | Empty | 2024-05-06 | 2024-05-06 | 2023-04-26 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 60 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 8 | 37 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 70 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 12 | 37 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 80 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | PRODTECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2021-05-02 | 2021-09-29 | 90 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 4 | 10 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 100 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-ROPE | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 8 | 8 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 110 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-SCAF | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 18 | 18 | Empty | 2024-05-06 | 2024-05-06 | 2023-05-07 | 2023-05-29 | 2021-05-02 | 2021-09-29 | 120 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2021-05-02 | 2021-09-29 | 130 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | DFFLPSEP | WDF | MTN-MECH | MTN-MECH | 2100045467 | DFF-HCV-360075 internal leak | Additional material order | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2021-05-02 | 2021-09-29 | 140 | PCNFAWSC | PCNFAWSC | DF /F /21/DFFA-HCV-360075 | Additional material order | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000752 | CAMPBOSS 01.01.19 TIL 31.12.19 | CAMPBOSS UGE 16 2020 |  |  | 0 | 0 | Empty | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /F | CAMPBOSS UGE 16 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000752 | CAMPBOSS 01.01.19 TIL 31.12.19 | CAMPBOSS UGE 16 2020 |  |  | 0 | 0 | Empty | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF /F | CAMPBOSS UGE 16 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000752 | CAMPBOSS 01.01.19 TIL 31.12.19 | CAMPBOSS UGE 16 2020 |  |  | 0 | 0 | Empty | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2020-04-17 | 2019-12-31 | 2019-12-31 | 30 |  |  | DF /F | CAMPBOSS UGE 16 2020 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009372 | Scaff Assits FORCE 20683 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /B /10/DFB-6-PHS-030-4010-FB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009372 | Scaff Assits FORCE 20683 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2024-01-13 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /B /10/DFB-6-PHS-030-4010-FB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009372 | Scaff Assits FORCE 20683 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-14 | 2024-01-14 | 2022-02-08 | 2022-07-08 | 25 |  |  | DF /B /10/DFB-6-PHS-030-4010-FB-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009372 | Scaff Assits FORCE 20683 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-14 | 2024-01-17 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /B /10/DFB-6-PHS-030-4010-FB-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 4 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-05 | 2024-10-05 | 2023-09-08 | 2024-01-21 | 10 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-06 | 2024-10-06 | 2023-09-08 | 2024-01-21 | 20 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 16 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-06 | 2024-10-08 | 2023-09-08 | 2024-01-21 | 30 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 4 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-06 | 2024-10-06 | 2023-09-08 | 2024-01-21 | 40 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-08 | 2024-10-08 | 2023-09-08 | 2024-01-21 | 50 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-08 | 2024-10-09 | 2023-09-08 | 2024-01-21 | 60 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095137 | oscillating part defect on monitor | Isolation of monitor | SECE | SECE | 2 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2023-09-08 | 2024-01-21 | 70 | SECE | SECE | DF /F /01/DFFA-A-0408 | Isolation of monitor | Unknown
4 | Empty | WRO | MTN-TELE | WELLSUPV | 2300001882 | 2022-10-26 L0512223: | Method Statement | AWSCSCH | AWSCSCH | 36 | 0 | Empty | 2023-01-16 | 2023-01-22 | 2023-01-16 | 2023-01-19 | 2020-11-12 | 2021-04-11 | 10 | AWSCSCH | AWSCSCH | DF /F /03/DFFA-FP-0153 | Method Statement | Unknown
4 | Empty | WRO | MTN-TELE | MTN-TELE | 2300001882 | 2022-10-26 L0512223: | Method Statement | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2023-01-16 | 2023-01-22 | 2023-01-19 | 2023-01-19 | 2020-11-12 | 2021-04-11 | 20 | AWSCSCH | AWSCSCH | DF /F /03/DFFA-FP-0153 | Method Statement | Unknown
4 | Empty | WRO | MTN-TELE | MTN-TELE | 2300001882 | 2022-10-26 L0512223: | Method Statement | AWSCSCH | AWSCSCH | 12 | 0 | Empty | 2023-01-16 | 2023-01-22 | 2023-01-19 | 2023-01-22 | 2020-11-12 | 2021-04-11 | 30 | AWSCSCH | AWSCSCH | DF /F /03/DFFA-FP-0153 | Method Statement | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337669 | 6M WATER TR PUMP MAINT DFCM-P-3509/10 | WATER TR PUMP MAINT DFCM-P-3509/10 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-04 | 2024-08-20 | 10 |  |  | DF /C /54/DFCM-P-3509 | WATER TR PUMP MAINT DFCM-P-3509/10 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079085 | DFG Hi-fog emerg Gen Main C-bank | Inform CCR about troubleshooiting | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2022-12-06 | 2023-01-20 | 10 | SCH | SCH | DF /G /01/DFGA-A-0461 | Inform CCR about troubleshooiting | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079085 | DFG Hi-fog emerg Gen Main C-bank | Inform CCR about troubleshooiting | SCH | SCH | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2022-12-06 | 2023-01-20 | 20 | SCH | SCH | DF /G /01/DFGA-A-0461 | Inform CCR about troubleshooiting | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284266 | PSV Exchange - DFFA-PSV-360040 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /21/DFFA-PSV-360040 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284266 | PSV Exchange - DFFA-PSV-360040 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /21/DFFA-PSV-360040 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284266 | PSV Exchange - DFFA-PSV-360040 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /21/DFFA-PSV-360040 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284266 | PSV Exchange - DFFA-PSV-360040 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /21/DFFA-PSV-360040 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284266 | PSV Exchange - DFFA-PSV-360040 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /21/DFFA-PSV-360040 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284266 | PSV Exchange - DFFA-PSV-360040 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /21/DFFA-PSV-360040 | Isolation of PSV | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087255 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 10 |  |  | DF /F /05/DFFB-DP-1832B-01-Q04 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087255 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-13 | 2023-04-27 | 20 |  |  | DF /F /05/DFFB-DP-1832B-01-Q04 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087255 | Battery fault on emergency light | Isolate and prove dead. |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 30 |  |  | DF /F /05/DFFB-DP-1832B-01-Q04 | Isolate and prove dead. | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087255 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-13 | 2023-04-27 | 40 |  |  | DF /F /05/DFFB-DP-1832B-01-Q04 | Isolate and prove dead. | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400219084 | 6M FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | FW JOCKEY PUMP MAINT -DFCM-P-0308/09 |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-11-29 | 2022-12-18 | 10 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 2 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 3 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 4 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 5 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 19 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-09 | 2021-06-04 | 2020-09-11 | 2020-12-10 | 10 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 20 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 60 | 70 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-12 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 40 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 100 | 208 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-11 | 2021-06-13 | 2020-09-11 | 2020-12-10 | 50 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 10.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-05 | 2020-09-11 | 2020-12-10 | 60 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 12 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 70 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 8 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 80 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 100 | 216 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-11 | 2021-06-13 | 2020-09-11 | 2020-12-10 | 90 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 60 | 79.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-13 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 100 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 100 | 114 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 110 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 5 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 120 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 130 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 15.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 140 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 4 | 39 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 150 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 24.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 155 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 78.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-14 | 2021-06-05 | 2020-09-11 | 2020-12-10 | 160 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 6 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 170 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 20 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-15 | 2021-06-05 | 2020-09-11 | 2020-12-10 | 180 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 2 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 190 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 40 | 36 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-16 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 200 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 6 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 210 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 4 | 4 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 220 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 16 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 230 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 38.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 240 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 18 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 250 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 26 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 260 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 14 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 270 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 3 | 25.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 280 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 24 | 94.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 290 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | INP-SITE | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 4 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 300 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 8 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 303 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 24 | 28 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 305 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 25.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-06 | 2020-09-11 | 2020-12-10 | 310 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 4 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 320 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 330 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 20 | 16.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 340 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 100 | 103.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-11 | 2020-09-11 | 2020-12-10 | 350 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 30 | 34 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-04 | 2020-09-11 | 2020-12-10 | 380 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 9 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-02 | 2020-09-11 | 2020-12-10 | 390 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 50 | 37 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 400 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 20 | 18.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-13 | 2020-09-11 | 2020-12-10 | 410 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 40 | 41.5 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-05 | 2020-09-11 | 2020-12-10 | 420 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 3 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 430 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 3 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 440 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 6 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 450 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 3 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 460 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 3 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-06-11 | 2020-09-11 | 2020-12-10 | 470 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | WELLSUPV | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-03-17 | 2021-05-26 | 2020-09-11 | 2020-12-10 | 480 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 490 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 500 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 510 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 520 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 530 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 60 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 540 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 100 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-08-01 | 2020-09-11 | 2020-12-10 | 550 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 5 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 560 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 570 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 6 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2021-05-26 | 2021-06-12 | 2020-09-11 | 2020-12-10 | 580 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 336 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-06 | 2024-08-19 | 2020-09-11 | 2020-12-10 | 590 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 20 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-08-01 | 2020-09-11 | 2020-12-10 | 595 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 96 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-06 | 2024-08-09 | 2020-09-11 | 2020-12-10 | 600 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 120 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-09 | 2024-08-14 | 2020-09-11 | 2020-12-10 | 610 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 40 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-31 | 2020-09-11 | 2020-12-10 | 615 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 24 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-08-01 | 2020-09-11 | 2020-12-10 | 620 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-15 | 2024-08-15 | 2020-09-11 | 2020-12-10 | 630 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-16 | 2024-08-17 | 2020-09-11 | 2020-12-10 | 640 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 32 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-16 | 2024-08-16 | 2020-09-11 | 2020-12-10 | 650 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 80 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-16 | 2024-08-18 | 2020-09-11 | 2020-12-10 | 660 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 144 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-16 | 2024-08-21 | 2020-09-11 | 2020-12-10 | 670 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 120 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-21 | 2024-08-24 | 2020-09-11 | 2020-12-10 | 680 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 144 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-08-04 | 2020-09-11 | 2020-12-10 | 690 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 56 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-21 | 2024-08-23 | 2020-09-11 | 2020-12-10 | 700 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | INP-SITE | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-23 | 2024-08-23 | 2020-09-11 | 2020-12-10 | 710 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-23 | 2024-08-23 | 2020-09-11 | 2020-12-10 | 720 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-23 | 2024-08-23 | 2020-09-11 | 2020-12-10 | 730 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-23 | 2024-08-23 | 2020-09-11 | 2020-12-10 | 740 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 110 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-23 | 2024-08-28 | 2020-09-11 | 2020-12-10 | 750 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 72 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-08-28 | 2024-09-03 | 2020-09-11 | 2020-12-10 | 760 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 12 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-08-01 | 2020-09-11 | 2020-12-10 | 770 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 168 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-09-03 | 2024-09-09 | 2020-09-11 | 2020-12-10 | 780 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-09-09 | 2024-09-09 | 2020-09-11 | 2020-12-10 | 790 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-09-09 | 2024-09-10 | 2020-09-11 | 2020-12-10 | 800 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PAIN | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-09-09 | 2024-09-09 | 2020-09-11 | 2020-12-10 | 810 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-ELEC | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-09-09 | 2024-09-11 | 2020-09-11 | 2020-12-10 | 820 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-LAGG | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 830 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 840 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 850 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-PIPF | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 860 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 870 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
3 | DFF-3520 | WDF | MTN-MECH | VEN-MECH | 2100038054 | DGSPR: Replace 16" Spool Section on WI | Lose and move cable tray | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-09-11 | 2024-07-30 | 2024-07-30 | 2020-09-11 | 2020-12-10 | 880 | PCNF | PCNF | DF /F /54/DFF-16-WI-035-7003-AB-U | Lose and move cable tray | Unknown
A | NOSD | WPM | INP-SITE | QAQCMECH | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 0 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-08 | 2022-09-13 | 2022-12-21 | 1 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-PIPF | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 24 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-10 | 2022-09-13 | 2022-12-21 | 3 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-SCAF | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 105 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-02-03 | 2022-09-13 | 2022-12-21 | 10 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-LAGG | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 12 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-09 | 2022-09-13 | 2022-12-21 | 20 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-ELEC | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 15 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-11 | 2022-09-13 | 2022-12-21 | 30 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-PAIN | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 39 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-12 | 2022-09-13 | 2022-12-21 | 40 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-PIPF | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 96 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-18 | 2022-09-13 | 2022-12-21 | 50 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-SCAF | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 72 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-25 | 2022-09-13 | 2022-12-21 | 60 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-ELEC | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 12 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-10 | 2022-09-13 | 2022-12-21 | 80 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-PAIN | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 30 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-08 | 2024-01-11 | 2022-09-13 | 2022-12-21 | 90 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | QAQCMECH | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 18 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-26 | 2024-01-28 | 2022-09-13 | 2022-12-21 | 100 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-PIPF | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 6 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-28 | 2024-01-28 | 2022-09-13 | 2022-12-21 | 110 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-SCAF | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 48 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-28 | 2024-02-09 | 2022-09-13 | 2022-12-21 | 120 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-LAGG | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 48 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-01-28 | 2024-02-02 | 2022-09-13 | 2022-12-21 | 130 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-ELEC | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 18 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-02-09 | 2024-02-13 | 2022-09-13 | 2022-12-21 | 140 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
A | NOSD | WPM | INP-SITE | MTN-PAIN | 2400116297 | 6Y PVI Internal Inspection DFGA-V-3441. | PREPARE WORK FOR PVI | SECE | SECE | 36 | 0 | Empty | 2024-01-08 | 2024-02-13 | 2024-02-09 | 2024-02-13 | 2022-09-13 | 2022-12-21 | 150 | SECE | SECE | DF /G /27/DFGA-V-3441 | PREPARE WORK FOR PVI | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012301 | Punch on Chemical inj. FVC DFF | ADD Service | PCNF | PCNF | 30 | 15 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-03 | 2022-12-18 | 10 | PCNF | PCNF | DF /F /75/DFFA-FCV-390053 | ADD Service | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012301 | Punch on Chemical inj. FVC DFF | ADD Service | PCNF | PCNF | 30 | 15 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-03 | 2022-12-18 | 20 | PCNF | PCNF | DF /F /75/DFFA-FCV-390053 | ADD Service | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012301 | Punch on Chemical inj. FVC DFF | ADD Service | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-03 | 2022-12-18 | 30 | PCNF | PCNF | DF /F /75/DFFA-FCV-390053 | ADD Service | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012301 | Punch on Chemical inj. FVC DFF | ADD Service | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-03 | 2022-12-18 | 40 | PCNF | PCNF | DF /F /75/DFFA-FCV-390053 | ADD Service | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012301 | Punch on Chemical inj. FVC DFF | ADD Service | PCNF | PCNF | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2022-11-03 | 2022-12-18 | 50 | PCNF | PCNF | DF /F /75/DFFA-FCV-390053 | ADD Service | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235750 | 1Y 400/230V UPS.SYS BATT&CHAR F.TEST-DFC | 400/230V UPS.SYS BATT&CHAR F.TEST-DFC | SECE | SECE | 15 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-19 | 2023-06-06 | 2023-07-06 | 10 | SECE | SECE | DF /C /06/UPS-SYSTEM-1 | 400/230V UPS.SYS BATT&CHAR F.TEST-DFC | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 10 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-ELEC | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 6 | 11 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 20 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 48 | 32 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 30 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 24 | 91 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 40 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 50 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-ROPE | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 18 | 21 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 60 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 70 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 80 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-ELEC | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 90 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2024-02-17 | 2024-04-02 | 93 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-MECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 25 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-17 | 2024-02-17 | 2024-04-02 | 95 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-RIGG | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 32 | 32 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-17 | 2024-02-17 | 2024-04-02 | 100 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-TURB | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 20 | 10 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-19 | 2024-02-17 | 2024-04-02 | 110 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-TURB | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 5 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-02-17 | 2024-04-02 | 120 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | MTN-TURB | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-02-17 | 2024-04-02 | 130 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
1 | DFF-IPHP | WDF | MTN-MECH | PRODTECH | 2100107512 | Leak and Noise from Comp. Lube Oil Pump | ***Service of lube oil pump onshore*** | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2024-02-17 | 2024-04-02 | 140 | PCNFSCH | PCNFSCH | DF /F /31/DFFA-P-4302A | ***Service of lube oil pump onshore*** | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100074855 | DFFØ/78: Drain main fuel tank | Drain main fuel located at slewbearing |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2022-10-31 | 2023-03-15 | 10 |  |  | DF /F /78/DFFA-A-6101 | Drain main fuel located at slewbearing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074855 | DFFØ/78: Drain main fuel tank | Drain main fuel located at slewbearing |  |  | 15 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-08-03 | 2022-10-31 | 2023-03-15 | 20 |  |  | DF /F /78/DFFA-A-6101 | Drain main fuel located at slewbearing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100074855 | DFFØ/78: Drain main fuel tank | Drain main fuel located at slewbearing |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2022-10-31 | 2023-03-15 | 30 |  |  | DF /F /78/DFFA-A-6101 | Drain main fuel located at slewbearing | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300003463 | Minor SCADA Change / CCR INPUT | Minor SCADA Change / CCR INPUT |  |  | 1 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-12-06 | 2022-03-06 | 10 |  |  | DF /G /04/DFGA-FP-2040 | Minor SCADA Change / CCR INPUT | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300004392 | Replaced by 2300005055 | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2023-06-27 | 2025-12-13 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038674 | DFA-17 test XCV in fault to close | Trouble shooting on XCV ZSO/ZSC |  |  | 1 | 0 | W31-W32 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2020-10-11 | 2020-11-20 | 10 |  |  | DF /A /10/DFAA-XCV-30325 | Trouble shooting on XCV ZSO/ZSC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038674 | DFA-17 test XCV in fault to close | Trouble shooting on XCV ZSO/ZSC |  |  | 1 | 0 | W31-W32 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2020-10-11 | 2020-11-20 | 20 |  |  | DF /A /10/DFAA-XCV-30325 | Trouble shooting on XCV ZSO/ZSC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038674 | DFA-17 test XCV in fault to close | Trouble shooting on XCV ZSO/ZSC |  |  | 1 | 0 | W31-W32 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2020-10-11 | 2020-11-20 | 30 |  |  | DF /A /10/DFAA-XCV-30325 | Trouble shooting on XCV ZSO/ZSC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038674 | DFA-17 test XCV in fault to close | Trouble shooting on XCV ZSO/ZSC |  |  | 1 | 0 | W31-W32 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2020-10-11 | 2020-11-20 | 40 |  |  | DF /A /10/DFAA-XCV-30325 | Trouble shooting on XCV ZSO/ZSC | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193021 | 1Y CHEMICAL INJ. PUMP SKID, DFAA-A-3931 | 1Y CHEMICAL INJ. PUMP SKID, DFAA-A-3931 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /75/DFAA-A-3931 | 1Y CHEMICAL INJ. PUMP SKID, DFAA-A-3931 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400193021 | 1Y CHEMICAL INJ. PUMP SKID, DFAA-A-3931 | 1Y CHEMICAL INJ. PUMP SKID, DFAA-A-3931 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-18 | 2022-04-26 | 2022-06-01 | 20 |  |  | DF /A /75/DFAA-A-3931 | 1Y CHEMICAL INJ. PUMP SKID, DFAA-A-3931 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100063449 | DFFA-HCV-380228. Gearbox poor condition | Remove Gearbox in poor condition | PCNF | PCNF | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-03-03 | 2022-04-12 | 10 | PCNF | PCNF | DF /F /23/DFFA-HCV-380228 | Remove Gearbox in poor condition | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100063449 | DFFA-HCV-380228. Gearbox poor condition | Remove Gearbox in poor condition | PCNF | PCNF | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-03-03 | 2022-04-12 | 20 | PCNF | PCNF | DF /F /23/DFFA-HCV-380228 | Remove Gearbox in poor condition | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100063449 | DFFA-HCV-380228. Gearbox poor condition | Remove Gearbox in poor condition | PCNF | PCNF | 3 | 10 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-03-03 | 2022-04-12 | 30 | PCNF | PCNF | DF /F /23/DFFA-HCV-380228 | Remove Gearbox in poor condition | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 2 | 6 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-02-01 | 2024-06-04 | 2023-09-12 | 2024-01-25 | 10 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 5 | 18 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-02-01 | 2024-06-04 | 2023-09-12 | 2024-01-25 | 20 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 30 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 5 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 40 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 2 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 50 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 60 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 10 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-02-19 | 2024-06-04 | 2023-09-12 | 2024-01-25 | 70 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 80 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 0 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 90 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100096115 | Missing Cooling Capacity | EXCHANGER,HEAT COMP AIR/H2O | PCNFSCH | PCNFSCH | 12 | 15 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2023-09-12 | 2024-01-25 | 100 | PCNFSCH | PCNFSCH | DF /C /07/DFCM-C-5409 | EXCHANGER,HEAT COMP AIR/H2O | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284241 | PSV Exchange - DFCI-PSV-38115 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /20/DFCI-PSV-38115 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284241 | PSV Exchange - DFCI-PSV-38115 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /20/DFCI-PSV-38115 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284241 | PSV Exchange - DFCI-PSV-38115 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /20/DFCI-PSV-38115 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284241 | PSV Exchange - DFCI-PSV-38115 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /20/DFCI-PSV-38115 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284241 | PSV Exchange - DFCI-PSV-38115 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /20/DFCI-PSV-38115 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284241 | PSV Exchange - DFCI-PSV-38115 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /20/DFCI-PSV-38115 | Isolation of PSV | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015384 | Replace FFLB2 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /G /02/DFGA-X-0702 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015384 | Replace FFLB2 coolant with GlysantinG30 | Isolate lifeboat |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /G /02/DFGA-X-0702 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015384 | Replace FFLB2 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /G /02/DFGA-X-0702 | Isolate lifeboat | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-07 | 2024-06-07 | 2020-05-10 | 2020-06-19 | 10 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-INST | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 3 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-07 | 2024-06-08 | 2020-05-10 | 2020-06-19 | 20 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 3 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-08 | 2024-06-09 | 2020-05-10 | 2020-06-19 | 30 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 3 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-09 | 2024-06-10 | 2020-05-10 | 2020-06-19 | 40 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 3 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-10 | 2024-06-10 | 2020-05-10 | 2020-06-19 | 50 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 3 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-10 | 2024-06-11 | 2020-05-10 | 2020-06-19 | 60 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-INST | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 3 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-11 | 2024-06-12 | 2020-05-10 | 2020-06-19 | 70 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-12 | 2024-06-12 | 2020-05-10 | 2020-06-19 | 80 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-INST | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-12 | 2024-06-13 | 2020-05-10 | 2020-06-19 | 90 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100031494 | DFG-LCV-340022 meget tæret | Isolate pneumatic and controls | SCH | SCH | 2 | 0 | W23-W24 | 2024-06-07 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2020-05-10 | 2020-06-19 | 100 | SCH | SCH | DF /G /20/DFGA-LCV-340022 | Isolate pneumatic and controls | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085205 | Valve handle missing. | Remove what is left of old gearbox |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-21 | 2023-08-03 | 10 |  |  | DF /C /01/DFC-6-WF-003-9038-AN-U | Remove what is left of old gearbox | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085205 | Valve handle missing. | Remove what is left of old gearbox |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-21 | 2023-08-03 | 20 |  |  | DF /C /01/DFC-6-WF-003-9038-AN-U | Remove what is left of old gearbox | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235705 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR04-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235705 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 18 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR04-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235705 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR04-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235705 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR04-DA001 | ISOLATION ELECTRICAL | Unknown
D | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344069 | 6M FRESH AIR FILTERS DAN F | FRESH AIR STATIONS DAN F |  |  | 5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-09-20 | 10 |  |  | DF /C /07 | FRESH AIR STATIONS DAN F | Unknown
D | NOSD | WPM | MTN-MECH | MTN-INST | 2400344069 | 6M FRESH AIR FILTERS DAN F | FRESH AIR STATIONS DAN F |  |  | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-08-26 | 2024-09-20 | 12 |  |  | DF /C /07 | FRESH AIR STATIONS DAN F | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300004544 | Replaced by 2300005541 | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2026-01-08 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300004544 | Replaced by 2300005541 | DK40 - CONSUMABLE PROD - DECK |  |  | 1 | 0 | Empty | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2023-07-23 | 2026-01-08 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200017015 | Accecc Point to cover Medic office DAF | Accecc Point to cover Medic office DAF |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-04 | 2024-02-18 | 10 |  |  | DF /C /08 | Accecc Point to cover Medic office DAF | Unknown