3 | NOSD | WGN | MTN-PAIN | MTN-ELEC | 2200011738 | Painting Jobs - DFC Cabins | PO Altrad | PCNF | PCNF | 0 | 0 | Empty | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2024-03-25 | 2022-10-15 | 2023-02-27 | 10 | PCNF | PCNF | DF /C /82 | PO Altrad | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200011738 | Painting Jobs - DFC Cabins | PO Altrad | PCNF | PCNF | 10 | 10 | Empty | 2024-03-25 | 2024-03-28 | 2024-03-25 | 2024-03-26 | 2022-10-15 | 2023-02-27 | 20 | PCNF | PCNF | DF /C /82 | PO Altrad | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200011738 | Painting Jobs - DFC Cabins | PO Altrad | PCNF | PCNF | 20 | 20 | Empty | 2024-03-25 | 2024-03-28 | 2024-03-26 | 2024-03-28 | 2022-10-15 | 2023-02-27 | 30 | PCNF | PCNF | DF /C /82 | PO Altrad | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200011738 | Painting Jobs - DFC Cabins | PO Altrad | PCNF | PCNF | 5 | 5 | Empty | 2024-03-25 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2022-10-15 | 2023-02-27 | 40 | PCNF | PCNF | DF /C /82 | PO Altrad | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200011738 | Painting Jobs - DFC Cabins | PO Altrad | PCNF | PCNF | 0 | 0 | Empty | 2024-03-25 | 2024-03-28 | 2024-03-28 | 2024-03-28 | 2022-10-15 | 2023-02-27 | 50 | PCNF | PCNF | DF /C /82 | PO Altrad | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100077102 | DFGA-PSV-570428B Misaligned flanges | Prod Assist (breaking containment) |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-22 | 2022-11-10 | 2023-03-25 | 10 |  |  | DF /G /70/DFGA-PSV-570428B | Prod Assist (breaking containment) | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100077102 | DFGA-PSV-570428B Misaligned flanges | Prod Assist (breaking containment) |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-23 | 2022-11-10 | 2023-03-25 | 20 |  |  | DF /G /70/DFGA-PSV-570428B | Prod Assist (breaking containment) | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | MTN-MECH | 2100077102 | DFGA-PSV-570428B Misaligned flanges | Prod Assist (breaking containment) |  |  | 5 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-24 | 2022-11-10 | 2023-03-25 | 30 |  |  | DF /G /70/DFGA-PSV-570428B | Prod Assist (breaking containment) | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100077102 | DFGA-PSV-570428B Misaligned flanges | Prod Assist (breaking containment) |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-24 | 2022-11-10 | 2023-03-25 | 50 |  |  | DF /G /70/DFGA-PSV-570428B | Prod Assist (breaking containment) | Unknown
3 | DFG-FUEL | WDF | MTN-MECH | PRODTECH | 2100077102 | DFGA-PSV-570428B Misaligned flanges | Prod Assist (breaking containment) |  |  | 4 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-24 | 2024-08-25 | 2022-11-10 | 2023-03-25 | 70 |  |  | DF /G /70/DFGA-PSV-570428B | Prod Assist (breaking containment) | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 22 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-18 | 2023-05-07 | 2025-10-23 | 10 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 8 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-17 | 2023-05-07 | 2025-10-23 | 20 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 20 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-15 | 2024-07-17 | 2023-05-07 | 2025-10-23 | 30 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 2 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-18 | 2024-07-18 | 2023-05-07 | 2025-10-23 | 40 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 28 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-18 | 2024-07-22 | 2023-05-07 | 2025-10-23 | 50 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 10 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-22 | 2024-07-23 | 2023-05-07 | 2025-10-23 | 60 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 75 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-22 | 2024-07-28 | 2023-05-07 | 2025-10-23 | 70 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 4 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-28 | 2024-07-29 | 2023-05-07 | 2025-10-23 | 80 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100077932 | DFG/78 Main winch onshore for overhaul | Assist with spool of wire |  |  | 2 | 0 | W27-W28 | 2024-07-15 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-07 | 2025-10-23 | 90 |  |  | DF /G /78/DFGA-A-6140 | Assist with spool of wire | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235821 | 4Y 380V E-SWB MAINT DFFA-N-1812-02 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 10 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235821 | 4Y 380V E-SWB MAINT DFFA-N-1812-02 | ISOLATION BY PRODUCTION | SCH | SCH | 8 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 20 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235821 | 4Y 380V E-SWB MAINT DFFA-N-1812-02 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235821 | 4Y 380V E-SWB MAINT DFFA-N-1812-02 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 40 | SCH | SCH | DF /F /05/DFFA-N-1812-03 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-LP-1 | WGN | MTN-MECH | PRODTECH | 2200003244 | SMAT:DFF Montere ny manometer | L3 Replace Pressure Gauge |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2018-04-05 | 2018-07-04 | 10 |  |  | DF /F /32/DFFA-ESDV-420001 | L3 Replace Pressure Gauge | Unknown
3 | DFF-LP-1 | WGN | MTN-MECH | MTN-MECH | 2200003244 | SMAT:DFF Montere ny manometer | L3 Replace Pressure Gauge |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-28 | 2018-04-05 | 2018-07-04 | 20 |  |  | DF /F /32/DFFA-ESDV-420001 | L3 Replace Pressure Gauge | Unknown
3 | DFF-LP-1 | WGN | MTN-MECH | PRODTECH | 2200003244 | SMAT:DFF Montere ny manometer | L3 Replace Pressure Gauge |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-28 | 2024-08-29 | 2018-04-05 | 2018-07-04 | 30 |  |  | DF /F /32/DFFA-ESDV-420001 | L3 Replace Pressure Gauge | Unknown
3 | DFF-LP-1 | WGN | MTN-MECH | MTN-MECH | 2200003244 | SMAT:DFF Montere ny manometer | L3 Replace Pressure Gauge |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2018-04-05 | 2018-07-04 | 40 |  |  | DF /F /32/DFFA-ESDV-420001 | L3 Replace Pressure Gauge | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100050105 | DFB-WH hydr. cabinet minor leaks inside | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 24 | 0 | W27-28 IOP 6-13/7 | 2024-06-03 | 2024-06-08 | 2024-06-03 | 2024-06-08 | 2021-06-10 | 2021-09-08 | 10 | AWSC | AWSC | DF /B /07/DFBA-A-3101 | Vendor troubleshoot Hydraulic cabinets | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200016094 | Cooling water replacement DFFA-A-1701 | Re-sending materials offshore | SCH | SCH | 2 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2023-11-25 | 2024-04-08 | 10 | SCH | SCH | DF /F /05/DFFA-A-1701 | Re-sending materials offshore | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200016094 | Cooling water replacement DFFA-A-1701 | Re-sending materials offshore | SCH | SCH | 6 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-03 | 2023-11-25 | 2024-04-08 | 20 | SCH | SCH | DF /F /05/DFFA-A-1701 | Re-sending materials offshore | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200016094 | Cooling water replacement DFFA-A-1701 | Re-sending materials offshore | SCH | SCH | 2 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2023-11-25 | 2024-04-08 | 30 | SCH | SCH | DF /F /05/DFFA-A-1701 | Re-sending materials offshore | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200016094 | Cooling water replacement DFFA-A-1701 | Re-sending materials offshore | SCH | SCH | 0 | 0 | Empty | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2023-11-25 | 2024-04-08 | 40 | SCH | SCH | DF /F /05/DFFA-A-1701 | Re-sending materials offshore | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057121 | utæt pulsationsdæmper | Isolate DFFA-PD-3924 |  |  | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-06 | 2024-07-29 | 2024-07-31 | 2021-11-11 | 2022-02-09 | 20 |  |  | DF /F /75/DFFA-P-3924 | Isolate DFFA-PD-3924 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057121 | utæt pulsationsdæmper | Isolate DFFA-PD-3924 |  |  | 20 | 0 | W29-W30 | 2024-07-29 | 2024-08-06 | 2024-07-31 | 2024-08-05 | 2021-11-11 | 2022-02-09 | 30 |  |  | DF /F /75/DFFA-P-3924 | Isolate DFFA-PD-3924 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057121 | utæt pulsationsdæmper | Isolate DFFA-PD-3924 |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-06 | 2024-08-05 | 2024-08-06 | 2021-11-11 | 2022-02-09 | 40 |  |  | DF /F /75/DFFA-P-3924 | Isolate DFFA-PD-3924 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235610 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-18 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-18 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235610 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-18 | ISOLATION ELECTRICAL |  |  | 29 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-22 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-18 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235610 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-18 | ISOLATION ELECTRICAL |  |  | 9 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-22 | 2024-09-25 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-18 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235610 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-18 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-18 | ISOLATION ELECTRICAL | Unknown
4 | DAN FG | WDF | MTN-ROPE | WELLSUPV | 2100056491 | FFSP Permanent rep DFF-24"-OCS-347014-AB | Permanent repair DFF-24"-OCS-347014-AB |  |  | 0 | 0 | Empty | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-09-24 | 10 |  |  | DF /F /20/DFF-24-OCS-034-7014-AB-U | Permanent repair DFF-24"-OCS-347014-AB | Unknown
4 | DAN FG | WDF | MTN-ROPE | MTN-ROPE | 2100056491 | FFSP Permanent rep DFF-24"-OCS-347014-AB | Permanent repair DFF-24"-OCS-347014-AB |  |  | 0 | 0 | Empty | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-01-27 | 2022-09-24 | 20 |  |  | DF /F /20/DFF-24-OCS-034-7014-AB-U | Permanent repair DFF-24"-OCS-347014-AB | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235644 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L06A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235644 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L06 | ISOLATION ELECTRICAL | AWSC | AWSC | 21 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L06A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235644 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L06 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-29 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L06A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235644 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L06A1 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400344058 | 1Y ESD CONTROL PANELS CHECK - DFA/B/E | ESD CONTROL PANELS CHECK - DFA/B/E | SECE | SECE | 3 | 4 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-25 | 2024-09-24 | 10 | SECE | SECE | DF /A /03/ESD-CONTROL-PANELS | ESD CONTROL PANELS CHECK - DFA/B/E | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284297 | PSV Exchange - DFGA-PSV-590426 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /07/DFGA-PSV-590426 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284297 | PSV Exchange - DFGA-PSV-590426 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /07/DFGA-PSV-590426 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284297 | PSV Exchange - DFGA-PSV-590426 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-13 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /07/DFGA-PSV-590426 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284297 | PSV Exchange - DFGA-PSV-590426 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /07/DFGA-PSV-590426 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284297 | PSV Exchange - DFGA-PSV-590426 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /07/DFGA-PSV-590426 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284297 | PSV Exchange - DFGA-PSV-590426 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /07/DFGA-PSV-590426 | Isolation of PSV | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235639 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L01-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235639 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L01 | ISOLATION ELECTRICAL | AWSC | AWSC | 18 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L01-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235639 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L01 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L01-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235639 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L01-01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100101564 | blocked deluge nozzles | clean blocked deluge nozzles |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-12-22 | 2024-05-05 | 10 |  |  | DF /A /01/DFAA-XCV-0313 | clean blocked deluge nozzles | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100099833 | salt extraction/corrosion, release panel | Investigate/repair leaking joints |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-11-26 | 2024-04-09 | 10 |  |  | DF /E /01/DFEZ-X-0301 | Investigate/repair leaking joints | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099833 | salt extraction/corrosion, release panel | Investigate/repair leaking joints |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-11-26 | 2024-04-09 | 20 |  |  | DF /E /01/DFEZ-X-0301 | Investigate/repair leaking joints | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100099833 | salt extraction/corrosion, release panel | Investigate/repair leaking joints |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-11-26 | 2024-04-09 | 30 |  |  | DF /E /01/DFEZ-X-0301 | Investigate/repair leaking joints | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200013986 | Switch for DAF office container | Switch for DAF office container |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-29 | 2023-05-13 | 10 |  |  | DF /C /08 | Switch for DAF office container | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2019-06-10 | 2019-07-20 | 10 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2019-06-10 | 2019-07-20 | 20 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 50 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-18 | 2019-06-10 | 2019-07-20 | 30 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-18 | 2024-09-18 | 2019-06-10 | 2019-07-20 | 40 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-18 | 2024-09-19 | 2019-06-10 | 2019-07-20 | 50 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-19 | 2024-09-20 | 2019-06-10 | 2019-07-20 | 60 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 30 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-20 | 2024-09-22 | 2019-06-10 | 2019-07-20 | 70 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 30 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2019-06-10 | 2019-07-20 | 80 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2019-06-10 | 2019-07-20 | 90 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2019-06-10 | 2019-07-20 | 100 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2019-06-10 | 2019-07-20 | 110 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2019-06-10 | 2019-07-20 | 120 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023241 | DFA/78: Replace Aircon unit due to corro | PO Conbit |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2019-06-10 | 2019-07-20 | 130 |  |  | DF /A /78/DFAA-X-6102 | PO Conbit | Unknown
A | DFF-GEN | WPM | MTN-MECH | PRODTECH | 2400306666 | 6M EMER. GENERATOR INSPECT DFFA-A-1701 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-23 | 2024-06-17 | 2024-06-17 | 2024-02-04 | 2024-02-20 | 10 | SCHSECE | SCHSECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
A | DFF-GEN | WPM | MTN-MECH | MTN-MECH | 2400306666 | 6M EMER. GENERATOR INSPECT DFFA-A-1701 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 24 | 0 | W25-W26 | 2024-06-17 | 2024-06-23 | 2024-06-17 | 2024-06-23 | 2024-02-04 | 2024-02-20 | 20 | SCHSECE | SCHSECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
A | DFF-GEN | WPM | MTN-MECH | PRODTECH | 2400306666 | 6M EMER. GENERATOR INSPECT DFFA-A-1701 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-23 | 2024-06-23 | 2024-06-23 | 2024-02-04 | 2024-02-20 | 30 | SCHSECE | SCHSECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | UNKNOWN | MTN-CRAN | 2100023281 | REPL connectn piece at batt switch | Isolate ExD box |  |  | 1 | 0 | 2023 - PARKED | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-02 | 2019-10-31 | 2019-11-20 | 10 |  |  | DF /E /78/DFEZ-X-6150 | Isolate ExD box | Unknown
3 | NOSD | WDF | UNKNOWN | MTN-CRAN | 2100023281 | REPL connectn piece at batt switch | Isolate ExD box |  |  | 2 | 0 | 2023 - PARKED | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-03 | 2019-10-31 | 2019-11-20 | 20 |  |  | DF /E /78/DFEZ-X-6150 | Isolate ExD box | Unknown
3 | NOSD | WDF | UNKNOWN | MTN-CRAN | 2100023281 | REPL connectn piece at batt switch | Isolate ExD box |  |  | 2 | 0 | 2023 - PARKED | 2023-01-02 | 2023-01-03 | 2023-01-03 | 2023-01-03 | 2019-10-31 | 2019-11-20 | 30 |  |  | DF /E /78/DFEZ-X-6150 | Isolate ExD box | Unknown
3 | NOSD | WDF | UNKNOWN | MTN-CRAN | 2100023281 | REPL connectn piece at batt switch | Isolate ExD box |  |  | 0 | 0 | 2023 - PARKED | 2023-01-02 | 2023-01-03 | 2023-01-02 | 2023-01-02 | 2019-10-31 | 2019-11-20 | 40 |  |  | DF /E /78/DFEZ-X-6150 | Isolate ExD box | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 0 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 25 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 27 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-12 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-12 | 2024-12-12 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284236 | PSV Exchange - DFCM-PSV-54370 | Remove PSV and Install blinds | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /07/DFCM-PSV-54370 | Remove PSV and Install blinds | Unknown
4 | NE | WRO | PRODLABO | PRODLABO | 2300000756 | LAB 01.01.19 TIL 31.12.19 | LAB 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /C | LAB 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODLABO | PRODLABO | 2300000756 | LAB 01.01.19 TIL 31.12.19 | LAB 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF /C | LAB 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODLABO | PRODLABO | 2300000756 | LAB 01.01.19 TIL 31.12.19 | LAB 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2019-12-31 | 2019-12-31 | 30 |  |  | DF /C | LAB 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODLABO | PRODLABO | 2300000756 | LAB 01.01.19 TIL 31.12.19 | LAB 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2019-12-31 | 2019-12-31 | 40 |  |  | DF /C | LAB 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODLABO | PRODLABO | 2300000756 | LAB 01.01.19 TIL 31.12.19 | LAB 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2020-05-03 | 2019-12-31 | 2019-12-31 | 50 |  |  | DF /C | LAB 01.03.20 TIL 31.12.20 | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-01 | 2019-10-05 | 2019-10-25 | 2 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-01 | 2019-10-05 | 2019-10-25 | 3 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-01 | 2019-10-05 | 2019-10-25 | 4 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-01 | 2019-10-05 | 2019-10-25 | 5 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-01 | 2019-10-05 | 2019-10-25 | 10 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | PRODTECH | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-02 | 2019-10-05 | 2019-10-25 | 20 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ELEC | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-03 | 2025-01-03 | 2019-10-05 | 2019-10-25 | 30 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-LAGG | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-04 | 2025-01-04 | 2019-10-05 | 2019-10-25 | 40 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-PIPF | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-04 | 2025-01-05 | 2019-10-05 | 2019-10-25 | 50 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ELEC | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-05 | 2025-01-06 | 2019-10-05 | 2019-10-25 | 60 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-06 | 2025-01-07 | 2019-10-05 | 2019-10-25 | 62 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-07 | 2025-01-08 | 2019-10-05 | 2019-10-25 | 63 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-08 | 2025-01-09 | 2019-10-05 | 2019-10-25 | 64 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ROPE | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-09 | 2025-01-10 | 2019-10-05 | 2019-10-25 | 65 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-PIPF | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-10 | 2025-01-10 | 2019-10-05 | 2019-10-25 | 70 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ELEC | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-10 | 2025-01-15 | 2019-10-05 | 2019-10-25 | 80 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ELEC | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-15 | 2025-01-16 | 2019-10-05 | 2019-10-25 | 90 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ELEC | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-16 | 2025-01-18 | 2019-10-05 | 2019-10-25 | 100 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-ELEC | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-18 | 2025-01-20 | 2019-10-05 | 2019-10-25 | 110 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | DFC-FUEL | WDF | MTN-ROPE | MTN-MECH | 2100025311 | ANOP DAN FC, Corroded pipes & valveses. | 2100025311-0002-COATING | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-20 | 2025-01-20 | 2019-10-05 | 2019-10-25 | 120 | AWSC | AWSC | DF /C /70/DFCI-PT-57132 | 2100025311-0002-COATING | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-17 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-17 | 2020-08-22 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 12.099999999999999644728632116 | 8.5 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-17 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 2.7000000000000001776356839392 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-17 | 2020-08-22 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 4 | 18 | Empty | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 2.7000000000000001776356839392 | 0 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-17 | 2021-01-14 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002922 | CMAT:DFG-Insulation assists FORCE 14343. | L3 Prepare Permit Scaff | PCNF | PCNF | 10.099999999999999644728632116 | 9 | Empty | 2026-01-01 | 2026-01-01 | 2020-08-17 | 2020-12-13 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /G /30/DFG-18-GPS-043-0017-DB-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060278 | Replace JB for HT 1832-C4-640A | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-12 | 2022-04-12 | 10 |  |  | DF /C /61/DFCI-DP-1832-04 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060278 | Replace JB for HT 1832-C4-640A | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-12 | 2022-04-12 | 20 |  |  | DF /C /61/DFCI-DP-1832-04 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060278 | Replace JB for HT 1832-C4-640A | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-01-12 | 2022-04-12 | 30 |  |  | DF /C /61/DFCI-DP-1832-04 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060278 | Replace JB for HT 1832-C4-640A | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-12 | 2022-04-12 | 40 |  |  | DF /C /61/DFCI-DP-1832-04 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100060278 | Replace JB for HT 1832-C4-640A | Isolate accordingly |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-12 | 2022-04-12 | 50 |  |  | DF /C /61/DFCI-DP-1832-04 | Isolate accordingly | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400337661 | 4Y FIELD PANEL LIFTGAS CONT MAINT | DE-ISOALTION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-06-07 | 2024-06-10 | 2024-06-07 | 2024-06-07 | 2024-06-07 | 2024-08-19 | 10 | SECE | SECE | DF /F /07/DFFA-FP-5915 | DE-ISOALTION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400337661 | 4Y FIELD PANEL LIFTGAS CONT MAINT | DE-ISOALTION BY PRODUCTION | SECE | SECE | 12 | 0 | Empty | 2024-06-07 | 2024-06-10 | 2024-06-07 | 2024-06-10 | 2024-06-07 | 2024-08-19 | 20 | SECE | SECE | DF /F /07/DFFA-FP-5915 | DE-ISOALTION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400337661 | 4Y FIELD PANEL LIFTGAS CONT MAINT | DE-ISOALTION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-06-07 | 2024-06-10 | 2024-06-10 | 2024-06-10 | 2024-06-07 | 2024-08-19 | 30 | SECE | SECE | DF /F /07/DFFA-FP-5915 | DE-ISOALTION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342410 | 6M DEAERATOR MAINT - DFBA-A-3561 - DFB | DEAERATOR MAINT - DFBA-A-3561 - DFB |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-15 | 2024-09-03 | 10 |  |  | DF /B /53/DFBA-A-3561 | DEAERATOR MAINT - DFBA-A-3561 - DFB | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 2 | 1 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-17 | 2024-01-06 | 2024-05-20 | 10 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 2 | 3 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-17 | 2024-06-17 | 2024-01-06 | 2024-05-20 | 20 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 2 | 6 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-18 | 2024-06-18 | 2024-01-06 | 2024-05-20 | 30 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 5 | 6 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-18 | 2024-06-19 | 2024-01-06 | 2024-05-20 | 40 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 2 | 3 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-19 | 2024-06-20 | 2024-01-06 | 2024-05-20 | 50 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 1 | 3 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-01-06 | 2024-05-20 | 60 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100102332 | Fail to open DFCI-BDV-33038 | Isolate Hydraulics | SCHSECE | SCHSECE | 1 | 1 | W25-W26 | 2024-06-17 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-01-06 | 2024-05-20 | 70 | SCHSECE | SCHSECE | DF /C /10/DFCI-BDV-33038 | Isolate Hydraulics | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342404 | 6M SW LIFT PUMP MAINT DFGA-P-5351/2/3 | SW LIFT PUMP MAINT DFGA-P-5351/2/3 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-23 | 2024-09-11 | 10 |  |  | DF /G /50/SEAWATER-LIFTPUMPS | SW LIFT PUMP MAINT DFGA-P-5351/2/3 | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400292166 | 3Y DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG | SCHSECE | SCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-12 | 2024-08-12 | 2023-10-20 | 2023-12-21 | 5 | SCHSECE | SCHSECE | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400292166 | 3Y DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG | SCHSECE | SCHSECE | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-12 | 2024-08-15 | 2023-10-20 | 2023-12-21 | 10 | SCHSECE | SCHSECE | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
A | NE | WPM | MTN-MECH | MTN-ELEC | 2400292166 | 3Y DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG | SCHSECE | SCHSECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2023-10-20 | 2023-12-21 | 20 | SCHSECE | SCHSECE | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
A | NE | WPM | MTN-MECH | MTN-INST | 2400292166 | 3Y DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG | SCHSECE | SCHSECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2023-10-20 | 2023-12-21 | 30 | SCHSECE | SCHSECE | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400292166 | 3Y DEAERATOR MAINT - DFGA-A-3541 - DFG | DEAERATOR MAINT - DFGA-A-3541 - DFG | SCHSECE | SCHSECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2023-10-20 | 2023-12-21 | 40 | SCHSECE | SCHSECE | DF /G /53/DFGA-A-3541 | DEAERATOR MAINT - DFGA-A-3541 - DFG | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235623 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-11 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-11 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235623 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-11 | ISOLATION ELECTRICAL | AWSC | AWSC | 23 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-11 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235623 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-11 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-29 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-11 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235623 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-11 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-11 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235729 | 4Y 380V E-SWB MAINT DFCI-N-1812-L01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235729 | 4Y 380V E-SWB MAINT DFCI-N-1812-L01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 6 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235729 | 4Y 380V E-SWB MAINT DFCI-N-1812-L01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235729 | 4Y 380V E-SWB MAINT DFCI-N-1812-L01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235729 | 4Y 380V E-SWB MAINT DFCI-N-1812-L01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100048282 | DFGA-A-0465 Replace 6 N2 gas cylindres | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | PCNF | PCNF | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 10 | PCNF | PCNF | DF /G /01/DFGA-A-0465 | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100048282 | DFGA-A-0465 Replace 6 N2 gas cylindres | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | PCNF | PCNF | 12 | 34 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 20 | PCNF | PCNF | DF /G /01/DFGA-A-0465 | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100048282 | DFGA-A-0465 Replace 6 N2 gas cylindres | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | PCNF | PCNF | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 25 | PCNF | PCNF | DF /G /01/DFGA-A-0465 | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100048282 | DFGA-A-0465 Replace 6 N2 gas cylindres | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | PCNF | PCNF | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 30 | PCNF | PCNF | DF /G /01/DFGA-A-0465 | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100048282 | DFGA-A-0465 Replace 6 N2 gas cylindres | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | PCNF | PCNF | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-07 | 2021-05-17 | 40 | PCNF | PCNF | DF /G /01/DFGA-A-0465 | Replace 6 pcs. N2 Cylindres DFGA-A-0465 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322243 | DFB-27-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 323 | 524.5 | Empty | 2021-07-26 | 2021-10-17 | 2021-07-26 | 2021-07-26 | 2021-02-01 | 2021-03-13 | 10 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 57 | 203 | Empty | 2021-07-26 | 2021-10-17 | 2021-07-26 | 2021-07-30 | 2021-02-01 | 2021-03-13 | 20 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 65 | 4.5 | Empty | 2021-07-26 | 2021-10-17 | 2021-07-30 | 2021-08-05 | 2021-02-01 | 2021-03-13 | 30 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 43 | 242 | Empty | 2021-07-26 | 2021-10-17 | 2021-08-05 | 2021-08-05 | 2021-02-01 | 2021-03-13 | 40 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 258 | 201 | Empty | 2021-07-26 | 2021-10-17 | 2021-08-05 | 2021-09-02 | 2021-02-01 | 2021-03-13 | 50 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 39 | 313.5 | Empty | 2021-07-26 | 2021-10-17 | 2021-09-02 | 2021-09-02 | 2021-02-01 | 2021-03-13 | 60 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 26 | 0.5 | Empty | 2021-07-26 | 2021-10-17 | 2021-09-02 | 2021-09-03 | 2021-02-01 | 2021-03-13 | 70 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 26 | 34 | Empty | 2021-07-26 | 2021-10-17 | 2021-09-03 | 2021-09-04 | 2021-02-01 | 2021-03-13 | 80 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 129 | 132.5 | Empty | 2021-07-26 | 2021-10-17 | 2021-09-04 | 2021-09-18 | 2021-02-01 | 2021-03-13 | 90 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 152 | 114 | Empty | 2021-07-26 | 2021-10-17 | 2021-09-18 | 2021-10-02 | 2021-02-01 | 2021-03-13 | 100 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 26 | 0 | Empty | 2021-07-26 | 2021-10-17 | 2021-10-02 | 2021-10-04 | 2021-02-01 | 2021-03-13 | 110 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 129 | 226.5 | Empty | 2021-07-26 | 2021-10-17 | 2021-10-04 | 2021-10-17 | 2021-02-01 | 2021-03-13 | 120 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002455 | DAF OCG NPT order - DFCI-V-3401 - TEST S | Meals & breaks | PCNF | PCNF | 0 | 0 | Empty | 2021-07-26 | 2021-10-17 | 2021-10-17 | 2021-10-17 | 2021-02-01 | 2021-03-13 | 130 | PCNF | PCNF | DF /C /11/DFCI-V-3401 | Meals & breaks | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337662 | 1Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SECE | SECE | 2 | 2 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-19 | 10 | SECE | SECE | DF /F /27/DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337662 | 1Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SECE | SECE | 4 | 4 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-08-19 | 20 | SECE | SECE | DF /F /27/DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337662 | 1Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SECE | SECE | 4 | 4 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-21 | 2024-07-22 | 2024-07-20 | 2024-08-19 | 30 | SECE | SECE | DF /F /27/DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400337662 | 1Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SECE | SECE | 1 | 1 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-22 | 2024-07-22 | 2024-07-20 | 2024-08-19 | 40 | SECE | SECE | DF /F /27/DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337662 | 1Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | SECE | SECE | 2 | 2 | Empty | 2024-07-20 | 2024-07-23 | 2024-07-22 | 2024-07-23 | 2024-07-20 | 2024-08-19 | 50 | SECE | SECE | DF /F /27/DFFA-A-5053 | SLOP OIL PACKAGE MAINT-DFFA-A-5053 | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400321270 | 1Y GLYCOL REGEN PKG MAINT-DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | SECE | SECE | 4 | 0 | Empty | 2024-10-05 | 2024-10-16 | 2024-10-05 | 2024-10-05 | 2024-04-08 | 2024-05-08 | 10 | SECE | SECE | DF /F /30/DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400321270 | 1Y GLYCOL REGEN PKG MAINT-DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | SECE | SECE | 18 | 0 | Empty | 2024-10-05 | 2024-10-16 | 2024-10-06 | 2024-10-10 | 2024-04-08 | 2024-05-08 | 20 | SECE | SECE | DF /F /30/DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-INST | 2400321270 | 1Y GLYCOL REGEN PKG MAINT-DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | SECE | SECE | 13 | 0 | Empty | 2024-10-05 | 2024-10-16 | 2024-10-10 | 2024-10-13 | 2024-04-08 | 2024-05-08 | 30 | SECE | SECE | DF /F /30/DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-ELEC | 2400321270 | 1Y GLYCOL REGEN PKG MAINT-DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | SECE | SECE | 8 | 0 | Empty | 2024-10-05 | 2024-10-16 | 2024-10-13 | 2024-10-15 | 2024-04-08 | 2024-05-08 | 40 | SECE | SECE | DF /F /30/DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400321270 | 1Y GLYCOL REGEN PKG MAINT-DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | SECE | SECE | 4 | 0 | Empty | 2024-10-05 | 2024-10-16 | 2024-10-15 | 2024-10-16 | 2024-04-08 | 2024-05-08 | 50 | SECE | SECE | DF /F /30/DFFA-A-4101 | GLYCOL REGEN PKG MAINT-DFFA-A-4101 | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 0 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-08 | 2023-02-08 | 2023-02-08 | 2023-03-25 | 10 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-TELE | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 6 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-08 | 2023-02-10 | 2023-02-08 | 2023-03-25 | 20 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 8 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-10 | 2023-02-11 | 2023-02-08 | 2023-03-25 | 30 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 12 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-11 | 2023-02-12 | 2023-02-08 | 2023-03-25 | 40 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-ELEC | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 3 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-12 | 2023-02-13 | 2023-02-08 | 2023-03-25 | 50 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-ELEC | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 2 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-13 | 2023-02-13 | 2023-02-08 | 2023-03-25 | 60 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 6 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-13 | 2023-02-14 | 2023-02-08 | 2023-03-25 | 70 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 4 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-14 | 2023-02-15 | 2023-02-08 | 2023-03-25 | 80 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 2 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-08 | 2023-03-25 | 90 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 0 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-08 | 2023-03-25 | 100 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
2 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200013518 | Built tent "changing room" for campagn | urgent ghettoblaster to dff |  |  | 0 | 0 | Empty | 2023-02-08 | 2023-02-15 | 2023-02-15 | 2023-02-15 | 2023-02-08 | 2023-03-25 | 110 |  |  | DF /C /82 | urgent ghettoblaster to dff | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337666 | 1Y MOB BOAT MAINT - DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | SECE | SECE | 8 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-10 | 2024-08-11 | 2024-07-21 | 2024-08-20 | 10 | SECE | SECE | DF /C /02/DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400337666 | 1Y MOB BOAT MAINT - DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | SECE | SECE | 10 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-12 | 2024-08-14 | 2024-07-21 | 2024-08-20 | 20 | SECE | SECE | DF /C /02/DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337666 | 1Y MOB BOAT MAINT - DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | SECE | SECE | 2 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-14 | 2024-08-14 | 2024-07-21 | 2024-08-20 | 30 | SECE | SECE | DF /C /02/DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400337666 | 1Y MOB BOAT MAINT - DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | SECE | SECE | 2 | 0 | Empty | 2024-08-10 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-07-21 | 2024-08-20 | 40 | SECE | SECE | DF /C /02/DFCI-X-0706 | MOB BOAT MAINT - DFCI-X-0706 | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400325366 | 1Y HVAC COOL UNIT VENDOR DFCI-A-12074 | TEST | AWSC | AWSC | 24 | 0 | Empty | 2024-04-26 | 2024-05-02 | 2024-04-26 | 2024-05-02 | 2024-04-08 | 2024-05-25 | 10 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | TEST | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400325366 | 1Y HVAC COOL UNIT VENDOR DFCI-A-12074 | TEST | AWSC | AWSC | 6 | 0 | Empty | 2024-04-26 | 2024-05-02 | 2024-04-28 | 2024-05-02 | 2024-04-08 | 2024-05-25 | 20 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | TEST | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400325366 | 1Y HVAC COOL UNIT VENDOR DFCI-A-12074 | TEST | AWSC | AWSC | 0 | 0 | Empty | 2024-04-26 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-04-08 | 2024-05-25 | 30 | AWSC | AWSC | DF /C /82/DFCI-A-12074 | TEST | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022914 | Handles are missing on DF /F /23/DFFA-HC | Install new handle |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-04 | 2019-07-14 | 10 |  |  | DF /F /23/DFFA-HCV-360079-U | Install new handle | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337420 | 1Y H2S+DEW POINT SKID DFGA-A-4460 | H2S+DEW POINT SKID DFGA-A-4460 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2024-04-24 | 2024-05-30 | 10 |  |  | DF /G /34/DFGA-A-4460 | H2S+DEW POINT SKID DFGA-A-4460 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400337420 | 1Y H2S+DEW POINT SKID DFGA-A-4460 | H2S+DEW POINT SKID DFGA-A-4460 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2024-04-24 | 2024-05-30 | 20 |  |  | DF /G /34/DFGA-A-4460 | H2S+DEW POINT SKID DFGA-A-4460 | Unknown
A | DFE-OIL | WPM | MTN-MECH | PRODTECH | 2400218581 | 1Y SDV LUBE/FUNC TEST OIL - DFE | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-11-11 | 2022-12-11 | 10 | SECE | SECE | DF /E /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFE-OIL | WPM | MTN-MECH | MTN-MECH | 2400218581 | 1Y SDV LUBE/FUNC TEST OIL - DFE | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2022-11-11 | 2022-12-11 | 20 | SECE | SECE | DF /E /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFE-OIL | WPM | MTN-MECH | PRODTECH | 2400218581 | 1Y SDV LUBE/FUNC TEST OIL - DFE | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2022-11-11 | 2022-12-11 | 30 | SECE | SECE | DF /E /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235663 | 4Y 400V N-SWB MAINT DFCI-N-1802-L0 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L0-R1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235663 | 4Y 400V N-SWB MAINT DFCI-N-1802-L0 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L0-R1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235663 | 4Y 400V N-SWB MAINT DFCI-N-1802-L0 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L0-R1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235663 | 4Y 400V N-SWB MAINT DFCI-N-1802-L0 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L0-R1 | DE-ISOLATION ELECTRICAL | Unknown
2 | DFA-O17 | WDF | MTN-MECH | MTN-INST | 2100089555 | DFA-17 Defect choke SOV Leak | Troubleshoot on leaking SOV |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-22 | 2023-06-06 | 10 |  |  | DF /A /10/DFAA-CVA-30305 | Troubleshoot on leaking SOV | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-CRAN | 2100094703 | DFFW/78 Aircondition not working | Troubleshoot |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-07-16 | 2023-08-30 | 10 |  |  | DF /F /78/DFFA-A-6102 | Troubleshoot | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094703 | DFFW/78 Aircondition not working | Troubleshoot |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-07-16 | 2023-08-30 | 20 |  |  | DF /F /78/DFFA-A-6102 | Troubleshoot | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094703 | DFFW/78 Aircondition not working | Troubleshoot |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2023-07-16 | 2023-08-30 | 30 |  |  | DF /F /78/DFFA-A-6102 | Troubleshoot | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094703 | DFFW/78 Aircondition not working | Troubleshoot |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2023-07-16 | 2023-08-30 | 40 |  |  | DF /F /78/DFFA-A-6102 | Troubleshoot | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094703 | DFFW/78 Aircondition not working | Troubleshoot |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2023-07-16 | 2023-08-30 | 50 |  |  | DF /F /78/DFFA-A-6102 | Troubleshoot | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100094703 | DFFW/78 Aircondition not working | Troubleshoot |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-07-16 | 2023-08-30 | 60 |  |  | DF /F /78/DFFA-A-6102 | Troubleshoot | Unknown
D | NOSD | WPM | PRODTECH | PRODTECH | 2400344171 | PIGGING, P3002 10" DFB-GOC OIL 2W | P3002_DFB-GOC | AWSC | AWSC | 4 | 0 | Empty | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-12 | 2024-09-18 | 10 | AWSC | AWSC | DF /B /23/DFBY-PL-673002 | P3002_DFB-GOC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400343678 | 1Y HVAC SUPP EMG GEN CHECK DFGA-B-1230 | PERSONAL ISOLATION |  |  | 1 | 0 | Empty | 2024-08-10 | 2024-08-13 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-09-15 | 10 |  |  | DF /G /09/DFGA-B-1230 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400343678 | 1Y HVAC SUPP EMG GEN CHECK DFGA-B-1230 | PERSONAL ISOLATION |  |  | 10 | 0 | Empty | 2024-08-10 | 2024-08-13 | 2024-08-10 | 2024-08-12 | 2024-08-10 | 2024-09-15 | 20 |  |  | DF /G /09/DFGA-B-1230 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400343678 | 1Y HVAC SUPP EMG GEN CHECK DFGA-B-1230 | PERSONAL ISOLATION |  |  | 1 | 0 | Empty | 2024-08-10 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-08-10 | 2024-09-15 | 30 |  |  | DF /G /09/DFGA-B-1230 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400343678 | 1Y HVAC SUPP EMG GEN CHECK DFGA-B-1230 | PERSONAL ISOLATION |  |  | 2 | 0 | Empty | 2024-08-10 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-10 | 2024-09-15 | 40 |  |  | DF /G /09/DFGA-B-1230 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344054 | 1Y LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-21 | 2024-08-25 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2024-09-20 | 10 | SECE | SECE | DF /F /50/SEAWATER-LIFTPUMPS | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344054 | 1Y LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-21 | 2024-08-25 | 2024-08-21 | 2024-08-23 | 2024-08-21 | 2024-09-20 | 20 | SECE | SECE | DF /F /50/SEAWATER-LIFTPUMPS | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344054 | 1Y LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-21 | 2024-08-25 | 2024-08-23 | 2024-08-25 | 2024-08-21 | 2024-09-20 | 30 | SECE | SECE | DF /F /50/SEAWATER-LIFTPUMPS | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344054 | 1Y LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-21 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-21 | 2024-09-20 | 40 | SECE | SECE | DF /F /50/SEAWATER-LIFTPUMPS | LIFT PUMP MAINT DFFA-P-5301/2/3/4/5 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053488 | Replace Floodlight DFE-1803-7-L1B | Replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-30 | 2022-03-29 | 10 |  |  | DF /E /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053488 | Replace Floodlight DFE-1803-7-L1B | Replace floodlight |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 20 |  |  | DF /E /62 | Replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053488 | Replace Floodlight DFE-1803-7-L1B | Replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 30 |  |  | DF /E /62 | Replace floodlight | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079189 | DFG Hot seal gas valve to be changed. | Build scaffold |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-01-20 | 2023-06-04 | 10 |  |  | DF /G /31/DFGA-HCV-440119 | Build scaffold | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079189 | DFG Hot seal gas valve to be changed. | Build scaffold |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-20 | 2023-06-04 | 20 |  |  | DF /G /31/DFGA-HCV-440119 | Build scaffold | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079189 | DFG Hot seal gas valve to be changed. | Build scaffold |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-01-20 | 2023-06-04 | 30 |  |  | DF /G /31/DFGA-HCV-440119 | Build scaffold | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079189 | DFG Hot seal gas valve to be changed. | Build scaffold |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-20 | 2023-06-04 | 40 |  |  | DF /G /31/DFGA-HCV-440119 | Build scaffold | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100079189 | DFG Hot seal gas valve to be changed. | Build scaffold |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-20 | 2023-06-04 | 50 |  |  | DF /G /31/DFGA-HCV-440119 | Build scaffold | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322231 | DFA-01-WF-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 85 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 10 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 20 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 30 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 40 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 50 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 60 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 70 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 80 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000654 | DK46 EL/INST MATERIAL ORDER 2020 | DK46 EL/INST MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-01-01 | 2020-12-31 | 90 |  |  | DF /C | DK46 EL/INST MATERIAL ORDER 2020 | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400328735 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-20 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 31 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2024-04-03 | 2024-06-04 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-20 | ATEX EQUIPMENT INSPECTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061492 | H2S scav PCV-390575 internal leaking | ICC |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2022-02-08 | 2022-05-09 | 10 |  |  | DF /F /75/DFFA-PCV-390575 | ICC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100061492 | H2S scav PCV-390575 internal leaking | ICC |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2022-02-08 | 2022-05-09 | 20 |  |  | DF /F /75/DFFA-PCV-390575 | ICC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061492 | H2S scav PCV-390575 internal leaking | ICC |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2022-02-08 | 2022-05-09 | 30 |  |  | DF /F /75/DFFA-PCV-390575 | ICC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100061492 | H2S scav PCV-390575 internal leaking | ICC |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2022-02-08 | 2022-05-09 | 40 |  |  | DF /F /75/DFFA-PCV-390575 | ICC | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061492 | H2S scav PCV-390575 internal leaking | ICC |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2022-02-08 | 2022-05-09 | 50 |  |  | DF /F /75/DFFA-PCV-390575 | ICC | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344337 | 6M WI FILT & BLOWERS MAINT-DFFA-A-3501 | WI FILT & BLOWERS MAINT-DFFA-A-3501 |  |  | 8 | 0 | Empty | 2024-09-13 | 2024-09-14 | 2024-09-13 | 2024-09-14 | 2024-09-13 | 2024-09-29 | 10 |  |  | DF /F /51/DFFA-A-3501 | WI FILT & BLOWERS MAINT-DFFA-A-3501 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2021-02-03 | 2021-02-03 | 2020-03-10 | 2020-08-07 | 10 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 32 | 25 | Empty | 2024-07-29 | 2024-08-03 | 2020-10-29 | 2021-02-03 | 2020-03-10 | 2020-08-07 | 20 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2021-02-03 | 2021-02-03 | 2020-03-10 | 2020-08-07 | 30 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 12 | 20 | Empty | 2024-07-29 | 2024-08-03 | 2020-10-16 | 2020-10-23 | 2020-03-10 | 2020-08-07 | 35 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 28 | 21 | Empty | 2024-07-29 | 2024-08-03 | 2020-10-29 | 2020-12-28 | 2020-03-10 | 2020-08-07 | 40 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 34 | 21 | Empty | 2024-07-29 | 2024-08-03 | 2020-10-30 | 2021-02-03 | 2020-03-10 | 2020-08-07 | 50 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 8 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2020-11-16 | 2020-12-28 | 2020-03-10 | 2020-08-07 | 60 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 28 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2020-03-10 | 2020-08-07 | 65 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 18 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-08-01 | 2020-03-10 | 2020-08-07 | 66 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2020-03-10 | 2020-08-07 | 70 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100024978 | DFF Blower B-3502 coroded pipe | Blower B-3502 coroded pipe | PCNF | PCNF | 6 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2020-03-10 | 2020-08-07 | 80 | PCNF | PCNF | DF /F /51/DFFA-B-3502 | Blower B-3502 coroded pipe | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100104202 | DFC malfunc. bleed valve on HCV-36025 | Remove old Bleed HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-02-09 | 2024-06-23 | 10 |  |  | DF /C /26/DFCI-HCV-36025 | Remove old Bleed HCV | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100104202 | DFC malfunc. bleed valve on HCV-36025 | Remove old Bleed HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2024-02-09 | 2024-06-23 | 20 |  |  | DF /C /26/DFCI-HCV-36025 | Remove old Bleed HCV | Unknown
3 | DAN-OIL | WDF | MTN-MECH | MTN-MECH | 2100104202 | DFC malfunc. bleed valve on HCV-36025 | Remove old Bleed HCV |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2024-02-09 | 2024-06-23 | 30 |  |  | DF /C /26/DFCI-HCV-36025 | Remove old Bleed HCV | Unknown
3 | DAN-OIL | WDF | MTN-MECH | PRODTECH | 2100104202 | DFC malfunc. bleed valve on HCV-36025 | Remove old Bleed HCV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2024-02-09 | 2024-06-23 | 40 |  |  | DF /C /26/DFCI-HCV-36025 | Remove old Bleed HCV | Unknown
D | NOSD | WPM | MTN-INST | MTN-INST | 2400302347 | 1Y FISCAL CALIBRATION EQ CHECK - DFC | FISCAL CALIBRATION EQ CHECK - DFC | PCNFAWSC | PCNFAWSC | 6.5 | 2 | 23-W51-52 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-12-26 | 2024-02-11 | 10 | PCNFAWSC | PCNFAWSC | DF /C /83/DFCA-CP-6901 | FISCAL CALIBRATION EQ CHECK - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 20 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-06 | 2023-10-19 | 2024-03-02 | 10 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-13 | 2023-10-19 | 2024-03-02 | 20 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-13 | 2024-07-14 | 2023-10-19 | 2024-03-02 | 30 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 6 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-14 | 2024-07-15 | 2023-10-19 | 2024-03-02 | 40 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 8 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 50 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 2 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 60 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 1 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2023-10-19 | 2024-03-02 | 70 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 10 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-10-19 | 2024-03-02 | 80 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097583 | LB2 Corroded wire sheaves to be replaced | Denso tape to cover greased thread | AWSC | AWSC | 0 | 0 | Empty | 2024-07-05 | 2024-07-17 | 2024-07-05 | 2024-07-05 | 2023-10-19 | 2024-03-02 | 90 | AWSC | AWSC | DF /C /02/DFCI-X-0702 | Denso tape to cover greased thread | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235662 | 4Y 400V N-SWB MAINT DFCI-N-1802-R05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R5A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235662 | 4Y 400V N-SWB MAINT DFCI-N-1802-R05 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R5A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235662 | 4Y 400V N-SWB MAINT DFCI-N-1802-R05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R5A | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235662 | 4Y 400V N-SWB MAINT DFCI-N-1802-R05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R5A | ISOLATION ELECTRICAL | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000782 | DK46 "BURET"PRO MATERIAL ORDER 2019 | DK46 "BURET"PRO MATERIAL ORDER 2019 |  |  | 0 | 0 | Empty | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2020-03-25 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /F | DK46 "BURET"PRO MATERIAL ORDER 2019 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322304 | DFG-36-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 2 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235794 | 4Y 380V N-SWB MAINT-DFAA-N-1800-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235794 | 4Y 380V N-SWB MAINT-DFAA-N-1800-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235794 | 4Y 380V N-SWB MAINT-DFAA-N-1800-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235794 | 4Y 380V N-SWB MAINT-DFAA-N-1800-01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_01 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235716 | 4Y 380V E-SWB MAINT DFCC-N-1813-01 | 380V E-SWB MAINT DFCC-N-1813-01 | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-01 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235716 | 4Y 380V E-SWB MAINT DFCC-N-1813-01 | 380V E-SWB MAINT DFCC-N-1813-01 | AWSCSECE | AWSCSECE | 4 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 20 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-01 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235716 | 4Y 380V E-SWB MAINT DFCC-N-1813-01 | 380V E-SWB MAINT DFCC-N-1813-01 | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 30 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-01 | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235716 | 4Y 380V E-SWB MAINT DFCC-N-1813-01 | 380V E-SWB MAINT DFCC-N-1813-01 | AWSCSECE | AWSCSECE | 1 | 0 | W09-W10 | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 40 | AWSCSECE | AWSCSECE | DF /C /05/DFCC-N-1813 | 380V E-SWB MAINT DFCC-N-1813-01 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058469 | DFGA-PI-553008 | Isolate P-55310 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2021-12-05 | 2022-03-05 | 20 |  |  | DF /G /75/DFGA-A-55300 | Isolate P-55310 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058469 | DFGA-PI-553008 | Isolate P-55310 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2021-12-05 | 2022-03-05 | 30 |  |  | DF /G /75/DFGA-A-55300 | Isolate P-55310 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058469 | DFGA-PI-553008 | Isolate P-55310 |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2021-12-05 | 2022-03-05 | 40 |  |  | DF /G /75/DFGA-A-55300 | Isolate P-55310 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100103977 | DFGA-HRF-03311 Triway valve broken | Isolate hosereel | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-12-20 | 2024-02-03 | 10 | SECE | SECE | DF /G /01/DFGA-HRF-03311 | Isolate hosereel | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100103977 | DFGA-HRF-03311 Triway valve broken | Isolate hosereel | SECE | SECE | 6 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2023-12-20 | 2024-02-03 | 20 | SECE | SECE | DF /G /01/DFGA-HRF-03311 | Isolate hosereel | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100103977 | DFGA-HRF-03311 Triway valve broken | Isolate hosereel | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2023-12-20 | 2024-02-03 | 30 | SECE | SECE | DF /G /01/DFGA-HRF-03311 | Isolate hosereel | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 10 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-06 | 2023-11-08 | 2018-03-03 | 2018-06-01 | 9 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 2 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-08 | 2023-11-09 | 2018-03-03 | 2018-06-01 | 10 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 20 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-09 | 2023-11-11 | 2018-03-03 | 2018-06-01 | 20 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 3 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-11 | 2023-11-12 | 2018-03-03 | 2018-06-01 | 30 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 10 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-12 | 2023-11-13 | 2018-03-03 | 2018-06-01 | 40 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 24 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-12 | 2023-11-15 | 2018-03-03 | 2018-06-01 | 50 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 64 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-15 | 2023-11-23 | 2018-03-03 | 2018-06-01 | 60 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 20 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-23 | 2023-11-25 | 2018-03-03 | 2018-06-01 | 70 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 1 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-25 | 2023-11-26 | 2018-03-03 | 2018-06-01 | 80 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 1 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-26 | 2023-11-26 | 2018-03-03 | 2018-06-01 | 90 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 20 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-13 | 2024-01-15 | 2018-03-03 | 2018-06-01 | 100 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 64 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-15 | 2024-01-23 | 2018-03-03 | 2018-06-01 | 110 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 10 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-23 | 2024-01-25 | 2018-03-03 | 2018-06-01 | 120 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 10 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-23 | 2024-01-25 | 2018-03-03 | 2018-06-01 | 130 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 24 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-23 | 2024-01-26 | 2018-03-03 | 2018-06-01 | 140 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 3 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-26 | 2024-01-27 | 2018-03-03 | 2018-06-01 | 150 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 2 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-27 | 2024-01-28 | 2018-03-03 | 2018-06-01 | 160 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 20 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2024-01-28 | 2024-01-30 | 2018-03-03 | 2018-06-01 | 170 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100027671 | DFC rep/return of filterhouse FT-5211 | Remounting of refurb. filterhouse. |  |  | 0 | 0 | W45-46 | 2023-11-06 | 2024-01-30 | 2023-11-06 | 2023-11-06 | 2018-03-03 | 2018-06-01 | 180 |  |  | DF /C /51/DFCM-FT-5211 | Remounting of refurb. filterhouse. | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053477 | Replace floodlight DFB 1810-48-L1E | De-Isolate above |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-10-30 | 2022-03-29 | 10 |  |  | DF /B /62 | De-Isolate above | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053477 | Replace floodlight DFB 1810-48-L1E | De-Isolate above |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 20 |  |  | DF /B /62 | De-Isolate above | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053477 | Replace floodlight DFB 1810-48-L1E | De-Isolate above |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-10-30 | 2022-03-29 | 30 |  |  | DF /B /62 | De-Isolate above | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100075989 | DFE/78: Replace Hyd. hoses, fittings, ch | Replace hydraulic hoses, valve, fittings | SCH | SCH | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2022-11-18 | 2023-04-02 | 10 | SCH | SCH | DF /E /78/DFEZ-X-6150 | Replace hydraulic hoses, valve, fittings | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100075989 | DFE/78: Replace Hyd. hoses, fittings, ch | Replace hydraulic hoses, valve, fittings | SCH | SCH | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-16 | 2024-07-17 | 2022-11-18 | 2023-04-02 | 20 | SCH | SCH | DF /E /78/DFEZ-X-6150 | Replace hydraulic hoses, valve, fittings | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075989 | DFE/78: Replace Hyd. hoses, fittings, ch | Replace hydraulic hoses, valve, fittings | SCH | SCH | 18 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-16 | 2024-07-17 | 2022-11-18 | 2023-04-02 | 30 | SCH | SCH | DF /E /78/DFEZ-X-6150 | Replace hydraulic hoses, valve, fittings | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100075989 | DFE/78: Replace Hyd. hoses, fittings, ch | Replace hydraulic hoses, valve, fittings | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2022-11-18 | 2023-04-02 | 40 | SCH | SCH | DF /E /78/DFEZ-X-6150 | Replace hydraulic hoses, valve, fittings | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100075989 | DFE/78: Replace Hyd. hoses, fittings, ch | Replace hydraulic hoses, valve, fittings | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2022-11-18 | 2023-04-02 | 50 | SCH | SCH | DF /E /78/DFEZ-X-6150 | Replace hydraulic hoses, valve, fittings | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100075989 | DFE/78: Replace Hyd. hoses, fittings, ch | Replace hydraulic hoses, valve, fittings | SCH | SCH | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-15 | 2022-11-18 | 2023-04-02 | 60 | SCH | SCH | DF /E /78/DFEZ-X-6150 | Replace hydraulic hoses, valve, fittings | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 10 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 0.5 | 14 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 20 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 25 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 6 | 4 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 30 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 40 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 50 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 4 | 4 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 60 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081821 | DFF-PT-300126 shows to little reading | Isolate Pressure transmitter | PCNF | PCNF | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-11 | 2023-07-24 | 70 | PCNF | PCNF | DF /F /07/DFFA-PT-300126 | Isolate Pressure transmitter | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-SCAF | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 18 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-03 | 2022-04-20 | 2022-09-17 | 10 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-03 | 2022-04-20 | 2022-09-17 | 20 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-ROPE | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-01 | 2022-04-20 | 2022-09-17 | 25 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-03 | 2025-01-04 | 2022-04-20 | 2022-09-17 | 30 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2025-01-05 | 2022-04-20 | 2022-09-17 | 40 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2025-01-05 | 2022-04-20 | 2022-09-17 | 50 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-01-05 | 2022-04-20 | 2022-09-17 | 60 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
4 | DFB-OIL | WDF | MTN-MECH | MTN-SCAF | 2100062057 | DFB fire water valve LV-72 | Rigger assistance |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2025-01-07 | 2022-04-20 | 2022-09-17 | 70 |  |  | DF /B /01/DFBA-HCV-03805 | Rigger assistance | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 8 | 6 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-17 | 2023-09-28 | 2024-02-10 | 20 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 1 | 2 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-17 | 2023-09-28 | 2024-02-10 | 30 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 2 | 1 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-18 | 2023-09-28 | 2024-02-10 | 40 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 2 | 1 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-18 | 2024-07-18 | 2023-09-28 | 2024-02-10 | 50 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 1 | 1 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-18 | 2024-07-18 | 2023-09-28 | 2024-02-10 | 60 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 1 | 1 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-18 | 2024-07-19 | 2023-09-28 | 2024-02-10 | 70 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200015626 | Socket outlets - Gaming room | Materials added | SCH | SCH | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2023-09-28 | 2024-02-10 | 80 | SCH | SCH | DF /C /09/ACCOMMODATION-LEVEL-2 | Materials added | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 24 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-17 | 2023-07-17 | 2023-02-18 | 2023-04-04 | 10 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 12 | 12 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-19 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 20 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 3 | 3 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-20 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 30 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 12 | 216 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-21 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 40 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 4 | 4 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-22 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 50 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 8 | 8 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 60 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 4 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 70 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 8 | 8 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 80 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 12 | 22 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 90 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 16 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 100 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 8 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 110 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 8 | 8 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 120 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 12 | 12 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 130 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 4 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-30 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 140 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 3 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-30 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 150 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 2 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 160 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 10 | 34 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 170 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 18 | 24 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 180 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 0 | 0 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-23 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 190 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085818 | DFF-FT-5311 filter element do not drive | Rig in Filter internals |  |  | 0 | 38 | W29-30 | 2023-07-17 | 2023-07-30 | 2023-07-30 | 2023-07-30 | 2023-02-18 | 2023-04-04 | 200 |  |  | DF /F /51/DFFA-FT-5311 | Rig in Filter internals | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 10 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 20 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 30 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 40 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 50 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 60 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 70 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 80 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 90 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 100 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 110 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 120 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 130 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 140 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000652 | DK46 SMEDE MATERIAL ORDER 2020 | DK46 SMEDE MATERIAL ORDER 2020 |  |  | 0 | 0 | Empty | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-01-01 | 2020-12-31 | 150 |  |  | DF /C | DK46 SMEDE MATERIAL ORDER 2020 | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 6 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 11 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 6 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 9 | 20 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 16 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 9 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 3 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 28 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 99 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 9 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 150 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 160 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 170 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 180 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 9 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 190 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 200 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 210 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 220 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 230 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 240 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 250 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 260 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 270 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ROPE | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 280 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 290 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 16 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 300 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ELEC | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 12 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 310 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 320 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-RIGG | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 330 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 48 | 20 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 340 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 48 | 24 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 350 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 360 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-RIGG | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 370 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 380 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-RIGG | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 16 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 390 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 391 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | VEN-INSP | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 392 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-RIGG | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 16 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 400 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 48 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 410 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | VEN-INSP | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 16 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 420 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PAIN | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 430 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 440 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 36 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 450 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-ELEC | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 4 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 460 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 470 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
3 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200009145 | DGSPR Dan F Permanent support phase 1 | Insert and tighten bolts acc. to spec. | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 2 | W35-36 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2023-08-28 | 2022-01-05 | 2022-04-05 | 480 | PCNFAWSCSCH | PCNFAWSCSCH | DF /A /86/22000 - TERT STRUCT | Insert and tighten bolts acc. to spec. | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107882 | Exchange of DFGA-P-3958 | Exchange of DFGA-P-3958 |  |  | 0 | 0 | Empty | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2027-01-30 | 10 |  |  | DF /G /75/DFGA-P-3958 | Exchange of DFGA-P-3958 | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300003744 | DFHMI Installation of BUZZER in CCR. | DFHMI Install BUZZ in CCR |  |  | 24 | 0 | W19-W20 | 2024-05-06 | 2024-05-14 | 2024-05-06 | 2024-05-11 | 2022-03-04 | 2022-03-24 | 10 |  |  | DF /C /04/DFCI-FP-2051 | DFHMI Install BUZZ in CCR | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300003744 | DFHMI Installation of BUZZER in CCR. | DFHMI Install BUZZ in CCR |  |  | 12 | 0 | W19-W20 | 2024-05-06 | 2024-05-14 | 2024-05-12 | 2024-05-14 | 2022-03-04 | 2022-03-24 | 20 |  |  | DF /C /04/DFCI-FP-2051 | DFHMI Install BUZZ in CCR | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300003744 | DFHMI Installation of BUZZER in CCR. | DFHMI Install BUZZ in CCR |  |  | 0 | 0 | W19-W20 | 2024-05-06 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2022-03-04 | 2022-03-24 | 30 |  |  | DF /C /04/DFCI-FP-2051 | DFHMI Install BUZZ in CCR | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235708 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR07-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235708 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR07-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235708 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR07-DA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235708 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR07-DA001 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 21 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 99 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 200 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 202 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 204 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-24 | 2020-10-03 | 205 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 22 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-24 | 2020-10-03 | 206 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 299 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 6 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-24 | 2020-10-03 | 400 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2023-11-20 | 2023-11-28 | 2020-08-24 | 2020-10-03 | 421 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 2 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-24 | 2020-10-03 | 431 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036414 | DFF-WE-390632A Vejecelle flipper. T-3938 | New material | PCNFSCH | PCNFSCH | 0 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-08-24 | 2020-10-03 | 441 | PCNFSCH | PCNFSCH | DF /F /75/DFFA-WE-390632A | New material | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235790 | 4Y 380V HT-DP MAINT-DFCI-DP-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1830 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235790 | 4Y 380V HT-DP MAINT-DFCI-DP-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1830 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235790 | 4Y 380V HT-DP MAINT-DFCI-DP-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1830 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235790 | 4Y 380V HT-DP MAINT-DFCI-DP-1830 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1830 | ISOLATION ELECTRICAL | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 2 | 0 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-16 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 10 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 4 | 0 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-16 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 20 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 26 | 0 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-17 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 30 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 16 | 8 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-21 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 40 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 26 | 12 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-23 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 50 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 12 | 0 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-25 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 60 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 4 | 6 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-07-25 | 2024-07-26 | 2024-07-23 | 2024-12-05 | 70 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 2 | 0 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-07-23 | 2024-12-05 | 80 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 4 | 0 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-07-23 | 2024-12-05 | 90 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100114205 | Chlorine P-55310 is externally leaky | Isolate DFGA-P-55310 - EIA |  |  | 12 | 2 | W29-W30 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-15 | 2024-07-23 | 2024-12-05 | 100 |  |  | DF /G /75/DFGA-P-55310 | Isolate DFGA-P-55310 - EIA | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235647 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L09B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235647 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L09 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L09B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235647 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L09B1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235647 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L09B1 | ISOLATION ELECTRICAL | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100050106 | DFB-WH hydr. cabinet minor leaks inside | Vendor troubleshoot Hydraulic cabinets | AWSC | AWSC | 24 | 0 | W27-28 IOP 6-13/7 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-27 | 2021-06-10 | 2021-09-08 | 10 | AWSC | AWSC | DF /B /07/DFBA-A-3101B | Vendor troubleshoot Hydraulic cabinets | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342427 | 18M IR GAS DETECTORS CHECK - DFG | IR GAS DETECTORS CHECK | SECE | SECE | 44 | 0 | W35-W36 | 2024-08-26 | 2024-09-06 | 2024-08-26 | 2024-09-06 | 2024-08-03 | 2024-09-02 | 10 | SECE | SECE | DF /G /03/FGS-DETECTORS | IR GAS DETECTORS CHECK | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235702 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF08 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF08-DA003 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235702 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF08 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF08-DA003 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235702 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF08 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF08-DA003 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235702 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF08 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF08-DA003 | 400V N-SWB INSP-DFGA-N-1842B-BF08 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2019-10-24 | 2020-01-22 | 10 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2019-10-24 | 2020-01-22 | 20 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2019-10-24 | 2020-01-22 | 30 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2019-10-24 | 2020-01-22 | 160 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2019-10-24 | 2020-01-22 | 165 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2019-10-24 | 2020-01-22 | 166 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100025167 | CMAT:H2S Scav. motor PM-3461 thermister | Isolate drawer in SWBD. DFGA-N-1842 (BUS |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2019-10-24 | 2020-01-22 | 170 |  |  | DF /G /27/DFGA-PM-3461 | Isolate drawer in SWBD. DFGA-N-1842 (BUS | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400329497 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2024-05-13 | 2024-06-18 | 10 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329497 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2024-05-13 | 2024-06-18 | 20 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329497 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2024-05-13 | 2024-06-18 | 30 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400329497 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2024-05-13 | 2024-06-18 | 40 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400329497 | 1Y FW JOCKEY PUMP MAINT -DFCM-P-0308/09 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2024-05-13 | 2024-06-18 | 50 |  |  | DF /C /01/FIREWATER-JOCKEY-PUMPS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322248 | DFB-01-WF-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 99 | 0 | Empty | 2024-10-30 | 2024-11-19 | 2024-10-30 | 2024-11-18 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /01/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000716 | DK46.014-BESTILLING/BACKLOAD Q2/Q3/Q4 | DK46.014 - BESTILLING/BACKLOAD Q2/Q3/Q4 |  |  | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2018-06-01 | 2019-01-01 | 10 |  |  | DF /A /08 | DK46.014 - BESTILLING/BACKLOAD Q2/Q3/Q4 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105402 | Repl pilot-vlv DFAA-XCV-0313,synergi#676 | Isolate and verifification by production |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-02-24 | 2024-07-08 | 10 |  |  | DF /A /01/DFAA-XCV-0313 | Isolate and verifification by production | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100105402 | Repl pilot-vlv DFAA-XCV-0313,synergi#676 | Isolate and verifification by production |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-02-24 | 2024-07-08 | 20 |  |  | DF /A /01/DFAA-XCV-0313 | Isolate and verifification by production | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105402 | Repl pilot-vlv DFAA-XCV-0313,synergi#676 | Isolate and verifification by production |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-02-24 | 2024-07-08 | 30 |  |  | DF /A /01/DFAA-XCV-0313 | Isolate and verifification by production | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100105402 | Repl pilot-vlv DFAA-XCV-0313,synergi#676 | Isolate and verifification by production |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2024-02-24 | 2024-07-08 | 40 |  |  | DF /A /01/DFAA-XCV-0313 | Isolate and verifification by production | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100105402 | Repl pilot-vlv DFAA-XCV-0313,synergi#676 | Isolate and verifification by production |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-02-24 | 2024-07-08 | 50 |  |  | DF /A /01/DFAA-XCV-0313 | Isolate and verifification by production | Unknown
3 | SIWL | WDF | MTN-INST | PRODTECH | 2100055791 | DFA07 ESDV-45007 falty indication | Mat for Mnt Inst Henrik Venø |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-10-15 | 2022-01-13 | 10 |  |  | DF /A /37/DFAA-ESDV-45007 | Mat for Mnt Inst Henrik Venø | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100055791 | DFA07 ESDV-45007 falty indication | Mat for Mnt Inst Henrik Venø |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-10-15 | 2022-01-13 | 20 |  |  | DF /A /37/DFAA-ESDV-45007 | Mat for Mnt Inst Henrik Venø | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100055791 | DFA07 ESDV-45007 falty indication | Mat for Mnt Inst Henrik Venø |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-10-15 | 2022-01-13 | 70 |  |  | DF /A /37/DFAA-ESDV-45007 | Mat for Mnt Inst Henrik Venø | Unknown
3 | SIWL | WDF | MTN-INST | MTN-MECH | 2100055791 | DFA07 ESDV-45007 falty indication | Mat for Mnt Inst Henrik Venø |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-10-15 | 2022-01-13 | 71 |  |  | DF /A /37/DFAA-ESDV-45007 | Mat for Mnt Inst Henrik Venø | Unknown
3 | SIWL | WDF | MTN-INST | PRODTECH | 2100055791 | DFA07 ESDV-45007 falty indication | Mat for Mnt Inst Henrik Venø |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-10-15 | 2022-01-13 | 80 |  |  | DF /A /37/DFAA-ESDV-45007 | Mat for Mnt Inst Henrik Venø | Unknown
3 | SIWL | WDF | MTN-INST | MTN-INST | 2100055791 | DFA07 ESDV-45007 falty indication | Mat for Mnt Inst Henrik Venø |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-10-15 | 2022-01-13 | 90 |  |  | DF /A /37/DFAA-ESDV-45007 | Mat for Mnt Inst Henrik Venø | Unknown
A | DFF-GEN | WPM | MTN-MECH | PRODTECH | 2400337668 | 4Y EMER. GENERATOR F.TEST DFFA-A-1701 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 0 | Empty | 2024-06-08 | 2024-06-30 | 2024-06-08 | 2024-06-09 | 2024-06-08 | 2024-08-20 | 10 | SECE | SECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
A | DFF-GEN | WPM | MTN-MECH | MTN-MECH | 2400337668 | 4Y EMER. GENERATOR F.TEST DFFA-A-1701 | ISOLATION BY PRODUCTION | SECE | SECE | 60 | 0 | Empty | 2024-06-08 | 2024-06-30 | 2024-06-09 | 2024-06-24 | 2024-06-08 | 2024-08-20 | 20 | SECE | SECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
A | DFF-GEN | WPM | MTN-MECH | MTN-INST | 2400337668 | 4Y EMER. GENERATOR F.TEST DFFA-A-1701 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | Empty | 2024-06-08 | 2024-06-30 | 2024-06-24 | 2024-06-25 | 2024-06-08 | 2024-08-20 | 30 | SECE | SECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
A | DFF-GEN | WPM | MTN-MECH | MTN-ELEC | 2400337668 | 4Y EMER. GENERATOR F.TEST DFFA-A-1701 | ISOLATION BY PRODUCTION | SECE | SECE | 16 | 0 | Empty | 2024-06-08 | 2024-06-30 | 2024-06-25 | 2024-06-29 | 2024-06-08 | 2024-08-20 | 40 | SECE | SECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
A | DFF-GEN | WPM | MTN-MECH | PRODTECH | 2400337668 | 4Y EMER. GENERATOR F.TEST DFFA-A-1701 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 0 | Empty | 2024-06-08 | 2024-06-30 | 2024-06-29 | 2024-06-30 | 2024-06-08 | 2024-08-20 | 50 | SECE | SECE | DF /F /05/DFFA-A-1701 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100076960 | DFB HVAC blower feed back faulty. | Troubleshooting |  |  | 12 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2022-12-10 | 2023-04-24 | 10 |  |  | DF /B /09/DFBA-BM-1201 | Troubleshooting | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100076960 | DFB HVAC blower feed back faulty. | Troubleshooting |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2022-12-10 | 2023-04-24 | 20 |  |  | DF /B /09/DFBA-BM-1201 | Troubleshooting | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 0 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 10 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 20 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 30 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2021-09-25 | 2021-10-15 | 40 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 50 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 60 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2021-09-25 | 2021-10-15 | 70 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 80 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 90 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2021-09-25 | 2021-10-15 | 100 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 110 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 120 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 2 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-25 | 2024-03-25 | 2021-09-25 | 2021-10-15 | 130 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 0 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 140 |  |  | DF /G /76 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055836 | DFG Cooling water pumps Olie skifte på p | Spare parts Order |  |  | 0 | 0 | Empty | 2024-03-24 | 2024-03-25 | 2024-03-24 | 2024-03-24 | 2021-09-25 | 2021-10-15 | 150 |  |  | DF /G /76 | Spare parts Order | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235640 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235640 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L02 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235640 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L02 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L02 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235640 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L02 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100089993 | HRF-0361 hose reel corroded | HRF-0361 hose reel corroded |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-15 | 2023-10-28 | 10 |  |  | DF /C /01/DFCI-HR-0361 | HRF-0361 hose reel corroded | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100075982 | DFA-10 choke zt udskiftning | Deisolate position transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-11-20 | 2023-04-04 | 10 |  |  | DF /A /55/DFAA-ZT-30010 | Deisolate position transmitter | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100075982 | DFA-10 choke zt udskiftning | Deisolate position transmitter |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-11-20 | 2023-04-04 | 20 |  |  | DF /A /55/DFAA-ZT-30010 | Deisolate position transmitter | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100075982 | DFA-10 choke zt udskiftning | Deisolate position transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-11-20 | 2023-04-04 | 30 |  |  | DF /A /55/DFAA-ZT-30010 | Deisolate position transmitter | Unknown
3 | DFA-W10 | WDF | MTN-INST | MTN-INST | 2100075982 | DFA-10 choke zt udskiftning | Deisolate position transmitter |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-11-20 | 2023-04-04 | 40 |  |  | DF /A /55/DFAA-ZT-30010 | Deisolate position transmitter | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100047740 | Slop oil Pump outlet HCV Corr sealface. | remove old Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-04-04 | 2021-05-14 | 10 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | remove old Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047740 | Slop oil Pump outlet HCV Corr sealface. | remove old Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-04-04 | 2021-05-14 | 20 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | remove old Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047740 | Slop oil Pump outlet HCV Corr sealface. | remove old Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2021-04-04 | 2021-05-14 | 30 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | remove old Valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100047740 | Slop oil Pump outlet HCV Corr sealface. | remove old Valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-04-04 | 2021-05-14 | 40 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | remove old Valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047740 | Slop oil Pump outlet HCV Corr sealface. | remove old Valve |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-04-04 | 2021-05-14 | 50 |  |  | DF /F /27/SYSTEM-27-MANUAL-VALVES | remove old Valve | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-04-17 | 2021-07-16 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 70 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-06 | 2021-04-17 | 2021-07-16 | 80 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 90 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 100 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047715 | dff-hcv-030122 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-04-17 | 2021-07-16 | 110 | AWSC | AWSC | DF /F /01/DFFA-HCV-030122 | Prepare freezing kit on site | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059773 | Change Out Light DFF Level 3 | Isolate accordingly |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-02-19 | 2022-07-19 | 10 |  |  | DF /F /61/DFFA-DP-180BA-7-F06 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059773 | Change Out Light DFF Level 3 | Isolate accordingly |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-02-19 | 2022-07-19 | 20 |  |  | DF /F /61/DFFA-DP-180BA-7-F06 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059773 | Change Out Light DFF Level 3 | Isolate accordingly |  |  | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-02-19 | 2022-07-19 | 30 |  |  | DF /F /61/DFFA-DP-180BA-7-F06 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059773 | Change Out Light DFF Level 3 | Isolate accordingly |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-02-19 | 2022-07-19 | 40 |  |  | DF /F /61/DFFA-DP-180BA-7-F06 | Isolate accordingly | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400235302 | 6M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-02 | 2023-03-18 | 10 |  |  | DF /G /07/DFGA-A-5940 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235302 | 6M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | DE-ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-02 | 2023-03-18 | 20 |  |  | DF /G /07/DFGA-A-5940 | DE-ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400235302 | 6M HYDRAULIC PACKAGE MAINT - DFGA-A-5940 | DE-ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-03-02 | 2023-03-18 | 30 |  |  | DF /G /07/DFGA-A-5940 | DE-ISOLATION BY PRODUCTION | Unknown
D | NOSD | WPM | MTN-PAIN | MTN-ROUS | 2400342414 | 1Y HOSES/ROLLERS/HANDLES MAINT - DFG | HOSES/ROLLERS/HANDLES MAINT - DFG |  |  | 6 | 9 | Empty | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-09-05 | 10 |  |  | DF /G /84 | HOSES/ROLLERS/HANDLES MAINT - DFG | Unknown
D | NOSD | WPM | PRODLABO | PRODLABO | 2400241847 | 1Y LABORATORY EQUIPMENT DAN | TL-1Y LABORATORY EQUIPMENT DAN |  |  | 1 | 0 | Empty | 2023-03-12 | 2023-03-12 | 2023-03-12 | 2023-03-12 | 2023-03-12 | 2023-04-28 | 10 |  |  | DF /C /80/DFCI-X-1390 | TL-1Y LABORATORY EQUIPMENT DAN | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400307846 | 1Y NORM EQUIPMENT MAINT - DFG | NORM EQUIPMENT MAINT - DFG |  |  | 8 | 6 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2024-02-01 | 2024-03-08 | 10 |  |  | DF /G /84 | NORM EQUIPMENT MAINT - DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047993 | PSV-410540 upstream Bleed Vlvhandle corr | Return data sheet back to onshore |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-04-23 | 2021-07-22 | 10 |  |  | DF /F /30/DFFA-PSV-410540 | Return data sheet back to onshore | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100047993 | PSV-410540 upstream Bleed Vlvhandle corr | Return data sheet back to onshore |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-04-23 | 2021-07-22 | 20 |  |  | DF /F /30/DFFA-PSV-410540 | Return data sheet back to onshore | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050104 | DFA-A-3102 Hydraulic WH cabinet leaks | PO Hytor | AWSC | AWSC | 24 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-27 | 2021-06-10 | 2021-09-08 | 10 | AWSC | AWSC | DF /A /07/DFAA-A-3102 | PO Hytor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050104 | DFA-A-3102 Hydraulic WH cabinet leaks | PO Hytor | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2021-06-10 | 2021-09-08 | 20 | AWSC | AWSC | DF /A /07/DFAA-A-3102 | PO Hytor | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-08-29 | 2024-08-29 | 2024-02-29 | 2024-07-13 | 10 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-08-29 | 2024-08-30 | 2024-02-29 | 2024-07-13 | 20 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-08-30 | 2024-08-30 | 2024-02-29 | 2024-07-13 | 30 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-08-30 | 2024-08-31 | 2024-02-29 | 2024-07-13 | 40 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-08-31 | 2024-08-31 | 2024-02-29 | 2024-07-13 | 50 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-08-31 | 2024-09-01 | 2024-02-29 | 2024-07-13 | 60 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 3 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-09-01 | 2024-09-01 | 2024-02-29 | 2024-07-13 | 70 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-09-01 | 2024-09-02 | 2024-02-29 | 2024-07-13 | 80 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 1 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-09-02 | 2024-09-02 | 2024-02-29 | 2024-07-13 | 90 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100105416 | DFF-ESDV-440004 internal leaking. | Isolate DFFA-ESDV-440004 | SECE | SECE | 2 | 0 | Empty | 2024-08-29 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2024-02-29 | 2024-07-13 | 100 | SECE | SECE | DF /F /32/DFFA-ESDV-440004 | Isolate DFFA-ESDV-440004 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100062486 | Fault finding on HT DP-1860-02 | Fault finding on HT DP-1860-02 | PCNFSCH | PCNFSCH | 1 | 1 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-02-26 | 2022-05-27 | 10 | PCNFSCH | PCNFSCH | DF /C /61/DFCC-DP-1860-02 | Fault finding on HT DP-1860-02 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100062486 | Fault finding on HT DP-1860-02 | Fault finding on HT DP-1860-02 | PCNFSCH | PCNFSCH | 6 | 14 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-02-26 | 2022-05-27 | 20 | PCNFSCH | PCNFSCH | DF /C /61/DFCC-DP-1860-02 | Fault finding on HT DP-1860-02 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100062486 | Fault finding on HT DP-1860-02 | Fault finding on HT DP-1860-02 | PCNFSCH | PCNFSCH | 1 | 1 | W15-W16 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2022-02-26 | 2022-05-27 | 30 | PCNFSCH | PCNFSCH | DF /C /61/DFCC-DP-1860-02 | Fault finding on HT DP-1860-02 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 3 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-01 | 2015-06-21 | 2015-09-19 | 10 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 0 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-01 | 2015-06-21 | 2015-09-19 | 15 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 8 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-02 | 2015-06-21 | 2015-09-19 | 20 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 12 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-03 | 2015-06-21 | 2015-09-19 | 30 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 3 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-01 | 2015-06-21 | 2015-09-19 | 35 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 3 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-03 | 2023-04-03 | 2015-06-21 | 2015-09-19 | 40 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 2 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-04 | 2023-04-04 | 2015-06-21 | 2015-09-19 | 50 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 0 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-01 | 2015-06-21 | 2015-09-19 | 60 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024158 | CMAT:Utæt rør ved hydrofore tank DFCC-V- | Set up fire guard |  |  | 0 | 0 | OIM FW 3 EXL | 2023-04-01 | 2023-04-04 | 2023-04-01 | 2023-04-01 | 2015-06-21 | 2015-09-19 | 70 |  |  | DF /C /01/DFCC-V-0301 | Set up fire guard | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004158 | Replaced by - 2300004544 | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2023-03-25 | 2023-03-25 | 2023-03-25 | 2023-03-25 | 2023-03-25 | 2025-09-10 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107864 | DFAA-HR-0348 CHANGE RUBBER HOSE 1,5" | Isolate hosereel | SECE | SECE | 1 | 0 | Empty | 2024-06-07 | 2024-06-08 | 2024-06-07 | 2024-06-08 | 2024-04-07 | 2024-08-20 | 10 | SECE | SECE | DF /A /01/DFAA-HR-0348 | Isolate hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107864 | DFAA-HR-0348 CHANGE RUBBER HOSE 1,5" | Isolate hosereel | SECE | SECE | 2 | 0 | Empty | 2024-06-07 | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-04-07 | 2024-08-20 | 20 | SECE | SECE | DF /A /01/DFAA-HR-0348 | Isolate hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100107864 | DFAA-HR-0348 CHANGE RUBBER HOSE 1,5" | Isolate hosereel | SECE | SECE | 1 | 0 | Empty | 2024-06-07 | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-04-07 | 2024-08-20 | 30 | SECE | SECE | DF /A /01/DFAA-HR-0348 | Isolate hosereel | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400263357 | 1Y CRUDE OIL PUMP MAINT-DFCI-P-3715 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2023-06-11 | 2023-07-11 | 10 |  |  | DF /C /26/DFCI-P-3715 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-INST | 2400263357 | 1Y CRUDE OIL PUMP MAINT-DFCI-P-3715 | ISOLATION BY PRODUCTION |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-31 | 2023-06-11 | 2023-07-11 | 20 |  |  | DF /C /26/DFCI-P-3715 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263357 | 1Y CRUDE OIL PUMP MAINT-DFCI-P-3715 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2023-06-11 | 2023-07-11 | 30 |  |  | DF /C /26/DFCI-P-3715 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400263357 | 1Y CRUDE OIL PUMP MAINT-DFCI-P-3715 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2023-06-11 | 2023-07-11 | 40 |  |  | DF /C /26/DFCI-P-3715 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400263357 | 1Y CRUDE OIL PUMP MAINT-DFCI-P-3715 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2023-06-11 | 2023-07-11 | 50 |  |  | DF /C /26/DFCI-P-3715 | ISOLATION BY PRODUCTION | Unknown
4 | DAN-GAS | WDF | MTN-INST | PRODTECH | 2100112077 | Slimline block internal leak | Replacing SDBB |  |  | 3 | 0 | Empty | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-06 | 2024-05-06 | 2024-06-20 | 10 |  |  | DF /F /31/DFFA-HCV-440116 | Replacing SDBB | Unknown
4 | DAN-GAS | WDF | MTN-INST | MTN-MECH | 2100112077 | Slimline block internal leak | Replacing SDBB |  |  | 2 | 0 | Empty | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-06 | 2024-05-06 | 2024-06-20 | 20 |  |  | DF /F /31/DFFA-HCV-440116 | Replacing SDBB | Unknown
4 | DAN-GAS | WDF | MTN-INST | PRODTECH | 2100112077 | Slimline block internal leak | Replacing SDBB |  |  | 3 | 0 | Empty | 2024-08-06 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2024-05-06 | 2024-06-20 | 30 |  |  | DF /F /31/DFFA-HCV-440116 | Replacing SDBB | Unknown
3 | DFF-3580 | WDF | MTN-LAGG | MTN-MECH | 2100096124 | Externally leak from spool or flange. | Erect dismantle scaffold | PCNF | PCNF | 0 | 0 | Empty | 2023-09-23 | 2023-10-04 | 2023-09-23 | 2023-09-23 | 2023-09-23 | 2024-02-05 | 10 | PCNF | PCNF | DF /F /54/DFFB-P-3580 | Erect dismantle scaffold | Unknown
3 | DFF-3580 | WDF | MTN-LAGG | WELLSUPV | 2100096124 | Externally leak from spool or flange. | Erect dismantle scaffold | PCNF | PCNF | 24 | 24 | Empty | 2023-09-23 | 2023-10-04 | 2023-09-23 | 2023-09-26 | 2023-09-23 | 2024-02-05 | 20 | PCNF | PCNF | DF /F /54/DFFB-P-3580 | Erect dismantle scaffold | Unknown
3 | DFF-3580 | WDF | MTN-LAGG | MTN-RIGG | 2100096124 | Externally leak from spool or flange. | Erect dismantle scaffold | PCNF | PCNF | 12 | 12 | Empty | 2023-09-23 | 2023-10-04 | 2023-09-26 | 2023-09-28 | 2023-09-23 | 2024-02-05 | 30 | PCNF | PCNF | DF /F /54/DFFB-P-3580 | Erect dismantle scaffold | Unknown
3 | DFF-3580 | WDF | MTN-LAGG | MTN-ROPE | 2100096124 | Externally leak from spool or flange. | Erect dismantle scaffold | PCNF | PCNF | 45 | 45 | Empty | 2023-09-23 | 2023-10-04 | 2023-09-29 | 2023-10-04 | 2023-09-23 | 2024-02-05 | 40 | PCNF | PCNF | DF /F /54/DFFB-P-3580 | Erect dismantle scaffold | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400346576 | 1Y CHEM DISTR PANEL MAINT-DFFA-A-39708 | CHEM DISTR PANEL MAINT-DFFA-A-39708 |  |  | 16 | 0 | Empty | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-10-01 | 10 |  |  | DF /F /75/DFFA-A-39708 | CHEM DISTR PANEL MAINT-DFFA-A-39708 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075980 | ANOP Externale leak from bleed valve by | Repair valve | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2022-10-10 | 2022-11-24 | 10 | SECE | SECE | DF /F /34/DFFA-EP-3803 | Repair valve | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235772 | 4Y 400V N-SWB MAINT-DFFB-N-1828 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235772 | 4Y 400V N-SWB MAINT-DFFB-N-1828 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235772 | 4Y 400V N-SWB MAINT-DFFB-N-1828 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235772 | 4Y 400V N-SWB MAINT-DFFB-N-1828 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-06 | 2023-12-19 | 10 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 1.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-06 | 2023-12-19 | 20 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 3.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-08-06 | 2023-12-19 | 30 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-08-06 | 2023-12-19 | 40 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-08-06 | 2023-12-19 | 50 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-08-06 | 2023-12-19 | 60 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200014807 | AIT-350507 need to be change out | Cut out brackets |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-08-06 | 2023-12-19 | 70 |  |  | DF /F /54/DFFA-AIT-350507 | Cut out brackets | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036335 | Needle valve stuck for LT-34011 | Inhibit level transmitter |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-09-03 | 2020-12-02 | 10 |  |  | DF /C /20/DFCI-LT-34011 | Inhibit level transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036335 | Needle valve stuck for LT-34011 | Inhibit level transmitter |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-09-03 | 2020-12-02 | 20 |  |  | DF /C /20/DFCI-LT-34011 | Inhibit level transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036335 | Needle valve stuck for LT-34011 | Inhibit level transmitter |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-09-03 | 2020-12-02 | 30 |  |  | DF /C /20/DFCI-LT-34011 | Inhibit level transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036335 | Needle valve stuck for LT-34011 | Inhibit level transmitter |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2020-09-03 | 2020-12-02 | 40 |  |  | DF /C /20/DFCI-LT-34011 | Inhibit level transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036335 | Needle valve stuck for LT-34011 | Inhibit level transmitter |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-09-03 | 2020-12-02 | 50 |  |  | DF /C /20/DFCI-LT-34011 | Inhibit level transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036335 | Needle valve stuck for LT-34011 | Inhibit level transmitter |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2020-09-03 | 2020-12-02 | 60 |  |  | DF /C /20/DFCI-LT-34011 | Inhibit level transmitter | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100027730 | SMAT:Replace DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | AWSC | AWSC | 5 | 0 | Empty | 2024-08-01 | 2024-08-09 | 2024-08-01 | 2024-08-02 | 2018-10-13 | 2019-01-11 | 10 | AWSC | AWSC | DF /F /27/DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-PIPF | 2100027730 | SMAT:Replace DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | AWSC | AWSC | 6.700000000000000177635683938 | 0 | Empty | 2024-08-01 | 2024-08-09 | 2024-08-01 | 2024-08-01 | 2018-10-13 | 2019-01-11 | 15 | AWSC | AWSC | DF /F /27/DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100027730 | SMAT:Replace DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | AWSC | AWSC | 60.29999999999999715782905694 | 0 | Empty | 2024-08-01 | 2024-08-09 | 2024-08-02 | 2024-08-09 | 2018-10-13 | 2019-01-11 | 20 | AWSC | AWSC | DF /F /27/DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-PIPF | 2100027730 | SMAT:Replace DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | AWSC | AWSC | 60.29999999999999715782905694 | 0 | Empty | 2024-08-01 | 2024-08-09 | 2024-08-02 | 2024-08-05 | 2018-10-13 | 2019-01-11 | 30 | AWSC | AWSC | DF /F /27/DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100027730 | SMAT:Replace DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | AWSC | AWSC | 5 | 0 | Empty | 2024-08-01 | 2024-08-09 | 2024-08-05 | 2024-08-06 | 2018-10-13 | 2019-01-11 | 40 | AWSC | AWSC | DF /F /27/DFFA-HCV-500729 | L2 Replace DFFA-HCV-500729 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235727 | 4Y 380V E-SWB MAINT DFCI-N-1812-R08 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235727 | 4Y 380V E-SWB MAINT DFCI-N-1812-R08 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 8 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235727 | 4Y 380V E-SWB MAINT DFCI-N-1812-R08 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235727 | 4Y 380V E-SWB MAINT DFCI-N-1812-R08 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235727 | 4Y 380V E-SWB MAINT DFCI-N-1812-R08 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
3 | DFF-1610 | WDF | MTN-TURB | PRODTECH | 2100093122 | GT-1610 High T5 when starting on diesel | De-isolate turbine |  |  | 2 | 0 | W45-46 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-08-02 | 2023-12-15 | 10 |  |  | DF /F /60/DFFA-GT-1610 | De-isolate turbine | Unknown
3 | DFF-1610 | WDF | MTN-TURB | MTN-TURB | 2100093122 | GT-1610 High T5 when starting on diesel | De-isolate turbine |  |  | 6 | 0 | W45-46 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-08-02 | 2023-12-15 | 20 |  |  | DF /F /60/DFFA-GT-1610 | De-isolate turbine | Unknown
3 | DFF-1610 | WDF | MTN-TURB | PRODTECH | 2100093122 | GT-1610 High T5 when starting on diesel | De-isolate turbine |  |  | 2 | 0 | W45-46 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-08-02 | 2023-12-15 | 30 |  |  | DF /F /60/DFFA-GT-1610 | De-isolate turbine | Unknown
3 | DFG-1640 | WGN | MTN-INST | MTN-INST | 2200009683 | DFGA-G-1640 barriers | Update inclosed drawings |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-02-13 | 2022-03-25 | 10 |  |  | DF /G /60/DFGA-CP-1640 | Update inclosed drawings | Unknown
3 | DFG-1640 | WGN | MTN-INST | PRODTECH | 2200009683 | DFGA-G-1640 barriers | Update inclosed drawings |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-02-13 | 2022-03-25 | 20 |  |  | DF /G /60/DFGA-CP-1640 | Update inclosed drawings | Unknown
3 | DFG-1640 | WGN | MTN-INST | MTN-INST | 2200009683 | DFGA-G-1640 barriers | Update inclosed drawings |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2022-02-13 | 2022-03-25 | 30 |  |  | DF /G /60/DFGA-CP-1640 | Update inclosed drawings | Unknown
3 | DFG-1640 | WGN | MTN-INST | MTN-TELE | 2200009683 | DFGA-G-1640 barriers | Update inclosed drawings |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2022-02-13 | 2022-03-25 | 40 |  |  | DF /G /60/DFGA-CP-1640 | Update inclosed drawings | Unknown
3 | DFG-1640 | WGN | MTN-INST | MTN-INST | 2200009683 | DFGA-G-1640 barriers | Update inclosed drawings |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2022-02-13 | 2022-03-25 | 50 |  |  | DF /G /60/DFGA-CP-1640 | Update inclosed drawings | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018138 | Replace Transformer relay 1841-M115 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M115-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018138 | Replace Transformer relay 1841-M115 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M115-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018138 | Replace Transformer relay 1841-M115 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M115-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018138 | Replace Transformer relay 1841-M115 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M115-02 | Isolation of Breaker section | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-29 | 2024-07-31 | 2021-02-05 | 2021-03-17 | 10 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-07-31 | 2024-08-01 | 2021-02-05 | 2021-03-17 | 20 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-01 | 2021-02-05 | 2021-03-17 | 30 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-01 | 2024-08-02 | 2021-02-05 | 2021-03-17 | 40 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-02 | 2024-08-03 | 2021-02-05 | 2021-03-17 | 50 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-03 | 2021-02-05 | 2021-03-17 | 60 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-03 | 2024-08-04 | 2021-02-05 | 2021-03-17 | 70 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-04 | 2024-08-06 | 2021-02-05 | 2021-03-17 | 80 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-06 | 2024-08-07 | 2021-02-05 | 2021-03-17 | 90 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-07 | 2021-02-05 | 2021-03-17 | 100 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-07 | 2024-08-08 | 2021-02-05 | 2021-03-17 | 110 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2021-02-05 | 2021-03-17 | 120 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044854 | Actuator for DFGA-PCV-500877 hole in top | Isolate PCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-10 | 2024-08-08 | 2024-08-10 | 2021-02-05 | 2021-03-17 | 130 |  |  | DF /G /27/DFGA-PCV-500877 | Isolate PCV | Unknown
3 | DFG-IPHP | WGN | MTN-MECH | MTN-MECH | 2200015655 | DFG; Rupture disc Primary line upgrade. | DFG; Rupture disc Primary line upgrade | SCH | SCH | 0 | 8 | W23-W24 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2024-06-06 | 2023-10-23 | 2024-03-06 | 10 | SCH | SCH | DF /G /31/DFGA-A-4302 | DFG; Rupture disc Primary line upgrade | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100085363 | Faultfinding on light fixtures lys DP-18 | Isolate and prove dead |  |  | 48 | 0 | W27-W28 | 2024-07-29 | 2024-08-19 | 2024-07-29 | 2024-08-10 | 2023-03-31 | 2023-08-13 | 10 |  |  | DF /C /61/DFCI-DP-1807-08 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085363 | Faultfinding on light fixtures lys DP-18 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-08-19 | 2024-08-10 | 2024-08-10 | 2023-03-31 | 2023-08-13 | 20 |  |  | DF /C /61/DFCI-DP-1807-08 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085363 | Faultfinding on light fixtures lys DP-18 | Isolate and prove dead |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-19 | 2024-08-10 | 2024-08-13 | 2023-03-31 | 2023-08-13 | 30 |  |  | DF /C /61/DFCI-DP-1807-08 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100085363 | Faultfinding on light fixtures lys DP-18 | Isolate and prove dead |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-08-19 | 2024-08-13 | 2024-08-13 | 2023-03-31 | 2023-08-13 | 40 |  |  | DF /C /61/DFCI-DP-1807-08 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100085363 | Faultfinding on light fixtures lys DP-18 | Isolate and prove dead |  |  | 24 | 0 | W27-W28 | 2024-07-29 | 2024-08-19 | 2024-08-13 | 2024-08-19 | 2023-03-31 | 2023-08-13 | 50 |  |  | DF /C /61/DFCI-DP-1807-08 | Isolate and prove dead | Unknown
4 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-02 | 2021-09-12 | 2022-02-09 | 10 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-INST | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-03 | 2021-09-12 | 2022-02-09 | 20 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-RIGG | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-03 | 2025-01-03 | 2021-09-12 | 2022-02-09 | 30 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-03 | 2025-01-04 | 2021-09-12 | 2022-02-09 | 40 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-RIGG | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2025-01-05 | 2021-09-12 | 2022-02-09 | 50 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-06 | 2021-09-12 | 2022-02-09 | 60 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-INST | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2025-01-07 | 2021-09-12 | 2022-02-09 | 70 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-INST | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-07 | 2021-09-12 | 2022-02-09 | 80 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-08 | 2021-09-12 | 2022-02-09 | 90 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | PRODTECH | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-08 | 2021-09-12 | 2022-02-09 | 100 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | DFE-OIL | WDF | MTN-MECH | MTN-MECH | 2100051374 | BDV-33010 DFE Prod.åbner ikke helt. | Rigging assist.Rig in/out | SECE | SECE | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-09 | 2021-09-12 | 2022-02-09 | 110 | SECE | SECE | DF /E /10/DFEZ-BDV-33010 | Rigging assist.Rig in/out | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100102278 | Replace filter and priming pump on MOB b | Replace filter and priming pump |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-05-18 | 2026-11-04 | 10 |  |  | DF /C /02/DFCI-X-0706 | Replace filter and priming pump | Unknown
4 | DAB-OIL | WDF | MTN-MECH | PRODTECH | 2100023913 | Exchange 2" bypass valve over hcv-380229 | L3 Isolate equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2019-05-15 | 2019-10-12 | 10 | AWSC | AWSC | DF /F /12 | L3 Isolate equipment | Unknown
4 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100023913 | Exchange 2" bypass valve over hcv-380229 | L3 Isolate equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-05-15 | 2019-10-12 | 20 | AWSC | AWSC | DF /F /12 | L3 Isolate equipment | Unknown
4 | DAB-OIL | WDF | MTN-MECH | PRODTECH | 2100023913 | Exchange 2" bypass valve over hcv-380229 | L3 Isolate equipment | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2019-05-15 | 2019-10-12 | 30 | AWSC | AWSC | DF /F /12 | L3 Isolate equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 8 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 20 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 20 | 24 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 30 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 20 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 40 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 4 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 50 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 8 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 60 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 70 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 30 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 80 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 30 | 10 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 90 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 100 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 30 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 110 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 120 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 30 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 130 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 4 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 140 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 20 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 150 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 160 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 10 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 170 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 16 | 16 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 180 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 190 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 12 | 0 | W17-W18 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2021-10-18 | 2022-03-17 | 200 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100053023 | DFG Hazz dræn pumpe 5041 | Install temporary pump MN 1200285 | PCNF | PCNF | 4 | 4 | W17-W18 | 2024-10-05 | 2024-10-05 | 2023-09-11 | 2023-09-19 | 2021-10-18 | 2022-03-17 | 210 | PCNF | PCNF | DF /G /28/DFGA-P-5041 | Install temporary pump MN 1200285 | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 8 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-15 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 10 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | PRODTECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-17 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 20 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 30 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-RIGG | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-18 | 2024-09-19 | 2021-02-18 | 2021-05-19 | 40 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-19 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 50 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-RIGG | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 60 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-20 | 2024-09-21 | 2021-02-18 | 2021-05-19 | 70 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-21 | 2024-09-23 | 2021-02-18 | 2021-05-19 | 80 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 4 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 90 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-INST | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 3 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 100 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-24 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 110 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | PRODTECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 2 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 120 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFG-1640 | WDF | MTN-MECH | MTN-MECH | 2100044916 | DFG PCV-530040 Dårlig integritet | Isolate PCV |  |  | 6 | 0 | Mat ETA 20/9 | 2024-09-15 | 2024-09-27 | 2024-09-25 | 2024-09-27 | 2021-02-18 | 2021-05-19 | 130 |  |  | DF /G /76/DFGA-PCV-530040 | Isolate PCV | Unknown
3 | DFF-5702 | WDF | MTN-MECH | MTN-MECH | 2100076544 | ESDV-570224 leak fra styrepanel. | Change Gauge and refit / change coupling |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-11-12 | 2023-03-27 | 10 |  |  | DF /F /70/DFFA-ESDV-570224 | Change Gauge and refit / change coupling | Unknown
3 | DFF-5702 | WDF | MTN-MECH | MTN-MECH | 2100076544 | ESDV-570224 leak fra styrepanel. | Change Gauge and refit / change coupling |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-11-12 | 2023-03-27 | 20 |  |  | DF /F /70/DFFA-ESDV-570224 | Change Gauge and refit / change coupling | Unknown
3 | DFF-5702 | WDF | MTN-MECH | MTN-MECH | 2100076544 | ESDV-570224 leak fra styrepanel. | Change Gauge and refit / change coupling |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-11-12 | 2023-03-27 | 30 |  |  | DF /F /70/DFFA-ESDV-570224 | Change Gauge and refit / change coupling | Unknown
3 | DFF-5702 | WDF | MTN-MECH | MTN-MECH | 2100076544 | ESDV-570224 leak fra styrepanel. | Change Gauge and refit / change coupling |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-11-12 | 2023-03-27 | 40 |  |  | DF /F /70/DFFA-ESDV-570224 | Change Gauge and refit / change coupling | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342431 | 1Y CATALYTIC GAS DETECTORS - DFC ROOF | CATALYTIC GAS DETECTORS CHECK | SECE | SECE | 19 | 0 | W31-W32 | 2024-08-11 | 2024-08-15 | 2024-08-11 | 2024-08-15 | 2024-07-29 | 2024-08-28 | 10 | SECE | SECE | DF /C /03/FGS-DETECTORS | CATALYTIC GAS DETECTORS CHECK | Unknown
3 | DFF-IPHP | WDF | MTN-TURB | MTN-MECH | 2100074262 | Seal gas PCV-441326 Fail to close | Seal gas PCV-441326 "Calibrating" |  |  | 12 | 0 | W33-W34 | 2024-08-14 | 2024-08-16 | 2024-08-14 | 2024-08-16 | 2022-10-20 | 2023-03-04 | 10 |  |  | DF /F /31/DFFA-PCV-441326 | Seal gas PCV-441326 "Calibrating" | Unknown
B | NOSD | WPM | UNKNOWN | MTN-MECH | 2400190550 | 6M DFFA-FP-3103, WELLHEAD CONTROL PANEL. | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 0 | 0 | Empty | 2022-09-17 | 2022-09-21 | 2022-09-17 | 2022-09-17 | 2022-03-06 | 2022-03-22 | 1 |  |  | DF /F /07/WELLHEAD-CONTROL-PANELS | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
B | NOSD | WPM | UNKNOWN | MTN-MECH | 2400190550 | 6M DFFA-FP-3103, WELLHEAD CONTROL PANEL. | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 14 | 0 | Empty | 2022-09-17 | 2022-09-21 | 2022-09-17 | 2022-09-20 | 2022-03-06 | 2022-03-22 | 10 |  |  | DF /F /07/WELLHEAD-CONTROL-PANELS | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
B | NOSD | WPM | UNKNOWN | MTN-INST | 2400190550 | 6M DFFA-FP-3103, WELLHEAD CONTROL PANEL. | GENERAL INFO VEDLIGEHOLD UDEN ASSU |  |  | 3.5 | 0 | Empty | 2022-09-17 | 2022-09-21 | 2022-09-20 | 2022-09-21 | 2022-03-06 | 2022-03-22 | 12 |  |  | DF /F /07/WELLHEAD-CONTROL-PANELS | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322307 | DFG-82-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /82/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 13 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 4 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-RIGG | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 13 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 5 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 13 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 6 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 36 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 10 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-RIGG | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 16 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 20 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 3 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 30 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 12 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 35 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-PIPF | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 16 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 40 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-RIGG | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 6 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 50 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 16 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2016-05-25 | 2016-06-14 | 54 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 0 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-03 | 2016-05-25 | 2016-06-14 | 55 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 16 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-03 | 2025-01-05 | 2016-05-25 | 2016-06-14 | 56 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 10 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2016-05-25 | 2016-06-14 | 57 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 3 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2016-05-25 | 2016-06-14 | 60 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-PIPF | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 3 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2016-05-25 | 2016-06-14 | 70 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-RIGG | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 10 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-05 | 2016-05-25 | 2016-06-14 | 80 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 27 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2016-05-25 | 2016-06-14 | 90 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100025337 | DFC HCV-03067 LV05 Intern læk | NDT of pipe | PCNFAWSC | PCNFAWSC | 0 | 0 | OIM FW INL | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-01 | 2016-05-25 | 2016-06-14 | 100 | PCNFAWSC | PCNFAWSC | DF /C /01/DFCM-HCV-03067 | NDT of pipe | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 0 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-10 | 2024-04-10 | 2019-06-04 | 2019-07-14 | 10 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 17.399999999999998578914528472 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2022-06-13 | 2022-06-15 | 2019-06-04 | 2019-07-14 | 170 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 13 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2022-06-15 | 2022-06-15 | 2019-06-04 | 2019-07-14 | 180 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 17.399999999999998578914528472 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2022-06-15 | 2022-06-15 | 2019-06-04 | 2019-07-14 | 190 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | INP-SITE | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 0 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-10 | 2024-04-10 | 2019-06-04 | 2019-07-14 | 200 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 0 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-10 | 2024-04-10 | 2019-06-04 | 2019-07-14 | 210 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 80 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-10 | 2024-04-14 | 2019-06-04 | 2019-07-14 | 220 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 75 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-14 | 2024-04-20 | 2019-06-04 | 2019-07-14 | 230 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 16 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-20 | 2024-04-21 | 2019-06-04 | 2019-07-14 | 240 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 25 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-21 | 2024-04-24 | 2019-06-04 | 2019-07-14 | 250 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 0 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-04 | 2019-07-14 | 260 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022923 | FFSPR: Utility & Instrument Air Batch-03 | Build scaffold for reaching spool | PCNF | PCNF | 0 | 0 | CNF WO ref. IRP project | 2024-04-10 | 2024-04-24 | 2024-04-24 | 2024-04-24 | 2019-06-04 | 2019-07-14 | 270 | PCNF | PCNF | DF /A /07 | Build scaffold for reaching spool | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2020-03-12 | 2020-08-09 | 10 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 3 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2020-03-12 | 2020-08-09 | 20 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 3 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2020-03-12 | 2020-08-09 | 30 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 6 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2020-03-12 | 2020-08-09 | 40 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-12 | 2020-08-09 | 50 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 1 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-12 | 2020-08-09 | 60 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | MTN-PIPF | 2100026483 | Diverse utæt fittings (INST-TUBF) | Replace fittings for PI-393502 |  |  | 0 | 0 | Empty | 2024-08-25 | 2024-08-26 | 2024-08-25 | 2024-08-25 | 2020-03-12 | 2020-08-09 | 70 |  |  | DF /F /75/DFFA-PRV-393400 | Replace fittings for PI-393502 | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100070240 | DFBA-SOV-57302 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 10 | SECE | SECE | DF /B /70/DFBA-ESDV-57302 | Isolate solenoid valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070240 | DFBA-SOV-57302 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 20 | SECE | SECE | DF /B /70/DFBA-ESDV-57302 | Isolate solenoid valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070240 | DFBA-SOV-57302 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 30 | SECE | SECE | DF /B /70/DFBA-ESDV-57302 | Isolate solenoid valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070240 | DFBA-SOV-57302 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 40 | SECE | SECE | DF /B /70/DFBA-ESDV-57302 | Isolate solenoid valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100070240 | DFBA-SOV-57302 is about to rust away. | Isolate solenoid valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 50 | SECE | SECE | DF /B /70/DFBA-ESDV-57302 | Isolate solenoid valve (SDV) | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235571 | 4Y 400V N-DP-MAINT-DFGA-LP-1850 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-LP-1850 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235571 | 4Y 400V N-DP-MAINT-DFGA-LP-1850 | ISOLATION ELECTRICAL | AWSC | AWSC | 21 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-LP-1850 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235571 | 4Y 400V N-DP-MAINT-DFGA-LP-1850 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-27 | 2024-09-29 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-LP-1850 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235571 | 4Y 400V N-DP-MAINT-DFGA-LP-1850 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-LP-1850 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 2 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | 2020-03-20 | 2020-04-29 | 10 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 3 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | 2020-03-20 | 2020-04-29 | 20 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 1 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | 2020-03-20 | 2020-04-29 | 30 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 1 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2020-03-20 | 2020-04-29 | 40 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 2 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2020-03-20 | 2020-04-29 | 50 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 1 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | 2020-03-20 | 2020-04-29 | 60 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100029428 | DFA extension panel def. styreventil | Isolate control valve acc. to PID |  |  | 0 | 0 | Empty | 2024-10-01 | 2024-10-02 | 2024-10-01 | 2024-10-01 | 2020-03-20 | 2020-04-29 | 70 |  |  | DF /A /07/DFAA-A-3102A | Isolate control valve acc. to PID | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008775 | Replace DFBA-PSV-59073 | Prod Assist (breaking containment) |  |  | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-08 | 2024-05-06 | 2024-05-06 | 2022-03-28 | 2022-11-23 | 10 |  |  | DF /B /07/DFBA-PSV-59073 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008775 | Replace DFBA-PSV-59073 | Prod Assist (breaking containment) |  |  | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-08 | 2024-05-06 | 2024-05-06 | 2022-03-28 | 2022-11-23 | 20 |  |  | DF /B /07/DFBA-PSV-59073 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008775 | Replace DFBA-PSV-59073 | Prod Assist (breaking containment) |  |  | 4 | 12 | W19-W20 | 2024-05-06 | 2024-05-08 | 2024-05-07 | 2024-05-07 | 2022-03-28 | 2022-11-23 | 30 |  |  | DF /B /07/DFBA-PSV-59073 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008775 | Replace DFBA-PSV-59073 | Prod Assist (breaking containment) |  |  | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2022-03-28 | 2022-11-23 | 40 |  |  | DF /B /07/DFBA-PSV-59073 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008775 | Replace DFBA-PSV-59073 | Prod Assist (breaking containment) |  |  | 0 | 0 | W19-W20 | 2024-05-06 | 2024-05-08 | 2024-05-08 | 2024-05-08 | 2022-03-28 | 2022-11-23 | 50 |  |  | DF /B /07/DFBA-PSV-59073 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2024-03-22 | 2024-08-04 | 10 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 6 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2024-03-22 | 2024-08-04 | 20 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-31 | 2024-03-22 | 2024-08-04 | 30 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-07-31 | 2024-03-22 | 2024-08-04 | 40 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-07-31 | 2024-03-22 | 2024-08-04 | 50 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2024-03-22 | 2024-08-04 | 60 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-01 | 2024-03-22 | 2024-08-04 | 70 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2024-03-22 | 2024-08-04 | 71 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2024-03-22 | 2024-08-04 | 75 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2024-03-22 | 2024-08-04 | 80 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100106933 | DFF HP-sep sandtrap XCV can't close 100% | Troubleshoot XCV can't close 100% |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2024-03-22 | 2024-08-04 | 90 |  |  | DF /F /20/DFFA-XCV-340515 | Troubleshoot XCV can't close 100% | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322245 | DFB-54-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /54/P-G | PIPING INSPECTION AND REPORTING | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 10 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 20 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 30 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 40 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 50 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 60 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 70 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 80 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 90 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 100 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004452 | DK40 - CONSUMABLE CAMPAIGN CoW23 - PROD. | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO |  |  | 0 | 0 | Empty | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2023-07-08 | 2025-12-24 | 110 |  |  | DF /C /84 | DK40 - MATERIAL INTERSTAGE MANIF.PBU PRO | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023562 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 3.399999999999999911182158029 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-13 | 2018-03-10 | 2018-06-08 | 10 |  |  | DF /F /79 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100023562 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 20 |  |  | DF /F /79 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023562 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 1 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 25 |  |  | DF /F /79 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023562 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-14 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 30 |  |  | DF /F /79 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023562 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-15 | 2023-02-15 | 2018-03-10 | 2018-06-08 | 40 |  |  | DF /F /79 | permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100023562 | DFF installation of insulation HTJB 1802 | permit prep |  |  | 8 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-15 | 2023-02-16 | 2018-03-10 | 2018-06-08 | 50 |  |  | DF /F /79 | permit prep | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093110 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-27 | 2023-12-09 | 10 |  |  | DF /B /03/DFBA-PB-02021 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093110 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-27 | 2023-12-09 | 20 |  |  | DF /B /03/DFBA-PB-02021 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093110 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 30 |  |  | DF /B /03/DFBA-PB-02021 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093110 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 40 |  |  | DF /B /03/DFBA-PB-02021 | Isolate PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093110 | old ESD 1 PB replace with new MEDC type | Isolate PB |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 50 |  |  | DF /B /03/DFBA-PB-02021 | Isolate PB | Unknown
3 | NOSD | WRO | MTN-INST | MTN-INST | 2300007625 | Alternative IR Gas Detectors for FG | Alternative IR Gas Detectors for FG |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-02-25 | 2024-07-09 | 10 |  |  | DF /A /54/INSTRUMENTS | Alternative IR Gas Detectors for FG | Unknown
3 | NOSD | WRO | MTN-INST | MTN-INST | 2300007625 | Alternative IR Gas Detectors for FG | Alternative IR Gas Detectors for FG |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-02-25 | 2024-07-09 | 20 |  |  | DF /A /54/INSTRUMENTS | Alternative IR Gas Detectors for FG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024959 | Fabricate consol and fasten DFFA-XCV-301 | L3 Fabricate consol and fasten DFFA-XCV- |  |  | 5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2019-04-17 | 2019-07-16 | 10 |  |  | DF /F /10/DFFA-XCV-301303 | L3 Fabricate consol and fasten DFFA-XCV- | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 10 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 20 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 30 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 40 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 50 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 60 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000770 | WSUIT 01.01.19 TIL 31.12.19 | WSUIT 01.03.20 TIL 31.12.20 |  |  | 0 | 0 | Empty | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2019-12-31 | 2019-12-31 | 70 |  |  | DF /C | WSUIT 01.03.20 TIL 31.12.20 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400206425 | 6M SDV LUB/MAINT FUEL GAS - DFG | SDV LUB/INSP FUEL GAS - DFG |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-07-16 | 2022-08-01 | 10 |  |  | DF /G /03/SDV-VALVES | SDV LUB/INSP FUEL GAS - DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046223 | hydraulic leakage on XCV-301328 | Production Assistance if necessary |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-03-08 | 2021-04-17 | 10 |  |  | DF /F /10/DFFA-XCV-301328 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100046223 | hydraulic leakage on XCV-301328 | Production Assistance if necessary |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-03-08 | 2021-04-17 | 20 |  |  | DF /F /10/DFFA-XCV-301328 | Production Assistance if necessary | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100046223 | hydraulic leakage on XCV-301328 | Production Assistance if necessary |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-03-08 | 2021-04-17 | 30 |  |  | DF /F /10/DFFA-XCV-301328 | Production Assistance if necessary | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400337683 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-8 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 28 | 0 | Empty | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-06-25 | 2024-06-24 | 2024-08-25 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-8 | ATEX EQUIPMENT INSPECTION | Unknown
A | NOSD | WPM | VEN-INSP | MTN-MECH | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 100 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-05-01 | 2024-05-25 | 2024-10-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 100 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-05-26 | 2024-06-19 | 2024-10-01 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 10 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-06-20 | 2024-06-22 | 2024-10-01 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 100 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-06-22 | 2024-07-17 | 2024-10-01 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PIPF | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-07-17 | 2024-07-17 | 2024-10-01 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-07-17 | 2024-07-17 | 2024-10-01 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-07-17 | 2024-07-17 | 2024-10-01 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PAIN | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 100 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-07-17 | 2024-07-28 | 2024-10-01 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 15 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-07-28 | 2024-07-31 | 2024-10-01 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-07-31 | 2024-08-02 | 2024-10-01 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400291988 | PVI Major - DFFA-V-5019 | PO BETECH | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-10-01 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5019 | PO BETECH | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325740 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /F /75/DFFA-A-39705 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054335 | DFFA-C-5401 Defekt drain SOV for INST ai | Isolate SOV 540110/540111 on DFFA-C-5401 |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-26 | 2021-09-16 | 2021-12-15 | 10 |  |  | DF /F /07/DFFA-C-5401 | Isolate SOV 540110/540111 on DFFA-C-5401 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100054335 | DFFA-C-5401 Defekt drain SOV for INST ai | Isolate SOV 540110/540111 on DFFA-C-5401 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-26 | 2024-08-27 | 2021-09-16 | 2021-12-15 | 20 |  |  | DF /F /07/DFFA-C-5401 | Isolate SOV 540110/540111 on DFFA-C-5401 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054335 | DFFA-C-5401 Defekt drain SOV for INST ai | Isolate SOV 540110/540111 on DFFA-C-5401 |  |  | 10 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-27 | 2024-08-29 | 2021-09-16 | 2021-12-15 | 30 |  |  | DF /F /07/DFFA-C-5401 | Isolate SOV 540110/540111 on DFFA-C-5401 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100054335 | DFFA-C-5401 Defekt drain SOV for INST ai | Isolate SOV 540110/540111 on DFFA-C-5401 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-30 | 2024-08-29 | 2024-08-30 | 2021-09-16 | 2021-12-15 | 40 |  |  | DF /F /07/DFFA-C-5401 | Isolate SOV 540110/540111 on DFFA-C-5401 | Unknown
3 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100079920 | utætte rør under blocken | Isolate transmiiter |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-05 | 2023-06-20 | 10 |  |  | DF /G /31/DFGA-PDIT-440430 | Isolate transmiiter | Unknown
3 | DFG-IPHP | WDF | MTN-INST | PRODTECH | 2100079920 | utætte rør under blocken | Isolate transmiiter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-05 | 2023-06-20 | 20 |  |  | DF /G /31/DFGA-PDIT-440430 | Isolate transmiiter | Unknown
3 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100079920 | utætte rør under blocken | Isolate transmiiter |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-05 | 2023-06-20 | 30 |  |  | DF /G /31/DFGA-PDIT-440430 | Isolate transmiiter | Unknown
3 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100079920 | utætte rør under blocken | Isolate transmiiter |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-02-05 | 2023-06-20 | 40 |  |  | DF /G /31/DFGA-PDIT-440430 | Isolate transmiiter | Unknown
3 | DFG-IPHP | WDF | MTN-INST | MTN-INST | 2100079920 | utætte rør under blocken | Isolate transmiiter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-02-05 | 2023-06-20 | 50 |  |  | DF /G /31/DFGA-PDIT-440430 | Isolate transmiiter | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300005428 | DK40 - REPLACED BY 2300008269 | DK40 - CONSUMABLE PROD - PPE |  |  | 0 | 0 | Empty | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2023-10-16 | 2026-04-03 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - PPE | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339211 | DFE_1Y_30600 INT STRUCT INSP - GVI | DFE_1Y_30600 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /86/EL_30600 (MAIN DECK) | DFE_1Y_30600 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 1 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-20 | 2019-09-18 | 10 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 1 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-20 | 2019-09-18 | 20 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 4 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-20 | 2019-09-18 | 30 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 1 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-20 | 2019-09-18 | 40 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 1 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-20 | 2019-09-18 | 50 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 1 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-06-20 | 2019-09-18 | 60 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 0 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2022-11-04 | 2023-10-27 | 2019-06-20 | 2019-09-18 | 70 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023243 | DFA/78: Replace Relief valve for starter | Re-order mats | PCNF | PCNF | 0 | 1 | Empty | 2024-07-29 | 2024-07-29 | 2022-11-04 | 2023-10-27 | 2019-06-20 | 2019-09-18 | 80 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Re-order mats | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200018658 | Miele landry maschine drainvalve defect | Miele landry maschine drainvalve defect |  |  | 2 | 0 | Empty | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-07-12 | 2024-11-24 | 10 |  |  | DF /C /82/DFCC-X-13005 | Miele landry maschine drainvalve defect | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235630 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235630 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 39 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-09-22 | 2024-10-01 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235630 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-10-02 | 2024-10-05 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235630 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-20 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-20 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193031 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /F /75/DFFA-A-39705 | 1Y CHEMICAL DISTRIBUTION PANEL A-39705 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329499 | 6M SDV LUB/MAINT TSEP - DFC | SDV LUB/INSP TSEP - DFC |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-30 | 2024-06-15 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP TSEP - DFC | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-MECH | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 10 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 8 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 20 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 30 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-RIGG | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 31 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-LAGG | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 40 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-LAGG | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 50 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | PRODTECH | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2024-08-17 | 60 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 12 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-04 | 2024-04-05 | 2024-04-04 | 2024-08-17 | 70 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-RIGG | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-05 | 2024-04-05 | 2024-04-04 | 2024-08-17 | 90 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | INP-SITE | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 2 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-05 | 2024-04-05 | 2024-04-04 | 2024-08-17 | 100 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-RIGG | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-05 | 2024-04-05 | 2024-04-04 | 2024-08-17 | 110 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 12 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-05 | 2024-04-06 | 2024-04-04 | 2024-08-17 | 120 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-SCAF | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 0 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-04 | 2024-08-17 | 130 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100107875 | FLMPR: Replace spool on 2"-WP-10601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F |  |  | 8 | 0 | Empty | 2024-04-04 | 2024-04-06 | 2024-04-06 | 2024-04-06 | 2024-04-04 | 2024-08-17 | 140 |  |  | DF /A /85/DFA-2-WP-010-0601-A1-F | FFS: Replace spool on 2"-WP-10601-A1-F | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400290950 | 1Y GYM EQUIPMENT CHECK - DFC (VENDOR) | GYM EQUIPMENT CHECK - DFC (VENDOR) | AWSC | AWSC | 8 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-10-08 | 2023-11-24 | 10 | AWSC | AWSC | DF /C /82/GYM-EQUIPMENT | GYM EQUIPMENT CHECK - DFC (VENDOR) | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-ROPE | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 16 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 8 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 3 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 9 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 1 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 10 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-ROPE | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 300 | 197 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-07 | 2019-06-10 | 2019-07-20 | 20 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 240 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-10 | 2019-06-10 | 2019-07-20 | 30 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 1 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2019-06-10 | 2019-07-20 | 40 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 18 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2019-06-10 | 2019-07-20 | 50 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 8 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2019-06-10 | 2019-07-20 | 60 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 70 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 80 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 0 | 0 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 90 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100022932 | DFA/78: Replace all wire sheaves on cran | Erect and dismantle scaffold | PCNF | PCNF | 0 | 42 | W17-W18 | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-05 | 2019-06-10 | 2019-07-20 | 100 | PCNF | PCNF | DF /A /78/DFAA-X-6102 | Erect and dismantle scaffold | Unknown
D | NOSD | WPM | MTN-PAIN | MTN-ROUS | 2400342416 | 1Y HOSES/ROLLERS/HANDLES MAINT - DFC | HOSES/ROLLERS/HANDLES MAINT - DFC |  |  | 6 | 7 | Empty | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-07-21 | 2024-07-20 | 2024-09-05 | 10 |  |  | DF /C /84 | HOSES/ROLLERS/HANDLES MAINT - DFC | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025073 | Exchange XCV including actuator. | L3 Isolate valve |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2019-03-11 | 2019-04-20 | 10 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025073 | Exchange XCV including actuator. | L3 Isolate valve |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-19 | 2019-03-11 | 2019-04-20 | 20 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025073 | Exchange XCV including actuator. | L3 Isolate valve |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-21 | 2019-03-11 | 2019-04-20 | 30 |  |  | DF /F /27/DFFA-XCV-500752 | L3 Isolate valve | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100104295 | Replace gas detektor DFFA-GD-124603 | Inhibit / Repeal inhibition GD-124603 | SECE | SECE | 1 | 0 | Empty | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2023-12-28 | 2024-02-11 | 10 | SECE | SECE | DF /F /03/DFFA-GD-124603 | Inhibit / Repeal inhibition GD-124603 | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100104295 | Replace gas detektor DFFA-GD-124603 | Inhibit / Repeal inhibition GD-124603 | SECE | SECE | 4 | 0 | Empty | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-12-28 | 2024-02-11 | 20 | SECE | SECE | DF /F /03/DFFA-GD-124603 | Inhibit / Repeal inhibition GD-124603 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329500 | 6M SDV LUB/MAINT OIL - DFE | SDV LUB/INSP OIL - DFE |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-26 | 2024-06-11 | 10 |  |  | DF /E /03/SDV-VALVES | SDV LUB/INSP OIL - DFE | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100063030 | Remount insulation on DFC jockey pumps | Remount insulation on both jockey pumps | SCH | SCH | 1 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-06 | 2023-11-06 | 2022-03-06 | 2022-06-04 | 10 | SCH | SCH | DF /C /01/DFCM-P-0309 | Remount insulation on both jockey pumps | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100063030 | Remount insulation on DFC jockey pumps | Remount insulation on both jockey pumps | SCH | SCH | 12 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-06 | 2023-11-09 | 2022-03-06 | 2022-06-04 | 20 | SCH | SCH | DF /C /01/DFCM-P-0309 | Remount insulation on both jockey pumps | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100063030 | Remount insulation on DFC jockey pumps | Remount insulation on both jockey pumps | SCH | SCH | 1 | 0 | W45-46 | 2023-11-06 | 2023-11-09 | 2023-11-09 | 2023-11-09 | 2022-03-06 | 2022-06-04 | 30 | SCH | SCH | DF /C /01/DFCM-P-0309 | Remount insulation on both jockey pumps | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100088256 | DFG Cooling Medium pump ESD VIP probe | Check wiring and loop |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-06 | 2023-09-18 | 10 |  |  | DF /G /76/DFGA-VT-530412 | Check wiring and loop | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100088256 | DFG Cooling Medium pump ESD VIP probe | Check wiring and loop |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-06 | 2023-09-18 | 20 |  |  | DF /G /76/DFGA-VT-530412 | Check wiring and loop | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100088256 | DFG Cooling Medium pump ESD VIP probe | Check wiring and loop |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-06 | 2023-09-18 | 30 |  |  | DF /G /76/DFGA-VT-530412 | Check wiring and loop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344043 | 4Y WELLH CONT PANEL MAINT - DFFA-FP-3103 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-07-11 | 2024-07-21 | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-09-22 | 10 | SECE | SECE | DF /F /07/DFFA-FP-3103 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344043 | 4Y WELLH CONT PANEL MAINT - DFFA-FP-3103 | ISOLATION BY PRODUCTION | SECE | SECE | 7 | 0 | Empty | 2024-07-11 | 2024-07-21 | 2024-07-11 | 2024-07-13 | 2024-07-11 | 2024-09-22 | 20 | SECE | SECE | DF /F /07/DFFA-FP-3103 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344043 | 4Y WELLH CONT PANEL MAINT - DFFA-FP-3103 | ISOLATION BY PRODUCTION | SECE | SECE | 23 | 0 | Empty | 2024-07-11 | 2024-07-21 | 2024-07-13 | 2024-07-18 | 2024-07-11 | 2024-09-22 | 30 | SECE | SECE | DF /F /07/DFFA-FP-3103 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344043 | 4Y WELLH CONT PANEL MAINT - DFFA-FP-3103 | ISOLATION BY PRODUCTION | SECE | SECE | 8.5 | 0 | Empty | 2024-07-11 | 2024-07-21 | 2024-07-19 | 2024-07-21 | 2024-07-11 | 2024-09-22 | 40 | SECE | SECE | DF /F /07/DFFA-FP-3103 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344043 | 4Y WELLH CONT PANEL MAINT - DFFA-FP-3103 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-07-11 | 2024-07-21 | 2024-07-21 | 2024-07-21 | 2024-07-11 | 2024-09-22 | 50 | SECE | SECE | DF /F /07/DFFA-FP-3103 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400259025 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-05-06 | 2023-06-05 | 10 | SECE | SECE | DF /F /09/DFFB-A-1251 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400259025 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | PERSONAL ISOLATION | SECE | SECE | 7 | 7 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-05-06 | 2023-06-05 | 20 | SECE | SECE | DF /F /09/DFFB-A-1251 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400259025 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-05-06 | 2023-06-05 | 30 | SECE | SECE | DF /F /09/DFFB-A-1251 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400259025 | 1Y HVAC SUPPLY AHU CHECK DFFB-A-1251 | PERSONAL ISOLATION | SECE | SECE | 2 | 2 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-05-06 | 2023-06-05 | 40 | SECE | SECE | DF /F /09/DFFB-A-1251 | PERSONAL ISOLATION | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059754 | FLMR DFC - Repl of gratings EL +63650 | DFC - Replacement of gratings EL +63650 |  |  | 0 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +63650 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059754 | FLMR DFC - Repl of gratings EL +63650 | DFC - Replacement of gratings EL +63650 |  |  | 2 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +63650 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059754 | FLMR DFC - Repl of gratings EL +63650 | DFC - Replacement of gratings EL +63650 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +63650 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059754 | FLMR DFC - Repl of gratings EL +63650 | DFC - Replacement of gratings EL +63650 |  |  | 4 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +63650 | Unknown
3 | NOSD | WDF | MTN-PIPF | MTN-PIPF | 2100059754 | FLMR DFC - Repl of gratings EL +63650 | DFC - Replacement of gratings EL +63650 |  |  | 1 | 0 | Empty | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-01-01 | 2022-04-01 | 50 |  |  | DF /C /86/50700 - GRATINGS | DFC - Replacement of gratings EL +63650 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258812 | 6M BOOSTER PUMP MAINT DFGA-P-3547/48 | BOOSTER PUMP MAINT DFGA-P-3547/48 |  |  | 4 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-05-10 | 2023-05-29 | 10 |  |  | DF /G /54/DFGA-P-3547 | BOOSTER PUMP MAINT DFGA-P-3547/48 | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073892 | Fusible loop holder ikke tæt | Prepare rope access |  |  | 20 | 0 | SR/MSI | 2023-02-13 | 2023-02-19 | 2023-02-13 | 2023-02-15 | 2022-08-29 | 2022-10-13 | 10 |  |  | DF /F /01/DFFA-A-0302 | Prepare rope access | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073892 | Fusible loop holder ikke tæt | Prepare rope access |  |  | 10 | 0 | SR/MSI | 2023-02-13 | 2023-02-19 | 2023-02-15 | 2023-02-16 | 2022-08-29 | 2022-10-13 | 20 |  |  | DF /F /01/DFFA-A-0302 | Prepare rope access | Unknown
2 | NOSD | WDF | MTN-INST | MTN-ROPE | 2100073892 | Fusible loop holder ikke tæt | Prepare rope access |  |  | 20 | 0 | SR/MSI | 2023-02-13 | 2023-02-19 | 2023-02-16 | 2023-02-19 | 2022-08-29 | 2022-10-13 | 30 |  |  | DF /F /01/DFFA-A-0302 | Prepare rope access | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044567 | Fail to close during exchange of hydrant | Replace DFCI-HCV-03339 |  |  | 1 | 0 | Empty | 2023-11-27 | 2023-11-29 | 2023-11-27 | 2023-11-27 | 2021-01-29 | 2021-03-10 | 10 |  |  | DF /C /01/DFCI-HCV-03339 | Replace DFCI-HCV-03339 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044567 | Fail to close during exchange of hydrant | Replace DFCI-HCV-03339 |  |  | 3 | 0 | Empty | 2023-11-27 | 2023-11-29 | 2023-11-27 | 2023-11-27 | 2021-01-29 | 2021-03-10 | 20 |  |  | DF /C /01/DFCI-HCV-03339 | Replace DFCI-HCV-03339 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044567 | Fail to close during exchange of hydrant | Replace DFCI-HCV-03339 |  |  | 1 | 0 | Empty | 2023-11-27 | 2023-11-29 | 2023-11-28 | 2023-11-28 | 2021-01-29 | 2021-03-10 | 30 |  |  | DF /C /01/DFCI-HCV-03339 | Replace DFCI-HCV-03339 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044567 | Fail to close during exchange of hydrant | Replace DFCI-HCV-03339 |  |  | 5 | 0 | Empty | 2023-11-27 | 2023-11-29 | 2023-11-28 | 2023-11-29 | 2021-01-29 | 2021-03-10 | 40 |  |  | DF /C /01/DFCI-HCV-03339 | Replace DFCI-HCV-03339 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044567 | Fail to close during exchange of hydrant | Replace DFCI-HCV-03339 |  |  | 0 | 0 | Empty | 2023-11-27 | 2023-11-29 | 2023-11-27 | 2023-11-27 | 2021-01-29 | 2021-03-10 | 50 |  |  | DF /C /01/DFCI-HCV-03339 | Replace DFCI-HCV-03339 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-11 | 2024-01-12 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-12 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 45 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-15 | 2024-01-19 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-19 | 2024-01-22 | 2022-02-09 | 2022-07-09 | 60 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009224 | Insulation assist bilfinger 19728 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-23 | 2024-01-22 | 2024-01-23 | 2022-02-09 | 2022-07-09 | 70 |  |  | DF /C /27/DFC-4-WOS-050-4099-AD-T | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036456 | DFF-40 C/I still chem ijn flow DFFA-FCV- | Replace DFFA-FCV-390059 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2020-09-05 | 2020-12-04 | 10 |  |  | DF /F /75/DFFA-FCV-390059 | Replace DFFA-FCV-390059 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036456 | DFF-40 C/I still chem ijn flow DFFA-FCV- | Replace DFFA-FCV-390059 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2020-09-05 | 2020-12-04 | 20 |  |  | DF /F /75/DFFA-FCV-390059 | Replace DFFA-FCV-390059 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100036456 | DFF-40 C/I still chem ijn flow DFFA-FCV- | Replace DFFA-FCV-390059 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2020-09-05 | 2020-12-04 | 30 |  |  | DF /F /75/DFFA-FCV-390059 | Replace DFFA-FCV-390059 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 0 | 0 | Empty | 2022-01-18 | 2022-02-06 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-06-17 | 10 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 15 | 15 | Empty | 2022-01-18 | 2022-02-06 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-06-17 | 20 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 100 | 21 | Empty | 2022-01-18 | 2022-02-06 | 2022-01-18 | 2022-01-26 | 2022-01-18 | 2022-06-17 | 30 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 90 | 37 | Empty | 2022-01-18 | 2022-02-06 | 2022-01-26 | 2022-01-30 | 2022-01-18 | 2022-06-17 | 40 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 90 | 81 | Empty | 2022-01-18 | 2022-02-06 | 2022-01-30 | 2022-02-02 | 2022-01-18 | 2022-06-17 | 50 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 50 | 0 | Empty | 2022-01-18 | 2022-02-06 | 2022-02-02 | 2022-02-06 | 2022-01-18 | 2022-06-17 | 60 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100057562 | SYNSR-667006 DFC - Replacement Handrail | DFC - Replacement Handrail EL. 50.700 |  |  | 15 | 0 | Empty | 2022-01-18 | 2022-02-06 | 2022-02-06 | 2022-02-06 | 2022-01-18 | 2022-06-17 | 70 |  |  | DF /C /86/50700 - HANDRAILS | DFC - Replacement Handrail EL. 50.700 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-25 | 2023-04-30 | 10 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-24 | 2023-03-25 | 2023-04-30 | 20 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2023-03-25 | 2023-04-30 | 30 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-26 | 2023-03-25 | 2023-04-30 | 40 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2023-03-25 | 2023-04-30 | 50 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-25 | 2023-04-30 | 60 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-25 | 2023-04-30 | 70 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400241889 | 1Y HVAC SUPP/EXH A-122/LAB-DFCI (VENDOR) | PERSONAL ISOLATION | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-25 | 2023-04-30 | 80 | AWSC | AWSC | DF /C /09/A-1222 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-15 | 2024-09-18 | 2023-02-28 | 2023-04-05 | 10 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
C | NOSD | WPM | MTN-MECH | WELLSUPV | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 100 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-18 | 2024-09-24 | 2023-02-28 | 2023-04-05 | 20 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 48 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-24 | 2024-09-27 | 2023-02-28 | 2023-04-05 | 30 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
C | NOSD | WPM | MTN-MECH | WELLSUPV | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 50 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-27 | 2024-09-30 | 2023-02-28 | 2023-04-05 | 40 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-10-01 | 2024-10-03 | 2023-02-28 | 2023-04-05 | 50 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-02-28 | 2023-04-05 | 60 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241064 | 1Y HYDRO/SAND CYCONER DFGA-5061/65 | HYDROCYCLONER DFGA-V-5061/62 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-02-28 | 2023-04-05 | 70 |  |  | DF /G /27/DFGA-A-5060 | HYDROCYCLONER DFGA-V-5061/62 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100063634 | Handle on butterfly valve brok off. | Replace Handwheel |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-03-16 | 2022-06-14 | 10 |  |  | DF /C /51/DFCM-FT-5221 | Replace Handwheel | Unknown
3 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100025098 | ANOS: Repair corroded railing | Clean handrail and fundation |  |  | 1 | 0 | Empty | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2024-03-15 | 2017-04-16 | 2017-07-15 | 9 |  |  | DF /F /78/DFFA-A-6102 | Clean handrail and fundation | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100025098 | ANOS: Repair corroded railing | Clean handrail and fundation |  |  | 12 | 0 | Empty | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2024-03-15 | 2017-04-16 | 2017-07-15 | 10 |  |  | DF /F /78/DFFA-A-6102 | Clean handrail and fundation | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100025098 | ANOS: Repair corroded railing | Clean handrail and fundation |  |  | 72 | 0 | Empty | 2024-03-15 | 2024-03-19 | 2024-03-15 | 2024-03-19 | 2017-04-16 | 2017-07-15 | 170 |  |  | DF /F /78/DFFA-A-6102 | Clean handrail and fundation | Unknown
3 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100025098 | ANOS: Repair corroded railing | Clean handrail and fundation |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-19 | 2024-03-19 | 2024-03-19 | 2017-04-16 | 2017-07-15 | 190 |  |  | DF /F /78/DFFA-A-6102 | Clean handrail and fundation | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235614 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-1 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-09-18 | 2023-04-30 | 2023-07-27 | 10 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235614 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-1 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 11 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-09-21 | 2023-04-30 | 2023-07-27 | 20 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235614 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-1 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 4 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 30 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235614 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-1 | ISOLATION ELECTRICAL | AWSCSCH | AWSCSCH | 1 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 40 | AWSCSCH | AWSCSCH | DF /F /61/DFFA-N-1802B-1 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400350906 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-19 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 11 | 0 | Empty | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-08-08 | 2024-10-09 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-19 | ATEX EQUIPMENT INSPECTION | Unknown
B | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400126430 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-10-03 | 2021-12-04 | 2 | AWSC | AWSC | DF /E /03/SDV-VALVES | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
B | DFE-3551 | WPM | MTN-MECH | MTN-ELEC | 2400126430 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-10-03 | 2021-12-04 | 10 | AWSC | AWSC | DF /E /03/SDV-VALVES | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
B | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400126430 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-10-03 | 2021-12-04 | 20 | AWSC | AWSC | DF /E /03/SDV-VALVES | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
B | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400126430 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-10-03 | 2021-12-04 | 30 | AWSC | AWSC | DF /E /03/SDV-VALVES | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
B | DFE-3551 | WPM | MTN-MECH | PRODTECH | 2400126430 | Cancel - 3Y FUNC, VISUAL, EX INSP ESDV ( | ESDV VISUAL AND FUNCTIONAL CHECK | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2021-10-03 | 2021-12-04 | 40 | AWSC | AWSC | DF /E /03/SDV-VALVES | ESDV VISUAL AND FUNCTIONAL CHECK | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009242 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7031-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009242 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-01-13 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7031-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009242 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-14 | 2024-01-16 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7031-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009242 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 18 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-16 | 2024-01-17 | 2022-02-08 | 2022-07-08 | 32 |  |  | DF /F /55/DFF-6-PHS-030-7031-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009242 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-17 | 2024-01-22 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /F /55/DFF-6-PHS-030-7031-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009242 | Insulation assist FORCE 14378 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-22 | 2024-01-25 | 2022-02-08 | 2022-07-08 | 50 |  |  | DF /F /55/DFF-6-PHS-030-7031-GF-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 2 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 3 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 4 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 5 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 24 | Empty | 2023-02-13 | 2023-03-20 | 2021-01-16 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 12 | Empty | 2023-02-13 | 2023-03-20 | 2021-01-14 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 4 | Empty | 2023-02-13 | 2023-03-20 | 2021-01-14 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 2 | Empty | 2023-02-13 | 2023-03-20 | 2021-01-16 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2021-01-16 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 4 | Empty | 2023-02-13 | 2023-03-20 | 2021-08-30 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 48 | Empty | 2023-02-13 | 2023-03-20 | 2021-08-31 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 24 | Empty | 2023-02-13 | 2023-03-20 | 2022-01-13 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 74 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 36 | 48 | Empty | 2023-02-13 | 2023-03-20 | 2022-01-13 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 75 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 12 | Empty | 2023-02-13 | 2023-03-20 | 2021-08-31 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 75 | 60 | Empty | 2023-02-13 | 2023-03-20 | 2021-08-31 | 2022-02-27 | 2021-01-16 | 2021-04-16 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 101 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 36 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-14 | 2023-03-16 | 2021-01-16 | 2021-04-16 | 102 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 36 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-17 | 2023-03-19 | 2021-01-16 | 2021-04-16 | 103 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-20 | 2023-03-20 | 2021-01-16 | 2021-04-16 | 104 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-02-13 | 2023-02-13 | 2021-01-16 | 2021-04-16 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 75 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-MECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 40 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 135 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 150 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 160 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 170 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 24 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 180 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-02-13 | 2023-02-13 | 2021-01-16 | 2021-04-16 | 190 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100043356 | Defect electrical motor PM-3620 | Add materials | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-02-13 | 2023-03-20 | 2023-03-13 | 2023-03-13 | 2021-01-16 | 2021-04-16 | 200 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /23/DFCM-PM-3620 | Add materials | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101813 | IP/HP-DFG Defect Humidity Sensor 431320B | Isolate Humidity Sensor |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-05-10 | 2026-10-27 | 10 |  |  | DF /G /31/DFGA-MT-431320B | Isolate Humidity Sensor | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101813 | IP/HP-DFG Defect Humidity Sensor 431320B | Isolate Humidity Sensor |  |  | 2.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-05-10 | 2026-10-27 | 20 |  |  | DF /G /31/DFGA-MT-431320B | Isolate Humidity Sensor | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100101813 | IP/HP-DFG Defect Humidity Sensor 431320B | Isolate Humidity Sensor |  |  | 1.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-05-10 | 2026-10-27 | 30 |  |  | DF /G /31/DFGA-MT-431320B | Isolate Humidity Sensor | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038177 | Replacement of RCDs | Prove dead |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-22 | 2024-09-22 | 2020-12-06 | 2021-05-05 | 10 |  |  | DF /G /61/DFGA-LP-1853 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038177 | Replacement of RCDs | Prove dead |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-23 | 2020-12-06 | 2021-05-05 | 20 |  |  | DF /G /61/DFGA-LP-1853 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038177 | Replacement of RCDs | Prove dead |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-23 | 2024-09-29 | 2020-12-06 | 2021-05-05 | 30 |  |  | DF /G /61/DFGA-LP-1853 | Prove dead | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100038177 | Replacement of RCDs | Prove dead |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-30 | 2024-09-29 | 2024-09-30 | 2020-12-06 | 2021-05-05 | 40 |  |  | DF /G /61/DFGA-LP-1853 | Prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100037393 | Troubleshoot HTJB-1802-20410 | Troubleshoot and fix if possible |  |  | 0.2999999999999999888977697536 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2020-09-25 | 2020-12-24 | 10 |  |  | DF /F /61/DFFA-DP-1802A-7-F13 | Troubleshoot and fix if possible | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100037393 | Troubleshoot HTJB-1802-20410 | Troubleshoot and fix if possible |  |  | 48 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-07 | 2020-09-25 | 2020-12-24 | 20 |  |  | DF /F /61/DFFA-DP-1802A-7-F13 | Troubleshoot and fix if possible | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100037393 | Troubleshoot HTJB-1802-20410 | Troubleshoot and fix if possible |  |  | 0.2000000000000000111022302462 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-07 | 2024-07-07 | 2020-09-25 | 2020-12-24 | 30 |  |  | DF /F /61/DFFA-DP-1802A-7-F13 | Troubleshoot and fix if possible | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100104201 | DFC HVAC Main Gen Flow switch faulty | Investigate on FE-12341 |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-01-18 | 2024-06-01 | 10 |  |  | DF /C /09/DFCI-FE-12341 | Investigate on FE-12341 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235609 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235609 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 |  |  | 29 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-15 | 2024-09-22 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235609 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 |  |  | 9 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-22 | 2024-09-25 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235609 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-N-1802A-17 | 380V N-SWB-INSP-DFFA-N-1802A-17 | Unknown
2 | NOSD | WGN | MTN-PAIN | WELLSUPV | 2200013995 | IRP ID 7962 ans 7967 supports | IRP ID 7962 ans 7967 supports |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-27 | 2023-03-27 | 2023-03-27 | 2023-03-27 | 2023-05-11 | 10 |  |  | DF /C /70 | IRP ID 7962 ans 7967 supports | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400337675 | 6M COLD PROVISIONS DFCC-C-1301/2/3 VEND | COLD PROVISIONS DFCC-C-1301/2/3 VEND | AWSC | AWSC | 12 | 0 | Empty | 2024-07-26 | 2024-07-28 | 2024-07-26 | 2024-07-27 | 2024-07-26 | 2024-08-20 | 10 | AWSC | AWSC | DF /C /82/CATERING-EQUIPMENT | COLD PROVISIONS DFCC-C-1301/2/3 VEND | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400337675 | 6M COLD PROVISIONS DFCC-C-1301/2/3 VEND | COLD PROVISIONS DFCC-C-1301/2/3 VEND | AWSC | AWSC | 6 | 0 | Empty | 2024-07-26 | 2024-07-28 | 2024-07-27 | 2024-07-28 | 2024-07-26 | 2024-08-20 | 20 | AWSC | AWSC | DF /C /82/CATERING-EQUIPMENT | COLD PROVISIONS DFCC-C-1301/2/3 VEND | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100024407 | ANOP DFF P-3520 oxygen scavenger line Le | DFF P-3520 oxygen scavenger line Leak |  |  | 0 | 0 | Empty | 2021-02-13 | 2021-02-13 | 2021-02-13 | 2021-02-13 | 2019-11-20 | 2019-12-30 | 10 |  |  | DF /F /75/DFF-0.5-CX-039-7065-AS-U | DFF P-3520 oxygen scavenger line Leak | Unknown
3 | DFC-TSEP | WDF | MTN-INST | PRODTECH | 2100055899 | Replace sup/ret hoses with inst tubing | Replace hoses with 904L tubing |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-10-16 | 2022-01-14 | 10 |  |  | DF /C /11/DFCI-BDV-34045 | Replace hoses with 904L tubing | Unknown
3 | DFC-TSEP | WDF | MTN-INST | MTN-INST | 2100055899 | Replace sup/ret hoses with inst tubing | Replace hoses with 904L tubing |  |  | 8 | 0 | BL-TEAM | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2021-10-16 | 2022-01-14 | 20 |  |  | DF /C /11/DFCI-BDV-34045 | Replace hoses with 904L tubing | Unknown
3 | DFC-TSEP | WDF | MTN-INST | PRODTECH | 2100055899 | Replace sup/ret hoses with inst tubing | Replace hoses with 904L tubing |  |  | 1 | 0 | BL-TEAM | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2021-10-16 | 2022-01-14 | 30 |  |  | DF /C /11/DFCI-BDV-34045 | Replace hoses with 904L tubing | Unknown
3 | DFF-3580 | WGN | MTN-INST | MTN-INST | 2200010753 | Service of Minox analyzers | Service of Minox analyzers |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-05-01 | 2022-05-21 | 10 |  |  | DF /F /53/DFFB-AIT-356611 | Service of Minox analyzers | Unknown
3 | DFF-COOL | WDF | MTN-INST | MTN-INST | 2100044092 | DFF-FI-410531 Fejl visning | Isolate, tag DFFA-FI-410531 |  |  | 0 | 0 | W51-52 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-01-19 | 2021-02-28 | 10 |  |  | DF /F /70/DFFA-PCV-410530 | Isolate, tag DFFA-FI-410531 | Unknown
3 | DFF-COOL | WDF | MTN-INST | PRODTECH | 2100044092 | DFF-FI-410531 Fejl visning | Isolate, tag DFFA-FI-410531 |  |  | 0.5 | 0 | W51-52 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-01-19 | 2021-02-28 | 20 |  |  | DF /F /70/DFFA-PCV-410530 | Isolate, tag DFFA-FI-410531 | Unknown
3 | DFF-COOL | WDF | MTN-INST | MTN-MECH | 2100044092 | DFF-FI-410531 Fejl visning | Isolate, tag DFFA-FI-410531 |  |  | 3 | 0 | W51-52 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-01-19 | 2021-02-28 | 30 |  |  | DF /F /70/DFFA-PCV-410530 | Isolate, tag DFFA-FI-410531 | Unknown
3 | DFF-COOL | WDF | MTN-INST | PRODTECH | 2100044092 | DFF-FI-410531 Fejl visning | Isolate, tag DFFA-FI-410531 |  |  | 0.5 | 0 | W51-52 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2021-01-19 | 2021-02-28 | 40 |  |  | DF /F /70/DFFA-PCV-410530 | Isolate, tag DFFA-FI-410531 | Unknown
3 | DFF-COOL | WDF | MTN-INST | MTN-INST | 2100044092 | DFF-FI-410531 Fejl visning | Isolate, tag DFFA-FI-410531 |  |  | 0.5 | 0 | W51-52 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-01-19 | 2021-02-28 | 50 |  |  | DF /F /70/DFFA-PCV-410530 | Isolate, tag DFFA-FI-410531 | Unknown
3 | DFF-COOL | WDF | MTN-INST | MTN-INST | 2100044092 | DFF-FI-410531 Fejl visning | Isolate, tag DFFA-FI-410531 |  |  | 0.5 | 0 | W51-52 | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2021-01-19 | 2021-02-28 | 60 |  |  | DF /F /70/DFFA-PCV-410530 | Isolate, tag DFFA-FI-410531 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057555 | FLMR DFB - Replacement Handrail EL. 30.6 | DFB - Replacement Handrail EL. 30.600 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 10 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 30.600 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057555 | FLMR DFB - Replacement Handrail EL. 30.6 | DFB - Replacement Handrail EL. 30.600 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 20 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 30.600 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057555 | FLMR DFB - Replacement Handrail EL. 30.6 | DFB - Replacement Handrail EL. 30.600 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 30 |  |  | DF /B /86/30600 - HANDRAILS | DFB - Replacement Handrail EL. 30.600 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322262 | DFC-60-FY-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /60/P-G | PIPING INSPECTION AND REPORTING | Unknown
2 | NE | WGN | MTN-MECH | PRODTECH | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 2 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-26 | 2021-08-26 | 2021-08-26 | 2021-08-31 | 10 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
2 | NE | WGN | MTN-MECH | MTN-INST | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 2 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-26 | 2021-08-27 | 2021-08-26 | 2021-08-31 | 20 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
2 | NE | WGN | MTN-MECH | MTN-MECH | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 1 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-27 | 2021-08-27 | 2021-08-26 | 2021-08-31 | 30 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
2 | NE | WGN | MTN-MECH | MTN-INST | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 2 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-27 | 2021-08-28 | 2021-08-26 | 2021-08-31 | 40 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
2 | NE | WGN | MTN-MECH | MTN-INST | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 2 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-28 | 2021-08-28 | 2021-08-26 | 2021-08-31 | 50 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
2 | NE | WGN | MTN-MECH | MTN-MECH | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 2 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-28 | 2021-08-29 | 2021-08-26 | 2021-08-31 | 60 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
2 | NE | WGN | MTN-MECH | PRODTECH | 2200007982 | DFE-04 SSSV CONTROL LINE PRESS REDUC | Isolation of Valves | SECE | SECE | 1 | 0 | Empty | 2021-08-26 | 2021-08-29 | 2021-08-29 | 2021-08-29 | 2021-08-26 | 2021-08-31 | 70 | SECE | SECE | DF /E /07/DFEZ-A-3102 | Isolation of Valves | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100023837 | Isolering af DFCC-XCV-03448/03449 | Etablering af isolering omkring XCV'erne |  |  | 30.19999999999999928945726423 | 0 | Empty | 2023-02-13 | 2023-02-16 | 2023-02-13 | 2023-02-16 | 2017-10-15 | 2018-01-13 | 10 |  |  | DF /C /01/DFCC-XCV-03448 | Etablering af isolering omkring XCV'erne | Unknown
2 | NOSD | WGN | MTN-TELE | MTN-TELE | 2200017474 | Replace switch DAN F | Replace switch DAN F | SCH | SCH | 6 | 6 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2024-02-06 | 2024-03-22 | 10 | SCH | SCH | DF /C /08 | Replace switch DAN F | Unknown
2 | NOSD | WGN | MTN-TELE | VEN-COMM | 2200017474 | Replace switch DAN F | Replace switch DAN F | SCH | SCH | 4 | 4 | W27-W28 | 2024-07-03 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2024-02-06 | 2024-03-22 | 20 | SCH | SCH | DF /C /08 | Replace switch DAN F | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 1 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 10 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 3 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 20 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 1 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 30 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 40 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 50 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 6 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-24 | 2022-12-08 | 2023-04-22 | 60 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-24 | 2022-12-08 | 2023-04-22 | 70 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 4 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-25 | 2024-09-25 | 2022-12-08 | 2023-04-22 | 80 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 1 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2022-12-08 | 2023-04-22 | 90 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2022-12-08 | 2023-04-22 | 100 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076709 | DFC-XCV-36708 mangler indikering (ny akt | Mount new switchbox and connect |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2022-12-08 | 2023-04-22 | 110 |  |  | DF /C /23/DFCM-XCV-36708 | Mount new switchbox and connect | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100086862 | DFF-29 Choke ustabil ZT | CVA valve in 'MANUAL' mode |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 10 |  |  | DF /F /10/DFFA-ZT-300729 | CVA valve in 'MANUAL' mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086862 | DFF-29 Choke ustabil ZT | CVA valve in 'MANUAL' mode |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 20 |  |  | DF /F /10/DFFA-ZT-300729 | CVA valve in 'MANUAL' mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086862 | DFF-29 Choke ustabil ZT | CVA valve in 'MANUAL' mode |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 30 |  |  | DF /F /10/DFFA-ZT-300729 | CVA valve in 'MANUAL' mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086862 | DFF-29 Choke ustabil ZT | CVA valve in 'MANUAL' mode |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 40 |  |  | DF /F /10/DFFA-ZT-300729 | CVA valve in 'MANUAL' mode | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100086862 | DFF-29 Choke ustabil ZT | CVA valve in 'MANUAL' mode |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-20 | 2023-09-02 | 50 |  |  | DF /F /10/DFFA-ZT-300729 | CVA valve in 'MANUAL' mode | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018144 | Replace Motor protection 1841-M121 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M121-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018144 | Replace Motor protection 1841-M121 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M121-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018144 | Replace Motor protection 1841-M121 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M121-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018144 | Replace Motor protection 1841-M121 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M121-02 | Isolation of Breaker section | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400351957 | 1Y DOWNHOLE GAUGE SYSTEM - DFE | DOWNHOLE GAUGE SYSTEM MAINT - DFE |  |  | 4 | 0 | W37-W38 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-10-15 | 10 |  |  | DF /E /10/CONTROL-PANELS | DOWNHOLE GAUGE SYSTEM MAINT - DFE | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235810 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235810 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235810 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235810 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF02-01 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040145 | DFFA-P-3911 Change of filterunit | Isolate strainer at DFFA-P-3911 |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-01-18 | 2021-06-17 | 10 |  |  | DF /F /75/DFFA-P-3911 | Isolate strainer at DFFA-P-3911 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040145 | DFFA-P-3911 Change of filterunit | Isolate strainer at DFFA-P-3911 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2021-01-18 | 2021-06-17 | 20 |  |  | DF /F /75/DFFA-P-3911 | Isolate strainer at DFFA-P-3911 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100040145 | DFFA-P-3911 Change of filterunit | Isolate strainer at DFFA-P-3911 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2021-01-18 | 2021-06-17 | 30 |  |  | DF /F /75/DFFA-P-3911 | Isolate strainer at DFFA-P-3911 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100040145 | DFFA-P-3911 Change of filterunit | Isolate strainer at DFFA-P-3911 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2021-01-18 | 2021-06-17 | 40 |  |  | DF /F /75/DFFA-P-3911 | Isolate strainer at DFFA-P-3911 | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036930 | DFFE/78: Replace bulkhead/weld plates | QC, clean-up | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2020-12-11 | 2021-08-08 | 10 | SCH | SCH | DF /F /78/DFFA-A-6101 | QC, clean-up | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036930 | DFFE/78: Replace bulkhead/weld plates | QC, clean-up | SCH | SCH | 14 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-17 | 2020-12-11 | 2021-08-08 | 20 | SCH | SCH | DF /F /78/DFFA-A-6101 | QC, clean-up | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036930 | DFFE/78: Replace bulkhead/weld plates | QC, clean-up | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-17 | 2020-12-11 | 2021-08-08 | 30 | SCH | SCH | DF /F /78/DFFA-A-6101 | QC, clean-up | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036930 | DFFE/78: Replace bulkhead/weld plates | QC, clean-up | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2020-12-11 | 2021-08-08 | 40 | SCH | SCH | DF /F /78/DFFA-A-6101 | QC, clean-up | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036930 | DFFE/78: Replace bulkhead/weld plates | QC, clean-up | SCH | SCH | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2020-12-11 | 2021-08-08 | 50 | SCH | SCH | DF /F /78/DFFA-A-6101 | QC, clean-up | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036930 | DFFE/78: Replace bulkhead/weld plates | QC, clean-up | SCH | SCH | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2020-12-11 | 2021-08-08 | 60 | SCH | SCH | DF /F /78/DFFA-A-6101 | QC, clean-up | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400352426 | 3Y BREATH. AIR COMP. MAINT- A-5405/5406 | BREATH. AIR COMP. MAINT- A-5405/5406 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-08-11 | 2024-10-24 | 10 |  |  | DF /G /02/DFGA-A-5405 | BREATH. AIR COMP. MAINT- A-5405/5406 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400352426 | 3Y BREATH. AIR COMP. MAINT- A-5405/5406 | BREATH. AIR COMP. MAINT- A-5405/5406 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-08-11 | 2024-10-24 | 20 |  |  | DF /G /02/DFGA-A-5405 | BREATH. AIR COMP. MAINT- A-5405/5406 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400222504 | 6M SYS 27 INSTRUMENTS/VALVES MAINT-DFF | SYS 27 INSTRUMENTS/VALVES MAINT-DFF |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-01-16 | 2023-02-04 | 10 |  |  | DF /F /27/DFFA-A-5002 | SYS 27 INSTRUMENTS/VALVES MAINT-DFF | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400222504 | 6M SYS 27 INSTRUMENTS/VALVES MAINT-DFF | SYS 27 INSTRUMENTS/VALVES MAINT-DFF |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-01-16 | 2023-02-04 | 20 |  |  | DF /F /27/DFFA-A-5002 | SYS 27 INSTRUMENTS/VALVES MAINT-DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100105892 | DFFA-HCV-435005 U Internal Leak | Isolate DFFA-HCV-435005 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2024-03-03 | 2024-07-16 | 10 |  |  | DF /F /32/DFFA-HCV-435005-U | Isolate DFFA-HCV-435005 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100105892 | DFFA-HCV-435005 U Internal Leak | Isolate DFFA-HCV-435005 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2024-03-03 | 2024-07-16 | 20 |  |  | DF /F /32/DFFA-HCV-435005-U | Isolate DFFA-HCV-435005 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100105892 | DFFA-HCV-435005 U Internal Leak | Isolate DFFA-HCV-435005 |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2024-03-03 | 2024-07-16 | 30 |  |  | DF /F /32/DFFA-HCV-435005-U | Isolate DFFA-HCV-435005 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100105892 | DFFA-HCV-435005 U Internal Leak | Isolate DFFA-HCV-435005 |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-03-03 | 2024-07-16 | 40 |  |  | DF /F /32/DFFA-HCV-435005-U | Isolate DFFA-HCV-435005 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100105892 | DFFA-HCV-435005 U Internal Leak | Isolate DFFA-HCV-435005 |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2024-03-03 | 2024-07-16 | 50 |  |  | DF /F /32/DFFA-HCV-435005-U | Isolate DFFA-HCV-435005 | Unknown
4 | NOSD | WDF | VEN-MECH | VEN-MECH | 2100061494 | Cleaning of open systems on DFF and DFG | operation_description_not_present |  |  | 160 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-13 | 2023-02-21 | 2022-04-05 | 2022-09-02 | 10 |  |  | DF /F /28 | operation_description_not_present | Unknown
4 | NOSD | WDF | VEN-MECH | VEN-MECH | 2100061494 | Cleaning of open systems on DFF and DFG | operation_description_not_present |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2022-04-05 | 2022-09-02 | 20 |  |  | DF /F /28 | operation_description_not_present | Unknown
4 | NOSD | WDF | VEN-MECH | MTN-MECH | 2100061494 | Cleaning of open systems on DFF and DFG | operation_description_not_present |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2022-04-05 | 2022-09-02 | 30 |  |  | DF /F /28 | operation_description_not_present | Unknown
4 | NOSD | WDF | VEN-MECH | VEN-MECH | 2100061494 | Cleaning of open systems on DFF and DFG | operation_description_not_present |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2022-04-05 | 2022-09-02 | 40 |  |  | DF /F /28 | operation_description_not_present | Unknown
4 | NOSD | WDF | VEN-MECH | VEN-MECH | 2100061494 | Cleaning of open systems on DFF and DFG | operation_description_not_present |  |  | 0 | 0 | Empty | 2023-02-13 | 2023-02-21 | 2023-02-21 | 2023-02-21 | 2022-04-05 | 2022-09-02 | 50 |  |  | DF /F /28 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342417 | 3M H2S GAS DETECTORS CHECK - DFA | H2S GAS DETECTORS CHECK - DFA DFC DF | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-25 | 2024-09-04 | 10 | SECE | SECE | DF /C /03/FGS-DETECTORS | H2S GAS DETECTORS CHECK - DFA DFC DF | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027417 | DFGA-DP-1854 Q24 aut. sikr. tripper | DC8 DFGA-DP-1854 Q24 aut. sikr. tripper |  |  | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-16 | 2024-07-01 | 2024-07-01 | 2019-02-18 | 2019-02-23 | 10 |  |  | DF /G /61/DFGA-DP-1854-24 | DC8 DFGA-DP-1854 Q24 aut. sikr. tripper | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100027417 | DFGA-DP-1854 Q24 aut. sikr. tripper | DC8 DFGA-DP-1854 Q24 aut. sikr. tripper |  |  | 60 | 0 | W27-W28 | 2024-07-01 | 2024-07-16 | 2024-07-01 | 2024-07-16 | 2019-02-18 | 2019-02-23 | 20 |  |  | DF /G /61/DFGA-DP-1854-24 | DC8 DFGA-DP-1854 Q24 aut. sikr. tripper | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400346582 | 3Y ATEX INSPECTION DF PLATFORM G/AREA-17 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 29 | 0 | Empty | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-08-04 | 2024-08-03 | 2024-10-04 | 10 | AWSCSECE | AWSCSECE | DF /G /63/ATEX-EARTH-AREA-17 | ATEX EQUIPMENT INSPECTION | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009243 | Insulation assist bilfinger 21918 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2022-02-13 | 2022-07-13 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009243 | Insulation assist bilfinger 21918 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2022-02-13 | 2022-07-13 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009243 | Insulation assist bilfinger 21918 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-09 | 2022-02-13 | 2022-07-13 | 22 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009243 | Insulation assist bilfinger 21918 | Bilfinger inspection |  |  | 48 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-12 | 2022-02-13 | 2022-07-13 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235723 | 4Y 380V E-SWB MAINT DFCI-N-1812-R04 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235723 | 4Y 380V E-SWB MAINT DFCI-N-1812-R04 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235723 | 4Y 380V E-SWB MAINT DFCI-N-1812-R04 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 24 | 106 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-11 | 2024-05-13 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235723 | 4Y 380V E-SWB MAINT DFCI-N-1812-R04 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235723 | 4Y 380V E-SWB MAINT DFCI-N-1812-R04 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 2 | 0 | W19-W20 | 2024-05-10 | 2024-05-14 | 2024-05-14 | 2024-05-14 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329993 | 2Y WINTER PUMP MAINT-DFGA-P-0342/0343 | WINTER PUMP MAINT-DFGA-P-0342/0343 | AWSCSCHSECE | AWSCSCHSECE | 6 | 0 | W25-W26 | 2024-06-20 | 2024-06-23 | 2024-06-20 | 2024-06-21 | 2024-05-11 | 2024-06-26 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /G /01/DFGA-P-0342 | WINTER PUMP MAINT-DFGA-P-0342/0343 | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400329993 | 2Y WINTER PUMP MAINT-DFGA-P-0342/0343 | WINTER PUMP MAINT-DFGA-P-0342/0343 | AWSCSCHSECE | AWSCSCHSECE | 6 | 0 | W25-W26 | 2024-06-20 | 2024-06-23 | 2024-06-21 | 2024-06-22 | 2024-05-11 | 2024-06-26 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /G /01/DFGA-P-0342 | WINTER PUMP MAINT-DFGA-P-0342/0343 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329993 | 2Y WINTER PUMP MAINT-DFGA-P-0342/0343 | WINTER PUMP MAINT-DFGA-P-0342/0343 | AWSCSCHSECE | AWSCSCHSECE | 6 | 0 | W25-W26 | 2024-06-20 | 2024-06-23 | 2024-06-22 | 2024-06-23 | 2024-05-11 | 2024-06-26 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /G /01/DFGA-P-0342 | WINTER PUMP MAINT-DFGA-P-0342/0343 | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284141 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-22 | 2023-11-01 | 10 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400284141 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 12 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-22 | 2023-11-01 | 20 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400284141 | 3M MINOX CATALYST WASH DFFB-VX-3566 | ISOLATION BY PRODUCTION |  |  | 2 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-10-22 | 2023-11-01 | 30 |  |  | DF /F /53/DFFB-A-3560 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235626 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-14 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-14 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235626 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-14 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-14 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235626 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-14 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-14 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235626 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-14 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-14 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112433 | DFCM-LBS-0609 lifebuoy replace rope | DFCM-LBS-0609 buoy new rope |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-06-24 | 2024-11-06 | 10 |  |  | DF /C /02/DFCM-LBS-0609 | DFCM-LBS-0609 buoy new rope | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284249 | PSV Exchange - DFCI-PSV-57148 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57148 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284249 | PSV Exchange - DFCI-PSV-57148 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57148 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284249 | PSV Exchange - DFCI-PSV-57148 | Isolation of PSV | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-31 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57148 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284249 | PSV Exchange - DFCI-PSV-57148 | Isolation of PSV | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57148 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284249 | PSV Exchange - DFCI-PSV-57148 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57148 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284249 | PSV Exchange - DFCI-PSV-57148 | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /C /70/DFCI-PSV-57148 | Isolation of PSV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100077101 | DFGA-PSV-530018 Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-11-10 | 2023-03-25 | 10 |  |  | DF /G /76/DFGA-PSV-530018 | Isolation of PSV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100077101 | DFGA-PSV-530018 Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2022-11-10 | 2023-03-25 | 20 |  |  | DF /G /76/DFGA-PSV-530018 | Isolation of PSV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | MTN-MECH | 2100077101 | DFGA-PSV-530018 Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2022-11-10 | 2023-03-25 | 40 |  |  | DF /G /76/DFGA-PSV-530018 | Isolation of PSV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100077101 | DFGA-PSV-530018 Misaligned flanges | Isolation of PSV |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2022-11-10 | 2023-03-25 | 50 |  |  | DF /G /76/DFGA-PSV-530018 | Isolation of PSV | Unknown
3 | DFG-IPHP | WDF | MTN-MECH | PRODTECH | 2100077101 | DFGA-PSV-530018 Misaligned flanges | Isolation of PSV |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2022-11-10 | 2023-03-25 | 70 |  |  | DF /G /76/DFGA-PSV-530018 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 10 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 20 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 25 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 30 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-03-19 | 2023-08-01 | 35 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-03-19 | 2023-08-01 | 40 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2023-03-19 | 2023-08-01 | 45 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
3 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100084664 | Load cell for DFF T-3936 Demulsifier | Empty tank and isolate |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-03-19 | 2023-08-01 | 50 |  |  | DF /F /75/DFFA-WE-390513A | Empty tank and isolate | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329997 | 3M COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 |  |  | 3 | 0 | W23-W24 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-06-18 | 2024-06-29 | 10 |  |  | DF /C /07/DFCM-A-5408 | COMP UNIT N2 GEN MAINT-DFCM-A-5408/09 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344331 | 6M INST AIR SYSTEM MAINT- DFGA-A-5450/51 | INST AIR SYSTEM MAINT- DFGA-A-5450/51 | AWSC | AWSC | 13 | 0 | Empty | 2024-09-13 | 2024-09-17 | 2024-09-13 | 2024-09-16 | 2024-09-13 | 2024-09-29 | 10 | AWSC | AWSC | DF /G /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYSTEM MAINT- DFGA-A-5450/51 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344331 | 6M INST AIR SYSTEM MAINT- DFGA-A-5450/51 | INST AIR SYSTEM MAINT- DFGA-A-5450/51 | AWSC | AWSC | 6 | 0 | Empty | 2024-09-13 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2024-09-13 | 2024-09-29 | 20 | AWSC | AWSC | DF /G /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYSTEM MAINT- DFGA-A-5450/51 | Unknown
2 | NOSD | WGN | MTN-INST | MTN-INST | 2200012098 | DAF Heleradio Replacement | DAF Heliradio Replacement |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2022-10-10 | 2022-11-24 | 10 |  |  | DF /C /08/DFCI-AC-14-08 | DAF Heliradio Replacement | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2021-04-17 | 2021-07-16 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-03 | 2021-04-17 | 2021-07-16 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-04 | 2025-01-04 | 2021-04-17 | 2021-07-16 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-05 | 2021-04-17 | 2021-07-16 | 70 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | PRODTECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-06 | 2021-04-17 | 2021-07-16 | 80 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-06 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 90 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-MECH | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-07 | 2021-04-17 | 2021-07-16 | 100 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
3 | DAN-FRYS | WDF | MTN-MECH | MTN-SCAF | 2100047713 | DFF-HCV-030120 internly leaking | Prepare freezing kit on site | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2021-04-17 | 2021-07-16 | 110 | AWSC | AWSC | DF /F /01/DFFA-HCV-030120 | Prepare freezing kit on site | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235853 | 4Y 400V N-SWB MAINT-DFGA-N-1842B | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235853 | 4Y 400V N-SWB MAINT-DFGA-N-1842B | ISOLATION ELECTRICAL | AWSC | AWSC | 33 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-30 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235853 | 4Y 400V N-SWB MAINT-DFGA-N-1842B | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-30 | 2024-10-03 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235853 | 4Y 400V N-SWB MAINT-DFGA-N-1842B | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B | ISOLATION ELECTRICAL | Unknown
4 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 3 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2024-12-30 | 2024-12-30 | 2023-10-30 | 2026-04-17 | 10 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-MECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 2 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2024-12-30 | 2024-12-31 | 2023-10-30 | 2026-04-17 | 20 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-RIGG | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 6 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2024-12-31 | 2025-01-01 | 2023-10-30 | 2026-04-17 | 30 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-MECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 6 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2024-12-31 | 2025-01-01 | 2023-10-30 | 2026-04-17 | 40 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-RIGG | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 6 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2025-01-01 | 2025-01-03 | 2023-10-30 | 2026-04-17 | 50 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-MECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 6 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2023-10-30 | 2026-04-17 | 60 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-MECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 3 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2023-10-30 | 2026-04-17 | 70 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | MTN-MECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 2 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2023-10-30 | 2026-04-17 | 80 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
4 | DFX-OIL | WDF | MTN-MECH | PRODTECH | 2100090000 | XCV-33073 Internal Leak | Isolate Hydraulic and Controls |  |  | 2 | 0 | Empty | 2024-12-30 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2023-10-30 | 2026-04-17 | 90 |  |  | DF /C /10/DFCM-XCV-33073 | Isolate Hydraulic and Controls | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235776 | 4Y 400V N-SWB MAINT-DFFB-N-1828-7 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828-07 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235776 | 4Y 400V N-SWB MAINT-DFFB-N-1828-7 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 33 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-22 | 2024-09-30 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828-07 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235776 | 4Y 400V N-SWB MAINT-DFFB-N-1828-7 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-09-30 | 2024-10-03 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828-07 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235776 | 4Y 400V N-SWB MAINT-DFFB-N-1828-7 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828-07 | DE-ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100045554 | Knækket håndtag på Block & Bleed. | Replace manifold |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-05-03 | 2021-09-30 | 10 |  |  | DF /F /37/DFFA-FIT-290128 | Replace manifold | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100045554 | Knækket håndtag på Block & Bleed. | Replace manifold |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-05-03 | 2021-09-30 | 20 |  |  | DF /F /37/DFFA-FIT-290128 | Replace manifold | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100045554 | Knækket håndtag på Block & Bleed. | Replace manifold |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-05-03 | 2021-09-30 | 30 |  |  | DF /F /37/DFFA-FIT-290128 | Replace manifold | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100045554 | Knækket håndtag på Block & Bleed. | Replace manifold |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-05-03 | 2021-09-30 | 40 |  |  | DF /F /37/DFFA-FIT-290128 | Replace manifold | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100045554 | Knækket håndtag på Block & Bleed. | Replace manifold |  |  | 0.1000000000000000055511151231 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-05-03 | 2021-09-30 | 50 |  |  | DF /F /37/DFFA-FIT-290128 | Replace manifold | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329509 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2024-06-14 | 10 | SCHSECE | SCHSECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329509 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-06-14 | 20 | SCHSECE | SCHSECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400329509 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-16 | 2024-05-17 | 2024-05-15 | 2024-06-14 | 30 | SCHSECE | SCHSECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400329509 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-17 | 2024-05-18 | 2024-05-15 | 2024-06-14 | 40 | SCHSECE | SCHSECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400329509 | 1Y HAZARD DRAIN PMPS MAINT-DFCM-P-5013/4 | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-15 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-15 | 2024-06-14 | 50 | SCHSECE | SCHSECE | DF /C /28/DFCM-T-5003 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235567 | 4Y 380V HT-DP-MAINT-DFCC-DP-1860 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /61/DFCC-DP-1860 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235567 | 4Y 380V HT-DP-MAINT-DFCC-DP-1860 | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 20 | AWSC | AWSC | DF /C /61/DFCC-DP-1860 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235567 | 4Y 380V HT-DP-MAINT-DFCC-DP-1860 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-05-13 | 30 | AWSC | AWSC | DF /C /61/DFCC-DP-1860 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235567 | 4Y 380V HT-DP-MAINT-DFCC-DP-1860 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-02-14 | 2023-05-13 | 40 | AWSC | AWSC | DF /C /61/DFCC-DP-1860 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | VEN-INSP | MTN-MECH | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 238 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-05-01 | 2024-06-29 | 2024-10-10 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 259 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-06-29 | 2024-09-02 | 2024-10-10 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 34 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-02 | 2024-09-10 | 2024-10-10 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-10 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PIPF | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-10 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-10 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-10 | 2024-10-10 | 2024-12-31 | 70 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PAIN | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 77 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-10 | 2024-09-18 | 2024-10-10 | 2024-12-31 | 80 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 20 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-18 | 2024-09-23 | 2024-10-10 | 2024-12-31 | 90 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-23 | 2024-09-25 | 2024-10-10 | 2024-12-31 | 100 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400298032 | PVI Major - DFFA-V-5017 | Material ordering | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-05-01 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-10-10 | 2024-12-31 | 110 | AWSCSECE | AWSCSECE | DF /F /27/DFFA-V-5017 | Material ordering | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100104837 | Findings after PM check, 3 Emg. light in | Isolate Equipment. |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2024-02-21 | 2024-07-05 | 10 |  |  | DF /C /62/EMERGENCY-LIGHTING-ACC.-IN | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104837 | Findings after PM check, 3 Emg. light in | Isolate Equipment. |  |  | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-02-21 | 2024-07-05 | 20 |  |  | DF /C /62/EMERGENCY-LIGHTING-ACC.-IN | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100104837 | Findings after PM check, 3 Emg. light in | Isolate Equipment. |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-02-21 | 2024-07-05 | 30 |  |  | DF /C /62/EMERGENCY-LIGHTING-ACC.-IN | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100104837 | Findings after PM check, 3 Emg. light in | Isolate Equipment. |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-02-21 | 2024-07-05 | 40 |  |  | DF /C /62/EMERGENCY-LIGHTING-ACC.-IN | Isolate Equipment. | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-07-30 | 2024-07-30 | 2020-10-08 | 2021-01-06 | 10 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 48 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-07-30 | 2024-08-04 | 2020-10-08 | 2021-01-06 | 20 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-05 | 2024-08-05 | 2020-10-08 | 2021-01-06 | 25 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 48 | 32 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-05 | 2024-08-05 | 2020-10-08 | 2021-01-06 | 30 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-05 | 2024-08-06 | 2020-10-08 | 2021-01-06 | 40 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-06 | 2024-08-07 | 2020-10-08 | 2021-01-06 | 50 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | INP-SITE | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 2 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-07 | 2024-08-07 | 2020-10-08 | 2021-01-06 | 60 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 12 | 12 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-07 | 2024-08-07 | 2020-10-08 | 2021-01-06 | 70 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-08 | 2024-08-08 | 2020-10-08 | 2021-01-06 | 80 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 24 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-08 | 2024-08-10 | 2020-10-08 | 2021-01-06 | 90 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | QAQCPAIN | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 2 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-10 | 2024-08-10 | 2020-10-08 | 2021-01-06 | 100 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 8 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-10 | 2024-08-11 | 2020-10-08 | 2021-01-06 | 105 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100038444 | ANOSR DFC Crane pedestal support flange | HEB300B support cut about crane pedestal | PCNF | PCNF | 16 | 0 | Empty | 2024-07-30 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2020-10-08 | 2021-01-06 | 110 | PCNF | PCNF | DF /C /86/CRANE-PEDESTAL | HEB300B support cut about crane pedestal | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235735 | 4Y 380V E-SWB MAINT DFEZ-N-1804-01 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-09-18 | 2023-01-30 | 2023-04-13 | 10 | AWSCSCH | AWSCSCH | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235735 | 4Y 380V E-SWB MAINT DFEZ-N-1804-01 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 22 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-18 | 2024-09-21 | 2023-01-30 | 2023-04-13 | 20 | AWSCSCH | AWSCSCH | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235735 | 4Y 380V E-SWB MAINT DFEZ-N-1804-01 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 30 | AWSCSCH | AWSCSCH | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235735 | 4Y 380V E-SWB MAINT DFEZ-N-1804-01 | ISOLATION BY PRODUCTION | AWSCSCH | AWSCSCH | 2 | 0 | W07-W08 | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 40 | AWSCSCH | AWSCSCH | DF /E /05/DFEZ-N-1804 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2021-07-28 | 2021-12-25 | 10 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-16 | 2021-07-28 | 2021-12-25 | 20 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-16 | 2021-07-28 | 2021-12-25 | 30 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-17 | 2021-07-28 | 2021-12-25 | 40 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-17 | 2021-07-28 | 2021-12-25 | 50 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-18 | 2021-07-28 | 2021-12-25 | 60 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-18 | 2021-07-28 | 2021-12-25 | 70 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2021-07-28 | 2021-12-25 | 80 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2021-07-28 | 2021-12-25 | 90 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2021-07-28 | 2021-12-25 | 100 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2021-07-28 | 2021-12-25 | 110 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2021-07-28 | 2021-12-25 | 120 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100049598 | Replace DFG-XCV-500880 vil ikke åbne | Remove Insulation |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2021-07-28 | 2021-12-25 | 130 |  |  | DF /G /27/DFGA-XCV-500880 | Remove Insulation | Unknown
2 | NOSD | WDF | MTN-TURB | PRODTECH | 2100078016 | Hydr oil filtration/replacement DFE FWP | Isolate firewater pump/engine from start | PCNFSCH | PCNFSCH | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-11-16 | 2022-12-31 | 10 | PCNFSCH | PCNFSCH | DF /E /01/DFEY-T-0327 | Isolate firewater pump/engine from start | Unknown
2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100078016 | Hydr oil filtration/replacement DFE FWP | Isolate firewater pump/engine from start | PCNFSCH | PCNFSCH | 50 | 76 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-11-16 | 2022-12-31 | 20 | PCNFSCH | PCNFSCH | DF /E /01/DFEY-T-0327 | Isolate firewater pump/engine from start | Unknown
2 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100078016 | Hydr oil filtration/replacement DFE FWP | Isolate firewater pump/engine from start | PCNFSCH | PCNFSCH | 50 | 20 | W21-W22 | 2024-05-20 | 2024-05-20 | 2023-06-20 | 2024-01-24 | 2022-11-16 | 2022-12-31 | 30 | PCNFSCH | PCNFSCH | DF /E /01/DFEY-T-0327 | Isolate firewater pump/engine from start | Unknown
2 | NOSD | WDF | MTN-TURB | PRODTECH | 2100078016 | Hydr oil filtration/replacement DFE FWP | Isolate firewater pump/engine from start | PCNFSCH | PCNFSCH | 3 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2022-11-16 | 2022-12-31 | 40 | PCNFSCH | PCNFSCH | DF /E /01/DFEY-T-0327 | Isolate firewater pump/engine from start | Unknown
3 | DFA-W19 | WDF | MTN-MECH | MTN-INST | 2100096132 | DFA-19 Choke fail to open on demand | Troubshoot on choke fail to open. |  |  | 4 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-14 | 2024-01-27 | 10 |  |  | DF /A /55/DFAA-CVA-30501 | Troubshoot on choke fail to open. | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400298208 | 1Y SDV LUBE/FUNC TEST IPHP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-09-22 | 2024-09-24 | 2023-12-12 | 2024-01-11 | 10 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400298208 | 1Y SDV LUBE/FUNC TEST IPHP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 38 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-09-25 | 2024-10-04 | 2023-12-12 | 2024-01-11 | 20 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-INST | 2400298208 | 1Y SDV LUBE/FUNC TEST IPHP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-10-04 | 2024-10-04 | 2023-12-12 | 2024-01-11 | 30 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400298208 | 1Y SDV LUBE/FUNC TEST IPHP - DFF | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-10-07 | 2024-10-04 | 2024-10-07 | 2023-12-12 | 2024-01-11 | 40 | SECE | SECE | DF /F /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
3 | NE | WDF | MTN-TELE | MTN-TELE | 2100095378 | DFC-S-CS-17, service problem | DFC-S-CS-17 restart | SCH | SCH | 6 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-07-30 | 2023-08-14 | 10 | SCH | SCH | DF /C /04/DFCI-FP-2012-1 | DFC-S-CS-17 restart | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087264 | Battery fault on emergency light | Isolate and prove dead. |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-27 | 2023-09-09 | 10 |  |  | DF /F /05/DFFB-DP-1832B-02-Q04 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087264 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-27 | 2023-09-09 | 20 |  |  | DF /F /05/DFFB-DP-1832B-02-Q04 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087264 | Battery fault on emergency light | Isolate and prove dead. |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-27 | 2023-09-09 | 30 |  |  | DF /F /05/DFFB-DP-1832B-02-Q04 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087264 | Battery fault on emergency light | Isolate and prove dead. |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-04-27 | 2023-09-09 | 40 |  |  | DF /F /05/DFFB-DP-1832B-02-Q04 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 8 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-18 | 2024-09-20 | 2021-12-17 | 2022-03-17 | 20 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 4 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-20 | 2024-09-21 | 2021-12-17 | 2022-03-17 | 25 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 16 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-20 | 2024-09-22 | 2021-12-17 | 2022-03-17 | 30 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 20 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-18 | 2024-09-20 | 2021-12-17 | 2022-03-17 | 33 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 32 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-22 | 2024-09-26 | 2021-12-17 | 2022-03-17 | 35 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 8 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-26 | 2024-09-27 | 2021-12-17 | 2022-03-17 | 40 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 0 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-27 | 2024-09-27 | 2021-12-17 | 2022-03-17 | 45 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 32 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-02-24 | 2025-02-28 | 2021-12-17 | 2022-03-17 | 50 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 24 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-02-28 | 2025-02-28 | 2021-12-17 | 2022-03-17 | 55 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 8 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-02-28 | 2025-03-02 | 2021-12-17 | 2022-03-17 | 60 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 2 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-03-02 | 2025-03-02 | 2021-12-17 | 2022-03-17 | 65 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 8 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-02-28 | 2025-03-01 | 2021-12-17 | 2022-03-17 | 70 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 10 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2024-09-18 | 2024-09-19 | 2021-12-17 | 2022-03-17 | 72 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 4 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-03-03 | 2025-03-04 | 2021-12-17 | 2022-03-17 | 75 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 4 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-03-02 | 2025-03-03 | 2021-12-17 | 2022-03-17 | 80 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100059023 | DFE-P-3960 unusual sound | Reinstall motor cables for PM-3960 |  |  | 8 | 0 | W07-W08 | 2024-09-18 | 2025-03-05 | 2025-03-04 | 2025-03-05 | 2021-12-17 | 2022-03-17 | 85 |  |  | DF /E /75/DFEZ-P-3960B | Reinstall motor cables for PM-3960 | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400298230 | 3M SMOKE CABINS AIR FILT.REPLACE -DFC/G | SMOKE CABINS AIR FILT.REPLACE -DFC/G |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-12-28 | 2024-01-12 | 10 |  |  | DF /C /82/DFCC-A-1332 | SMOKE CABINS AIR FILT.REPLACE -DFC/G | Unknown
1 | DFF-3580 | WDF | MTN-ELEC | VEN-ELEC | 2100106972 | Defect power supply in relay | additional materials |  |  | 0 | 0 | Empty | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-24 | 10 |  |  | DF /F /61/DFFB-N-1831-02-02 | additional materials | Unknown
1 | DFF-3580 | WDF | MTN-ELEC | VEN-ELEC | 2100106972 | Defect power supply in relay | additional materials |  |  | 12 | 0 | Empty | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-24 | 20 |  |  | DF /F /61/DFFB-N-1831-02-02 | additional materials | Unknown
1 | DFF-3580 | WDF | MTN-ELEC | VEN-ELEC | 2100106972 | Defect power supply in relay | additional materials |  |  | 0 | 0 | Empty | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-09 | 2024-02-24 | 30 |  |  | DF /F /61/DFFB-N-1831-02-02 | additional materials | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100105417 | DFB-15 MCV ZSC indication missing | DFB-15 MCV ZSC investigation |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-02-18 | 2024-07-02 | 10 |  |  | DF /B /10/DFBA-MCV-30314 | DFB-15 MCV ZSC investigation | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 1 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 10 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 3 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 20 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 10 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 30 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 8 | 15 | W13-W14 | 2024-09-22 | 2024-09-22 | 2023-11-10 | 2023-11-13 | 2023-04-06 | 2025-09-22 | 35 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 10 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 40 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 24 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 50 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 1 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 60 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100076006 | DFG/78 A/C unit enclosure outside | Isolate-de-isolate | PCNF | PCNF | 0 | 0 | W13-W14 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-06 | 2025-09-22 | 70 | PCNF | PCNF | DF /G /78/DFGA-A-6140 | Isolate-de-isolate | Unknown
4 | D-FLARE | WGN | MTN-MECH | PRODTECH | 2200003040 | CMAT:Replace DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | AWSC | AWSC | 48 | 0 | Empty | 2025-01-01 | 2025-01-29 | 2025-01-01 | 2025-01-12 | 2018-08-14 | 2019-01-11 | 10 | AWSC | AWSC | DF /C /10/DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-RIGG | 2200003040 | CMAT:Replace DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-29 | 2025-01-13 | 2025-01-15 | 2018-08-14 | 2019-01-11 | 15 | AWSC | AWSC | DF /C /10/DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | Unknown
4 | D-FLARE | WGN | MTN-MECH | MTN-MECH | 2200003040 | CMAT:Replace DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-29 | 2025-01-15 | 2025-01-17 | 2018-08-14 | 2019-01-11 | 20 | AWSC | AWSC | DF /C /10/DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | Unknown
4 | D-FLARE | WGN | MTN-MECH | PRODTECH | 2200003040 | CMAT:Replace DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | AWSC | AWSC | 48 | 0 | Empty | 2025-01-01 | 2025-01-29 | 2025-01-17 | 2025-01-29 | 2018-08-14 | 2019-01-11 | 30 | AWSC | AWSC | DF /C /10/DFCI-HCV-33030-D | L3 Isolation of DFCI-HCV-33030-D | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100098377 | SWLP 5304 header tank LT faulty | Calibrate transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-19 | 2024-03-02 | 10 |  |  | DF /F /50/DFFA-LIT-530643 | Calibrate transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100098377 | SWLP 5304 header tank LT faulty | Calibrate transmitter |  |  | 2.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-19 | 2024-03-02 | 20 |  |  | DF /F /50/DFFA-LIT-530643 | Calibrate transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100098377 | SWLP 5304 header tank LT faulty | Calibrate transmitter |  |  | 0.5 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-10-19 | 2024-03-02 | 30 |  |  | DF /F /50/DFFA-LIT-530643 | Calibrate transmitter | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 24 | 24 | Empty | 2024-04-24 | 2024-12-29 | 2024-04-25 | 2024-04-28 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 5 | 6 | Empty | 2024-04-24 | 2024-12-29 | 2024-04-25 | 2024-04-28 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 6 | Empty | 2024-04-24 | 2024-12-29 | 2024-04-25 | 2024-04-28 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 4 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 12 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 5 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 4 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 2 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-12-29 | 2024-12-29 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284289 | PSV Calibration - DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | PCNFAWSCSECE | PCNFAWSCSECE | 0 | 0 | Empty | 2024-04-24 | 2024-12-29 | 2024-10-29 | 2024-10-29 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSCSECE | PCNFAWSCSECE | DF /F /70/DFFA-PSV-570218 | DFFA-PSV-570218 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235721 | 4Y 380V E-SWB MAINT DFCI-N-1812-R01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235721 | 4Y 380V E-SWB MAINT DFCI-N-1812-R01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 8 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235721 | 4Y 380V E-SWB MAINT DFCI-N-1812-R01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235721 | 4Y 380V E-SWB MAINT DFCI-N-1812-R01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235721 | 4Y 380V E-SWB MAINT DFCI-N-1812-R01 | ISOLATION BY EIA | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-11 | 2024-05-11 | 2024-05-11 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | ISOLATION BY EIA | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-03-27 | 2023-03-27 | 2022-02-14 | 2022-07-14 | 10 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-03-27 | 2023-03-29 | 2022-02-14 | 2022-07-14 | 20 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-03-30 | 2023-04-01 | 2022-02-14 | 2022-07-14 | 30 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-02 | 2023-04-03 | 2022-02-14 | 2022-07-14 | 40 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 9 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-03 | 2023-04-03 | 2022-02-14 | 2022-07-14 | 44 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 16 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-03 | 2023-04-07 | 2022-02-14 | 2022-07-14 | 50 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-07 | 2023-04-10 | 2022-02-14 | 2022-07-14 | 60 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009253 | Insulation assist bilfinger 21309(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-10 | 2023-04-10 | 2023-04-10 | 2022-02-14 | 2022-07-14 | 70 |  |  | DF /G /27/DFG-2-WOS-034-0050-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100075998 | DFFW/78 Overpresure system in eng room | Troubleshooting - Bypassed?? |  |  | 4 | 7 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-11-21 | 2023-04-05 | 10 |  |  | DF /F /78/DFFA-A-6102 | Troubleshooting - Bypassed?? | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048568 | DKDF0005 Leak fra pre-filter for C-5440 | Spare parts Order |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-27 | 2021-06-06 | 10 |  |  | DF /F /53/DFFB-C-5440 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048568 | DKDF0005 Leak fra pre-filter for C-5440 | Spare parts Order |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-27 | 2021-06-06 | 20 |  |  | DF /F /53/DFFB-C-5440 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048568 | DKDF0005 Leak fra pre-filter for C-5440 | Spare parts Order |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2021-04-27 | 2021-06-06 | 30 |  |  | DF /F /53/DFFB-C-5440 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100048568 | DKDF0005 Leak fra pre-filter for C-5440 | Spare parts Order |  |  | 3 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2021-04-27 | 2021-06-06 | 40 |  |  | DF /F /53/DFFB-C-5440 | Spare parts Order | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100048568 | DKDF0005 Leak fra pre-filter for C-5440 | Spare parts Order |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2021-04-27 | 2021-06-06 | 50 |  |  | DF /F /53/DFFB-C-5440 | Spare parts Order | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-MECH | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 102 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-05-01 | 2024-05-26 | 2024-10-10 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-SCAF | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 222 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-05-26 | 2024-07-20 | 2024-10-10 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-ELEC | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 25 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-07-21 | 2024-07-27 | 2024-10-10 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-RIGG | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 20 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-07-27 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-PIPF | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-ROPE | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-INST | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-PAIN | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 37 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-05 | 2024-10-10 | 2024-12-31 | 80 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | PRODTECH | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 5 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-05 | 2024-08-06 | 2024-10-10 | 2024-12-31 | 90 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | VEN-INSP | 2400298040 | PVI Major - DFGA-S-4153 | Mechanical work | AWSC | AWSC | 12 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2024-10-10 | 2024-12-31 | 100 | AWSC | AWSC | DF /G /30/DFGA-S-4153 | Mechanical work | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2022-05-31 | 2022-10-28 | 10 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-SCAF | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2022-05-31 | 2022-10-28 | 20 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2022-05-31 | 2022-10-28 | 30 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2022-05-31 | 2022-10-28 | 40 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-RIGG | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2022-05-31 | 2022-10-28 | 60 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2022-05-31 | 2022-10-28 | 70 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2022-05-31 | 2022-10-28 | 80 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | PRODTECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2022-05-31 | 2022-10-28 | 90 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2022-05-31 | 2022-10-28 | 100 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
4 | DAN-WI | WDF | MTN-MECH | MTN-MECH | 2100064529 | Manifold HCVer intern utæt DFF-19 | Build Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2022-05-31 | 2022-10-28 | 110 |  |  | DF /F /55/DFF19-WATER-INJECTION-LINE | Build Scaffold | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325738 | 1Y CHEMICAL INJ. PUMP SKID A-3942 | 1Y CHEMICAL INJ. PUMP SKID A-3942 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /F /75/DFFA-A-3942 | 1Y CHEMICAL INJ. PUMP SKID A-3942 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400325738 | 1Y CHEMICAL INJ. PUMP SKID A-3942 | 1Y CHEMICAL INJ. PUMP SKID A-3942 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-08-01 | 2024-04-26 | 2024-06-01 | 20 |  |  | DF /F /75/DFFA-A-3942 | 1Y CHEMICAL INJ. PUMP SKID A-3942 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-07-29 | 2024-07-30 | 2018-09-27 | 2019-02-24 | 10 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-07-30 | 2024-07-30 | 2018-09-27 | 2019-02-24 | 20 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-07-30 | 2024-07-31 | 2018-09-27 | 2019-02-24 | 30 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-07-31 | 2024-08-01 | 2018-09-27 | 2019-02-24 | 40 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-01 | 2024-08-02 | 2018-09-27 | 2019-02-24 | 50 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-02 | 2018-09-27 | 2019-02-24 | 60 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-02 | 2024-08-03 | 2018-09-27 | 2019-02-24 | 70 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022445 | Exchange internals PCV-080501B | L3 Prepare Rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-04 | 2024-08-03 | 2024-08-04 | 2018-09-27 | 2019-02-24 | 80 |  |  | DF /G /76/DFGA-PCV-080501B | L3 Prepare Rigging equipment | Unknown
A | DFF-1630 | WPM | MTN-MECH | PRODTECH | 2400221280 | 40KH BDV/SDV MAINT, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 0 | W29-W30 | 2024-07-16 | 2024-07-20 | 2024-07-16 | 2024-07-17 | 2022-10-27 | 2023-01-15 | 10 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-MECH | MTN-MECH | 2400221280 | 40KH BDV/SDV MAINT, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 6 | 4 | W29-W30 | 2024-07-16 | 2024-07-20 | 2024-07-17 | 2024-07-19 | 2022-10-27 | 2023-01-15 | 20 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
A | DFF-1630 | WPM | MTN-MECH | PRODTECH | 2400221280 | 40KH BDV/SDV MAINT, COUNTER-A-1630 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 5 | 0 | W29-W30 | 2024-07-16 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2022-10-27 | 2023-01-15 | 30 | AWSCSECE | AWSCSECE | DF /F /60/DFFA-A-1630 | ISOLATION BY PRODUCTION | Unknown
D | DAB-WI | WPM | PRODTECH | PRODTECH | 2400342609 | PIGGING, P3010 12" DFF-DAD WI 2W | P3010_DFF-DAD | AWSC | AWSC | 4 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-23 | 2024-08-29 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673010 | P3010_DFF-DAD | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281093 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | Remove scaffold | SECE | SECE | 1 | 1 | Empty | 2024-07-05 | 2024-07-06 | 2024-07-01 | 2024-07-05 | 2023-09-04 | 2023-10-04 | 10 | SECE | SECE | DF /E /01/DFEY-A-0303 | Remove scaffold | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281093 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | Remove scaffold | SECE | SECE | 12 | 12 | Empty | 2024-07-05 | 2024-07-06 | 2024-07-01 | 2024-07-05 | 2023-09-04 | 2023-10-04 | 20 | SECE | SECE | DF /E /01/DFEY-A-0303 | Remove scaffold | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281093 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | Remove scaffold | SECE | SECE | 1 | 1 | Empty | 2024-07-05 | 2024-07-06 | 2024-07-04 | 2024-07-05 | 2023-09-04 | 2023-10-04 | 30 | SECE | SECE | DF /E /01/DFEY-A-0303 | Remove scaffold | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400281093 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | Remove scaffold | SECE | SECE | 2 | 2 | Empty | 2024-07-05 | 2024-07-06 | 2024-07-04 | 2024-07-05 | 2023-09-04 | 2023-10-04 | 40 | SECE | SECE | DF /E /01/DFEY-A-0303 | Remove scaffold | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400281093 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | Remove scaffold | SECE | SECE | 8 | 4 | Empty | 2024-07-05 | 2024-07-06 | 2024-07-04 | 2024-07-05 | 2023-09-04 | 2023-10-04 | 50 | SECE | SECE | DF /E /01/DFEY-A-0303 | Remove scaffold | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400281093 | 1Y HVAC SUPP FIRE PUMP CHECK DFEY-A-0303 | Remove scaffold | SECE | SECE | 4 | 4 | Empty | 2024-07-05 | 2024-07-06 | 2024-07-05 | 2024-07-06 | 2023-09-04 | 2023-10-04 | 60 | SECE | SECE | DF /E /01/DFEY-A-0303 | Remove scaffold | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235694 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR07-JA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235694 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR07-JA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235694 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR07-JA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235654 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R13 | 400V N-SWB INSP-DFCI-N-1802-R13 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R13F | 400V N-SWB INSP-DFCI-N-1802-R13 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235654 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R13 | 400V N-SWB INSP-DFCI-N-1802-R13 | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R13F | 400V N-SWB INSP-DFCI-N-1802-R13 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235654 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R13 | 400V N-SWB INSP-DFCI-N-1802-R13 | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R13F | 400V N-SWB INSP-DFCI-N-1802-R13 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235654 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R13 | 400V N-SWB INSP-DFCI-N-1802-R13 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R13F | 400V N-SWB INSP-DFCI-N-1802-R13 | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-MECH | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 102 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-05-01 | 2024-05-26 | 2024-10-10 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-SCAF | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 222 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-05-26 | 2024-07-20 | 2024-10-10 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-ELEC | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 25 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-07-21 | 2024-07-27 | 2024-10-10 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-RIGG | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 20 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-07-27 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-PIPF | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-ROPE | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-INST | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 0 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-01 | 2024-10-10 | 2024-12-31 | 70 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | MTN-PAIN | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 37 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-01 | 2024-08-05 | 2024-10-10 | 2024-12-31 | 80 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | PRODTECH | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 5 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-05 | 2024-08-06 | 2024-10-10 | 2024-12-31 | 90 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
A | DFG-IPHP | WPM | VEN-INSP | VEN-INSP | 2400298039 | PVI Major - DFGA-S-4146 | Mechanical work | AWSC | AWSC | 12 | 0 | Empty | 2024-05-01 | 2024-08-07 | 2024-08-06 | 2024-08-07 | 2024-10-10 | 2024-12-31 | 100 | AWSC | AWSC | DF /G /30/DFGA-S-4146 | Mechanical work | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-INST | 2100112900 | DFFB minox seawater dublex filter fail. | DFFB minox seawater dublex filter fail. |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-05-20 | 2024-07-04 | 10 |  |  | DF /F /54/DFFB-FT-5312 | DFFB minox seawater dublex filter fail. | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112900 | DFFB minox seawater dublex filter fail. | DFFB minox seawater dublex filter fail. |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-05-20 | 2024-07-04 | 20 |  |  | DF /F /54/DFFB-FT-5312 | DFFB minox seawater dublex filter fail. | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112900 | DFFB minox seawater dublex filter fail. | DFFB minox seawater dublex filter fail. |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-05-20 | 2024-07-04 | 30 |  |  | DF /F /54/DFFB-FT-5312 | DFFB minox seawater dublex filter fail. | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112900 | DFFB minox seawater dublex filter fail. | DFFB minox seawater dublex filter fail. |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-05-20 | 2024-07-04 | 40 |  |  | DF /F /54/DFFB-FT-5312 | DFFB minox seawater dublex filter fail. | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100081820 | ANO Leak detected in sewage piping | Leak testing Sewage/Vacuum Sys. |  |  | 48 | 0 | Empty | 2024-09-15 | 2024-10-11 | 2024-09-15 | 2024-09-17 | 2023-03-10 | 2023-07-23 | 10 |  |  | DF /C /82/DFCM-A-5101 | Leak testing Sewage/Vacuum Sys. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100081820 | ANO Leak detected in sewage piping | Leak testing Sewage/Vacuum Sys. |  |  | 200 | 0 | Empty | 2024-09-15 | 2024-10-11 | 2024-09-17 | 2024-10-04 | 2023-03-10 | 2023-07-23 | 20 |  |  | DF /C /82/DFCM-A-5101 | Leak testing Sewage/Vacuum Sys. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100081820 | ANO Leak detected in sewage piping | Leak testing Sewage/Vacuum Sys. |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-10-11 | 2024-10-04 | 2024-10-06 | 2023-03-10 | 2023-07-23 | 30 |  |  | DF /C /82/DFCM-A-5101 | Leak testing Sewage/Vacuum Sys. | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100081820 | ANO Leak detected in sewage piping | Leak testing Sewage/Vacuum Sys. |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-10-11 | 2024-10-06 | 2024-10-11 | 2023-03-10 | 2023-07-23 | 40 |  |  | DF /C /82/DFCM-A-5101 | Leak testing Sewage/Vacuum Sys. | Unknown
D | NOSD | WPM | PRODTECH | PRODTECH | 2400330107 | PIGGING, P3014 16" DFF-HDA WI 2W | P3014_DFF-HDA | AWSC | AWSC | 4 | 0 | Empty | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-06-22 | 2024-06-23 | 2024-06-29 | 10 | AWSC | AWSC | DF /F /54/DFFY-PL-673014 | P3014_DFF-HDA | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337672 | 6M SAND REMOVAL SYSTEM MAINT-DFFA-A-5002 | SAND REMOVAL SYSTEM INSP-DFFA-A-5002 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-08-05 | 2024-08-24 | 10 |  |  | DF /F /27/DFFA-A-5002 | SAND REMOVAL SYSTEM INSP-DFFA-A-5002 | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 1 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2021-04-06 | 2021-07-05 | 10 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-16 | 2021-04-06 | 2021-07-05 | 20 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2021-04-06 | 2021-07-05 | 30 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 12 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-16 | 2021-04-06 | 2021-07-05 | 35 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2021-04-06 | 2021-07-05 | 40 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 3 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2021-04-06 | 2021-07-05 | 50 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 1 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2021-04-06 | 2021-07-05 | 60 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100047333 | DFA: Replace Corroded valve for cooling | Order valve |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2021-04-06 | 2021-07-05 | 70 |  |  | DF /A /78/DFAA-X-6102 | Order valve | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400325742 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39710 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39710 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /B /75/DFBA-A-39710 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39710 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400309006 | 1Y BDV LUBE/FUNC TEST - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | W21-W22 | 2024-05-20 | 2024-05-30 | 2024-05-20 | 2024-05-22 | 2024-02-22 | 2024-03-23 | 10 | SECE | SECE | DF /G /34/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400309006 | 1Y BDV LUBE/FUNC TEST - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 24 | 0 | W21-W22 | 2024-05-20 | 2024-05-30 | 2024-05-22 | 2024-05-28 | 2024-02-22 | 2024-03-23 | 20 | SECE | SECE | DF /G /34/BDV | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400309006 | 1Y BDV LUBE/FUNC TEST - DFG | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | W21-W22 | 2024-05-20 | 2024-05-30 | 2024-05-28 | 2024-05-30 | 2024-02-22 | 2024-03-23 | 30 | SECE | SECE | DF /G /34/BDV | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099371 | DFC/78: Replace Battery | Isolate-de-isolate |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-18 | 2023-11-18 | 2024-04-01 | 10 |  |  | DF /C /78/DFCI-X-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100099371 | DFC/78: Replace Battery | Isolate-de-isolate |  |  | 6 | 0 | Empty | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-20 | 2023-11-18 | 2024-04-01 | 20 |  |  | DF /C /78/DFCI-X-6101 | Isolate-de-isolate | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ROUS | 2100099371 | DFC/78: Replace Battery | Isolate-de-isolate |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-11-18 | 2024-04-01 | 30 |  |  | DF /C /78/DFCI-X-6101 | Isolate-de-isolate | Unknown
3 | DFE-OIL | WDF | MTN-INST | MTN-SCAF | 2100052654 | Hydraulik lækage. | Tightend fittings. If still leaking iden |  |  | 15 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-19 | 2021-07-29 | 2021-09-07 | 10 |  |  | DF /F /07/DFF-4-OH-059-7010-AS-U | Tightend fittings. If still leaking iden | Unknown
3 | DFE-OIL | WDF | MTN-INST | MTN-INST | 2100052654 | Hydraulik lækage. | Tightend fittings. If still leaking iden |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-19 | 2021-07-29 | 2021-09-07 | 20 |  |  | DF /F /07/DFF-4-OH-059-7010-AS-U | Tightend fittings. If still leaking iden | Unknown
3 | DFE-OIL | WDF | MTN-INST | MTN-SCAF | 2100052654 | Hydraulik lækage. | Tightend fittings. If still leaking iden |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-22 | 2021-07-29 | 2021-09-07 | 30 |  |  | DF /F /07/DFF-4-OH-059-7010-AS-U | Tightend fittings. If still leaking iden | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 10 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 20 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 24 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-16 | 2024-07-18 | 2023-06-03 | 2025-11-19 | 30 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-19 | 2024-07-20 | 2023-06-03 | 2025-11-19 | 40 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-20 | 2024-07-20 | 2023-06-03 | 2025-11-19 | 50 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 12 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-20 | 2024-07-21 | 2023-06-03 | 2025-11-19 | 60 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-21 | 2024-07-22 | 2023-06-03 | 2025-11-19 | 70 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-22 | 2024-07-23 | 2023-06-03 | 2025-11-19 | 80 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 4 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2023-06-03 | 2025-11-19 | 90 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012642 | PSV Exchange - DFFA-PSV-330014 - PSV 202 | new PSV |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2023-06-03 | 2025-11-19 | 100 |  |  | DF /F /10/DFFA-PSV-330014 | new PSV | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024943 | DFF: Replace isolation on exhaust. | Replace isolation on exhaust |  |  | 1 | 0 | 2023 - PARKED | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-01-15 | 2020-04-14 | 10 |  |  | DF /F /78/DFFA-A-6101 | Replace isolation on exhaust | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024943 | DFF: Replace isolation on exhaust. | Replace isolation on exhaust |  |  | 4 | 0 | 2023 - PARKED | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2020-01-15 | 2020-04-14 | 20 |  |  | DF /F /78/DFFA-A-6101 | Replace isolation on exhaust | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100024943 | DFF: Replace isolation on exhaust. | Replace isolation on exhaust |  |  | 1 | 0 | 2023 - PARKED | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2020-01-15 | 2020-04-14 | 30 |  |  | DF /F /78/DFFA-A-6101 | Replace isolation on exhaust | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235656 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R11 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R11A1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235656 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R11 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R11A1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235656 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R11 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R11A1 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235656 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R11 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R11A1 | DE-ISOLATION ELECTRICAL | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100104296 | Replace gas detektor DFFA-GD-124609 | Replace gas detector | SECE | SECE | 1 | 0 | Empty | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2023-12-28 | 2024-02-11 | 10 | SECE | SECE | DF /F /03/DFFA-GD-124609 | Replace gas detector | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100104296 | Replace gas detektor DFFA-GD-124609 | Replace gas detector | SECE | SECE | 4 | 0 | Empty | 2024-07-30 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-12-28 | 2024-02-11 | 20 | SECE | SECE | DF /F /03/DFFA-GD-124609 | Replace gas detector | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100104199 | DFB-16 XCV-30410 indic. not workin | Safe the line |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-01-21 | 2024-06-04 | 10 |  |  | DF /B /10/DFBA-XCV-30410 | Safe the line | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100104199 | DFB-16 XCV-30410 indic. not workin | Safe the line |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-01-21 | 2024-06-04 | 20 |  |  | DF /B /10/DFBA-XCV-30410 | Safe the line | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100080525 | DFA/78 Replace K80 with new | order spare contactor and Diode |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-04 | 2025-12-20 | 10 |  |  | DF /A /78/DFAA-X-6102 | order spare contactor and Diode | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080525 | DFA/78 Replace K80 with new | order spare contactor and Diode |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-07-04 | 2025-12-20 | 20 |  |  | DF /A /78/DFAA-X-6102 | order spare contactor and Diode | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100080525 | DFA/78 Replace K80 with new | order spare contactor and Diode |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-04 | 2025-12-20 | 30 |  |  | DF /A /78/DFAA-X-6102 | order spare contactor and Diode | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100023881 | PMAT:XCV kører træg / udskift | Rigger ass ophæng af spool + rigge venti |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2017-09-18 | 2017-12-17 | 5 |  |  | DF /C /51/DFCM-XCV-52213 | Rigger ass ophæng af spool + rigge venti | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023881 | PMAT:XCV kører træg / udskift | Rigger ass ophæng af spool + rigge venti |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2017-09-18 | 2017-12-17 | 10 |  |  | DF /C /51/DFCM-XCV-52213 | Rigger ass ophæng af spool + rigge venti | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023881 | PMAT:XCV kører træg / udskift | Rigger ass ophæng af spool + rigge venti |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2017-09-18 | 2017-12-17 | 30 |  |  | DF /C /51/DFCM-XCV-52213 | Rigger ass ophæng af spool + rigge venti | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023881 | PMAT:XCV kører træg / udskift | Rigger ass ophæng af spool + rigge venti |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2017-09-18 | 2017-12-17 | 40 |  |  | DF /C /51/DFCM-XCV-52213 | Rigger ass ophæng af spool + rigge venti | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400263657 | 1Y GLYCOL REGEN PKG MAINT-DFGA-A-4140 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 0 | W33-W34 | 2024-08-12 | 2024-08-24 | 2024-08-12 | 2024-08-13 | 2023-06-20 | 2023-07-20 | 10 | SECE | SECE | DF /G /30/DFGA-A-4140 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400263657 | 1Y GLYCOL REGEN PKG MAINT-DFGA-A-4140 | ISOLATION BY PRODUCTION | SECE | SECE | 20 | 0 | W33-W34 | 2024-08-12 | 2024-08-24 | 2024-08-13 | 2024-08-18 | 2023-06-20 | 2023-07-20 | 20 | SECE | SECE | DF /G /30/DFGA-A-4140 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-INST | 2400263657 | 1Y GLYCOL REGEN PKG MAINT-DFGA-A-4140 | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-24 | 2024-08-18 | 2024-08-21 | 2023-06-20 | 2023-07-20 | 30 | SECE | SECE | DF /G /30/DFGA-A-4140 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-ELEC | 2400263657 | 1Y GLYCOL REGEN PKG MAINT-DFGA-A-4140 | ISOLATION BY PRODUCTION | SECE | SECE | 8 | 0 | W33-W34 | 2024-08-12 | 2024-08-24 | 2024-08-21 | 2024-08-23 | 2023-06-20 | 2023-07-20 | 40 | SECE | SECE | DF /G /30/DFGA-A-4140 | ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400263657 | 1Y GLYCOL REGEN PKG MAINT-DFGA-A-4140 | ISOLATION BY PRODUCTION | SECE | SECE | 5 | 0 | W33-W34 | 2024-08-12 | 2024-08-24 | 2024-08-23 | 2024-08-24 | 2023-06-20 | 2023-07-20 | 50 | SECE | SECE | DF /G /30/DFGA-A-4140 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-03 | 2024-06-03 | 2023-06-03 | 2025-11-19 | 10 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-03 | 2024-06-04 | 2023-06-03 | 2025-11-19 | 20 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 5 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-04 | 2024-06-05 | 2023-06-03 | 2025-11-19 | 30 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 0 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-05 | 2024-06-05 | 2023-06-03 | 2025-11-19 | 40 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 2 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-05 | 2024-06-06 | 2023-06-03 | 2025-11-19 | 50 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 5 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-06 | 2024-06-07 | 2023-06-03 | 2025-11-19 | 60 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 4 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-07 | 2024-06-08 | 2023-06-03 | 2025-11-19 | 70 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 0 | 0 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-08 | 2024-06-08 | 2023-06-03 | 2025-11-19 | 80 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-SCAF | 2200012586 | PSV - Calibration DFFA-PSV-570038 - PSV | new PSV | PCNFSECE | PCNFSECE | 8 | 4 | Empty | 2024-06-03 | 2024-06-10 | 2024-06-08 | 2024-06-10 | 2023-06-03 | 2025-11-19 | 90 | PCNFSECE | PCNFSECE | DF /F /70/DFFA-PSV-570038 | new PSV | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339286 | DFF_1Y_BRIDGE F-C INT STRUCT INSP - GVI | DFF_1Y_BRIDGE F-C INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/BRIDGE-DFF-DFC | DFF_1Y_BRIDGE F-C INT STRUCT INSP - GVI | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001380 | DK40 - erstattes af 2300002152 - OIL | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001380 | DK40 - erstattes af 2300002152 - OIL | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001380 | DK40 - erstattes af 2300002152 - OIL | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-09-09 | 2021-07-06 | 30 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001380 | DK40 - erstattes af 2300002152 - OIL | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-09-09 | 2021-07-06 | 40 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001380 | DK40 - erstattes af 2300002152 - OIL | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-09-09 | 2021-07-06 | 50 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001380 | DK40 - erstattes af 2300002152 - OIL | DK40 - CONSUMABLE PROD - OIL |  |  | 0 | 0 | Empty | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-12-04 | 2020-09-09 | 2021-07-06 | 60 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - OIL | Unknown
A | DFF-3520 | WPM | MTN-MECH | PRODTECH | 2400308680 | 8KH SDV/BDV FUNC TEST WI DFFA-A-3520 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 1 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-16 | 2024-02-10 | 2024-03-11 | 10 | AWSCSECE | AWSCSECE | DF /F /54/DFFA-A-3520 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3520 | WPM | MTN-MECH | MTN-MECH | 2400308680 | 8KH SDV/BDV FUNC TEST WI DFFA-A-3520 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4.5 | 4 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2024-02-10 | 2024-03-11 | 20 | AWSCSECE | AWSCSECE | DF /F /54/DFFA-A-3520 | ISOLATION BY PRODUCTION | Unknown
A | DFF-3520 | WPM | MTN-MECH | PRODTECH | 2400308680 | 8KH SDV/BDV FUNC TEST WI DFFA-A-3520 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 1 | W29-W30 | 2024-07-16 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2024-02-10 | 2024-03-11 | 30 | AWSCSECE | AWSCSECE | DF /F /54/DFFA-A-3520 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400298222 | 1Y 3KV TRAFO-MAINT-DFGA-TN-1844/5/6/7 | Isolate Trafo | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-01-13 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1841 | Isolate Trafo | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400298222 | 1Y 3KV TRAFO-MAINT-DFGA-TN-1844/5/6/7 | Isolate Trafo | AWSC | AWSC | 4 | 0 | Empty | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2023-12-08 | 2024-01-13 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1841 | Isolate Trafo | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400298222 | 1Y 3KV TRAFO-MAINT-DFGA-TN-1844/5/6/7 | Isolate Trafo | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2023-12-08 | 2024-01-13 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1841 | Isolate Trafo | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400298222 | 1Y 3KV TRAFO-MAINT-DFGA-TN-1844/5/6/7 | Isolate Trafo | AWSC | AWSC | 1 | 0 | Empty | 2024-06-03 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2023-12-08 | 2024-01-13 | 50 | AWSC | AWSC | DF /G /61/DFGA-N-1841 | Isolate Trafo | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400337278 | 6M CRANE HOIST EQUIP, DFB | CRANE HOIST EQUIP, DFB |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-10-13 | 2024-11-01 | 10 |  |  | DF /B /78/DFB-LIFTING | CRANE HOIST EQUIP, DFB | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-05-31 | 10 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-05-31 | 20 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2024-07-29 | 2024-08-01 | 2022-01-01 | 2022-05-31 | 45 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 8 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2024-08-01 | 2024-08-03 | 2022-01-01 | 2022-05-31 | 50 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-05-31 | 55 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 8 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2024-12-31 | 2025-01-02 | 2022-01-01 | 2022-05-31 | 60 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 12 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2025-01-02 | 2025-01-05 | 2022-01-01 | 2022-05-31 | 65 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100057022 | DAN-2021-144 Shell Repair to FT5310 | DAN-2021-144 Shell Repair to FT5310 |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2022-01-01 | 2022-05-31 | 70 |  |  | DF /F /51/DFFA-FT-5310 | DAN-2021-144 Shell Repair to FT5310 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235706 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235706 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235706 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR05-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235706 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR05-BA001 | ISOLATION ELECTRICAL | Unknown
4 | DFDFLARE | WDF | MTN-INST | MTN-MECH | 2100022771 | SMAT Replace of defect 2" Ball & Globe v | L3 Post. Remove Rigging gear | PCNF | PCNF | 1.3000000000000000444089209845 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2019-02-19 | 2021-02-08 | 10 | PCNF | PCNF | DF /C /36/DFCM-V-4001 | L3 Post. Remove Rigging gear | Unknown
4 | DFDFLARE | WDF | MTN-INST | MTN-SCAF | 2100022771 | SMAT Replace of defect 2" Ball & Globe v | L3 Post. Remove Rigging gear | PCNF | PCNF | 8 | 12 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2019-02-19 | 2021-02-08 | 20 | PCNF | PCNF | DF /C /36/DFCM-V-4001 | L3 Post. Remove Rigging gear | Unknown
4 | DFDFLARE | WDF | MTN-INST | MTN-MECH | 2100022771 | SMAT Replace of defect 2" Ball & Globe v | L3 Post. Remove Rigging gear | PCNF | PCNF | 3 | 4 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2019-02-19 | 2021-02-08 | 30 | PCNF | PCNF | DF /C /36/DFCM-V-4001 | L3 Post. Remove Rigging gear | Unknown
4 | DFDFLARE | WDF | MTN-INST | MTN-SCAF | 2100022771 | SMAT Replace of defect 2" Ball & Globe v | L3 Post. Remove Rigging gear | PCNF | PCNF | 4 | 8 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2019-02-19 | 2021-02-08 | 40 | PCNF | PCNF | DF /C /36/DFCM-V-4001 | L3 Post. Remove Rigging gear | Unknown
1 | NOSD | WDF | MTN-TURB | MTN-ELEC | 2100112138 | Deif system switches from auto to manuel | Deif system switches from auto to manuel |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2024-04-11 | 2024-04-26 | 10 |  |  | DF /F /61/DFFA-CP-1838 | Deif system switches from auto to manuel | Unknown
1 | NOSD | WDF | MTN-TURB | MTN-TURB | 2100112138 | Deif system switches from auto to manuel | Deif system switches from auto to manuel |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-04-11 | 2024-04-26 | 20 |  |  | DF /F /61/DFFA-CP-1838 | Deif system switches from auto to manuel | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100070247 | Pressure Gage Failure DFFA-ESDV-441330 | Replace Pressure indicator |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-18 | 2025-06-05 | 10 |  |  | DF /F /31/DFFA-ESDV-441330 | Replace Pressure indicator | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070247 | Pressure Gage Failure DFFA-ESDV-441330 | Replace Pressure indicator |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-18 | 2025-06-05 | 20 |  |  | DF /F /31/DFFA-ESDV-441330 | Replace Pressure indicator | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100070247 | Pressure Gage Failure DFFA-ESDV-441330 | Replace Pressure indicator |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-18 | 2025-06-05 | 30 |  |  | DF /F /31/DFFA-ESDV-441330 | Replace Pressure indicator | Unknown
A | DFE-3551 | WPM | MTN-MECH | MTN-MECH | 2400343652 | 18M DFEY-P-3551 | TL-18M DFEY-P-3551 | SECE | SECE | 5 | 0 | Empty | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-14 | 20 | SECE | SECE | DF /E /54/DFEY-P-3551 | TL-18M DFEY-P-3551 | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400293741 | 1Y DFFA-FT-340306 PROD WATER-METERING | Production removes insulation | AWSC | AWSC | 3 | 0 | Empty | 2024-08-01 | 2024-08-03 | 2024-08-01 | 2024-08-01 | 2023-11-25 | 2023-12-31 | 10 | AWSC | AWSC | DF /F /27/METERING | Production removes insulation | Unknown
C | NOSD | WPM | MTN-INST | PRODTECH | 2400293741 | 1Y DFFA-FT-340306 PROD WATER-METERING | Production removes insulation | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-03 | 2024-08-01 | 2024-08-01 | 2023-11-25 | 2023-12-31 | 20 | AWSC | AWSC | DF /F /27/METERING | Production removes insulation | Unknown
C | NOSD | WPM | MTN-INST | MTN-RIGG | 2400293741 | 1Y DFFA-FT-340306 PROD WATER-METERING | Production removes insulation | AWSC | AWSC | 2 | 0 | Empty | 2024-08-01 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2023-11-25 | 2023-12-31 | 30 | AWSC | AWSC | DF /F /27/METERING | Production removes insulation | Unknown
C | NOSD | WPM | MTN-INST | MTN-MECH | 2400293741 | 1Y DFFA-FT-340306 PROD WATER-METERING | Production removes insulation | AWSC | AWSC | 2 | 0 | Empty | 2024-08-01 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2023-11-25 | 2023-12-31 | 40 | AWSC | AWSC | DF /F /27/METERING | Production removes insulation | Unknown
C | NOSD | WPM | MTN-INST | PRODTECH | 2400293741 | 1Y DFFA-FT-340306 PROD WATER-METERING | Production removes insulation | AWSC | AWSC | 1 | 0 | Empty | 2024-08-01 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2023-11-25 | 2023-12-31 | 50 | AWSC | AWSC | DF /F /27/METERING | Production removes insulation | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400293741 | 1Y DFFA-FT-340306 PROD WATER-METERING | Production removes insulation | AWSC | AWSC | 2 | 0 | Empty | 2024-08-01 | 2024-08-03 | 2024-08-03 | 2024-08-03 | 2023-11-25 | 2023-12-31 | 60 | AWSC | AWSC | DF /F /27/METERING | Production removes insulation | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100102421 | DELUGE VALVE DFFA-XV-035255 - LEAKING | Replace deluge valve |  |  | 3 | 0 | Empty | 2024-07-06 | 2024-07-09 | 2024-07-06 | 2024-07-07 | 2024-01-06 | 2024-05-20 | 10 |  |  | DF /F /01/DFFA-XV-035255 | Replace deluge valve | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100102421 | DELUGE VALVE DFFA-XV-035255 - LEAKING | Replace deluge valve |  |  | 6 | 0 | Empty | 2024-07-06 | 2024-07-09 | 2024-07-07 | 2024-07-09 | 2024-01-06 | 2024-05-20 | 20 |  |  | DF /F /01/DFFA-XV-035255 | Replace deluge valve | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100102421 | DELUGE VALVE DFFA-XV-035255 - LEAKING | Replace deluge valve |  |  | 3 | 0 | Empty | 2024-07-06 | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2024-01-06 | 2024-05-20 | 30 |  |  | DF /F /01/DFFA-XV-035255 | Replace deluge valve | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235692 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR05-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235692 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR05-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235692 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR05-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235692 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AR05 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AR05-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400329955 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 5 | Empty | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-20 | 2024-06-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339044 | DFB_1Y_22000 INT STRUCT INSP - GVI | DFB_1Y_22000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_22000 (CELLAR DECK) | DFB_1Y_22000 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400193033 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39710 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39710 |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /B /75/DFBA-A-39710 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39710 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 0 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-03-28 | 2022-05-24 | 2022-10-21 | 10 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 10 | 10 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-03-28 | 2022-05-24 | 2022-10-21 | 20 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 25 | 12 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-28 | 2024-03-30 | 2022-05-24 | 2022-10-21 | 30 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 20 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-30 | 2024-03-31 | 2022-05-24 | 2022-10-21 | 40 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 20 | 0 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-31 | 2024-03-31 | 2022-05-24 | 2022-10-21 | 50 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 20 | 18 | Empty | 2024-03-28 | 2024-04-04 | 2024-03-31 | 2024-04-01 | 2022-05-24 | 2022-10-21 | 60 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 20 | 20 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-01 | 2024-04-02 | 2022-05-24 | 2022-10-21 | 70 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 25 | 6 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-02 | 2024-04-04 | 2022-05-24 | 2022-10-21 | 80 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100064274 | SYNSR-667006 DFC - Repair stair EL +5735 | DFC - Repair stair EL +57350 ST040 |  |  | 10 | 8 | Empty | 2024-03-28 | 2024-04-04 | 2024-04-04 | 2024-04-04 | 2022-05-24 | 2022-10-21 | 90 |  |  | DF /C /86/50700 - GRATINGS | DFC - Repair stair EL +57350 ST040 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097610 | DFBA-PSV-30088 Intern leak | Prod Assist (breaking containment) | SECE | SECE | 2 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-22 | 2023-10-19 | 2024-03-02 | 10 | SECE | SECE | DF /B /07/DFBA-PSV-30088 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097610 | DFBA-PSV-30088 Intern leak | Prod Assist (breaking containment) | SECE | SECE | 2 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-22 | 2024-08-23 | 2023-10-19 | 2024-03-02 | 20 | SECE | SECE | DF /B /07/DFBA-PSV-30088 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097610 | DFBA-PSV-30088 Intern leak | Prod Assist (breaking containment) | SECE | SECE | 4 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-23 | 2024-08-24 | 2023-10-19 | 2024-03-02 | 30 | SECE | SECE | DF /B /07/DFBA-PSV-30088 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097610 | DFBA-PSV-30088 Intern leak | Prod Assist (breaking containment) | SECE | SECE | 2 | 0 | Empty | 2024-08-22 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2023-10-19 | 2024-03-02 | 40 | SECE | SECE | DF /B /07/DFBA-PSV-30088 | Prod Assist (breaking containment) | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057916 | Change Socketoutlet DFCI-SO-1808-14L2F | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-24 | 2022-02-22 | 10 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057916 | Change Socketoutlet DFCI-SO-1808-14L2F | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-24 | 2022-02-22 | 20 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057916 | Change Socketoutlet DFCI-SO-1808-14L2F | Prove circuit is dead |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-11-24 | 2022-02-22 | 30 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057916 | Change Socketoutlet DFCI-SO-1808-14L2F | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-11-24 | 2022-02-22 | 40 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057916 | Change Socketoutlet DFCI-SO-1808-14L2F | Prove circuit is dead |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-24 | 2022-02-22 | 50 |  |  | DF /C /61/DFCI-DP-1808-14 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100075991 | DFFE/78 Boom step hits hyd. hoses | Move hose clamps to left side | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-15 | 2022-11-23 | 2023-04-07 | 10 | SCH | SCH | DF /F /78/DFFA-A-6101 | Move hose clamps to left side | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100075991 | DFFE/78 Boom step hits hyd. hoses | Move hose clamps to left side | SCH | SCH | 12 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-16 | 2022-11-23 | 2023-04-07 | 20 | SCH | SCH | DF /F /78/DFFA-A-6101 | Move hose clamps to left side | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100075991 | DFFE/78 Boom step hits hyd. hoses | Move hose clamps to left side | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-16 | 2024-07-16 | 2022-11-23 | 2023-04-07 | 30 | SCH | SCH | DF /F /78/DFFA-A-6101 | Move hose clamps to left side | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100075991 | DFFE/78 Boom step hits hyd. hoses | Move hose clamps to left side | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-16 | 2024-07-17 | 2022-11-23 | 2023-04-07 | 40 | SCH | SCH | DF /F /78/DFFA-A-6101 | Move hose clamps to left side | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235615 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-2 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235615 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-2 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235615 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-2 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235615 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-2 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-2 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300007131 | DK40 - CONSUMABLE PROD - WORKSHOP | DK40 - CONSUMABLE PROD - WORKSHOP |  |  | 0 | 0 | Empty | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 | 2026-11-04 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - WORKSHOP | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057636 | FLMR DFB - Repl. Steps/Stair. EL. 22.000 | DFB - Repl. Steps/Stair Str. EL. 22.000 | PCNF | PCNF | 0 | 0 | Empty | 2022-01-18 | 2022-01-19 | 2022-01-18 | 2022-01-18 | 2022-01-18 | 2022-06-17 | 10 | PCNF | PCNF | DF /B /86/22000 - GRATINGS | DFB - Repl. Steps/Stair Str. EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057636 | FLMR DFB - Repl. Steps/Stair. EL. 22.000 | DFB - Repl. Steps/Stair Str. EL. 22.000 | PCNF | PCNF | 12 | 22 | Empty | 2022-01-18 | 2022-01-19 | 2022-01-18 | 2022-01-19 | 2022-01-18 | 2022-06-17 | 20 | PCNF | PCNF | DF /B /86/22000 - GRATINGS | DFB - Repl. Steps/Stair Str. EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057636 | FLMR DFB - Repl. Steps/Stair. EL. 22.000 | DFB - Repl. Steps/Stair Str. EL. 22.000 | PCNF | PCNF | 0 | 0 | Empty | 2022-01-18 | 2022-01-19 | 2022-01-19 | 2022-01-19 | 2022-01-18 | 2022-06-17 | 30 | PCNF | PCNF | DF /B /86/22000 - GRATINGS | DFB - Repl. Steps/Stair Str. EL. 22.000 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057636 | FLMR DFB - Repl. Steps/Stair. EL. 22.000 | DFB - Repl. Steps/Stair Str. EL. 22.000 | PCNF | PCNF | 0 | 0 | Empty | 2022-01-18 | 2022-01-19 | 2022-01-19 | 2022-01-19 | 2022-01-18 | 2022-06-17 | 40 | PCNF | PCNF | DF /B /86/22000 - GRATINGS | DFB - Repl. Steps/Stair Str. EL. 22.000 | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100112076 | Air dryer seams not to change over | Isolate DFFA-A-5401 - PROD |  |  | 2 | 0 | Empty | 2024-07-06 | 2024-07-10 | 2024-07-06 | 2024-07-06 | 2024-05-06 | 2024-06-20 | 10 |  |  | DF /F /07/DFFA-CP-5403 | Isolate DFFA-A-5401 - PROD | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112076 | Air dryer seams not to change over | Isolate DFFA-A-5401 - PROD |  |  | 2 | 0 | Empty | 2024-07-06 | 2024-07-10 | 2024-07-06 | 2024-07-07 | 2024-05-06 | 2024-06-20 | 20 |  |  | DF /F /07/DFFA-CP-5403 | Isolate DFFA-A-5401 - PROD | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100112076 | Air dryer seams not to change over | Isolate DFFA-A-5401 - PROD |  |  | 9 | 0 | Empty | 2024-07-06 | 2024-07-10 | 2024-07-07 | 2024-07-09 | 2024-05-06 | 2024-06-20 | 30 |  |  | DF /F /07/DFFA-CP-5403 | Isolate DFFA-A-5401 - PROD | Unknown
2 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100112076 | Air dryer seams not to change over | Isolate DFFA-A-5401 - PROD |  |  | 2 | 0 | Empty | 2024-07-06 | 2024-07-10 | 2024-07-09 | 2024-07-09 | 2024-05-06 | 2024-06-20 | 40 |  |  | DF /F /07/DFFA-CP-5403 | Isolate DFFA-A-5401 - PROD | Unknown
2 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100112076 | Air dryer seams not to change over | Isolate DFFA-A-5401 - PROD |  |  | 2 | 0 | Empty | 2024-07-06 | 2024-07-10 | 2024-07-09 | 2024-07-10 | 2024-05-06 | 2024-06-20 | 50 |  |  | DF /F /07/DFFA-CP-5403 | Isolate DFFA-A-5401 - PROD | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077614 | Finding A-04 from 1Y inspection helifuel | Isolate helifuel system | PCNFSCH | PCNFSCH | 2 | 0 | W25-W26 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2023-04-30 | 2025-10-16 | 20 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate helifuel system | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077614 | Finding A-04 from 1Y inspection helifuel | Isolate helifuel system | PCNFSCH | PCNFSCH | 4 | 0 | W25-W26 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-16 | 2023-04-30 | 2025-10-16 | 30 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate helifuel system | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100077614 | Finding A-04 from 1Y inspection helifuel | Isolate helifuel system | PCNFSCH | PCNFSCH | 4 | 0 | W25-W26 | 2024-07-15 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2023-04-30 | 2025-10-16 | 40 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate helifuel system | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100077614 | Finding A-04 from 1Y inspection helifuel | Isolate helifuel system | PCNFSCH | PCNFSCH | 2 | 0 | W25-W26 | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2023-04-30 | 2025-10-16 | 50 | PCNFSCH | PCNFSCH | DF /C /81/DFCL-A-5602 | Isolate helifuel system | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339038 | DFA_1Y_24720 INT STRUCT INSP - GVI | DFA_1Y_24720 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /86/EL_24720 (MEZZANINE DECK) | DFA_1Y_24720 INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342402 | 6M DEMULSIFIER SKID MAINT - DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-08 | 2024-08-27 | 10 |  |  | DF /F /75/DFFA-A-3957 | DEMULSIFIER SKID MAINT - DFFA-A-3957 | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018135 | Replace Motor protection 1841-M111 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M111-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018135 | Replace Motor protection 1841-M111 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M111-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018135 | Replace Motor protection 1841-M111 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M111-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018135 | Replace Motor protection 1841-M111 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M111-02 | New mat num | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235759 | 1Y 110V UPS.SYST BATT & CHAR F.TEST-DFC | 110V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 2023-08-29 | 2023-09-28 | 10 | AWSCSECE | AWSCSECE | DF /C /06/DFCI-A-1905 | 110V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341926 | DFG_1Y_FIRE AND BLAST-WALLS INSP | DFG_1Y_FIRE AND BLAST-WALLS INSP | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /02/FIRE AND BLAST-WALLS | DFG_1Y_FIRE AND BLAST-WALLS INSP | Unknown
2 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200017182 | DFB/78 Greasing of wire ropes | Greasing of aux wire |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2024-01-17 | 2024-03-02 | 10 |  |  | DF /B /78/DFBA-X-6102 | Greasing of aux wire | Unknown
2 | NOSD | WGN | MTN-CRAN | MTN-ROUS | 2200017182 | DFB/78 Greasing of wire ropes | Greasing of aux wire |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-30 | 2024-01-17 | 2024-03-02 | 20 |  |  | DF /B /78/DFBA-X-6102 | Greasing of aux wire | Unknown
2 | NOSD | WGN | MTN-CRAN | MTN-ROUS | 2200017182 | DFB/78 Greasing of wire ropes | Greasing of aux wire |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2024-01-17 | 2024-03-02 | 40 |  |  | DF /B /78/DFBA-X-6102 | Greasing of aux wire | Unknown
2 | NOSD | WGN | MTN-CRAN | MTN-CRAN | 2200017182 | DFB/78 Greasing of wire ropes | Greasing of aux wire |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2024-01-17 | 2024-03-02 | 50 |  |  | DF /B /78/DFBA-X-6102 | Greasing of aux wire | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100058311 | DFF-30 THP Scada PT-300530 throubleshoot | Troubleshoot Pressure transmitter |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-11-28 | 2022-02-26 | 10 |  |  | DF /F /10/DFFA-PIT-300530 | Troubleshoot Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100058311 | DFF-30 THP Scada PT-300530 throubleshoot | Troubleshoot Pressure transmitter |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-11-28 | 2022-02-26 | 20 |  |  | DF /F /10/DFFA-PIT-300530 | Troubleshoot Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100058311 | DFF-30 THP Scada PT-300530 throubleshoot | Troubleshoot Pressure transmitter |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-11-28 | 2022-02-26 | 30 |  |  | DF /F /10/DFFA-PIT-300530 | Troubleshoot Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100058311 | DFF-30 THP Scada PT-300530 throubleshoot | Troubleshoot Pressure transmitter |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-11-28 | 2022-02-26 | 40 |  |  | DF /F /10/DFFA-PIT-300530 | Troubleshoot Pressure transmitter | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-SCAF | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 48 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-04 | 2021-06-02 | 2021-08-31 | 10 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-RIGG | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-04 | 2025-01-07 | 2021-06-02 | 2021-08-31 | 20 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-08 | 2025-01-09 | 2021-06-02 | 2021-08-31 | 30 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-07 | 2025-01-08 | 2021-06-02 | 2021-08-31 | 35 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | PRODTECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-09 | 2025-01-10 | 2021-06-02 | 2021-08-31 | 40 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-RIGG | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-10 | 2025-01-13 | 2021-06-02 | 2021-08-31 | 50 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-13 | 2025-01-14 | 2021-06-02 | 2021-08-31 | 60 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-14 | 2025-01-15 | 2021-06-02 | 2021-08-31 | 70 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-15 | 2025-01-15 | 2021-06-02 | 2021-08-31 | 80 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-15 | 2025-01-16 | 2021-06-02 | 2021-08-31 | 90 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | PRODTECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-16 | 2025-01-16 | 2021-06-02 | 2021-08-31 | 100 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-16 | 2025-01-17 | 2021-06-02 | 2021-08-31 | 110 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-RIGG | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-17 | 2025-01-18 | 2021-06-02 | 2021-08-31 | 120 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-17 | 2025-01-18 | 2021-06-02 | 2021-08-31 | 125 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-SCAF | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 36 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-18 | 2025-01-20 | 2021-06-02 | 2021-08-31 | 130 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-MECH | 2100049758 | HCV-380337+bypass Vlv internal leaking | Line for missing Bolts | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-20 | 2025-01-01 | 2025-01-01 | 2021-06-02 | 2021-08-31 | 140 | AWSC | AWSC | DF /F /34/DFFA-HCV-380338 | Line for missing Bolts | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023565 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 3.399999999999999911182158029 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-03-10 | 2018-06-08 | 10 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100023565 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 20 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023565 | DFF installation of insulation HTJB 1802 | L3 permit prep |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-14 | 2023-02-14 | 2018-03-10 | 2018-06-08 | 30 |  |  | DF /F /61/DFFA-N-1802 | L3 permit prep | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286644 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PERSONAL ISOLATION |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-26 | 2023-10-14 | 2023-11-19 | 10 |  |  | DF /C /09/DFCI-B-1212 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286644 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PERSONAL ISOLATION |  |  | 10 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2023-10-14 | 2023-11-19 | 20 |  |  | DF /C /09/DFCI-B-1212 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286644 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PERSONAL ISOLATION |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2023-10-14 | 2023-11-19 | 30 |  |  | DF /C /09/DFCI-B-1212 | PERSONAL ISOLATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286644 | 1Y HVAC SUPPLY CHECK DFCI-B-1212 | PERSONAL ISOLATION |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2023-10-14 | 2023-11-19 | 40 |  |  | DF /C /09/DFCI-B-1212 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | VEN-INSP | MTN-MECH | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-03 | 2024-05-03 | 2024-10-19 | 2024-12-31 | 10 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-SCAF | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 100 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-03 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 20 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ELEC | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 30 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-RIGG | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 40 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PIPF | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 50 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-ROPE | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 60 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-INST | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 70 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | MTN-PAIN | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 80 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | PRODTECH | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 0 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-10-19 | 2024-12-31 | 90 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
A | NOSD | WPM | VEN-INSP | VEN-INSP | 2400292008 | PVI Intermediate - DFGA-V-4441 | Scaffolding work | SECE | SECE | 12 | 0 | Empty | 2024-05-03 | 2024-05-29 | 2024-05-28 | 2024-05-29 | 2024-10-19 | 2024-12-31 | 100 | SECE | SECE | DF /G /32/DFGA-V-4441 | Scaffolding work | Unknown
4 | NE | WDF | MTN-INST | WELLSUPV | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-08-18 | 2024-07-26 | 2024-07-26 | 2021-12-16 | 2022-05-15 | 10 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
4 | NE | WDF | MTN-INST | MTN-INST | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-08-18 | 2024-07-26 | 2024-07-26 | 2021-12-16 | 2022-05-15 | 20 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 36 | 30 | Empty | 2024-07-26 | 2024-08-18 | 2024-07-26 | 2024-07-30 | 2021-12-16 | 2022-05-15 | 30 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
4 | NE | WDF | MTN-INST | MTN-ROPE | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 36 | 20 | Empty | 2024-07-26 | 2024-08-18 | 2024-07-30 | 2024-08-01 | 2021-12-16 | 2022-05-15 | 40 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
4 | NE | WDF | MTN-INST | MTN-SCAF | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 18 | 0 | Empty | 2024-07-26 | 2024-08-18 | 2024-08-01 | 2024-08-03 | 2021-12-16 | 2022-05-15 | 50 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
4 | NE | WDF | MTN-INST | MTN-INST | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 0 | 0 | Empty | 2024-07-26 | 2024-08-18 | 2024-08-03 | 2024-08-03 | 2021-12-16 | 2022-05-15 | 60 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
4 | NE | WDF | MTN-INST | MTN-INST | 2100055902 | DGSPR: Utility & Instrument Air Batch-02 | Fabr. of instr. air replacement spools | PCNF | PCNF | 60 | 66 | Empty | 2024-07-26 | 2024-08-18 | 2024-08-03 | 2024-08-18 | 2021-12-16 | 2022-05-15 | 70 | PCNF | PCNF | DF /B /07/DFB-1-AI-054-0809-A1-U | Fabr. of instr. air replacement spools | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | PRODTECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 10 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 20 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-24 | 2020-09-14 | 2020-10-24 | 15 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-23 | 2020-09-14 | 2020-10-24 | 20 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 10 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-23 | 2020-09-14 | 2020-10-24 | 25 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | PRODTECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 30 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | PRODTECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 40 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 15 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-26 | 2020-09-14 | 2020-10-24 | 50 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-26 | 2024-09-27 | 2020-09-14 | 2020-10-24 | 60 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-27 | 2024-09-28 | 2020-09-14 | 2020-10-24 | 70 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-RIGG | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-27 | 2024-09-28 | 2020-09-14 | 2020-10-24 | 80 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-28 | 2024-09-28 | 2020-09-14 | 2020-10-24 | 90 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | PRODTECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-29 | 2024-09-29 | 2020-09-14 | 2020-10-24 | 100 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-SCAF | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 10 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-29 | 2024-10-02 | 2020-09-14 | 2020-10-24 | 110 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2020-09-14 | 2020-10-24 | 120 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
3 | DFC-FUEL | WDF | MTN-MECH | MTN-MECH | 2100038045 | HCV-57148-U Intern læk | Isolate Valve |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2020-09-14 | 2020-10-24 | 130 |  |  | DF /C /70/DFCI-HCV-57148-U | Isolate Valve | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200003363 | Liftgasrør er ikke fastgjort.DFB-13. | Liftgasrør er ikke fastgjort.DFB-13. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-17 | 2024-03-15 | 2024-03-15 | 2020-05-21 | 2020-10-18 | 10 |  |  | DF /A /01/P-G | Liftgasrør er ikke fastgjort.DFB-13. | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200003363 | Liftgasrør er ikke fastgjort.DFB-13. | Liftgasrør er ikke fastgjort.DFB-13. |  |  | 36 | 0 | Empty | 2024-03-15 | 2024-03-17 | 2024-03-15 | 2024-03-17 | 2020-05-21 | 2020-10-18 | 20 |  |  | DF /A /01/P-G | Liftgasrør er ikke fastgjort.DFB-13. | Unknown
4 | NOSD | WGN | MTN-ROPE | MTN-ROPE | 2200003363 | Liftgasrør er ikke fastgjort.DFB-13. | Liftgasrør er ikke fastgjort.DFB-13. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-17 | 2024-03-17 | 2024-03-17 | 2020-05-21 | 2020-10-18 | 30 |  |  | DF /A /01/P-G | Liftgasrør er ikke fastgjort.DFB-13. | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400264130 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3660 | ISOLATION BY PRODUCTION | SCH | SCH | 4 | 0 | 24-W03-04 | 2024-07-29 | 2024-08-05 | 2024-07-29 | 2024-07-29 | 2023-07-10 | 2023-07-26 | 10 | SCH | SCH | DF /C /23/DFCM-A-3660 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400264130 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3660 | ISOLATION BY PRODUCTION | SCH | SCH | 20 | 0 | 24-W03-04 | 2024-07-29 | 2024-08-05 | 2024-07-30 | 2024-08-03 | 2023-07-10 | 2023-07-26 | 20 | SCH | SCH | DF /C /23/DFCM-A-3660 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400264130 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3660 | ISOLATION BY PRODUCTION | SCH | SCH | 1 | 0 | 24-W03-04 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-04 | 2023-07-10 | 2023-07-26 | 30 | SCH | SCH | DF /C /23/DFCM-A-3660 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400264130 | 6M CRUDE OIL EXP. SKD MAINT-DFCM-A-3660 | ISOLATION BY PRODUCTION | SCH | SCH | 4 | 0 | 24-W03-04 | 2024-07-29 | 2024-08-05 | 2024-08-04 | 2024-08-05 | 2023-07-10 | 2023-07-26 | 40 | SCH | SCH | DF /C /23/DFCM-A-3660 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2020-09-07 | 2020-09-07 | 2019-09-19 | 2019-12-18 | 10 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 12.099999999999999644728632116 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-19 | 2019-12-18 | 20 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 6 | 5 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-19 | 2019-12-18 | 30 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 2 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-19 | 2019-12-18 | 40 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 6 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-19 | 2019-12-18 | 50 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 8 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-08 | 2019-09-19 | 2019-12-18 | 60 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 96 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-13 | 2019-09-19 | 2019-12-18 | 70 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 12 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2019-09-19 | 2019-12-18 | 80 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-09 | 2019-09-19 | 2019-12-18 | 90 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 24 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2019-09-19 | 2019-12-18 | 100 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-SCAF | 2200002923 | scaff/insulation FORCE: 15962 | Scaffold for reaching insulation | PCNF | PCNF | 48 | 0 | Empty | 2024-01-08 | 2024-01-13 | 2024-01-08 | 2024-01-10 | 2019-09-19 | 2019-12-18 | 110 | PCNF | PCNF | DF /F /28/DFF-2-DPS-050-7633-AD-T | Scaffold for reaching insulation | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235659 | 4Y 400V N-SWB MAINT DFCI-N-1802-R08 | 400V N-SWB INSP DFCI-N-1802-R08 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R08B | 400V N-SWB INSP DFCI-N-1802-R08 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235659 | 4Y 400V N-SWB MAINT DFCI-N-1802-R08 | 400V N-SWB INSP DFCI-N-1802-R08 | AWSC | AWSC | 15 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-25 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R08B | 400V N-SWB INSP DFCI-N-1802-R08 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235659 | 4Y 400V N-SWB MAINT DFCI-N-1802-R08 | 400V N-SWB INSP DFCI-N-1802-R08 | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R08B | 400V N-SWB INSP DFCI-N-1802-R08 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235659 | 4Y 400V N-SWB MAINT DFCI-N-1802-R08 | 400V N-SWB INSP DFCI-N-1802-R08 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R08B | 400V N-SWB INSP DFCI-N-1802-R08 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061292 | DFF-04 Scale inj unstable flow 0% output | Replace DFFA-FCV-390061 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2022-01-07 | 2022-02-16 | 10 |  |  | DF /F /75/DFFA-FCV-390061 | Replace DFFA-FCV-390061 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100061292 | DFF-04 Scale inj unstable flow 0% output | Replace DFFA-FCV-390061 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2022-01-07 | 2022-02-16 | 20 |  |  | DF /F /75/DFFA-FCV-390061 | Replace DFFA-FCV-390061 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100061292 | DFF-04 Scale inj unstable flow 0% output | Replace DFFA-FCV-390061 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2022-01-07 | 2022-02-16 | 30 |  |  | DF /F /75/DFFA-FCV-390061 | Replace DFFA-FCV-390061 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100107880 | Exchange of DFFA-P-3914 | Exchange of DFFA-P-3914 |  |  | 0 | 0 | Empty | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2027-01-28 | 10 |  |  | DF /F /75/DFFA-P-3914 | Exchange of DFFA-P-3914 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400291613 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | SCH | SCH | 0 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-12-01 | 2023-12-12 | 1 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-ROUS | 2400291613 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | SCH | SCH | 4 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-12-01 | 2023-12-12 | 10 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400291613 | 2M CHECK AF GULVDRÆN, DFC | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | SCH | SCH | 4 | 0 | 24-W05-06 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-12-01 | 2023-12-12 | 12 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | CHECK AF GULVDRÆN, DAN FC PROCES LEVEL 1 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009217 | Insulation assits FORCE 9547 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /B /28/DFB-3-DP-050-0902-B5-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009217 | Insulation assits FORCE 9547 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /B /28/DFB-3-DP-050-0902-B5-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009217 | Insulation assits FORCE 9547 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 22 |  |  | DF /B /28/DFB-3-DP-050-0902-B5-F | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009217 | Insulation assits FORCE 9547 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-12 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /B /28/DFB-3-DP-050-0902-B5-F | Bilfinger inspection | Unknown
1 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200014666 | IRP welding pipe support. | Perform UT |  |  | 32 | 0 | Empty | 2023-06-02 | 2023-06-10 | 2023-06-02 | 2023-06-06 | 2023-06-02 | 2023-06-17 | 10 |  |  | DF /E /12/DFE-16-PHS-033-9018-BD-U | Perform UT | Unknown
1 | NOSD | WGN | MTN-PIPF | MTN-PIPF | 2200014666 | IRP welding pipe support. | Perform UT |  |  | 16 | 0 | Empty | 2023-06-02 | 2023-06-10 | 2023-06-06 | 2023-06-07 | 2023-06-02 | 2023-06-17 | 20 |  |  | DF /E /12/DFE-16-PHS-033-9018-BD-U | Perform UT | Unknown
1 | NOSD | WGN | MTN-PIPF | INP-SITE | 2200014666 | IRP welding pipe support. | Perform UT |  |  | 4 | 0 | Empty | 2023-06-02 | 2023-06-10 | 2023-06-07 | 2023-06-07 | 2023-06-02 | 2023-06-17 | 30 |  |  | DF /E /12/DFE-16-PHS-033-9018-BD-U | Perform UT | Unknown
1 | NOSD | WGN | MTN-PIPF | MTN-SCAF | 2200014666 | IRP welding pipe support. | Perform UT |  |  | 10 | 0 | Empty | 2023-06-02 | 2023-06-10 | 2023-06-07 | 2023-06-08 | 2023-06-02 | 2023-06-17 | 40 |  |  | DF /E /12/DFE-16-PHS-033-9018-BD-U | Perform UT | Unknown
1 | NOSD | WGN | MTN-PIPF | MTN-PAIN | 2200014666 | IRP welding pipe support. | Perform UT |  |  | 12 | 0 | Empty | 2023-06-02 | 2023-06-10 | 2023-06-08 | 2023-06-09 | 2023-06-02 | 2023-06-17 | 50 |  |  | DF /E /12/DFE-16-PHS-033-9018-BD-U | Perform UT | Unknown
1 | NOSD | WGN | MTN-PIPF | MTN-PAIN | 2200014666 | IRP welding pipe support. | Perform UT |  |  | 4 | 0 | Empty | 2023-06-02 | 2023-06-10 | 2023-06-09 | 2023-06-10 | 2023-06-02 | 2023-06-17 | 60 |  |  | DF /E /12/DFE-16-PHS-033-9018-BD-U | Perform UT | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284305 | PSV Exchange - DFGA-PSV-570011B | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /30/DFGA-PSV-570011B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284305 | PSV Exchange - DFGA-PSV-570011B | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-12-31 | 20 | AWSCSECE | AWSCSECE | DF /G /30/DFGA-PSV-570011B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284305 | PSV Exchange - DFGA-PSV-570011B | Isolation of PSV | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-10-31 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 30 | AWSCSECE | AWSCSECE | DF /G /30/DFGA-PSV-570011B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284305 | PSV Exchange - DFGA-PSV-570011B | Isolation of PSV | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-01 | 2024-10-30 | 2024-12-31 | 40 | AWSCSECE | AWSCSECE | DF /G /30/DFGA-PSV-570011B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284305 | PSV Exchange - DFGA-PSV-570011B | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-01 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 50 | AWSCSECE | AWSCSECE | DF /G /30/DFGA-PSV-570011B | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284305 | PSV Exchange - DFGA-PSV-570011B | Isolation of PSV | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2024-10-30 | 2024-12-31 | 60 | AWSCSECE | AWSCSECE | DF /G /30/DFGA-PSV-570011B | Isolation of PSV | Unknown
4 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100025297 | Repair/replacement of VFD | L3 Power down & up of LO VFD | PCNFAWSC | PCNFAWSC | 2 | 5 | W21-W22 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-07-01 | 2019-11-28 | 10 | PCNFAWSC | PCNFAWSC | DF /G /54/DFGA-A-3590 | L3 Power down & up of LO VFD | Unknown
4 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100025297 | Repair/replacement of VFD | L3 Power down & up of LO VFD | PCNFAWSC | PCNFAWSC | 2 | 0 | W21-W22 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-07-01 | 2019-11-28 | 20 | PCNFAWSC | PCNFAWSC | DF /G /54/DFGA-A-3590 | L3 Power down & up of LO VFD | Unknown
4 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100025297 | Repair/replacement of VFD | L3 Power down & up of LO VFD | PCNFAWSC | PCNFAWSC | 2 | 0 | W21-W22 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-07-01 | 2019-11-28 | 30 | PCNFAWSC | PCNFAWSC | DF /G /54/DFGA-A-3590 | L3 Power down & up of LO VFD | Unknown
4 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100025297 | Repair/replacement of VFD | L3 Power down & up of LO VFD | PCNFAWSC | PCNFAWSC | 1 | 0 | W21-W22 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-07-01 | 2019-11-28 | 40 | PCNFAWSC | PCNFAWSC | DF /G /54/DFGA-A-3590 | L3 Power down & up of LO VFD | Unknown
4 | DFG-3590 | WDF | MTN-TURB | MTN-TURB | 2100025297 | Repair/replacement of VFD | L3 Power down & up of LO VFD | PCNFAWSC | PCNFAWSC | 0 | 0 | W21-W22 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2019-07-01 | 2019-11-28 | 50 | PCNFAWSC | PCNFAWSC | DF /G /54/DFGA-A-3590 | L3 Power down & up of LO VFD | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400241132 | 1Y INST AIR DRYER SKID MAINT-DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 |  |  | 2 | 0 | W31-W32 | 2024-08-01 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2023-02-21 | 2023-03-29 | 10 |  |  | DF /F /07/DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400241132 | 1Y INST AIR DRYER SKID MAINT-DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 |  |  | 3 | 0 | W31-W32 | 2024-08-01 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2023-02-21 | 2023-03-29 | 20 |  |  | DF /F /07/DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241132 | 1Y INST AIR DRYER SKID MAINT-DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 |  |  | 3 | 44 | W31-W32 | 2024-08-01 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2023-02-21 | 2023-03-29 | 30 |  |  | DF /F /07/DFFA-A-5401 | INST AIR DRYER SKID MAINT-DFFA-A-5401 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235703 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR01-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235703 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR01 | ISOLATION ELECTRICAL | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR01-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235703 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR01 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR01-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235703 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BR01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BR01-01 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322277 | DFF-28-DO-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400268046 | 6M SDV LUB/MAINT IPHP - DFG | SDV LUB/INSP IPHP - DFG |  |  | 12 | 0 | W23-W24 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-07-20 | 2023-08-05 | 10 |  |  | DF /G /03/SDV-VALVES | SDV LUB/INSP IPHP - DFG | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316003 | 4000H TURBINE SKID, COUNTER | Extra spares - KIT 1148030 | AWSCSCH | AWSCSCH | 14 | 20 | Empty | 2024-06-20 | 2024-06-24 | 2024-06-20 | 2024-06-23 | 2024-04-03 | 2024-04-19 | 10 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | Extra spares - KIT 1148030 | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316003 | 4000H TURBINE SKID, COUNTER | Extra spares - KIT 1148030 | AWSCSCH | AWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-06-24 | 2024-06-23 | 2024-06-24 | 2024-04-03 | 2024-04-19 | 20 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | Extra spares - KIT 1148030 | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316003 | 4000H TURBINE SKID, COUNTER | Extra spares - KIT 1148030 | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-06-20 | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-04-03 | 2024-04-19 | 30 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | Extra spares - KIT 1148030 | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316003 | 4000H TURBINE SKID, COUNTER | Extra spares - KIT 1148030 | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-06-20 | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-04-03 | 2024-04-19 | 40 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | Extra spares - KIT 1148030 | Unknown
B | DFF-IPHP | WPM | MTN-TURB | MTN-TURB | 2400316003 | 4000H TURBINE SKID, COUNTER | Extra spares - KIT 1148030 | AWSCSCH | AWSCSCH | 0 | 0 | Empty | 2024-06-20 | 2024-06-24 | 2024-06-24 | 2024-06-24 | 2024-04-03 | 2024-04-19 | 50 | AWSCSCH | AWSCSCH | DF /F /31/DFFA-A-4301 | Extra spares - KIT 1148030 | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052317 | ANOCR Localised external corrosion. | Set up equipment |  |  | 0 | 0 | Empty | 2021-07-31 | 2021-08-09 | 2021-07-31 | 2021-07-31 | 2021-07-31 | 2021-10-29 | 10 |  |  | DF /C /12/DFC-24-PHS-034-6511-AB-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052317 | ANOCR Localised external corrosion. | Set up equipment |  |  | 12 | 0 | Empty | 2021-07-31 | 2021-08-09 | 2021-07-31 | 2021-08-01 | 2021-07-31 | 2021-10-29 | 20 |  |  | DF /C /12/DFC-24-PHS-034-6511-AB-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052317 | ANOCR Localised external corrosion. | Set up equipment |  |  | 6 | 0 | Empty | 2021-07-31 | 2021-08-09 | 2021-08-01 | 2021-08-02 | 2021-07-31 | 2021-10-29 | 30 |  |  | DF /C /12/DFC-24-PHS-034-6511-AB-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052317 | ANOCR Localised external corrosion. | Set up equipment |  |  | 78 | 0 | Empty | 2021-07-31 | 2021-08-09 | 2021-08-02 | 2021-08-08 | 2021-07-31 | 2021-10-29 | 40 |  |  | DF /C /12/DFC-24-PHS-034-6511-AB-U | Set up equipment | Unknown
3 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100052317 | ANOCR Localised external corrosion. | Set up equipment |  |  | 12 | 0 | Empty | 2021-07-31 | 2021-08-09 | 2021-08-08 | 2021-08-09 | 2021-07-31 | 2021-10-29 | 50 |  |  | DF /C /12/DFC-24-PHS-034-6511-AB-U | Set up equipment | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100044566 | DFB/78: Lightfixtures repair crane DFB | Isolate crane |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2021-02-02 | 2021-03-14 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100044566 | DFB/78: Lightfixtures repair crane DFB | Isolate crane |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2021-02-02 | 2021-03-14 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100044566 | DFB/78: Lightfixtures repair crane DFB | Isolate crane |  |  | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2021-02-02 | 2021-03-14 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100044566 | DFB/78: Lightfixtures repair crane DFB | Isolate crane |  |  | 7 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2021-02-02 | 2021-03-14 | 32 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100044566 | DFB/78: Lightfixtures repair crane DFB | Isolate crane |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2021-02-02 | 2021-03-14 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100044566 | DFB/78: Lightfixtures repair crane DFB | Isolate crane |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2021-02-02 | 2021-03-14 | 50 |  |  | DF /B /78/DFBA-X-6102 | Isolate crane | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006293 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2021-02-16 | 2021-03-28 | 10 |  |  | DF /G /28/DFG-2-DOS-050-0170-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-LAGG | 2200006293 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2024-01-09 | 2021-02-16 | 2021-03-28 | 20 |  |  | DF /G /28/DFG-2-DOS-050-0170-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-ELEC | 2200006293 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-09 | 2024-01-11 | 2021-02-16 | 2021-03-28 | 30 |  |  | DF /G /28/DFG-2-DOS-050-0170-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-INSP | 2200006293 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-11 | 2024-01-11 | 2021-02-16 | 2021-03-28 | 35 |  |  | DF /G /28/DFG-2-DOS-050-0170-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WGN | UNKNOWN | MTN-ELEC | 2200006293 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-11 | 2024-01-15 | 2021-02-16 | 2021-03-28 | 40 |  |  | DF /G /28/DFG-2-DOS-050-0170-AB-T | Bilfinger inspection | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200006293 | Insulation assits FORCE 15879 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-15 | 2024-01-17 | 2021-02-16 | 2021-03-28 | 50 |  |  | DF /G /28/DFG-2-DOS-050-0170-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055443 | defekt beskyttelseshætte P-3989 | Exchange P-3989 |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-28 | 2021-12-07 | 2022-05-06 | 20 |  |  | DF /G /75/DFGA-A-3988 | Exchange P-3989 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100055443 | defekt beskyttelseshætte P-3989 | Exchange P-3989 |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-09-02 | 2021-12-07 | 2022-05-06 | 30 |  |  | DF /G /75/DFGA-A-3988 | Exchange P-3989 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055443 | defekt beskyttelseshætte P-3989 | Exchange P-3989 |  |  | 10 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-08-30 | 2021-12-07 | 2022-05-06 | 40 |  |  | DF /G /75/DFGA-A-3988 | Exchange P-3989 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055443 | defekt beskyttelseshætte P-3989 | Exchange P-3989 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2021-12-07 | 2022-05-06 | 50 |  |  | DF /G /75/DFGA-A-3988 | Exchange P-3989 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-29 | 2024-07-31 | 2018-08-13 | 2019-01-10 | 10 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-07-31 | 2024-08-02 | 2018-08-13 | 2019-01-10 | 20 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-02 | 2024-08-04 | 2018-08-13 | 2019-01-10 | 30 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-04 | 2024-08-06 | 2018-08-13 | 2019-01-10 | 40 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-06 | 2024-08-08 | 2018-08-13 | 2019-01-10 | 50 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-08 | 2024-08-10 | 2018-08-13 | 2019-01-10 | 60 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-10 | 2024-08-12 | 2018-08-13 | 2019-01-10 | 70 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027391 | DFF level 1 transits | L3 DFF-L1-001 TYPE RGSFB6x4 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-14 | 2024-08-12 | 2024-08-14 | 2018-08-13 | 2019-01-10 | 80 |  |  | DF /F /6 | L3 DFF-L1-001 TYPE RGSFB6x4 | Unknown
4 | DFF-3520 | WGN | MTN-PAIN | PRODTECH | 2200003162 | CMAT:DFF Efterfyldning af dual media fil | L3 Safinng of DFFA-FT-3501 | AWSC | AWSC | 6 | 0 | ? after Minox PVI | 2025-01-01 | 2025-01-17 | 2025-01-01 | 2025-01-03 | 2018-05-13 | 2018-06-22 | 10 | AWSC | AWSC | DF /F /51/DFFA-FT-3501 | L3 Safinng of DFFA-FT-3501 | Unknown
4 | DFF-3520 | WGN | MTN-PAIN | MTN-PIPF | 2200003162 | CMAT:DFF Efterfyldning af dual media fil | L3 Safinng of DFFA-FT-3501 | AWSC | AWSC | 36.20000000000000284217094303 | 0 | ? after Minox PVI | 2025-01-01 | 2025-01-17 | 2025-01-03 | 2025-01-04 | 2018-05-13 | 2018-06-22 | 20 | AWSC | AWSC | DF /F /51/DFFA-FT-3501 | L3 Safinng of DFFA-FT-3501 | Unknown
4 | DFF-3520 | WGN | MTN-PAIN | MTN-SCAF | 2200003162 | CMAT:DFF Efterfyldning af dual media fil | L3 Safinng of DFFA-FT-3501 | AWSC | AWSC | 72.40000000000000568434188606 | 0 | ? after Minox PVI | 2025-01-01 | 2025-01-17 | 2025-01-04 | 2025-01-13 | 2018-05-13 | 2018-06-22 | 30 | AWSC | AWSC | DF /F /51/DFFA-FT-3501 | L3 Safinng of DFFA-FT-3501 | Unknown
4 | DFF-3520 | WGN | MTN-PAIN | MTN-PIPF | 2200003162 | CMAT:DFF Efterfyldning af dual media fil | L3 Safinng of DFFA-FT-3501 | AWSC | AWSC | 36.20000000000000284217094303 | 0 | ? after Minox PVI | 2025-01-01 | 2025-01-17 | 2025-01-13 | 2025-01-15 | 2018-05-13 | 2018-06-22 | 40 | AWSC | AWSC | DF /F /51/DFFA-FT-3501 | L3 Safinng of DFFA-FT-3501 | Unknown
4 | DFF-3520 | WGN | MTN-PAIN | PRODTECH | 2200003162 | CMAT:DFF Efterfyldning af dual media fil | L3 Safinng of DFFA-FT-3501 | AWSC | AWSC | 6 | 0 | ? after Minox PVI | 2025-01-01 | 2025-01-17 | 2025-01-15 | 2025-01-17 | 2018-05-13 | 2018-06-22 | 50 | AWSC | AWSC | DF /F /51/DFFA-FT-3501 | L3 Safinng of DFFA-FT-3501 | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 1454 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 10 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 266 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 20 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TELE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 949 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 30 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TELE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 194 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 40 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TELE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 97 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 50 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-INST | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 365 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 60 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TELE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 76 | Empty | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 70 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 23 | Empty | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 80 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-INST | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 120 | Empty | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 90 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 749.5 | Empty | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 100 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 26 | Empty | 2024-09-15 | 2024-09-15 | 2023-01-29 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 110 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 36 | Empty | 2024-09-15 | 2024-09-15 | 2023-02-04 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 120 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 50 | Empty | 2024-09-15 | 2024-09-15 | 2023-02-11 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 125 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 19 | Empty | 2024-09-15 | 2024-09-15 | 2023-02-10 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 130 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 10 | 153 | Empty | 2024-09-15 | 2024-09-15 | 2023-02-10 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 140 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 1 | 1 | Empty | 2024-09-15 | 2024-09-15 | 2023-03-03 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 150 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 14 | Empty | 2024-09-15 | 2024-09-15 | 2023-03-03 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 160 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 288 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 170 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2023-03-09 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 180 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2023-03-13 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 190 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 12 | 15 | Empty | 2024-09-15 | 2024-09-15 | 2023-04-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 200 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 50 | 40 | Empty | 2024-09-15 | 2024-09-15 | 2023-04-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 210 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 100 | 30 | Empty | 2024-09-15 | 2024-09-15 | 2023-04-24 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 220 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 20 | 20 | Empty | 2024-09-15 | 2024-09-15 | 2023-04-25 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 230 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 3 | Empty | 2024-09-15 | 2024-09-15 | 2023-06-12 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 240 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-06-12 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 250 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-06-12 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 260 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 10 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2023-06-24 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 270 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 30 | 9 | Empty | 2024-09-15 | 2024-09-15 | 2023-06-26 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 280 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 2 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 290 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 18 | 21 | Empty | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 300 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 24 | 37 | Empty | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 310 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 4 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 320 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 35 | Empty | 2024-09-15 | 2024-09-15 | 2023-08-04 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 330 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 7 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2023-08-28 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 340 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 12 | 12 | Empty | 2024-09-15 | 2024-09-15 | 2023-09-05 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 350 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 22 | Empty | 2024-09-15 | 2024-09-15 | 2023-09-09 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 360 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 29 | Empty | 2024-09-15 | 2024-09-15 | 2023-09-14 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 370 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 2 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2023-10-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 380 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 30 | 25 | Empty | 2024-09-15 | 2024-09-15 | 2023-10-10 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 390 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 50 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2023-10-15 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 400 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-TURB | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 100 | 15 | Empty | 2024-09-15 | 2024-09-15 | 2023-10-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 410 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 16 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-10 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 420 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 16 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-11 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 430 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 5 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-16 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 440 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 24 | 24 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 450 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 1 | 1 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 460 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 22 | 47.5 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 470 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 5 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 480 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 16 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 490 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 10 | 10 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-19 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 500 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 5 | 5 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-20 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 510 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 4 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-22 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 520 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 4 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-11-23 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 530 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 4 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2023-12-22 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 540 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 8 | 8 | Empty | 2024-09-15 | 2024-09-15 | 2023-12-28 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 550 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 3 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-11 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 560 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 12 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-14 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 570 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 580 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 3 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-17 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 590 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 32 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-18 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 600 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-20 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 610 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 16 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-21 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 620 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 8 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-21 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 630 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-22 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 640 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-22 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 650 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 19 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-23 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 660 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 9 | 9 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-25 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 670 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 22 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-25 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 680 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 16 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-28 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 690 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 8 | 8 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-30 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 700 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 15 | 15 | Empty | 2024-09-15 | 2024-09-15 | 2024-01-30 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 710 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 145 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 720 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 7 | Empty | 2024-09-15 | 2024-09-15 | 2024-02-18 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 730 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 20 | Empty | 2024-09-15 | 2024-09-15 | 2024-02-20 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 740 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 7 | Empty | 2024-09-15 | 2024-09-15 | 2024-02-20 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 750 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 7 | Empty | 2024-09-15 | 2024-09-15 | 2024-02-22 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 760 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 15 | Empty | 2024-09-15 | 2024-09-15 | 2024-02-25 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 770 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 40 | Empty | 2024-09-15 | 2024-09-15 | 2024-02-28 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 780 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 1 | 19 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 790 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 40 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 800 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 3 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 810 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-02 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 820 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 6 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-02 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 830 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-03 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 840 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 8 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-03 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 850 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-04 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 860 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 10 | 10 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-21 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 870 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-28 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 880 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 62 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-30 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 890 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 20 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-31 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 900 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 24 | Empty | 2024-09-15 | 2024-09-15 | 2024-03-31 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 910 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-04-02 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 920 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 10 | Empty | 2024-09-15 | 2024-09-15 | 2024-04-08 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 930 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 940 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 950 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-02 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 960 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-02 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 970 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 12 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-14 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 980 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 32 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-14 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 990 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 8 | Empty | 2024-09-15 | 2024-09-15 | 2024-05-31 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1000 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 32 | Empty | 2024-09-15 | 2024-09-15 | 2024-06-04 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1010 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-06-22 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1020 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 4 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-06-24 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1030 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ROPE | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 12 | 12 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-01 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1040 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 6 | 6 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 1050 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-11 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1060 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 3 | 15 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 1070 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 12 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-11 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1080 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 27 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 1090 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-PIPF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-15 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1100 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-PIPF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 2 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-15 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1110 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-PIPF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-15 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1120 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-SCAF | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-15 | 2024-07-20 | 2023-07-17 | 2026-01-02 | 1130 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-MECH | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 15 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 1140 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-RIGG | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 5 | 3 | Empty | 2024-09-15 | 2024-09-15 | 2024-07-21 | 2024-07-21 | 2023-07-17 | 2026-01-02 | 1150 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
4 | NOSD | WRO | MTN-ELEC | MTN-ELEC | 2300004499 | DK40 - HOURS MTN - FLM - FIRST LEVEL MTN | Assiting ONSHORE with various tasks | PCNF | PCNF | 0 | 4 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-07-17 | 2026-01-02 | 1160 | PCNF | PCNF | DF /C /84 | Assiting ONSHORE with various tasks | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100078445 | Faultfinding on batt charge signals | HVAC stop don't stop charging of batt | AWSC | AWSC | 5 | 0 | W21-W22 | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-11-24 | 2023-01-08 | 10 | AWSC | AWSC | DF /E /06/DFEZ-AE-19254 | HVAC stop don't stop charging of batt | Unknown
2 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100078445 | Faultfinding on batt charge signals | HVAC stop don't stop charging of batt | AWSC | AWSC | 0 | 0 | W21-W22 | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-11-24 | 2023-01-08 | 20 | AWSC | AWSC | DF /E /06/DFEZ-AE-19254 | HVAC stop don't stop charging of batt | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 0 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-18 | 2022-09-25 | 2023-02-07 | 10 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-SCAF | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 15 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-18 | 2024-09-19 | 2022-09-25 | 2023-02-07 | 20 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | PRODTECH | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-19 | 2024-09-20 | 2022-09-25 | 2023-02-07 | 30 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-ELEC | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 10 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-20 | 2024-09-21 | 2022-09-25 | 2023-02-07 | 40 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-MECH | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 10 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-21 | 2024-09-22 | 2022-09-25 | 2023-02-07 | 50 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-RIGG | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 15 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-22 | 2024-09-23 | 2022-09-25 | 2023-02-07 | 60 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-ELEC | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 10 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-23 | 2024-09-25 | 2022-09-25 | 2023-02-07 | 70 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | PRODTECH | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2022-09-25 | 2023-02-07 | 80 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
3 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100072694 | A-1640 Encl.Fan Ducts Corroded for Blowe | Build scaffold |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2022-09-25 | 2023-02-07 | 90 |  |  | DF /G /60/DFGA-G-1640 | Build scaffold | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400290936 | 4Y H2S PANEL MAINT - DFBA-FP-3806 | H2S PANEL MAINT - DFBA-FP-3806 |  |  | 14 | 0 | W29-W30 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-08-30 | 2023-11-26 | 10 |  |  | DF /B /34/DFBA-FP-3806 | H2S PANEL MAINT - DFBA-FP-3806 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339270 | DFF_1Y_22000 INT STRUCT INSP - GVI | DFF_1Y_22000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_22000 (LEVEL1) | DFF_1Y_22000 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106762 | No heat on HT on Hips FG | Remove Lagging. |  |  | 3 | 0 | W27-W28 | 2024-06-17 | 2024-06-21 | 2024-06-17 | 2024-06-18 | 2024-03-05 | 2024-07-18 | 20 |  |  | DF /G /34/DFGA-PIT-02476 | Remove Lagging. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106762 | No heat on HT on Hips FG | Remove Lagging. |  |  | 3 | 0 | W27-W28 | 2024-06-17 | 2024-06-21 | 2024-06-18 | 2024-06-18 | 2024-03-05 | 2024-07-18 | 30 |  |  | DF /G /34/DFGA-PIT-02476 | Remove Lagging. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106762 | No heat on HT on Hips FG | Remove Lagging. |  |  | 3 | 0 | W27-W28 | 2024-06-17 | 2024-06-21 | 2024-06-18 | 2024-06-19 | 2024-03-05 | 2024-07-18 | 40 |  |  | DF /G /34/DFGA-PIT-02476 | Remove Lagging. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106762 | No heat on HT on Hips FG | Remove Lagging. |  |  | 3 | 0 | W27-W28 | 2024-06-17 | 2024-06-21 | 2024-06-19 | 2024-06-20 | 2024-03-05 | 2024-07-18 | 50 |  |  | DF /G /34/DFGA-PIT-02476 | Remove Lagging. | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106762 | No heat on HT on Hips FG | Remove Lagging. |  |  | 3 | 0 | W27-W28 | 2024-06-17 | 2024-06-21 | 2024-06-20 | 2024-06-21 | 2024-03-05 | 2024-07-18 | 60 |  |  | DF /G /34/DFGA-PIT-02476 | Remove Lagging. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 8 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 10 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 20 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 30 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 40 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 50 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 60 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-06-05 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 70 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 12 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-05-23 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 80 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2022-09-14 | 2022-09-25 | 2022-03-18 | 2022-04-07 | 90 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-TELE | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 10 | 17 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2023-09-25 | 2023-09-26 | 2022-03-18 | 2022-04-07 | 100 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 6 | 5 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2023-09-25 | 2023-09-27 | 2022-03-18 | 2022-04-07 | 110 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100064888 | Varmtvandstank HEATER DFCC-V-1020. | Check control for water heaters | SCHSECE | SCHSECE | 0 | 0 | Wait mats - incorrect | 2023-09-25 | 2023-09-27 | 2023-09-25 | 2023-09-25 | 2022-03-18 | 2022-04-07 | 120 | SCHSECE | SCHSECE | DF /C /85/DFCC-TSHH-10691 | Check control for water heaters | Unknown
4 | DFB-O13 | WDF | MTN-INST | MTN-INST | 2100024610 | CMAT:Replace of ball valve HCV 40119 | L3 Isolate B & B | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2024-12-31 | 2025-01-01 | 2019-07-20 | 2020-07-14 | 10 | AWSC | AWSC | DF /B /37/DFBA-HCV-40119 | L3 Isolate B & B | Unknown
4 | DFB-O13 | WDF | MTN-INST | MTN-INST | 2100024610 | CMAT:Replace of ball valve HCV 40119 | L3 Isolate B & B | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2019-07-20 | 2020-07-14 | 20 | AWSC | AWSC | DF /B /37/DFBA-HCV-40119 | L3 Isolate B & B | Unknown
4 | DFB-O13 | WDF | MTN-INST | MTN-INST | 2100024610 | CMAT:Replace of ball valve HCV 40119 | L3 Isolate B & B | AWSC | AWSC | 8 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2019-07-20 | 2020-07-14 | 30 | AWSC | AWSC | DF /B /37/DFBA-HCV-40119 | L3 Isolate B & B | Unknown
4 | DFB-O13 | WDF | MTN-INST | MTN-INST | 2100024610 | CMAT:Replace of ball valve HCV 40119 | L3 Isolate B & B | AWSC | AWSC | 2 | 0 | W39-40 | 2024-12-31 | 2025-01-03 | 2025-01-02 | 2025-01-03 | 2019-07-20 | 2020-07-14 | 40 | AWSC | AWSC | DF /B /37/DFBA-HCV-40119 | L3 Isolate B & B | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084629 | udskifte batterier på emg.light | Additional material |  |  | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-22 | 2024-05-20 | 2024-05-20 | 2023-03-18 | 2023-07-31 | 10 |  |  | DF /C /05/DFCI-DP-1821-03 | Additional material | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084629 | udskifte batterier på emg.light | Additional material |  |  | 6 | 0 | W21-W22 | 2024-05-20 | 2024-05-22 | 2024-05-20 | 2024-05-22 | 2023-03-18 | 2023-07-31 | 20 |  |  | DF /C /05/DFCI-DP-1821-03 | Additional material | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084629 | udskifte batterier på emg.light | Additional material |  |  | 1 | 0 | W21-W22 | 2024-05-20 | 2024-05-22 | 2024-05-22 | 2024-05-22 | 2023-03-18 | 2023-07-31 | 30 |  |  | DF /C /05/DFCI-DP-1821-03 | Additional material | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100084629 | udskifte batterier på emg.light | Additional material |  |  | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-22 | 2024-05-20 | 2024-05-20 | 2023-03-18 | 2023-07-31 | 40 |  |  | DF /C /05/DFCI-DP-1821-03 | Additional material | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095452 | Replace defect light DFGA-LN-18328 | Isolate and prove dead |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 10 |  |  | DF /G /61/DFGA-LP-1853-09 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095452 | Replace defect light DFGA-LN-18328 | Isolate and prove dead |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-09-09 | 2024-01-22 | 20 |  |  | DF /G /61/DFGA-LP-1853-09 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100095452 | Replace defect light DFGA-LN-18328 | Isolate and prove dead |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-09-09 | 2024-01-22 | 40 |  |  | DF /G /61/DFGA-LP-1853-09 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100095452 | Replace defect light DFGA-LN-18328 | Isolate and prove dead |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-09 | 2024-01-22 | 50 |  |  | DF /G /61/DFGA-LP-1853-09 | Isolate and prove dead | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-06-19 | 2022-06-09 | 10 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-16 | 2020-06-19 | 2022-06-09 | 20 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-06-19 | 2022-06-09 | 30 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-18 | 2020-06-19 | 2022-06-09 | 40 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2020-06-19 | 2022-06-09 | 50 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-06-19 | 2022-06-09 | 60 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100023111 | Exchange valve in ringmain HCV-030016 | Exchange valve |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-06-19 | 2022-06-09 | 70 |  |  | DF /C /01/DFCC-HCV-030016 | Exchange valve | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100031699 | Troubleshoot DFA Trace heating cir.no.54 | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2020-05-27 | 2020-08-25 | 10 |  |  | DF /A /61/DFAA-N-1800-C_54 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100031699 | Troubleshoot DFA Trace heating cir.no.54 | Set personal isolation |  |  | 5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2020-05-27 | 2020-08-25 | 20 |  |  | DF /A /61/DFAA-N-1800-C_54 | Set personal isolation | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100031699 | Troubleshoot DFA Trace heating cir.no.54 | Set personal isolation |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2020-05-27 | 2020-08-25 | 30 |  |  | DF /A /61/DFAA-N-1800-C_54 | Set personal isolation | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000543 | Overskyende kampagneværktøj/PPE leveret | operation_description_not_present |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-03-05 | 2019-12-31 | 10 |  |  | DF /F | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400268065 | 1Y HVAC SUPP WALK-IN CABIN CHECK - DFB | Scaffold support | SCHSECE | SCHSECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-22 | 2024-06-17 | 2024-06-17 | 2023-07-06 | 2023-08-05 | 10 | SCHSECE | SCHSECE | DF /B /09/DFBA-X-9920 | Scaffold support | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400268065 | 1Y HVAC SUPP WALK-IN CABIN CHECK - DFB | Scaffold support | SCHSECE | SCHSECE | 15 | 0 | W25-W26 | 2024-06-17 | 2024-06-22 | 2024-06-17 | 2024-06-20 | 2023-07-06 | 2023-08-05 | 20 | SCHSECE | SCHSECE | DF /B /09/DFBA-X-9920 | Scaffold support | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400268065 | 1Y HVAC SUPP WALK-IN CABIN CHECK - DFB | Scaffold support | SCHSECE | SCHSECE | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-22 | 2024-06-21 | 2024-06-21 | 2023-07-06 | 2023-08-05 | 30 | SCHSECE | SCHSECE | DF /B /09/DFBA-X-9920 | Scaffold support | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400268065 | 1Y HVAC SUPP WALK-IN CABIN CHECK - DFB | Scaffold support | SCHSECE | SCHSECE | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-22 | 2024-06-21 | 2024-06-21 | 2023-07-06 | 2023-08-05 | 40 | SCHSECE | SCHSECE | DF /B /09/DFBA-X-9920 | Scaffold support | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-SCAF | 2400268065 | 1Y HVAC SUPP WALK-IN CABIN CHECK - DFB | Scaffold support | SCHSECE | SCHSECE | 6 | 0 | W25-W26 | 2024-06-17 | 2024-06-22 | 2024-06-21 | 2024-06-22 | 2023-07-06 | 2023-08-05 | 50 | SCHSECE | SCHSECE | DF /B /09/DFBA-X-9920 | Scaffold support | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012619 | Replace DFAA-PSV-30087 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-15 | 2023-06-03 | 2025-11-19 | 10 | SCH | SCH | DF /A /07/DFAA-PSV-30087 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012619 | Replace DFAA-PSV-30087 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-15 | 2024-07-16 | 2023-06-03 | 2025-11-19 | 20 | SCH | SCH | DF /A /07/DFAA-PSV-30087 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012619 | Replace DFAA-PSV-30087 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 5 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-16 | 2024-07-17 | 2023-06-03 | 2025-11-19 | 30 | SCH | SCH | DF /A /07/DFAA-PSV-30087 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200012619 | Replace DFAA-PSV-30087 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-17 | 2024-07-18 | 2023-06-03 | 2025-11-19 | 40 | SCH | SCH | DF /A /07/DFAA-PSV-30087 | Prod Assist (breaking containment) | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012619 | Replace DFAA-PSV-30087 - PSV 2023 | Prod Assist (breaking containment) | SCH | SCH | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-18 | 2024-07-18 | 2024-07-18 | 2023-06-03 | 2025-11-19 | 50 | SCH | SCH | DF /A /07/DFAA-PSV-30087 | Prod Assist (breaking containment) | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100057166 | DFG vacuum ejector weared out | Replace worn injector nozzle |  |  | 2 | 0 | Empty | 2024-11-02 | 2024-11-03 | 2024-11-02 | 2024-11-02 | 2021-11-02 | 2022-01-31 | 10 |  |  | DF /G /53/DFGA-X-3543 | Replace worn injector nozzle | Unknown
3 | DFG-3590 | WDF | MTN-MECH | MTN-MECH | 2100057166 | DFG vacuum ejector weared out | Replace worn injector nozzle |  |  | 8 | 0 | Empty | 2024-11-02 | 2024-11-03 | 2024-11-02 | 2024-11-03 | 2021-11-02 | 2022-01-31 | 20 |  |  | DF /G /53/DFGA-X-3543 | Replace worn injector nozzle | Unknown
3 | DFG-3590 | WDF | MTN-MECH | PRODTECH | 2100057166 | DFG vacuum ejector weared out | Replace worn injector nozzle |  |  | 2 | 0 | Empty | 2024-11-02 | 2024-11-03 | 2024-11-03 | 2024-11-03 | 2021-11-02 | 2022-01-31 | 30 |  |  | DF /G /53/DFGA-X-3543 | Replace worn injector nozzle | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112431 | DFCI-HR-0361 ball valve broken leaking | Add matr/Swivel grease nipple | SECE | SECE | 0 | 0 | Empty | 2024-09-02 | 2024-09-05 | 2024-09-02 | 2024-09-02 | 2024-06-22 | 2024-11-04 | 10 | SECE | SECE | DF /C /01/DFCI-HR-0361 | Add matr/Swivel grease nipple | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112431 | DFCI-HR-0361 ball valve broken leaking | Add matr/Swivel grease nipple | SECE | SECE | 2 | 0 | Empty | 2024-09-02 | 2024-09-05 | 2024-09-02 | 2024-09-03 | 2024-06-22 | 2024-11-04 | 20 | SECE | SECE | DF /C /01/DFCI-HR-0361 | Add matr/Swivel grease nipple | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112431 | DFCI-HR-0361 ball valve broken leaking | Add matr/Swivel grease nipple | SECE | SECE | 8 | 0 | Empty | 2024-09-02 | 2024-09-05 | 2024-09-03 | 2024-09-04 | 2024-06-22 | 2024-11-04 | 30 | SECE | SECE | DF /C /01/DFCI-HR-0361 | Add matr/Swivel grease nipple | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112431 | DFCI-HR-0361 ball valve broken leaking | Add matr/Swivel grease nipple | SECE | SECE | 2 | 0 | Empty | 2024-09-02 | 2024-09-05 | 2024-09-04 | 2024-09-04 | 2024-06-22 | 2024-11-04 | 40 | SECE | SECE | DF /C /01/DFCI-HR-0361 | Add matr/Swivel grease nipple | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100112431 | DFCI-HR-0361 ball valve broken leaking | Add matr/Swivel grease nipple | SECE | SECE | 8 | 0 | Empty | 2024-09-02 | 2024-09-05 | 2024-09-04 | 2024-09-05 | 2024-06-22 | 2024-11-04 | 50 | SECE | SECE | DF /C /01/DFCI-HR-0361 | Add matr/Swivel grease nipple | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112431 | DFCI-HR-0361 ball valve broken leaking | Add matr/Swivel grease nipple | SECE | SECE | 0 | 0 | Empty | 2024-09-02 | 2024-09-05 | 2024-09-05 | 2024-09-05 | 2024-06-22 | 2024-11-04 | 60 | SECE | SECE | DF /C /01/DFCI-HR-0361 | Add matr/Swivel grease nipple | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | MTN-MECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 0 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2023-02-18 | 2023-07-03 | 10 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | PRODTECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 2 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2023-04-28 | 2023-04-28 | 2023-02-18 | 2023-07-03 | 20 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | PRODTECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 4 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2023-02-18 | 2023-07-03 | 21 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | VEN-MECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 25 | 3 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-08-01 | 2023-02-18 | 2023-07-03 | 30 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | MTN-MECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 10 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2023-04-28 | 2023-04-29 | 2023-02-18 | 2023-07-03 | 40 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | MTN-MECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 0 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2023-05-04 | 2023-05-04 | 2023-02-18 | 2023-07-03 | 60 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | MTN-MECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 15 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2023-02-18 | 2023-07-03 | 70 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | PRODTECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 2 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2023-02-18 | 2023-07-03 | 80 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | VEN-MECH | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 4 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2023-02-18 | 2023-07-03 | 90 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | MTN-TURB | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 2 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2023-02-18 | 2023-07-03 | 100 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | DFG-IPHP | WGN | MTN-TURB | MTN-TURB | 2200012951 | DFG IP ASV leak | IMI CCI / PO | PCNF | PCNF | 0 | 0 | W35-36 break-in | 2024-07-30 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2023-02-18 | 2023-07-03 | 110 | PCNF | PCNF | DF /G /31/DFGA-FCV-430016 | IMI CCI / PO | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097008 | DFFE/78 Flush of slew bearing _ Grease | Assist | SCH | SCH | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2023-10-12 | 2024-02-24 | 10 | SCH | SCH | DF /F /78/DFFA-A-6101 | Assist | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100097008 | DFFE/78 Flush of slew bearing _ Grease | Assist | SCH | SCH | 4 | 0 | W23-W24 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2023-10-12 | 2024-02-24 | 20 | SCH | SCH | DF /F /78/DFFA-A-6101 | Assist | Unknown
2 | NE | WRO | MTN-TELE | MTN-TELE | 2300004042 | IT0098 - Telecom/Atcom assist. to B-link | IT0098 - Telecom/Atcom assist. to B-link | SCH | SCH | 84 | 0 | W21-W22 | 2024-05-20 | 2024-06-10 | 2024-05-20 | 2024-06-10 | 2022-07-18 | 2022-09-01 | 10 | SCH | SCH | DF /C /08/DFCI-DT-14-10-02 | IT0098 - Telecom/Atcom assist. to B-link | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400219093 | 1Y WI INST/CHOKE VALVES MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-03 | 2024-07-03 | 2022-11-15 | 2022-12-15 | 5 | SECE | SECE | DF /F /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400219093 | 1Y WI INST/CHOKE VALVES MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-03 | 2024-07-06 | 2022-11-15 | 2022-12-15 | 10 | SECE | SECE | DF /F /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400219093 | 1Y WI INST/CHOKE VALVES MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 12 | 0 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-06 | 2024-07-09 | 2022-11-15 | 2022-12-15 | 20 | SECE | SECE | DF /F /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400219093 | 1Y WI INST/CHOKE VALVES MAINT-DFF | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W27-W28 | 2024-07-03 | 2024-07-09 | 2024-07-09 | 2024-07-09 | 2022-11-15 | 2022-12-15 | 30 | SECE | SECE | DF /F /55/WATER-INJECTION-WELLS | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097349 | DFGA-HCV-030234 valve must be changed | Deisolate, check func / for leaks | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-05 | 2023-10-19 | 2024-03-02 | 10 | SECE | SECE | DF /G /01/DFGA-HRF-03303 | Deisolate, check func / for leaks | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097349 | DFGA-HCV-030234 valve must be changed | Deisolate, check func / for leaks | SECE | SECE | 6 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2023-10-19 | 2024-03-02 | 20 | SECE | SECE | DF /G /01/DFGA-HRF-03303 | Deisolate, check func / for leaks | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097349 | DFGA-HCV-030234 valve must be changed | Deisolate, check func / for leaks | SECE | SECE | 1 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-06 | 2024-10-06 | 2023-10-19 | 2024-03-02 | 30 | SECE | SECE | DF /G /01/DFGA-HRF-03303 | Deisolate, check func / for leaks | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322268 | DFC-27-WO-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 20 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 10 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 20 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 30 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 40 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 50 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 60 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 70 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 80 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 90 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 100 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 110 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 120 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 130 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 140 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002236 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002236 27.04.21 MAT FAN.EX PROF MUEH |  |  | 0 | 0 | Empty | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-04-18 | 2021-01-07 | 2021-02-16 | 150 |  |  | DF /F | 2300002236 27.04.21 MAT FAN.EX PROF MUEH | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027604 | Missing handle on DF /B /01/DFBA-HCV-038 | Isolate the leaking HCV-03812 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2019-07-24 | 2020-07-18 | 10 |  |  | DF /B /01/DFBA-HCV-03812 | Isolate the leaking HCV-03812 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100027604 | Missing handle on DF /B /01/DFBA-HCV-038 | Isolate the leaking HCV-03812 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2019-07-24 | 2020-07-18 | 20 |  |  | DF /B /01/DFBA-HCV-03812 | Isolate the leaking HCV-03812 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027604 | Missing handle on DF /B /01/DFBA-HCV-038 | Isolate the leaking HCV-03812 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2019-07-24 | 2020-07-18 | 30 |  |  | DF /B /01/DFBA-HCV-03812 | Isolate the leaking HCV-03812 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100027604 | Missing handle on DF /B /01/DFBA-HCV-038 | Isolate the leaking HCV-03812 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2019-07-24 | 2020-07-18 | 40 |  |  | DF /B /01/DFBA-HCV-03812 | Isolate the leaking HCV-03812 | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018141 | Replace Feeder protection 1841-M118 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M118-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018141 | Replace Feeder protection 1841-M118 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M118-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018141 | Replace Feeder protection 1841-M118 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M118-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018141 | Replace Feeder protection 1841-M118 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M118-02 | New mat num | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 2 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-02 | 2024-08-02 | 2024-08-30 | 2024-09-29 | 10 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 72 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-02 | 2024-08-06 | 2024-08-30 | 2024-09-29 | 20 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 12 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-06 | 2024-08-09 | 2024-08-30 | 2024-09-29 | 30 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 2 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-09 | 2024-08-09 | 2024-08-30 | 2024-09-29 | 50 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 24 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-09 | 2024-08-15 | 2024-08-30 | 2024-09-29 | 60 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 12 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-15 | 2024-08-18 | 2024-08-30 | 2024-09-29 | 70 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-ROUS | 2400322631 | 1Y PED CRANE CHECK VENDOR-DFFA-A-6101 | Check of slip ring & electric checks | AWSC | AWSC | 16 | 0 | Empty | 2024-08-02 | 2024-08-22 | 2024-08-18 | 2024-08-22 | 2024-08-30 | 2024-09-29 | 80 | AWSC | AWSC | DF /F /78/DFFA-A-6101 | Check of slip ring & electric checks | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058082 | DFF-30 Scale inj with unstable flow | Replace DFFA-FCV-390196 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2021-11-28 | 2022-02-26 | 10 |  |  | DF /F /75/DFFA-FCV-390196 | Replace DFFA-FCV-390196 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100058082 | DFF-30 Scale inj with unstable flow | Replace DFFA-FCV-390196 |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2021-11-28 | 2022-02-26 | 20 |  |  | DF /F /75/DFFA-FCV-390196 | Replace DFFA-FCV-390196 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100058082 | DFF-30 Scale inj with unstable flow | Replace DFFA-FCV-390196 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2021-11-28 | 2022-02-26 | 30 |  |  | DF /F /75/DFFA-FCV-390196 | Replace DFFA-FCV-390196 | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018149 | Replace Generator relay 1801A-07-02 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /F /61/DFFA-N-1801A-07-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018149 | Replace Generator relay 1801A-07-02 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /F /61/DFFA-N-1801A-07-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018149 | Replace Generator relay 1801A-07-02 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /F /61/DFFA-N-1801A-07-02 | Isolation of Breaker section | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018149 | Replace Generator relay 1801A-07-02 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /F /61/DFFA-N-1801A-07-02 | Isolation of Breaker section | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057923 | Replace defect light 1806-4-L1D DFClvl3 | De-isolate accordingly |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-21 | 2022-06-20 | 10 |  |  | DF /C /62 | De-isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057923 | Replace defect light 1806-4-L1D DFClvl3 | De-isolate accordingly |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-21 | 2022-06-20 | 20 |  |  | DF /C /62 | De-isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057923 | Replace defect light 1806-4-L1D DFClvl3 | De-isolate accordingly |  |  | 2 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-01-21 | 2022-06-20 | 30 |  |  | DF /C /62 | De-isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057923 | Replace defect light 1806-4-L1D DFClvl3 | De-isolate accordingly |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-01-21 | 2022-06-20 | 40 |  |  | DF /C /62 | De-isolate accordingly | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339096 | DFC_1Y_47000 INT STRUCT INSP - GVI | DFC_1Y_47000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_47000 (ROOF DECK) | DFC_1Y_47000 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2020-06-23 | 2024-04-02 | 2020-03-16 | 2020-04-05 | 10 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 6 | 2 | W35-W36 | 2024-08-26 | 2024-08-26 | 2020-06-23 | 2024-04-02 | 2020-03-16 | 2020-04-05 | 30 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2020-06-23 | 2024-04-02 | 2020-03-16 | 2020-04-05 | 40 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 4 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-16 | 2020-04-05 | 50 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 6 | 20 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-16 | 2020-04-05 | 60 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-16 | 2020-04-05 | 70 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-16 | 2020-04-05 | 80 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-16 | 2020-04-05 | 90 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 0 | 10 | W35-W36 | 2024-08-26 | 2024-08-26 | 2021-04-05 | 2024-04-02 | 2020-03-16 | 2020-04-05 | 100 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 0 | 4 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-03-13 | 2024-04-02 | 2020-03-16 | 2020-04-05 | 110 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 16 | 16 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-03-11 | 2024-04-02 | 2020-03-16 | 2020-04-05 | 120 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100029794 | Pump defect. Backload for repair. | REP&RETUR | PCNFSCH | PCNFSCH | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2020-03-16 | 2020-04-05 | 130 | PCNFSCH | PCNFSCH | DF /F /50/DFFA-P-3403 | REP&RETUR | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400293719 | 2Y SYS 10 INSTRUMENTS MAINT- DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 4 | W29-W30 | 2024-07-16 | 2024-07-20 | 2024-07-16 | 2024-07-17 | 2023-11-14 | 2023-12-30 | 10 | SCHSECE | SCHSECE | DF /C /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400293719 | 2Y SYS 10 INSTRUMENTS MAINT- DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 10 | 10 | W29-W30 | 2024-07-16 | 2024-07-20 | 2024-07-17 | 2024-07-19 | 2023-11-14 | 2023-12-30 | 20 | SCHSECE | SCHSECE | DF /C /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400293719 | 2Y SYS 10 INSTRUMENTS MAINT- DFC | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 4 | W29-W30 | 2024-07-16 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2023-11-14 | 2023-12-30 | 30 | SCHSECE | SCHSECE | DF /C /10/INSTRUMENTS | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023950 | CMAT:Change out backlight LG-760001 | Isolate LG-760001 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2018-08-10 | 2020-07-30 | 10 |  |  | DF /G /75/DFGA-LG-760001 | Isolate LG-760001 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023950 | CMAT:Change out backlight LG-760001 | Isolate LG-760001 |  |  | 10 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2018-08-10 | 2020-07-30 | 20 |  |  | DF /G /75/DFGA-LG-760001 | Isolate LG-760001 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100023950 | CMAT:Change out backlight LG-760001 | Isolate LG-760001 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2018-08-10 | 2020-07-30 | 30 |  |  | DF /G /75/DFGA-LG-760001 | Isolate LG-760001 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235555 | 4Y 3KV N-SWB MAINT DFCI-N-1801-15 | PO Caverion | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2022-12-31 | 2023-03-29 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801-15A-01 | PO Caverion | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235555 | 4Y 3KV N-SWB MAINT DFCI-N-1801-15 | PO Caverion | AWSC | AWSC | 13 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2022-12-31 | 2023-03-29 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801-15A-01 | PO Caverion | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235555 | 4Y 3KV N-SWB MAINT DFCI-N-1801-15 | PO Caverion | AWSC | AWSC | 5 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801-15A-01 | PO Caverion | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235555 | 4Y 3KV N-SWB MAINT DFCI-N-1801-15 | PO Caverion | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801-15A-01 | PO Caverion | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235555 | 4Y 3KV N-SWB MAINT DFCI-N-1801-15 | PO Caverion | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2022-12-31 | 2023-03-29 | 50 | AWSC | AWSC | DF /C /61/DFCI-N-1801-15A-01 | PO Caverion | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259015 | 1Y SCRAPER RECEIVER MAINT-DFAA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-05-08 | 2023-06-07 | 10 | SECE | SECE | DF /A /12/DFAA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400259015 | 1Y SCRAPER RECEIVER MAINT-DFAA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-05-08 | 2023-06-07 | 20 | SECE | SECE | DF /A /12/DFAA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259015 | 1Y SCRAPER RECEIVER MAINT-DFAA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2023-05-08 | 2023-06-07 | 30 | SECE | SECE | DF /A /12/DFAA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400259015 | 1Y SCRAPER RECEIVER MAINT-DFAA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-05-08 | 2023-06-07 | 40 | SECE | SECE | DF /A /12/DFAA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 10 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | PRODTECH | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 20 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 30 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-PIPF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 40 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-PIPF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 50 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 60 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | PRODTECH | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-14 | 2018-02-27 | 2019-02-22 | 70 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 4 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 80 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-PIPF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 85 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-PIPF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 6.700000000000000177635683938 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 90 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | PRODTECH | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 3 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 100 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | VEN-ELEC | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 110 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
4 | NOSD | WGN | MTN-SCAF | MTN-SCAF | 2200003179 | CMAT:FCV-290119 heavly corroded. | Prepair rigging |  |  | 5.4000000000000003552713678785 | 0 | Empty | 2023-02-13 | 2023-02-14 | 2023-02-13 | 2023-02-13 | 2018-02-27 | 2019-02-22 | 120 |  |  | DF /F /37/DFFA-FCV-290119 | Prepair rigging | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400341904 | DFG_1Y_JACKET ABOVE WATER INSPECTION | DFG_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /86/JACKET - L.A.T. TO EL 22000 | DFG_1Y_JACKET ABOVE WATER INSPECTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235698 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235698 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 23 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-22 | 2024-09-27 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235698 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-28 | 2024-09-29 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF04-BA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235698 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF04 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF04-BA001 | ISOLATION ELECTRICAL | Unknown
3 | DFB-OIL | WDF | MTN-INST | PRODTECH | 2100023126 | 2 stk PIèr på ESDV control hydraulikpane | Change out PI |  |  | 2 | 0 | W27-28 SECE INST | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2020-02-06 | 2020-05-06 | 10 |  |  | DF /C /12/DFCI-ESDV-33021 | Change out PI | Unknown
3 | DFB-OIL | WDF | MTN-INST | MTN-INST | 2100023126 | 2 stk PIèr på ESDV control hydraulikpane | Change out PI |  |  | 2 | 0 | W27-28 SECE INST | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2020-02-06 | 2020-05-06 | 20 |  |  | DF /C /12/DFCI-ESDV-33021 | Change out PI | Unknown
3 | DFB-OIL | WDF | MTN-INST | MTN-INST | 2100023126 | 2 stk PIèr på ESDV control hydraulikpane | Change out PI |  |  | 1 | 0 | W27-28 SECE INST | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2020-02-06 | 2020-05-06 | 30 |  |  | DF /C /12/DFCI-ESDV-33021 | Change out PI | Unknown
3 | DFB-OIL | WDF | MTN-INST | PRODTECH | 2100023126 | 2 stk PIèr på ESDV control hydraulikpane | Change out PI |  |  | 2 | 0 | W27-28 SECE INST | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2020-02-06 | 2020-05-06 | 40 |  |  | DF /C /12/DFCI-ESDV-33021 | Change out PI | Unknown
3 | DFB-OIL | WDF | MTN-INST | MTN-INST | 2100023126 | 2 stk PIèr på ESDV control hydraulikpane | Change out PI |  |  | 0 | 0 | W27-28 SECE INST | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2020-02-06 | 2020-05-06 | 50 |  |  | DF /C /12/DFCI-ESDV-33021 | Change out PI | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100042074 | Internal leaking upstream HCV-035219 | Order deluge valve parts | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-12-24 | 2021-03-24 | 10 | AWSC | AWSC | DF /F /01/DFFA-HCV-035219 | Order deluge valve parts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042074 | Internal leaking upstream HCV-035219 | Order deluge valve parts | AWSC | AWSC | 10 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2020-12-24 | 2021-03-24 | 20 | AWSC | AWSC | DF /F /01/DFFA-HCV-035219 | Order deluge valve parts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042074 | Internal leaking upstream HCV-035219 | Order deluge valve parts | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-04 | 2020-12-24 | 2021-03-24 | 30 | AWSC | AWSC | DF /F /01/DFFA-HCV-035219 | Order deluge valve parts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100042074 | Internal leaking upstream HCV-035219 | Order deluge valve parts | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-04 | 2020-12-24 | 2021-03-24 | 40 | AWSC | AWSC | DF /F /01/DFFA-HCV-035219 | Order deluge valve parts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100042074 | Internal leaking upstream HCV-035219 | Order deluge valve parts | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2020-12-24 | 2021-03-24 | 50 | AWSC | AWSC | DF /F /01/DFFA-HCV-035219 | Order deluge valve parts | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100042074 | Internal leaking upstream HCV-035219 | Order deluge valve parts | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2020-12-24 | 2021-03-24 | 60 | AWSC | AWSC | DF /F /01/DFFA-HCV-035219 | Order deluge valve parts | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2020-02-27 | 2020-07-26 | 10 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-18 | 2020-02-27 | 2020-07-26 | 20 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-17 | 2020-02-27 | 2020-07-26 | 30 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-18 | 2020-02-27 | 2020-07-26 | 40 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-18 | 2020-02-27 | 2020-07-26 | 50 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-19 | 2020-02-27 | 2020-07-26 | 60 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 16 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-21 | 2020-02-27 | 2020-07-26 | 70 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-22 | 2020-02-27 | 2020-07-26 | 80 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2020-02-27 | 2020-07-26 | 90 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2020-02-27 | 2020-07-26 | 100 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2020-02-27 | 2020-07-26 | 110 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100023363 | DFB/78: A/C unit on cabin roof corroded | Increase of PO 4500053524 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2020-02-27 | 2020-07-26 | 120 |  |  | DF /B /78/DFBA-X-6102 | Increase of PO 4500053524 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344060 | 1Y SAND JETTING PUMP MAINT-DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-17 | 2024-08-19 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2024-09-16 | 10 | SECE | SECE | DF /C /27/DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344060 | 1Y SAND JETTING PUMP MAINT-DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-17 | 2024-08-19 | 2024-08-17 | 2024-08-18 | 2024-08-17 | 2024-09-16 | 20 | SECE | SECE | DF /C /27/DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344060 | 1Y SAND JETTING PUMP MAINT-DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-17 | 2024-08-19 | 2024-08-18 | 2024-08-18 | 2024-08-17 | 2024-09-16 | 30 | SECE | SECE | DF /C /27/DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344060 | 1Y SAND JETTING PUMP MAINT-DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-17 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-17 | 2024-09-16 | 40 | SECE | SECE | DF /C /27/DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344060 | 1Y SAND JETTING PUMP MAINT-DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-17 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-17 | 2024-09-16 | 50 | SECE | SECE | DF /C /27/DFCI-P-5044 | SAND JETTING PUMP MAINT-DFCI-P-5044 | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300002067 | BACKLOAD AF INSTRUMENTS FOR RE-CAL. | Materials |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-19 | 2022-02-13 | 10 |  |  | DF /C /84 | Materials | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300002067 | BACKLOAD AF INSTRUMENTS FOR RE-CAL. | Materials |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-19 | 2022-02-13 | 20 |  |  | DF /C /84 | Materials | Unknown
4 | NE | WRO | MTN-INST | MTN-INST | 2300002067 | BACKLOAD AF INSTRUMENTS FOR RE-CAL. | Materials |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-04-19 | 2022-02-13 | 30 |  |  | DF /C /84 | Materials | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400243998 | 6M SDV LUB/MAINT OIL - DFA | SDV LUB/INSP OIL - DFA |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-19 | 2023-05-05 | 10 |  |  | DF /A /03/SDV-VALVES | SDV LUB/INSP OIL - DFA | Unknown
D | NOSD | WPM | MTN-MECH | MTN-PAIN | 2400274690 | 1Y SLIDING DOORS DFA | SLIDING DOORS DF |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2023-08-08 | 2023-09-24 | 10 |  |  | DF /A /86 | SLIDING DOORS DF | Unknown
4 | NOSD | WGN | VEN-INST | MTN-LAGG | 2200009245 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-29 | 2024-01-08 | 2024-01-08 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7141-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-SCAF | 2200009245 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 144 | 0 | Empty | 2024-01-08 | 2024-01-29 | 2024-01-08 | 2024-01-16 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7141-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-LAGG | 2200009245 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-29 | 2024-01-17 | 2024-01-19 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7141-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | VEN-INST | 2200009245 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-29 | 2024-01-19 | 2024-01-20 | 2022-02-07 | 2022-07-07 | 35 |  |  | DF /F /55/DFF-6-PHS-030-7141-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-LAGG | 2200009245 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-29 | 2024-01-20 | 2024-01-23 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /F /55/DFF-6-PHS-030-7141-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INST | MTN-SCAF | 2200009245 | Insulation assist FORCE 15795 | Bilfinger inspection |  |  | 96 | 0 | Empty | 2024-01-08 | 2024-01-29 | 2024-01-23 | 2024-01-29 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /F /55/DFF-6-PHS-030-7141-GF-U | Bilfinger inspection | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092674 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 4.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-13 | 2023-07-27 | 2023-12-09 | 10 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100092674 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 13 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-13 | 2024-08-16 | 2023-07-27 | 2023-12-09 | 20 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092674 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 3.5 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-13 | 2023-07-27 | 2023-12-09 | 30 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100092674 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-13 | 2024-08-14 | 2023-07-27 | 2023-12-09 | 40 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100092674 | Rep of Lighting Fixtures | SCAFFOLD INSTALLATION |  |  | 12 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-15 | 2023-07-27 | 2023-12-09 | 50 |  |  | DF /F /05/DFFA-N-1812 | SCAFFOLD INSTALLATION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 22 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 0 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 25 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 26 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 27 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-12 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-11 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284237 | PSV Exchange - DFCM-PSV-54381 | Prod Assist (breaking containment) | AWSC | AWSC | 10 | 0 | Empty | 2024-10-12 | 2024-12-12 | 2024-12-10 | 2024-12-11 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /C /07/DFCM-PSV-54381 | Prod Assist (breaking containment) | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342426 | 1Y CATALYTIC GAS DETECTORS - DFC LVL 1 | CATALYTIC GAS DETECTORS CHECK | SECE | SECE | 26 | 0 | W33-W34 | 2024-08-12 | 2024-08-18 | 2024-08-12 | 2024-08-18 | 2024-07-29 | 2024-08-28 | 10 | SECE | SECE | DF /C /03/FGS-DETECTORS | CATALYTIC GAS DETECTORS CHECK | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100106070 | Change the 69,7 mm orifices to a 46,0 mm | Change the 69,7 mm orifices to a 46,0 mm |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-03-09 | 2024-07-22 | 10 |  |  | DF /F /55/DFFA-FE-351010 | Change the 69,7 mm orifices to a 46,0 mm | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 1.3000000000000000444089209845 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-11 | 2024-03-11 | 2018-04-04 | 2018-09-01 | 10 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 2.7000000000000001776356839392 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-11 | 2024-03-11 | 2018-04-04 | 2018-09-01 | 20 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 26.100000000000001421085471512 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-11 | 2024-03-14 | 2018-04-04 | 2018-09-01 | 30 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-14 | 2024-03-15 | 2018-04-04 | 2018-09-01 | 40 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 4 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-15 | 2024-03-16 | 2018-04-04 | 2018-09-01 | 50 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-16 | 2024-03-17 | 2018-04-04 | 2018-09-01 | 60 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 0.6999999999999999555910790147 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-17 | 2024-03-17 | 2018-04-04 | 2018-09-01 | 70 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 13.400000000000000355271367876 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-17 | 2024-03-18 | 2018-04-04 | 2018-09-01 | 80 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 8.699999999999999289457264236 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-18 | 2024-03-19 | 2018-04-04 | 2018-09-01 | 85 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-ELEC | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 21.39999999999999857891452847 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-19 | 2024-03-22 | 2018-04-04 | 2018-09-01 | 90 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-LAGG | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 57 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-22 | 2024-03-25 | 2018-04-04 | 2018-09-01 | 100 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 4 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-25 | 2024-03-26 | 2018-04-04 | 2018-09-01 | 110 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100027605 | ANOP CMAT:DFC Replacement of spools at P | L3 Demol of Heat Tracing |  |  | 26.100000000000001421085471512 | 0 | Empty | 2024-03-11 | 2024-03-29 | 2024-03-26 | 2024-03-29 | 2018-04-04 | 2018-09-01 | 120 |  |  | DF /C /28 | L3 Demol of Heat Tracing | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-29 | 2024-07-31 | 2021-02-05 | 2021-03-17 | 10 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-07-31 | 2024-08-01 | 2021-02-05 | 2021-03-17 | 20 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-01 | 2021-02-05 | 2021-03-17 | 30 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-02 | 2021-02-05 | 2021-03-17 | 40 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-01 | 2024-08-02 | 2021-02-05 | 2021-03-17 | 50 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-03 | 2021-02-05 | 2021-03-17 | 60 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-02 | 2024-08-03 | 2021-02-05 | 2021-03-17 | 70 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-03 | 2024-08-04 | 2021-02-05 | 2021-03-17 | 80 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-04 | 2024-08-05 | 2021-02-05 | 2021-03-17 | 90 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-05 | 2024-08-06 | 2021-02-05 | 2021-03-17 | 100 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-06 | 2024-08-06 | 2021-02-05 | 2021-03-17 | 110 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-06 | 2024-08-07 | 2021-02-05 | 2021-03-17 | 120 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044997 | Hole in actuator for DFGA-PDCV-340411 | Isolate PCV |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-08 | 2024-08-07 | 2024-08-08 | 2021-02-05 | 2021-03-17 | 130 |  |  | DF /G /27/DFGA-PDCV-340411 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100094032 | Scale/Corrosion Pump DFA-PM-39222 | Scale/Corrosion Pump DFA-PM-39222 |  |  | 0 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2023-08-16 | 2023-12-29 | 10 |  |  | DF /A /75/DFAA-PM-39222 | Scale/Corrosion Pump DFA-PM-39222 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100079750 | PIT-02476 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 10 |  |  | DF /G /34/DFGA-PIT-02476 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100079750 | PIT-02476 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 20 |  |  | DF /G /34/DFGA-PIT-02476 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-LAGG | 2100079750 | PIT-02476 is missing insulation | Isolate Heat Tracing |  |  | 8 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 30 |  |  | DF /G /34/DFGA-PIT-02476 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100079750 | PIT-02476 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-02 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 40 |  |  | DF /G /34/DFGA-PIT-02476 | Isolate Heat Tracing | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100079750 | PIT-02476 is missing insulation | Isolate Heat Tracing |  |  | 1 | 0 | Empty | 2023-06-02 | 2023-06-03 | 2023-06-03 | 2023-06-03 | 2023-02-02 | 2023-06-17 | 50 |  |  | DF /G /34/DFGA-PIT-02476 | Isolate Heat Tracing | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009255 | Insulation assist bilfinger 20985(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /G /30/DFG-18-GPS-043-0017-DB-A | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009255 | Insulation assist bilfinger 20985(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-28 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /G /30/DFG-18-GPS-043-0017-DB-A | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009255 | Insulation assist bilfinger 20985(COMP) | Bilfinger inspection |  |  | 6 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-28 | 2023-03-28 | 2022-02-09 | 2022-07-09 | 25 |  |  | DF /G /30/DFG-18-GPS-043-0017-DB-A | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009255 | Insulation assist bilfinger 20985(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-28 | 2023-03-31 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /G /30/DFG-18-GPS-043-0017-DB-A | Bilfinger inspection | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400337271 | 6M SW FILT FEED PUMP MAINT P-3511/12/13 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2024-07-27 | 2024-08-15 | 5 |  |  | DF /C /54/DFCM-P-3511 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337271 | 6M SW FILT FEED PUMP MAINT P-3511/12/13 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2024-07-27 | 2024-08-15 | 10 |  |  | DF /C /54/DFCM-P-3511 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400337271 | 6M SW FILT FEED PUMP MAINT P-3511/12/13 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2024-07-27 | 2024-08-15 | 20 |  |  | DF /C /54/DFCM-P-3511 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003265 | CMAT:Snap-tite leaking hydraulic fluid | L3 Safing skid |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2018-07-29 | 2018-10-27 | 10 |  |  | DF /F /10/DFFA-XCV-301237 | L3 Safing skid | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200003265 | CMAT:Snap-tite leaking hydraulic fluid | L3 Safing skid |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-07-29 | 2018-10-27 | 20 |  |  | DF /F /10/DFFA-XCV-301237 | L3 Safing skid | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003265 | CMAT:Snap-tite leaking hydraulic fluid | L3 Safing skid |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2018-07-29 | 2018-10-27 | 30 |  |  | DF /F /10/DFFA-XCV-301237 | L3 Safing skid | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050335 | DFFA-A-5901 Bad hyd hose | Personal isolation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-06-10 | 2021-09-08 | 10 |  |  | DF /F /07/DFFA-A-5901 | Personal isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050335 | DFFA-A-5901 Bad hyd hose | Personal isolation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-06-10 | 2021-09-08 | 20 |  |  | DF /F /07/DFFA-A-5901 | Personal isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050335 | DFFA-A-5901 Bad hyd hose | Personal isolation |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-06-10 | 2021-09-08 | 30 |  |  | DF /F /07/DFFA-A-5901 | Personal isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050335 | DFFA-A-5901 Bad hyd hose | Personal isolation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-06-10 | 2021-09-08 | 40 |  |  | DF /F /07/DFFA-A-5901 | Personal isolation | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050335 | DFFA-A-5901 Bad hyd hose | Personal isolation |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-06-10 | 2021-09-08 | 50 |  |  | DF /F /07/DFFA-A-5901 | Personal isolation | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193024 | 1Y CHEMICAL TANK SKID, A-39850 | 1Y CHEMICAL TANK SKID, A-39850 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /75/DFAA-A-39850 | 1Y CHEMICAL TANK SKID, A-39850 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036097 | Utæt ved tilgangsrør & pumpehus. | find out why pump is leaking |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2020-07-22 | 2020-08-31 | 10 |  |  | DF /F /75/DFFA-P-3912 | find out why pump is leaking | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036097 | Utæt ved tilgangsrør & pumpehus. | find out why pump is leaking |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-07-22 | 2020-08-31 | 20 |  |  | DF /F /75/DFFA-P-3912 | find out why pump is leaking | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036097 | Utæt ved tilgangsrør & pumpehus. | find out why pump is leaking |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-07-22 | 2020-08-31 | 30 |  |  | DF /F /75/DFFA-P-3912 | find out why pump is leaking | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100036097 | Utæt ved tilgangsrør & pumpehus. | find out why pump is leaking |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2020-07-22 | 2020-08-31 | 40 |  |  | DF /F /75/DFFA-P-3912 | find out why pump is leaking | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 0.5 | 6 | W49-50 | 2024-08-12 | 2024-08-13 | 2023-12-10 | 2023-12-18 | 2020-08-20 | 2020-11-18 | 10 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 0.5 | 6 | W49-50 | 2024-08-12 | 2024-08-13 | 2023-12-10 | 2023-12-18 | 2020-08-20 | 2020-11-18 | 20 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 2 | 16 | W49-50 | 2024-08-12 | 2024-08-13 | 2023-12-10 | 2023-12-18 | 2020-08-20 | 2020-11-18 | 30 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 1 | 1 | W49-50 | 2024-08-12 | 2024-08-13 | 2023-12-10 | 2023-12-18 | 2020-08-20 | 2020-11-18 | 40 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 0.5 | 1 | W49-50 | 2024-08-12 | 2024-08-13 | 2023-12-10 | 2023-12-18 | 2020-08-20 | 2020-11-18 | 50 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 0 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2020-08-20 | 2020-11-18 | 60 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 1 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2020-08-20 | 2020-11-18 | 70 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 1 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2020-08-20 | 2020-11-18 | 80 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 4 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2020-08-20 | 2020-11-18 | 90 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 2.5 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2020-08-20 | 2020-11-18 | 100 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 1 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2020-08-20 | 2020-11-18 | 110 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100036450 | Positions indicator is stuck | Isolate position switches | PCNFSCH | PCNFSCH | 1 | 0 | W49-50 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2020-08-20 | 2020-11-18 | 120 | PCNFSCH | PCNFSCH | DF /F /10/DFFA-XCV-301118 | Isolate position switches | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400193032 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59190 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59190 |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /B /07/DFBA-FP-59190 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59190 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400219096 | 6M POT WATER SAMPLE PUMP MAINT-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-11-25 | 2022-12-14 | 10 |  |  | DF /C /85/DFCM-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400219096 | 6M POT WATER SAMPLE PUMP MAINT-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-11-25 | 2022-12-14 | 20 |  |  | DF /C /85/DFCM-P-5009 | POT WATER SAMPLE PUMP MAINT-P-5009 | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 2 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-05-20 | 2022-12-26 | 2023-05-10 | 10 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 2 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-20 | 2024-05-21 | 2022-12-26 | 2023-05-10 | 20 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 2 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-21 | 2024-05-21 | 2022-12-26 | 2023-05-10 | 30 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 2 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-21 | 2024-05-22 | 2022-12-26 | 2023-05-10 | 40 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 3 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-21 | 2024-05-22 | 2022-12-26 | 2023-05-10 | 50 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 3 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-21 | 2024-05-22 | 2022-12-26 | 2023-05-10 | 60 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 2 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-22 | 2024-05-22 | 2022-12-26 | 2023-05-10 | 70 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 1 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-22 | 2024-05-23 | 2022-12-26 | 2023-05-10 | 80 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100081827 | ESDV-500011 DFF HP Cyklon STUCK!! | Isolate controls and hydraulic | SECE | SECE | 2 | 0 | Empty | 2024-05-20 | 2024-05-23 | 2024-05-23 | 2024-05-23 | 2022-12-26 | 2023-05-10 | 90 | SECE | SECE | DF /F /27/DFFA-ESDV-500011 | Isolate controls and hydraulic | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2023-12-31 | 2023-12-31 | 2021-06-27 | 2021-08-06 | 2 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2023-12-31 | 2023-12-31 | 2021-06-27 | 2021-08-06 | 3 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 0 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2023-12-31 | 2023-12-31 | 2021-06-27 | 2021-08-06 | 10 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 6 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2023-12-31 | 2023-12-31 | 2021-06-27 | 2021-08-06 | 20 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2023-12-31 | 2024-01-01 | 2021-06-27 | 2021-08-06 | 30 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 6 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2024-01-01 | 2024-01-01 | 2021-06-27 | 2021-08-06 | 40 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2024-01-02 | 2024-01-02 | 2021-06-27 | 2021-08-06 | 50 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 12 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2024-01-03 | 2024-01-03 | 2021-06-27 | 2021-08-06 | 60 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
3 | NOSD | WDF | INP-SITE | MTN-ROPE | 2100051102 | ANOP Leak on line DFF-4"-WF-037015-AN P | QC-LOG, COAT SPOOL+SUP+VALVE | AWSC | AWSC | 3 | 0 | Empty | 2023-12-31 | 2024-01-04 | 2024-01-04 | 2024-01-04 | 2021-06-27 | 2021-08-06 | 70 | AWSC | AWSC | DF /F /01/DFF-4-WF-003-7015-AN-T | QC-LOG, COAT SPOOL+SUP+VALVE | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 20 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 24 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-17 | 2024-07-20 | 2024-10-30 | 2024-12-31 | 30 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 5 | 8 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-20 | 2024-07-21 | 2024-10-30 | 2024-12-31 | 40 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 2 | 2 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-21 | 2024-07-22 | 2024-10-30 | 2024-12-31 | 50 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-22 | 2024-07-23 | 2024-10-30 | 2024-12-31 | 60 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 12 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-23 | 2024-07-24 | 2024-10-30 | 2024-12-31 | 70 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-24 | 2024-07-25 | 2024-10-30 | 2024-12-31 | 80 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 5 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-25 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 90 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 4 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-26 | 2024-10-30 | 2024-12-31 | 100 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-26 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 110 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284225 | PSV Calibration - DFAA-PSV-35582 | Rigging assist (remove) | AWSC | AWSC | 2 | 0 | Empty | 2024-07-16 | 2024-07-27 | 2024-07-27 | 2024-07-27 | 2024-10-30 | 2024-12-31 | 120 | AWSC | AWSC | DF /A /53/DFAA-PSV-35582 | Rigging assist (remove) | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100086993 | FSL-120023 defekt/mangler kalibrering | Isolate Flow Switch |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-22 | 2023-09-04 | 10 |  |  | DF /F /09/DFFA-FS-120023 | Isolate Flow Switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086993 | FSL-120023 defekt/mangler kalibrering | Isolate Flow Switch |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-22 | 2023-09-04 | 20 |  |  | DF /F /09/DFFA-FS-120023 | Isolate Flow Switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086993 | FSL-120023 defekt/mangler kalibrering | Isolate Flow Switch |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-22 | 2023-09-04 | 30 |  |  | DF /F /09/DFFA-FS-120023 | Isolate Flow Switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100086993 | FSL-120023 defekt/mangler kalibrering | Isolate Flow Switch |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-22 | 2023-09-04 | 40 |  |  | DF /F /09/DFFA-FS-120023 | Isolate Flow Switch | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100086993 | FSL-120023 defekt/mangler kalibrering | Isolate Flow Switch |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-22 | 2023-09-04 | 50 |  |  | DF /F /09/DFFA-FS-120023 | Isolate Flow Switch | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325734 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39240 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39240 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /A /75/DFAA-A-39240 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39240 | Unknown
4 | NE | WRO | MTN-ROUS | MTN-ROUS | 2300000769 | DÆKKETS MAX/MIN 01.01.19 TIL 31.12.19 | DÆKKET MAX/MIN 01.03.20 TIL31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2019-12-02 | 2019-12-31 | 10 |  |  | DF /C | DÆKKET MAX/MIN 01.03.20 TIL31.12.20 | Unknown
4 | NE | WRO | MTN-ROUS | MTN-ROUS | 2300000769 | DÆKKETS MAX/MIN 01.01.19 TIL 31.12.19 | DÆKKET MAX/MIN 01.03.20 TIL31.12.20 |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2019-12-02 | 2019-12-31 | 20 |  |  | DF /C | DÆKKET MAX/MIN 01.03.20 TIL31.12.20 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058040 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | BL-TEAM | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 99 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058040 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 4 | 0 | BL-TEAM | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 100 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058040 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 4 | 0 | BL-TEAM | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-01-25 | 2022-06-24 | 110 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058040 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | BL-TEAM | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 199 |  |  | DF /F /62 | Isolate light group | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100058040 | Replace defect lighting fixture dff lvl2 | Isolate light group |  |  | 1 | 0 | BL-TEAM | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-01-25 | 2022-06-24 | 400 |  |  | DF /F /62 | Isolate light group | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400293738 | 1Y HV TESTER/EARTHING EQUIP MAINT - DFC | HV TESTER/EARTHING EQUIP MAINT - DFC |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-23 | 2023-12-29 | 10 |  |  | DF /C /84/TEST-EQUIPMENT | HV TESTER/EARTHING EQUIP MAINT - DFC | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059290 | Troubleshoot Q54 LNJB-1850-0054-L3-A | Troubleshoot to locate fault |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-01 | 2021-12-23 | 2022-03-23 | 10 |  |  | DF /G /61/DFGA-LP-1850-54 | Troubleshoot to locate fault | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059290 | Troubleshoot Q54 LNJB-1850-0054-L3-A | Troubleshoot to locate fault |  |  | 6 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2021-12-23 | 2022-03-23 | 20 |  |  | DF /G /61/DFGA-LP-1850-54 | Troubleshoot to locate fault | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059290 | Troubleshoot Q54 LNJB-1850-0054-L3-A | Troubleshoot to locate fault |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-02 | 2021-12-23 | 2022-03-23 | 30 |  |  | DF /G /61/DFGA-LP-1850-54 | Troubleshoot to locate fault | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059290 | Troubleshoot Q54 LNJB-1850-0054-L3-A | Troubleshoot to locate fault |  |  | 3 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2021-12-23 | 2022-03-23 | 40 |  |  | DF /G /61/DFGA-LP-1850-54 | Troubleshoot to locate fault | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100059290 | Troubleshoot Q54 LNJB-1850-0054-L3-A | Troubleshoot to locate fault |  |  | 0.5 | 0 | W25-W26 | 2024-07-01 | 2024-07-03 | 2024-07-03 | 2024-07-03 | 2021-12-23 | 2022-03-23 | 50 |  |  | DF /G /61/DFGA-LP-1850-54 | Troubleshoot to locate fault | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-15 | 2022-11-19 | 2023-04-03 | 10 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-16 | 2022-11-19 | 2023-04-03 | 15 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 40 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-19 | 2022-11-19 | 2023-04-03 | 20 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-22 | 2022-11-19 | 2023-04-03 | 30 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-19 | 2024-09-22 | 2022-11-19 | 2023-04-03 | 40 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 21 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2022-11-19 | 2023-04-03 | 50 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-16 | 2022-11-19 | 2023-04-03 | 55 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 36 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-18 | 2022-11-19 | 2023-04-03 | 56 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 36 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-18 | 2022-11-19 | 2023-04-03 | 57 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 24 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-15 | 2024-09-17 | 2022-11-19 | 2023-04-03 | 58 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100075985 | 78/DFB: Bolts + buffer under cabin | Site Inspector, CRANE Release |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-11-19 | 2023-04-03 | 60 |  |  | DF /B /78/DFBA-X-6102 | Site Inspector, CRANE Release | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100108174 | DFGA-FIT-390602 Calibration | Calibrate transmitter with new range |  |  | 4 | 4 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-04-01 | 2024-08-14 | 10 |  |  | DF /G /75/DFGA-FIT-390602 | Calibrate transmitter with new range | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003143 | DFA 23 Replacment of PI på A casing | L3 Safing of PI- |  |  | 3 | 0 | Order new PI | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2018-03-15 | 2018-04-04 | 10 |  |  | DF /A /10 | L3 Safing of PI- | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-INST | 2200003143 | DFA 23 Replacment of PI på A casing | L3 Safing of PI- |  |  | 2 | 0 | Order new PI | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-16 | 2018-03-15 | 2018-04-04 | 20 |  |  | DF /A /10 | L3 Safing of PI- | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003143 | DFA 23 Replacment of PI på A casing | L3 Safing of PI- |  |  | 3 | 0 | Order new PI | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2018-03-15 | 2018-04-04 | 30 |  |  | DF /A /10 | L3 Safing of PI- | Unknown
A | DFCLPSEP | WPM | MTN-MECH | PRODTECH | 2400218580 | 1Y SDV LUBE/FUNC TEST LPSEP - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2022-11-11 | 2022-12-11 | 10 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFCLPSEP | WPM | MTN-MECH | MTN-MECH | 2400218580 | 1Y SDV LUBE/FUNC TEST LPSEP - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2022-11-11 | 2022-12-11 | 20 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFCLPSEP | WPM | MTN-MECH | PRODTECH | 2400218580 | 1Y SDV LUBE/FUNC TEST LPSEP - DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-03 | 2025-01-03 | 2022-11-11 | 2022-12-11 | 30 | SECE | SECE | DF /C /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100088071 | ANOCR DFB-DFC Bridge - Paint Ladder FR#0 | DFB-DFC Bridge - Paint Ladder FR#08 |  |  | 0 | 0 | Empty | 2023-09-12 | 2023-09-15 | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2026-02-28 | 10 |  |  | DF /C /86/BRIDGE-DFB-DFC | DFB-DFC Bridge - Paint Ladder FR#08 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100088071 | ANOCR DFB-DFC Bridge - Paint Ladder FR#0 | DFB-DFC Bridge - Paint Ladder FR#08 |  |  | 4 | 4 | Empty | 2023-09-12 | 2023-09-15 | 2023-09-12 | 2023-09-12 | 2023-09-12 | 2026-02-28 | 20 |  |  | DF /C /86/BRIDGE-DFB-DFC | DFB-DFC Bridge - Paint Ladder FR#08 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100088071 | ANOCR DFB-DFC Bridge - Paint Ladder FR#0 | DFB-DFC Bridge - Paint Ladder FR#08 |  |  | 2 | 2 | Empty | 2023-09-12 | 2023-09-15 | 2023-09-12 | 2023-09-13 | 2023-09-12 | 2026-02-28 | 30 |  |  | DF /C /86/BRIDGE-DFB-DFC | DFB-DFC Bridge - Paint Ladder FR#08 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100088071 | ANOCR DFB-DFC Bridge - Paint Ladder FR#0 | DFB-DFC Bridge - Paint Ladder FR#08 |  |  | 9 | 9 | Empty | 2023-09-12 | 2023-09-15 | 2023-09-13 | 2023-09-14 | 2023-09-12 | 2026-02-28 | 40 |  |  | DF /C /86/BRIDGE-DFB-DFC | DFB-DFC Bridge - Paint Ladder FR#08 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100088071 | ANOCR DFB-DFC Bridge - Paint Ladder FR#0 | DFB-DFC Bridge - Paint Ladder FR#08 |  |  | 9 | 9 | Empty | 2023-09-12 | 2023-09-15 | 2023-09-14 | 2023-09-15 | 2023-09-12 | 2026-02-28 | 50 |  |  | DF /C /86/BRIDGE-DFB-DFC | DFB-DFC Bridge - Paint Ladder FR#08 | Unknown
4 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100088071 | ANOCR DFB-DFC Bridge - Paint Ladder FR#0 | DFB-DFC Bridge - Paint Ladder FR#08 |  |  | 2 | 2 | Empty | 2023-09-12 | 2023-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-12 | 2026-02-28 | 60 |  |  | DF /C /86/BRIDGE-DFB-DFC | DFB-DFC Bridge - Paint Ladder FR#08 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101569 | NOTICEABLE VIBRATION ON MOTOR | NOTICEABLE VIBRATION ON MOTOR |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-12-04 | 2024-04-17 | 10 |  |  | DF /G /28/DFGA-PM-5074 | NOTICEABLE VIBRATION ON MOTOR | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-22 | 2024-09-22 | 2023-05-09 | 2025-10-25 | 10 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 12 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-23 | 2024-09-25 | 2023-05-09 | 2025-10-25 | 11 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-26 | 2024-09-26 | 2023-05-09 | 2025-10-25 | 20 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-26 | 2024-09-27 | 2023-05-09 | 2025-10-25 | 30 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-27 | 2024-09-27 | 2023-05-09 | 2025-10-25 | 40 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-27 | 2024-09-27 | 2023-05-09 | 2025-10-25 | 50 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-27 | 2024-09-28 | 2023-05-09 | 2025-10-25 | 60 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-28 | 2024-09-28 | 2023-05-09 | 2025-10-25 | 70 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-28 | 2024-09-29 | 2023-05-09 | 2025-10-25 | 80 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-29 | 2024-09-29 | 2023-05-09 | 2025-10-25 | 90 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-29 | 2024-09-30 | 2023-05-09 | 2025-10-25 | 100 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-09-30 | 2024-10-01 | 2023-05-09 | 2025-10-25 | 110 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-01 | 2024-10-02 | 2023-05-09 | 2025-10-25 | 130 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-02 | 2024-10-03 | 2023-05-09 | 2025-10-25 | 140 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-03 | 2024-10-04 | 2023-05-09 | 2025-10-25 | 150 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-03 | 2024-10-04 | 2023-05-09 | 2025-10-25 | 160 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-04 | 2024-10-05 | 2023-05-09 | 2025-10-25 | 170 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 4 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-05 | 2024-10-06 | 2023-05-09 | 2025-10-25 | 180 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-06 | 2024-10-06 | 2023-05-09 | 2025-10-25 | 190 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-06 | 2024-10-06 | 2023-05-09 | 2025-10-25 | 200 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-07 | 2024-10-07 | 2023-05-09 | 2025-10-25 | 210 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-SCAF | 2100077725 | Intern læk ESDV-430001 & 430101 | Isolate ESDV-430001 & 430101 | SECE | SECE | 6 | 0 | Empty | 2024-09-22 | 2024-10-08 | 2024-10-07 | 2024-10-08 | 2023-05-09 | 2025-10-25 | 220 | SECE | SECE | DF /F /32/DFFA-ESDV-430001 | Isolate ESDV-430001 & 430101 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 2 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-03 | 2024-06-03 | 2024-04-17 | 2024-06-01 | 10 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 2 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-03 | 2024-06-04 | 2024-04-17 | 2024-06-01 | 20 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 8 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-04 | 2024-06-05 | 2024-04-17 | 2024-06-01 | 30 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 14 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-05 | 2024-06-06 | 2024-04-17 | 2024-06-01 | 40 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 18 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-06 | 2024-06-09 | 2024-04-17 | 2024-06-01 | 50 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 14 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-09 | 2024-06-10 | 2024-04-17 | 2024-06-01 | 60 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 8 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-10 | 2024-06-11 | 2024-04-17 | 2024-06-01 | 70 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 2 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-11 | 2024-06-12 | 2024-04-17 | 2024-06-01 | 80 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 2 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-12 | 2024-06-12 | 2024-04-17 | 2024-06-01 | 90 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 2 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-12 | 2024-06-13 | 2024-04-17 | 2024-06-01 | 100 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 22 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-13 | 2024-06-15 | 2024-04-17 | 2024-06-01 | 110 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100110788 | Hydrocyclon P-5001 ext leak mech seal | Erect and dismantle scaffold |  |  | 22 | 0 | Empty | 2024-06-03 | 2024-06-18 | 2024-06-15 | 2024-06-18 | 2024-04-17 | 2024-06-01 | 120 |  |  | DF /F /27/DFFA-P-5001 | Erect and dismantle scaffold | Unknown
1 | Empty | WDF | MTN-INST | MTN-INST | 2100115334 | LP Comp. ESDV-420001 SOV | FLM LP Comp. ESDV-420001 SOV | PCNFSECE | PCNFSECE | 0 | 13 | W29-W30 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-06-25 | 2024-07-10 | 10 | PCNFSECE | PCNFSECE | DF /F /32/DFFA-ESDV-420001 | FLM LP Comp. ESDV-420001 SOV | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2023-12-30 | 2020-01-19 | 2020-06-17 | 81 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 36 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2023-12-30 | 2024-01-01 | 2020-01-19 | 2020-06-17 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2024-01-01 | 2024-01-02 | 2020-01-19 | 2020-06-17 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 18 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2024-01-02 | 2024-01-02 | 2020-01-19 | 2020-06-17 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2024-01-02 | 2024-01-02 | 2020-01-19 | 2020-06-17 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 14 | 0 | Empty | 2023-12-30 | 2024-01-03 | 2024-01-02 | 2024-01-02 | 2020-01-19 | 2020-06-17 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 9 | 1 | Empty | 2023-12-30 | 2024-01-03 | 2024-01-02 | 2024-01-02 | 2020-01-19 | 2020-06-17 | 140 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100023218 | ANOCR DFB-R3007 External Corrosion | DFB - R3007 External Corrosion | PCNFAWSCSCH | PCNFAWSCSCH | 7 | 3 | Empty | 2023-12-30 | 2024-01-03 | 2024-01-02 | 2024-01-03 | 2020-01-19 | 2020-06-17 | 150 | PCNFAWSCSCH | PCNFAWSCSCH | DF /B /23/DFBA-RI-663007 | DFB - R3007 External Corrosion | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022757 | DFB 100b. hyd 5931 kommer med høj tryk | DFB 100b. hyd 5931 kommer med høj tryk |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2019-03-20 | 2019-04-29 | 10 |  |  | DF /B /07/DFBA-P-5931 | DFB 100b. hyd 5931 kommer med høj tryk | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 1 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2021-10-23 | 2022-01-21 | 10 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2021-10-23 | 2022-01-21 | 20 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-23 | 2022-01-21 | 30 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-23 | 2022-01-21 | 40 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 1 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2021-10-23 | 2022-01-21 | 50 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2021-10-23 | 2022-01-21 | 60 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
3 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100056264 | DFCM/78: axel bent on travelgear | Order new bolt |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-15 | 2021-10-23 | 2022-01-21 | 70 |  |  | DF /C /78/DFCM-X-6105 | Order new bolt | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284126 | 6M PED CRANE CHECK VENDOR-DFGA-A-6140 | Assist with oil samples from gears | AWSC | AWSC | 42 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-20 | 2024-01-04 | 2024-01-20 | 20 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | Assist with oil samples from gears | Unknown
B | NOSD | WPM | MTN-MECH | MTN-ROPE | 2400284126 | 6M PED CRANE CHECK VENDOR-DFGA-A-6140 | Assist with oil samples from gears | AWSC | AWSC | 12 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-18 | 2024-01-04 | 2024-01-20 | 30 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | Assist with oil samples from gears | Unknown
B | NOSD | WPM | MTN-MECH | MTN-CRAN | 2400284126 | 6M PED CRANE CHECK VENDOR-DFGA-A-6140 | Assist with oil samples from gears | AWSC | AWSC | 6 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2024-01-04 | 2024-01-20 | 40 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | Assist with oil samples from gears | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269624 | 6M SAND REMOVAL SYSTEM MAINT-DFFA-A-5002 | SAND REMOVAL SYSTEM INSP-DFFA-A-5002 |  |  | 6 | 0 | Empty | 2024-10-05 | 2024-10-06 | 2024-10-05 | 2024-10-06 | 2023-08-05 | 2023-08-24 | 10 |  |  | DF /F /27/DFFA-A-5002 | SAND REMOVAL SYSTEM INSP-DFFA-A-5002 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100095421 | DFF-30 Scada PT-300930 faulty | Isolate pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-09-05 | 2024-01-18 | 10 |  |  | DF /F /10/DFFA-PIT-300930 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100095421 | DFF-30 Scada PT-300930 faulty | Isolate pressure transmitter |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-09-05 | 2024-01-18 | 20 |  |  | DF /F /10/DFFA-PIT-300930 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100095421 | DFF-30 Scada PT-300930 faulty | Isolate pressure transmitter |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-09-05 | 2024-01-18 | 30 |  |  | DF /F /10/DFFA-PIT-300930 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100095421 | DFF-30 Scada PT-300930 faulty | Isolate pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-09-05 | 2024-01-18 | 40 |  |  | DF /F /10/DFFA-PIT-300930 | Isolate pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100095421 | DFF-30 Scada PT-300930 faulty | Isolate pressure transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-09-05 | 2024-01-18 | 50 |  |  | DF /F /10/DFFA-PIT-300930 | Isolate pressure transmitter | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 5 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-13 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 4 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-14 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 2 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284267 | PSV Exchange - DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | AWSC | AWSC | 0 | 0 | Empty | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-10-12 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /27/DFFA-PSV-500411 | DFFA-PSV-500411 Offshore from WS Måde | Unknown
3 | DFF-IPHP | WDF | MTN-INST | PRODTECH | 2100088907 | BDV-420008 fail on switch's ZSO/ZSC | Deisolate and Test with CCR position swi |  |  | 0.5 | 0 | W35-W36 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-22 | 2023-10-04 | 10 |  |  | DF /F /31/DFFA-BDV-420008 | Deisolate and Test with CCR position swi | Unknown
3 | DFF-IPHP | WDF | MTN-INST | MTN-INST | 2100088907 | BDV-420008 fail on switch's ZSO/ZSC | Deisolate and Test with CCR position swi |  |  | 0.5 | 0 | W35-W36 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-22 | 2023-10-04 | 20 |  |  | DF /F /31/DFFA-BDV-420008 | Deisolate and Test with CCR position swi | Unknown
3 | DFF-IPHP | WDF | MTN-INST | MTN-INST | 2100088907 | BDV-420008 fail on switch's ZSO/ZSC | Deisolate and Test with CCR position swi |  |  | 2 | 0 | W35-W36 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-22 | 2023-10-04 | 30 |  |  | DF /F /31/DFFA-BDV-420008 | Deisolate and Test with CCR position swi | Unknown
3 | DFF-IPHP | WDF | MTN-INST | MTN-INST | 2100088907 | BDV-420008 fail on switch's ZSO/ZSC | Deisolate and Test with CCR position swi |  |  | 0.5 | 0 | W35-W36 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-22 | 2023-10-04 | 40 |  |  | DF /F /31/DFFA-BDV-420008 | Deisolate and Test with CCR position swi | Unknown
3 | DFF-IPHP | WDF | MTN-INST | PRODTECH | 2100088907 | BDV-420008 fail on switch's ZSO/ZSC | Deisolate and Test with CCR position swi |  |  | 0.5 | 0 | W35-W36 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2023-05-22 | 2023-10-04 | 50 |  |  | DF /F /31/DFFA-BDV-420008 | Deisolate and Test with CCR position swi | Unknown
B | NOSD | WPM | PRODLABO | PRODLABO | 2400281070 | 3M PW SAMPLE F. NORM CONTENT DFGA-V-5081 | PW SAMPLE F. NORM CONTENT DFF,DFG,DFC |  |  | 1 | 0 | Empty | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-09-25 | 2023-10-05 | 10 |  |  | DF /G /27/DFGA-V-5081 | PW SAMPLE F. NORM CONTENT DFF,DFG,DFC | Unknown
4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100025267 | DFG/78: CON-ROPE, Repair corrosion on ca | Isolation of crane DFGA-A-6140 |  |  | 1 | 0 | Empty | 2023-04-03 | 2023-04-11 | 2023-04-03 | 2023-04-03 | 2018-06-13 | 2018-11-10 | 10 |  |  | DF /G /78/DFGA-A-6140 | Isolation of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100025267 | DFG/78: CON-ROPE, Repair corrosion on ca | Isolation of crane DFGA-A-6140 |  |  | 120 | 0 | Empty | 2023-04-03 | 2023-04-11 | 2023-04-03 | 2023-04-11 | 2018-06-13 | 2018-11-10 | 20 |  |  | DF /G /78/DFGA-A-6140 | Isolation of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-CRAN | 2100025267 | DFG/78: CON-ROPE, Repair corrosion on ca | Isolation of crane DFGA-A-6140 |  |  | 12 | 0 | Empty | 2023-04-03 | 2023-04-11 | 2023-04-03 | 2023-04-06 | 2018-06-13 | 2018-11-10 | 30 |  |  | DF /G /78/DFGA-A-6140 | Isolation of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100025267 | DFG/78: CON-ROPE, Repair corrosion on ca | Isolation of crane DFGA-A-6140 |  |  | 1 | 0 | Empty | 2023-04-03 | 2023-04-11 | 2023-04-06 | 2023-04-06 | 2018-06-13 | 2018-11-10 | 40 |  |  | DF /G /78/DFGA-A-6140 | Isolation of crane DFGA-A-6140 | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322287 | DFF-54-FYS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 5 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /54/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 97 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 98 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 103 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 199 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 400 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 402 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100046278 | DFC-PT-10087 I signalfejl | Isolate input device NON EX |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2021-03-10 | 2021-04-19 | 412 |  |  | DF /C /85/DFCM-PT-10087 | Isolate input device NON EX | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193026 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39250 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39250 |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /75/DFAA-A-39250 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39250 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235850 | 4Y 400V E-SWB MAINT DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235850 | 4Y 400V E-SWB MAINT DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235850 | 4Y 400V E-SWB MAINT DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235850 | 4Y 400V E-SWB MAINT DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A13 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200010769 | Handheld vib meas. rotating Eq Dan F R2 | Handheld vib meas. rotating Eq Dan F R2 | SCH | SCH | 0 | 0 | W26-27 IOP 27/6-4/7 | 2023-12-11 | 2023-12-21 | 2023-12-11 | 2023-12-11 | 2022-06-10 | 2022-09-08 | 10 | SCH | SCH | DF /F /9 | Handheld vib meas. rotating Eq Dan F R2 | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200010769 | Handheld vib meas. rotating Eq Dan F R2 | Handheld vib meas. rotating Eq Dan F R2 | SCH | SCH | 0 | 0 | W26-27 IOP 27/6-4/7 | 2023-12-11 | 2023-12-21 | 2023-12-11 | 2023-12-11 | 2022-06-10 | 2022-09-08 | 20 | SCH | SCH | DF /F /9 | Handheld vib meas. rotating Eq Dan F R2 | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200010769 | Handheld vib meas. rotating Eq Dan F R2 | Handheld vib meas. rotating Eq Dan F R2 | SCH | SCH | 96 | 0 | W26-27 IOP 27/6-4/7 | 2023-12-11 | 2023-12-21 | 2023-12-11 | 2023-12-21 | 2022-06-10 | 2022-09-08 | 30 | SCH | SCH | DF /F /9 | Handheld vib meas. rotating Eq Dan F R2 | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200010769 | Handheld vib meas. rotating Eq Dan F R2 | Handheld vib meas. rotating Eq Dan F R2 | SCH | SCH | 0 | 0 | W26-27 IOP 27/6-4/7 | 2023-12-11 | 2023-12-21 | 2023-12-21 | 2023-12-21 | 2022-06-10 | 2022-09-08 | 40 | SCH | SCH | DF /F /9 | Handheld vib meas. rotating Eq Dan F R2 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284251 | PSV Exchange - DFCM-PSV-57663 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /70/DFCM-PSV-57663 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284251 | PSV Exchange - DFCM-PSV-57663 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /70/DFCM-PSV-57663 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284251 | PSV Exchange - DFCM-PSV-57663 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-20 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /70/DFCM-PSV-57663 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284251 | PSV Exchange - DFCM-PSV-57663 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-21 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /70/DFCM-PSV-57663 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284251 | PSV Exchange - DFCM-PSV-57663 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-21 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /70/DFCM-PSV-57663 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284251 | PSV Exchange - DFCM-PSV-57663 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /70/DFCM-PSV-57663 | Isolation of PSV | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 0 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2021-12-14 | 2022-01-23 | 10 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 0 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2021-12-14 | 2022-01-23 | 30 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2021-12-14 | 2022-01-23 | 40 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 8 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-16 | 2021-12-14 | 2022-01-23 | 42 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 2 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-16 | 2024-09-17 | 2021-12-14 | 2022-01-23 | 44 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-17 | 2021-12-14 | 2022-01-23 | 46 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-17 | 2024-09-18 | 2021-12-14 | 2022-01-23 | 50 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 8 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-19 | 2021-12-14 | 2022-01-23 | 52 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 2 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-19 | 2021-12-14 | 2022-01-23 | 54 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-19 | 2021-12-14 | 2022-01-23 | 56 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 0 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-19 | 2021-12-14 | 2022-01-23 | 60 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-20 | 2021-12-14 | 2022-01-23 | 70 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 8 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-20 | 2024-09-21 | 2021-12-14 | 2022-01-23 | 72 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 2 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-21 | 2021-12-14 | 2022-01-23 | 74 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-22 | 2021-12-14 | 2022-01-23 | 76 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 4 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2021-12-14 | 2022-01-23 | 80 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 8 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2021-12-14 | 2022-01-23 | 82 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 2 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2021-12-14 | 2022-01-23 | 84 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059335 | Replace to correct bolt spec. on FT | Replace faulty bolts on DFAA-FT-45074 |  |  | 2 | 0 | Vendor | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2021-12-14 | 2022-01-23 | 86 |  |  | DF /A /37/DFAA-FT-45050 | Replace faulty bolts on DFAA-FT-45074 | Unknown
3 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200006799 | scaffold assits FORCE 21768 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2021-04-13 | 2021-05-23 | 10 |  |  | DF /C /28/DFC-2-DO-050-0802-B-U | Bilfinger inspection | Unknown
3 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200006799 | scaffold assits FORCE 21768 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2021-04-13 | 2021-05-23 | 20 |  |  | DF /C /28/DFC-2-DO-050-0802-B-U | Bilfinger inspection | Unknown
3 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200006799 | scaffold assits FORCE 21768 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-10 | 2021-04-13 | 2021-05-23 | 22 |  |  | DF /C /28/DFC-2-DO-050-0802-B-U | Bilfinger inspection | Unknown
3 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200006799 | scaffold assits FORCE 21768 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-10 | 2024-01-12 | 2021-04-13 | 2021-05-23 | 30 |  |  | DF /C /28/DFC-2-DO-050-0802-B-U | Bilfinger inspection | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100063032 | Replace deluge XV-035353 & HCV-0035343 | Replace HCV-035343 and deluge valve |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2022-05-05 | 2022-10-02 | 10 |  |  | DF /F /01/DFFA-XV-035353 | Replace HCV-035343 and deluge valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100063032 | Replace deluge XV-035353 & HCV-0035343 | Replace HCV-035343 and deluge valve |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-18 | 2022-05-05 | 2022-10-02 | 20 |  |  | DF /F /01/DFFA-XV-035353 | Replace HCV-035343 and deluge valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100063032 | Replace deluge XV-035353 & HCV-0035343 | Replace HCV-035343 and deluge valve |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-18 | 2022-05-05 | 2022-10-02 | 30 |  |  | DF /F /01/DFFA-XV-035353 | Replace HCV-035343 and deluge valve | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100063032 | Replace deluge XV-035353 & HCV-0035343 | Replace HCV-035343 and deluge valve |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-05-05 | 2022-10-02 | 40 |  |  | DF /F /01/DFFA-XV-035353 | Replace HCV-035343 and deluge valve | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | MTN-MECH | 2100023469 | DAN FE replace all 3 valves in gaslif | L3-Check materials | AWSCSCH | AWSCSCH | 2 | 0 | W/49116 | 2025-01-01 | 2025-01-07 | 2025-01-01 | 2025-01-02 | 2018-05-06 | 2018-05-26 | 10 | AWSCSCH | AWSCSCH | DF /E /10 | L3-Check materials | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100023469 | DAN FE replace all 3 valves in gaslif | L3-Check materials | AWSCSCH | AWSCSCH | 3 | 0 | W/49116 | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2025-01-02 | 2018-05-06 | 2018-05-26 | 20 | AWSCSCH | AWSCSCH | DF /E /10 | L3-Check materials | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | MTN-MECH | 2100023469 | DAN FE replace all 3 valves in gaslif | L3-Check materials | AWSCSCH | AWSCSCH | 12 | 0 | W/49116 | 2025-01-01 | 2025-01-07 | 2025-01-02 | 2025-01-04 | 2018-05-06 | 2018-05-26 | 30 | AWSCSCH | AWSCSCH | DF /E /10 | L3-Check materials | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | MTN-MECH | 2100023469 | DAN FE replace all 3 valves in gaslif | L3-Check materials | AWSCSCH | AWSCSCH | 12 | 0 | W/49116 | 2025-01-01 | 2025-01-07 | 2025-01-04 | 2025-01-05 | 2018-05-06 | 2018-05-26 | 40 | AWSCSCH | AWSCSCH | DF /E /10 | L3-Check materials | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | PRODTECH | 2100023469 | DAN FE replace all 3 valves in gaslif | L3-Check materials | AWSCSCH | AWSCSCH | 3 | 0 | W/49116 | 2025-01-01 | 2025-01-07 | 2025-01-05 | 2025-01-06 | 2018-05-06 | 2018-05-26 | 50 | AWSCSCH | AWSCSCH | DF /E /10 | L3-Check materials | Unknown
3 | DFX-LIFT | WDF | MTN-MECH | MTN-MECH | 2100023469 | DAN FE replace all 3 valves in gaslif | L3-Check materials | AWSCSCH | AWSCSCH | 2 | 0 | W/49116 | 2025-01-01 | 2025-01-07 | 2025-01-06 | 2025-01-07 | 2018-05-06 | 2018-05-26 | 60 | AWSCSCH | AWSCSCH | DF /E /10 | L3-Check materials | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400264132 | 1Y OPEN/CLOSE DRAIN DISPOSAL MAINT-DFA | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-10 | 2024-05-06 | 2024-05-06 | 2023-06-30 | 2023-07-30 | 10 | SCHSECE | SCHSECE | DF /A /28/DRAIN-DISPOSAL | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400264132 | 1Y OPEN/CLOSE DRAIN DISPOSAL MAINT-DFA | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 8 | 0 | W19-W20 | 2024-05-06 | 2024-05-10 | 2024-05-06 | 2024-05-08 | 2023-06-30 | 2023-07-30 | 20 | SCHSECE | SCHSECE | DF /A /28/DRAIN-DISPOSAL | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400264132 | 1Y OPEN/CLOSE DRAIN DISPOSAL MAINT-DFA | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 3 | 0 | W19-W20 | 2024-05-06 | 2024-05-10 | 2024-05-08 | 2024-05-09 | 2023-06-30 | 2023-07-30 | 30 | SCHSECE | SCHSECE | DF /A /28/DRAIN-DISPOSAL | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400264132 | 1Y OPEN/CLOSE DRAIN DISPOSAL MAINT-DFA | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 4 | 0 | W19-W20 | 2024-05-06 | 2024-05-10 | 2024-05-09 | 2024-05-10 | 2023-06-30 | 2023-07-30 | 40 | SCHSECE | SCHSECE | DF /A /28/DRAIN-DISPOSAL | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400264132 | 1Y OPEN/CLOSE DRAIN DISPOSAL MAINT-DFA | ISOLATION BY PRODUCTION | SCHSECE | SCHSECE | 2 | 0 | W19-W20 | 2024-05-06 | 2024-05-10 | 2024-05-10 | 2024-05-10 | 2023-06-30 | 2023-07-30 | 50 | SCHSECE | SCHSECE | DF /A /28/DRAIN-DISPOSAL | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235625 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-13 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-13 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235625 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-13 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-13 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235625 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-13 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-13 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235625 | 4Y 380V N-SWB MAINT-DFFA-N-1802B-13 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-13 | ISOLATION ELECTRICAL | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-ROPE | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 0 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-06-17 | 10 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-LAGG | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 5 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-03 | 2024-02-03 | 2024-02-03 | 2024-06-17 | 20 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-SCAF | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 12 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-03 | 2024-02-05 | 2024-02-03 | 2024-06-17 | 21 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-RIGG | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 6 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-05 | 2024-02-05 | 2024-02-03 | 2024-06-17 | 22 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-PIPF | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 6 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-05 | 2024-02-06 | 2024-02-03 | 2024-06-17 | 30 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | PRODTECH | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 4 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-06 | 2024-02-06 | 2024-02-03 | 2024-06-17 | 40 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-PIPF | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 24 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-06 | 2024-02-08 | 2024-02-03 | 2024-06-17 | 50 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-RIGG | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 18 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-08 | 2024-02-10 | 2024-02-03 | 2024-06-17 | 60 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-RIGG | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 18 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-10 | 2024-02-12 | 2024-02-03 | 2024-06-17 | 70 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-PIPF | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 24 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-12 | 2024-02-13 | 2024-02-03 | 2024-06-17 | 80 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-LAGG | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 10 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-13 | 2024-02-14 | 2024-02-03 | 2024-06-17 | 81 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-SCAF | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 12 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-14 | 2024-02-15 | 2024-02-03 | 2024-06-17 | 90 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | Empty | WDF | MTN-PIPF | MTN-PIPF | 2100105418 | FFSPR: 3" DPS Leaking Spool P-5076- Tee | FFS 3" DPS Leaking Spool - Tee Section | SECE | SECE | 6 | 0 | Empty | 2024-02-03 | 2024-02-16 | 2024-02-15 | 2024-02-16 | 2024-02-03 | 2024-06-17 | 100 | SECE | SECE | DF /G /28/DFG-3-DPS-050-0215-AB-T | FFS 3" DPS Leaking Spool - Tee Section | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-MECH | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-12-23 | 2024-05-06 | 10 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 2 | 2 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 30 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 4 | 6 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 33 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-PIPF | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 4 | 4 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 40 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 4 | 6 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 41 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-PIPF | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 4 | 8 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 50 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-RIGG | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 2 | 2 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 51 | PCNF | PCNF | DF /B | Rig out spool | Unknown
3 | DFB-O16 | WDF | MTN-MECH | MTN-SCAF | 2100101557 | ANOPR: New Gas Lift hook-up spool DFB16 | Rig out spool | PCNF | PCNF | 8 | 2 | Empty | 2024-07-30 | 2024-07-30 | 2023-11-17 | 2023-12-14 | 2023-12-23 | 2024-05-06 | 61 | PCNF | PCNF | DF /B | Rig out spool | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322313 | DFG-28-OD-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 3 | 2 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /G /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NE | WDF | MTN-INST | PRODTECH | 2100110798 | DFG-PIT-340621 Defective block and bleed | Inhibit transmitter and replace block |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2024-05-28 | 2024-10-10 | 10 |  |  | DF /G /27/DFGA-PIT-340621 | Inhibit transmitter and replace block | Unknown
3 | NE | WDF | MTN-INST | MTN-INST | 2100110798 | DFG-PIT-340621 Defective block and bleed | Inhibit transmitter and replace block |  |  | 5 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2024-05-28 | 2024-10-10 | 20 |  |  | DF /G /27/DFGA-PIT-340621 | Inhibit transmitter and replace block | Unknown
3 | NE | WDF | MTN-INST | MTN-INST | 2100110798 | DFG-PIT-340621 Defective block and bleed | Inhibit transmitter and replace block |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-05-28 | 2024-10-10 | 30 |  |  | DF /G /27/DFGA-PIT-340621 | Inhibit transmitter and replace block | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235840 | 4Y 400V E-SWB MAINT DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235840 | 4Y 400V E-SWB MAINT DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | AWSC | AWSC | 24 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235840 | 4Y 400V E-SWB MAINT DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235840 | 4Y 400V E-SWB MAINT DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A02 | 400V E-SWB MAINT DFGA-N-1843-A02 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339093 | DFC_1Y_35000 INT STRUCT INSP - GVI | DFC_1Y_35000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /86/EL_35000 (L3 IP-COMP DECK) | DFC_1Y_35000 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 0 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-18 | 2021-10-19 | 2021-11-18 | 1 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 1 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-18 | 2021-10-19 | 2021-11-18 | 9 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 28 | 22 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-25 | 2021-10-19 | 2021-11-18 | 10 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-INST | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 12 | 16 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-21 | 2021-10-19 | 2021-11-18 | 12 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 1 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2021-10-19 | 2021-11-18 | 14 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-INST | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 0 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2021-10-19 | 2021-11-18 | 20 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-INST | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 0 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2021-10-19 | 2021-11-18 | 290 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-INST | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 0 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-18 | 2021-10-19 | 2021-11-18 | 300 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 0 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-18 | 2021-10-19 | 2021-11-18 | 310 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400151196 | 1Y POT WATER TANK, DFC-V-1010/20 | GENERAL INFO VEDLIGEHOLD MED ASSU | SECE | SECE | 0 | 0 | 23-W51-52 | 2023-12-18 | 2023-12-25 | 2023-12-18 | 2023-12-18 | 2021-10-19 | 2021-11-18 | 320 | SECE | SECE | DF /C /85/DFCC-V-1010 | GENERAL INFO VEDLIGEHOLD MED ASSU | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 6 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-06 | 2024-08-07 | 2024-06-06 | 2024-10-19 | 10 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 1 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2024-06-06 | 2024-10-19 | 20 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 2 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2024-06-06 | 2024-10-19 | 30 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 2 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-08 | 2024-08-08 | 2024-06-06 | 2024-10-19 | 40 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 4 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-08 | 2024-08-09 | 2024-06-06 | 2024-10-19 | 50 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 4 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-09 | 2024-08-09 | 2024-06-06 | 2024-10-19 | 60 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 2 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-09 | 2024-08-10 | 2024-06-06 | 2024-10-19 | 70 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 2 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-09 | 2024-08-10 | 2024-06-06 | 2024-10-19 | 80 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 1 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-06 | 2024-08-06 | 2024-06-06 | 2024-10-19 | 90 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100111178 | Replace electrical motor DFC LB3 hoist | Setup rigging equipment LB3 hoist motor | SECE | SECE | 2 | 0 | Empty | 2024-08-06 | 2024-08-10 | 2024-08-10 | 2024-08-10 | 2024-06-06 | 2024-10-19 | 100 | SECE | SECE | DF /C /02/DFCI-X-0703 | Setup rigging equipment LB3 hoist motor | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ROPE | 2100024825 | Fastening of HV cables DFF lev2 north. O | L3 fastening cable | AWSC | AWSC | 8 | 0 | W35-W36 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2019-08-06 | 2020-07-31 | 10 | AWSC | AWSC | DF /G /6 | L3 fastening cable | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 24 | 8 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-16 | 2024-07-19 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 5 | 4.5 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-16 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 4 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-17 | 2024-07-17 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 4 | 2 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-17 | 2024-07-18 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 12 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-14 | 2024-09-15 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-13 | 2024-09-14 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 5 | 8 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-14 | 2024-09-15 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-13 | 2024-09-14 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-13 | 2024-09-14 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-13 | 2024-09-14 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 10 | 0 | Empty | 2024-07-16 | 2024-09-15 | 2024-09-12 | 2024-09-14 | 2024-10-30 | 2024-12-31 | 130 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284281 | PSV Calibration - DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | PCNFAWSC | PCNFAWSC | 0 | 2 | Empty | 2024-07-16 | 2024-09-15 | 2024-07-16 | 2024-07-16 | 2024-10-30 | 2024-12-31 | 140 | PCNFAWSC | PCNFAWSC | DF /F /51/DFFA-PSV-354169 | DFFA-PSV-354169 Offshore from WS Måde | Unknown
A | KRA-OIL | WPM | MTN-MECH | PRODTECH | 2400325537 | 1Y ESDV LEAK TEST - DFFA-ESDV-290500 | ESDV LEAK TEST - DFFA-ESDV-290500 | AWSCSECE | AWSCSECE | 6 | 0 | Empty | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-05-11 | 2024-05-10 | 2024-06-09 | 10 | AWSCSECE | AWSCSECE | DF /F /31/DFFA-ESDV-290500 | ESDV LEAK TEST - DFFA-ESDV-290500 | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009354 | sandblasting assists FORCE 8757 | SANDBLASTNING |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /A /12/DFA-6-PT-033-0612-C2-U | SANDBLASTNING | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009354 | sandblasting assists FORCE 8757 | SANDBLASTNING |  |  | 20 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-08 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 12 |  |  | DF /A /12/DFA-6-PT-033-0612-C2-U | SANDBLASTNING | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009354 | sandblasting assists FORCE 8757 | SANDBLASTNING |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 18 |  |  | DF /A /12/DFA-6-PT-033-0612-C2-U | SANDBLASTNING | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-PAIN | 2200009354 | sandblasting assists FORCE 8757 | SANDBLASTNING |  |  | 37 | 0 | Empty | 2024-01-08 | 2024-01-11 | 2024-01-09 | 2024-01-11 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /A /12/DFA-6-PT-033-0612-C2-U | SANDBLASTNING | Unknown
1 | DFF-LP-1 | WDF | MTN-INST | MTN-INST | 2100105290 | DFF LP C-4201 stage 1 sporious operation | Change SOV-420580/420581 |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-01-12 | 2024-01-27 | 10 |  |  | DF /F /31/DFFA-C-4201 | Change SOV-420580/420581 | Unknown
1 | DFF-LP-1 | WDF | MTN-INST | MTN-INST | 2100105290 | DFF LP C-4201 stage 1 sporious operation | Change SOV-420580/420581 |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-01-12 | 2024-01-27 | 20 |  |  | DF /F /31/DFFA-C-4201 | Change SOV-420580/420581 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087403 | BATTERY REPLACEMENT EMERGENCY LIGHT. | Isolate and prove dead. |  |  | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-04-27 | 2023-09-09 | 10 |  |  | DF /G /05/DFGA-LP-1852 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087403 | BATTERY REPLACEMENT EMERGENCY LIGHT. | Isolate and prove dead. |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-04-27 | 2023-09-09 | 20 |  |  | DF /G /05/DFGA-LP-1852 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087403 | BATTERY REPLACEMENT EMERGENCY LIGHT. | Isolate and prove dead. |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-04-27 | 2023-09-09 | 30 |  |  | DF /G /05/DFGA-LP-1852 | Isolate and prove dead. | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100087403 | BATTERY REPLACEMENT EMERGENCY LIGHT. | Isolate and prove dead. |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-04-27 | 2023-09-09 | 40 |  |  | DF /G /05/DFGA-LP-1852 | Isolate and prove dead. | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100087753 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  | 2 | 0 | Empty | 2024-07-16 | 2024-08-21 | 2024-07-16 | 2024-07-16 | 2023-09-16 | 2026-03-04 | 10 |  |  | DF /F /78/DFFA-A-6101 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087753 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  | 100 | 0 | Empty | 2024-07-16 | 2024-08-21 | 2024-07-16 | 2024-07-29 | 2023-09-16 | 2026-03-04 | 20 |  |  | DF /F /78/DFFA-A-6101 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100087753 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  | 120 | 0 | Empty | 2024-07-16 | 2024-08-21 | 2024-07-29 | 2024-08-08 | 2023-09-16 | 2026-03-04 | 30 |  |  | DF /F /78/DFFA-A-6101 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-RIGG | 2100087753 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  | 70 | 0 | Empty | 2024-07-16 | 2024-08-21 | 2024-08-08 | 2024-08-17 | 2023-09-16 | 2026-03-04 | 40 |  |  | DF /F /78/DFFA-A-6101 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100087753 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  | 16 | 0 | Empty | 2024-07-16 | 2024-08-21 | 2024-08-17 | 2024-08-19 | 2023-09-16 | 2026-03-04 | 50 |  |  | DF /F /78/DFFA-A-6101 | Isolate and de-isolate | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100087753 | DFFE/78 Wire sheave replacement | Isolate and de-isolate |  |  | 16 | 0 | Empty | 2024-07-16 | 2024-08-21 | 2024-08-19 | 2024-08-21 | 2023-09-16 | 2026-03-04 | 60 |  |  | DF /F /78/DFFA-A-6101 | Isolate and de-isolate | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075272 | DFF level 2 syd test manifold slot 26. | Change tube/fittings causing leak |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-11-10 | 2023-03-25 | 10 |  |  | DF /F /10/DFFA-XCV-301126 | Change tube/fittings causing leak | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100075272 | DFF level 2 syd test manifold slot 26. | Change tube/fittings causing leak |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-11-10 | 2023-03-25 | 20 |  |  | DF /F /10/DFFA-XCV-301126 | Change tube/fittings causing leak | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100075272 | DFF level 2 syd test manifold slot 26. | Change tube/fittings causing leak |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-11-10 | 2023-03-25 | 30 |  |  | DF /F /10/DFFA-XCV-301126 | Change tube/fittings causing leak | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 0 | 0 | Empty | 2024-10-05 | 2024-11-02 | 2024-10-05 | 2024-10-05 | 2020-11-22 | 2021-01-01 | 10 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-LAGG | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 12 | 12 | Empty | 2024-10-05 | 2024-11-02 | 2023-05-05 | 2023-11-04 | 2020-11-22 | 2021-01-01 | 15 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 4 | 0 | Empty | 2024-10-05 | 2024-11-02 | 2024-10-05 | 2024-10-05 | 2020-11-22 | 2021-01-01 | 20 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 12 | 0 | Empty | 2024-10-05 | 2024-11-02 | 2024-10-05 | 2024-10-05 | 2020-11-22 | 2021-01-01 | 30 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-INST | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 24 | 0 | Empty | 2024-10-05 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2020-11-22 | 2021-01-01 | 40 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-LAGG | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 12 | 20 | Empty | 2024-10-05 | 2024-11-02 | 2023-05-07 | 2023-11-04 | 2020-11-22 | 2021-01-01 | 45 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 4 | 0 | Empty | 2024-10-05 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2020-11-22 | 2021-01-01 | 50 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | DFFHPSEP | WDF | MTN-MECH | MTN-ROPE | 2100040807 | Water clarifier quill blocked DFF | Water clarifier quill blocked DFF | PCNF | PCNF | 20 | 14 | Empty | 2024-10-05 | 2024-11-02 | 2024-10-05 | 2024-10-09 | 2020-11-22 | 2021-01-01 | 60 | PCNF | PCNF | DF /F /75/DFFA-P-3905 | Water clarifier quill blocked DFF | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057921 | Change Socketoutlet DFFA-SO-0431A | Prove circuit is dead |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-23 | 2022-02-21 | 10 |  |  | DF /F /61/DFFA-N-1803 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057921 | Change Socketoutlet DFFA-SO-0431A | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-23 | 2022-02-21 | 20 |  |  | DF /F /61/DFFA-N-1803 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057921 | Change Socketoutlet DFFA-SO-0431A | Prove circuit is dead |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-11-23 | 2022-02-21 | 30 |  |  | DF /F /61/DFFA-N-1803 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057921 | Change Socketoutlet DFFA-SO-0431A | Prove circuit is dead |  |  | 0.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-11-23 | 2022-02-21 | 40 |  |  | DF /F /61/DFFA-N-1803 | Prove circuit is dead | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100057921 | Change Socketoutlet DFFA-SO-0431A | Prove circuit is dead |  |  | 0 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-11-23 | 2022-02-21 | 50 |  |  | DF /F /61/DFFA-N-1803 | Prove circuit is dead | Unknown
3 | DFF-3520 | WDF | MTN-TURB | MTN-TURB | 2100045551 | LM-1600 Starter hose FX-308 replacement | New hose ordered | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 11 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-03-03 | 2021-06-01 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PT-3520 | New hose ordered | Unknown
3 | DFF-3520 | WDF | MTN-TURB | MTN-TURB | 2100045551 | LM-1600 Starter hose FX-308 replacement | New hose ordered | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-03-03 | 2021-06-01 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PT-3520 | New hose ordered | Unknown
3 | DFF-3520 | WDF | MTN-TURB | MTN-TURB | 2100045551 | LM-1600 Starter hose FX-308 replacement | New hose ordered | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2021-03-03 | 2021-06-01 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /54/DFFA-PT-3520 | New hose ordered | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235672 | 4Y 380V N-SWB MAINT-DFCI-N-1822-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1822-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235672 | 4Y 380V N-SWB MAINT-DFCI-N-1822-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 7 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1822-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235672 | 4Y 380V N-SWB MAINT-DFCI-N-1822-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1822-1A01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235672 | 4Y 380V N-SWB MAINT-DFCI-N-1822-1 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1822-1A01 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322275 | DFE-54-FY-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /54/P-G | PIPING INSPECTION AND REPORTING | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-18 | 2024-07-18 | 2024-11-30 | 10 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2024-07-18 | 2024-11-30 | 20 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-19 | 2024-07-18 | 2024-11-30 | 30 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2024-07-18 | 2024-11-30 | 40 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-MECH | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 9 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-20 | 2024-07-18 | 2024-11-30 | 50 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2024-07-18 | 2024-11-30 | 60 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 1 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2024-07-18 | 2024-11-30 | 70 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100113952 | 78/DFC hyd actuator and minor rep | Replace actuator |  |  | 0 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-18 | 2024-07-18 | 2024-11-30 | 80 |  |  | DF /C /78/DFCI-X-6101 | Replace actuator | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015380 | Replace LB3 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 10 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015380 | Replace LB3 coolant with GlysantinG30 | Isolate lifeboat |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 20 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat | Unknown
3 | NOSD | WGN | MTN-MECH | VEN-MECH | 2200015380 | Replace LB3 coolant with GlysantinG30 | Isolate lifeboat |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2023-10-01 | 2024-02-13 | 30 |  |  | DF /C /02/DFCI-X-0703 | Isolate lifeboat | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-15 | 2024-07-15 | 2021-12-31 | 2022-08-28 | 10 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-SCAF | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 40 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-16 | 2024-07-19 | 2021-12-31 | 2022-08-28 | 20 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-19 | 2024-07-20 | 2021-12-31 | 2022-08-28 | 30 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 40 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-20 | 2024-07-23 | 2021-12-31 | 2022-08-28 | 40 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 45 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-20 | 2024-07-24 | 2021-12-31 | 2022-08-28 | 50 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 24 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-23 | 2024-07-24 | 2021-12-31 | 2022-08-28 | 60 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100055692 | DFG/78: Replace AH&MH wire rope pulleys | Isolate/de-isolate of crane DFGA-A-6140 |  |  | 24 | 0 | W29-W30 | 2024-07-15 | 2024-07-26 | 2024-07-23 | 2024-07-26 | 2021-12-31 | 2022-08-28 | 70 |  |  | DF /G /78/DFGA-A-6140 | Isolate/de-isolate of crane DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | PRODTECH | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 2 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-08-21 | 2024-08-21 | 2024-06-20 | 2024-07-20 | 10 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 72 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-08-21 | 2024-08-30 | 2024-06-20 | 2024-07-20 | 20 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 12 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-08-30 | 2024-09-02 | 2024-06-20 | 2024-07-20 | 30 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-TELE | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 4 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-09-02 | 2024-09-03 | 2024-06-20 | 2024-07-20 | 50 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | PRODTECH | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 2 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-09-03 | 2024-09-03 | 2024-06-20 | 2024-07-20 | 60 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-ELEC | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 24 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-09-04 | 2024-09-09 | 2024-06-20 | 2024-07-20 | 70 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-ROPE | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 12 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-09-10 | 2024-09-12 | 2024-06-20 | 2024-07-20 | 80 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 24 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-09-13 | 2024-09-15 | 2024-06-20 | 2024-07-20 | 90 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
A | NOSD | WPM | MTN-CRAN | MTN-RIGG | 2400316037 | 1Y PED CRANE CHECK VENDOR-DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | AWSC | AWSC | 20 | 0 | Empty | 2024-08-21 | 2024-09-18 | 2024-09-16 | 2024-09-18 | 2024-06-20 | 2024-07-20 | 100 | AWSC | AWSC | DF /G /78/DFGA-A-6140 | TELECOMMUNICATION CHECK-DFGA-A-6140 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 10 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 20 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 30 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 40 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 50 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 60 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 70 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 80 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 90 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 100 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 110 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 120 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 130 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 140 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 150 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 160 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 170 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 180 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 190 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 200 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 210 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 220 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 230 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 240 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 250 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 260 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 270 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 280 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 290 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 300 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 310 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 320 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 330 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 340 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 350 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 360 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 370 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 380 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 390 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 400 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 410 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 420 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 430 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 440 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 450 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200009862 | 2022 DAN PVI materiels | IR-Heater (Altrad) Break-in 1982 |  |  | 0 | 0 | Empty | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-03-11 | 2022-06-09 | 460 |  |  | DF /F /11/DFFA-V-3403 | IR-Heater (Altrad) Break-in 1982 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 0 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-04-19 | 2024-04-19 | 2022-01-12 | 2022-09-09 | 10 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | VEN-MECH | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 0 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-04-19 | 2024-04-19 | 2022-01-12 | 2022-09-09 | 20 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 75 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-04-19 | 2024-04-28 | 2022-01-12 | 2022-09-09 | 30 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 0 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-04-28 | 2024-04-28 | 2022-01-12 | 2022-09-09 | 40 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 200 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-04-28 | 2024-05-05 | 2022-01-12 | 2022-09-09 | 50 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | PRODTECH | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 0 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-05-05 | 2024-05-05 | 2022-01-12 | 2022-09-09 | 60 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 0 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-05-05 | 2024-05-05 | 2022-01-12 | 2022-09-09 | 70 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100055731 | FFSPR Utility & Instrument Air Batch-03 | DFC Level 3 failed utility air line |  |  | 25 | 0 | Empty | 2024-04-19 | 2024-05-08 | 2024-05-05 | 2024-05-08 | 2022-01-12 | 2022-09-09 | 80 |  |  | DF /C /07/DFC-1-AU-054-0118-A1-F | DFC Level 3 failed utility air line | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344036 | 1Y PIG RECEIVER MAINT-DFFA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-24 | 2024-08-25 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-09-23 | 10 | SECE | SECE | DF /F /34/DFFA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344036 | 1Y PIG RECEIVER MAINT-DFFA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | W33-W34 | 2024-08-24 | 2024-08-25 | 2024-08-24 | 2024-08-24 | 2024-08-24 | 2024-09-23 | 20 | SECE | SECE | DF /F /34/DFFA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344036 | 1Y PIG RECEIVER MAINT-DFFA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 1.5 | 0 | W33-W34 | 2024-08-24 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-24 | 2024-09-23 | 30 | SECE | SECE | DF /F /34/DFFA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344036 | 1Y PIG RECEIVER MAINT-DFFA-EP-3803 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W33-W34 | 2024-08-24 | 2024-08-25 | 2024-08-25 | 2024-08-25 | 2024-08-24 | 2024-09-23 | 40 | SECE | SECE | DF /F /34/DFFA-EP-3803 | ISOLATION BY PRODUCTION | Unknown
3 | DAB-OIL | WDF | MTN-MECH | PRODTECH | 2100056176 | FFS Corroded flange sealing face on 1" v | Remove old HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-16 | 2021-07-23 | 2021-09-01 | 10 |  |  | DF /F /23/DFF-16-PHS-038-7002-FC-U | Remove old HCV | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100056176 | FFS Corroded flange sealing face on 1" v | Remove old HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-16 | 2021-07-23 | 2021-09-01 | 20 |  |  | DF /F /23/DFF-16-PHS-038-7002-FC-U | Remove old HCV | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100056176 | FFS Corroded flange sealing face on 1" v | Remove old HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-16 | 2024-09-18 | 2021-07-23 | 2021-09-01 | 30 |  |  | DF /F /23/DFF-16-PHS-038-7002-FC-U | Remove old HCV | Unknown
3 | DAB-OIL | WDF | MTN-MECH | MTN-MECH | 2100056176 | FFS Corroded flange sealing face on 1" v | Remove old HCV |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2021-07-23 | 2021-09-01 | 40 |  |  | DF /F /23/DFF-16-PHS-038-7002-FC-U | Remove old HCV | Unknown
3 | DAB-OIL | WDF | MTN-MECH | PRODTECH | 2100056176 | FFS Corroded flange sealing face on 1" v | Remove old HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2021-07-23 | 2021-09-01 | 50 |  |  | DF /F /23/DFF-16-PHS-038-7002-FC-U | Remove old HCV | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400258779 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 |  |  | 12 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2023-04-26 | 2023-06-01 | 10 |  |  | DF /F /75/DFFA-A-39704 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235688 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF06-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235688 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 27 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-28 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF06-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235688 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-29 | 2024-10-01 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF06-CA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235688 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF06 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF06-CA001 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100028058 | DFFA-FIL-311703 has to be changeout | L3 Isolate DFFA-FIL-311703 |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-12 | 2024-08-13 | 2019-09-29 | 2019-11-08 | 10 |  |  | DF /F /07/DFFA-FIL-311703 | L3 Isolate DFFA-FIL-311703 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100028058 | DFFA-FIL-311703 has to be changeout | L3 Isolate DFFA-FIL-311703 |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-13 | 2019-09-29 | 2019-11-08 | 20 |  |  | DF /F /07/DFFA-FIL-311703 | L3 Isolate DFFA-FIL-311703 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100028058 | DFFA-FIL-311703 has to be changeout | L3 Isolate DFFA-FIL-311703 |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-14 | 2024-08-13 | 2024-08-14 | 2019-09-29 | 2019-11-08 | 30 |  |  | DF /F /07/DFFA-FIL-311703 | L3 Isolate DFFA-FIL-311703 | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400321282 | 3M ANODE REPLACEMENT - DFGA-A-1202/3 | ANODE REPLACEMENT - DFGA-A-1202/3 |  |  | 8 | 12 | W21-W22 | 2024-05-20 | 2024-05-21 | 2024-05-20 | 2024-05-21 | 2024-04-26 | 2024-05-11 | 10 |  |  | DF /G /09/DFGA-A-1202 | ANODE REPLACEMENT - DFGA-A-1202/3 | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-12 | 2026-05-14 | 2019-02-21 | 2019-03-13 | 4 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 8.699999999999999289457264236 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-14 | 2026-05-15 | 2019-02-21 | 2019-03-13 | 5 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 8 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-15 | 2026-05-16 | 2019-02-21 | 2019-03-13 | 10 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 16.800000000000000710542735753 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-16 | 2026-05-17 | 2019-02-21 | 2019-03-13 | 20 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 3 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-17 | 2026-05-18 | 2019-02-21 | 2019-03-13 | 30 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 10.699999999999999289457264235 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-18 | 2026-05-19 | 2019-02-21 | 2019-03-13 | 40 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-19 | 2026-05-19 | 2019-02-21 | 2019-03-13 | 50 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | QAQCELEC | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 1 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-19 | 2026-05-19 | 2019-02-21 | 2019-03-13 | 60 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 3 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-19 | 2026-05-20 | 2019-02-21 | 2019-03-13 | 70 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 0.6999999999999999555910790147 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-20 | 2026-05-20 | 2019-02-21 | 2019-03-13 | 80 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-20 | 2026-05-21 | 2019-02-21 | 2019-03-13 | 90 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 8 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-21 | 2026-05-22 | 2019-02-21 | 2019-03-13 | 160 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 16.800000000000000710542735753 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-22 | 2026-05-24 | 2019-02-21 | 2019-03-13 | 170 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 3 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-24 | 2026-05-24 | 2019-02-21 | 2019-03-13 | 180 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 10.699999999999999289457264235 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-24 | 2026-05-25 | 2019-02-21 | 2019-03-13 | 190 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-25 | 2026-05-25 | 2019-02-21 | 2019-03-13 | 210 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | QAQCELEC | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 1 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-25 | 2026-05-25 | 2019-02-21 | 2019-03-13 | 220 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 3 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-25 | 2026-05-26 | 2019-02-21 | 2019-03-13 | 230 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 0.6999999999999999555910790147 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-26 | 2026-05-26 | 2019-02-21 | 2019-03-13 | 240 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-26 | 2026-05-27 | 2019-02-21 | 2019-03-13 | 250 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 8 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-27 | 2026-05-28 | 2019-02-21 | 2019-03-13 | 320 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 11.400000000000000355271367876 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-28 | 2026-05-29 | 2019-02-21 | 2019-03-13 | 330 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 3 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-29 | 2026-05-30 | 2019-02-21 | 2019-03-13 | 340 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 10.699999999999999289457264235 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-30 | 2026-05-30 | 2019-02-21 | 2019-03-13 | 350 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | QAQCELEC | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 1 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-30 | 2026-05-30 | 2019-02-21 | 2019-03-13 | 360 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 3 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-30 | 2026-05-31 | 2019-02-21 | 2019-03-13 | 370 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 0.6999999999999999555910790147 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-31 | 2026-05-31 | 2019-02-21 | 2019-03-13 | 380 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023925 | Utætte flanger/ventiler | Permit, SCAFF | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-06-01 | 2026-05-31 | 2026-06-01 | 2019-02-21 | 2019-03-13 | 390 | AWSC | AWSC | DF /G /01 | Permit, SCAFF | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ACCO | 2400346580 | 6M GALLEY VENDOR MAINT DFC | GALLEY VENDOR MAINT DFC | AWSC | AWSC | 24 | 0 | Empty | 2024-09-12 | 2024-09-14 | 2024-09-12 | 2024-09-14 | 2024-09-12 | 2024-10-01 | 10 | AWSC | AWSC | DF /C /82/CATERING-EQUIPMENT | GALLEY VENDOR MAINT DFC | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055442 | defekt beskyttelseshætte P-3988 | Isolate P-3988 |  |  | 8 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-26 | 2024-08-28 | 2021-12-07 | 2022-05-06 | 20 |  |  | DF /G /75/DFGA-A-3988 | Isolate P-3988 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100055442 | defekt beskyttelseshætte P-3988 | Isolate P-3988 |  |  | 20 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-09-02 | 2021-12-07 | 2022-05-06 | 30 |  |  | DF /G /75/DFGA-A-3988 | Isolate P-3988 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055442 | defekt beskyttelseshætte P-3988 | Isolate P-3988 |  |  | 10 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-08-28 | 2024-08-30 | 2021-12-07 | 2022-05-06 | 40 |  |  | DF /G /75/DFGA-A-3988 | Isolate P-3988 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055442 | defekt beskyttelseshætte P-3988 | Isolate P-3988 |  |  | 4 | 0 | W35-W36 | 2024-08-26 | 2024-09-03 | 2024-09-02 | 2024-09-03 | 2021-12-07 | 2022-05-06 | 50 |  |  | DF /G /75/DFGA-A-3988 | Isolate P-3988 | Unknown
3 | NOSD | WGN | MTN-PAIN | WELLSUPV | 2200005890 | DFA, paint beams lifting structure Manif | DFA, paint beams lifting structure Manif | PCNF | PCNF | 0 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2021-01-09 | 2021-02-28 | 2020-12-24 | 2021-03-24 | 10 | PCNF | PCNF | DF /A /86 | DFA, paint beams lifting structure Manif | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-SCAF | 2200005890 | DFA, paint beams lifting structure Manif | DFA, paint beams lifting structure Manif | PCNF | PCNF | 66 | 47.5 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-13 | 2023-02-18 | 2020-12-24 | 2021-03-24 | 20 | PCNF | PCNF | DF /A /86 | DFA, paint beams lifting structure Manif | Unknown
3 | NOSD | WGN | MTN-PAIN | MTN-PAIN | 2200005890 | DFA, paint beams lifting structure Manif | DFA, paint beams lifting structure Manif | PCNF | PCNF | 79 | 60.5 | Empty | 2023-02-13 | 2023-02-18 | 2020-12-26 | 2021-03-22 | 2020-12-24 | 2021-03-24 | 30 | PCNF | PCNF | DF /A /86 | DFA, paint beams lifting structure Manif | Unknown
3 | NOSD | WGN | MTN-PAIN | VEN-ELEC | 2200005890 | DFA, paint beams lifting structure Manif | DFA, paint beams lifting structure Manif | PCNF | PCNF | 6 | 0 | Empty | 2023-02-13 | 2023-02-18 | 2023-02-13 | 2023-02-13 | 2020-12-24 | 2021-03-24 | 40 | PCNF | PCNF | DF /A /86 | DFA, paint beams lifting structure Manif | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322258 | DFC-23-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 12 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /23/P-G | PIPING INSPECTION AND REPORTING | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269308 | 6M VISUAL INSPECT OF ESDV (DHDHPGAS) | ESDV VISUAL INSPECTION | SCH | SCH | 1 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-08-03 | 2023-08-19 | 10 | SCH | SCH | DF /F /34/DFFA-ESDV-380304 | ESDV VISUAL INSPECTION | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012956 | Cleaning of open drain | PO Ocean Team |  |  | 336 | 0 | Empty | 2024-09-22 | 2024-11-02 | 2024-09-22 | 2024-11-02 | 2023-01-05 | 2023-02-19 | 10 |  |  | DF /C /28 | PO Ocean Team | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012956 | Cleaning of open drain | PO Ocean Team |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2023-01-05 | 2023-02-19 | 20 |  |  | DF /C /28 | PO Ocean Team | Unknown
2 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200012956 | Cleaning of open drain | PO Ocean Team |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-11-02 | 2024-11-02 | 2024-11-02 | 2023-01-05 | 2023-02-19 | 30 |  |  | DF /C /28 | PO Ocean Team | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024945 | Change gauge and repair hydraulic l | L3 Deisolate hydraulics |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2020-02-06 | 2022-01-26 | 10 |  |  | DF /F /10/DFFA-ESDV-330005 | L3 Deisolate hydraulics | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024945 | Change gauge and repair hydraulic l | L3 Deisolate hydraulics |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2020-02-06 | 2022-01-26 | 20 |  |  | DF /F /10/DFFA-ESDV-330005 | L3 Deisolate hydraulics | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024945 | Change gauge and repair hydraulic l | L3 Deisolate hydraulics |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2020-02-06 | 2022-01-26 | 30 |  |  | DF /F /10/DFFA-ESDV-330005 | L3 Deisolate hydraulics | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024945 | Change gauge and repair hydraulic l | L3 Deisolate hydraulics |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2020-02-06 | 2022-01-26 | 40 |  |  | DF /F /10/DFFA-ESDV-330005 | L3 Deisolate hydraulics | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100024945 | Change gauge and repair hydraulic l | L3 Deisolate hydraulics |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2020-02-06 | 2022-01-26 | 50 |  |  | DF /F /10/DFFA-ESDV-330005 | L3 Deisolate hydraulics | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024945 | Change gauge and repair hydraulic l | L3 Deisolate hydraulics |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2020-02-06 | 2022-01-26 | 60 |  |  | DF /F /10/DFFA-ESDV-330005 | L3 Deisolate hydraulics | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TURB | 2100078731 | Ordre new manifold block PIT-440022 | Control in MANUAL mode |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-11-30 | 2022-12-15 | 10 |  |  | DF /G /31/DFGA-PIT-440022 | Control in MANUAL mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100078731 | Ordre new manifold block PIT-440022 | Control in MANUAL mode |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-11-30 | 2022-12-15 | 20 |  |  | DF /G /31/DFGA-PIT-440022 | Control in MANUAL mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100078731 | Ordre new manifold block PIT-440022 | Control in MANUAL mode |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-11-30 | 2022-12-15 | 30 |  |  | DF /G /31/DFGA-PIT-440022 | Control in MANUAL mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100078731 | Ordre new manifold block PIT-440022 | Control in MANUAL mode |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-11-30 | 2022-12-15 | 40 |  |  | DF /G /31/DFGA-PIT-440022 | Control in MANUAL mode | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TURB | 2100078731 | Ordre new manifold block PIT-440022 | Control in MANUAL mode |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-11-30 | 2022-12-15 | 50 |  |  | DF /G /31/DFGA-PIT-440022 | Control in MANUAL mode | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004287 | DK40 - REPLACED BY 2300008268 | Increase of PO 4300029290 |  |  | 0 | 0 | Empty | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2025-11-07 | 10 |  |  | DF /C /84 | Increase of PO 4300029290 | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004287 | DK40 - REPLACED BY 2300008268 | Increase of PO 4300029290 |  |  | 0 | 0 | Empty | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2025-11-07 | 20 |  |  | DF /C /84 | Increase of PO 4300029290 | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004287 | DK40 - REPLACED BY 2300008268 | Increase of PO 4300029290 |  |  | 0 | 0 | Empty | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2023-05-22 | 2025-11-07 | 30 |  |  | DF /C /84 | Increase of PO 4300029290 | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 13 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2020-09-03 | 2020-09-08 | 2018-12-28 | 2019-03-28 | 10 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2018-12-28 | 2019-03-28 | 20 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 52.29999999999999715782905694 | 53.5 | Empty | 2026-01-01 | 2026-01-02 | 2020-09-05 | 2020-09-08 | 2018-12-28 | 2019-03-28 | 30 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 17.399999999999998578914528472 | 3 | Empty | 2026-01-01 | 2026-01-02 | 2020-08-29 | 2020-09-06 | 2018-12-28 | 2019-03-28 | 31 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 1 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-01 | 2018-12-28 | 2019-03-28 | 40 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 17.399999999999998578914528472 | 9 | Empty | 2026-01-01 | 2026-01-02 | 2021-01-13 | 2024-07-23 | 2018-12-28 | 2019-03-28 | 41 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 34.799999999999997157829056945 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2018-12-28 | 2019-03-28 | 50 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003031 | Scaff / Iso assists FORCE 14240 | L3 Create permit. | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-02 | 2026-01-02 | 2018-12-28 | 2019-03-28 | 60 | PCNF | PCNF | DF /C /28/DFC-3-DO-050-0315-B-F | L3 Create permit. | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100110897 | Gaslækage fra BDV-34057 | Isolate DFCI-BDV-34057 | SECE | SECE | 3 | 0 | Empty | 2024-06-30 | 2024-07-03 | 2024-06-30 | 2024-06-30 | 2024-04-18 | 2024-06-02 | 10 | SECE | SECE | DF /C /20/DFCI-BDV-34057 | Isolate DFCI-BDV-34057 | Unknown
2 | NE | WDF | MTN-MECH | MTN-INST | 2100110897 | Gaslækage fra BDV-34057 | Isolate DFCI-BDV-34057 | SECE | SECE | 1 | 0 | Empty | 2024-06-30 | 2024-07-03 | 2024-06-30 | 2024-07-01 | 2024-04-18 | 2024-06-02 | 20 | SECE | SECE | DF /C /20/DFCI-BDV-34057 | Isolate DFCI-BDV-34057 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100110897 | Gaslækage fra BDV-34057 | Isolate DFCI-BDV-34057 | SECE | SECE | 5 | 0 | Empty | 2024-06-30 | 2024-07-03 | 2024-07-01 | 2024-07-02 | 2024-04-18 | 2024-06-02 | 30 | SECE | SECE | DF /C /20/DFCI-BDV-34057 | Isolate DFCI-BDV-34057 | Unknown
2 | NE | WDF | MTN-MECH | MTN-INST | 2100110897 | Gaslækage fra BDV-34057 | Isolate DFCI-BDV-34057 | SECE | SECE | 1 | 0 | Empty | 2024-06-30 | 2024-07-03 | 2024-07-02 | 2024-07-02 | 2024-04-18 | 2024-06-02 | 40 | SECE | SECE | DF /C /20/DFCI-BDV-34057 | Isolate DFCI-BDV-34057 | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100110897 | Gaslækage fra BDV-34057 | Isolate DFCI-BDV-34057 | SECE | SECE | 3 | 0 | Empty | 2024-06-30 | 2024-07-03 | 2024-07-02 | 2024-07-03 | 2024-04-18 | 2024-06-02 | 50 | SECE | SECE | DF /C /20/DFCI-BDV-34057 | Isolate DFCI-BDV-34057 | Unknown
3 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100045947 | ANOP New support flarepipe DFFA-V-4401 | Rope to measure according to file | PCNF | PCNF | 0 | 0 | W21-22 MPM | 2022-05-26 | 2023-12-25 | 2023-12-24 | 2023-12-24 | 2021-02-21 | 2021-03-13 | 10 | PCNF | PCNF | DF /F /32/DFFA-V-4401 | Rope to measure according to file | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045947 | ANOP New support flarepipe DFFA-V-4401 | Rope to measure according to file | PCNF | PCNF | 72 | 0 | W21-22 MPM | 2022-05-26 | 2023-12-25 | 2023-12-24 | 2023-12-24 | 2021-02-21 | 2021-03-13 | 20 | PCNF | PCNF | DF /F /32/DFFA-V-4401 | Rope to measure according to file | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045947 | ANOP New support flarepipe DFFA-V-4401 | Rope to measure according to file | PCNF | PCNF | 0 | 0 | W21-22 MPM | 2022-05-26 | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2021-02-21 | 2021-03-13 | 30 | PCNF | PCNF | DF /F /32/DFFA-V-4401 | Rope to measure according to file | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045947 | ANOP New support flarepipe DFFA-V-4401 | Rope to measure according to file | PCNF | PCNF | 15 | 9 | W21-22 MPM | 2022-05-26 | 2023-12-25 | 2022-05-26 | 2022-06-05 | 2021-02-21 | 2021-03-13 | 40 | PCNF | PCNF | DF /F /32/DFFA-V-4401 | Rope to measure according to file | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100045947 | ANOP New support flarepipe DFFA-V-4401 | Rope to measure according to file | PCNF | PCNF | 0 | 0 | W21-22 MPM | 2022-05-26 | 2023-12-25 | 2023-12-25 | 2023-12-25 | 2021-02-21 | 2021-03-13 | 50 | PCNF | PCNF | DF /F /32/DFFA-V-4401 | Rope to measure according to file | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235666 | 4Y 400V N-SWB MAINT DFCI-N-1802-R03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R03H-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235666 | 4Y 400V N-SWB MAINT DFCI-N-1802-R03 | ISOLATION ELECTRICAL | AWSC | AWSC | 17 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R03H-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235666 | 4Y 400V N-SWB MAINT DFCI-N-1802-R03 | ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R03H-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235666 | 4Y 400V N-SWB MAINT DFCI-N-1802-R03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R03H-01 | ISOLATION ELECTRICAL | Unknown
3 | DFGHPSEP | WGN | MTN-INST | PRODTECH | 2200003183 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-340003 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2017-12-29 | 2018-03-29 | 10 | AWSC | AWSC | DF /G /12/DFGA-ESDV-340003 | Hydraulic isolation DFGA-ESDV-340003 | Unknown
3 | DFGHPSEP | WGN | MTN-INST | MTN-INST | 2200003183 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-340003 | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-04 | 2017-12-29 | 2018-03-29 | 20 | AWSC | AWSC | DF /G /12/DFGA-ESDV-340003 | Hydraulic isolation DFGA-ESDV-340003 | Unknown
3 | DFGHPSEP | WGN | MTN-INST | PRODTECH | 2200003183 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-340003 | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2017-12-29 | 2018-03-29 | 30 | AWSC | AWSC | DF /G /12/DFGA-ESDV-340003 | Hydraulic isolation DFGA-ESDV-340003 | Unknown
3 | DFGHPSEP | WGN | MTN-INST | MTN-INST | 2200003183 | DFG Mount PRV on ESDV control panel | Hydraulic isolation DFGA-ESDV-340003 | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2017-12-29 | 2018-03-29 | 40 | AWSC | AWSC | DF /G /12/DFGA-ESDV-340003 | Hydraulic isolation DFGA-ESDV-340003 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-15 | 2024-03-15 | 2019-04-02 | 2019-08-30 | 5 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-15 | 2024-03-15 | 2019-04-02 | 2019-08-30 | 10 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-15 | 2024-03-15 | 2019-04-02 | 2019-08-30 | 20 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 2 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-15 | 2024-03-15 | 2019-04-02 | 2019-08-30 | 30 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 2 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-15 | 2024-03-15 | 2019-04-02 | 2019-08-30 | 40 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 6 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-15 | 2024-03-16 | 2019-04-02 | 2019-08-30 | 50 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 12 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-16 | 2024-03-17 | 2019-04-02 | 2019-08-30 | 61 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 12 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-17 | 2024-03-18 | 2019-04-02 | 2019-08-30 | 62 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 12 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-18 | 2024-03-19 | 2019-04-02 | 2019-08-30 | 63 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 4 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-19 | 2024-03-20 | 2019-04-02 | 2019-08-30 | 65 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-INSP | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 2 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-20 | 2024-03-20 | 2019-04-02 | 2019-08-30 | 70 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 4 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-20 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 80 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 1 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 90 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 100 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 110 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 120 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 130 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 140 |  |  | DF /E /54 | Build of hard barrier. | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100024548 | ANOP DFE-07 6" WI spool class med struc. | Build of hard barrier. |  |  | 0 | 0 | Empty | 2024-03-15 | 2024-03-21 | 2024-03-21 | 2024-03-21 | 2019-04-02 | 2019-08-30 | 150 |  |  | DF /E /54 | Build of hard barrier. | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025037 | CMAT:DEFEKT HCV FØR FILTER | L3 Desafing of DFFA-FT-5052 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2018-09-04 | 2018-12-03 | 10 |  |  | DF /F /28/DFFA-FT-5052 | L3 Desafing of DFFA-FT-5052 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025037 | CMAT:DEFEKT HCV FØR FILTER | L3 Desafing of DFFA-FT-5052 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2018-09-04 | 2018-12-03 | 20 |  |  | DF /F /28/DFFA-FT-5052 | L3 Desafing of DFFA-FT-5052 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025037 | CMAT:DEFEKT HCV FØR FILTER | L3 Desafing of DFFA-FT-5052 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2018-09-04 | 2018-12-03 | 30 |  |  | DF /F /28/DFFA-FT-5052 | L3 Desafing of DFFA-FT-5052 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100044250 | DFC LEVEL 1. DFCM-XCV-50446 LUKKE IKKE | Vendor to Troubleshoot on XCV-50446 | AWSC | AWSC | 0 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-07-05 | 2022-05-01 | 10 | AWSC | AWSC | DF /C /27/DFCI-XCV-50446 | Vendor to Troubleshoot on XCV-50446 | Unknown
4 | DFCHPSEP | WDF | MTN-MECH | MTN-MECH | 2100044250 | DFC LEVEL 1. DFCM-XCV-50446 LUKKE IKKE | Vendor to Troubleshoot on XCV-50446 | AWSC | AWSC | 6 | 0 | W9 IOP 23/2-1/3 | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2021-07-05 | 2022-05-01 | 20 | AWSC | AWSC | DF /C /27/DFCI-XCV-50446 | Vendor to Troubleshoot on XCV-50446 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193027 | 1Y CHEMICAL INJ. PUMP SKID, A-39220 | 1Y CHEMICAL INJ. PUMP SKID, A-39220 |  |  | 6 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-22 | 2024-08-23 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /75/DFAA-A-39220 | 1Y CHEMICAL INJ. PUMP SKID, A-39220 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400193027 | 1Y CHEMICAL INJ. PUMP SKID, A-39220 | 1Y CHEMICAL INJ. PUMP SKID, A-39220 |  |  | 6 | 0 | Empty | 2024-08-22 | 2024-08-25 | 2024-08-23 | 2024-08-25 | 2022-04-26 | 2022-06-01 | 20 |  |  | DF /A /75/DFAA-A-39220 | 1Y CHEMICAL INJ. PUMP SKID, A-39220 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235839 | 4Y 400V E-SWB MAINT DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235839 | 4Y 400V E-SWB MAINT DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | AWSC | AWSC | 26 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235839 | 4Y 400V E-SWB MAINT DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235839 | 4Y 400V E-SWB MAINT DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A01 | ISOLATION BY PRODUCTION | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 2 | 2 | Empty | 2024-08-12 | 2024-08-12 | 2024-01-22 | 2024-02-05 | 2024-01-15 | 2024-02-29 | 10 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 2 | 2 | Empty | 2024-08-12 | 2024-08-12 | 2024-01-22 | 2024-02-05 | 2024-01-15 | 2024-02-29 | 20 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 12 | 12 | Empty | 2024-08-12 | 2024-08-12 | 2024-01-23 | 2024-02-05 | 2024-01-15 | 2024-02-29 | 30 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 6 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-15 | 2024-02-29 | 40 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 2 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-15 | 2024-02-29 | 50 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 2 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-15 | 2024-02-29 | 60 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
2 | DFG-1640 | WDF | MTN-TURB | MTN-TURB | 2100105558 | $1640 Lubeoil Temp. high | Isolation of DFGA-A-1640 - EIA | PCNF | PCNF | 0 | 0 | Empty | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-01-15 | 2024-02-29 | 70 | PCNF | PCNF | DF /G /60/DFGA-A-1640 | Isolation of DFGA-A-1640 - EIA | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072927 | HT faultfinding cir.nr 62 | HT faultfinding cir.nr 62 |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2023-02-10 | 2025-07-29 | 10 |  |  | DF /B /61/DFBA-N-1810-C_62 | HT faultfinding cir.nr 62 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072927 | HT faultfinding cir.nr 62 | HT faultfinding cir.nr 62 |  |  | 8 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-02-10 | 2025-07-29 | 20 |  |  | DF /B /61/DFBA-N-1810-C_62 | HT faultfinding cir.nr 62 | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100072927 | HT faultfinding cir.nr 62 | HT faultfinding cir.nr 62 |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2023-02-10 | 2025-07-29 | 30 |  |  | DF /B /61/DFBA-N-1810-C_62 | HT faultfinding cir.nr 62 | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 10 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 4 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 20 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 1 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 30 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 24 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 40 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 6 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 50 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 6 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 60 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 70 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 80 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 90 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 100 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 110 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 120 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-TELE | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 12 | 24 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 130 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
3 | NOSD | WGN | MTN-ELEC | MTN-ELEC | 2200013612 | DFGA-A-1202 & 1203, Replace PLC | Increase of PO 4300039387 Johnson | PCNF | PCNF | 0 | 0 | Empty | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2023-04-06 | 2023-08-19 | 140 | PCNF | PCNF | DF /G /09/DFGA-A-1202 | Increase of PO 4300039387 Johnson | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346566 | 1Y DELUGE SKIDS, SMOKE TEST-DFG | DELUGE SKIDS, SMOKE TEST-DFG | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-19 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /G /01/DFGA-A-0340 | DELUGE SKIDS, SMOKE TEST-DFG | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346566 | 1Y DELUGE SKIDS, SMOKE TEST-DFG | DELUGE SKIDS, SMOKE TEST-DFG | AWSCSECE | AWSCSECE | 8 | 0 | W33-W34 | 2024-08-14 | 2024-08-19 | 2024-08-15 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /G /01/DFGA-A-0340 | DELUGE SKIDS, SMOKE TEST-DFG | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346566 | 1Y DELUGE SKIDS, SMOKE TEST-DFG | DELUGE SKIDS, SMOKE TEST-DFG | AWSCSECE | AWSCSECE | 5 | 0 | W33-W34 | 2024-08-14 | 2024-08-19 | 2024-08-17 | 2024-08-18 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /G /01/DFGA-A-0340 | DELUGE SKIDS, SMOKE TEST-DFG | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346566 | 1Y DELUGE SKIDS, SMOKE TEST-DFG | DELUGE SKIDS, SMOKE TEST-DFG | AWSCSECE | AWSCSECE | 5 | 0 | W33-W34 | 2024-08-14 | 2024-08-19 | 2024-08-18 | 2024-08-19 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /G /01/DFGA-A-0340 | DELUGE SKIDS, SMOKE TEST-DFG | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346566 | 1Y DELUGE SKIDS, SMOKE TEST-DFG | DELUGE SKIDS, SMOKE TEST-DFG | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-19 | 2024-08-19 | 2024-08-19 | 2024-08-31 | 2024-09-30 | 50 | AWSCSECE | AWSCSECE | DF /G /01/DFGA-A-0340 | DELUGE SKIDS, SMOKE TEST-DFG | Unknown
2 | DFF-3580 | WDF | MTN-ELEC | PRODTECH | 2100077767 | Fedbackfejl luboilp. 3589 | Faultfinding signals |  |  | 1 | 0 | Waiting SD of P-3580 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-10 | 2022-12-25 | 10 |  |  | DF /F /06/DFFA-N-1903B | Faultfinding signals | Unknown
2 | DFF-3580 | WDF | MTN-ELEC | MTN-ELEC | 2100077767 | Fedbackfejl luboilp. 3589 | Faultfinding signals |  |  | 2 | 0 | Waiting SD of P-3580 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-10 | 2022-12-25 | 20 |  |  | DF /F /06/DFFA-N-1903B | Faultfinding signals | Unknown
2 | DFF-3580 | WDF | MTN-ELEC | MTN-TELE | 2100077767 | Fedbackfejl luboilp. 3589 | Faultfinding signals |  |  | 2 | 0 | Waiting SD of P-3580 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-10 | 2022-12-25 | 30 |  |  | DF /F /06/DFFA-N-1903B | Faultfinding signals | Unknown
2 | DFF-3580 | WDF | MTN-ELEC | PRODTECH | 2100077767 | Fedbackfejl luboilp. 3589 | Faultfinding signals |  |  | 1 | 0 | Waiting SD of P-3580 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-11-10 | 2022-12-25 | 40 |  |  | DF /F /06/DFFA-N-1903B | Faultfinding signals | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000931 | F&G SW for DFDCOM | F&G SW for DFDCOM | AWSC | AWSC | 24 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-05 | 2024-10-07 | 2019-06-20 | 2019-11-17 | 10 | AWSC | AWSC | DF /C /03/DFCI-FP-0136 | F&G SW for DFDCOM | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000931 | F&G SW for DFDCOM | F&G SW for DFDCOM | AWSC | AWSC | 10 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-07 | 2024-10-10 | 2019-06-20 | 2019-11-17 | 20 | AWSC | AWSC | DF /C /03/DFCI-FP-0136 | F&G SW for DFDCOM | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000931 | F&G SW for DFDCOM | F&G SW for DFDCOM | AWSC | AWSC | 0 | 0 | Empty | 2024-10-05 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2019-06-20 | 2019-11-17 | 30 | AWSC | AWSC | DF /C /03/DFCI-FP-0136 | F&G SW for DFDCOM | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024133 | SMAT:Bleedvlv ved launcherlåge mangler(D | L3 De-isolate DFFA-EP-3801 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2016-07-25 | 2016-12-22 | 20 |  |  | DF /F /34/DFFA-EP-3801 | L3 De-isolate DFFA-EP-3801 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024133 | SMAT:Bleedvlv ved launcherlåge mangler(D | L3 De-isolate DFFA-EP-3801 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2016-07-25 | 2016-12-22 | 30 |  |  | DF /F /34/DFFA-EP-3801 | L3 De-isolate DFFA-EP-3801 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024133 | SMAT:Bleedvlv ved launcherlåge mangler(D | L3 De-isolate DFFA-EP-3801 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2016-07-25 | 2016-12-22 | 40 |  |  | DF /F /34/DFFA-EP-3801 | L3 De-isolate DFFA-EP-3801 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024133 | SMAT:Bleedvlv ved launcherlåge mangler(D | L3 De-isolate DFFA-EP-3801 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2016-07-25 | 2016-12-22 | 50 |  |  | DF /F /34/DFFA-EP-3801 | L3 De-isolate DFFA-EP-3801 | Unknown
4 | DFB-O17 | WDF | MTN-INST | MTN-INST | 2100023075 | DFB Defekt SOV WH Panel A-3101B DFB-19 | Isolate equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2024-12-31 | 2020-06-30 | 2022-06-20 | 10 | AWSC | AWSC | DF /B /07/DFBA-A-3101B | Isolate equipment | Unknown
4 | DFB-O17 | WDF | MTN-INST | MTN-INST | 2100023075 | DFB Defekt SOV WH Panel A-3101B DFB-19 | Isolate equipment | AWSC | AWSC | 2 | 0 | Empty | 2024-12-31 | 2025-01-01 | 2024-12-31 | 2025-01-01 | 2020-06-30 | 2022-06-20 | 20 | AWSC | AWSC | DF /B /07/DFBA-A-3101B | Isolate equipment | Unknown
4 | DFB-O17 | WDF | MTN-INST | MTN-INST | 2100023075 | DFB Defekt SOV WH Panel A-3101B DFB-19 | Isolate equipment | AWSC | AWSC | 1 | 0 | Empty | 2024-12-31 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2020-06-30 | 2022-06-20 | 30 | AWSC | AWSC | DF /B /07/DFBA-A-3101B | Isolate equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 8.699999999999999289457264236 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-14 | 2023-02-14 | 2016-05-21 | 2016-08-19 | 4 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 3 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-14 | 2023-02-15 | 2016-05-21 | 2016-08-19 | 5 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 52.29999999999999715782905694 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-15 | 2023-02-18 | 2016-05-21 | 2016-08-19 | 10 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 3 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-18 | 2023-02-19 | 2016-05-21 | 2016-08-19 | 20 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 3 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-19 | 2023-02-19 | 2016-05-21 | 2016-08-19 | 30 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-PIPF | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 52.29999999999999715782905694 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-19 | 2023-02-21 | 2016-05-21 | 2016-08-19 | 40 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025431 | Replace spools (Bullheadlinie/defekt ven | L2 Replace spool |  |  | 3 | 0 | Empty | 2023-02-14 | 2023-02-22 | 2023-02-21 | 2023-02-22 | 2016-05-21 | 2016-08-19 | 50 |  |  | DF /B /10 | L2 Replace spool | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2021-09-18 | 2021-12-17 | 10 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2021-09-18 | 2021-12-17 | 20 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-30 | 2021-09-18 | 2021-12-17 | 30 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-31 | 2021-09-18 | 2021-12-17 | 39 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 8 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-02 | 2021-09-18 | 2021-12-17 | 40 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 5 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-02 | 2021-09-18 | 2021-12-17 | 50 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2021-09-18 | 2021-12-17 | 60 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2021-09-18 | 2021-12-17 | 69 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100054379 | Install overhauled anti fouling vessel | Rubber gaskets |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2021-09-18 | 2021-12-17 | 70 |  |  | DF /C /52/DFCM-V-5522 | Rubber gaskets | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2022-12-01 | 2023-04-15 | 10 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2022-12-01 | 2023-04-15 | 20 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-16 | 2024-07-17 | 2022-12-01 | 2023-04-15 | 30 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-17 | 2022-12-01 | 2023-04-15 | 40 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 2 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-17 | 2022-12-01 | 2023-04-15 | 50 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 5 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-18 | 2022-12-01 | 2023-04-15 | 60 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 4 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2022-12-01 | 2023-04-15 | 70 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2022-12-01 | 2023-04-15 | 80 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076357 | PSV - DFCM-PSV-10380 on potwater maker l | Add Matr/Spool piece/PSV |  |  | 0 | 0 | Empty | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2022-12-01 | 2023-04-15 | 90 |  |  | DF /C /85/DFCM-PSV-10380 | Add Matr/Spool piece/PSV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-21 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 10 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 14 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-21 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 20 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-21 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 30 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 40 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 4 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 50 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 60 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 70 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 5 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 80 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 90 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 100 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 110 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2020-12-22 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 120 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-29 | 2022-07-23 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 130 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 2 | W31-W32 | 2024-07-29 | 2024-07-29 | 2022-07-23 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 140 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-CRAN | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 1 | W31-W32 | 2024-07-29 | 2024-07-29 | 2022-07-23 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 150 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2023-03-02 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 160 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 10 | W31-W32 | 2024-07-29 | 2024-07-29 | 2023-03-02 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 170 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2023-03-02 | 2023-03-17 | 2020-09-30 | 2020-12-29 | 180 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-09-30 | 2020-12-29 | 190 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-09-30 | 2020-12-29 | 200 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-09-30 | 2020-12-29 | 210 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-09-30 | 2020-12-29 | 220 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-09-30 | 2020-12-29 | 230 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100038052 | DFG/78: take oil sample and replace oil | Isolate crane DFG Aug 2024. | PCNFSCH | PCNFSCH | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-09-30 | 2020-12-29 | 240 | PCNFSCH | PCNFSCH | DF /G /78/DFGA-A-6140 | Isolate crane DFG Aug 2024. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004151 | Change 100Mbit F&G MB300 network card | Secure that redundant network is running | SCH | SCH | 10 | 30 | W07-W08 | 2024-02-12 | 2024-02-14 | 2024-02-12 | 2024-02-14 | 2022-11-06 | 2023-03-21 | 10 | SCH | SCH | DF /C /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004151 | Change 100Mbit F&G MB300 network card | Secure that redundant network is running | SCH | SCH | 0 | 0 | W07-W08 | 2024-02-12 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2022-11-06 | 2023-03-21 | 20 | SCH | SCH | DF /C /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004151 | Change 100Mbit F&G MB300 network card | Secure that redundant network is running | SCH | SCH | 0 | 0 | W07-W08 | 2024-02-12 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2022-11-06 | 2023-03-21 | 30 | SCH | SCH | DF /C /03 | Secure that redundant network is running | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300004151 | Change 100Mbit F&G MB300 network card | Secure that redundant network is running | SCH | SCH | 0 | 0 | W07-W08 | 2024-02-12 | 2024-02-14 | 2024-02-14 | 2024-02-14 | 2022-11-06 | 2023-03-21 | 40 | SCH | SCH | DF /C /03 | Secure that redundant network is running | Unknown
3 | DFC-5705 | WDF | MTN-MECH | PRODTECH | 2100025443 | CMAT:DFC fuelgas udskift trim @ LCV-5769 | Safing af LVC-57690 - FG filter V-5705 | AWSC | AWSC | 5 | 0 | Moved-RPJ006 | 2025-01-01 | 2025-01-06 | 2025-01-01 | 2025-01-02 | 2017-10-17 | 2017-11-26 | 10 | AWSC | AWSC | DF /C /70/DFCM-LCV-57690 | Safing af LVC-57690 - FG filter V-5705 | Unknown
3 | DFC-5705 | WDF | MTN-MECH | MTN-MECH | 2100025443 | CMAT:DFC fuelgas udskift trim @ LCV-5769 | Safing af LVC-57690 - FG filter V-5705 | AWSC | AWSC | 12 | 0 | Moved-RPJ006 | 2025-01-01 | 2025-01-06 | 2025-01-02 | 2025-01-05 | 2017-10-17 | 2017-11-26 | 20 | AWSC | AWSC | DF /C /70/DFCM-LCV-57690 | Safing af LVC-57690 - FG filter V-5705 | Unknown
3 | DFC-5705 | WDF | MTN-MECH | PRODTECH | 2100025443 | CMAT:DFC fuelgas udskift trim @ LCV-5769 | Safing af LVC-57690 - FG filter V-5705 | AWSC | AWSC | 5 | 0 | Moved-RPJ006 | 2025-01-01 | 2025-01-06 | 2025-01-05 | 2025-01-06 | 2017-10-17 | 2017-11-26 | 30 | AWSC | AWSC | DF /C /70/DFCM-LCV-57690 | Safing af LVC-57690 - FG filter V-5705 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337664 | 6M SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | SCALE INH INJ PMP MAINT-DFGA-P-3952/3 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-30 | 2024-08-18 | 10 |  |  | DF /G /75/DFGA-A-3940 | SCALE INH INJ PMP MAINT-DFGA-P-3952/3 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 1 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2022-09-29 | 2023-02-11 | 10 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 6 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2022-09-29 | 2023-02-11 | 20 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 10 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2022-09-29 | 2023-02-11 | 30 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 1 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2022-09-29 | 2023-02-11 | 40 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-LAGG | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 12 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2022-09-29 | 2023-02-11 | 50 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 1 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2022-09-29 | 2023-02-11 | 60 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100073122 | Defekt heattracing cable f DFF-LG-500101 | Additional materials | SCH | SCH | 0 | 0 | 23-W51-52 | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2022-09-29 | 2023-02-11 | 70 | SCH | SCH | DF /F /28/DFFA-LG-500101 | Additional materials | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 3 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-05-28 | 2024-05-28 | 2023-05-28 | 2025-11-13 | 10 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | WELLSUPV | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 3 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-05-28 | 2024-05-29 | 2023-05-28 | 2025-11-13 | 20 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 8 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-05-29 | 2024-05-30 | 2023-05-28 | 2025-11-13 | 30 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 8 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-05-30 | 2024-06-01 | 2023-05-28 | 2025-11-13 | 40 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 8 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-06-01 | 2024-06-02 | 2023-05-28 | 2025-11-13 | 50 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 6 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-06-02 | 2024-06-03 | 2023-05-28 | 2025-11-13 | 60 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 3 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-06-02 | 2024-06-03 | 2023-05-28 | 2025-11-13 | 65 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 3 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-06-02 | 2024-06-03 | 2023-05-28 | 2025-11-13 | 70 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | WELLSUPV | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 3 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-05-28 | 2025-11-13 | 80 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100078737 | HCV-352033 internal leak | Isolate HCV-352033 |  |  | 2 | 0 | Empty | 2024-05-28 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2023-05-28 | 2025-11-13 | 90 |  |  | DF /F /55/DFFA-HCV-352033 | Isolate HCV-352033 | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2018-11-16 | 2019-04-15 | 10 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-02 | 2018-11-16 | 2019-04-15 | 20 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-01 | 2025-01-01 | 2018-11-16 | 2019-04-15 | 30 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-02 | 2025-01-03 | 2018-11-16 | 2019-04-15 | 40 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-03 | 2018-11-16 | 2019-04-15 | 50 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-03 | 2018-11-16 | 2019-04-15 | 60 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-SCAF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-03 | 2018-11-16 | 2019-04-15 | 70 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | MTN-PIPF | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2018-11-16 | 2019-04-15 | 80 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | VEN-ELEC | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-03 | 2025-01-04 | 2018-11-16 | 2019-04-15 | 90 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
4 | DAN-GAS | WDF | MTN-MECH | PRODTECH | 2100026133 | Exchange DFFA-ESDV-441330 | L3 Pre permit & linewalk | AWSC | AWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-04 | 2025-01-04 | 2025-01-04 | 2018-11-16 | 2019-04-15 | 100 | AWSC | AWSC | DF /F /31/DFFA-ESDV-441330 | L3 Pre permit & linewalk | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337659 | 1Y SYS 28 DRAINS PUMPS MAINT-DFF | SYS 28 DRAINS PUMPS MAINT-DFF | SECE | SECE | 4 | 0 | Empty | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-19 | 10 | SECE | SECE | DF /F /28/DFFA-T-5050 | SYS 28 DRAINS PUMPS MAINT-DFF | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337659 | 1Y SYS 28 DRAINS PUMPS MAINT-DFF | SYS 28 DRAINS PUMPS MAINT-DFF | SECE | SECE | 4 | 0 | Empty | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-19 | 20 | SECE | SECE | DF /F /28/DFFA-T-5050 | SYS 28 DRAINS PUMPS MAINT-DFF | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400337659 | 1Y SYS 28 DRAINS PUMPS MAINT-DFF | SYS 28 DRAINS PUMPS MAINT-DFF | SECE | SECE | 4 | 0 | Empty | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-07-20 | 2024-08-19 | 30 | SECE | SECE | DF /F /28/DFFA-T-5050 | SYS 28 DRAINS PUMPS MAINT-DFF | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235685 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-05-30 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235685 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF03 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-05-30 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235685 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-05-30 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF03-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235685 | 4Y 400V N-SWB MAINT-DFGA-N-1842A-AF03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-05-30 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842A-AF03-01 | ISOLATION ELECTRICAL | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000888 | SMAT:Repl obsolete ESD/F&G NW components | Repl. of obsolete ESD/F&G NW components | PCNF | PCNF | 29 | 29 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2010-01-01 | 2030-12-31 | 10 | PCNF | PCNF | DF /C /03 | Repl. of obsolete ESD/F&G NW components | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024420 | C&P Leak diesel transfer line DFC-DFF | Klargøring af jobbet | PCNF | PCNF | 6 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-10-23 | 2018-10-28 | 10 | PCNF | PCNF | DF /C /71/DFC-2-OD-057-6511-AA-U | Klargøring af jobbet | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024420 | C&P Leak diesel transfer line DFC-DFF | Klargøring af jobbet | PCNF | PCNF | 27.699999999999999289457264232 | 19 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-10-23 | 2018-10-28 | 20 | PCNF | PCNF | DF /C /71/DFC-2-OD-057-6511-AA-U | Klargøring af jobbet | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100024420 | C&P Leak diesel transfer line DFC-DFF | Klargøring af jobbet | PCNF | PCNF | 12 | 12 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-10-23 | 2018-10-28 | 30 | PCNF | PCNF | DF /C /71/DFC-2-OD-057-6511-AA-U | Klargøring af jobbet | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100024420 | C&P Leak diesel transfer line DFC-DFF | Klargøring af jobbet | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-10-23 | 2018-10-28 | 40 | PCNF | PCNF | DF /C /71/DFC-2-OD-057-6511-AA-U | Klargøring af jobbet | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100024420 | C&P Leak diesel transfer line DFC-DFF | Klargøring af jobbet | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-10-23 | 2018-10-28 | 50 | PCNF | PCNF | DF /C /71/DFC-2-OD-057-6511-AA-U | Klargøring af jobbet | Unknown
3 | NOSD | WDF | MTN-MECH | WELLSUPV | 2100024420 | C&P Leak diesel transfer line DFC-DFF | Klargøring af jobbet | PCNF | PCNF | 0 | 0 | Empty | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2024-03-15 | 2018-10-23 | 2018-10-28 | 60 | PCNF | PCNF | DF /C /71/DFC-2-OD-057-6511-AA-U | Klargøring af jobbet | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322261 | DFC-36-FY-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 24 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /C /36/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-01 | 2025-01-01 | 2023-06-03 | 2023-08-04 | 5 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 26 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-01 | 2025-01-08 | 2023-06-03 | 2023-08-04 | 10 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-MECH | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 0 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-08 | 2025-01-08 | 2023-06-03 | 2023-08-04 | 11 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-ELEC | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 5 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-08 | 2025-01-09 | 2023-06-03 | 2023-08-04 | 20 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
A | DFF-3580 | WPM | MTN-MECH | MTN-INST | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 18 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-09 | 2025-01-13 | 2023-06-03 | 2023-08-04 | 30 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
A | DFF-3580 | WPM | MTN-MECH | VEN-INST | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 24 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-13 | 2025-01-16 | 2023-06-03 | 2023-08-04 | 40 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
A | DFF-3580 | WPM | MTN-MECH | PRODTECH | 2400268062 | 3Y DEAERATOR MAINT - DFFB-A-3560 - DFF | Oil change material | AWSC | AWSC | 1 | 0 | Empty | 2025-01-01 | 2025-01-16 | 2025-01-16 | 2025-01-16 | 2023-06-03 | 2023-08-04 | 50 | AWSC | AWSC | DF /F /53 | Oil change material | Unknown
4 | Empty | WRO | MTN-ELEC | MTN-ELEC | 2300001487 | DK40 - erstattes af 2300002016 - ELEC | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | Empty | WRO | MTN-ELEC | MTN-ELEC | 2300001487 | DK40 - erstattes af 2300002016 - ELEC | DK40 - CONSUMABLE MTN - ELEC |  |  | 0 | 0 | Empty | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-28 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE MTN - ELEC | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100070242 | DFCI-SOV-33021 is about to rust away. | Isolate and Inhibit ShutDown Valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 10 | SECE | SECE | DF /C /12/DFCI-ESDV-33021 | Isolate and Inhibit ShutDown Valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070242 | DFCI-SOV-33021 is about to rust away. | Isolate and Inhibit ShutDown Valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 20 | SECE | SECE | DF /C /12/DFCI-ESDV-33021 | Isolate and Inhibit ShutDown Valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070242 | DFCI-SOV-33021 is about to rust away. | Isolate and Inhibit ShutDown Valve (SDV) | SECE | SECE | 2.5 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 30 | SECE | SECE | DF /C /12/DFCI-ESDV-33021 | Isolate and Inhibit ShutDown Valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100070242 | DFCI-SOV-33021 is about to rust away. | Isolate and Inhibit ShutDown Valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 40 | SECE | SECE | DF /C /12/DFCI-ESDV-33021 | Isolate and Inhibit ShutDown Valve (SDV) | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100070242 | DFCI-SOV-33021 is about to rust away. | Isolate and Inhibit ShutDown Valve (SDV) | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2022-12-18 | 2025-06-05 | 50 | SECE | SECE | DF /C /12/DFCI-ESDV-33021 | Isolate and Inhibit ShutDown Valve (SDV) | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000959 | SCADA SW for ENG469L Vacuum pump | SCADA SW for ENG469L Vacuum pump | AWSC | AWSC | 12 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2019-02-04 | 2019-07-04 | 10 | AWSC | AWSC | DF /B /04/DFBA-FP-2002 | SCADA SW for ENG469L Vacuum pump | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000959 | SCADA SW for ENG469L Vacuum pump | SCADA SW for ENG469L Vacuum pump | AWSC | AWSC | 6 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-04 | 2019-07-04 | 20 | AWSC | AWSC | DF /B /04/DFBA-FP-2002 | SCADA SW for ENG469L Vacuum pump | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000959 | SCADA SW for ENG469L Vacuum pump | SCADA SW for ENG469L Vacuum pump | AWSC | AWSC | 0 | 0 | date TBC | 2024-09-18 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2019-02-04 | 2019-07-04 | 30 | AWSC | AWSC | DF /B /04/DFBA-FP-2002 | SCADA SW for ENG469L Vacuum pump | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-HVAC | 2400221609 | 3Y DUCT CLEAN LIVING QUARTERS VEND -DFC | DUCT CLEAN LIVING QUARTERS VEND -DFC | AWSCSCH | AWSCSCH | 180 | 0 | W13-W14 | 2024-09-22 | 2024-10-10 | 2024-09-22 | 2024-10-10 | 2022-10-16 | 2023-01-23 | 10 | AWSCSCH | AWSCSCH | DF /C /09 | DUCT CLEAN LIVING QUARTERS VEND -DFC | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235595 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-6 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 |  |  | DF /F /61/DFFA-DP-1802A-6 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235595 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-6 | ISOLATION ELECTRICAL |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2023-04-15 | 2023-07-12 | 20 |  |  | DF /F /61/DFFA-DP-1802A-6 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235595 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-6 | ISOLATION ELECTRICAL |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2023-04-15 | 2023-07-12 | 30 |  |  | DF /F /61/DFFA-DP-1802A-6 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235595 | 4Y 380V N-SWB-MAINT-DFFA-N-1802A-6 | ISOLATION ELECTRICAL |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-17 | 2024-09-17 | 2023-04-15 | 2023-07-12 | 40 |  |  | DF /F /61/DFFA-DP-1802A-6 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093108 | old ESD 1 PB replace with new MEDC type | Inhibit PB |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-27 | 2023-12-09 | 10 |  |  | DF /A /03/DFAA-PB-02061 | Inhibit PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093108 | old ESD 1 PB replace with new MEDC type | Inhibit PB |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-27 | 2023-12-09 | 20 |  |  | DF /A /03/DFAA-PB-02061 | Inhibit PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093108 | old ESD 1 PB replace with new MEDC type | Inhibit PB |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 30 |  |  | DF /A /03/DFAA-PB-02061 | Inhibit PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093108 | old ESD 1 PB replace with new MEDC type | Inhibit PB |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 40 |  |  | DF /A /03/DFAA-PB-02061 | Inhibit PB | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100093108 | old ESD 1 PB replace with new MEDC type | Inhibit PB |  |  | 0.5 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-07-27 | 2023-12-09 | 50 |  |  | DF /A /03/DFAA-PB-02061 | Inhibit PB | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259014 | 6M SDV LUB/MAINT OIL - DFE | SDV LUB/INSP OIL - DFE |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-26 | 2023-06-11 | 10 |  |  | DF /E /03/SDV-VALVES | SDV LUB/INSP OIL - DFE | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 10 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2022-12-08 | 2023-04-22 | 20 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-23 | 2022-12-08 | 2023-04-22 | 30 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-24 | 2024-09-24 | 2022-12-08 | 2023-04-22 | 40 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2022-12-08 | 2023-04-22 | 50 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2022-12-08 | 2023-04-22 | 60 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076712 | Faulfinding on XCV-570203 Synergy 663200 | Isolate controls and pneumatic |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2022-12-08 | 2023-04-22 | 70 |  |  | DF /F /71/DFFA-XCV-570203 | Isolate controls and pneumatic | Unknown
4 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100068309 | DFB/78 Replace operator seat | Isolation/deisolation of crane |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-15 | 2022-08-08 | 2023-01-05 | 10 |  |  | DF /B /78/DFBA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | VEN-CRAN | 2100068309 | DFB/78 Replace operator seat | Isolation/deisolation of crane |  |  | 15 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-17 | 2022-08-08 | 2023-01-05 | 20 |  |  | DF /B /78/DFBA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100068309 | DFB/78 Replace operator seat | Isolation/deisolation of crane |  |  | 30 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-15 | 2024-07-19 | 2022-08-08 | 2023-01-05 | 30 |  |  | DF /B /78/DFBA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WDF | MTN-CRAN | MTN-ROUS | 2100068309 | DFB/78 Replace operator seat | Isolation/deisolation of crane |  |  | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-20 | 2024-07-19 | 2024-07-20 | 2022-08-08 | 2023-01-05 | 40 |  |  | DF /B /78/DFBA-X-6102 | Isolation/deisolation of crane | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-11 | 2024-01-12 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-12 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 9 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-15 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 45 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-ELEC | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-15 | 2024-01-19 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 36 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-19 | 2024-01-23 | 2022-02-09 | 2022-07-09 | 60 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009229 | Insulation assist bilfinger 20867 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-25 | 2024-01-23 | 2024-01-25 | 2022-02-09 | 2022-07-09 | 70 |  |  | DF /E /55/DFE-6-WI-035-5011-FE-U | Bilfinger inspection | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235586 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1830-03C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235586 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 16 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-26 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1830-03C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235586 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1830-03C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235586 | 4Y 380V N-SWB-MAINT-DFBA-N-1830-03 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1830-03C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241145 | 6M CHEM DISTR PANEL MAINT-DFFA-A-39705 | CHEM DISTR PANEL MAINT-DFFA-A-39705 |  |  | 10 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-31 | 2023-03-13 | 2023-04-01 | 10 |  |  | DF /F /75/DFFA-A-39705 | CHEM DISTR PANEL MAINT-DFFA-A-39705 | Unknown
4 | Empty | WDF | MTN-ROPE | WELLSUPV | 2100061594 | FFSPR: Utility & Instrument Air Batch-03 | SCF6V corrosion & unapproved temp repair |  |  | 0 | 0 | Empty | 2024-04-29 | 2024-05-11 | 2024-04-29 | 2024-04-29 | 2022-04-10 | 2022-09-07 | 10 |  |  | DF /C /07/DFC-1.5-AI-054-0013-A1-U | SCF6V corrosion & unapproved temp repair | Unknown
4 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100061594 | FFSPR: Utility & Instrument Air Batch-03 | SCF6V corrosion & unapproved temp repair |  |  | 0 | 0 | Empty | 2024-04-29 | 2024-05-11 | 2024-04-29 | 2024-04-29 | 2022-04-10 | 2022-09-07 | 20 |  |  | DF /C /07/DFC-1.5-AI-054-0013-A1-U | SCF6V corrosion & unapproved temp repair | Unknown
4 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100061594 | FFSPR: Utility & Instrument Air Batch-03 | SCF6V corrosion & unapproved temp repair |  |  | 50 | 0 | Empty | 2024-04-29 | 2024-05-11 | 2024-04-29 | 2024-05-05 | 2022-04-10 | 2022-09-07 | 30 |  |  | DF /C /07/DFC-1.5-AI-054-0013-A1-U | SCF6V corrosion & unapproved temp repair | Unknown
4 | Empty | WDF | MTN-ROPE | MTN-ROPE | 2100061594 | FFSPR: Utility & Instrument Air Batch-03 | SCF6V corrosion & unapproved temp repair |  |  | 75 | 0 | Empty | 2024-04-29 | 2024-05-11 | 2024-05-05 | 2024-05-11 | 2022-04-10 | 2022-09-07 | 40 |  |  | DF /C /07/DFC-1.5-AI-054-0013-A1-U | SCF6V corrosion & unapproved temp repair | Unknown
B | DFGHPSEP | WPM | MTN-MECH | PRODTECH | 2400176982 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | DE-ISOLATION | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2021-12-03 | 2022-02-03 | 2 | AWSC | AWSC | DF /G /03/SDV-VALVES | DE-ISOLATION | Unknown
B | DFGHPSEP | WPM | MTN-MECH | MTN-ELEC | 2400176982 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | DE-ISOLATION | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-23 | 2024-09-23 | 2021-12-03 | 2022-02-03 | 10 | AWSC | AWSC | DF /G /03/SDV-VALVES | DE-ISOLATION | Unknown
B | DFGHPSEP | WPM | MTN-MECH | MTN-MECH | 2400176982 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | DE-ISOLATION | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-24 | 2024-09-26 | 2021-12-03 | 2022-02-03 | 20 | AWSC | AWSC | DF /G /03/SDV-VALVES | DE-ISOLATION | Unknown
B | DFGHPSEP | WPM | MTN-MECH | MTN-MECH | 2400176982 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | DE-ISOLATION | AWSC | AWSC | 0 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-26 | 2021-12-03 | 2022-02-03 | 30 | AWSC | AWSC | DF /G /03/SDV-VALVES | DE-ISOLATION | Unknown
B | DFGHPSEP | WPM | MTN-MECH | PRODTECH | 2400176982 | 3Y FUNC, VISUAL, EX INSP ESDV (DFGHPSEP) | DE-ISOLATION | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2021-12-03 | 2022-02-03 | 40 | AWSC | AWSC | DF /G /03/SDV-VALVES | DE-ISOLATION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284314 | PSV Calibration - DFGA-PSV-390536 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 10 | AWSC | AWSC | DF /G /75/DFGA-PSV-390536 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284314 | PSV Calibration - DFGA-PSV-390536 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-12 | 2024-10-12 | 2024-10-12 | 2024-12-31 | 20 | AWSC | AWSC | DF /G /75/DFGA-PSV-390536 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284314 | PSV Calibration - DFGA-PSV-390536 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-13 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 30 | AWSC | AWSC | DF /G /75/DFGA-PSV-390536 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284314 | PSV Calibration - DFGA-PSV-390536 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-14 | 2024-10-12 | 2024-12-31 | 40 | AWSC | AWSC | DF /G /75/DFGA-PSV-390536 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284314 | PSV Calibration - DFGA-PSV-390536 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-14 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 50 | AWSC | AWSC | DF /G /75/DFGA-PSV-390536 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284314 | PSV Calibration - DFGA-PSV-390536 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-12 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-12 | 2024-12-31 | 60 | AWSC | AWSC | DF /G /75/DFGA-PSV-390536 | Isolation of PSV | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400241140 | 1Y SYS 27 INSTRUMENTS/VALVES MAINT-DFB | SYS 27 INSTRUMENTS/VALVES MAINT-DFB |  |  | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2023-02-24 | 2023-04-01 | 10 |  |  | DF /B /27/INSTRUMENTS | SYS 27 INSTRUMENTS/VALVES MAINT-DFB | Unknown
C | NOSD | WPM | MTN-INST | MTN-INST | 2400274692 | 3Y DFFA LIFT GAS - METERING | DFFA LIFT GAS - METERING | AWSC | AWSC | 16 | 0 | Empty | 2024-06-03 | 2024-06-06 | 2024-06-03 | 2024-06-06 | 2023-07-17 | 2023-09-29 | 10 | AWSC | AWSC | DF /F /37/GAS-LIFT-METERING | DFFA LIFT GAS - METERING | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 8 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-15 | 2024-09-17 | 2021-02-18 | 2021-05-19 | 10 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-17 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 20 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-17 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 30 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-18 | 2021-02-18 | 2021-05-19 | 40 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-18 | 2024-09-19 | 2021-02-18 | 2021-05-19 | 50 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-19 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 60 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-20 | 2024-09-20 | 2021-02-18 | 2021-05-19 | 70 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 6 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-20 | 2024-09-22 | 2021-02-18 | 2021-05-19 | 80 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 4 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-22 | 2024-09-23 | 2021-02-18 | 2021-05-19 | 90 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-INST | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 3 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-23 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 100 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-24 | 2021-02-18 | 2021-05-19 | 110 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 2 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-24 | 2024-09-25 | 2021-02-18 | 2021-05-19 | 120 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100044913 | DFG LCV-400422 Dårlig integritet | Isolate LCV |  |  | 6 | 0 | Cancel see w/2100024680 | 2024-09-15 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2021-02-18 | 2021-05-19 | 130 |  |  | DF /G /36/DFGA-LCV-400422 | Isolate LCV | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009244 | Insulation assist bilfinger 21500(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-16 | 2023-03-27 | 2023-03-27 | 2022-02-13 | 2022-07-13 | 10 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009244 | Insulation assist bilfinger 21500(COMP) | Bilfinger inspection |  |  | 96 | 0 | Empty | 2023-03-27 | 2023-04-16 | 2023-03-27 | 2023-04-03 | 2022-02-13 | 2022-07-13 | 20 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009244 | Insulation assist bilfinger 21500(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-16 | 2023-04-04 | 2023-04-06 | 2022-02-13 | 2022-07-13 | 30 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009244 | Insulation assist bilfinger 21500(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-16 | 2023-04-06 | 2023-04-07 | 2022-02-13 | 2022-07-13 | 33 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009244 | Insulation assist bilfinger 21500(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-16 | 2023-04-07 | 2023-04-12 | 2022-02-13 | 2022-07-13 | 40 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009244 | Insulation assist bilfinger 21500(COMP) | Bilfinger inspection |  |  | 48 | 0 | Empty | 2023-03-27 | 2023-04-16 | 2023-04-12 | 2023-04-16 | 2022-02-13 | 2022-07-13 | 50 |  |  | DF /F /55/DFF-6-PHS-030-7101-GF-U | Bilfinger inspection | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235838 | 4Y 400V E-SWB MAINT DFGA-N-1843 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-N-1843 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235838 | 4Y 400V E-SWB MAINT DFGA-N-1843 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 16 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 20 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-N-1843 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235838 | 4Y 400V E-SWB MAINT DFGA-N-1843 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 30 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-N-1843 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235838 | 4Y 400V E-SWB MAINT DFGA-N-1843 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 40 | AWSCSECE | AWSCSECE | DF /G /05/DFGA-N-1843 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400342405 | 6M SW LIFT PUMP MAINT DFCM-P-5303 | SW LIFT PUMP MAINT DFCM-P-5303 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-08 | 2024-08-27 | 10 |  |  | DF /C /50/DFCM-P-5303 | SW LIFT PUMP MAINT DFCM-P-5303 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400343676 | 1Y BIOCIDE/SCALE INHIB SKID MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-26 | 2024-08-15 | 2024-09-14 | 10 | SECE | SECE | DF /C /75/DFCI-A-3910 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400343676 | 1Y BIOCIDE/SCALE INHIB SKID MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 9.5 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-26 | 2024-08-28 | 2024-08-15 | 2024-09-14 | 20 | SECE | SECE | DF /C /75/DFCI-A-3910 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400343676 | 1Y BIOCIDE/SCALE INHIB SKID MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-28 | 2024-08-30 | 2024-08-15 | 2024-09-14 | 30 | SECE | SECE | DF /C /75/DFCI-A-3910 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400343676 | 1Y BIOCIDE/SCALE INHIB SKID MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-30 | 2024-08-30 | 2024-08-15 | 2024-09-14 | 40 | SECE | SECE | DF /C /75/DFCI-A-3910 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400343676 | 1Y BIOCIDE/SCALE INHIB SKID MAINT-DFC | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-31 | 2024-08-30 | 2024-08-31 | 2024-08-15 | 2024-09-14 | 50 | SECE | SECE | DF /C /75/DFCI-A-3910 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235564 | 4Y 380V N-DP- MAINT-DFBA-DP-1801 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-02-14 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-DP-1801 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235564 | 4Y 380V N-DP- MAINT-DFBA-DP-1801 | ISOLATION ELECTRICAL | AWSC | AWSC | 13 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-02-14 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-DP-1801 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235564 | 4Y 380V N-DP- MAINT-DFBA-DP-1801 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-02-14 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-DP-1801 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235564 | 4Y 380V N-DP- MAINT-DFBA-DP-1801 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-02-14 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-DP-1801 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100107871 | FSL faulty LV room DFG | Remove inhibit / Test | SCHSECE | SCHSECE | 0.5 | 0.5 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-03-16 | 2024-07-29 | 5 | SCHSECE | SCHSECE | DF /G /09/DFGA-FSL-123456 | Remove inhibit / Test | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100107871 | FSL faulty LV room DFG | Remove inhibit / Test | SCHSECE | SCHSECE | 4 | 4 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-03-16 | 2024-07-29 | 10 | SCHSECE | SCHSECE | DF /G /09/DFGA-FSL-123456 | Remove inhibit / Test | Unknown
3 | NOSD | WDF | MTN-INST | MTN-TELE | 2100107871 | FSL faulty LV room DFG | Remove inhibit / Test | SCHSECE | SCHSECE | 0.5 | 0.5 | W33-W34 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-08-12 | 2024-03-16 | 2024-07-29 | 20 | SCHSECE | SCHSECE | DF /G /09/DFGA-FSL-123456 | Remove inhibit / Test | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322282 | DFF-11-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 2 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /11/P-G | PIPING INSPECTION AND REPORTING | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193025 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39240 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39240 |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /A /75/DFAA-A-39240 | 1Y CHEMICAL DISTRIBUTION PANEL, A-39240 | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 0 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 10 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 20 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 22 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 24 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 26 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 30 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 32 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 34 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 36 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 40 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 42 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 44 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 46 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 50 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 52 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 54 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 56 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 60 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 62 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 64 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 66 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 70 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 72 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 74 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 76 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 80 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 82 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 84 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 86 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 90 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 92 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 94 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 96 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 100 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 102 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 104 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 106 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 3 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 110 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 112 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 114 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2022-10-03 | 2023-02-15 | 116 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 120 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 122 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 124 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 126 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 130 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 132 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 134 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 136 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 140 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 142 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 144 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 146 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 150 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 152 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 154 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 0 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 156 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 160 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 162 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 164 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 166 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 170 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 8 | 8 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 172 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 2 | 2 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 174 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100073102 | Syn. 650656 Bolts in wrong mat. DAN FG | Syn. 650656 Bolts in wrong mat. DAN FG | PCNFSCH | PCNFSCH | 4 | 4 | W23-W24 | 2024-06-03 | 2024-06-03 | 2023-12-08 | 2024-03-24 | 2022-10-03 | 2023-02-15 | 176 | PCNFSCH | PCNFSCH | DF /G /54/DFGA-FIT-350902 | Syn. 650656 Bolts in wrong mat. DAN FG | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-26 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 10 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-01 | 2023-03-11 | 2023-07-24 | 20 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 12 | 16 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-26 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 30 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 3 | 4 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-27 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 40 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 16 | 55 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-28 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 50 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 2 | 20 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 55 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 3 | 2 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 60 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 1 | 35 | Empty | 2026-01-01 | 2026-01-02 | 2023-07-01 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 70 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-SCAF | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 30 | 31 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-26 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 80 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-01 | 2023-03-11 | 2023-07-24 | 90 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 12 | 20 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 100 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 3 | 5 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 110 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 2 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 120 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 7 | 12 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 130 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 7 | 20 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 140 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 2 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 150 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 3 | 3 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 160 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | PRODTECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 2 | 2 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 170 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 180 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 2 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 190 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 3 | 2 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 200 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 8 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 210 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 2 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 220 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 2 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 230 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 12 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 240 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-RIGG | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 12 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-06-30 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 250 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-01 | 2023-03-11 | 2023-07-24 | 260 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2023-12-04 | 2023-12-14 | 2023-03-11 | 2023-07-24 | 270 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 12 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2023-03-11 | 2023-07-24 | 280 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
3 | DFF-3520 | WDF | MTN-MECH | MTN-MECH | 2100081826 | FCV 350301 leaks 200m3/h. | Rigger assist | PCNF | PCNF | 12 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2023-03-11 | 2023-07-24 | 290 | PCNF | PCNF | DF /F /54/DFFA-FCV-350301 | Rigger assist | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400329505 | 1Y FIRE DOORS TEST - DFC | FIRE DOORS TEST - DFC | SECE | SECE | 42 | 0 | Empty | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-05-13 | 2024-06-12 | 10 | SECE | SECE | DF /C /02/FIRE-DOORS | FIRE DOORS TEST - DFC | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235763 | Test4Y 220V UPS-DP F.TEST-DFCI-AS-14-33 | 220V UPS-DP F.TEST-DFCI-AS-14-33 | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-13 | 10 | AWSC | AWSC | DF /C /08/DFCI-AS-14-33 | 220V UPS-DP F.TEST-DFCI-AS-14-33 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235724 | 4Y 380V E-SWB MAINT DFCI-N-1812-R05 | 380V E-SWB MAINT DFCI-N-1812-R05 | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-15 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R05 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235724 | 4Y 380V E-SWB MAINT DFCI-N-1812-R05 | 380V E-SWB MAINT DFCI-N-1812-R05 | AWSCSCHSECE | AWSCSCHSECE | 21 | 44 | W19-W20 | 2024-05-10 | 2024-05-15 | 2024-05-10 | 2024-05-15 | 2023-03-01 | 2023-05-13 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R05 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235724 | 4Y 380V E-SWB MAINT DFCI-N-1812-R05 | 380V E-SWB MAINT DFCI-N-1812-R05 | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2023-03-01 | 2023-05-13 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R05 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235724 | 4Y 380V E-SWB MAINT DFCI-N-1812-R05 | 380V E-SWB MAINT DFCI-N-1812-R05 | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W19-W20 | 2024-05-10 | 2024-05-15 | 2024-05-10 | 2024-05-10 | 2023-03-01 | 2023-05-13 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R05 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235724 | 4Y 380V E-SWB MAINT DFCI-N-1812-R05 | 380V E-SWB MAINT DFCI-N-1812-R05 | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W19-W20 | 2024-05-10 | 2024-05-15 | 2024-05-15 | 2024-05-15 | 2023-03-01 | 2023-05-13 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /05/DFCI-N-1812 | 380V E-SWB MAINT DFCI-N-1812-R05 | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-02 | 2022-03-20 | 2022-08-17 | 10 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-02 | 2022-03-20 | 2022-08-17 | 20 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-02 | 2022-03-20 | 2022-08-17 | 30 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-04 | 2022-03-20 | 2022-08-17 | 40 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2025-01-05 | 2022-03-20 | 2022-08-17 | 50 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-RIGG | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-05 | 2022-03-20 | 2022-08-17 | 60 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-07 | 2022-03-20 | 2022-08-17 | 70 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-08 | 2022-03-20 | 2022-08-17 | 80 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-09 | 2022-03-20 | 2022-08-17 | 90 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2022-03-20 | 2022-08-17 | 100 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2022-03-20 | 2022-08-17 | 110 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2022-03-20 | 2022-08-17 | 120 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-MECH | 2100060627 | FF-31 Manifold Valves Internal leak | Remove Scaffold |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2022-03-20 | 2022-08-17 | 130 |  |  | DF /F /55/DFF31-WATER-INJECTION-LINE | Remove Scaffold | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084825 | DAN F Level glass LG-40841 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 10 |  |  | DF /C /36/DFCM-LG-40841 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084825 | DAN F Level glass LG-40841 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-08-02 | 2026-01-18 | 20 |  |  | DF /C /36/DFCM-LG-40841 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100084825 | DAN F Level glass LG-40841 | Isolate Heat Tracing and Light |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-08-02 | 2026-01-18 | 30 |  |  | DF /C /36/DFCM-LG-40841 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100084825 | DAN F Level glass LG-40841 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-08-02 | 2026-01-18 | 40 |  |  | DF /C /36/DFCM-LG-40841 | Isolate Heat Tracing and Light | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100084825 | DAN F Level glass LG-40841 | Isolate Heat Tracing and Light |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-08-02 | 2026-01-18 | 50 |  |  | DF /C /36/DFCM-LG-40841 | Isolate Heat Tracing and Light | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344046 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FE | CHEMICAL INJECTION PUMPS MAINT-DAN FE | SECE | SECE | 1 | 0 | Empty | 2024-08-18 | 2024-09-09 | 2024-08-18 | 2024-08-18 | 2024-08-18 | 2024-09-17 | 10 | SECE | SECE | DF /E /75/DFEY-A-3901 | CHEMICAL INJECTION PUMPS MAINT-DAN FE | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400344046 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FE | CHEMICAL INJECTION PUMPS MAINT-DAN FE | SECE | SECE | 19 | 0 | Empty | 2024-08-18 | 2024-09-09 | 2024-08-18 | 2024-08-22 | 2024-08-18 | 2024-09-17 | 20 | SECE | SECE | DF /E /75/DFEY-A-3901 | CHEMICAL INJECTION PUMPS MAINT-DAN FE | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344046 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FE | CHEMICAL INJECTION PUMPS MAINT-DAN FE | SECE | SECE | 26 | 0 | Empty | 2024-08-18 | 2024-09-09 | 2024-08-23 | 2024-08-29 | 2024-08-18 | 2024-09-17 | 30 | SECE | SECE | DF /E /75/DFEY-A-3901 | CHEMICAL INJECTION PUMPS MAINT-DAN FE | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344046 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FE | CHEMICAL INJECTION PUMPS MAINT-DAN FE | SECE | SECE | 42 | 0 | Empty | 2024-08-18 | 2024-09-09 | 2024-08-29 | 2024-09-08 | 2024-08-18 | 2024-09-17 | 40 | SECE | SECE | DF /E /75/DFEY-A-3901 | CHEMICAL INJECTION PUMPS MAINT-DAN FE | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400344046 | 1Y CHEMICAL INJECTION PUMPS MAINT-DAN FE | CHEMICAL INJECTION PUMPS MAINT-DAN FE | SECE | SECE | 1 | 0 | Empty | 2024-08-18 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-08-18 | 2024-09-17 | 50 | SECE | SECE | DF /E /75/DFEY-A-3901 | CHEMICAL INJECTION PUMPS MAINT-DAN FE | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 13 | 0 | Empty | 2020-08-10 | 2026-01-08 | 2026-01-01 | 2026-01-02 | 2018-12-28 | 2019-03-28 | 10 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 100 | 0 | Empty | 2020-08-10 | 2026-01-08 | 2026-01-02 | 2026-01-08 | 2018-12-28 | 2019-03-28 | 30 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 20.100000000000001421085471515 | 16 | Empty | 2020-08-10 | 2026-01-08 | 2020-08-18 | 2020-12-13 | 2018-12-28 | 2019-03-28 | 35 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 5 | 0 | Empty | 2020-08-10 | 2026-01-08 | 2026-01-01 | 2026-01-01 | 2018-12-28 | 2019-03-28 | 40 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 20.100000000000001421085471515 | 36.5 | Empty | 2020-08-10 | 2026-01-08 | 2020-12-14 | 2021-01-12 | 2018-12-28 | 2019-03-28 | 45 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 46 | 0 | Empty | 2020-08-10 | 2026-01-08 | 2022-06-13 | 2022-06-16 | 2018-12-28 | 2019-03-28 | 50 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003033 | Scaff / Iso assists FORCE 13452 | L3 remove insulation | PCNF | PCNF | 0 | 0 | Empty | 2020-08-10 | 2026-01-08 | 2025-12-31 | 2025-12-31 | 2018-12-28 | 2019-03-28 | 60 | PCNF | PCNF | DF /G /51/DFG-20-WS-053-0046-AM-U | L3 remove insulation | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003062 | ScaffAssist to Force 9081 | L3 Tools checked for defects before use | PCNF | PCNF | 13 | 0 | Empty | 2019-11-24 | 2020-11-27 | 2019-09-12 | 2020-08-24 | 2018-12-27 | 2019-03-27 | 5 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7051-GF-U | L3 Tools checked for defects before use | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003062 | ScaffAssist to Force 9081 | L3 Tools checked for defects before use | PCNF | PCNF | 13 | 13 | Empty | 2019-11-24 | 2020-11-27 | 2019-09-09 | 2020-08-24 | 2018-12-27 | 2019-03-27 | 10 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7051-GF-U | L3 Tools checked for defects before use | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003062 | ScaffAssist to Force 9081 | L3 Tools checked for defects before use | PCNF | PCNF | 73.700000000000002842170943015 | 119.5 | Empty | 2019-11-24 | 2020-11-27 | 2019-09-09 | 2020-11-27 | 2018-12-27 | 2019-03-27 | 20 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7051-GF-U | L3 Tools checked for defects before use | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200003062 | ScaffAssist to Force 9081 | L3 Tools checked for defects before use | PCNF | PCNF | 6 | 0 | Empty | 2019-11-24 | 2020-11-27 | 2020-11-27 | 2020-11-27 | 2018-12-27 | 2019-03-27 | 30 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7051-GF-U | L3 Tools checked for defects before use | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200003062 | ScaffAssist to Force 9081 | L3 Tools checked for defects before use | PCNF | PCNF | 67 | 67 | Empty | 2019-11-24 | 2020-11-27 | 2019-11-25 | 2020-09-30 | 2018-12-27 | 2019-03-27 | 40 | PCNF | PCNF | DF /F /10/DFF-6-PHS-030-7051-GF-U | L3 Tools checked for defects before use | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 16 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-15 | 2024-09-19 | 2019-07-26 | 2019-08-15 | 5 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 3 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-21 | 2024-09-22 | 2019-07-26 | 2019-08-15 | 10 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 4 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-22 | 2024-09-23 | 2019-07-26 | 2019-08-15 | 15 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 6 | 6 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-23 | 2024-09-23 | 2019-07-26 | 2019-08-15 | 17 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 16 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-23 | 2024-09-25 | 2019-07-26 | 2019-08-15 | 20 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 6 | 24 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-25 | 2024-09-25 | 2019-07-26 | 2019-08-15 | 25 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 8 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-25 | 2024-09-26 | 2019-07-26 | 2019-08-15 | 30 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 8 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-26 | 2024-09-27 | 2019-07-26 | 2019-08-15 | 40 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 3 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-27 | 2024-09-28 | 2019-07-26 | 2019-08-15 | 50 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 4 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-28 | 2024-09-29 | 2019-07-26 | 2019-08-15 | 65 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 12 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-29 | 2024-10-02 | 2019-07-26 | 2019-08-15 | 70 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROUS | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 26 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-15 | 2024-09-21 | 2019-07-26 | 2019-08-15 | 80 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100022470 | DFCI-HCV-03350 Intern leak | L3 Scaf up for reaching DFCI-HCV-03350 | PCNF | PCNF | 0 | 0 | OIM FW EXL | 2024-09-15 | 2024-10-02 | 2024-09-15 | 2024-09-15 | 2019-07-26 | 2019-08-15 | 90 | PCNF | PCNF | DF /C /01/DFCI-HCV-03350 | L3 Scaf up for reaching DFCI-HCV-03350 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235665 | 4Y 400V N-SWB MAINT DFCI-N-1802-R01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R1-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235665 | 4Y 400V N-SWB MAINT DFCI-N-1802-R01 | ISOLATION ELECTRICAL | AWSC | AWSC | 16 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R1-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235665 | 4Y 400V N-SWB MAINT DFCI-N-1802-R01 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R1-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235665 | 4Y 400V N-SWB MAINT DFCI-N-1802-R01 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R1-01 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095055 | Monitor handel is missing | Insert new Handle | SECE | SECE | 4 | 1 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-15 | 2024-07-16 | 2023-09-06 | 2024-01-19 | 10 | SECE | SECE | DF /F /01/DFFA-A-0409 | Insert new Handle | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100095055 | Monitor handel is missing | Insert new Handle | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-16 | 2024-07-16 | 2024-07-16 | 2023-09-06 | 2024-01-19 | 20 | SECE | SECE | DF /F /01/DFFA-A-0409 | Insert new Handle | Unknown
4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100105895 | DFCC External PA Speakers replacement | Replace DFCC-PA-14-07-035 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-07-18 | 2027-01-04 | 10 |  |  | DF /C /08 | Replace DFCC-PA-14-07-035 | Unknown
4 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100105895 | DFCC External PA Speakers replacement | Replace DFCC-PA-14-07-035 |  |  | 3 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-07-18 | 2027-01-04 | 20 |  |  | DF /C /08 | Replace DFCC-PA-14-07-035 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400290935 | 6M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-11-04 | 2023-11-20 | 10 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400290935 | 6M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-11-04 | 2023-11-20 | 20 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
B | NOSD | WPM | MTN-MECH | PRODTECH | 2400290935 | 6M HPU FOR ESDV MAINT - DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-11-04 | 2023-11-20 | 30 |  |  | DF /A /07/DFAA-A-5902 | HPU FOR ESDV MAINT - DFAA-A-5902 | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400302663 | 2M CHECK AF GULVDRÆN, DFC | GENERAL INFO VEDLIGEHOLD UDEN ASSU | SCH | SCH | 0 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2024-02-01 | 2024-02-12 | 1 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-ROUS | 2400302663 | 2M CHECK AF GULVDRÆN, DFC | GENERAL INFO VEDLIGEHOLD UDEN ASSU | SCH | SCH | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2024-02-01 | 2024-02-12 | 10 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
C | NOSD | WPM | MTN-ROUS | MTN-INST | 2400302663 | 2M CHECK AF GULVDRÆN, DFC | GENERAL INFO VEDLIGEHOLD UDEN ASSU | SCH | SCH | 4 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-16 | 2024-09-17 | 2024-02-01 | 2024-02-12 | 12 | SCH | SCH | DF /C /28/DRAIN-DISPOSAL | GENERAL INFO VEDLIGEHOLD UDEN ASSU | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 2 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 3 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 4 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 10 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 20 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 22 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 23 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | INP-SITE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 18 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 25 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 12 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-01 | 2021-02-02 | 2021-07-02 | 27 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 24 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-01 | 2024-05-04 | 2021-02-02 | 2021-07-02 | 28 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | PRODTECH | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 5 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-04 | 2024-05-05 | 2021-02-02 | 2021-07-02 | 30 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 6 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-05 | 2024-05-06 | 2021-02-02 | 2021-07-02 | 40 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 1 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-06 | 2024-05-06 | 2021-02-02 | 2021-07-02 | 45 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 36 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-06 | 2024-05-07 | 2021-02-02 | 2021-07-02 | 46 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 4 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-07 | 2024-05-07 | 2021-02-02 | 2021-07-02 | 47 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 24 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-07 | 2024-05-08 | 2021-02-02 | 2021-07-02 | 48 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 1 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-08 | 2024-05-08 | 2021-02-02 | 2021-07-02 | 49 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 6 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-08 | 2024-05-09 | 2021-02-02 | 2021-07-02 | 50 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 1 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-09 | 2024-05-09 | 2021-02-02 | 2021-07-02 | 53 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 8 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-09 | 2024-05-09 | 2021-02-02 | 2021-07-02 | 55 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 1 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-09 | 2024-05-09 | 2021-02-02 | 2021-07-02 | 57 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 3 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-09 | 2024-05-10 | 2021-02-02 | 2021-07-02 | 60 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 12 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-10 | 2024-05-11 | 2021-02-02 | 2021-07-02 | 65 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 2 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-11 | 2024-05-11 | 2021-02-02 | 2021-07-02 | 67 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 6 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-11 | 2024-05-12 | 2021-02-02 | 2021-07-02 | 68 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100040998 | FFSPR Corroded hole in helifuel drain. | 2100040998-0002-2in~COATING |  |  | 0 | 0 | Empty | 2024-05-01 | 2024-05-12 | 2024-05-12 | 2024-05-12 | 2021-02-02 | 2021-07-02 | 70 |  |  | DF /C /28/DFC-2-DO-050-0472-B-U | 2100040998-0002-2in~COATING | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400351959 | 1Y DOWNHOLE GAUGE SYSTEM - DFA | DOWNHOLE GAUGE SYSTEM MAINT - DFA |  |  | 4 | 0 | W37-W38 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-09-09 | 2024-10-15 | 10 |  |  | DF /A /10/CONTROL-PANELS | DOWNHOLE GAUGE SYSTEM MAINT - DFA | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 12 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-07-29 | 2024-07-30 | 2018-10-28 | 2019-03-27 | 10 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-07-30 | 2024-07-31 | 2018-10-28 | 2019-03-27 | 20 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-INST | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-07-31 | 2024-08-01 | 2018-10-28 | 2019-03-27 | 30 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ELEC | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-01 | 2024-08-01 | 2018-10-28 | 2019-03-27 | 35 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 10 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-01 | 2024-08-02 | 2018-10-28 | 2019-03-27 | 40 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 10 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-02 | 2024-08-03 | 2018-10-28 | 2019-03-27 | 50 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-PAIN | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 10 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-05 | 2024-08-06 | 2018-10-28 | 2019-03-27 | 60 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-INST | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 2 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-08 | 2024-08-09 | 2018-10-28 | 2019-03-27 | 70 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-ELEC | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-09 | 2024-08-10 | 2018-10-28 | 2019-03-27 | 75 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 3 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-10 | 2024-08-10 | 2018-10-28 | 2019-03-27 | 80 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-RIGG | 2200003146 | Dan FF, Corroded Actuator FCV-290122 | Paint actuator on FCV-290122 - TOP COAT |  |  | 8 | 0 | W23-W24 | 2024-07-29 | 2024-08-11 | 2024-08-10 | 2024-08-11 | 2018-10-28 | 2019-03-27 | 90 |  |  | DF /F /37/DFFA-FCV-290122 | Paint actuator on FCV-290122 - TOP COAT | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100025277 | Exchange of valve and actuator. | L3 Transport valve to lower deck | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2018-08-08 | 2018-11-06 | 5 | AWSC | AWSC | DF /G /28/DFGA-XCV-500412 | L3 Transport valve to lower deck | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100025277 | Exchange of valve and actuator. | L3 Transport valve to lower deck | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2018-08-08 | 2018-11-06 | 10 | AWSC | AWSC | DF /G /28/DFGA-XCV-500412 | L3 Transport valve to lower deck | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-MECH | 2100025277 | Exchange of valve and actuator. | L3 Transport valve to lower deck | AWSC | AWSC | 12 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2018-08-08 | 2018-11-06 | 20 | AWSC | AWSC | DF /G /28/DFGA-XCV-500412 | L3 Transport valve to lower deck | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100025277 | Exchange of valve and actuator. | L3 Transport valve to lower deck | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-04 | 2018-08-08 | 2018-11-06 | 30 | AWSC | AWSC | DF /G /28/DFGA-XCV-500412 | L3 Transport valve to lower deck | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100025277 | Exchange of valve and actuator. | L3 Transport valve to lower deck | AWSC | AWSC | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2018-08-08 | 2018-11-06 | 40 | AWSC | AWSC | DF /G /28/DFGA-XCV-500412 | L3 Transport valve to lower deck | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339282 | DFF_1Y_46740 INT STRUCT INSP - GVI | DFF_1Y_46740 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/EL_46740 (WL MODULE DECK) | DFF_1Y_46740 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200017710 | Weekly/daily cleaning of sewage syst. Da | Isolate |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-04-12 | 2024-08-25 | 10 |  |  | DF /C /82/DFCM-A-5160 | Isolate | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200017710 | Weekly/daily cleaning of sewage syst. Da | Isolate |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-04-12 | 2024-08-25 | 15 |  |  | DF /C /82/DFCM-A-5160 | Isolate | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200017710 | Weekly/daily cleaning of sewage syst. Da | Isolate |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-04-12 | 2024-08-25 | 20 |  |  | DF /C /82/DFCM-A-5160 | Isolate | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200017710 | Weekly/daily cleaning of sewage syst. Da | Isolate |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-04-12 | 2024-08-25 | 30 |  |  | DF /C /82/DFCM-A-5160 | Isolate | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100058031 | Water damage on cabin 415 | PO Seacabin |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-06 | 2021-11-26 | 10 |  |  | DF /C /82 | PO Seacabin | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ACCO | 2100058031 | Water damage on cabin 415 | PO Seacabin |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2021-11-06 | 2021-11-26 | 20 |  |  | DF /C /82 | PO Seacabin | Unknown
D | NOSD | WPM | MTN-ELEC | VEN-MECH | 2400344065 | 6M COOL UNIT DFCC-A-1331 VENDOR | COOL UNIT DFCC-A-1331 VENDOR | AWSC | AWSC | 12 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-09-20 | 10 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | COOL UNIT DFCC-A-1331 VENDOR | Unknown
D | NOSD | WPM | MTN-ELEC | MTN-MECH | 2400344065 | 6M COOL UNIT DFCC-A-1331 VENDOR | COOL UNIT DFCC-A-1331 VENDOR | AWSC | AWSC | 6 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-08-26 | 2024-09-20 | 20 | AWSC | AWSC | DF /C /82/DFCC-A-1331 | COOL UNIT DFCC-A-1331 VENDOR | Unknown
3 | NE | WGN | VEN-ELEC | MTN-ELEC | 2200018126 | Replace Generator relay 1841-M102 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-06-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M102-02 | Isolation of Breaker section | Unknown
3 | NE | WGN | VEN-ELEC | VEN-ELEC | 2200018126 | Replace Generator relay 1841-M102 | Isolation of Breaker section |  |  | 1 | 0 | Empty | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-06-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M102-02 | Isolation of Breaker section | Unknown
3 | NE | WGN | VEN-ELEC | MTN-ELEC | 2200018126 | Replace Generator relay 1841-M102 | Isolation of Breaker section |  |  | 6 | 0 | Empty | 2024-06-27 | 2024-06-29 | 2024-06-27 | 2024-06-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M102-02 | Isolation of Breaker section | Unknown
3 | NE | WGN | VEN-ELEC | VEN-ELEC | 2200018126 | Replace Generator relay 1841-M102 | Isolation of Breaker section |  |  | 0 | 0 | Empty | 2024-06-27 | 2024-06-29 | 2024-06-29 | 2024-06-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M102-02 | Isolation of Breaker section | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286638 | 1Y HVAC SUPPLY AHU CHECK DFGA-A-1240 | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W31-W32 | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-01 | 2023-10-20 | 2023-11-19 | 10 | SECE | SECE | DF /G /09/DFGA-A-1240 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286638 | 1Y HVAC SUPPLY AHU CHECK DFGA-A-1240 | PERSONAL ISOLATION | SECE | SECE | 14 | 7 | W31-W32 | 2024-08-01 | 2024-08-05 | 2024-08-01 | 2024-08-04 | 2023-10-20 | 2023-11-19 | 20 | SECE | SECE | DF /G /09/DFGA-A-1240 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286638 | 1Y HVAC SUPPLY AHU CHECK DFGA-A-1240 | PERSONAL ISOLATION | SECE | SECE | 1 | 0 | W31-W32 | 2024-08-01 | 2024-08-05 | 2024-08-04 | 2024-08-04 | 2023-10-20 | 2023-11-19 | 30 | SECE | SECE | DF /G /09/DFGA-A-1240 | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286638 | 1Y HVAC SUPPLY AHU CHECK DFGA-A-1240 | PERSONAL ISOLATION | SECE | SECE | 2 | 0 | W31-W32 | 2024-08-01 | 2024-08-05 | 2024-08-05 | 2024-08-05 | 2023-10-20 | 2023-11-19 | 40 | SECE | SECE | DF /G /09/DFGA-A-1240 | PERSONAL ISOLATION | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400322632 | 1Y PRIME MOVER DFFA-MD-6101 | Assistance for vendor | AWSC | AWSC | 2 | 0 | Empty | 2024-06-10 | 2024-06-18 | 2024-06-10 | 2024-06-10 | 2024-08-30 | 2024-09-29 | 10 | AWSC | AWSC | DF /F /78/DFFA-MD-6101 | Assistance for vendor | Unknown
B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400322632 | 1Y PRIME MOVER DFFA-MD-6101 | Assistance for vendor | AWSC | AWSC | 41 | 0 | Empty | 2024-06-10 | 2024-06-18 | 2024-06-10 | 2024-06-14 | 2024-08-30 | 2024-09-29 | 20 | AWSC | AWSC | DF /F /78/DFFA-MD-6101 | Assistance for vendor | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400322632 | 1Y PRIME MOVER DFFA-MD-6101 | Assistance for vendor | AWSC | AWSC | 10 | 0 | Empty | 2024-06-10 | 2024-06-18 | 2024-06-14 | 2024-06-17 | 2024-08-30 | 2024-09-29 | 40 | AWSC | AWSC | DF /F /78/DFFA-MD-6101 | Assistance for vendor | Unknown
B | NOSD | WPM | MTN-CRAN | PRODTECH | 2400322632 | 1Y PRIME MOVER DFFA-MD-6101 | Assistance for vendor | AWSC | AWSC | 2 | 0 | Empty | 2024-06-10 | 2024-06-18 | 2024-06-17 | 2024-06-17 | 2024-08-30 | 2024-09-29 | 50 | AWSC | AWSC | DF /F /78/DFFA-MD-6101 | Assistance for vendor | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400322632 | 1Y PRIME MOVER DFFA-MD-6101 | Assistance for vendor | AWSC | AWSC | 4 | 0 | Empty | 2024-06-10 | 2024-06-18 | 2024-06-17 | 2024-06-18 | 2024-08-30 | 2024-09-29 | 60 | AWSC | AWSC | DF /F /78/DFFA-MD-6101 | Assistance for vendor | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059775 | Leak from lubrication screw on strainer | Leak from lubrication screw on strainer |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-02-22 | 2022-07-22 | 10 |  |  | DF /G /27/DFGA-S-3401 | Leak from lubrication screw on strainer | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100059775 | Leak from lubrication screw on strainer | Leak from lubrication screw on strainer |  |  | 3 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-02-22 | 2022-07-22 | 20 |  |  | DF /G /27/DFGA-S-3401 | Leak from lubrication screw on strainer | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337267 | 4Y HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | SECE | SECE | 2 | 0 | Empty | 2024-06-04 | 2024-06-08 | 2024-06-04 | 2024-06-04 | 2024-06-04 | 2024-08-16 | 10 | SECE | SECE | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400337267 | 4Y HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | SECE | SECE | 3 | 0 | Empty | 2024-06-04 | 2024-06-08 | 2024-06-04 | 2024-06-05 | 2024-06-04 | 2024-08-16 | 20 | SECE | SECE | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337267 | 4Y HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | SECE | SECE | 10 | 0 | Empty | 2024-06-04 | 2024-06-08 | 2024-06-05 | 2024-06-07 | 2024-06-04 | 2024-08-16 | 30 | SECE | SECE | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400337267 | 4Y HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | SECE | SECE | 2 | 0 | Empty | 2024-06-04 | 2024-06-08 | 2024-06-07 | 2024-06-08 | 2024-06-04 | 2024-08-16 | 40 | SECE | SECE | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400337267 | 4Y HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | SECE | SECE | 2 | 0 | Empty | 2024-06-04 | 2024-06-08 | 2024-06-08 | 2024-06-08 | 2024-06-04 | 2024-08-16 | 50 | SECE | SECE | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325768 | 3M FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | SECE | SECE | 6 | 0 | W19-W20 | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-05-24 | 2024-05-23 | 2024-06-02 | 10 | SECE | SECE | DF /C /01/FIREWATER-PUMPS | FW LIFT PUMPS MAINT-DFCM-P-0303/0304 | Unknown
3 | DFF-IPHP | WDF | MTN-INST | PRODTECH | 2100095428 | DFF ESDV-410001 hydraulic int. Leak | Isolate the line |  |  | 1 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-07 | 2024-01-20 | 10 |  |  | DF /F /31/DFFA-ESDV-410001 | Isolate the line | Unknown
3 | DFF-IPHP | WDF | MTN-INST | MTN-INST | 2100095428 | DFF ESDV-410001 hydraulic int. Leak | Isolate the line |  |  | 0.5 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-07 | 2024-01-20 | 20 |  |  | DF /F /31/DFFA-ESDV-410001 | Isolate the line | Unknown
3 | DFF-IPHP | WDF | MTN-INST | MTN-INST | 2100095428 | DFF ESDV-410001 hydraulic int. Leak | Isolate the line |  |  | 3 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-07 | 2024-01-20 | 30 |  |  | DF /F /31/DFFA-ESDV-410001 | Isolate the line | Unknown
3 | DFF-IPHP | WDF | MTN-INST | MTN-INST | 2100095428 | DFF ESDV-410001 hydraulic int. Leak | Isolate the line |  |  | 1 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-07 | 2024-01-20 | 40 |  |  | DF /F /31/DFFA-ESDV-410001 | Isolate the line | Unknown
3 | DFF-IPHP | WDF | MTN-INST | PRODTECH | 2100095428 | DFF ESDV-410001 hydraulic int. Leak | Isolate the line |  |  | 1 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-09-07 | 2024-01-20 | 50 |  |  | DF /F /31/DFFA-ESDV-410001 | Isolate the line | Unknown
4 | D-GASEXP | WDF | MTN-MECH | PRODTECH | 2100067376 | Relocate hyd panel ESDV-38097 (NOGAT) | Production Isolation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-01 | 2025-01-02 | 2022-08-15 | 2023-04-12 | 10 | AWSC | AWSC | DF /B /34/DFBA-ESDV-38097 | Production Isolation | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100067376 | Relocate hyd panel ESDV-38097 (NOGAT) | Production Isolation | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-02 | 2025-01-03 | 2022-08-15 | 2023-04-12 | 20 | AWSC | AWSC | DF /B /34/DFBA-ESDV-38097 | Production Isolation | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-MECH | 2100067376 | Relocate hyd panel ESDV-38097 (NOGAT) | Production Isolation | AWSC | AWSC | 20 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-03 | 2025-01-05 | 2022-08-15 | 2023-04-12 | 30 | AWSC | AWSC | DF /B /34/DFBA-ESDV-38097 | Production Isolation | Unknown
4 | D-GASEXP | WDF | MTN-MECH | MTN-INST | 2100067376 | Relocate hyd panel ESDV-38097 (NOGAT) | Production Isolation | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-05 | 2025-01-07 | 2022-08-15 | 2023-04-12 | 35 | AWSC | AWSC | DF /B /34/DFBA-ESDV-38097 | Production Isolation | Unknown
4 | D-GASEXP | WDF | MTN-MECH | PRODTECH | 2100067376 | Relocate hyd panel ESDV-38097 (NOGAT) | Production Isolation | AWSC | AWSC | 3 | 0 | Empty | 2025-01-01 | 2025-01-08 | 2025-01-07 | 2025-01-08 | 2022-08-15 | 2023-04-12 | 40 | AWSC | AWSC | DF /B /34/DFBA-ESDV-38097 | Production Isolation | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106039 | DFCI-TI-57684. need too be replacet. | Replace thermometer |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-03-07 | 2024-07-20 | 10 |  |  | DF /C /70/DFCM-E-5705 | Replace thermometer | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 3 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-16 | 2024-06-16 | 2023-12-16 | 2024-04-29 | 10 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 2 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-16 | 2024-06-17 | 2023-12-16 | 2024-04-29 | 20 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 4 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-17 | 2024-06-18 | 2023-12-16 | 2024-04-29 | 30 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 4 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-18 | 2024-06-19 | 2023-12-16 | 2024-04-29 | 40 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 4 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-18 | 2024-06-19 | 2023-12-16 | 2024-04-29 | 50 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 4 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-19 | 2024-06-20 | 2023-12-16 | 2024-04-29 | 60 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 2 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-20 | 2024-06-20 | 2023-12-16 | 2024-04-29 | 70 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101068 | XCV-570133 externally leaking. | Isolate XCV-570133 |  |  | 2 | 0 | Empty | 2024-06-16 | 2024-06-21 | 2024-06-20 | 2024-06-21 | 2023-12-16 | 2024-04-29 | 80 |  |  | DF /F /70/DFFA-XCV-570133 | Isolate XCV-570133 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100023965 | CMAT:Replace vacuum control valve -> at | L3 Isolate vacuum breaker |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-29 | 2018-06-27 | 2018-09-25 | 5 |  |  | DF /F /76 | L3 Isolate vacuum breaker | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100023965 | CMAT:Replace vacuum control valve -> at | L3 Isolate vacuum breaker |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-07-30 | 2018-06-27 | 2018-09-25 | 10 |  |  | DF /F /76 | L3 Isolate vacuum breaker | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023965 | CMAT:Replace vacuum control valve -> at | L3 Isolate vacuum breaker |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-30 | 2024-07-31 | 2018-06-27 | 2018-09-25 | 20 |  |  | DF /F /76 | L3 Isolate vacuum breaker | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100023965 | CMAT:Replace vacuum control valve -> at | L3 Isolate vacuum breaker |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-07-31 | 2018-06-27 | 2018-09-25 | 30 |  |  | DF /F /76 | L3 Isolate vacuum breaker | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023965 | CMAT:Replace vacuum control valve -> at | L3 Isolate vacuum breaker |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-07-31 | 2024-08-01 | 2018-06-27 | 2018-09-25 | 50 |  |  | DF /F /76 | L3 Isolate vacuum breaker | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100023965 | CMAT:Replace vacuum control valve -> at | L3 Isolate vacuum breaker |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-08-01 | 2024-08-01 | 2024-08-01 | 2018-06-27 | 2018-09-25 | 51 |  |  | DF /F /76 | L3 Isolate vacuum breaker | Unknown
4 | NOSD | WDF | MTN-INST | WELLSUPV | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-03-28 | 2024-03-28 | 2021-12-15 | 2022-05-14 | 10 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 8 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-03-28 | 2024-03-28 | 2021-12-15 | 2022-05-14 | 20 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-PIPF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 224 | 168 | Empty | 2024-03-28 | 2024-04-13 | 2024-03-29 | 2024-04-09 | 2021-12-15 | 2022-05-14 | 30 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-PIPF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 12 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-09 | 2024-04-10 | 2021-12-15 | 2022-05-14 | 40 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-PIPF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 48 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-10 | 2024-04-12 | 2021-12-15 | 2022-05-14 | 50 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-PIPF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 16 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-12 | 2024-04-13 | 2021-12-15 | 2022-05-14 | 60 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-PIPF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 4 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2021-12-15 | 2022-05-14 | 70 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-RIGG | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2021-12-15 | 2022-05-14 | 80 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-SCAF | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2021-12-15 | 2022-05-14 | 90 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100055839 | Utility & Instrument Air Batch-01 | Instrument air spools SCFM 9V corrosion | PCNF | PCNF | 0 | 0 | Empty | 2024-03-28 | 2024-04-13 | 2024-04-13 | 2024-04-13 | 2021-12-15 | 2022-05-14 | 100 | PCNF | PCNF | DF /A /07/DFA-2-AI-054-0601-A1-U | Instrument air spools SCFM 9V corrosion | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100085209 | Leak inst block PT-44002 on HP comp | Repeal inhibit Pressure transmitter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-30 | 2023-08-12 | 10 |  |  | DF /F /31/DFFA-PIT-440022 | Repeal inhibit Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100085209 | Leak inst block PT-44002 on HP comp | Repeal inhibit Pressure transmitter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-30 | 2023-08-12 | 20 |  |  | DF /F /31/DFFA-PIT-440022 | Repeal inhibit Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100085209 | Leak inst block PT-44002 on HP comp | Repeal inhibit Pressure transmitter |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-30 | 2023-08-12 | 30 |  |  | DF /F /31/DFFA-PIT-440022 | Repeal inhibit Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100085209 | Leak inst block PT-44002 on HP comp | Repeal inhibit Pressure transmitter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-30 | 2023-08-12 | 40 |  |  | DF /F /31/DFFA-PIT-440022 | Repeal inhibit Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100085209 | Leak inst block PT-44002 on HP comp | Repeal inhibit Pressure transmitter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-03-30 | 2023-08-12 | 50 |  |  | DF /F /31/DFFA-PIT-440022 | Repeal inhibit Pressure transmitter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099369 | DFF Closed drain LIT-500106 Malfunktion | Replace seals |  |  | 0.5 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-10-06 | 2023-11-20 | 10 |  |  | DF /F /28/DFFA-LIT-500106 | Replace seals | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099369 | DFF Closed drain LIT-500106 Malfunktion | Replace seals |  |  | 2.5 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-10-06 | 2023-11-20 | 20 |  |  | DF /F /28/DFFA-LIT-500106 | Replace seals | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099369 | DFF Closed drain LIT-500106 Malfunktion | Replace seals |  |  | 1 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-10-06 | 2023-11-20 | 30 |  |  | DF /F /28/DFFA-LIT-500106 | Replace seals | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100099369 | DFF Closed drain LIT-500106 Malfunktion | Replace seals |  |  | 1 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-10-06 | 2023-11-20 | 40 |  |  | DF /F /28/DFFA-LIT-500106 | Replace seals | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100099369 | DFF Closed drain LIT-500106 Malfunktion | Replace seals |  |  | 2.5 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-10-06 | 2023-11-20 | 50 |  |  | DF /F /28/DFFA-LIT-500106 | Replace seals | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-05 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 10 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | WELLSUPV | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 13 | 13 | Empty | 2024-09-15 | 2024-09-17 | 2019-09-11 | 2023-08-18 | 2019-07-11 | 2019-07-31 | 15 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 20.100000000000001421085471515 | 20 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-05 | 2023-08-18 | 2019-07-11 | 2019-07-31 | 16 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-SCAF | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 126.59999999999999431565811388 | 79 | Empty | 2024-09-15 | 2024-09-17 | 2019-09-11 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 20 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 60.29999999999999715782905694 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-10 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 25 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 100.5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-10 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 30 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-10 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 31 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 60.29999999999999715782905694 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-07 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 32 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 69.700000000000002842170943015 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-16 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 33 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 20.100000000000001421085471515 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-18 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 34 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 40.20000000000000284217094303 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-18 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 35 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 20.100000000000001421085471515 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2023-08-18 | 2023-09-20 | 2019-07-11 | 2019-07-31 | 36 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 33.5 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-17 | 2019-07-11 | 2019-07-31 | 40 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | MTN-ROPE | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 10.099999999999999644728632116 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-16 | 2019-07-11 | 2019-07-31 | 50 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | VEN-MECH | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2019-07-11 | 2019-07-31 | 60 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
3 | DHDLPGAS | WDF | MTN-MECH | VEN-MECH | 2100024394 | ANOP Replacement of 12"PHS+ check valve | Permit for 12" PHS spool replacement | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-17 | 2024-09-15 | 2024-09-15 | 2019-07-11 | 2019-07-31 | 70 | PCNFAWSC | PCNFAWSC | DF /F /12/DFF-12-PHS-038-9004-AB-U | Permit for 12" PHS spool replacement | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100075417 | DFC XCV-34308 skal fjernes | Remove XCV and Check Valve |  |  | 4 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2023-03-27 | 2025-09-12 | 10 |  |  | DF /C /27/DFCM-XCV-34308 | Remove XCV and Check Valve | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100075417 | DFC XCV-34308 skal fjernes | Remove XCV and Check Valve |  |  | 3 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2023-03-27 | 2025-09-12 | 20 |  |  | DF /C /27/DFCM-XCV-34308 | Remove XCV and Check Valve | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100075417 | DFC XCV-34308 skal fjernes | Remove XCV and Check Valve |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-20 | 2023-03-27 | 2025-09-12 | 30 |  |  | DF /C /27/DFCM-XCV-34308 | Remove XCV and Check Valve | Unknown
4 | DFC-TSEP | WDF | MTN-MECH | MTN-MECH | 2100075417 | DFC XCV-34308 skal fjernes | Remove XCV and Check Valve |  |  | 2 | 0 | Empty | 2024-09-18 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2023-03-27 | 2025-09-12 | 40 |  |  | DF /C /27/DFCM-XCV-34308 | Remove XCV and Check Valve | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339039 | DFA_1Y_26200 INT STRUCT INSP - GVI | DFA_1Y_26200 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /86/EL_26200 (MEZZANINE DECK) | DFA_1Y_26200 INT STRUCT INSP - GVI | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344061 | 3Y FIRE DAMPER CHECK - DFF | PERSONAL ISOLATION | SECE | SECE | 5 | 5 | W29-W30 | 2024-07-23 | 2024-07-30 | 2024-07-23 | 2024-07-24 | 2024-07-23 | 2024-09-23 | 10 | SECE | SECE | DF /F /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344061 | 3Y FIRE DAMPER CHECK - DFF | PERSONAL ISOLATION | SECE | SECE | 12 | 12 | W29-W30 | 2024-07-23 | 2024-07-30 | 2024-07-24 | 2024-07-27 | 2024-07-23 | 2024-09-23 | 20 | SECE | SECE | DF /F /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344061 | 3Y FIRE DAMPER CHECK - DFF | PERSONAL ISOLATION | SECE | SECE | 5 | 5 | W29-W30 | 2024-07-23 | 2024-07-30 | 2024-07-27 | 2024-07-28 | 2024-07-23 | 2024-09-23 | 30 | SECE | SECE | DF /F /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400344061 | 3Y FIRE DAMPER CHECK - DFF | PERSONAL ISOLATION | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-23 | 2024-07-30 | 2024-07-28 | 2024-07-28 | 2024-07-23 | 2024-09-23 | 40 | SECE | SECE | DF /F /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-TELE | 2400344061 | 3Y FIRE DAMPER CHECK - DFF | PERSONAL ISOLATION | SECE | SECE | 4 | 7 | W29-W30 | 2024-07-23 | 2024-07-30 | 2024-07-28 | 2024-07-29 | 2024-07-23 | 2024-09-23 | 50 | SECE | SECE | DF /F /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ROPE | 2400344061 | 3Y FIRE DAMPER CHECK - DFF | PERSONAL ISOLATION | SECE | SECE | 4 | 0 | W29-W30 | 2024-07-23 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-07-23 | 2024-09-23 | 60 | SECE | SECE | DF /F /09/FIRE-DAMPERS | PERSONAL ISOLATION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079313 | HCV 380015 Local indicator stuck | Report findings to sys. resp. for next A |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-06-10 | 2025-11-26 | 10 |  |  | DF /F /54/DFFA-HCV-380015 | Report findings to sys. resp. for next A | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079313 | HCV 380015 Local indicator stuck | Report findings to sys. resp. for next A |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-06-10 | 2025-11-26 | 20 |  |  | DF /F /54/DFFA-HCV-380015 | Report findings to sys. resp. for next A | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | PRODTECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 2 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 10 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | PRODTECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 2 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 20 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | MTN-RIGG | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 24 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 30 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | MTN-MECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 5 | 6 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 40 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | MTN-MECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 0 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 50 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | MTN-RIGG | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 12 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 60 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | PRODTECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 2 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 70 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | MTN-MECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 5 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 80 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | PRODTECH | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 4 | 0 | W29-30 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-03 | 2025-11-19 | 90 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
4 | DFGHPSEP | WGN | MTN-MECH | MTN-ROPE | 2200012644 | DFGA-VAB-500867 - PSV 2023 | Rigging assist (remove) | PCNF | PCNF | 2 | 2 | W29-30 | 2024-09-22 | 2024-09-22 | 2023-07-12 | 2023-07-16 | 2023-06-03 | 2025-11-19 | 100 | PCNF | PCNF | DF /G /27/DFGA-VAB-500867 | Rigging assist (remove) | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325732 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59180 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59180 |  |  | 3 | 0 | Empty | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-10-05 | 2024-04-26 | 2024-06-01 | 10 |  |  | DF /A /07/DFAA-FP-59180 | 1Y HYDRAULIC VLV CONTROL PANEL FP-59180 | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100059697 | DFF Sacale level / weight tank transmitt | Clean the lines |  |  | 0.5 | 0 | W25-W26 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /F /75/DFFA-LIT-398200 | Clean the lines | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100059697 | DFF Sacale level / weight tank transmitt | Clean the lines |  |  | 1 | 0 | W25-W26 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /F /75/DFFA-LIT-398200 | Clean the lines | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100059697 | DFF Sacale level / weight tank transmitt | Clean the lines |  |  | 1 | 0 | W25-W26 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /F /75/DFFA-LIT-398200 | Clean the lines | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100059697 | DFF Sacale level / weight tank transmitt | Clean the lines |  |  | 0.5 | 0 | W25-W26 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /F /75/DFFA-LIT-398200 | Clean the lines | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235777 | 4Y 400V N-SWB MAINT-DFFB-N-1828-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828-08 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235777 | 4Y 400V N-SWB MAINT-DFFB-N-1828-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 28 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-22 | 2024-09-29 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828-08 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235777 | 4Y 400V N-SWB MAINT-DFFB-N-1828-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 9 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-09-29 | 2024-10-01 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828-08 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235777 | 4Y 400V N-SWB MAINT-DFFB-N-1828-8 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828-08 | ISOLATION ELECTRICAL | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001382 | DK40 - erstattes af 2300002153 - PPE | DK40 - CONSUMABLE PROD - PPE |  |  | 0 | 0 | Empty | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-09-09 | 2021-07-06 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - PPE | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300001382 | DK40 - erstattes af 2300002153 - PPE | DK40 - CONSUMABLE PROD - PPE |  |  | 0 | 0 | Empty | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-09-09 | 2021-07-06 | 20 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - PPE | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2020-09-01 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 3 | Empty | 2026-01-01 | 2026-01-02 | 2020-08-23 | 2020-09-01 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 60 | 34.5 | Empty | 2026-01-01 | 2026-01-02 | 2020-08-17 | 2020-09-10 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 12.099999999999999644728632116 | 29 | Empty | 2026-01-01 | 2026-01-02 | 2020-08-24 | 2020-09-04 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 18 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-02 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 12.099999999999999644728632116 | 81.75 | Empty | 2026-01-01 | 2026-01-02 | 2020-08-18 | 2021-04-05 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 40.20000000000000284217094303 | 39.5 | Empty | 2026-01-01 | 2026-01-02 | 2021-03-17 | 2021-04-05 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002920 | DFG-Insulation assists FORCE 13514. | L3 Prepare Permit Scaff | PCNF | PCNF | 0 | 0 | Empty | 2026-01-01 | 2026-01-02 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /G /31/DFG-20-GPS-043-0014-DO-A | L3 Prepare Permit Scaff | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009251 | Insulation assist Bilfinger 21489(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-27 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /F /55/DFF-6-WI-035-7307-GF-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009251 | Insulation assist Bilfinger 21489(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-27 | 2023-03-28 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /F /55/DFF-6-WI-035-7307-GF-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009251 | Insulation assist Bilfinger 21489(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-28 | 2023-03-28 | 2022-02-09 | 2022-07-09 | 22 |  |  | DF /F /55/DFF-6-WI-035-7307-GF-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009251 | Insulation assist Bilfinger 21489(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-03-31 | 2023-03-28 | 2023-03-31 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /F /55/DFF-6-WI-035-7307-GF-T | Bilfinger inspection | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400344035 | 6M PRIME MOVER DFCI-MD-6101 | PRIME MOVER MAINTENANCE DFCI-MD-6101 |  |  | 15 | 0 | Empty | 2024-11-21 | 2024-11-25 | 2024-11-21 | 2024-11-24 | 2024-11-21 | 2024-12-07 | 10 |  |  | DF /C /78/DFCI-MD-6101 | PRIME MOVER MAINTENANCE DFCI-MD-6101 | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-MECH | 2400344035 | 6M PRIME MOVER DFCI-MD-6101 | PRIME MOVER MAINTENANCE DFCI-MD-6101 |  |  | 2 | 0 | Empty | 2024-11-21 | 2024-11-25 | 2024-11-24 | 2024-11-25 | 2024-11-21 | 2024-12-07 | 20 |  |  | DF /C /78/DFCI-MD-6101 | PRIME MOVER MAINTENANCE DFCI-MD-6101 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235606 | 4Y 380V N-SWB-DFFA-N-1802A-12 | ISOLATION ELECTRICAL | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 10 | PCNF | PCNF | DF /F /61/DFFA-N-1802A-12 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235606 | 4Y 380V N-SWB-DFFA-N-1802A-12 | ISOLATION ELECTRICAL | PCNF | PCNF | 39 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 20 | PCNF | PCNF | DF /F /61/DFFA-N-1802A-12 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235606 | 4Y 380V N-SWB-DFFA-N-1802A-12 | ISOLATION ELECTRICAL | PCNF | PCNF | 13 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 30 | PCNF | PCNF | DF /F /61/DFFA-N-1802A-12 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235606 | 4Y 380V N-SWB-DFFA-N-1802A-12 | ISOLATION ELECTRICAL | PCNF | PCNF | 1 | 0 | Empty | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-07-12 | 40 | PCNF | PCNF | DF /F /61/DFFA-N-1802A-12 | ISOLATION ELECTRICAL | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 10 | 32 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 10 | 31 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-INST | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 7 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 0.5 | 12 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 332 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 333 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 334 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 8 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 335 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 10 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 345 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 355 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 365 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 375 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | DFF-OIL | WDF | MTN-MECH | MTN-MECH | 2100052316 | DFF Hydro cyclon outlet XCV stock | Isolate pneumatic and controls | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | Empty | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2025-01-01 | 2021-07-08 | 2021-07-28 | 385 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /27/DFFA-XCV-500722 | Isolate pneumatic and controls | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 0 | Empty | 2022-04-17 | 2026-01-01 | 2020-09-16 | 2020-10-16 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 8.699999999999999289457264236 | 7.5 | Empty | 2022-04-17 | 2026-01-01 | 2020-08-29 | 2020-09-16 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 54 | 36.5 | Empty | 2022-04-17 | 2026-01-01 | 2020-08-19 | 2020-11-27 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 6 | 26.5 | Empty | 2022-04-17 | 2026-01-01 | 2020-08-29 | 2020-09-16 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 9 | 0 | Empty | 2022-04-17 | 2026-01-01 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 6 | 39.5 | Empty | 2022-04-17 | 2026-01-01 | 2020-09-16 | 2021-01-12 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 26 | 0 | Empty | 2022-04-17 | 2026-01-01 | 2022-04-17 | 2022-04-18 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002918 | DFE-Insulation assists FORCE 13370. | L3 Prepare Permit Scaff | PCNF | PCNF | 0 | 0 | Empty | 2022-04-17 | 2026-01-01 | 2020-09-16 | 2021-02-24 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /E /55/DFE-6-WI-035-5011-FE-U | L3 Prepare Permit Scaff | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 4 | Empty | 2024-11-29 | 2024-12-13 | 2020-12-21 | 2023-10-05 | 2020-11-18 | 2020-12-08 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 3 | Empty | 2024-11-29 | 2024-12-13 | 2020-12-21 | 2023-10-05 | 2020-11-18 | 2020-12-08 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 3 | Empty | 2024-11-29 | 2024-12-13 | 2020-12-22 | 2023-10-05 | 2020-11-18 | 2020-12-08 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | VEN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 12 | Empty | 2024-11-29 | 2024-12-13 | 2020-12-22 | 2023-10-05 | 2020-11-18 | 2020-12-08 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 130 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 139 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-29 | 2020-11-18 | 2020-12-08 | 140 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-RIGG | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 8 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-29 | 2024-11-30 | 2020-11-18 | 2020-12-08 | 150 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 8 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-11-30 | 2024-12-01 | 2020-11-18 | 2020-12-08 | 160 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 8 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-01 | 2024-12-02 | 2020-11-18 | 2020-12-08 | 161 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-02 | 2024-12-02 | 2020-11-18 | 2020-12-08 | 168 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-02 | 2024-12-03 | 2020-11-18 | 2020-12-08 | 169 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-03 | 2024-12-05 | 2020-11-18 | 2020-12-08 | 170 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-05 | 2024-12-06 | 2020-11-18 | 2020-12-08 | 179 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-06 | 2024-12-07 | 2020-11-18 | 2020-12-08 | 180 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-07 | 2024-12-09 | 2020-11-18 | 2020-12-08 | 181 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 6 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-09 | 2024-12-10 | 2020-11-18 | 2020-12-08 | 189 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 6 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-10 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 190 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 6 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 191 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 199 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 200 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 210 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 220 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 230 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-11 | 2020-11-18 | 2020-12-08 | 240 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-ROPE | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 9 | 9 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-11 | 2024-12-13 | 2020-11-18 | 2020-12-08 | 250 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2020-11-18 | 2020-12-08 | 260 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2020-11-18 | 2020-12-08 | 270 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-MECH | 2100041176 | ESDV-38169 failing inflow test DGS 63863 | Line for sending S.Tools & Internals off | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-11-29 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2020-11-18 | 2020-12-08 | 280 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /A /12/DFAA-ESDV-38169 | Line for sending S.Tools & Internals off | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-RIGG | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 6 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | PRODTECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 3 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 30 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-RIGG | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 12 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-INST | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 9 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | PRODTECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 1 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-RIGG | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 4 | W23-24 | 2024-09-15 | 2024-09-15 | 2023-03-02 | 2023-11-22 | 2023-02-26 | 2023-04-12 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-02-26 | 2023-04-12 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 6 | 44 | W23-24 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-02-26 | 2023-04-12 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 0 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-02-26 | 2023-04-12 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
2 | DFF-O32 | WDF | MTN-MECH | MTN-MECH | 2100086259 | DFF-32 choke internal broken. CVA300732 | Rig up hoist equipment | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 0 | W23-24 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2023-02-26 | 2023-04-12 | 130 | PCNFAWSCSCH | PCNFAWSCSCH | DF /F /10/DFFA-CVA-300732 | Rig up hoist equipment | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322645 | 2Y 24V UPS.SYST BATT & CHAR F.TEST-DFC | 24V UPS.SYST BATT & CHAR F.TEST-DFC | AWSCSCHSECE | AWSCSCHSECE | 24 | 0 | W25-W26 | 2024-06-28 | 2024-07-03 | 2024-06-28 | 2024-07-03 | 2024-04-01 | 2024-05-17 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /06/UPS-SYSTEM-2 | 24V UPS.SYST BATT & CHAR F.TEST-DFC | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100106536 | DFE DM-0320 malfunction thermometer TI-0 | DM-0320 engine isolated |  |  | 1.5 | 0 | Empty | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-05-16 | 2024-03-15 | 2024-07-28 | 10 |  |  | DF /E /01/DFEY-DM-0320 | DM-0320 engine isolated | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100106536 | DFE DM-0320 malfunction thermometer TI-0 | DM-0320 engine isolated |  |  | 3 | 0 | Empty | 2024-05-15 | 2024-05-16 | 2024-05-15 | 2024-05-16 | 2024-03-15 | 2024-07-28 | 20 |  |  | DF /E /01/DFEY-DM-0320 | DM-0320 engine isolated | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100106536 | DFE DM-0320 malfunction thermometer TI-0 | DM-0320 engine isolated |  |  | 1 | 0 | Empty | 2024-05-15 | 2024-05-16 | 2024-05-16 | 2024-05-16 | 2024-03-15 | 2024-07-28 | 30 |  |  | DF /E /01/DFEY-DM-0320 | DM-0320 engine isolated | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2020-07-05 | 2022-06-25 | 10 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2020-07-05 | 2022-06-25 | 20 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2020-07-05 | 2022-06-25 | 30 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2020-07-05 | 2022-06-25 | 40 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2020-07-05 | 2022-06-25 | 50 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-17 | 2020-07-05 | 2022-06-25 | 60 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
4 | DFE-3551 | WDF | MTN-MECH | MTN-MECH | 2100023110 | DFE FCV-35549 Luft lækage. | Isolate pneumatic/controls |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2020-07-05 | 2022-06-25 | 70 |  |  | DF /E /51/DFEY-FCV-35549 | Isolate pneumatic/controls | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200002981 | DFE ESDV-45004 hyd rør, dårlig suppor | L3 Production of support for hydraulic p |  |  | 6.700000000000000177635683938 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2018-05-30 | 2018-07-09 | 10 |  |  | DF /E /37/DFEZ-ESDV-45004 | L3 Production of support for hydraulic p | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200002981 | DFE ESDV-45004 hyd rør, dårlig suppor | L3 Production of support for hydraulic p |  |  | 2 | 0 | W27-W28 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2018-05-30 | 2018-07-09 | 20 |  |  | DF /E /37/DFEZ-ESDV-45004 | L3 Production of support for hydraulic p | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-01-31 | 2022-09-28 | 10 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2022-01-31 | 2022-09-28 | 20 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2022-01-31 | 2022-09-28 | 30 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-01-31 | 2022-09-28 | 31 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-01-31 | 2022-09-28 | 40 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-01-31 | 2022-09-28 | 50 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100056882 | Replace tubing for PI-350465 (INST-TUBF) | operation_description_not_present |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2022-01-31 | 2022-09-28 | 60 |  |  | DF /G /54/DFGA-PI-350465 | operation_description_not_present | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100101424 | Kileremme på DFC-C-5409 knækket | Materials |  |  | 1 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2024-04-28 | 2026-10-15 | 10 |  |  | DF /C /07/DFCM-CM-5409 | Materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101424 | Kileremme på DFC-C-5409 knækket | Materials |  |  | 5 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-26 | 2024-08-27 | 2024-04-28 | 2026-10-15 | 20 |  |  | DF /C /07/DFCM-CM-5409 | Materials | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100101424 | Kileremme på DFC-C-5409 knækket | Materials |  |  | 1 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-27 | 2024-08-28 | 2024-04-28 | 2026-10-15 | 30 |  |  | DF /C /07/DFCM-CM-5409 | Materials | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101424 | Kileremme på DFC-C-5409 knækket | Materials |  |  | 0 | 0 | Empty | 2024-08-26 | 2024-08-28 | 2024-08-28 | 2024-08-28 | 2024-04-28 | 2026-10-15 | 40 |  |  | DF /C /07/DFCM-CM-5409 | Materials | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112432 | DFCC-STR-0650 new harness | DFCC-STR-0650 Replace harness |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2024-06-24 | 2024-11-06 | 10 |  |  | DF /C /02/DFCI-STR-0642 | DFCC-STR-0650 Replace harness | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235631 | 4Y 380V N-SWB MAINT-DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235631 | 4Y 380V N-SWB MAINT-DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | AWSC | AWSC | 18 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235631 | 4Y 380V N-SWB MAINT-DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-28 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235631 | 4Y 380V N-SWB MAINT-DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803 | 380V N-SWB INSP-DFFA-N-1803 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 24 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-20 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-22 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 9 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-23 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 1 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-23 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 51 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-06-22 | 2024-06-23 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 12 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-08-20 | 2024-08-21 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-08-21 | 2024-08-22 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-08-21 | 2024-08-23 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-08-21 | 2024-08-21 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-08-21 | 2024-08-21 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284304 | PSV Calibration - DFGA-PSV-410423B | Backload PSV to Norspie Workshop | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-06-20 | 2024-08-23 | 2024-08-21 | 2024-08-21 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /30/DFGA-PSV-410423B | Backload PSV to Norspie Workshop | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096580 | DFG-LCV-400402 på flare drum, bælg defek | Isolate LCV |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2023-10-06 | 10 |  |  | DF /G /36/DFGA-LCV-400402 | Isolate LCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096580 | DFG-LCV-400402 på flare drum, bælg defek | Isolate LCV |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2023-10-06 | 20 |  |  | DF /G /36/DFGA-LCV-400402 | Isolate LCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096580 | DFG-LCV-400402 på flare drum, bælg defek | Isolate LCV |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2023-10-06 | 30 |  |  | DF /G /36/DFGA-LCV-400402 | Isolate LCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096580 | DFG-LCV-400402 på flare drum, bælg defek | Isolate LCV |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2023-10-06 | 40 |  |  | DF /G /36/DFGA-LCV-400402 | Isolate LCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096580 | DFG-LCV-400402 på flare drum, bælg defek | Isolate LCV |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2023-10-06 | 50 |  |  | DF /G /36/DFGA-LCV-400402 | Isolate LCV | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100096580 | DFG-LCV-400402 på flare drum, bælg defek | Isolate LCV |  |  | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-08-22 | 2023-10-06 | 60 |  |  | DF /G /36/DFGA-LCV-400402 | Isolate LCV | Unknown
3 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 0 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-01-09 | 2023-01-09 | 2018-09-07 | 2018-12-06 | 10 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 180 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-01-09 | 2023-01-31 | 2018-09-07 | 2018-12-06 | 20 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 16 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-01-31 | 2023-02-02 | 2018-09-07 | 2018-12-06 | 30 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 21 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-02 | 2023-02-04 | 2018-09-07 | 2018-12-06 | 40 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 6 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-04 | 2023-02-05 | 2018-09-07 | 2018-12-06 | 50 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 32 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-05 | 2023-02-09 | 2018-09-07 | 2018-12-06 | 60 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 32 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-09 | 2023-02-11 | 2018-09-07 | 2018-12-06 | 70 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 64 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-11 | 2023-02-19 | 2018-09-07 | 2018-12-06 | 80 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 64 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-19 | 2023-02-22 | 2018-09-07 | 2018-12-06 | 90 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-MECH | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 6 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-22 | 2023-02-23 | 2018-09-07 | 2018-12-06 | 100 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 80 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-23 | 2023-02-27 | 2018-09-07 | 2018-12-06 | 110 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | VEN-ELEC | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 20 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-02-27 | 2023-03-01 | 2018-09-07 | 2018-12-06 | 120 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-LAGG | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 58 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-03-01 | 2023-03-07 | 2018-09-07 | 2018-12-06 | 130 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-RIGG | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 16 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-03-07 | 2023-03-09 | 2018-09-07 | 2018-12-06 | 140 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-SCAF | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 80 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-03-09 | 2023-03-19 | 2018-09-07 | 2018-12-06 | 150 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-MECH | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 0 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-03-19 | 2023-03-19 | 2018-09-07 | 2018-12-06 | 160 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
3 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100023744 | ANOP Change spool 2"-DO-50506-B-F | RW6 Change spool 2"-DO-50506-B-F |  |  | 0 | 0 | Empty | 2023-01-09 | 2023-03-19 | 2023-03-19 | 2023-03-19 | 2018-09-07 | 2018-12-06 | 170 |  |  | DF /C /28/DFCM-P-5006 | RW6 Change spool 2"-DO-50506-B-F | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-15 | 2024-09-18 | 2023-05-26 | 2023-07-01 | 10 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
C | NOSD | WPM | MTN-MECH | WELLSUPV | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 100 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-18 | 2024-09-24 | 2023-05-26 | 2023-07-01 | 20 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 48 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-24 | 2024-09-27 | 2023-05-26 | 2023-07-01 | 30 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
C | NOSD | WPM | MTN-MECH | WELLSUPV | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 50 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-09-27 | 2024-09-30 | 2023-05-26 | 2023-07-01 | 40 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-10-01 | 2024-10-03 | 2023-05-26 | 2023-07-01 | 50 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-05-26 | 2023-07-01 | 60 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259830 | 1Y HYDRO/SAND CYCONER DFGA-5062/5066 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2023-05-26 | 2023-07-01 | 70 |  |  | DF /G /27/DFGA-A-5060 | TL-1Y HYDRO/SAND CYCONER DFGA-5062/5066 | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 4 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 10 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 4.4000000000000003552713678785 | 1 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-06-12 | 2014-11-09 | 20 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-06-12 | 2014-11-09 | 30 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-06-12 | 2014-11-09 | 40 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-06-12 | 2014-11-09 | 45 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 17.399999999999998578914528472 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2014-06-12 | 2014-11-09 | 50 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 60 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 70 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 80 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 2.7000000000000001776356839392 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 85 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | PRODTECH | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 90 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-PIPF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 4.700000000000000177635683938 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2014-06-12 | 2014-11-09 | 100 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | DFF-OIL | WDF | MTN-MECH | MTN-SCAF | 2100023804 | DFF-06 OIL XCV-301306 intern læk | Clean-up | PCNFAWSC | PCNFAWSC | 4.700000000000000177635683938 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2014-06-12 | 2014-11-09 | 110 | PCNFAWSC | PCNFAWSC | DF /F /10/DFFA-XCV-301306 | Clean-up | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100094374 | SDBB leaking DFCI-PIT-37145 | Isolatepressure transmitter |  |  | 2.5 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-01-05 | 2026-06-23 | 10 |  |  | DF /C /26/DFCI-PIT-37145 | Isolatepressure transmitter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100094374 | SDBB leaking DFCI-PIT-37145 | Isolatepressure transmitter |  |  | 1.5 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-01-05 | 2026-06-23 | 20 |  |  | DF /C /26/DFCI-PIT-37145 | Isolatepressure transmitter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100094374 | SDBB leaking DFCI-PIT-37145 | Isolatepressure transmitter |  |  | 2.5 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-01-05 | 2026-06-23 | 30 |  |  | DF /C /26/DFCI-PIT-37145 | Isolatepressure transmitter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100094374 | SDBB leaking DFCI-PIT-37145 | Isolatepressure transmitter |  |  | 2 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-01-05 | 2026-06-23 | 40 |  |  | DF /C /26/DFCI-PIT-37145 | Isolatepressure transmitter | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100094374 | SDBB leaking DFCI-PIT-37145 | Isolatepressure transmitter |  |  | 1.5 | 0 | Empty | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-01-05 | 2026-06-23 | 50 |  |  | DF /C /26/DFCI-PIT-37145 | Isolatepressure transmitter | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | MTN-PIPF | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-05-09 | 2019-05-04 | 10 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | MTN-SCAF | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 5.4000000000000003552713678785 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-05-09 | 2019-05-04 | 20 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | PRODTECH | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-01 | 2018-05-09 | 2019-05-04 | 30 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | MTN-SCAF | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 6.700000000000000177635683938 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2018-05-09 | 2019-05-04 | 40 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | MTN-PIPF | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 6.700000000000000177635683938 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-05-09 | 2019-05-04 | 50 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | PRODTECH | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-02 | 2025-01-02 | 2018-05-09 | 2019-05-04 | 60 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | MTN-SCAF | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-03 | 2018-05-09 | 2019-05-04 | 70 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | DFX-OIL | WGN | MTN-PIPF | MTN-PIPF | 2200003055 | CMAT:DFC, replacement of checkvalve | Checking of the received materials | AWSC | AWSC | 8 | 0 | Empty | 2025-01-01 | 2025-01-03 | 2025-01-01 | 2025-01-02 | 2018-05-09 | 2019-05-04 | 80 | AWSC | AWSC | DF /C /10 | Checking of the received materials | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055729 | Defekt 3" HCV på sand header DFF | Rigging assist.Rig in/out (If needed) |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-16 | 2021-12-13 | 2022-05-12 | 10 |  |  | DF /F /27 | Rigging assist.Rig in/out (If needed) | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100055729 | Defekt 3" HCV på sand header DFF | Rigging assist.Rig in/out (If needed) |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-16 | 2021-12-13 | 2022-05-12 | 20 |  |  | DF /F /27 | Rigging assist.Rig in/out (If needed) | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055729 | Defekt 3" HCV på sand header DFF | Rigging assist.Rig in/out (If needed) |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-16 | 2024-09-17 | 2021-12-13 | 2022-05-12 | 30 |  |  | DF /F /27 | Rigging assist.Rig in/out (If needed) | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100055729 | Defekt 3" HCV på sand header DFF | Rigging assist.Rig in/out (If needed) |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-17 | 2024-09-18 | 2021-12-13 | 2022-05-12 | 40 |  |  | DF /F /27 | Rigging assist.Rig in/out (If needed) | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100055729 | Defekt 3" HCV på sand header DFF | Rigging assist.Rig in/out (If needed) |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-18 | 2024-09-18 | 2021-12-13 | 2022-05-12 | 50 |  |  | DF /F /27 | Rigging assist.Rig in/out (If needed) | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235799 | 4Y 380V N-SWB MAINT-DFBA-N-1810-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-28 | 10 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_04 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235799 | 4Y 380V N-SWB MAINT-DFBA-N-1810-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 20 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_04 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235799 | 4Y 380V N-SWB MAINT-DFBA-N-1810-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-24 | 2024-09-24 | 2023-01-30 | 2023-04-28 | 30 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_04 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235799 | 4Y 380V N-SWB MAINT-DFBA-N-1810-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-01-30 | 2023-04-28 | 40 | AWSC | AWSC | DF /B /61/DFBA-N-1810-C_04 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400328720 | 1Y FIRE DOORS TEST - DFB | FIRE DOORS TEST - DFB | SECE | SECE | 7 | 0 | Empty | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-05-06 | 2024-06-05 | 10 | SECE | SECE | DF /B /02/FIRE-DOORS | FIRE DOORS TEST - DFB | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 0 | 0 | Empty | 2024-06-26 | 2024-07-02 | 2024-06-26 | 2024-06-26 | 2023-04-30 | 2023-12-31 | 10 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 21 | 9 | Empty | 2024-06-26 | 2024-07-02 | 2024-06-26 | 2024-06-26 | 2023-04-30 | 2023-12-31 | 20 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 24 | 0 | Empty | 2024-06-26 | 2024-07-02 | 2024-06-26 | 2024-06-27 | 2023-04-30 | 2023-12-31 | 30 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 12 | 0 | Empty | 2024-06-26 | 2024-07-02 | 2024-06-27 | 2024-06-28 | 2023-04-30 | 2023-12-31 | 40 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 32 | 30 | Empty | 2024-06-26 | 2024-07-02 | 2024-06-28 | 2024-06-30 | 2023-04-30 | 2023-12-31 | 50 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 32 | 30 | Empty | 2024-06-26 | 2024-07-02 | 2024-06-30 | 2024-07-02 | 2023-04-30 | 2023-12-31 | 60 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PIPF | 2100077171 | FLM DFE - Rep. Handr./Steps ST024 EL. 26 | Prepare worksite | PCNF | PCNF | 21 | 0 | Empty | 2024-06-26 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2023-04-30 | 2023-12-31 | 70 | PCNF | PCNF | DF /E /86/26200 - HANDRAILS | Prepare worksite | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100085369 | DFF-33 Choke not able to operate | operation_description_not_present |  |  | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-17 | 2023-07-30 | 10 |  |  | DF /F /55/DFFA-CVA-300733 | operation_description_not_present | Unknown
3 | SIWL | WDF | MTN-MECH | MTN-INST | 2100085369 | DFF-33 Choke not able to operate | operation_description_not_present |  |  | 0 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-17 | 2023-07-30 | 20 |  |  | DF /F /55/DFFA-CVA-300733 | operation_description_not_present | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400308564 | 3Y ATEX INSPECTION DF PLATFORM F/AREA-4 | ATEX EQUIPMENT INSPECTION | AWSCSECE | AWSCSECE | 31 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2024-01-15 | 2024-03-17 | 10 | AWSCSECE | AWSCSECE | DF /F /63/ATEX-EARTH-AREA-4 | ATEX EQUIPMENT INSPECTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235842 | 4Y 400V E-SWB MAINT DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-08-26 | 10 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235842 | 4Y 400V E-SWB MAINT DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | AWSC | AWSC | 14 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-08-26 | 20 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235842 | 4Y 400V E-SWB MAINT DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 30 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235842 | 4Y 400V E-SWB MAINT DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-06-14 | 2023-08-26 | 40 | AWSC | AWSC | DF /G /05/DFGA-N-1843-A04 | 400V E-SWB MAINT DFGA-N-1843-A04 | Unknown
A | DFB-OIL | WPM | MTN-MECH | PRODTECH | 2400214776 | 1Y SDV LUBE/FUNC TEST OIL - DFB | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-10-04 | 2022-11-03 | 10 | SECE | SECE | DF /B /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFB-OIL | WPM | MTN-MECH | MTN-MECH | 2400214776 | 1Y SDV LUBE/FUNC TEST OIL - DFB | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2022-10-04 | 2022-11-03 | 20 | SECE | SECE | DF /B /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFB-OIL | WPM | MTN-MECH | PRODTECH | 2400214776 | 1Y SDV LUBE/FUNC TEST OIL - DFB | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2022-10-04 | 2022-11-03 | 30 | SECE | SECE | DF /B /03/SDV-VALVES | ISOLATION BY PRODUCTION | Unknown
A | DFC-1630 | WPM | MTN-MECH | PRODTECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | PRODTECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-RIGG | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 24 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-20 | 2024-10-22 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-MECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-23 | 2024-10-24 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-MECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-24 | 2024-10-24 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-MECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-24 | 2024-10-25 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-RIGG | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 12 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-25 | 2024-10-27 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | PRODTECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-27 | 2024-10-27 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-MECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 5 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-27 | 2024-10-28 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | PRODTECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 4 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-29 | 2024-10-29 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | MTN-MECH | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-29 | 2024-10-29 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
A | DFC-1630 | WPM | MTN-MECH | VEN-INSP | 2400284253 | PSV Exchange - DFCI-PSV-53551 | Isolation of PSV | AWSC | AWSC | 2 | 0 | Empty | 2024-10-19 | 2024-10-30 | 2024-10-30 | 2024-10-30 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /C /76/DFCI-PSV-53551 | Isolation of PSV | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 144 | 179.5 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-04 | 2022-04-04 | 2021-03-04 | 2021-03-09 | 10 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 25 | 35 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-04 | 2022-04-04 | 2021-03-04 | 2021-03-09 | 20 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 29 | 0 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-04 | 2022-04-07 | 2021-03-04 | 2021-03-09 | 30 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 19 | 80 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-07 | 2022-04-07 | 2021-03-04 | 2021-03-09 | 40 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 115 | 78.5 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-07 | 2022-04-07 | 2021-03-04 | 2021-03-09 | 50 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 17 | 155 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-07 | 2022-04-07 | 2021-03-04 | 2021-03-09 | 60 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 12 | 128 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-07 | 2022-04-08 | 2021-03-04 | 2021-03-09 | 70 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 12 | 2 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-08 | 2022-04-08 | 2021-03-04 | 2021-03-09 | 80 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 58 | 12 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-08 | 2022-04-13 | 2021-03-04 | 2021-03-09 | 90 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 68 | 15.5 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-13 | 2022-04-13 | 2021-03-04 | 2021-03-09 | 100 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 12 | 0 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-13 | 2022-04-15 | 2021-03-04 | 2021-03-09 | 110 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WRO | UNKNOWN | WELLSUPV | 2300002766 | DAF OCG NPT order - TFUIESD1, ESD Step 1 | Meals & breaks | PCNF | PCNF | 58 | 66 | Empty | 2022-04-04 | 2022-04-15 | 2022-04-15 | 2022-04-15 | 2021-03-04 | 2021-03-09 | 120 | PCNF | PCNF | DF /C | Meals & breaks | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081339 | Transmitterhus er defekt dfga-ft-550023 | Isolate Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 10 |  |  | DF /G /52/DFGA-FT-550023 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081339 | Transmitterhus er defekt dfga-ft-550023 | Isolate Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 20 |  |  | DF /G /52/DFGA-FT-550023 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-MECH | 2100081339 | Transmitterhus er defekt dfga-ft-550023 | Isolate Flow meter |  |  | 2.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 30 |  |  | DF /G /52/DFGA-FT-550023 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081339 | Transmitterhus er defekt dfga-ft-550023 | Isolate Flow meter |  |  | 0.5 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 40 |  |  | DF /G /52/DFGA-FT-550023 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100081339 | Transmitterhus er defekt dfga-ft-550023 | Isolate Flow meter |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-03-04 | 2023-07-17 | 50 |  |  | DF /G /52/DFGA-FT-550023 | Isolate Flow meter | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100081339 | Transmitterhus er defekt dfga-ft-550023 | Isolate Flow meter |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-03-04 | 2023-07-17 | 60 |  |  | DF /G /52/DFGA-FT-550023 | Isolate Flow meter | Unknown
A | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400322643 | 2Y 400V UPS.SYST BATT & CHAR F.TEST-DFG | Rental - Caverion | AWSCSECE | AWSCSECE | 80 | 0 | Empty | 2024-06-28 | 2024-07-08 | 2024-06-28 | 2024-07-06 | 2024-04-04 | 2024-05-20 | 10 | AWSCSECE | AWSCSECE | DF /G /06/UPS-SYSTEMS | Rental - Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322643 | 2Y 400V UPS.SYST BATT & CHAR F.TEST-DFG | Rental - Caverion | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-06-28 | 2024-07-08 | 2024-07-06 | 2024-07-08 | 2024-04-04 | 2024-05-20 | 20 | AWSCSECE | AWSCSECE | DF /G /06/UPS-SYSTEMS | Rental - Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322643 | 2Y 400V UPS.SYST BATT & CHAR F.TEST-DFG | Rental - Caverion | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-28 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-04-04 | 2024-05-20 | 30 | AWSCSECE | AWSCSECE | DF /G /06/UPS-SYSTEMS | Rental - Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322643 | 2Y 400V UPS.SYST BATT & CHAR F.TEST-DFG | Rental - Caverion | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-28 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-04-04 | 2024-05-20 | 40 | AWSCSECE | AWSCSECE | DF /G /06/UPS-SYSTEMS | Rental - Caverion | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400322643 | 2Y 400V UPS.SYST BATT & CHAR F.TEST-DFG | Rental - Caverion | AWSCSECE | AWSCSECE | 0 | 0 | Empty | 2024-06-28 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-04-04 | 2024-05-20 | 50 | AWSCSECE | AWSCSECE | DF /G /06/UPS-SYSTEMS | Rental - Caverion | Unknown
C | NOSD | WPM | MTN-TELE | MTN-ELEC | 2400269615 | 4Y ABB SCADA FUNC - DFA/B/C/E/F/G | Extra hardware |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-18 | 2023-05-27 | 2023-08-23 | 10 |  |  | DF /C /04/CONTROL-PANELS | Extra hardware | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400269615 | 4Y ABB SCADA FUNC - DFA/B/C/E/F/G | Extra hardware |  |  | 18 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-22 | 2023-05-27 | 2023-08-23 | 20 |  |  | DF /C /04/CONTROL-PANELS | Extra hardware | Unknown
C | NOSD | WPM | MTN-TELE | MTN-TELE | 2400269615 | 4Y ABB SCADA FUNC - DFA/B/C/E/F/G | Extra hardware |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-05-27 | 2023-08-23 | 30 |  |  | DF /C /04/CONTROL-PANELS | Extra hardware | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-SCAF | 2100056364 | XCV-380603 intern læk | New valve |  |  | 12 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-09 | 2023-01-11 | 2021-12-26 | 2022-05-25 | 10 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100056364 | XCV-380603 intern læk | New valve |  |  | 4 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-11 | 2023-01-11 | 2021-12-26 | 2022-05-25 | 20 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100056364 | XCV-380603 intern læk | New valve |  |  | 3 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-11 | 2023-01-12 | 2021-12-26 | 2022-05-25 | 30 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100056364 | XCV-380603 intern læk | New valve |  |  | 24 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-12 | 2023-01-15 | 2021-12-26 | 2022-05-25 | 40 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100056364 | XCV-380603 intern læk | New valve |  |  | 24 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-12 | 2023-01-15 | 2021-12-26 | 2022-05-25 | 50 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | PRODTECH | 2100056364 | XCV-380603 intern læk | New valve |  |  | 3 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-15 | 2023-01-16 | 2021-12-26 | 2022-05-25 | 60 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100056364 | XCV-380603 intern læk | New valve |  |  | 4 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-12-26 | 2022-05-25 | 70 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | DFF-WI | WDF | MTN-MECH | MTN-ROPE | 2100056364 | XCV-380603 intern læk | New valve |  |  | 0 | 0 | Empty | 2023-01-09 | 2023-01-16 | 2023-01-09 | 2023-01-09 | 2021-12-26 | 2022-05-25 | 80 |  |  | DF /F /54/DFFA-XCV-380603 | New valve | Unknown
4 | NE | WDF | MTN-MECH | MTN-PAIN | 2100068040 | FFSPR: Utility & Instrument Air Batch-03 | FFSP: 1,5" air utility pipe replacement |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-31 | 2024-08-22 | 2024-08-22 | 2022-06-02 | 2022-06-30 | 10 |  |  | DF /C /07/DFC-1.5-AU-054-0128-A1-F | FFSP: 1,5" air utility pipe replacement | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100068040 | FFSPR: Utility & Instrument Air Batch-03 | FFSP: 1,5" air utility pipe replacement |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-31 | 2024-08-22 | 2024-08-22 | 2022-06-02 | 2022-06-30 | 20 |  |  | DF /C /07/DFC-1.5-AU-054-0128-A1-F | FFSP: 1,5" air utility pipe replacement | Unknown
4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100068040 | FFSPR: Utility & Instrument Air Batch-03 | FFSP: 1,5" air utility pipe replacement |  |  | 36 | 0 | Empty | 2024-08-22 | 2024-08-31 | 2024-08-22 | 2024-08-26 | 2022-06-02 | 2022-06-30 | 30 |  |  | DF /C /07/DFC-1.5-AU-054-0128-A1-F | FFSP: 1,5" air utility pipe replacement | Unknown
4 | NE | WDF | MTN-MECH | MTN-ROPE | 2100068040 | FFSPR: Utility & Instrument Air Batch-03 | FFSP: 1,5" air utility pipe replacement |  |  | 36 | 0 | Empty | 2024-08-22 | 2024-08-31 | 2024-08-26 | 2024-08-29 | 2022-06-02 | 2022-06-30 | 40 |  |  | DF /C /07/DFC-1.5-AU-054-0128-A1-F | FFSP: 1,5" air utility pipe replacement | Unknown
4 | NE | WDF | MTN-MECH | MTN-SCAF | 2100068040 | FFSPR: Utility & Instrument Air Batch-03 | FFSP: 1,5" air utility pipe replacement |  |  | 18 | 0 | Empty | 2024-08-22 | 2024-08-31 | 2024-08-29 | 2024-08-31 | 2022-06-02 | 2022-06-30 | 50 |  |  | DF /C /07/DFC-1.5-AU-054-0128-A1-F | FFSP: 1,5" air utility pipe replacement | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100068040 | FFSPR: Utility & Instrument Air Batch-03 | FFSP: 1,5" air utility pipe replacement |  |  | 0 | 0 | Empty | 2024-08-22 | 2024-08-31 | 2024-08-31 | 2024-08-31 | 2022-06-02 | 2022-06-30 | 60 |  |  | DF /C /07/DFC-1.5-AU-054-0128-A1-F | FFSP: 1,5" air utility pipe replacement | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100075343 | Assembly of interlock to earthing switch | Isolate and prove dead | SCH | SCH | 0.5 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2022-11-07 | 2023-03-22 | 10 | SCH | SCH | DF /G /61/DFGA-N-1841-M112-01 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100075343 | Assembly of interlock to earthing switch | Isolate and prove dead | SCH | SCH | 2 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2022-11-07 | 2023-03-22 | 20 | SCH | SCH | DF /G /61/DFGA-N-1841-M112-01 | Isolate and prove dead | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-ELEC | 2100075343 | Assembly of interlock to earthing switch | Isolate and prove dead | SCH | SCH | 0.5 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2022-11-07 | 2023-03-22 | 30 | SCH | SCH | DF /G /61/DFGA-N-1841-M112-01 | Isolate and prove dead | Unknown
1 | Empty | WRO | PRODTECH | PRODTECH | 2300007668 | TME1863 Notification for pur. Nozomi equ | TME1863 Notification for pur. Nozomi equ |  |  | 0 | 0 | Empty | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2024-02-01 | 10 |  |  | DF /C | TME1863 Notification for pur. Nozomi equ | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-20 | 2024-10-19 | 2024-12-31 | 10 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-20 | 2024-06-21 | 2024-10-19 | 2024-12-31 | 20 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 24 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-21 | 2024-06-24 | 2024-10-19 | 2024-12-31 | 30 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 6 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-24 | 2024-06-25 | 2024-10-19 | 2024-12-31 | 40 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-25 | 2024-06-26 | 2024-10-19 | 2024-12-31 | 50 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-26 | 2024-06-27 | 2024-10-19 | 2024-12-31 | 60 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-RIGG | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 12 | 5 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-27 | 2024-06-28 | 2024-10-19 | 2024-12-31 | 70 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-28 | 2024-06-29 | 2024-10-19 | 2024-12-31 | 80 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 5 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-29 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 90 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 4 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-06-30 | 2024-10-19 | 2024-12-31 | 100 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-06-30 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 110 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284240 | PSV Calibration - DFCI-PSV-34019 | Isolation of PSV | PCNFAWSCSCH | PCNFAWSCSCH | 2 | 0 | Empty | 2024-06-20 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-10-19 | 2024-12-31 | 120 | PCNFAWSCSCH | PCNFAWSCSCH | DF /C /20/DFCI-PSV-34019 | Isolation of PSV | Unknown
A | DFG20MPH | WPM | MTN-MECH | PRODTECH | 2400325547 | 1Y ESDV LEAK TEST DFGA-ESDV-380131 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-06-25 | 2024-06-26 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-07-25 | 5 | AWSCSECE | AWSCSECE | DF /G /34/DFGA-ESDV-380131 | ISOLATION BY PRODUCTION | Unknown
A | DFG20MPH | WPM | MTN-MECH | PRODTECH | 2400325547 | 1Y ESDV LEAK TEST DFGA-ESDV-380131 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-06-25 | 2024-06-26 | 2024-06-25 | 2024-06-26 | 2024-06-25 | 2024-07-25 | 10 | AWSCSECE | AWSCSECE | DF /G /34/DFGA-ESDV-380131 | ISOLATION BY PRODUCTION | Unknown
A | DFG20MPH | WPM | MTN-MECH | PRODTECH | 2400325547 | 1Y ESDV LEAK TEST DFGA-ESDV-380131 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-06-25 | 2024-06-26 | 2024-06-26 | 2024-06-26 | 2024-06-25 | 2024-07-25 | 20 | AWSCSECE | AWSCSECE | DF /G /34/DFGA-ESDV-380131 | ISOLATION BY PRODUCTION | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300008966 | Instalation if IIOT TT DK220546 | Dan F telecom assisance |  |  | 0 | 0 | Empty | 2024-07-28 | 2024-07-29 | 2024-07-28 | 2024-07-28 | 2024-05-24 | 2024-07-08 | 10 |  |  | DF /F | Dan F telecom assisance | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300008966 | Instalation if IIOT TT DK220546 | Dan F telecom assisance |  |  | 5 | 0 | Empty | 2024-07-28 | 2024-07-29 | 2024-07-28 | 2024-07-29 | 2024-05-24 | 2024-07-08 | 20 |  |  | DF /F | Dan F telecom assisance | Unknown
2 | Empty | WRO | MTN-TELE | MTN-TELE | 2300008966 | Instalation if IIOT TT DK220546 | Dan F telecom assisance |  |  | 0 | 0 | Empty | 2024-07-28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-05-24 | 2024-07-08 | 30 |  |  | DF /F | Dan F telecom assisance | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053643 | Replace/repair DFF1802-7513-L1B floodlig | Repair or replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-11-01 | 2022-03-31 | 10 |  |  | DF /F /62 | Repair or replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053643 | Replace/repair DFF1802-7513-L1B floodlig | Repair or replace floodlight |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-11-01 | 2022-03-31 | 20 |  |  | DF /F /62 | Repair or replace floodlight | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100053643 | Replace/repair DFF1802-7513-L1B floodlig | Repair or replace floodlight |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2021-11-01 | 2022-03-31 | 30 |  |  | DF /F /62 | Repair or replace floodlight | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100022706 | Replace Bypass HCV | L3 Isolation of HCV | AWSC | AWSC | 3 | 0 | W05-06? IOP SMAT | 2024-08-01 | 2024-08-11 | 2024-08-01 | 2024-08-01 | 2018-11-30 | 2019-04-29 | 10 | AWSC | AWSC | DF /F /20 | L3 Isolation of HCV | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100022706 | Replace Bypass HCV | L3 Isolation of HCV | AWSC | AWSC | 12 | 0 | W05-06? IOP SMAT | 2024-08-01 | 2024-08-11 | 2024-08-01 | 2024-08-04 | 2018-11-30 | 2019-04-29 | 15 | AWSC | AWSC | DF /F /20 | L3 Isolation of HCV | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022706 | Replace Bypass HCV | L3 Isolation of HCV | AWSC | AWSC | 16 | 0 | W05-06? IOP SMAT | 2024-08-01 | 2024-08-11 | 2024-08-04 | 2024-08-08 | 2018-11-30 | 2019-04-29 | 20 | AWSC | AWSC | DF /F /20 | L3 Isolation of HCV | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-RIGG | 2100022706 | Replace Bypass HCV | L3 Isolation of HCV | AWSC | AWSC | 8 | 0 | W05-06? IOP SMAT | 2024-08-01 | 2024-08-11 | 2024-08-08 | 2024-08-10 | 2018-11-30 | 2019-04-29 | 25 | AWSC | AWSC | DF /F /20 | L3 Isolation of HCV | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | PRODTECH | 2100022706 | Replace Bypass HCV | L3 Isolation of HCV | AWSC | AWSC | 3 | 0 | W05-06? IOP SMAT | 2024-08-01 | 2024-08-11 | 2024-08-10 | 2024-08-11 | 2018-11-30 | 2019-04-29 | 30 | AWSC | AWSC | DF /F /20 | L3 Isolation of HCV | Unknown
4 | DFFHPSEP | WDF | MTN-MECH | MTN-MECH | 2100022706 | Replace Bypass HCV | L3 Isolation of HCV | AWSC | AWSC | 0 | 0 | W05-06? IOP SMAT | 2024-08-01 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2018-11-30 | 2019-04-29 | 40 | AWSC | AWSC | DF /F /20 | L3 Isolation of HCV | Unknown
4 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100024676 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2018-05-12 | 2020-05-01 | 10 |  |  | DF /A /37/DFAA-ESDV-45092 | L3 Rigg up for DFAA-ESDV-45092 out | Unknown
4 | SIWL | WDF | MTN-MECH | PRODTECH | 2100024676 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-23 | 2018-05-12 | 2020-05-01 | 20 |  |  | DF /A /37/DFAA-ESDV-45092 | L3 Rigg up for DFAA-ESDV-45092 out | Unknown
4 | SIWL | WDF | MTN-MECH | MTN-MECH | 2100024676 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  | 24 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-23 | 2024-09-26 | 2018-05-12 | 2020-05-01 | 30 |  |  | DF /A /37/DFAA-ESDV-45092 | L3 Rigg up for DFAA-ESDV-45092 out | Unknown
4 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100024676 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-26 | 2024-09-26 | 2018-05-12 | 2020-05-01 | 40 |  |  | DF /A /37/DFAA-ESDV-45092 | L3 Rigg up for DFAA-ESDV-45092 out | Unknown
4 | SIWL | WDF | MTN-MECH | PRODTECH | 2100024676 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  | 3 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-27 | 2018-05-12 | 2020-05-01 | 50 |  |  | DF /A /37/DFAA-ESDV-45092 | L3 Rigg up for DFAA-ESDV-45092 out | Unknown
4 | SIWL | WDF | MTN-MECH | MTN-RIGG | 2100024676 | Replace DFAA-ESDV-45092 (DFA LG ESDV-450 | L3 Rigg up for DFAA-ESDV-45092 out |  |  | 4 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2018-05-12 | 2020-05-01 | 60 |  |  | DF /A /37/DFAA-ESDV-45092 | L3 Rigg up for DFAA-ESDV-45092 out | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 21 | 52 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-13 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 10 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | VEN-ELEC | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 1 | 0 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-16 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 20 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | VEN-ELEC | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 8 | 0 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-16 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 30 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 4 | 88 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-13 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 35 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | VEN-ELEC | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 0.5 | 0 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-16 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 40 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-ROPE | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 12 | 18 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-16 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 50 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-13 | 2023-03-13 | 2021-07-28 | 2021-10-26 | 60 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-TELE | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 0 | 0 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-13 | 2023-04-28 | 2021-07-28 | 2021-10-26 | 70 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
3 | NOSD | WDF | MTN-TELE | MTN-SCAF | 2100050673 | PMAT Troubleshoot DFCM-XE-1502 Main ligh | Isolate accordingly | AWSCSCHSECE | AWSCSCHSECE | 15 | 12 | W11-12 IOP | 2023-03-13 | 2023-04-28 | 2023-03-13 | 2023-03-17 | 2021-07-28 | 2021-10-26 | 80 | AWSCSCHSECE | AWSCSCHSECE | DF /C /64/DFCM-XE-1502 | Isolate accordingly | Unknown
4 | DFA-O15 | WGN | MTN-MECH | PRODTECH | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 3 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-01 | 2024-12-01 | 2018-09-21 | 2019-02-18 | 10 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-INST | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 2 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-01 | 2024-12-02 | 2018-09-21 | 2019-02-18 | 20 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-RIGG | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 3 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-02 | 2024-12-02 | 2018-09-21 | 2019-02-18 | 30 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-MECH | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 6 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-03 | 2024-12-04 | 2018-09-21 | 2019-02-18 | 40 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-RIGG | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 3 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-04 | 2024-12-05 | 2018-09-21 | 2019-02-18 | 50 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-MECH | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 6 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-05 | 2024-12-06 | 2018-09-21 | 2019-02-18 | 60 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-INST | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 2 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-06 | 2024-12-07 | 2018-09-21 | 2019-02-18 | 70 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-INST | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 4 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-07 | 2024-12-08 | 2018-09-21 | 2019-02-18 | 80 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-MECH | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 2 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-08 | 2024-12-08 | 2018-09-21 | 2019-02-18 | 90 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | PRODTECH | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 2 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-08 | 2024-12-09 | 2018-09-21 | 2019-02-18 | 100 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
4 | DFA-O15 | WGN | MTN-MECH | MTN-MECH | 2200003147 | Corroded Valtek Act FCV-45033 DFA | Isolate PCV |  |  | 2 | 0 | W33-34 | 2024-12-01 | 2024-12-09 | 2024-12-09 | 2024-12-09 | 2018-09-21 | 2019-02-18 | 110 |  |  | DF /A /37/DFAA-FCV-45033 | Isolate PCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086058 | Gear defective so valve cannot be closed | Remove defect gearbox |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-10 | 2023-08-23 | 10 |  |  | DF /A /12/DFAA-HCV-330019 | Remove defect gearbox | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086058 | Gear defective so valve cannot be closed | Remove defect gearbox |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-10 | 2023-08-23 | 20 |  |  | DF /A /12/DFAA-HCV-330019 | Remove defect gearbox | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086058 | Gear defective so valve cannot be closed | Remove defect gearbox |  |  | 1 | 0 | W29-W30 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-10 | 2023-08-23 | 30 |  |  | DF /A /12/DFAA-HCV-330019 | Remove defect gearbox | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235701 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF07-FA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235701 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-22 | 2024-09-24 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF07-FA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235701 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF07-FA001 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235701 | 4Y 400V N-SWB MAINT-DFGA-N-1842B-BF07 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-N-1842B-BF07-FA001 | ISOLATION ELECTRICAL | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400223093 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-01. | PO ABB | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2022-11-16 | 2023-02-12 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-01 | PO ABB | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400223093 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-01. | PO ABB | AWSC | AWSC | 11 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2022-11-16 | 2023-02-12 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-01 | PO ABB | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400223093 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-01. | PO ABB | AWSC | AWSC | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-11-16 | 2023-02-12 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-01 | PO ABB | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400223093 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-01. | PO ABB | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-11-16 | 2023-02-12 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-01 | PO ABB | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400223093 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-01. | PO ABB | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2022-11-16 | 2023-02-12 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-01 | PO ABB | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053306 | Level transmitter change PVENT. | Deisolate & Leaktest Contact Level trans |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2021-08-28 | 2021-11-26 | 10 |  |  | DF /G /30/DFGA-LIT-410520 | Deisolate & Leaktest Contact Level trans | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053306 | Level transmitter change PVENT. | Deisolate & Leaktest Contact Level trans |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2021-08-28 | 2021-11-26 | 20 |  |  | DF /G /30/DFGA-LIT-410520 | Deisolate & Leaktest Contact Level trans | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053306 | Level transmitter change PVENT. | Deisolate & Leaktest Contact Level trans |  |  | 2 | 0 | Empty | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2021-08-28 | 2021-11-26 | 30 |  |  | DF /G /30/DFGA-LIT-410520 | Deisolate & Leaktest Contact Level trans | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093113 | Sync on/off switch broken | Isolate system |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-07-26 | 2023-12-08 | 20 |  |  | DF /G /05/DFGA-N-1843-A10-01 | Isolate system | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093113 | Sync on/off switch broken | Isolate system |  |  | 6 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-07-26 | 2023-12-08 | 30 |  |  | DF /G /05/DFGA-N-1843-A10-01 | Isolate system | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093113 | Sync on/off switch broken | Isolate system |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-26 | 2023-12-08 | 40 |  |  | DF /G /05/DFGA-N-1843-A10-01 | Isolate system | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100093113 | Sync on/off switch broken | Isolate system |  |  | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-07-26 | 2023-12-08 | 50 |  |  | DF /G /05/DFGA-N-1843-A10-01 | Isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-05-26 | 2023-10-08 | 20 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 1 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-22 | 2023-05-26 | 2023-10-08 | 30 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 6 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-05-26 | 2023-10-08 | 40 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 4 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-23 | 2024-09-23 | 2023-05-26 | 2023-10-08 | 50 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 1 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-05-26 | 2023-10-08 | 60 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 2 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-05-26 | 2023-10-08 | 70 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088998 | DFC Potwater pump P1019 replace | Prod isolation/permit |  |  | 1 | 0 | W11-W12 | 2024-09-22 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2023-05-26 | 2023-10-08 | 80 |  |  | DF /C /85/DFCM-P-1019 | Prod isolation/permit | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339049 | DFB_1Y_34000 INT STRUCT INSP - GVI | DFB_1Y_34000 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_34000 (PLAN ACCESS DECK) | DFB_1Y_34000 INT STRUCT INSP - GVI | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 10 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 20 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 5 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 30 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 40 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 50 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 5 | 20 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 60 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | PRODTECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 4 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 70 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 80 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200008953 | Exchange DFAA-PSV-33001 - 2022 | DFAA-PSV-33001 Offshore from WS Måde | PCNFSCH | PCNFSCH | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-03-28 | 2022-11-23 | 90 | PCNFSCH | PCNFSCH | DF /A /10/DFAA-PSV-33001 | DFAA-PSV-33001 Offshore from WS Måde | Unknown
4 | NE | WRO | PRODTECH | PRODTECH | 2300000781 | DK46 BOLTE MIN/MAX MATERIAL ORDER 2019 | DK46 BOLTE MIN/MAX MATERIAL ORDER 2019 |  |  | 0 | 0 | Empty | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2020-02-14 | 2019-01-01 | 2019-12-31 | 10 |  |  | DF /F | DK46 BOLTE MIN/MAX MATERIAL ORDER 2019 | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100074497 | Backload and repair of DFBA-B-1224A | Demounting of cable |  |  | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2022-10-28 | 2023-03-12 | 10 |  |  | DF /B /09/DFBA-B-1224A | Demounting of cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100074497 | Backload and repair of DFBA-B-1224A | Demounting of cable |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2022-10-28 | 2023-03-12 | 20 |  |  | DF /B /09/DFBA-B-1224A | Demounting of cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-RIGG | 2100074497 | Backload and repair of DFBA-B-1224A | Demounting of cable |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-02 | 2022-10-28 | 2023-03-12 | 30 |  |  | DF /B /09/DFBA-B-1224A | Demounting of cable | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074497 | Backload and repair of DFBA-B-1224A | Demounting of cable |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-03 | 2022-10-28 | 2023-03-12 | 35 |  |  | DF /B /09/DFBA-B-1224A | Demounting of cable | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100074497 | Backload and repair of DFBA-B-1224A | Demounting of cable |  |  | 20 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2022-10-28 | 2023-03-12 | 40 |  |  | DF /B /09/DFBA-B-1224A | Demounting of cable | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100074497 | Backload and repair of DFBA-B-1224A | Demounting of cable |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-04 | 2024-07-04 | 2022-10-28 | 2023-03-12 | 50 |  |  | DF /B /09/DFBA-B-1224A | Demounting of cable | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-15 | 2023-08-10 | 2023-12-23 | 10 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 22 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-15 | 2024-09-18 | 2023-08-10 | 2023-12-23 | 20 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-18 | 2024-09-19 | 2023-08-10 | 2023-12-23 | 30 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-19 | 2024-09-21 | 2023-08-10 | 2023-12-23 | 40 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-21 | 2024-09-22 | 2023-08-10 | 2023-12-23 | 50 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-22 | 2024-09-23 | 2023-08-10 | 2023-12-23 | 60 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100093861 | DFFA-MM-3552D Twinfilter backw rod broke | Isolation of mixer/filter/motor |  |  | 10 | 0 | Empty | 2024-09-15 | 2024-09-24 | 2024-09-23 | 2024-09-24 | 2023-08-10 | 2023-12-23 | 70 |  |  | DF /F /51/DFFB-MM-3552D | Isolation of mixer/filter/motor | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100052528 | Internal leak on HCV. | Production isolation w flushing |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2021-10-05 | 2022-03-04 | 10 |  |  | DF /B /10/DFBA-XCV-30401 | Production isolation w flushing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100052528 | Internal leak on HCV. | Production isolation w flushing |  |  | 16 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-18 | 2021-10-05 | 2022-03-04 | 20 |  |  | DF /B /10/DFBA-XCV-30401 | Production isolation w flushing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100052528 | Internal leak on HCV. | Production isolation w flushing |  |  | 6 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-18 | 2024-09-19 | 2021-10-05 | 2022-03-04 | 30 |  |  | DF /B /10/DFBA-XCV-30401 | Production isolation w flushing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100052528 | Internal leak on HCV. | Production isolation w flushing |  |  | 16 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-21 | 2021-10-05 | 2022-03-04 | 40 |  |  | DF /B /10/DFBA-XCV-30401 | Production isolation w flushing | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100052528 | Internal leak on HCV. | Production isolation w flushing |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2021-10-05 | 2022-03-04 | 50 |  |  | DF /B /10/DFBA-XCV-30401 | Production isolation w flushing | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100052528 | Internal leak on HCV. | Production isolation w flushing |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2021-10-05 | 2022-03-04 | 60 |  |  | DF /B /10/DFBA-XCV-30401 | Production isolation w flushing | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235616 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235616 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235616 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-04-30 | 2023-07-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235616 | 4Y 380V N-SWB-MAINT-DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-04-30 | 2023-07-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1802B-4 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235638 | 4Y 380V N-SWB MAINT-DFFA-N-1803-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1803-07 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235638 | 4Y 380V N-SWB MAINT-DFFA-N-1803-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 16 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1803-07 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235638 | 4Y 380V N-SWB MAINT-DFFA-N-1803-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1803-07 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235638 | 4Y 380V N-SWB MAINT-DFFA-N-1803-7 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1803-07 | ISOLATION ELECTRICAL | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339048 | DFB_1Y_30600 INT STRUCT INSP - GVI | DFB_1Y_30600 INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /86/EL_30600 (MAIN DECK) | DFB_1Y_30600 INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-PAIN | MTN-PAIN | 2100078650 | ANOCR DFC-10-PHS-033-9015-BD-U | Perf. Std defect Notif:-SECE-id: P4.2 |  |  | 0 | 0 | Empty | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-05-11 | 2023-06-23 | 10 |  |  | DF /C /12/DFC-10-PHS-033-9015-BD-U | Perf. Std defect Notif:-SECE-id: P4.2 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235280 | 4Y 3KV N-SWB MAINT DFCI-N-1801-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2022-12-16 | 2023-03-14 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1801-02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | VEN-ELEC | 2400235280 | 4Y 3KV N-SWB MAINT DFCI-N-1801-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 29 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-18 | 2022-12-16 | 2023-03-14 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1801-02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235280 | 4Y 3KV N-SWB MAINT DFCI-N-1801-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 8 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-20 | 2022-12-16 | 2023-03-14 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1801-02-01 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235280 | 4Y 3KV N-SWB MAINT DFCI-N-1801-02 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | 24-W01-02 | 2024-09-15 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2022-12-16 | 2023-03-14 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1801-02-01 | ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400244899 | 3M HYD POWER UNIT MAINT - DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-06 | 2023-05-16 | 10 |  |  | DF /C /07/DFCM-A-5901 | HYD POWER UNIT MAINT - DFCM-A-5901 | Unknown
3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200011358 | Protection Settings DFFB-N-1828-06P1 | Protection Settings DFFB-N-1828-06P1 |  |  | 1 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-08-26 | 2023-01-08 | 10 |  |  | DF /F /61/DFFB-N-1828-06P1 | Protection Settings DFFB-N-1828-06P1 | Unknown
3 | NOSD | WGN | MTN-ELEC | VEN-ELEC | 2200011358 | Protection Settings DFFB-N-1828-06P1 | Protection Settings DFFB-N-1828-06P1 |  |  | 2 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-08-26 | 2023-01-08 | 20 |  |  | DF /F /61/DFFB-N-1828-06P1 | Protection Settings DFFB-N-1828-06P1 | Unknown
3 | NOSD | WGN | MTN-ELEC | PRODTECH | 2200011358 | Protection Settings DFFB-N-1828-06P1 | Protection Settings DFFB-N-1828-06P1 |  |  | 1 | 0 | W23-W24 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2022-08-26 | 2023-01-08 | 30 |  |  | DF /F /61/DFFB-N-1828-06P1 | Protection Settings DFFB-N-1828-06P1 | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100050465 | DFGA-A-5453 Strainers damaged | isolate DFGA-A-5453 | SCH | SCH | 0 | 0 | W41-42 | 2024-09-06 | 2024-09-07 | 2024-09-06 | 2024-09-06 | 2021-08-17 | 2022-01-14 | 10 | SCH | SCH | DF /G /07/DFGA-A-5453 | isolate DFGA-A-5453 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050465 | DFGA-A-5453 Strainers damaged | isolate DFGA-A-5453 | SCH | SCH | 3 | 0 | W41-42 | 2024-09-06 | 2024-09-07 | 2024-09-06 | 2024-09-06 | 2021-08-17 | 2022-01-14 | 20 | SCH | SCH | DF /G /07/DFGA-A-5453 | isolate DFGA-A-5453 | Unknown
4 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100050465 | DFGA-A-5453 Strainers damaged | isolate DFGA-A-5453 | SCH | SCH | 6 | 0 | W41-42 | 2024-09-06 | 2024-09-07 | 2024-09-06 | 2024-09-07 | 2021-08-17 | 2022-01-14 | 30 | SCH | SCH | DF /G /07/DFGA-A-5453 | isolate DFGA-A-5453 | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100050465 | DFGA-A-5453 Strainers damaged | isolate DFGA-A-5453 | SCH | SCH | 3 | 0 | W41-42 | 2024-09-06 | 2024-09-07 | 2024-09-07 | 2024-09-07 | 2021-08-17 | 2022-01-14 | 40 | SCH | SCH | DF /G /07/DFGA-A-5453 | isolate DFGA-A-5453 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100050465 | DFGA-A-5453 Strainers damaged | isolate DFGA-A-5453 | SCH | SCH | 0 | 0 | W41-42 | 2024-09-06 | 2024-09-07 | 2024-09-06 | 2024-09-06 | 2021-08-17 | 2022-01-14 | 50 | SCH | SCH | DF /G /07/DFGA-A-5453 | isolate DFGA-A-5453 | Unknown
3 | DFF-W03 | WDF | MTN-INST | MTN-INST | 2100105410 | DFF-03 Choke ZT needs adjust. or replace | DFF-03 Choke ZT to adjust |  |  | 4 | 0 | Empty | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-09-03 | 2024-02-28 | 2024-07-12 | 10 |  |  | DF /F /55/DFFA-ZT-300703 | DFF-03 Choke ZT to adjust | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200002970 | SMAT:DFA HCV er ekstern læk | L3 Change of 1" Ball Valve |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-03-05 | 2018-04-14 | 10 |  |  | DF /A /07/DFAA-ACC-59022 | L3 Change of 1" Ball Valve | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200002970 | SMAT:DFA HCV er ekstern læk | L3 Change of 1" Ball Valve |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-03-05 | 2018-04-14 | 20 |  |  | DF /A /07/DFAA-ACC-59022 | L3 Change of 1" Ball Valve | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200002970 | SMAT:DFA HCV er ekstern læk | L3 Change of 1" Ball Valve |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-03-05 | 2018-04-14 | 70 |  |  | DF /A /07/DFAA-ACC-59022 | L3 Change of 1" Ball Valve | Unknown
3 | NOSD | WGN | MTN-MECH | MTN-MECH | 2200002970 | SMAT:DFA HCV er ekstern læk | L3 Change of 1" Ball Valve |  |  | 5 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-03-05 | 2018-04-14 | 80 |  |  | DF /A /07/DFAA-ACC-59022 | L3 Change of 1" Ball Valve | Unknown
3 | NOSD | WGN | MTN-MECH | PRODTECH | 2200002970 | SMAT:DFA HCV er ekstern læk | L3 Change of 1" Ball Valve |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2018-03-05 | 2018-04-14 | 90 |  |  | DF /A /07/DFAA-ACC-59022 | L3 Change of 1" Ball Valve | Unknown
1 | NOSD | WRO | MTN-INST | MTN-TELE | 2300007446 | Change of Cv for DFF-FCV-430011A | Change of Cv for DFF-FCV-430011A |  |  | 3 | 3 | Empty | 2023-12-21 | 2023-12-22 | 2023-12-21 | 2023-12-21 | 2023-12-20 | 2024-01-04 | 10 |  |  | DF /F /32/DFFA-FY-430011A | Change of Cv for DFF-FCV-430011A | Unknown
1 | NOSD | WRO | MTN-INST | MTN-TELE | 2300007446 | Change of Cv for DFF-FCV-430011A | Change of Cv for DFF-FCV-430011A |  |  | 1 | 1 | Empty | 2023-12-21 | 2023-12-22 | 2023-12-21 | 2023-12-22 | 2023-12-20 | 2024-01-04 | 20 |  |  | DF /F /32/DFFA-FY-430011A | Change of Cv for DFF-FCV-430011A | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-ROPE | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-15 | 2022-01-01 | 2022-04-01 | 5 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-ROPE | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-15 | 2022-01-01 | 2022-04-01 | 7 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-15 | 2024-09-16 | 2022-01-01 | 2022-04-01 | 10 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-16 | 2024-09-17 | 2022-01-01 | 2022-04-01 | 20 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 5 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-17 | 2024-09-18 | 2022-01-01 | 2022-04-01 | 30 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-18 | 2024-09-19 | 2022-01-01 | 2022-04-01 | 40 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-19 | 2024-09-20 | 2022-01-01 | 2022-04-01 | 50 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
3 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100059696 | DFCI-HCV-33014-U Intern Leak | Check PTW/Site visit/Line work |  |  | 2 | 0 | Empty | 2024-09-15 | 2024-09-21 | 2024-09-20 | 2024-09-21 | 2022-01-01 | 2022-04-01 | 60 |  |  | DF /C /10/DFCI-HCV-33014-U | Check PTW/Site visit/Line work | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346559 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0328 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0328 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346559 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0328 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0328 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346559 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0328 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 4 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0328 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346559 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0328 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0328 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346559 | 1Y DELUGE SKID, SMOKE TEST-DFCI-X-0328 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /C /01/DFCI-X-0328 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235667 | 4Y 400V N-SWB MAINT-DFCI-N-1802-LX | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-LX | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235667 | 4Y 400V N-SWB MAINT-DFCI-N-1802-LX | ISOLATION ELECTRICAL | AWSC | AWSC | 2 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-LX | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235667 | 4Y 400V N-SWB MAINT-DFCI-N-1802-LX | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-LX | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235667 | 4Y 400V N-SWB MAINT-DFCI-N-1802-LX | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-LX | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100053021 | LG-34005 on DFC Test Sep need change out | Install new backlight |  |  | 0 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2021-08-18 | 2021-11-16 | 10 |  |  | DF /C /11/DFCI-LG-34005 | Install new backlight | Unknown
3 | NOSD | WDF | MTN-INST | MTN-ELEC | 2100053021 | LG-34005 on DFC Test Sep need change out | Install new backlight |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2021-08-18 | 2021-11-16 | 20 |  |  | DF /C /11/DFCI-LG-34005 | Install new backlight | Unknown
3 | NOSD | WDF | MTN-INST | PRODTECH | 2100053021 | LG-34005 on DFC Test Sep need change out | Install new backlight |  |  | 6 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2021-08-18 | 2021-11-16 | 30 |  |  | DF /C /11/DFCI-LG-34005 | Install new backlight | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400325772 | 4Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | AWSCSECE | AWSCSECE | 56 | 0 | Empty | 2024-06-10 | 2024-06-13 | 2024-06-10 | 2024-06-12 | 2024-03-20 | 2024-06-01 | 10 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400325772 | 4Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-06-10 | 2024-06-13 | 2024-06-12 | 2024-06-13 | 2024-03-20 | 2024-06-01 | 20 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400325772 | 4Y LIFE BOAT MAINT - DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | AWSCSECE | AWSCSECE | 1 | 0 | Empty | 2024-06-10 | 2024-06-13 | 2024-06-13 | 2024-06-13 | 2024-03-20 | 2024-06-01 | 30 | AWSCSECE | AWSCSECE | DF /G /02/DFGA-X-0702 | LIFE BOAT MAINT - DFGA-X-0702 | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344047 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3931 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-15 | 2024-08-22 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2024-09-20 | 10 |  |  | DF /F /75/DFFA-A-3931 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344047 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3931 | ISOLATION BY PRODUCTION |  |  | 19 | 0 | Empty | 2024-08-15 | 2024-08-22 | 2024-08-15 | 2024-08-19 | 2024-08-15 | 2024-09-20 | 20 |  |  | DF /F /75/DFFA-A-3931 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400344047 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3931 | ISOLATION BY PRODUCTION |  |  | 9 | 0 | Empty | 2024-08-15 | 2024-08-22 | 2024-08-20 | 2024-08-22 | 2024-08-15 | 2024-09-20 | 30 |  |  | DF /F /75/DFFA-A-3931 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | PRODTECH | 2400344047 | 1Y CHEM INJ PUMP SKID MAINT-DFFA-A-3931 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-08-15 | 2024-08-22 | 2024-08-22 | 2024-08-22 | 2024-08-15 | 2024-09-20 | 40 |  |  | DF /F /75/DFFA-A-3931 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100076958 | Change motor potentiometer | Change potentiometer | SCH | SCH | 1 | 0 | W23-W24 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2022-12-10 | 2023-04-24 | 10 | SCH | SCH | DF /F /60/DFFA-FP-1610 | Change potentiometer | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-TURB | 2100076958 | Change motor potentiometer | Change potentiometer | SCH | SCH | 6 | 0 | W23-W24 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2022-12-10 | 2023-04-24 | 20 | SCH | SCH | DF /F /60/DFFA-FP-1610 | Change potentiometer | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100076958 | Change motor potentiometer | Change potentiometer | SCH | SCH | 1 | 0 | W23-W24 | 2024-07-01 | 2024-07-02 | 2024-07-02 | 2024-07-02 | 2022-12-10 | 2023-04-24 | 30 | SCH | SCH | DF /F /60/DFFA-FP-1610 | Change potentiometer | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 12 | 12 | Empty | 2024-07-30 | 2024-07-30 | 2019-02-11 | 2019-08-04 | 2018-11-13 | 2018-12-23 | 10 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 24 | 24 | Empty | 2024-07-30 | 2024-07-30 | 2019-02-12 | 2019-08-04 | 2018-11-13 | 2018-12-23 | 20 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 0 | 0 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2018-11-13 | 2018-12-23 | 30 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 6 | 6 | Empty | 2024-07-30 | 2024-07-30 | 2019-04-17 | 2019-08-04 | 2018-11-13 | 2018-12-23 | 40 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 36 | 36 | Empty | 2024-07-30 | 2024-07-30 | 2019-04-17 | 2019-08-04 | 2018-11-13 | 2018-12-23 | 50 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 12 | 12 | Empty | 2024-07-30 | 2024-07-30 | 2019-07-03 | 2019-08-04 | 2018-11-13 | 2018-12-23 | 60 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | WELLSUPV | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 12 | 12 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2018-11-13 | 2018-12-23 | 70 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NE | WRO | MTN-TELE | MTN-TELE | 2300000834 | SMAT:DAF install ICS Firewall TOTAL inte | DAF install of ICS Firewall TOTAL integ. | PCNF | PCNF | 12 | 12 | Empty | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2018-11-13 | 2018-12-23 | 80 | PCNF | PCNF | DF | DAF install of ICS Firewall TOTAL integ. | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100088056 | Basket stretcher rusty hook | Basket stretcher rusty hook |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-10 | 2023-09-22 | 10 |  |  | DF /C /02/DFCI-STR-0641 | Basket stretcher rusty hook | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339288 | DFF_1Y_FIRE AND BLAST-WALLS INSP | DFF_1Y_FIRE AND BLAST-WALLS INSP | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /02/FIRE AND BLAST-WALLS | DFF_1Y_FIRE AND BLAST-WALLS INSP | Unknown
3 | DFB-3550 | WDF | MTN-MECH | PRODTECH | 2100057170 | Rusten sov på ESDV | Replace and adjust Control panel (SDV) | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-11-12 | 2022-02-10 | 10 | AWSC | AWSC | DF /B /11/DFBA-ESDV-34081 | Replace and adjust Control panel (SDV) | Unknown
3 | DFB-3550 | WDF | MTN-MECH | MTN-MECH | 2100057170 | Rusten sov på ESDV | Replace and adjust Control panel (SDV) | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2021-11-12 | 2022-02-10 | 20 | AWSC | AWSC | DF /B /11/DFBA-ESDV-34081 | Replace and adjust Control panel (SDV) | Unknown
3 | DFB-3550 | WDF | MTN-MECH | PRODTECH | 2100057170 | Rusten sov på ESDV | Replace and adjust Control panel (SDV) | AWSC | AWSC | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2021-11-12 | 2022-02-10 | 30 | AWSC | AWSC | DF /B /11/DFBA-ESDV-34081 | Replace and adjust Control panel (SDV) | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241118 | 6M SDV LUB/MAINT- DFF | SDV LUB/MAINT- DFF |  |  | 13 | 0 | W35-W36 | 2024-08-26 | 2024-08-29 | 2024-08-26 | 2024-08-29 | 2023-03-23 | 2023-04-08 | 10 |  |  | DF /F /03/SDV-VALVES | SDV LUB/MAINT- DFF | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009218 | Insulation assits FORCE 21670(COMP) | Bilfinger inspection |  |  | 0 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-27 | 2023-03-27 | 2022-02-07 | 2022-07-07 | 10 |  |  | DF /B /55/DFB-4-WI-035-4073-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009218 | Insulation assits FORCE 21670(COMP) | Bilfinger inspection |  |  | 32 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-27 | 2023-03-30 | 2022-02-07 | 2022-07-07 | 20 |  |  | DF /B /55/DFB-4-WI-035-4073-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009218 | Insulation assits FORCE 21670(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-03-31 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 30 |  |  | DF /B /55/DFB-4-WI-035-4073-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009218 | Insulation assits FORCE 21670(COMP) | Bilfinger inspection |  |  | 12 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-04-01 | 2023-04-01 | 2022-02-07 | 2022-07-07 | 33 |  |  | DF /B /55/DFB-4-WI-035-4073-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009218 | Insulation assits FORCE 21670(COMP) | Bilfinger inspection |  |  | 24 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-04-01 | 2023-04-04 | 2022-02-07 | 2022-07-07 | 40 |  |  | DF /B /55/DFB-4-WI-035-4073-FC-U | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009218 | Insulation assits FORCE 21670(COMP) | Bilfinger inspection |  |  | 20 | 0 | Empty | 2023-03-27 | 2023-04-06 | 2023-04-04 | 2023-04-06 | 2022-02-07 | 2022-07-07 | 50 |  |  | DF /B /55/DFB-4-WI-035-4073-FC-U | Bilfinger inspection | Unknown
B | NOSD | WPM | MTN-CRAN | MTN-CRAN | 2400294023 | 6M GANTRY CRANE CHECK VENDR-DFEZ-X-6150 | Wire rope and Hose inspection | AWSC | AWSC | 18 | 0 | Empty | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2024-06-05 | 2024-03-10 | 2024-03-26 | 10 | AWSC | AWSC | DF /E /78/DFEZ-X-6150 | Wire rope and Hose inspection | Unknown
B | NOSD | WPM | MTN-CRAN | VEN-CRAN | 2400294023 | 6M GANTRY CRANE CHECK VENDR-DFEZ-X-6150 | Wire rope and Hose inspection | AWSC | AWSC | 6 | 0 | Empty | 2024-06-03 | 2024-06-05 | 2024-06-03 | 2024-06-03 | 2024-03-10 | 2024-03-26 | 20 | AWSC | AWSC | DF /E /78/DFEZ-X-6150 | Wire rope and Hose inspection | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235813 | 4Y 400V N-DP-MAINT-DFCI-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-DP-1831 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235813 | 4Y 400V N-DP-MAINT-DFCI-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-DP-1831 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235813 | 4Y 400V N-DP-MAINT-DFCI-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 3 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-DP-1831 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235813 | 4Y 400V N-DP-MAINT-DFCI-DP-1831 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-DP-1831 | ISOLATION ELECTRICAL | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100080798 | Fejlvisning på ESD transmitter | Isolate and deisolate | SECE | SECE | 0 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-08 | 2025-12-24 | 10 | SECE | SECE | DF /G /75/DFGA-PIT-398803 | Isolate and deisolate | Unknown
4 | NOSD | WDF | MTN-INST | PRODTECH | 2100080798 | Fejlvisning på ESD transmitter | Isolate and deisolate | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-07-08 | 2025-12-24 | 20 | SECE | SECE | DF /G /75/DFGA-PIT-398803 | Isolate and deisolate | Unknown
4 | NOSD | WDF | MTN-INST | MTN-INST | 2100080798 | Fejlvisning på ESD transmitter | Isolate and deisolate | SECE | SECE | 3 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-07-08 | 2025-12-24 | 30 | SECE | SECE | DF /G /75/DFGA-PIT-398803 | Isolate and deisolate | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112430 | Clean request of Flame arrestor DFD vent | Isolate DFDA-FLA-40071 | PCNFSECE | PCNFSECE | 0 | 0 | W33-W34 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2024-05-09 | 2024-06-23 | 10 | PCNFSECE | PCNFSECE | DF /D /36/DFDA-FLA-40071 | Isolate DFDA-FLA-40071 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112430 | Clean request of Flame arrestor DFD vent | Isolate DFDA-FLA-40071 | PCNFSECE | PCNFSECE | 4 | 0 | W33-W34 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-09 | 2024-06-23 | 50 | PCNFSECE | PCNFSECE | DF /D /36/DFDA-FLA-40071 | Isolate DFDA-FLA-40071 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100112430 | Clean request of Flame arrestor DFD vent | Isolate DFDA-FLA-40071 | PCNFSECE | PCNFSECE | 4 | 4 | W33-W34 | 2024-07-29 | 2024-07-30 | 2024-07-01 | 2024-07-01 | 2024-05-09 | 2024-06-23 | 60 | PCNFSECE | PCNFSECE | DF /D /36/DFDA-FLA-40071 | Isolate DFDA-FLA-40071 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100112430 | Clean request of Flame arrestor DFD vent | Isolate DFDA-FLA-40071 | PCNFSECE | PCNFSECE | 4 | 4 | W33-W34 | 2024-07-29 | 2024-07-30 | 2024-07-01 | 2024-07-01 | 2024-05-09 | 2024-06-23 | 70 | PCNFSECE | PCNFSECE | DF /D /36/DFDA-FLA-40071 | Isolate DFDA-FLA-40071 | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100112430 | Clean request of Flame arrestor DFD vent | Isolate DFDA-FLA-40071 | PCNFSECE | PCNFSECE | 12 | 12 | W33-W34 | 2024-07-29 | 2024-07-30 | 2024-07-01 | 2024-07-01 | 2024-05-09 | 2024-06-23 | 80 | PCNFSECE | PCNFSECE | DF /D /36/DFDA-FLA-40071 | Isolate DFDA-FLA-40071 | Unknown
2 | NOSD | WDF | MTN-MECH | PRODTECH | 2100112430 | Clean request of Flame arrestor DFD vent | Isolate DFDA-FLA-40071 | PCNFSECE | PCNFSECE | 4 | 0 | W33-W34 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-05-09 | 2024-06-23 | 90 | PCNFSECE | PCNFSECE | DF /D /36/DFDA-FLA-40071 | Isolate DFDA-FLA-40071 | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100118 | DFE/78 Fault indication in cabin | Order 2 new batteries |  |  | 6 | 8 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-12-01 | 2024-04-14 | 10 |  |  | DF /E /78/DFEZ-X-6150 | Order 2 new batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-CRAN | 2100100118 | DFE/78 Fault indication in cabin | Order 2 new batteries |  |  | 5 | 8 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-12-01 | 2024-04-14 | 20 |  |  | DF /E /78/DFEZ-X-6150 | Order 2 new batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100118 | DFE/78 Fault indication in cabin | Order 2 new batteries |  |  | 5 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-12-01 | 2024-04-14 | 25 |  |  | DF /E /78/DFEZ-X-6150 | Order 2 new batteries | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100100118 | DFE/78 Fault indication in cabin | Order 2 new batteries |  |  | 0 | 0 | Empty | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-12-01 | 2024-04-14 | 30 |  |  | DF /E /78/DFEZ-X-6150 | Order 2 new batteries | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339212 | DFE_1Y_BRIDGE E-A INT STRUCT INSP - GVI | DFE_1Y_BRIDGE E-A INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /86/BRIDGE-DFE-DFA | DFE_1Y_BRIDGE E-A INT STRUCT INSP - GVI | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400193030 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 |  |  | 12 | 0 | W27-W28 | 2024-07-29 | 2024-08-01 | 2024-07-29 | 2024-08-01 | 2022-04-26 | 2022-06-01 | 10 |  |  | DF /F /75/DFFA-A-39704 | 1Y CHEMICAL DISTRIBUTION PANEL A-39704 | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400342409 | 1Y WI INST/CHOKE VALVES MAINT-DFB | DE-ISOLATION BY PRODUCTION | SECE | SECE | 2.5 | 0 | Empty | 2024-08-11 | 2024-08-19 | 2024-08-11 | 2024-08-11 | 2024-08-11 | 2024-09-10 | 5 | SECE | SECE | DF /B /55/WATER-INJECTION-WELLS | DE-ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-INST | 2400342409 | 1Y WI INST/CHOKE VALVES MAINT-DFB | DE-ISOLATION BY PRODUCTION | SECE | SECE | 14 | 0 | Empty | 2024-08-11 | 2024-08-19 | 2024-08-11 | 2024-08-15 | 2024-08-11 | 2024-09-10 | 10 | SECE | SECE | DF /B /55/WATER-INJECTION-WELLS | DE-ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | MTN-MECH | 2400342409 | 1Y WI INST/CHOKE VALVES MAINT-DFB | DE-ISOLATION BY PRODUCTION | SECE | SECE | 14 | 0 | Empty | 2024-08-11 | 2024-08-19 | 2024-08-15 | 2024-08-18 | 2024-08-11 | 2024-09-10 | 20 | SECE | SECE | DF /B /55/WATER-INJECTION-WELLS | DE-ISOLATION BY PRODUCTION | Unknown
A | NE | WPM | MTN-MECH | PRODTECH | 2400342409 | 1Y WI INST/CHOKE VALVES MAINT-DFB | DE-ISOLATION BY PRODUCTION | SECE | SECE | 2.5 | 0 | Empty | 2024-08-11 | 2024-08-19 | 2024-08-18 | 2024-08-19 | 2024-08-11 | 2024-09-10 | 30 | SECE | SECE | DF /B /55/WATER-INJECTION-WELLS | DE-ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077164 | FLM DFC - Replace Steps on ST057 EL. 47. | Remove old grating |  |  | 6 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-04-30 | 2023-04-30 | 2023-04-30 | 2023-12-31 | 10 |  |  | DF /C /86/47000 - GRATINGS | Remove old grating | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077164 | FLM DFC - Replace Steps on ST057 EL. 47. | Remove old grating |  |  | 8 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-04-30 | 2023-05-01 | 2023-04-30 | 2023-12-31 | 20 |  |  | DF /C /86/47000 - GRATINGS | Remove old grating | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077164 | FLM DFC - Replace Steps on ST057 EL. 47. | Remove old grating |  |  | 8 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-05-01 | 2023-05-02 | 2023-04-30 | 2023-12-31 | 30 |  |  | DF /C /86/47000 - GRATINGS | Remove old grating | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100077164 | FLM DFC - Replace Steps on ST057 EL. 47. | Remove old grating |  |  | 6 | 0 | Empty | 2023-04-30 | 2023-05-03 | 2023-05-02 | 2023-05-03 | 2023-04-30 | 2023-12-31 | 40 |  |  | DF /C /86/47000 - GRATINGS | Remove old grating | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400337270 | 6M H2S SCAVENGER PUMP MAINT-DFGA-P-7602 | H2S SCAVENGER PUMP MAINT-DFGA-P-7602 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-08-17 | 10 |  |  | DF /G /75/DFGA-A-7602 | H2S SCAVENGER PUMP MAINT-DFGA-P-7602 | Unknown
C | NOSD | WPM | PRODLABO | PRODLABO | 2400264114 | 1M GAS SAMPLE FOR CO2 EMISSION | CO2 EMISSION SAMPLE |  |  | 2 | 0 | Empty | 2023-07-20 | 2023-07-20 | 2023-07-20 | 2023-07-20 | 2023-07-20 | 2023-07-25 | 10 |  |  | DF /F /80 | CO2 EMISSION SAMPLE | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 10 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-05 | 2024-12-05 | 2024-10-19 | 2024-12-31 | 20 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 24 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-06 | 2024-12-08 | 2024-10-19 | 2024-12-31 | 30 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-09 | 2024-12-10 | 2024-10-19 | 2024-12-31 | 40 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-10 | 2024-12-10 | 2024-10-19 | 2024-12-31 | 50 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-10 | 2024-12-11 | 2024-10-19 | 2024-12-31 | 60 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-RIGG | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 12 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-11 | 2024-12-13 | 2024-10-19 | 2024-12-31 | 70 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-13 | 2024-12-13 | 2024-10-19 | 2024-12-31 | 80 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 5 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-13 | 2024-12-14 | 2024-10-19 | 2024-12-31 | 90 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | PRODTECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 4 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-15 | 2024-12-15 | 2024-10-19 | 2024-12-31 | 100 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-MECH | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-15 | 2024-12-15 | 2024-10-19 | 2024-12-31 | 110 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | VEN-INSP | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 2 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-16 | 2024-12-16 | 2024-10-19 | 2024-12-31 | 120 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
A | DFF-IPHP | WPM | MTN-MECH | MTN-SCAF | 2400284273 | PSV Calibration - DFFA-PSV-430037 | De-isolation and leak test | AWSC | AWSC | 10 | 0 | Empty | 2024-12-05 | 2024-12-17 | 2024-12-16 | 2024-12-17 | 2024-10-19 | 2024-12-31 | 130 | AWSC | AWSC | DF /F /31/DFFA-PSV-430037 | De-isolation and leak test | Unknown
3 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-01 | 2022-10-14 | 2023-02-26 | 10 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-01 | 2024-07-02 | 2022-10-14 | 2023-02-26 | 20 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-02 | 2024-07-03 | 2022-10-14 | 2023-02-26 | 30 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-03 | 2024-07-03 | 2022-10-14 | 2023-02-26 | 40 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-03 | 2024-07-04 | 2022-10-14 | 2023-02-26 | 50 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-MECH | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-04 | 2024-07-04 | 2022-10-14 | 2023-02-26 | 51 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-04 | 2024-07-05 | 2022-10-14 | 2023-02-26 | 60 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-05 | 2024-07-05 | 2022-10-14 | 2023-02-26 | 70 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100074498 | Control damper DFBA-CD-12001 stuck open | Control damper DFBA-CD-12001 stuck open |  |  | 6 | 0 | W27-W28 | 2024-07-01 | 2024-07-07 | 2024-07-05 | 2024-07-07 | 2022-10-14 | 2023-02-26 | 80 |  |  | DF /B /09/DFBA-CD-12001 | Control damper DFBA-CD-12001 stuck open | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055327 | Change Floodlight bulb | Change Floodlight bulb |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-12-05 | 2022-05-04 | 10 |  |  | DF /G /62 | Change Floodlight bulb | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055327 | Change Floodlight bulb | Change Floodlight bulb |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2021-12-05 | 2022-05-04 | 20 |  |  | DF /G /62 | Change Floodlight bulb | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100055327 | Change Floodlight bulb | Change Floodlight bulb |  |  | 1 | 0 | W25-W26 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2021-12-05 | 2022-05-04 | 30 |  |  | DF /G /62 | Change Floodlight bulb | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 10 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 20 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 12 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 30 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 40 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 50 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 3 | 6 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 60 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 14 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 70 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 2 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 80 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 90 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 100 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 110 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 120 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 130 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 140 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 150 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 2 | 18 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 160 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 1 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-09-24 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 170 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2023-10-16 | 2023-10-17 | 2023-09-07 | 2023-10-22 | 180 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 0 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-01 | 2023-09-07 | 2023-10-22 | 190 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | PRODTECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-09-07 | 2023-10-22 | 200 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | MTN-MECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 8 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-09-07 | 2023-10-22 | 210 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
2 | DFF-3580 | WGN | MTN-MECH | PRODTECH | 2200015650 | 1. Modification of trim for DFFB-PCV-539 | Production Isolation | PCNF | PCNF | 3 | 0 | W27-W28 | 2024-07-01 | 2024-07-02 | 2024-07-01 | 2024-07-02 | 2023-09-07 | 2023-10-22 | 220 | PCNF | PCNF | DF /F /54/DFFB-PCV-539003 | Production Isolation | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235789 | 4Y 400V-N-DP MAINT-DFGA-LP-1851 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-06-14 | 2023-09-10 | 10 | AWSC | AWSC | DF /G /61/DFGA-LP-1851 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235789 | 4Y 400V-N-DP MAINT-DFGA-LP-1851 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 20 | AWSC | AWSC | DF /G /61/DFGA-LP-1851 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235789 | 4Y 400V-N-DP MAINT-DFGA-LP-1851 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 30 | AWSC | AWSC | DF /G /61/DFGA-LP-1851 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235789 | 4Y 400V-N-DP MAINT-DFGA-LP-1851 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-06-14 | 2023-09-10 | 40 | AWSC | AWSC | DF /G /61/DFGA-LP-1851 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087749 | Nød armatue DFFA-1812-10901-L1A | Nød armatue DFFA-1812-10901-L1A |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 10 |  |  | DF /F /05/DFFA-N-1812-01 | Nød armatue DFFA-1812-10901-L1A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087749 | Nød armatue DFFA-1812-10901-L1A | Nød armatue DFFA-1812-10901-L1A |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-05-05 | 2023-09-17 | 20 |  |  | DF /F /05/DFFA-N-1812-01 | Nød armatue DFFA-1812-10901-L1A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087749 | Nød armatue DFFA-1812-10901-L1A | Nød armatue DFFA-1812-10901-L1A |  |  | 2 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 30 |  |  | DF /F /05/DFFA-N-1812-01 | Nød armatue DFFA-1812-10901-L1A | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100087749 | Nød armatue DFFA-1812-10901-L1A | Nød armatue DFFA-1812-10901-L1A |  |  | 1 | 0 | Empty | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-05-05 | 2023-09-17 | 40 |  |  | DF /F /05/DFFA-N-1812-01 | Nød armatue DFFA-1812-10901-L1A | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263663 | 1Y DRAIN DISPOSAL MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-06-21 | 2023-07-21 | 10 | SECE | SECE | DF /E /28/DFEZ-V-5012 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263663 | 1Y DRAIN DISPOSAL MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-06-21 | 2023-07-21 | 20 | SECE | SECE | DF /E /28/DFEZ-V-5012 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400263663 | 1Y DRAIN DISPOSAL MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-13 | 2023-06-21 | 2023-07-21 | 30 | SECE | SECE | DF /E /28/DFEZ-V-5012 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400263663 | 1Y DRAIN DISPOSAL MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2023-06-21 | 2023-07-21 | 40 | SECE | SECE | DF /E /28/DFEZ-V-5012 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400263663 | 1Y DRAIN DISPOSAL MAINT-DFE | ISOLATION BY PRODUCTION | SECE | SECE | 0 | 0 | W33-W34 | 2024-08-12 | 2024-08-13 | 2024-08-12 | 2024-08-12 | 2023-06-21 | 2023-07-21 | 50 | SECE | SECE | DF /E /28/DFEZ-V-5012 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400221195 | 6M DRAIN DISPOSAL MAINT-DFE | DRAIN DISPOSAL MAINT-DFE |  |  | 1 | 0 | W25-W26 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2024-06-17 | 2023-01-02 | 2023-01-21 | 10 |  |  | DF /E /28/DFEZ-V-5012 | DRAIN DISPOSAL MAINT-DFE | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259012 | 6M SDV LUB/MAINT HPSEP - DFC | SDV LUB/INSP HPSEP - DFC |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-22 | 2023-06-07 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP HPSEP - DFC | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088255 | DFCXM5211 trips thermal. | Rigging and scaff | PCNFSCH | PCNFSCH | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-09-25 | 10 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5211 | Rigging and scaff | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088255 | DFCXM5211 trips thermal. | Rigging and scaff | PCNFSCH | PCNFSCH | 1 | 2 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-09-25 | 20 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5211 | Rigging and scaff | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088255 | DFCXM5211 trips thermal. | Rigging and scaff | PCNFSCH | PCNFSCH | 6 | 4 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-09-25 | 30 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5211 | Rigging and scaff | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088255 | DFCXM5211 trips thermal. | Rigging and scaff | PCNFSCH | PCNFSCH | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-09-25 | 40 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5211 | Rigging and scaff | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100088255 | DFCXM5211 trips thermal. | Rigging and scaff | PCNFSCH | PCNFSCH | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-09-25 | 50 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5211 | Rigging and scaff | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-SCAF | 2100088255 | DFCXM5211 trips thermal. | Rigging and scaff | PCNFSCH | PCNFSCH | 6 | 4 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-05-13 | 2023-09-25 | 60 | PCNFSCH | PCNFSCH | DF /C /51/DFCM-XM-5211 | Rigging and scaff | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 18 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-07-15 | 2024-07-15 | 2020-10-16 | 2021-03-15 | 10 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 2 | 12 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-07-15 | 2024-07-15 | 2020-10-16 | 2021-03-15 | 20 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 3 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-07-16 | 2024-07-17 | 2020-10-16 | 2021-03-15 | 30 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 3 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-07-17 | 2024-07-17 | 2020-10-16 | 2021-03-15 | 40 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 3 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-07-17 | 2024-07-17 | 2020-10-16 | 2021-03-15 | 50 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 3 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-09-17 | 2024-09-17 | 2020-10-16 | 2021-03-15 | 60 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 3 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-09-17 | 2024-09-18 | 2020-10-16 | 2021-03-15 | 70 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | PRODTECH | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2020-10-16 | 2021-03-15 | 80 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 2 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-09-18 | 2024-09-18 | 2020-10-16 | 2021-03-15 | 90 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 10 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2020-10-16 | 2021-03-15 | 100 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
4 | NOSD | WDF | MTN-ELEC | VEN-HVAC | 2100035819 | Replace blower motor IP/HP W/I cabin. | Check and verify overpressure is ok | PCNF | PCNF | 1 | 0 | W29-W30 | 2024-07-15 | 2024-09-19 | 2024-07-15 | 2024-07-15 | 2020-10-16 | 2021-03-15 | 110 | PCNF | PCNF | DF /F /09/DFFA-BM-1209 | Check and verify overpressure is ok | Unknown
2 | NE | WRO | MTN-TELE | MTN-TELE | 2300004742 | TME1863 - Dan F Telecom support | Fiber between FP-1007 and 2012-2+2 | PCNFSCH | PCNFSCH | 500 | 172 | W31-W32 | 2024-08-01 | 2024-08-10 | 2024-08-01 | 2024-08-01 | 2023-01-31 | 2023-03-17 | 10 | PCNFSCH | PCNFSCH | DF /C | Fiber between FP-1007 and 2012-2+2 | Unknown
2 | NE | WRO | MTN-TELE | MTN-TELE | 2300004742 | TME1863 - Dan F Telecom support | Fiber between FP-1007 and 2012-2+2 | PCNFSCH | PCNFSCH | 40 | 12 | W31-W32 | 2024-08-01 | 2024-08-10 | 2024-08-01 | 2024-08-10 | 2023-01-31 | 2023-03-17 | 20 | PCNFSCH | PCNFSCH | DF /C | Fiber between FP-1007 and 2012-2+2 | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400243997 | 6M SDV LUB/MAINT OIL - DFB | SDV LUB/INSP OIL - DFB |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-04-17 | 2023-05-03 | 10 |  |  | DF /B /03/SDV-VALVES | SDV LUB/INSP OIL - DFB | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339053 | DFB_1Y_FIRE AND BLAST-WALLS INSP | DFB_1Y_FIRE AND BLAST-WALLS INSP | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /B /02/FIRE AND BLAST-WALLS | DFB_1Y_FIRE AND BLAST-WALLS INSP | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400337280 | 6M CRANE HOIST EQUIP, DFG | CRANE HOIST EQUIP, DFG |  |  | 2 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-10-13 | 2024-11-01 | 10 |  |  | DF /G /78/DFG-LIFTING-1 | CRANE HOIST EQUIP, DFG | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007084 | Stud mounting, baseline vib meas. FG | Assist Vendor | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 10 | PCNFAWSC | PCNFAWSC | DF /G /9 | Assist Vendor | Unknown
3 | NOSD | WGN | VEN-MECH | MTN-MECH | 2200007084 | Stud mounting, baseline vib meas. FG | Assist Vendor | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 20 | PCNFAWSC | PCNFAWSC | DF /G /9 | Assist Vendor | Unknown
3 | NOSD | WGN | VEN-MECH | MTN-TURB | 2200007084 | Stud mounting, baseline vib meas. FG | Assist Vendor | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 30 | PCNFAWSC | PCNFAWSC | DF /G /9 | Assist Vendor | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007084 | Stud mounting, baseline vib meas. FG | Assist Vendor | PCNFAWSC | PCNFAWSC | 60 | 59 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 40 | PCNFAWSC | PCNFAWSC | DF /G /9 | Assist Vendor | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007084 | Stud mounting, baseline vib meas. FG | Assist Vendor | PCNFAWSC | PCNFAWSC | 180 | 155 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 50 | PCNFAWSC | PCNFAWSC | DF /G /9 | Assist Vendor | Unknown
3 | NOSD | WGN | VEN-MECH | VEN-MECH | 2200007084 | Stud mounting, baseline vib meas. FG | Assist Vendor | PCNFAWSC | PCNFAWSC | 50 | 45 | Empty | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2023-01-16 | 2021-05-28 | 2021-08-26 | 60 | PCNFAWSC | PCNFAWSC | DF /G /9 | Assist Vendor | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235043 | 1Y PIG RECEIVER MAINT-DFGA-EP-3813 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-15 | 2023-02-10 | 2023-03-12 | 10 | SECE | SECE | DF /G /34/DFGA-EP-3813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400235043 | 1Y PIG RECEIVER MAINT-DFGA-EP-3813 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-15 | 2024-07-17 | 2023-02-10 | 2023-03-12 | 20 | SECE | SECE | DF /G /34/DFGA-EP-3813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400235043 | 1Y PIG RECEIVER MAINT-DFGA-EP-3813 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 9 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-02-10 | 2023-03-12 | 30 | SECE | SECE | DF /G /34/DFGA-EP-3813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400235043 | 1Y PIG RECEIVER MAINT-DFGA-EP-3813 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-17 | 2024-07-17 | 2024-07-17 | 2023-02-10 | 2023-03-12 | 40 | SECE | SECE | DF /G /34/DFGA-EP-3813 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000809 | Create new WM server on Dan WM3 | Create new WM server on Dan WM3 |  |  | 0 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2019-03-09 | 2019-03-14 | 10 |  |  | DF /C /04 | Create new WM server on Dan WM3 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346561 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0323 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2024-08-31 | 2024-09-30 | 10 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0323 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400346561 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0323 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 20 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0323 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | VEN-MECH | 2400346561 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0323 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 3 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 25 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0323 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400346561 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0323 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 1 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-16 | 2024-08-31 | 2024-09-30 | 30 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0323 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400346561 | 1Y DELUGE SKID, SMOKE TEST-DFCM-X-0323 | ISOLATION BY PRODUCTION | AWSCSECE | AWSCSECE | 2 | 0 | W33-W34 | 2024-08-14 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2024-08-31 | 2024-09-30 | 40 | AWSCSECE | AWSCSECE | DF /C /01/DFCM-X-0323 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235770 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-01-15 | 2023-04-13 | 10 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-09C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235770 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-09 | ISOLATION ELECTRICAL | AWSC | AWSC | 11 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-24 | 2023-01-15 | 2023-04-13 | 20 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-09C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235770 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-09 | ISOLATION ELECTRICAL | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-25 | 2023-01-15 | 2023-04-13 | 30 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-09C1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235770 | 4Y 380V N-SWB MAINT-DFEZ-N-1803-09 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-01-15 | 2023-04-13 | 40 | AWSC | AWSC | DF /E /61/DFEZ-N-1803-09C1 | ISOLATION ELECTRICAL | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018148 | Replace Feeder protection 1841-M125 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 10 |  |  | DF /G /61/DFGA-N-1841-M125-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018148 | Replace Feeder protection 1841-M125 | New mat num |  |  | 1 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-27 | 2024-05-27 | 2024-10-09 | 20 |  |  | DF /G /61/DFGA-N-1841-M125-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | MTN-ELEC | 2200018148 | Replace Feeder protection 1841-M125 | New mat num |  |  | 6 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 30 |  |  | DF /G /61/DFGA-N-1841-M125-02 | New mat num | Unknown
3 | Empty | WGN | VEN-ELEC | VEN-ELEC | 2200018148 | Replace Feeder protection 1841-M125 | New mat num |  |  | 0 | 0 | Empty | 2024-05-27 | 2024-05-29 | 2024-05-29 | 2024-05-29 | 2024-05-27 | 2024-10-09 | 40 |  |  | DF /G /61/DFGA-N-1841-M125-02 | New mat num | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097348 | DFGA-HRF-03302 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-03 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 10 | SECE | SECE | DF /G /01/DFGA-HRF-03302 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100097348 | DFGA-HRF-03302 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 2 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 20 | SECE | SECE | DF /G /01/DFGA-HRF-03302 | Replace hose on hosereel | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100097348 | DFGA-HRF-03302 hose reel to be replaced | Replace hose on hosereel | SECE | SECE | 1 | 0 | Empty | 2024-09-03 | 2024-09-04 | 2024-09-04 | 2024-09-04 | 2023-10-19 | 2024-03-02 | 30 | SECE | SECE | DF /G /01/DFGA-HRF-03302 | Replace hose on hosereel | Unknown
B | NOSD | WPM | MTN-MECH | MTN-MECH | 2400241117 | 6M SDV LUB/MAINT - DFA/B/C/E | SDV LUB/INSP - DFA/B/C/E |  |  | 15 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-08-02 | 2023-03-19 | 2023-04-04 | 10 |  |  | DF /C /03/SDV-VALVES | SDV LUB/INSP - DFA/B/C/E | Unknown
3 | DFE-W01 | WDF | MTN-MECH | MTN-SCAF | 2100057416 | ½" welded WI HCV leaking at valve handle | Prepare matr/tool |  |  | 18 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-03 | 2021-11-13 | 2022-02-11 | 10 |  |  | DF /E /55/DFE01-WATER-INJECTION-LINE | Prepare matr/tool | Unknown
3 | DFE-W01 | WDF | MTN-MECH | MTN-MECH | 2100057416 | ½" welded WI HCV leaking at valve handle | Prepare matr/tool |  |  | 1 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-01 | 2021-11-13 | 2022-02-11 | 20 |  |  | DF /E /55/DFE01-WATER-INJECTION-LINE | Prepare matr/tool | Unknown
3 | DFE-W01 | WDF | MTN-MECH | PRODTECH | 2100057416 | ½" welded WI HCV leaking at valve handle | Prepare matr/tool |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-03 | 2021-11-13 | 2022-02-11 | 30 |  |  | DF /E /55/DFE01-WATER-INJECTION-LINE | Prepare matr/tool | Unknown
3 | DFE-W01 | WDF | MTN-MECH | MTN-MECH | 2100057416 | ½" welded WI HCV leaking at valve handle | Prepare matr/tool |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-03 | 2025-01-04 | 2021-11-13 | 2022-02-11 | 40 |  |  | DF /E /55/DFE01-WATER-INJECTION-LINE | Prepare matr/tool | Unknown
3 | DFE-W01 | WDF | MTN-MECH | PRODTECH | 2100057416 | ½" welded WI HCV leaking at valve handle | Prepare matr/tool |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-04 | 2025-01-05 | 2021-11-13 | 2022-02-11 | 50 |  |  | DF /E /55/DFE01-WATER-INJECTION-LINE | Prepare matr/tool | Unknown
3 | DFE-W01 | WDF | MTN-MECH | MTN-SCAF | 2100057416 | ½" welded WI HCV leaking at valve handle | Prepare matr/tool |  |  | 12 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2021-11-13 | 2022-02-11 | 60 |  |  | DF /E /55/DFE01-WATER-INJECTION-LINE | Prepare matr/tool | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-15 | 2020-09-10 | 2020-12-09 | 9 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-15 | 2020-09-10 | 2020-12-09 | 10 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ROPE | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 18 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-15 | 2024-07-17 | 2020-09-10 | 2020-12-09 | 20 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-17 | 2024-07-19 | 2020-09-10 | 2020-12-09 | 30 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-ELEC | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 10 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-19 | 2024-07-21 | 2020-09-10 | 2020-12-09 | 40 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 6 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-21 | 2024-07-23 | 2020-09-10 | 2020-12-09 | 50 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | PRODTECH | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2020-09-10 | 2020-12-09 | 70 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2020-09-10 | 2020-12-09 | 80 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-CRAN | MTN-CRAN | 2100036720 | DFE/78: Replace Corroded Ex cabinet top | deisolate crane |  |  | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-23 | 2024-07-23 | 2024-07-23 | 2020-09-10 | 2020-12-09 | 81 |  |  | DF /E /78/DFEZ-X-6150 | deisolate crane | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101415 | Breaker for DFFB-MM-3551A not working | additional materials |  |  | 3 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-12-13 | 2024-04-26 | 10 |  |  | DF /F /51/DFFB-MM-3551A | additional materials | Unknown
3 | NOSD | WDF | MTN-ELEC | MTN-ELEC | 2100101415 | Breaker for DFFB-MM-3551A not working | additional materials |  |  | 0 | 0 | W21-W22 | 2024-07-29 | 2024-07-30 | 2024-07-30 | 2024-07-30 | 2023-12-13 | 2024-04-26 | 20 |  |  | DF /F /51/DFFB-MM-3551A | additional materials | Unknown
2 | NOSD | WDF | MTN-INST | MTN-INST | 2100104499 | Flow out of Test FF is faulty | Faultfinding |  |  | 5 | 12 | W31-W32 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2024-01-01 | 2024-02-15 | 10 |  |  | DF /F /20/DFFA-FE-340311 | Faultfinding | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100035089 | Maintenance Follow-up DFGA-FI-570017 | Remove old Flowmeter |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 10 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035089 | Maintenance Follow-up DFGA-FI-570017 | Remove old Flowmeter |  |  | 1.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 20 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035089 | Maintenance Follow-up DFGA-FI-570017 | Remove old Flowmeter |  |  | 1.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 30 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100035089 | Maintenance Follow-up DFGA-FI-570017 | Remove old Flowmeter |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 40 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100035089 | Maintenance Follow-up DFGA-FI-570017 | Remove old Flowmeter |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 50 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-INST | 2100035089 | Maintenance Follow-up DFGA-FI-570017 | Remove old Flowmeter |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2020-10-06 | 2021-03-05 | 60 |  |  | DF /G /70/DFG-PURGEGAS-1 | Remove old Flowmeter | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400230508 | 1Y SAND REMOVAL SYSTEM TEST-DFFA-A-5002 | SAND REMOVAL SYSTEM TEST-DFFA-A-5002 | SECE | SECE | 15 | 0 | W33-W34 | 2024-08-12 | 2024-08-16 | 2024-08-12 | 2024-08-16 | 2023-01-25 | 2023-02-24 | 10 | SECE | SECE | DF /F /27/DFFA-A-5002 | SAND REMOVAL SYSTEM TEST-DFFA-A-5002 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 12 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-16 | 2020-02-12 | 2020-05-12 | 5 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-16 | 2024-09-17 | 2020-02-12 | 2020-05-12 | 10 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 15 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-17 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 20 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 3 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-19 | 2020-02-12 | 2020-05-12 | 30 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 8 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2020-02-12 | 2020-05-12 | 40 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 50 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025198 | DFGA-LG-410550 changeout of LG and HCV's | Isolate DFGA-LG-410550 LG and HCV |  |  | 0 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2020-02-12 | 2020-05-12 | 60 |  |  | DF /G /30/DFGA-LG-410550 | Isolate DFGA-LG-410550 LG and HCV | Unknown
3 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 5 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2021-07-28 | 2021-09-06 | 10 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2021-07-28 | 2021-09-06 | 20 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-INST | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2021-07-28 | 2021-09-06 | 30 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-03 | 2021-07-28 | 2021-09-06 | 40 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-04 | 2025-01-04 | 2021-07-28 | 2021-09-06 | 50 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-05 | 2021-07-28 | 2021-09-06 | 60 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2025-01-06 | 2021-07-28 | 2021-09-06 | 70 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-INST | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-07 | 2021-07-28 | 2021-09-06 | 80 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-08 | 2021-07-28 | 2021-09-06 | 90 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 1 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2021-07-28 | 2021-09-06 | 100 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-08 | 2021-07-28 | 2021-09-06 | 110 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 5 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-02 | 2021-07-28 | 2021-09-06 | 130 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-02 | 2021-07-28 | 2021-09-06 | 140 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-INST | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-02 | 2025-01-03 | 2021-07-28 | 2021-09-06 | 150 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-RIGG | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 8 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-03 | 2025-01-05 | 2021-07-28 | 2021-09-06 | 160 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-05 | 2025-01-06 | 2021-07-28 | 2021-09-06 | 170 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-06 | 2025-01-07 | 2021-07-28 | 2021-09-06 | 180 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 4 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-07 | 2025-01-08 | 2021-07-28 | 2021-09-06 | 190 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-INST | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-08 | 2021-07-28 | 2021-09-06 | 200 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | PRODTECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2021-07-28 | 2021-09-06 | 210 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 1 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-08 | 2025-01-08 | 2021-07-28 | 2021-09-06 | 220 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 3 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2021-07-28 | 2021-09-06 | 230 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
3 | DFB-OIL | WDF | MTN-MECH | MTN-MECH | 2100052620 | (DFB16)XCV-30410 & 30401 intern leaking | Aktuator to Score- put on MN 1274540 |  |  | 0 | 0 | Empty | 2025-01-01 | 2025-01-09 | 2025-01-01 | 2025-01-01 | 2021-07-28 | 2021-09-06 | 240 |  |  | DF /B /10/DFBA-XCV-30410 | Aktuator to Score- put on MN 1274540 | Unknown
A | NOSD | WPM | MTN-INST | MTN-ROPE | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 8 | 0 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-15 | 2024-07-17 | 2024-05-28 | 2024-06-27 | 10 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 3 | 0 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-17 | 2024-07-18 | 2024-05-28 | 2024-06-27 | 20 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-INST | MTN-INST | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 26 | 45 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-18 | 2024-07-24 | 2024-05-28 | 2024-06-27 | 30 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-INST | MTN-MECH | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 3 | 6 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-24 | 2024-07-25 | 2024-05-28 | 2024-06-27 | 40 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-INST | PRODTECH | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 3 | 0 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-25 | 2024-07-26 | 2024-05-28 | 2024-06-27 | 50 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-INST | MTN-ROPE | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 8 | 0 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-26 | 2024-07-28 | 2024-05-28 | 2024-06-27 | 60 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-INST | MTN-PIPF | 2400329995 | 1Y SYSTEM 20 INSTRUMENT/VALVE MAINT-DFF | Rope Access Assistance | SCHSECE | SCHSECE | 0 | 14 | W29-W30 | 2024-07-15 | 2024-07-28 | 2024-07-28 | 2024-07-28 | 2024-05-28 | 2024-06-27 | 70 | SCHSECE | SCHSECE | DF /F /20/INSTRUMENTS | Rope Access Assistance | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ROUS | 2400306655 | 1Y H2S ESCAPE EQ. LOCKERS MAINT - DF | H2S ESCAPE EQ. LOCKERS INSP - DF | PCNFSECE | PCNFSECE | 6 | 7 | Empty | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-01-21 | 2024-02-20 | 10 | PCNFSECE | PCNFSECE | DF /C /02/FIREMANS-EQUIPMENT | H2S ESCAPE EQ. LOCKERS INSP - DF | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 4 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-07-29 | 2024-07-30 | 2023-04-06 | 2025-09-22 | 10 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 50 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-07-30 | 2024-08-05 | 2023-04-06 | 2025-09-22 | 20 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 20 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-08-05 | 2024-08-08 | 2023-04-06 | 2025-09-22 | 30 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 12 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-08-08 | 2024-08-11 | 2023-04-06 | 2025-09-22 | 40 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 12 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-08-11 | 2024-08-14 | 2023-04-06 | 2025-09-22 | 50 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 28 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-08-11 | 2024-08-14 | 2023-04-06 | 2025-09-22 | 60 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-PAIN | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 24 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-08-14 | 2024-08-16 | 2023-04-06 | 2025-09-22 | 70 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076004 | DFFE: Replace buffer, bolts and support | order bolts+washer for support beam |  |  | 0 | 0 | Empty | 2024-07-29 | 2024-08-16 | 2024-07-29 | 2024-07-29 | 2023-04-06 | 2025-09-22 | 80 |  |  | DF /F /78/DFFA-A-6101 | order bolts+washer for support beam | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286640 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | RETURN TO OPERATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-12 | 2023-10-14 | 2023-11-19 | 10 |  |  | DF /C /09/DFCC-A-1216 | RETURN TO OPERATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286640 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | RETURN TO OPERATION |  |  | 10 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-12 | 2024-08-15 | 2023-10-14 | 2023-11-19 | 20 |  |  | DF /C /09/DFCC-A-1216 | RETURN TO OPERATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286640 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | RETURN TO OPERATION |  |  | 1 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2023-10-14 | 2023-11-19 | 30 |  |  | DF /C /09/DFCC-A-1216 | RETURN TO OPERATION | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400286640 | 1Y HVAC SUPPLY AHU CHECK DFCC-A-1216 | RETURN TO OPERATION |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-15 | 2024-08-15 | 2024-08-15 | 2023-10-14 | 2023-11-19 | 40 |  |  | DF /C /09/DFCC-A-1216 | RETURN TO OPERATION | Unknown
3 | NOSD | WDF | MTN-ROPE | WELLSUPV | 2100053640 | ANOPR-FLM: Incorrect spec blind flange & | Incorrect spec blind flange & gasket |  |  | 0 | 0 | Empty | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-12-03 | 10 |  |  | DF /C /51/DFC-6-WS-052-0025-AM-U | Incorrect spec blind flange & gasket | Unknown
3 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100053640 | ANOPR-FLM: Incorrect spec blind flange & | Incorrect spec blind flange & gasket |  |  | 0 | 0 | Empty | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-09-04 | 2021-12-03 | 20 |  |  | DF /C /51/DFC-6-WS-052-0025-AM-U | Incorrect spec blind flange & gasket | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057553 | FLMR DFB - Replacement Handrail EL. 26.2 | DFB - Replacement Handrail EL. 26.200 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 10 |  |  | DF /B /86/26200 - HANDRAILS | DFB - Replacement Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057553 | FLMR DFB - Replacement Handrail EL. 26.2 | DFB - Replacement Handrail EL. 26.200 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 20 |  |  | DF /B /86/26200 - HANDRAILS | DFB - Replacement Handrail EL. 26.200 | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100057553 | FLMR DFB - Replacement Handrail EL. 26.2 | DFB - Replacement Handrail EL. 26.200 |  |  | 0 | 0 | Empty | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-06-15 | 30 |  |  | DF /B /86/26200 - HANDRAILS | DFB - Replacement Handrail EL. 26.200 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-07-26 | 2024-07-26 | 2022-01-07 | 2022-06-06 | 10 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 48 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-07-26 | 2024-07-28 | 2022-01-07 | 2022-06-06 | 20 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 200 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-07-28 | 2024-08-08 | 2022-01-07 | 2022-06-06 | 30 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | PRODTECH | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-08 | 2024-08-08 | 2022-01-07 | 2022-06-06 | 40 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 48 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-08 | 2024-08-10 | 2022-01-07 | 2022-06-06 | 50 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-RIGG | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-10 | 2024-08-10 | 2022-01-07 | 2022-06-06 | 60 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 100 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-10 | 2024-08-15 | 2022-01-07 | 2022-06-06 | 70 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-PIPF | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 24 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-15 | 2024-08-17 | 2022-01-07 | 2022-06-06 | 80 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | PRODTECH | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2022-01-07 | 2022-06-06 | 90 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
4 | NE | WDF | MTN-MECH | MTN-MECH | 2100057178 | ANOPR: Utility & Instrument Air Batch-01 | External corrosion to DFB-1"-AU-54854-A1 |  |  | 0 | 0 | Empty | 2024-07-26 | 2024-08-17 | 2024-08-17 | 2024-08-17 | 2022-01-07 | 2022-06-06 | 100 |  |  | DF /B /07/DFB-1-AU-054-0854-A1-U | External corrosion to DFB-1"-AU-54854-A1 | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235761 | 4Y 380V UPS-DP F.TEST DFCC-DP-1910 | 380V UPS-DP F.TEST DFCC-DP-1910 | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-13 | 10 | AWSCSECE | AWSCSECE | DF /C /06/DFCC-DP-1910 | 380V UPS-DP F.TEST DFCC-DP-1910 | Unknown
3 | DFA-O05 | WDF | MTN-INST | PRODTECH | 2100077152 | DFA-05 Choke ZT unstable feed back | Replace and adjust position transmitter |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-12-13 | 2023-04-27 | 10 |  |  | DF /A /10/DFAA-CVA-30005 | Replace and adjust position transmitter | Unknown
3 | DFA-O05 | WDF | MTN-INST | MTN-INST | 2100077152 | DFA-05 Choke ZT unstable feed back | Replace and adjust position transmitter |  |  | 0.5 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-12-13 | 2023-04-27 | 20 |  |  | DF /A /10/DFAA-CVA-30005 | Replace and adjust position transmitter | Unknown
3 | DFA-O05 | WDF | MTN-INST | MTN-INST | 2100077152 | DFA-05 Choke ZT unstable feed back | Replace and adjust position transmitter |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-12-13 | 2023-04-27 | 30 |  |  | DF /A /10/DFAA-CVA-30005 | Replace and adjust position transmitter | Unknown
3 | DFA-O05 | WDF | MTN-INST | MTN-INST | 2100077152 | DFA-05 Choke ZT unstable feed back | Replace and adjust position transmitter |  |  | 1 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-12-13 | 2023-04-27 | 40 |  |  | DF /A /10/DFAA-CVA-30005 | Replace and adjust position transmitter | Unknown
3 | DFA-O05 | WDF | MTN-INST | PRODTECH | 2100077152 | DFA-05 Choke ZT unstable feed back | Replace and adjust position transmitter |  |  | 2 | 0 | Empty | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2022-12-13 | 2023-04-27 | 50 |  |  | DF /A /10/DFAA-CVA-30005 | Replace and adjust position transmitter | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400344327 | 6M INST AIR SYS MAINT - A-5485/86/87/93 | INST AIR SYS MAINT - A-5485/86/87/93 |  |  | 14 | 0 | Empty | 2024-09-10 | 2024-09-13 | 2024-09-10 | 2024-09-13 | 2024-09-10 | 2024-09-29 | 10 |  |  | DF /C /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYS MAINT - A-5485/86/87/93 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-INST | 2400344327 | 6M INST AIR SYS MAINT - A-5485/86/87/93 | INST AIR SYS MAINT - A-5485/86/87/93 |  |  | 2 | 0 | Empty | 2024-09-10 | 2024-09-13 | 2024-09-13 | 2024-09-13 | 2024-09-10 | 2024-09-29 | 20 |  |  | DF /C /07/INSTRUMENT-AIR-SYSTEM | INST AIR SYS MAINT - A-5485/86/87/93 | Unknown
4 | DFFHPSEP | WRO | MTN-TELE | MTN-TELE | 2300000939 | Range change DFRODS1 DFF-FIT-500435 | Range change DFRODS1 FIT-500435 | AWSC | AWSC | 5 | 0 | Empty | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-05-17 | 2019-07-12 | 2020-07-06 | 10 | AWSC | AWSC | DF /F /04/DFFA-FP-2093 | Range change DFRODS1 FIT-500435 | Unknown
4 | DFFHPSEP | WRO | MTN-TELE | MTN-TELE | 2300000939 | Range change DFRODS1 DFF-FIT-500435 | Range change DFRODS1 FIT-500435 | AWSC | AWSC | 3 | 0 | Empty | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-05-16 | 2019-07-12 | 2020-07-06 | 20 | AWSC | AWSC | DF /F /04/DFFA-FP-2093 | Range change DFRODS1 FIT-500435 | Unknown
4 | DFFHPSEP | WRO | MTN-TELE | MTN-TELE | 2300000939 | Range change DFRODS1 DFF-FIT-500435 | Range change DFRODS1 FIT-500435 | AWSC | AWSC | 0 | 0 | Empty | 2024-05-16 | 2024-05-17 | 2024-05-16 | 2024-05-16 | 2019-07-12 | 2020-07-06 | 30 | AWSC | AWSC | DF /F /04/DFFA-FP-2093 | Range change DFRODS1 FIT-500435 | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2023-12-27 | 2024-02-10 | 10 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-07-30 | 2023-12-27 | 2024-02-10 | 20 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-08-01 | 2023-12-27 | 2024-02-10 | 30 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-31 | 2023-12-27 | 2024-02-10 | 40 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-31 | 2024-08-01 | 2023-12-27 | 2024-02-10 | 50 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-RIGG | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-03 | 2023-12-27 | 2024-02-10 | 60 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 8 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-30 | 2024-08-01 | 2023-12-27 | 2024-02-10 | 70 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2023-12-27 | 2024-02-10 | 80 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | PRODTECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2023-12-27 | 2024-02-10 | 90 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
2 | NE | WDF | MTN-MECH | MTN-MECH | 2100104299 | DFF-PCV-530001 needs cleaning. | Isolate DFF-PCV-530001 |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-02 | 2023-12-27 | 2024-02-10 | 100 |  |  | DF /F /50/DFFA-PCV-530001 | Isolate DFF-PCV-530001 | Unknown
4 | NOSD | WRO | MTN-TELE | MTN-TELE | 2300000846 | Upgrade of DAN F F&G MB300 Network. | Upgrade of DAN F F&G MB300 Network. |  |  | 400 | 0 | W21-W22 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2024-05-20 | 2017-01-17 | 2017-11-13 | 10 |  |  | DF /C /03 | Upgrade of DAN F F&G MB300 Network. | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339189 | DFE_1Y_JACKET ABOVE WATER INSPECTION | DFE_1Y_JACKET ABOVE WATER INSPECTION | AWSCSECE | AWSCSECE | 4 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /E /86/STR CAISSON - LAT TO EL22400 | DFE_1Y_JACKET ABOVE WATER INSPECTION | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100022472 | Purchase of parts for Dump Valves | Install new possitioner acc. to manual | AWSC | AWSC | 1 | 0 | No materials ordered! | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2024-09-18 | 2019-08-22 | 2019-10-01 | 10 | AWSC | AWSC | DF /G /54 | Install new possitioner acc. to manual | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100022472 | Purchase of parts for Dump Valves | Install new possitioner acc. to manual | AWSC | AWSC | 4 | 0 | No materials ordered! | 2024-09-18 | 2024-09-23 | 2024-09-18 | 2024-09-19 | 2019-08-22 | 2019-10-01 | 20 | AWSC | AWSC | DF /G /54 | Install new possitioner acc. to manual | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100022472 | Purchase of parts for Dump Valves | Install new possitioner acc. to manual | AWSC | AWSC | 10 | 0 | No materials ordered! | 2024-09-18 | 2024-09-23 | 2024-09-19 | 2024-09-22 | 2019-08-22 | 2019-10-01 | 30 | AWSC | AWSC | DF /G /54 | Install new possitioner acc. to manual | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100022472 | Purchase of parts for Dump Valves | Install new possitioner acc. to manual | AWSC | AWSC | 2 | 0 | No materials ordered! | 2024-09-18 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2019-08-22 | 2019-10-01 | 40 | AWSC | AWSC | DF /G /54 | Install new possitioner acc. to manual | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100022472 | Purchase of parts for Dump Valves | Install new possitioner acc. to manual | AWSC | AWSC | 2 | 0 | No materials ordered! | 2024-09-18 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2019-08-22 | 2019-10-01 | 50 | AWSC | AWSC | DF /G /54 | Install new possitioner acc. to manual | Unknown
3 | DFG-3590 | WDF | MTN-INST | MTN-INST | 2100022472 | Purchase of parts for Dump Valves | Install new possitioner acc. to manual | AWSC | AWSC | 2 | 0 | No materials ordered! | 2024-09-18 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2019-08-22 | 2019-10-01 | 60 | AWSC | AWSC | DF /G /54 | Install new possitioner acc. to manual | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004061 | DK40 - REplaced by 2300004287 | Increase of PO 4300029290 Hytor |  |  | 0 | 0 | Empty | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2025-07-23 | 10 |  |  | DF /C /84 | Increase of PO 4300029290 Hytor | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004061 | DK40 - REplaced by 2300004287 | Increase of PO 4300029290 Hytor |  |  | 0 | 0 | Empty | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2025-07-23 | 20 |  |  | DF /C /84 | Increase of PO 4300029290 Hytor | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004061 | DK40 - REplaced by 2300004287 | Increase of PO 4300029290 Hytor |  |  | 0 | 0 | Empty | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2025-07-23 | 30 |  |  | DF /C /84 | Increase of PO 4300029290 Hytor | Unknown
4 | NOSD | WRO | PRODTECH | PRODTECH | 2300004061 | DK40 - REplaced by 2300004287 | Increase of PO 4300029290 Hytor |  |  | 0 | 0 | Empty | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2023-02-04 | 2025-07-23 | 40 |  |  | DF /C /84 | Increase of PO 4300029290 Hytor | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024961 | change DFFA-XCV-500751 | L3 Isolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2019-03-27 | 2019-06-25 | 10 |  |  | DF /F /27/DFFA-XCV-500751 | L3 Isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024961 | change DFFA-XCV-500751 | L3 Isolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2019-03-27 | 2019-06-25 | 20 |  |  | DF /F /27/DFFA-XCV-500751 | L3 Isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024961 | change DFFA-XCV-500751 | L3 Isolate system |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2019-03-27 | 2019-06-25 | 30 |  |  | DF /F /27/DFFA-XCV-500751 | L3 Isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024961 | change DFFA-XCV-500751 | L3 Isolate system |  |  | 0.5 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2019-03-27 | 2019-06-25 | 40 |  |  | DF /F /27/DFFA-XCV-500751 | L3 Isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100024961 | change DFFA-XCV-500751 | L3 Isolate system |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2019-03-27 | 2019-06-25 | 50 |  |  | DF /F /27/DFFA-XCV-500751 | L3 Isolate system | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024961 | change DFFA-XCV-500751 | L3 Isolate system |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2019-03-27 | 2019-06-25 | 333 |  |  | DF /F /27/DFFA-XCV-500751 | L3 Isolate system | Unknown
A | DFG-1640 | WPM | MTN-TURB | PRODTECH | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 5 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-19 | 2024-07-20 | 2024-04-08 | 2024-05-08 | 10 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | DFG-1640 | WPM | MTN-TURB | MTN-TURB | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 32 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-20 | 2024-07-24 | 2024-04-08 | 2024-05-08 | 20 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | DFG-1640 | WPM | MTN-TURB | MTN-INST | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 18 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-24 | 2024-07-26 | 2024-04-08 | 2024-05-08 | 30 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | DFG-1640 | WPM | MTN-TURB | MTN-ELEC | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 18 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-26 | 2024-07-28 | 2024-04-08 | 2024-05-08 | 40 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | DFG-1640 | WPM | MTN-TURB | PRODTECH | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 5 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-28 | 2024-07-29 | 2024-04-08 | 2024-05-08 | 50 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | DFG-1640 | WPM | MTN-TURB | MTN-TURB | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 0 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-29 | 2024-07-29 | 2024-04-08 | 2024-05-08 | 60 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | DFG-1640 | WPM | MTN-TURB | MTN-TURB | 2400321374 | 8KH MAIN GEN. SERVICE,COUNTER-A-1640 | Missing materials in kit added seperatel | AWSCSECE | AWSCSECE | 16 | 16 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2024-04-08 | 2024-05-08 | 70 | AWSCSECE | AWSCSECE | DF /G /60/DFGA-A-1640 | Missing materials in kit added seperatel | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235736 | 4Y 380V E-DP MAINT EME.LGHT DFFA-DP-1813 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 | SECE | SECE | DF /F /05/DFFA-DP-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235736 | 4Y 380V E-DP MAINT EME.LGHT DFFA-DP-1813 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-15 | 2024-09-16 | 2023-04-15 | 2023-06-27 | 20 | SECE | SECE | DF /F /05/DFFA-DP-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235736 | 4Y 380V E-DP MAINT EME.LGHT DFFA-DP-1813 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-04-15 | 2023-06-27 | 30 | SECE | SECE | DF /F /05/DFFA-DP-1813 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235736 | 4Y 380V E-DP MAINT EME.LGHT DFFA-DP-1813 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 0 | Empty | 2024-09-15 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2023-04-15 | 2023-06-27 | 40 | SECE | SECE | DF /F /05/DFFA-DP-1813 | ISOLATION BY PRODUCTION | Unknown
C | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400259308 | 1Y BRIDGE TROLLEY 10T - DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | AWSC | AWSC | 10 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-05 | 2024-10-07 | 2023-05-07 | 2023-06-12 | 10 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400259308 | 1Y BRIDGE TROLLEY 10T - DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | AWSC | AWSC | 7 | 0 | Empty | 2024-10-05 | 2024-10-09 | 2024-10-07 | 2024-10-09 | 2023-05-07 | 2023-06-12 | 20 | AWSC | AWSC | DF /F /78/DFFZ-X-6150 | BRIDGE TROLLEY MAINT 10T - DFFZ-X-6150 | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100024567 | DFC hydro cyclone reject DFCM-XCV-50408 | Vendor to Troubleshoot on XCV-50408 | AWSC | AWSC | 6 | 0 | W23-W24 | 2024-06-03 | 2024-06-04 | 2024-06-03 | 2024-06-04 | 2019-10-21 | 2020-10-15 | 70 | AWSC | AWSC | DF /C /27/DFCM-XCV-50408 | Vendor to Troubleshoot on XCV-50408 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400264129 | 1Y WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-15 | 2023-06-28 | 2023-07-28 | 10 | SECE | SECE | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400264129 | 1Y WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA | SECE | SECE | 14 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-19 | 2023-06-28 | 2023-07-28 | 20 | SECE | SECE | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400264129 | 1Y WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA | SECE | SECE | 9 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-19 | 2024-09-21 | 2023-06-28 | 2023-07-28 | 30 | SECE | SECE | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400264129 | 1Y WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2023-06-28 | 2023-07-28 | 40 | SECE | SECE | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400264129 | 1Y WELLHEAD CONTROL PANELS MAINT- DFA | WELLHEAD CONTROL PANELS MAINT- DFA | SECE | SECE | 2 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2023-06-28 | 2023-07-28 | 50 | SECE | SECE | DF /A /07/WELLHEAD-CONTROL-PANELS | WELLHEAD CONTROL PANELS MAINT- DFA | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 1 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-19 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 10 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 1 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-20 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 19 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 9 | 9 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-20 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 20 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 9 | 9 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-20 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 30 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 2 | 15 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-21 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 40 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 24 | 24 | Empty | 2024-06-10 | 2024-06-16 | 2022-01-03 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 45 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-ROPE | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 10 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-21 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 50 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2021-12-21 | 2022-06-02 | 2021-10-24 | 2021-12-03 | 60 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-10 | 2024-06-10 | 2021-10-24 | 2021-12-03 | 70 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 20 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-10 | 2024-06-12 | 2021-10-24 | 2021-12-03 | 75 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 18 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-12 | 2024-06-14 | 2021-10-24 | 2021-12-03 | 77 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 20 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-14 | 2024-06-16 | 2021-10-24 | 2021-12-03 | 80 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2021-10-24 | 2021-12-03 | 90 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2021-10-24 | 2021-12-03 | 100 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2021-10-24 | 2021-12-03 | 110 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100056840 | Refurbished Winch to be installed LB2 an | Preparing equipment | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2024-06-10 | 2024-06-16 | 2024-06-16 | 2024-06-16 | 2021-10-24 | 2021-12-03 | 120 | PCNFAWSC | PCNFAWSC | DF /G /02/DFGA-X-0702 | Preparing equipment | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400232984 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-02 | PO Caverion | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-15 | 2022-12-01 | 2023-02-27 | 10 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-02 | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232984 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-02 | PO Caverion | AWSC | AWSC | 29 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-15 | 2024-09-18 | 2022-12-01 | 2023-02-27 | 20 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-02 | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | VEN-ELEC | 2400232984 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-02 | PO Caverion | AWSC | AWSC | 9 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-18 | 2024-09-19 | 2022-12-01 | 2023-02-27 | 30 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-02 | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | PRODTECH | 2400232984 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-02 | PO Caverion | AWSC | AWSC | 1 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2022-12-01 | 2023-02-27 | 40 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-02 | PO Caverion | Unknown
C | DAN-OIL | WPM | MTN-ELEC | MTN-ELEC | 2400232984 | 4Y 3KV N-SWB MAINT-DFFA-N-1801B-02 | PO Caverion | AWSC | AWSC | 0 | 0 | Empty | 2024-09-15 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2022-12-01 | 2023-02-27 | 50 | AWSC | AWSC | DF /F /61/DFFA-N-1801B-02 | PO Caverion | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235648 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L10B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235648 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L10 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-22 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L10B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235648 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L10B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235648 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L10 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-23 | 2024-09-23 | 2024-09-23 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L10B | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235655 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R12 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-22 | 2023-03-16 | 2023-06-12 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R12A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235655 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R12 | ISOLATION ELECTRICAL | AWSC | AWSC | 16 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-22 | 2024-09-26 | 2023-03-16 | 2023-06-12 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R12A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235655 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R12 | ISOLATION ELECTRICAL | AWSC | AWSC | 5 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-26 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R12A1 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235655 | 4Y 400V N-SWB MAINT-DFCI-N-1802-R12 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2023-03-16 | 2023-06-12 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-R12A1 | ISOLATION ELECTRICAL | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 3 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2018-11-19 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 10 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 20 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2018-11-19 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 20 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | VEN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 3 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2018-11-19 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 30 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 12 | 12 | CNF | 2024-06-03 | 2024-06-03 | 2018-11-19 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 40 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 3 | 3 | CNF | 2024-06-03 | 2024-06-03 | 2019-11-18 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 50 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 20 | 6 | CNF | 2024-06-03 | 2024-06-03 | 2019-11-18 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 60 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 3 | 3 | CNF | 2024-06-03 | 2024-06-03 | 2019-11-18 | 2020-12-14 | 2018-03-07 | 2018-06-05 | 70 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 3 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2018-03-07 | 2018-06-05 | 80 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 4 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2018-03-07 | 2018-06-05 | 90 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 3 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2018-03-07 | 2018-06-05 | 100 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025380 | FB REPL hoses on HIFOG DFBA-A-0460 | Safing DFBA-A-0460 | PCNFAWSC | PCNFAWSC | 0 | 0 | CNF | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2018-03-07 | 2018-06-05 | 110 | PCNFAWSC | PCNFAWSC | DF /B /01/DFBA-A-0460 | Safing DFBA-A-0460 | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085823 | DFF-P-3914 bleed valve leaking | DFF-P-3914 bleed valve leaking |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-05 | 2023-08-18 | 10 |  |  | DF /F /75/DFFA-P-3914 | DFF-P-3914 bleed valve leaking | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100085823 | DFF-P-3914 bleed valve leaking | DFF-P-3914 bleed valve leaking |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-05 | 2023-08-18 | 20 |  |  | DF /F /75/DFFA-P-3914 | DFF-P-3914 bleed valve leaking | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085823 | DFF-P-3914 bleed valve leaking | DFF-P-3914 bleed valve leaking |  |  | 3 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-05 | 2023-08-18 | 30 |  |  | DF /F /75/DFFA-P-3914 | DFF-P-3914 bleed valve leaking | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085823 | DFF-P-3914 bleed valve leaking | DFF-P-3914 bleed valve leaking |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-30 | 2023-04-05 | 2023-08-18 | 40 |  |  | DF /F /75/DFFA-P-3914 | DFF-P-3914 bleed valve leaking | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100085823 | DFF-P-3914 bleed valve leaking | DFF-P-3914 bleed valve leaking |  |  | 0 | 0 | W27-W28 | 2024-07-29 | 2024-07-30 | 2024-07-29 | 2024-07-29 | 2023-04-05 | 2023-08-18 | 50 |  |  | DF /F /75/DFFA-P-3914 | DFF-P-3914 bleed valve leaking | Unknown
3 | NOSD | WGN | MTN-INST | MTN-INST | 2200012416 | DAF LTE Installation | DAF LTE Installation |  |  | 0 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2022-12-30 | 2023-05-14 | 10 |  |  | DF /C /08 | DAF LTE Installation | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235643 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L05 | 400V N-SWB INSP-DFCI-N-1802-L05 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2023-03-01 | 2023-05-28 | 10 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L05B1 | 400V N-SWB INSP-DFCI-N-1802-L05 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235643 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L05 | 400V N-SWB INSP-DFCI-N-1802-L05 | AWSC | AWSC | 12 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-25 | 2023-03-01 | 2023-05-28 | 20 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L05B1 | 400V N-SWB INSP-DFCI-N-1802-L05 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235643 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L05 | 400V N-SWB INSP-DFCI-N-1802-L05 | AWSC | AWSC | 4 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 30 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L05B1 | 400V N-SWB INSP-DFCI-N-1802-L05 | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235643 | 4Y 400V N-SWB MAINT-DFCI-N-1802-L05 | 400V N-SWB INSP-DFCI-N-1802-L05 | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2023-03-01 | 2023-05-28 | 40 | AWSC | AWSC | DF /C /61/DFCI-N-1802-L05B1 | 400V N-SWB INSP-DFCI-N-1802-L05 | Unknown
A | NOSD | WPM | INP-SITE | VEN-INSP | 2400339287 | DFF_1Y_BRIDGE F-G INT STRUCT INSP - GVI | DFF_1Y_BRIDGE F-G INT STRUCT INSP - GVI | AWSCSECE | AWSCSECE | 8 | 0 | Empty | 2024-12-01 | 2025-01-30 | 2024-12-01 | 2025-01-29 | 2024-12-01 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /86/BRIDGE-DFF-DFG | DFF_1Y_BRIDGE F-G INT STRUCT INSP - GVI | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 4 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-29 | 2024-07-30 | 2020-04-10 | 2020-07-09 | 5 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-30 | 2020-04-10 | 2020-07-09 | 10 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-30 | 2024-07-31 | 2020-04-10 | 2020-07-09 | 30 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-07-31 | 2024-08-01 | 2020-04-10 | 2020-07-09 | 40 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-01 | 2020-04-10 | 2020-07-09 | 50 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 3 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-01 | 2024-08-02 | 2020-04-10 | 2020-07-09 | 60 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100029889 | Replace Actuator DFFA-XCV-301116 (Ekst. | Prepare rigging equipment |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2020-04-10 | 2020-07-09 | 70 |  |  | DF /F /10/DFFA-XCV-301116 | Prepare rigging equipment | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-28 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 10 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-29 | 2023-06-13 | 20 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-28 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 30 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-28 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 40 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-29 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 50 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-01-29 | 2023-06-13 | 60 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-29 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 70 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-29 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 80 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-30 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 90 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-30 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 100 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-30 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 110 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-30 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 120 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 1 | 1 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-31 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 130 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2023-08-31 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 140 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100079742 | Caps and gaskets on firehydrants Dan F | FW HR/HYD/MONIT MAINT-DFG | PCNF | PCNF | 0 | 0 | W23-W24 | 2024-07-29 | 2024-07-29 | 2024-05-10 | 2024-05-27 | 2023-01-29 | 2023-06-13 | 150 | PCNF | PCNF | DF /C /01 | FW HR/HYD/MONIT MAINT-DFG | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 4 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 10 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 12.099999999999999644728632116 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 20 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 40.20000000000000284217094303 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-23 | 2024-08-26 | 2016-06-08 | 2016-07-18 | 30 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-26 | 2024-08-28 | 2016-06-08 | 2016-07-18 | 40 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 50 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 60 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-25 | 2016-06-08 | 2016-07-18 | 70 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 26.100000000000001421085471512 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-25 | 2024-08-27 | 2016-06-08 | 2016-07-18 | 80 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 17.399999999999998578914528472 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-25 | 2024-08-26 | 2016-06-08 | 2016-07-18 | 90 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | PRODTECH | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 0.1000000000000000055511151231 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-26 | 2024-08-26 | 2016-06-08 | 2016-07-18 | 100 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-SCAF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 52.29999999999999715782905694 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-26 | 2016-06-08 | 2016-07-18 | 110 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | KRA-OIL | WDF | MTN-MECH | MTN-PIPF | 2100027001 | Udskiftning af HCV-38170 (EP-3803) | Klargøring for udrigning af ventil | AWSC | AWSC | 4 | 0 | Empty | 2024-08-22 | 2024-08-28 | 2024-08-22 | 2024-08-22 | 2016-06-08 | 2016-07-18 | 120 | AWSC | AWSC | DF /A /12/DFAA-HV-38170 | Klargøring for udrigning af ventil | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100049940 | fit 45004 er defekt skal skiftes. | Test and QC |  |  | 2 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2021-05-26 | 2021-07-05 | 10 |  |  | DF /E /37/DFEZ-FT-45004 | Test and QC | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100049940 | fit 45004 er defekt skal skiftes. | Test and QC |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2021-05-26 | 2021-07-05 | 20 |  |  | DF /E /37/DFEZ-FT-45004 | Test and QC | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100049940 | fit 45004 er defekt skal skiftes. | Test and QC |  |  | 6 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-30 | 2021-05-26 | 2021-07-05 | 30 |  |  | DF /E /37/DFEZ-FT-45004 | Test and QC | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100049940 | fit 45004 er defekt skal skiftes. | Test and QC |  |  | 1 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2021-05-26 | 2021-07-05 | 40 |  |  | DF /E /37/DFEZ-FT-45004 | Test and QC | Unknown
3 | NOSD | WDF | MTN-INST | MTN-INST | 2100049940 | fit 45004 er defekt skal skiftes. | Test and QC |  |  | 0 | 0 | W31-W32 | 2024-07-29 | 2024-07-31 | 2024-07-31 | 2024-07-31 | 2021-05-26 | 2021-07-05 | 50 |  |  | DF /E /37/DFEZ-FT-45004 | Test and QC | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086692 | DFAA-EP-3803 pig door is binding | Exercise/lubricate Clsd-Door |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-22 | 2024-05-20 | 2024-05-20 | 2023-04-17 | 2023-08-30 | 10 |  |  | DF /A /12/DFAA-EP-3803 | Exercise/lubricate Clsd-Door | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100086692 | DFAA-EP-3803 pig door is binding | Exercise/lubricate Clsd-Door |  |  | 8 | 0 | Empty | 2024-05-20 | 2024-05-22 | 2024-05-20 | 2024-05-21 | 2023-04-17 | 2023-08-30 | 20 |  |  | DF /A /12/DFAA-EP-3803 | Exercise/lubricate Clsd-Door | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100086692 | DFAA-EP-3803 pig door is binding | Exercise/lubricate Clsd-Door |  |  | 2 | 0 | Empty | 2024-05-20 | 2024-05-22 | 2024-05-21 | 2024-05-22 | 2023-04-17 | 2023-08-30 | 30 |  |  | DF /A /12/DFAA-EP-3803 | Exercise/lubricate Clsd-Door | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100051516 | ZSC 120114 allways ON | Isolate accordingly |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2021-09-12 | 2022-02-09 | 10 |  |  | DF /F /09/DFFA-FD-1214 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100051516 | ZSC 120114 allways ON | Isolate accordingly |  |  | 2 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2021-09-12 | 2022-02-09 | 20 |  |  | DF /F /09/DFFA-FD-1214 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100051516 | ZSC 120114 allways ON | Isolate accordingly |  |  | 1 | 0 | W35-W36 | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2021-09-12 | 2022-02-09 | 30 |  |  | DF /F /09/DFFA-FD-1214 | Isolate accordingly | Unknown
4 | NE | WRO | MTN-TELE | WELLSUPV | 2300000925 | SCADA SW for DFBWID2 | SCADA SW for DFBWID2 | AWSC | AWSC | 24 | 0 | W49 ABB | 2024-01-16 | 2024-01-21 | 2024-01-16 | 2024-01-18 | 2019-06-12 | 2019-11-09 | 10 | AWSC | AWSC | DF /B /04/DFBA-FP-2039 | SCADA SW for DFBWID2 | Unknown
4 | NE | WRO | MTN-TELE | MTN-TELE | 2300000925 | SCADA SW for DFBWID2 | SCADA SW for DFBWID2 | AWSC | AWSC | 10 | 0 | W49 ABB | 2024-01-16 | 2024-01-21 | 2024-01-18 | 2024-01-21 | 2019-06-12 | 2019-11-09 | 20 | AWSC | AWSC | DF /B /04/DFBA-FP-2039 | SCADA SW for DFBWID2 | Unknown
4 | NE | WRO | MTN-TELE | VEN-COMM | 2300000925 | SCADA SW for DFBWID2 | SCADA SW for DFBWID2 | AWSC | AWSC | 0 | 0 | W49 ABB | 2024-01-16 | 2024-01-21 | 2024-01-21 | 2024-01-21 | 2019-06-12 | 2019-11-09 | 30 | AWSC | AWSC | DF /B /04/DFBA-FP-2039 | SCADA SW for DFBWID2 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 10 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 20 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-06-21 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 30 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 6 | Empty | 2024-08-26 | 2024-08-27 | 2024-06-22 | 2024-06-24 | 2024-10-30 | 2024-12-31 | 40 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 50 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 60 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 5 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 70 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 4 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 80 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 90 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | VEN-INSP | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 2 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-26 | 2024-10-30 | 2024-12-31 | 100 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-SCAF | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 10 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-26 | 2024-08-27 | 2024-10-30 | 2024-12-31 | 110 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400284313 | PSV Calibration - DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | 0 | 0 | Empty | 2024-08-26 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-10-30 | 2024-12-31 | 120 | PCNFAWSCSCHSECE | PCNFAWSCSCHSECE | DF /G /70/DFGA-PSV-570015B | DFGA-PSV-570015B Offshore from WS Måde | Unknown
3 | DFX-LIFT | WDF | MTN-INST | PRODTECH | 2100057173 | Rusten sov. G.LIFT MAN'D FROM GASEXPORT | Replace and adjust SOV valve (SDV) |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2021-11-12 | 2022-02-10 | 10 |  |  | DF /E /34/DFEZ-ESDV-45092 | Replace and adjust SOV valve (SDV) | Unknown
3 | DFX-LIFT | WDF | MTN-INST | MTN-INST | 2100057173 | Rusten sov. G.LIFT MAN'D FROM GASEXPORT | Replace and adjust SOV valve (SDV) |  |  | 2.5 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2021-11-12 | 2022-02-10 | 20 |  |  | DF /E /34/DFEZ-ESDV-45092 | Replace and adjust SOV valve (SDV) | Unknown
3 | DFX-LIFT | WDF | MTN-INST | PRODTECH | 2100057173 | Rusten sov. G.LIFT MAN'D FROM GASEXPORT | Replace and adjust SOV valve (SDV) |  |  | 1 | 0 | W29-W30 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2024-07-15 | 2021-11-12 | 2022-02-10 | 30 |  |  | DF /E /34/DFEZ-ESDV-45092 | Replace and adjust SOV valve (SDV) | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 10 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 20 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 30 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 40 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 50 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 60 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 70 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 80 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 90 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 100 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 110 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 120 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 130 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 140 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 150 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 160 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 170 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 180 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 190 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 200 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 210 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 220 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 230 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 240 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 250 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 260 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 270 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 280 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
3 | Empty | WRO | UNKNOWN | WELLSUPV | 2300002648 | DK40 SCAFF MATERIAL ORDER 2021 | 2300002648 MAT 12.11 INTERIE REEL TOT |  |  | 0 | 0 | Empty | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-11-12 | 2021-03-09 | 2021-04-18 | 290 |  |  | DF /F | 2300002648 MAT 12.11 INTERIE REEL TOT | Unknown
A | DFF-1610 | WPM | MTN-TURB | PRODTECH | 2400264196 | 8KH MAIN GEN. SERVICE, COUNTER-A-1610 | Boroscope inspection | AWSCSCH | AWSCSCH | 5 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-19 | 2024-07-20 | 2023-06-30 | 2023-07-30 | 10 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1610 | Boroscope inspection | Unknown
A | DFF-1610 | WPM | MTN-TURB | MTN-TURB | 2400264196 | 8KH MAIN GEN. SERVICE, COUNTER-A-1610 | Boroscope inspection | AWSCSCH | AWSCSCH | 32 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-20 | 2024-07-24 | 2023-06-30 | 2023-07-30 | 20 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1610 | Boroscope inspection | Unknown
A | DFF-1610 | WPM | MTN-TURB | MTN-INST | 2400264196 | 8KH MAIN GEN. SERVICE, COUNTER-A-1610 | Boroscope inspection | AWSCSCH | AWSCSCH | 18 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-24 | 2024-07-26 | 2023-06-30 | 2023-07-30 | 30 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1610 | Boroscope inspection | Unknown
A | DFF-1610 | WPM | MTN-TURB | MTN-ELEC | 2400264196 | 8KH MAIN GEN. SERVICE, COUNTER-A-1610 | Boroscope inspection | AWSCSCH | AWSCSCH | 18 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-26 | 2024-07-28 | 2023-06-30 | 2023-07-30 | 40 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1610 | Boroscope inspection | Unknown
A | DFF-1610 | WPM | MTN-TURB | PRODTECH | 2400264196 | 8KH MAIN GEN. SERVICE, COUNTER-A-1610 | Boroscope inspection | AWSCSCH | AWSCSCH | 5 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-28 | 2024-07-29 | 2023-06-30 | 2023-07-30 | 50 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1610 | Boroscope inspection | Unknown
A | DFF-1610 | WPM | MTN-TURB | MTN-TURB | 2400264196 | 8KH MAIN GEN. SERVICE, COUNTER-A-1610 | Boroscope inspection | AWSCSCH | AWSCSCH | 16 | 0 | W29-W30 | 2024-07-19 | 2024-08-02 | 2024-07-30 | 2024-08-02 | 2023-06-30 | 2023-07-30 | 60 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1610 | Boroscope inspection | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235795 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-22 | 2023-01-30 | 2023-04-13 | 10 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_11 | DE-ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235795 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 19 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-22 | 2024-09-26 | 2023-01-30 | 2023-04-13 | 20 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_11 | DE-ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235795 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 6 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-27 | 2024-09-28 | 2023-01-30 | 2023-04-13 | 30 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_11 | DE-ISOLATION ELECTRICAL | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235795 | 4Y 380V N-SWB MAINT-DFAA-N-1800-02 | DE-ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2023-01-30 | 2023-04-13 | 40 | AWSC | AWSC | DF /A /61/DFAA-N-1800-C_11 | DE-ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235774 | 4Y 400V N-SWB MAINT-DFFB-N-1828-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-22 | 2023-05-15 | 2023-08-11 | 10 | AWSC | AWSC | DF /F /61/DFFB-N-1828-03 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235774 | 4Y 400V N-SWB MAINT-DFFB-N-1828-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 29 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-22 | 2024-09-29 | 2023-05-15 | 2023-08-11 | 20 | AWSC | AWSC | DF /F /61/DFFB-N-1828-03 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235774 | 4Y 400V N-SWB MAINT-DFFB-N-1828-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 10 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-09-29 | 2024-10-01 | 2023-05-15 | 2023-08-11 | 30 | AWSC | AWSC | DF /F /61/DFFB-N-1828-03 | ISOLATION ELECTRICAL | Unknown
C | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235774 | 4Y 400V N-SWB MAINT-DFFB-N-1828-3 | ISOLATION ELECTRICAL | AWSC | AWSC | 1 | 0 | Empty | 2024-09-22 | 2024-10-02 | 2024-10-02 | 2024-10-02 | 2023-05-15 | 2023-08-11 | 40 | AWSC | AWSC | DF /F /61/DFFB-N-1828-03 | ISOLATION ELECTRICAL | Unknown
2 | DFE-O03 | WDF | MTN-INST | PRODTECH | 2100078165 | ZSC-30027 not working - replace | Isolate Position Switch |  |  | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-11-18 | 2023-01-02 | 10 |  |  | DF /E /10/DFEZ-WCV-30027 | Isolate Position Switch | Unknown
2 | DFE-O03 | WDF | MTN-INST | MTN-INST | 2100078165 | ZSC-30027 not working - replace | Isolate Position Switch |  |  | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-11-18 | 2023-01-02 | 20 |  |  | DF /E /10/DFEZ-WCV-30027 | Isolate Position Switch | Unknown
2 | DFE-O03 | WDF | MTN-INST | MTN-INST | 2100078165 | ZSC-30027 not working - replace | Isolate Position Switch |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-02 | 2022-11-18 | 2023-01-02 | 30 |  |  | DF /E /10/DFEZ-WCV-30027 | Isolate Position Switch | Unknown
2 | DFE-O03 | WDF | MTN-INST | MTN-INST | 2100078165 | ZSC-30027 not working - replace | Isolate Position Switch |  |  | 0.5 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-11-18 | 2023-01-02 | 40 |  |  | DF /E /10/DFEZ-WCV-30027 | Isolate Position Switch | Unknown
2 | DFE-O03 | WDF | MTN-INST | PRODTECH | 2100078165 | ZSC-30027 not working - replace | Isolate Position Switch |  |  | 1 | 0 | Empty | 2025-01-01 | 2025-01-02 | 2025-01-01 | 2025-01-01 | 2022-11-18 | 2023-01-02 | 50 |  |  | DF /E /10/DFEZ-WCV-30027 | Isolate Position Switch | Unknown
A | NOSD | WPM | MTN-TELE | MTN-TELE | 2400342422 | 1Y UHF PORTABLE FIRE RADIOS | UHF PORTABLE FIRE RADIOS | SECE | SECE | 5 | 5 | W29-W30 | 2024-07-28 | 2024-07-29 | 2024-07-28 | 2024-07-29 | 2024-07-28 | 2024-08-27 | 10 | SECE | SECE | DF /C /08/EXTERNAL-COMMUNICATION | UHF PORTABLE FIRE RADIOS | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322281 | DFF-27-DPS-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 39 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /F /27/P-G | PIPING INSPECTION AND REPORTING | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269338 | 4Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 2 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-15 | 2023-06-07 | 2023-08-19 | 10 | SECE | SECE | DF /F /27/DFFA-A-5053 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400269338 | 4Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 6 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-15 | 2024-07-17 | 2023-06-07 | 2023-08-19 | 20 | SECE | SECE | DF /F /27/DFFA-A-5053 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400269338 | 4Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 6 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-17 | 2024-07-18 | 2023-06-07 | 2023-08-19 | 30 | SECE | SECE | DF /F /27/DFFA-A-5053 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400269338 | 4Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | ISOLATION BY PRODUCTION | SECE | SECE | 1 | 1 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-18 | 2024-07-19 | 2023-06-07 | 2023-08-19 | 40 | SECE | SECE | DF /F /27/DFFA-A-5053 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400269338 | 4Y SLOP OIL PACKAGE MAINT-DFFA-A-5053 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 12 | W29-W30 | 2024-07-15 | 2024-07-19 | 2024-07-19 | 2024-07-19 | 2023-06-07 | 2023-08-19 | 50 | SECE | SECE | DF /F /27/DFFA-A-5053 | ISOLATION BY PRODUCTION | Unknown
3 | DFF-IPHP | WDF | MTN-ELEC | PRODTECH | 2100059454 | Control voltage DFF 1907A | Isolate accordingly |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-01 | 2025-01-02 | 2021-12-16 | 2022-01-25 | 10 |  |  | DF /F /06/DFFA-DP-1907 | Isolate accordingly | Unknown
3 | DFF-IPHP | WDF | MTN-ELEC | MTN-ELEC | 2100059454 | Control voltage DFF 1907A | Isolate accordingly |  |  | 12 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-05 | 2021-12-16 | 2022-01-25 | 20 |  |  | DF /F /06/DFFA-DP-1907 | Isolate accordingly | Unknown
3 | DFF-IPHP | WDF | MTN-ELEC | MTN-TELE | 2100059454 | Control voltage DFF 1907A | Isolate accordingly |  |  | 6 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-02 | 2025-01-03 | 2021-12-16 | 2022-01-25 | 30 |  |  | DF /F /06/DFFA-DP-1907 | Isolate accordingly | Unknown
3 | DFF-IPHP | WDF | MTN-ELEC | PRODTECH | 2100059454 | Control voltage DFF 1907A | Isolate accordingly |  |  | 2 | 0 | Empty | 2025-01-01 | 2025-01-05 | 2025-01-05 | 2025-01-05 | 2021-12-16 | 2022-01-25 | 40 |  |  | DF /F /06/DFFA-DP-1907 | Isolate accordingly | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2021-07-18 | 2021-12-15 | 10 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-01 | 2021-07-18 | 2021-12-15 | 20 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-01 | 2024-07-02 | 2021-07-18 | 2021-12-15 | 30 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-02 | 2021-07-18 | 2021-12-15 | 40 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-02 | 2024-07-03 | 2021-07-18 | 2021-12-15 | 50 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 4 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-03 | 2024-07-03 | 2021-07-18 | 2021-12-15 | 60 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
4 | NOSD | WDF | MTN-ELEC | MTN-INST | 2100049119 | Replace lighting DFA tower V3501 | Replace light fixture 1800-358-L3E |  |  | 0.5 | 0 | W27-W28 | 2024-07-01 | 2024-07-04 | 2024-07-03 | 2024-07-04 | 2021-07-18 | 2021-12-15 | 70 |  |  | DF /A /62 | Replace light fixture 1800-358-L3E | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 8.699999999999999289457264236 | 0 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 10 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 8.699999999999999289457264236 | 4 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2020-08-17 | 2020-08-25 | 2019-09-12 | 2019-12-11 | 20 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 56 | 30 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2020-08-25 | 2024-07-29 | 2019-09-12 | 2019-12-11 | 30 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 3.399999999999999911182158029 | 5 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2020-08-17 | 2020-08-25 | 2019-09-12 | 2019-12-11 | 40 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | VEN-MECH | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 5 | 0 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 50 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 3.399999999999999911182158029 | 0 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2026-01-01 | 2026-01-01 | 2019-09-12 | 2019-12-11 | 60 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 32 | 0 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2026-01-01 | 2026-01-02 | 2019-09-12 | 2019-12-11 | 70 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
3 | NOSD | WGN | UNKNOWN | WELLSUPV | 2200002921 | DFG-Insulation assists FORCE 15937. | L3 Prepare Permit Lagger | PCNF | PCNF | 0 | 0 | CNF - To be closed | 2026-01-01 | 2026-01-03 | 2026-01-03 | 2026-01-03 | 2019-09-12 | 2019-12-11 | 80 | PCNF | PCNF | DF /G /11/DFG-6-GPS-034-0008-AB-T | L3 Prepare Permit Lagger | Unknown
4 | Empty | WRO | PRODTECH | PRODTECH | 2300006488 | -DO NOT USE- | DK40 - CONSUMABLE PROD - DECK |  |  | 0 | 0 | Empty | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2024-02-24 | 2026-08-12 | 10 |  |  | DF /C /84 | DK40 - CONSUMABLE PROD - DECK | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 8.699999999999999289457264236 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 20 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 30 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 40 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 50 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | QAQCELEC | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 60 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 70 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 0.6999999999999999555910790147 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 80 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 100 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 110 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 130 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | QAQCELEC | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 150 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 160 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 0.6999999999999999555910790147 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 170 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 8 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 180 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 190 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 5.4000000000000003552713678785 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 200 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | QAQCELEC | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 1 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 210 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | PRODTECH | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 3 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 220 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 0.6999999999999999555910790147 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 230 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-PIPF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 0 | 0 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 240 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-SCAF | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 30 | 25 | Empty | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2026-05-12 | 2018-12-20 | 2019-01-09 | 250 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
3 | DAN FG | WDF | MTN-MECH | MTN-RIGG | 2100023974 | Utætte flanger/ventiler | Permit, WELD | PCNFAWSC | PCNFAWSC | 25 | 24 | Empty | 2026-05-12 | 2026-05-12 | 2023-05-26 | 2023-05-30 | 2018-12-20 | 2019-01-09 | 260 | PCNFAWSC | PCNFAWSC | DF /G /01 | Permit, WELD | Unknown
B | DFF-LP-1 | WPM | MTN-MECH | PRODTECH | 2400298420 | 4KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 5 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-15 | 2024-09-16 | 2023-12-25 | 2024-01-10 | 10 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
B | DFF-LP-1 | WPM | MTN-MECH | MTN-MECH | 2400298420 | 4KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 20 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-16 | 2024-09-21 | 2023-12-25 | 2024-01-10 | 20 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
B | DFF-LP-1 | WPM | MTN-MECH | PRODTECH | 2400298420 | 4KH LP COMP - DFFA-C-4201, COUNTER | ISOLATION BY PRODUCTION | AWSC | AWSC | 5 | 0 | Empty | 2024-09-15 | 2024-09-22 | 2024-09-21 | 2024-09-22 | 2023-12-25 | 2024-01-10 | 30 | AWSC | AWSC | DF /F /31/DFFA-C-4201 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235824 | 4Y 380V E-SWB MAINT DFFA-N-1812-05 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-15 | 2023-04-15 | 2023-06-27 | 10 |  |  | DF /F /05/DFFA-N-1812-05 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235824 | 4Y 380V E-SWB MAINT DFFA-N-1812-05 | ISOLATION BY PRODUCTION |  |  | 26 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-18 | 2023-04-15 | 2023-06-27 | 20 |  |  | DF /F /05/DFFA-N-1812-05 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | MTN-ELEC | 2400235824 | 4Y 380V E-SWB MAINT DFFA-N-1812-05 | ISOLATION BY PRODUCTION |  |  | 4 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-18 | 2024-09-19 | 2023-04-15 | 2023-06-27 | 30 |  |  | DF /F /05/DFFA-N-1812-05 | ISOLATION BY PRODUCTION | Unknown
B | NOSD | WPM | MTN-ELEC | PRODTECH | 2400235824 | 4Y 380V E-SWB MAINT DFFA-N-1812-05 | ISOLATION BY PRODUCTION |  |  | 1 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-19 | 2024-09-20 | 2023-04-15 | 2023-06-27 | 40 |  |  | DF /F /05/DFFA-N-1812-05 | ISOLATION BY PRODUCTION | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 8 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-24 | 2025-12-24 | 2020-03-01 | 2020-07-29 | 10 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 2 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-24 | 2025-12-24 | 2020-03-01 | 2020-07-29 | 20 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 4 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-25 | 2025-12-25 | 2020-03-01 | 2020-07-29 | 30 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 2 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-25 | 2025-12-25 | 2020-03-01 | 2020-07-29 | 40 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 4 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-25 | 2025-12-26 | 2020-03-01 | 2020-07-29 | 50 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 4 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-26 | 2025-12-26 | 2020-03-01 | 2020-07-29 | 60 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 3 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-27 | 2025-12-27 | 2020-03-01 | 2020-07-29 | 70 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-ELEC | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 3 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-27 | 2025-12-27 | 2020-03-01 | 2020-07-29 | 80 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | PRODTECH | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 4 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-27 | 2025-12-28 | 2020-03-01 | 2020-07-29 | 90 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-RIGG | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 1 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-28 | 2025-12-28 | 2020-03-01 | 2020-07-29 | 100 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-SCAF | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 2 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-28 | 2025-12-28 | 2020-03-01 | 2020-07-29 | 110 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
4 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100025586 | P-3507 XCV-35915-Exchange actuator | Prepare scaffold for valve access |  |  | 0 | 0 | Empty | 2025-12-24 | 2025-12-28 | 2025-12-24 | 2025-12-24 | 2020-03-01 | 2020-07-29 | 120 |  |  | DF /A /54/DFAA-XCV-35915 | Prepare scaffold for valve access | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400322636 | 4Y HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2024-03-08 | 2024-05-20 | 10 | SECE | SECE | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400322636 | 4Y HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-22 | 2024-09-22 | 2024-03-08 | 2024-05-20 | 20 | SECE | SECE | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400322636 | 4Y HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-23 | 2024-09-25 | 2024-03-08 | 2024-05-20 | 30 | SECE | SECE | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400322636 | 4Y HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-25 | 2024-09-26 | 2024-03-08 | 2024-05-20 | 40 | SECE | SECE | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400322636 | 4Y HPU FOR ESDV MAINT - DFAA-A-5902 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 0 | Empty | 2024-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-03-08 | 2024-05-20 | 50 | SECE | SECE | DF /A /07/DFAA-A-5902 | ISOLATION BY PRODUCTION | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076546 | DFE mezz dæk cva-30004 utæt hyd. | De isolate |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-29 | 2022-10-06 | 2023-02-18 | 10 |  |  | DF /E /10/DFEZ-CVA-30004 | De isolate | Unknown
3 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100076546 | DFE mezz dæk cva-30004 utæt hyd. | De isolate |  |  | 4 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-29 | 2024-07-30 | 2022-10-06 | 2023-02-18 | 20 |  |  | DF /E /10/DFEZ-CVA-30004 | De isolate | Unknown
3 | NOSD | WDF | MTN-MECH | PRODTECH | 2100076546 | DFE mezz dæk cva-30004 utæt hyd. | De isolate |  |  | 2 | 0 | W29-W30 | 2024-07-29 | 2024-07-31 | 2024-07-30 | 2024-07-31 | 2022-10-06 | 2023-02-18 | 30 |  |  | DF /E /10/DFEZ-CVA-30004 | De isolate | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400352430 | 3M CRUDE OIL EXP. SKD MAINT-DFCM-A-3670 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3670 |  |  | 1 | 0 | Empty | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-22 | 10 |  |  | DF /C /23/DFCM-A-3670 | CRUDE OIL EXPORT SKD INSP-DFCM-A-3670 | Unknown
C | NOSD | WPM | MTN-MECH | MTN-MECH | 2400302346 | 1Y JIB CRANE/TRLR-WINCH-MAINT-X-6135A/B | Assist (Wire inspection) | AWSC | AWSC | 12 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-18 | 2024-01-04 | 2024-02-09 | 10 | AWSC | AWSC | DF /G /78/DFGA-X-6135B | Assist (Wire inspection) | Unknown
C | NOSD | WPM | MTN-MECH | VEN-CRAN | 2400302346 | 1Y JIB CRANE/TRLR-WINCH-MAINT-X-6135A/B | Assist (Wire inspection) | AWSC | AWSC | 4 | 0 | Empty | 2024-09-15 | 2024-09-18 | 2024-09-15 | 2024-09-15 | 2024-01-04 | 2024-02-09 | 20 | AWSC | AWSC | DF /G /78/DFGA-X-6135B | Assist (Wire inspection) | Unknown
2 | NOSD | WDF | MTN-MECH | MTN-MECH | 2100101799 | DFAA-HR-0349 Foam Nozzle Replacement | DFAA-HR-0349 Foam Nozzle Replacement |  |  | 1 | 0 | W27-W28 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2023-11-13 | 2023-12-28 | 10 |  |  | DF /A /01/DFAA-HR-0349 | DFAA-HR-0349 Foam Nozzle Replacement | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009212 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 10 |  |  | DF /A /28/DFA-2-DPS-050-4051-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009212 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-08 | 2022-02-08 | 2022-07-08 | 20 |  |  | DF /A /28/DFA-2-DPS-050-4051-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009212 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-08 | 2024-01-09 | 2022-02-08 | 2022-07-08 | 30 |  |  | DF /A /28/DFA-2-DPS-050-4051-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009212 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-09 | 2024-01-10 | 2022-02-08 | 2022-07-08 | 35 |  |  | DF /A /28/DFA-2-DPS-050-4051-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009212 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 16 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-10 | 2024-01-11 | 2022-02-08 | 2022-07-08 | 40 |  |  | DF /A /28/DFA-2-DPS-050-4051-AD-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009212 | Insulation assits FORCE 16322 | Bilfinger inspection |  |  | 8 | 0 | Empty | 2024-01-08 | 2024-01-12 | 2024-01-11 | 2024-01-12 | 2022-02-08 | 2022-07-08 | 50 |  |  | DF /A /28/DFA-2-DPS-050-4051-AD-T | Bilfinger inspection | Unknown
A | NOSD | WPM | INP-SITE | INP-SITE | 2400322226 | DFA-28-DP-PIPING EXT INSP SECE | PIPING INSPECTION AND REPORTING | AWSCSECE | AWSCSECE | 20 | 0 | Empty | 2024-10-30 | 2024-11-09 | 2024-10-30 | 2024-11-08 | 2024-10-30 | 2024-12-31 | 10 | AWSCSECE | AWSCSECE | DF /A /28/P-G | PIPING INSPECTION AND REPORTING | Unknown
D | NOSD | WPM | MTN-INST | MTN-SCAF | 2400070944 | 1Y TRANSPORTABLE STIGER | 14.02.2013 |  |  | 20 | 0 | Empty | 2024-09-15 | 2024-09-20 | 2024-09-15 | 2024-09-20 | 2020-08-16 | 2020-11-20 | 10 |  |  | DF /C /84 | 14.02.2013 | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286629 | 1Y WATER MIST SKID MAINT-DFGA-A-0464 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 3 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-29 | 2023-10-16 | 2023-11-15 | 10 | SECE | SECE | DF /G /01/DFGA-A-0464 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286629 | 1Y WATER MIST SKID MAINT-DFGA-A-0464 | ISOLATION BY PRODUCTION | SECE | SECE | 10 | 22 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-08-01 | 2023-10-16 | 2023-11-15 | 20 | SECE | SECE | DF /G /01/DFGA-A-0464 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-MECH | 2400286629 | 1Y WATER MIST SKID MAINT-DFGA-A-0464 | ISOLATION BY PRODUCTION | SECE | SECE | 6 | 18 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-01 | 2024-08-02 | 2023-10-16 | 2023-11-15 | 30 | SECE | SECE | DF /G /01/DFGA-A-0464 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-INST | 2400286629 | 1Y WATER MIST SKID MAINT-DFGA-A-0464 | ISOLATION BY PRODUCTION | SECE | SECE | 4 | 4 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2023-10-16 | 2023-11-15 | 40 | SECE | SECE | DF /G /01/DFGA-A-0464 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | MTN-ELEC | 2400286629 | 1Y WATER MIST SKID MAINT-DFGA-A-0464 | ISOLATION BY PRODUCTION | SECE | SECE | 2 | 2 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-07-29 | 2024-07-30 | 2023-10-16 | 2023-11-15 | 50 | SECE | SECE | DF /G /01/DFGA-A-0464 | ISOLATION BY PRODUCTION | Unknown
A | NOSD | WPM | MTN-MECH | PRODTECH | 2400286629 | 1Y WATER MIST SKID MAINT-DFGA-A-0464 | ISOLATION BY PRODUCTION | SECE | SECE | 3 | 3 | W31-W32 | 2024-07-29 | 2024-08-03 | 2024-08-02 | 2024-08-03 | 2023-10-16 | 2023-11-15 | 60 | SECE | SECE | DF /G /01/DFGA-A-0464 | ISOLATION BY PRODUCTION | Unknown
C | DFF-1630 | WPM | MTN-INST | MTN-INST | 2400325777 | 3Y DFFA-A-1630 FUEL - METERING | DFFA-A-1630 FUEL - METERING | AWSCSCH | AWSCSCH | 3 | 0 | W23-W24 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 | 2024-03-17 | 2024-05-30 | 10 | AWSCSCH | AWSCSCH | DF /F /60/DFFA-A-1630 | DFFA-A-1630 FUEL - METERING | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-PAIN | 2100030540 | ANOCR Painting of crane pedestal after i | Set up equipment |  |  | 0 | 0 | Empty | 2023-09-25 | 2023-09-29 | 2023-09-25 | 2023-09-25 | 2020-09-21 | 2021-07-18 | 10 |  |  | DF /C /86/CRANE-PEDESTAL | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030540 | ANOCR Painting of crane pedestal after i | Set up equipment |  |  | 6 | 0 | Empty | 2023-09-25 | 2023-09-29 | 2023-09-25 | 2023-09-25 | 2020-09-21 | 2021-07-18 | 20 |  |  | DF /C /86/CRANE-PEDESTAL | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030540 | ANOCR Painting of crane pedestal after i | Set up equipment |  |  | 24 | 0 | Empty | 2023-09-25 | 2023-09-29 | 2023-09-25 | 2023-09-28 | 2020-09-21 | 2021-07-18 | 30 |  |  | DF /C /86/CRANE-PEDESTAL | Set up equipment | Unknown
4 | NOSD | WDF | MTN-ROPE | MTN-ROPE | 2100030540 | ANOCR Painting of crane pedestal after i | Set up equipment |  |  | 6 | 0 | Empty | 2023-09-25 | 2023-09-29 | 2023-09-28 | 2023-09-29 | 2020-09-21 | 2021-07-18 | 40 |  |  | DF /C /86/CRANE-PEDESTAL | Set up equipment | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-12 | 2024-08-12 | 2023-12-18 | 2024-05-01 | 10 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-12 | 2024-08-13 | 2023-12-18 | 2024-05-01 | 20 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-13 | 2024-08-14 | 2023-12-18 | 2024-05-01 | 30 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-14 | 2024-08-14 | 2023-12-18 | 2024-05-01 | 40 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-14 | 2024-08-15 | 2023-12-18 | 2024-05-01 | 50 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-MECH | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-15 | 2024-08-15 | 2023-12-18 | 2024-05-01 | 60 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | PRODTECH | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 2 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-15 | 2024-08-16 | 2023-12-18 | 2024-05-01 | 70 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
3 | NE | WDF | MTN-MECH | MTN-RIGG | 2100101419 | DFF-C-5402, leaking cooler | Isolate Cooler |  |  | 3 | 0 | W33-W34 | 2024-08-12 | 2024-08-17 | 2024-08-16 | 2024-08-17 | 2023-12-18 | 2024-05-01 | 80 |  |  | DF /F /07/DFFA-C-5402 | Isolate Cooler | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009236 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 0 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2024-01-08 | 2022-02-09 | 2022-07-09 | 10 |  |  | DF /F /28/DFF-2-DPS-050-7666-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009236 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-08 | 2024-01-10 | 2022-02-09 | 2022-07-09 | 20 |  |  | DF /F /28/DFF-2-DPS-050-7666-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009236 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 12 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-11 | 2024-01-12 | 2022-02-09 | 2022-07-09 | 30 |  |  | DF /F /28/DFF-2-DPS-050-7666-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | VEN-INSP | 2200009236 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 6 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-12 | 2024-01-12 | 2022-02-09 | 2022-07-09 | 35 |  |  | DF /F /28/DFF-2-DPS-050-7666-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-LAGG | 2200009236 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 24 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-12 | 2024-01-15 | 2022-02-09 | 2022-07-09 | 40 |  |  | DF /F /28/DFF-2-DPS-050-7666-AB-T | Bilfinger inspection | Unknown
4 | NOSD | WGN | VEN-INSP | MTN-SCAF | 2200009236 | Insulation assist bilfinger 20864 | Bilfinger inspection |  |  | 18 | 0 | Empty | 2024-01-08 | 2024-01-17 | 2024-01-15 | 2024-01-17 | 2022-02-09 | 2022-07-09 | 50 |  |  | DF /F /28/DFF-2-DPS-050-7666-AB-T | Bilfinger inspection | Unknown