## Sheet1
Monitor Field Indicator | Work center | Earliest start date | Earliest start time | Latest Allowed Finish Date | Order Type | Priority | ABC indicator | Earliest finish date | Earliest finish time | Priority text | Order | Activity | Order Description | Object Description | Number | Notes 2 | Unloading Point | Notes 1 | Remaining Work | Work | Actual work | Order User Status | Op User Status | Order System Status | Functional Location | Description of functional location | Revision | Earliest Allowed Start Date
| MTN-MECH | 2023-11-05 | 16:04 | 2019-02-24 | WDF | 4 | I | 2023-11-06 | 16:04 | 4. Long | 2100022445 | 0070 | Exchange internals PCV-080501B | L3 Install actuator onto valve | 1 | 7 |  |  | 4 | 4 | 0 | APPR SMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /76/DFGA-PCV-080501B | INERT GAS TO V-5350 | NOSD | 2018-09-27
| PRODTECH | 2023-11-06 | 16:04 | 2019-02-24 | WDF | 4 | I | 2023-11-07 | 10:04 | 4. Long | 2100022445 | 0080 | Exchange internals PCV-080501B | L3 Remove isolation | 2 | 7 |  |  | 4 | 4 | 0 | APPR SMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /G /76/DFGA-PCV-080501B | INERT GAS TO V-5350 | NOSD | 2018-09-27
| PRODTECH | 2023-11-07 | 16:04 | 2019-08-15 | WDF | 3 | S | 2023-11-08 | 13:04 | 3. Intermediate | 2100022470 | 0010 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Isolate DFCI-HCV-03350 | 1 | 2 | OIM FW EXL | ICC:E mat eta 2/8-21 W/2100022470+24158 | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-MECH | 2023-11-08 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-09 | 13:04 | 3. Intermediate | 2100022470 | 0015 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 CAREFULLY remove insulation 03350 | 1 | 2 | OIM FW 3 EXL | ICC:E mat eta 2/8-21 w/2100023592+2100024158 | 4 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-RIGG | 2023-11-09 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-09 | 13:04 | 3. Intermediate | 2100022470 | 0017 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Help remove old valve | 1 | 2 | OIM FW EXL | ICC:E mat eta 2/8-21 W/2100022470+24158 | 0 | 6 | 6 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-MECH | 2023-11-09 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-11 | 13:04 | 3. Intermediate | 2100022470 | 0020 | 21place DFCI-HCV-03350 (Used to be: "Uds | L2 Replace DFCI-HCV-03350 | 2 | 2 | OIM FW 3 EXL | ICC:E mat eta 2/8-21 w/2100023592+2100024158 | 16 | 16 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-RIGG | 2023-11-11 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-11 | 13:04 | 3. Intermediate | 2100022470 | 0025 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Help install new valve | 1 | 2 | OIM FW EXL | ICC:E mat eta 2/8-21 W/2100022470+24158 | 0 | 6 | 24 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-MECH | 2023-11-11 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-12 | 13:04 | 3. Intermediate | 2100022470 | 0030 | 21place DFCI-HCV-03350 (Used to be: "Uds | L2 Replace valve for X-0358 | 2 | 2 | OIM FW 3 EXL | ICC:E mat eta 2/8-21 w/2100023592+2100024158 | 8 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-MECH | 2023-11-12 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-13 | 13:04 | 3. Intermediate | 2100022470 | 0040 | 21place DFCI-HCV-03350 (Used to be: "Uds | L2 Replace valve for X-0359 | 2 | 2 | OIM FW 3 EXL | ICC:E mat eta 2/8-21 w/2100023592+2100024158 | 8 | 8 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| PRODTECH | 2023-11-13 | 13:04 | 2019-08-15 | WDF | 3 | S | 2023-11-14 | 10:04 | 3. Intermediate | 2100022470 | 0050 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Deisolate DFCI-HCV-03350 | 1 | 2 | OIM FW EXL | ICC:E mat eta 2/8-21 W/2100022470+24158 | 3 | 3 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-ROPE | 2023-11-14 | 10:04 | 2019-08-15 | WDF | 3 | S | 2023-11-15 | 10:04 | 3. Intermediate | 2100022470 | 0065 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Put back insulation | 1 | 2 | OIM FW EXL | ICC:E mat eta 2/8-21 W/2100022470+24158 | 4 | 4 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-MECH | 2023-11-15 | 10:04 | 2019-08-15 | WDF | 3 | S | 2023-11-18 | 10:04 | 3. Intermediate | 2100022470 | 0070 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Remove scaff | 1 | 2 | OIM FW EXL | ICC:E mat eta 2/8-21 W/2100022470+24158 | 12 | 12 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-ROUS | 2023-11-01 | 10:04 | 2019-08-15 | WDF | 3 | S | 2023-11-07 | 16:04 | 3. Intermediate | 2100022470 | 0080 | 21place DFCI-HCV-03350 (Used to be: "Uds | L3 Firewatch during WO | 1 | 2 | OIM FW EXL | Hold Step+2100022470+24158 | 26 | 26 | 0 | APPR PMAT RDBL | APPR OPND | REL PCNF PRT CSER GMPS MANC PRC SETC | DF /C /01/DFCI-HCV-03350 | LO - HAND CONTROL VALVE | NOSD | 2019-07-26
| MTN-INST | 2023-11-05 | 13:04 | 2019-10-01 | WDF | 3 | V | 2023-11-06 | 7:04 | 3. Intermediate | 2100022472 | 0050 | Purchase of parts for Dump Valves | De isolate and clean up | 1 | 6 |  |  | 2 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /G /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFG-3590 | 2019-08-22
| MTN-INST | 2023-11-06 | 7:04 | 2019-10-01 | WDF | 3 | V | 2023-11-06 | 13:04 | 3. Intermediate | 2100022472 | 0060 | Purchase of parts for Dump Valves | QC update documentation | 1 | 6 |  |  | 2 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC PRC SETC | DF /G /54 | WATER INJ (INCL PUMPS, METERING, HEADER) | DFG-3590 | 2019-08-22
| MTN-MECH | 2023-11-01 | 10:04 | 2019-08-21 | WDF | 3 | V | 2023-11-08 | 16:04 | 3. Intermediate | 2100022493 | 0140 | Spool til monitor wm-0343 er extern utæt | install new valve | 2 | 5 | BL-TEAM |  | 60 | 60 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL PCNF PRT GMPS MANC PRC SETC | DF /B /01/DFBA-WM-0343 | FIREWATER MONITOR | NOSD | 2019-08-01
| VEN-ACCO | 2023-11-27 | 9:04 | 2020-12-25 | WDF | 4 | V | 2023-12-03 | 12:51 | 4. Long | 2100022591 | 0010 | Rep/change of floor in telecom and eqip | L3 rep/change of floor | 1 | 5 | No VEND booking |  | 60 | 60 | 0 | APPR RDBL | APPR OPND | REL MANC NMAT PRC SETC | DF /C /82 | LIVING AND WELFARE QTRS | NOSD | 2019-12-31
| VEN-ACCO | 2023-12-30 | 7:00 | 2019-10-02 | WDF | 3 | V | 2023-12-31 | 10:09 | 3. Intermediate | 2100022602 | 0010 | Repair fire doors Level 1&Mezzanine DFC | Repair fire doors Level 1 & Mezzanine | 2 | 3 |  |  | 24 | 24 | 0 | APPR AWSC RDBL | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /C /82 | LIVING AND WELFARE QTRS | NOSD | 2019-09-12
| PRODTECH | 2023-11-05 | 16:04 | 2019-09-01 | WDF | 3 | V | 2023-11-07 | 16:04 | 3. Intermediate | 2100022680 | 0040 | CMAT:Check valve DFG IP/HP hot gas | Desafing of plant | 2 |  | Hold Step |  | 16 | 16 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /31 | GAS COMPRESSION | DFG-IPHP | 2019-06-03
| MTN-MECH | 2023-11-07 | 16:04 | 2019-09-01 | WDF | 3 | V | 2023-11-08 | 10:04 | 3. Intermediate | 2100022680 | 0050 | CMAT:Check valve DFG IP/HP hot gas | Leak test | 1 |  | Hold Step |  | 2 | 2 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /31 | GAS COMPRESSION | DFG-IPHP | 2019-06-03
| MTN-MECH | 2023-11-08 | 17:34 | 2019-09-01 | WDF | 3 | V | 2023-11-09 | 14:34 | 3. Intermediate | 2100022680 | 0055 | CMAT:Check valve DFG IP/HP hot gas | Housekeeping | 1 |  | Hold Step | POST | 3 | 3 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /31 | GAS COMPRESSION | DFG-IPHP | 2019-06-03
| MTN-RIGG | 2023-11-08 | 17:34 | 2019-09-01 | WDF | 3 | V | 2023-11-09 | 11:34 | 3. Intermediate | 2100022680 | 0060 | CMAT:Check valve DFG IP/HP hot gas | Remove lifting arrangement | 2 |  | Hold Step | POST | 4 | 4 | 0 | APPR AWSC RDBL | APPR OPND | REL MANC PRC SETC | DF /G /31 | GAS COMPRESSION | DFG-IPHP | 2019-06-03
| VEN-ROPE | 2023-12-26 | 16:44 | 2019-07-20 | WDF | 3 | V | 2023-12-28 | 12:57 | 3. Intermediate | 2100022932 | 0008 | DFA/78: Replace all wire sheaves on cran | Prepare permit, riggin/lift plan & equip | 1 | 2 |  | W41-42 | 16 | 16 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| MTN-MECH | 2023-12-26 | 16:44 | 2019-07-20 | WDF | 3 | V | 2023-12-27 | 13:44 | 3. Intermediate | 2100022932 | 0009 | DFA/78: Replace all wire sheaves on cran | Find and check materials | 1 | 2 |  | W41-42 | 3 | 3 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| PRODTECH | 2023-12-27 | 13:44 | 2019-07-20 | WDF | 3 | V | 2023-12-27 | 16:44 | 3. Intermediate | 2100022932 | 0010 | DFA/78: Replace all wire sheaves on cran | Isolation of crane DFA | 1 | 2 |  | W41-42 | 1 | 1 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| VEN-ROPE | 2023-12-27 | 16:44 | 2019-07-20 | WDF | 3 | V | 2024-01-07 | 11:03 | 3. Intermediate | 2100022932 | 0020 | DFA/78: Replace all wire sheaves on cran | Assist to replace wire sheaves and build | 3 | 2 |  | W41-42 | 300 | 300 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| VEN-CRAN | 2023-12-27 | 16:44 | 2019-07-20 | WDF | 3 | V | 2024-01-09 | 12:19 | 3. Intermediate | 2100022932 | 0030 | DFA/78: Replace all wire sheaves on cran | Replace all wire sheaves | 2 | 2 |  | W41-42 | 240 | 240 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| PRODTECH | 2024-01-09 | 12:19 | 2019-07-20 | WDF | 3 | V | 2024-01-09 | 15:19 | 3. Intermediate | 2100022932 | 0040 | DFA/78: Replace all wire sheaves on cran | Deisolation of crane DFA | 1 | 2 |  | W41-42 | 1 | 1 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| VEN-CRAN | 2024-01-09 | 15:19 | 2019-07-20 | WDF | 3 | V | 2024-01-10 | 14:41 | 3. Intermediate | 2100022932 | 0050 | DFA/78: Replace all wire sheaves on cran | Clean up, Proff load test, report, QC an | 2 | 2 |  | W41-42 | 18 | 18 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| MTN-ROUS | 2024-01-09 | 15:19 | 2019-07-20 | WDF | 3 | V | 2024-01-11 | 15:19 | 3. Intermediate | 2100022932 | 0060 | DFA/78: Replace all wire sheaves on cran | Ass. with proff load test | 1 | 2 |  | W41-42 | 8 | 8 | 0 | APPR PMAT AWDO RDBL ROUT | APPR OPND | REL GMPS MANC PPRT PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| PRODTECH | 2023-12-03 | 7:00 | 2021-01-09 | WDF | 4 | V | 2023-12-03 | 10:00 | 4. Long | 2100023024 | 0010 | Replace broken Mech. Interlock | Set Isolation, pull drawer | 2 | 5 |  |  | 2 | 2 | 0 | APPR SMAT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /61/DFFA-N-1801B-02-01 | LIMITER TIE-LINE TO DFCI-N-1801 / 1840 | NOSD | 2020-01-15
| VEN-ELEC | 2023-12-03 | 10:00 | 2021-01-09 | WDF | 4 | V | 2023-12-03 | 13:47 | 4. Long | 2100023024 | 0020 | Replace broken Mech. Interlock | Replace interlocking device | 1 | 5 |  |  | 3 | 3 | 0 | APPR SMAT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /61/DFFA-N-1801B-02-01 | LIMITER TIE-LINE TO DFCI-N-1801 / 1840 | NOSD | 2020-01-15
| PRODTECH | 2023-12-03 | 13:47 | 2021-01-09 | WDF | 4 | V | 2023-12-03 | 16:47 | 4. Long | 2100023024 | 0030 | Replace broken Mech. Interlock | De-isolate | 2 | 5 |  |  | 2 | 2 | 0 | APPR SMAT | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /F /61/DFFA-N-1801B-02-01 | LIMITER TIE-LINE TO DFCI-N-1801 / 1840 | NOSD | 2020-01-15
| MTN-SCAF | 2023-11-05 | 10:53 | 2022-06-09 | WDF | 4 | S | 2023-11-06 | 7:53 | 4. Long | 2100023111 | 0070 | Exchange valve in ringmain HCV-030016 | Remove hop up | 2 | 7 |  | ¦10/01/2022 Wrk. Ctr. Migration | 6 | 6 | 0 | APPR PMAT RDBL | APPR OPND | REL GMPS MANC PRC SETC | DF /C /01/DFCC-HCV-030016 | LO - HAND CONTROL VALVE | NOSD | 2020-06-19
| MTN-ROPE | 2023-12-30 | 12:45 | 2020-06-17 | WDF | 4 | V | 2023-12-31 | 12:45 | 4. Long | 2100023218 | 0050 | ANOCR DFB-R3007 External Corrosion | PREP; Rig Up, Gear, Sandblaster & Grit | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 12 | 12 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2023-12-30 | 13:53 | 2020-06-17 | WDF | 4 | V | 2023-12-31 | 7:53 | 4. Long | 2100023218 | 0060 | ANOCR DFB-R3007 External Corrosion | PREP; Remove grating access R3007 | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 6 | 6 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2023-12-30 | 13:53 | 2020-06-17 | WDF | 4 | V | 2023-12-31 | 9:59 | 4. Long | 2100023218 | 0070 | ANOCR DFB-R3007 External Corrosion | PREP; Build SCAF-FRAME around grating | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 8 | 8 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2023-12-30 | 13:53 | 2020-06-17 | WDF | 4 | V | 2023-12-31 | 13:53 | 4. Long | 2100023218 | 0080 | ANOCR DFB-R3007 External Corrosion | PREP; 15-Set-Up Rope & Rescue System | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 12 | 12 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| INP-SITE | 2023-12-30 | 15:01 | 2020-06-17 | WDF | 4 | V | 2023-12-30 | 17:33 | 4. Long | 2100023218 | 0081 | ANOCR DFB-R3007 External Corrosion | Line release | 1 |  |  |  | 2 | 2 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | INIT OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2023-12-30 | 17:33 | 2020-06-17 | WDF | 4 | V | 2024-01-02 | 17:33 | 4. Long | 2100023218 | 0090 | ANOCR DFB-R3007 External Corrosion | WORK; 15-INSPECT+Blast R3007 | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 36 | 36 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2024-01-01 | 18:41 | 2020-06-17 | WDF | 4 | V | 2024-01-02 | 18:41 | 4. Long | 2100023218 | 0100 | ANOCR DFB-R3007 External Corrosion | WORK; 15-MIO-Primer close steel | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 12 | 12 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2024-01-02 | 7:49 | 2020-06-17 | WDF | 4 | V | 2024-01-03 | 13:49 | 4. Long | 2100023218 | 0110 | ANOCR DFB-R3007 External Corrosion | WORK; 15-Multi-Strength 600μ DFT | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 18 | 18 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2024-01-02 | 14:57 | 2020-06-17 | WDF | 4 | V | 2024-01-03 | 8:57 | 4. Long | 2100023218 | 0120 | ANOCR DFB-R3007 External Corrosion | POST; 15-De-rig SB & Rope EQ | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 6 | 6 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2024-01-02 | 14:57 | 2020-06-17 | WDF | 4 | V | 2024-01-03 | 17:03 | 4. Long | 2100023218 | 0130 | ANOCR DFB-R3007 External Corrosion | POST; Remount Grating & SCAF | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 14 | 14 | 0 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2024-01-02 | 18:11 | 2020-06-17 | WDF | 4 | V | 2024-01-03 | 14:11 | 4. Long | 2100023218 | 0140 | ANOCR DFB-R3007 External Corrosion | POST; Tidy-Up, Waste & Backload | 3 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 8 | 9 | 1 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | APPR OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| MTN-ROPE | 2024-01-02 | 18:11 | 2020-06-17 | WDF | 4 | V | 2024-01-03 | 18:11 | 4. Long | 2100023218 | 0150 | ANOCR DFB-R3007 External Corrosion | Correctiing PTW writting from onshore | 1 | 2 | W45-46 IOP | W45-46 SMAT Awating insp Bilfinger | 4 | 7 | 3 | APPR APOG PMAT AWDO AWSC RDBL RFRZ ROUT | INIT OPND | REL PCNF GMPS MANC PPRT PRC SETC | DF /B /23/DFBA-RI-663007 | R3007 - 12" DAN FB TO P3004 | NOSD | 2020-01-19
| VEN-CRAN | 2023-11-05 | 16:51 | 2019-07-20 | WDF | 3 | V | 2023-11-06 | 17:29 | 3. Intermediate | 2100023241 | 0060 | DFA/78: Replace Aircon unit due to corro | Rigg up new A/C unit | 2 | 5 |  |  | 20 | 20 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| VEN-CRAN | 2023-11-06 | 17:29 | 2019-07-20 | WDF | 3 | V | 2023-11-08 | 12:26 | 3. Intermediate | 2100023241 | 0070 | DFA/78: Replace Aircon unit due to corro | Install new A/C unit (El/Mech) | 2 | 5 |  |  | 30 | 30 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| VEN-CRAN | 2023-11-08 | 12:26 | 2019-07-20 | WDF | 3 | V | 2023-11-10 | 7:23 | 3. Intermediate | 2100023241 | 0080 | DFA/78: Replace Aircon unit due to corro | Remove lifting setup | 2 | 5 |  |  | 30 | 30 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| VEN-CRAN | 2023-11-10 | 7:23 | 2019-07-20 | WDF | 3 | V | 2023-11-10 | 11:10 | 3. Intermediate | 2100023241 | 0090 | DFA/78: Replace Aircon unit due to corro | QC, functioncheck ,report, clean-up, bac | 1 | 5 |  |  | 3 | 3 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| MTN-MECH | 2023-11-10 | 11:10 | 2019-07-20 | WDF | 3 | V | 2023-11-11 | 8:10 | 3. Intermediate | 2100023241 | 0100 | DFA/78: Replace Aircon unit due to corro | Assist & Backload old A/C unit | 1 | 5 |  |  | 3 | 3 | 0 | APPR WMAT AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /A /78/DFAA-X-6102 | CRANE - 60 T | NOSD | 2019-06-10
| MTN-SCAF | 2023-11-05 | 7:04 | 2020-07-26 | WDF | 4 | V | 2023-11-07 | 7:04 | 4. Long | 2100023363 | 0070 | DFB/78: A/C unit on cabin roof corroded | Build scaffold/rigging. | 2 | 6 |  |  | 16 | 16 | 0 | APPR APOG AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD | 2020-02-27
| MTN-RIGG | 2023-11-07 | 7:04 | 2020-07-26 | WDF | 4 | V | 2023-11-08 | 10:04 | 4. Long | 2100023363 | 0080 | DFB/78: A/C unit on cabin roof corroded | Rig up the AC unit. | 2 | 6 |  |  | 10 | 10 | 0 | APPR APOG AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD | 2020-02-27
| MTN-CRAN | 2023-11-08 | 10:04 | 2020-07-26 | WDF | 4 | V | 2023-11-09 | 16:04 | 4. Long | 2100023363 | 0090 | DFB/78: A/C unit on cabin roof corroded | Mount the refurbished AC unit. | 1 | 6 |  |  | 6 | 6 | 0 | APPR APOG AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD | 2020-02-27
| MTN-CRAN | 2023-11-09 | 16:04 | 2020-07-26 | WDF | 4 | V | 2023-11-10 | 13:04 | 4. Long | 2100023363 | 0100 | DFB/78: A/C unit on cabin roof corroded | Deisolation,Test, QC, CNF | 1 | 6 |  |  | 3 | 3 | 0 | APPR APOG AWDO RDBL ROUT | APPR OPND | REL MANC PRC SETC | DF /B /78/DFBA-X-6102 | CRANE - 60 T | NOSD | 2020-02-27
| MTN-MECH | 2023-11-05 | 7:04 | 2020-01-22 | WDF | 3 | V | 2023-11-07 | 7:04 | 3. Intermediate | 2100023393 | 0030 | SBTDF 'SmallBoreTubing DFC Lev.2' | Fabricate support for finding 1 | 1 | 5 |  |  | 8 | 8 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| PRODTECH | 2023-11-07 | 7:04 | 2020-01-22 | WDF | 3 | V | 2023-11-07 | 11:34 | 3. Intermediate | 2100023393 | 0040 | SBTDF 'SmallBoreTubing DFC Lev.2' | Isolate for finding 2 | 2 | 5 |  |  | 3 | 3 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| MTN-MECH | 2023-11-07 | 11:34 | 2020-01-22 | WDF | 3 | V | 2023-11-08 | 17:34 | 3. Intermediate | 2100023393 | 0050 | SBTDF 'SmallBoreTubing DFC Lev.2' | Change or tighten fitting | 1 | 5 |  |  | 6 | 6 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| PRODTECH | 2023-11-08 | 17:34 | 2020-01-22 | WDF | 3 | V | 2023-11-09 | 10:04 | 3. Intermediate | 2100023393 | 0060 | SBTDF 'SmallBoreTubing DFC Lev.2' | De- Isolate for finding 2 | 2 | 5 |  |  | 3 | 3 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| MTN-SCAF | 2023-11-09 | 10:04 | 2020-01-22 | WDF | 3 | V | 2023-11-13 | 7:04 | 3. Intermediate | 2100023393 | 0065 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 3 | 1 | 5 |  |  | 15 | 15 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| PRODTECH | 2023-11-13 | 7:04 | 2020-01-22 | WDF | 3 | V | 2023-11-13 | 13:04 | 3. Intermediate | 2100023393 | 0070 | SBTDF 'SmallBoreTubing DFC Lev.2' | Isolate for finding 3 | 2 | 5 |  |  | 4 | 4 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| MTN-MECH | 2023-11-13 | 13:04 | 2020-01-22 | WDF | 3 | V | 2023-11-16 | 7:04 | 3. Intermediate | 2100023393 | 0080 | SBTDF 'SmallBoreTubing DFC Lev.2' | Change or tighten fitting/tubing | 1 | 5 |  |  | 10 | 10 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| PRODTECH | 2023-11-16 | 7:04 | 2020-01-22 | WDF | 3 | V | 2023-11-16 | 13:04 | 3. Intermediate | 2100023393 | 0090 | SBTDF 'SmallBoreTubing DFC Lev.2' | De- Isolate for finding 3 | 2 | 5 |  |  | 4 | 4 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| MTN-SCAF | 2023-11-16 | 13:04 | 2020-01-22 | WDF | 3 | V | 2023-11-20 | 10:04 | 3. Intermediate | 2100023393 | 0100 | SBTDF 'SmallBoreTubing DFC Lev.2' | build scarffold for finding 3 | 1 | 5 |  |  | 15 | 15 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| PRODTECH | 2023-11-20 | 10:04 | 2020-01-22 | WDF | 3 | V | 2023-11-20 | 16:04 | 3. Intermediate | 2100023393 | 0110 | SBTDF 'SmallBoreTubing DFC Lev.2' | Isolate for finding 3 | 2 | 5 |  |  | 4 | 4 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| MTN-MECH | 2023-11-20 | 16:04 | 2020-01-22 | WDF | 3 | V | 2023-11-23 | 10:04 | 3. Intermediate | 2100023393 | 0120 | SBTDF 'SmallBoreTubing DFC Lev.2' | Change or tighten fitting | 1 | 5 |  |  | 10 | 10 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| PRODTECH | 2023-11-23 | 10:04 | 2020-01-22 | WDF | 3 | V | 2023-11-23 | 16:04 | 3. Intermediate | 2100023393 | 0130 | SBTDF 'SmallBoreTubing DFC Lev.2' | De- Isolate for finding 3 | 2 | 5 |  |  | 4 | 4 | 0 | APPR RDBL SREQ | APPR OPND | REL MANC NMAT PRC SETC | DF /A /03 | ESD AND FIRE & GAS | NOSD | 2019-10-24
| VEN-ELEC | 2023-11-13 | 7:00 | 2020-03-20 | WDF | 3 | V | 2023-11-13 | 9:32 | 3. Intermediate | 2100023425 | 0010 | DFC Em. SwG-Blackstart selectorswitch | Troubleshoot and document switch | 1 | 5 | Onshore action | PARKED 01-06 Awaiiting NJF update | 2 | 2 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC NMAT PRC SETC | DF /C /05/DFCI-N-1811-01-01 | CIRC.BREAK. MAIN 3KV SWBD DFCI-N-1801 | NOSD | 2019-12-21
| MTN-INST | 2023-11-05 | 10:04 | 2018-10-06 | WDF | 4 | V | 2023-11-06 | 10:04 | 4. Long | 2100023576 | 0070 | Faultfinding on ESD level transmitter | E+H - Checking gamma detection | 1 | 5 | BL-TEAM | SECE TEAM | 4 | 4 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-INST | 2023-11-06 | 10:04 | 2018-10-06 | WDF | 4 | V | 2023-11-08 | 7:04 | 4. Long | 2100023576 | 0080 | Faultfinding on ESD level transmitter | Force - Preparation for exposure | 1 | 5 | BL-TEAM | SECE TEAM | 7 | 7 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| PRODTECH | 2023-11-08 | 7:04 | 2018-10-06 | WDF | 4 | V | 2023-11-09 | 7:04 | 4. Long | 2100023576 | 0090 | Faultfinding on ESD level transmitter | Inhibiting necessary detectors | 1 | 5 |  | SECE TEAM | 4 | 4 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-INST | 2023-11-09 | 7:04 | 2018-10-06 | WDF | 4 | V | 2023-11-10 | 16:04 | 4. Long | 2100023576 | 0100 | Faultfinding on ESD level transmitter | Force - X-ray exposure is performed | 1 | 5 | BL-TEAM | SECE TEAM | 7 | 7 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-INST | 2023-11-10 | 16:04 | 2018-10-06 | WDF | 4 | V | 2023-11-12 | 13:04 | 4. Long | 2100023576 | 0110 | Faultfinding on ESD level transmitter | E+H - X-ray exposure is detected | 1 | 5 | BL-TEAM | SECE TEAM | 7 | 7 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| PRODTECH | 2023-11-12 | 13:04 | 2018-10-06 | WDF | 4 | V | 2023-11-13 | 13:04 | 4. Long | 2100023576 | 0120 | Faultfinding on ESD level transmitter | Bringing the inhibited detectors online | 1 | 5 |  | SECE TEAM | 4 | 4 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-INST | 2023-11-13 | 13:04 | 2018-10-06 | WDF | 4 | V | 2023-11-14 | 7:04 | 4. Long | 2100023576 | 0130 | Faultfinding on ESD level transmitter | Force - Clean-up | 1 | 5 | BL-TEAM | SECE TEAM | 2 | 2 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-INST | 2023-11-14 | 7:04 | 2018-10-06 | WDF | 4 | V | 2023-11-14 | 13:04 | 4. Long | 2100023576 | 0140 | Faultfinding on ESD level transmitter | E+H - Clean-up | 1 | 5 | BL-TEAM | SECE TEAM | 2 | 2 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-INST | 2023-11-14 | 13:04 | 2018-10-06 | WDF | 4 | V | 2023-11-15 | 10:04 | 4. Long | 2100023576 | 0150 | Faultfinding on ESD level transmitter | E+H - Job evaluation | 1 | 5 | BL-TEAM | SECE TEAM | 3 | 3 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| PRODTECH | 2023-11-15 | 10:04 | 2018-10-06 | WDF | 4 | V | 2023-11-16 | 7:04 | 4. Long | 2100023576 | 0160 | Faultfinding on ESD level transmitter | Job evaluation | 1 | 5 |  | SECE TEAM | 3 | 3 | 0 | APPR AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /28/DFCM-LT-50742 | LEVEL TRANSMITTER (ESD) | NOSD | 2018-05-09
| MTN-MECH | 2023-11-05 | 7:04 | 2018-06-09 | WDF | 4 | I | 2023-11-07 | 10:04 | 4. Long | 2100023667 | 0050 | Dan FC, LCV-50741 Replacement of actuato | L3 Replace Actuator | 2 | 7 |  |  | 18 | 18 | 0 | APPR APOG CMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /28/DFCM-LCV-50741 | LEVEL CONTROL VALVE FOR V-5002 | NOSD | 2018-04-30
| MTN-MECH | 2023-11-07 | 10:04 | 2018-06-09 | WDF | 4 | I | 2023-11-08 | 16:04 | 4. Long | 2100023667 | 0055 | Dan FC, LCV-50741 Replacement of actuato | L3 Replace LCV-50741 | 2 | 7 |  |  | 12 | 12 | 0 | APPR APOG CMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /28/DFCM-LCV-50741 | LEVEL CONTROL VALVE FOR V-5002 | NOSD | 2018-04-30
| MTN-INST | 2023-11-07 | 16:04 | 2018-06-09 | WDF | 4 | I | 2023-11-08 | 16:04 | 4. Long | 2100023667 | 0060 | Dan FC, LCV-50741 Replacement of actuato | L3 Connect tubing | 1 | 7 |  |  | 4 | 4 | 0 | APPR APOG CMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /28/DFCM-LCV-50741 | LEVEL CONTROL VALVE FOR V-5002 | NOSD | 2018-04-30
| QAQCMECH | 2023-11-08 | 16:04 | 2018-06-09 | WDF | 4 | I | 2023-11-08 | 17:34 | 4. Long | 2100023667 | 0070 | Dan FC, LCV-50741 Replacement of actuato | L3 Functional test and QC | 1 | 7 |  |  | 1 | 1 | 0 | APPR APOG CMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /28/DFCM-LCV-50741 | LEVEL CONTROL VALVE FOR V-5002 | NOSD | 2018-04-30
| PRODTECH | 2023-11-08 | 17:34 | 2018-06-09 | WDF | 4 | I | 2023-11-09 | 14:34 | 4. Long | 2100023667 | 0080 | Dan FC, LCV-50741 Replacement of actuato | L3 De-isolate LCV-50741 | 1 | 7 |  |  | 3 | 3 | 0 | APPR APOG CMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /28/DFCM-LCV-50741 | LEVEL CONTROL VALVE FOR V-5002 | NOSD | 2018-04-30
| MTN-RIGG | 2023-11-09 | 14:34 | 2018-06-09 | WDF | 4 | I | 2023-11-10 | 14:34 | 4. Long | 2100023667 | 0090 | Dan FC, LCV-50741 Replacement of actuato | L3 Rig-down hoist | 2 | 7 |  |  | 8 | 8 | 0 | APPR APOG CMAT RDBL | APPR OPND | REL PRT GMPS MANC PRC SETC | DF /C /28/DFCM-LCV-50741 | LEVEL CONTROL VALVE FOR V-5002 | NOSD | 2018-04-30
| MTN-MECH | 2023-11-04 | 7:04 | 2018-06-08 | WDF | 3 | S | 2023-11-06 | 7:04 | 3. Intermediate | 2100023697 | 0040 | CMAT:DAN FC replacement of sealkit at va | L2-Replace seals | 1 | 6 |  | Hold Step | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC PRC SETC | DF /C /51/DFCM-XCV-52213 | SEAWATER FILTER PACKAGE A-5201 | NOSD | 2018-04-29
| MTN-MECH | 2023-11-06 | 7:04 | 2018-06-08 | WDF | 3 | S | 2023-11-06 | 16:04 | 3. Intermediate | 2100023697 | 0050 | CMAT:DAN FC replacement of sealkit at va | L2-Mount actuator | 2 | 6 |  | Hold Step | 6 | 6 | 0 | APPR RDBL | APPR OPND | REL MANC PRC SETC | DF /C /51/DFCM-XCV-52213 | SEAWATER FILTER PACKAGE A-5201 | NOSD | 2018-04-29
| MTN-RIGG | 2023-11-06 | 16:04 | 2018-06-08 | WDF | 3 | S | 2023-11-07 | 16:04 | 3. Intermediate | 2100023697 | 0060 | CMAT:DAN FC replacement of sealkit at va | L3-Demount hoist | 2 | 6 |  | Hold Step | 8 | 8 | 0 | APPR RDBL | APPR OPND | REL MANC PRC SETC | DF /C /51/DFCM-XCV-52213 | SEAWATER FILTER PACKAGE A-5201 | NOSD | 2018-04-29
| PRODTECH | 2023-11-07 | 16:04 | 2018-06-08 | WDF | 3 | S | 2023-11-08 | 13:04 | 3. Intermediate | 2100023697 | 0070 | CMAT:DAN FC replacement of sealkit at va | L3-Desafing of XCV-52213 | 1 | 6 |  | Hold Step | 3 | 3 | 0 | APPR RDBL | APPR OPND | REL MANC PRC SETC | DF /C /51/DFCM-XCV-52213 | SEAWATER FILTER PACKAGE A-5201 | NOSD | 2018-04-29
| MTN-MECH | 2023-11-08 | 13:04 | 2018-06-08 | WDF | 3 | S | 2023-11-08 | 16:04 | 3. Intermediate | 2100023697 | 0080 | CMAT:DAN FC replacement of sealkit at va | L3-Test and documentation | 1 | 6 |  | Hold Step | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL MANC PRC SETC | DF /C /51/DFCM-XCV-52213 | SEAWATER FILTER PACKAGE A-5201 | NOSD | 2018-04-29
| MTN-SCAF | 2023-11-02 | 7:04 | 2018-04-06 | WDF | 3 | V | 2023-11-08 | 7:04 | 3. Intermediate | 2100023703 | 0020 | DFC/78: SMAT:DFC øverste wireskiver kan | Scaffolding Assistence | 2 | 6 |  |  | 48 | 48 | 0 | APPR PROK AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /78/DFCI-X-6101 | CRANE - 60 T | NOSD | 2018-01-06
| MTN-CRAN | 2023-11-02 | 7:04 | 2018-04-06 | WDF | 3 | V | 2023-11-08 | 7:04 | 3. Intermediate | 2100023703 | 0030 | DFC/78: SMAT:DFC øverste wireskiver kan | Remove Wire disc for cleaning | 2 | 6 |  |  | 48 | 48 | 0 | APPR PROK AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /78/DFCI-X-6101 | CRANE - 60 T | NOSD | 2018-01-06
| MTN-CRAN | 2023-11-08 | 7:04 | 2018-04-06 | WDF | 3 | V | 2023-11-08 | 16:04 | 3. Intermediate | 2100023703 | 0040 | DFC/78: SMAT:DFC øverste wireskiver kan | Desafing of DFCI-X-6101 | 1 | 6 |  |  | 3 | 3 | 0 | APPR PROK AWDO RDBL ROUT | APPR OPND | REL PRT MANC PRC SETC | DF /C /78/DFCI-X-6101 | CRANE - 60 T | NOSD | 2018-01-06
| MTN-ELEC | 2023-11-05 | 15:10 | 2018-04-01 | WDF | 3 | V | 2023-11-07 | 17:16 | 3. Intermediate | 2100023728 | 0030 | CMAT:DFB Frost ruptore of eye wash pipe | Check Heat tracing and repair it | 1 | 5 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 8.7 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /B /02 | SAFETY/EVACUATION EQUIPMENT | NOSD | 2018-03-12
| MTN-LAGG | 2023-11-07 | 17:16 | 2018-04-01 | WDF | 3 | V | 2023-11-08 | 16:15 | 3. Intermediate | 2100023728 | 0040 | CMAT:DFB Frost ruptore of eye wash pipe | Ripair Insulation Again | 1 | 5 |  | ¦10/01/2022 Wrk. Ctr. Migration | 8.7 | 8.7 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /B /02 | SAFETY/EVACUATION EQUIPMENT | NOSD | 2018-03-12
| PRODTECH | 2023-11-08 | 16:15 | 2018-04-01 | WDF | 3 | V | 2023-11-09 | 7:15 | 3. Intermediate | 2100023728 | 0050 | CMAT:DFB Frost ruptore of eye wash pipe | Desafe of First Aid/Medical | 1 | 5 |  | ¦10/01/2022 Wrk. Ctr. Migration | 1 | 1 | 0 | APPR RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /B /02 | SAFETY/EVACUATION EQUIPMENT | NOSD | 2018-03-12
| VEN-MECH | 2023-12-31 | 7:00 | 2017-11-20 | WDF | 3 | V | 2023-12-31 | 7:00 | 3. Intermediate | 2100023841 | 0010 | SMAT:Mont af slang for vinterbleed DFG ( | Klargøring for rope access | 2 | 2 | OIM FW Low |  | 0 | 13 | 13 | APPR PROK AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /G /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2017-10-11
| VEN-MECH | 2023-12-31 | 7:00 | 2017-11-20 | WDF | 3 | V | 2023-12-31 | 9:32 | 3. Intermediate | 2100023841 | 0020 | SMAT:Mont af slang for vinterbleed DFG ( | Afmontering af blindflange | 3 | 2 | OIM FW Low |  | 6 | 6 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /G /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2017-10-11
| VEN-MECH | 2023-12-31 | 9:32 | 2017-11-20 | WDF | 3 | V | 2023-12-31 | 12:03 | 3. Intermediate | 2100023841 | 0030 | SMAT:Mont af slang for vinterbleed DFG ( | Montering af slange for vinterbleed | 3 | 2 | OIM FW Low |  | 6 | 6 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /G /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2017-10-11
| VEN-MECH | 2023-12-31 | 12:03 | 2017-11-20 | WDF | 3 | V | 2023-12-31 | 14:35 | 3. Intermediate | 2100023841 | 0040 | SMAT:Mont af slang for vinterbleed DFG ( | Oprydning | 2 | 2 | OIM FW Low |  | 4 | 4 | 0 | APPR PROK AWSC RDBL | APPR OPND | REL PCNF MANC PRC SETC | DF /G /01 | FIRE FIGHTING GENERATION/DISTRIBUTION | NOSD | 2017-10-11